## Task Properties
Sl.No. | Task Genealogy* | Task Name* | WBS Level Code | Parent WBS Level | Task Status | Edit Schedule Dates | Edit Actual Dates | Planned Start | Planned Finish | Forecasted Start | Forecasted Finish | Internal Start | Internal Finish | Actual Start | Actual Finish | Constraint Start | Constraint Finish | Planned Percentage | Percentage Completed | Approval Code Based Progress | Area Description (Area Code) | System Description (System Code) | Document Genealogy | Document Number | Sheet Number | Document Created Date | Client Document Number | Vendor Document Number | Origin Type | Origin Name | Approval Requirement Code | Approval Status Code(Internal) | Approval Status Code(Client) | Task Workflow Team | Progress Contribution To Parent | Progress Contribution To Project | Weightage | Progress Towards | Progress Captured As | Task UOM | Budgeted Cost | Forecasted Cost | Actual Cost | Budgeted Duration | Forecasted Duration | Actual Duration | Budgeted Quantity | Forecasted Quantity | Actual Quantity | As Built Quantity | Baseline Duration | Conversion Factor | Alpha | Beta | Interval | Distribution Type | Customer Weightage | Milestone Task | Customer Schedule | Task Code | Task Revision Number | Task Level | Task Priority | Resource Names | Privileged Task Resources | Task Remarks | Early Start Date | Early Finish Date | Late Start Date | Late Finish Date | Early Percentage | Late Percentage | Ruleset Name | Engineering-Drawing Start(Planned Finish Date) | Engineering-Drawing Start(Forecasted Finish Date) | Engineering-Drawing Start(Schedule Code) | Engineering-Drawing Start(Percentage) | Engineering-Drawing Start(Actual Finish Date) | Engineering-Drawing Start(Early Finish Date) | Engineering-Drawing Start(Late Finish Date) | Engineering-Document Submission(Planned Finish Date) | Engineering-Document Submission(Forecasted Finish Date) | Engineering-Document Submission(Schedule Code) | Engineering-Document Submission(Percentage) | Engineering-Document Submission(Actual Finish Date) | Engineering-Document Submission(Early Finish Date) | Engineering-Document Submission(Late Finish Date) | Engineering-IDC Review(Planned Finish Date) | Engineering-IDC Review(Forecasted Finish Date) | Engineering-IDC Review(Schedule Code) | Engineering-IDC Review(Percentage) | Engineering-IDC Review(Actual Finish Date) | Engineering-IDC Review(Early Finish Date) | Engineering-IDC Review(Late Finish Date) | Engineering-Issue to Client(Planned Finish Date) | Engineering-Issue to Client(Forecasted Finish Date) | Engineering-Issue to Client(Schedule Code) | Engineering-Issue to Client(Percentage) | Engineering-Issue to Client(Actual Finish Date) | Engineering-Issue to Client(Early Finish Date) | Engineering-Issue to Client(Late Finish Date) | Engineering-Client Review(Planned Finish Date) | Engineering-Client Review(Forecasted Finish Date) | Engineering-Client Review(Schedule Code) | Engineering-Client Review(Percentage) | Engineering-Client Review(Actual Finish Date) | Engineering-Client Review(Early Finish Date) | Engineering-Client Review(Late Finish Date) | Engineering-Client Review (R1)(Planned Finish Date) | Engineering-Client Review (R1)(Forecasted Finish Date) | Engineering-Client Review (R1)(Schedule Code) | Engineering-Client Review (R1)(Percentage) | Engineering-Client Review (R1)(Actual Finish Date) | Engineering-Client Review (R1)(Early Finish Date) | Engineering-Client Review (R1)(Late Finish Date) | Engineering-Issue to Client(R1)(Planned Finish Date) | Engineering-Issue to Client(R1)(Forecasted Finish Date) | Engineering-Issue to Client(R1)(Schedule Code) | Engineering-Issue to Client(R1)(Percentage) | Engineering-Issue to Client(R1)(Actual Finish Date) | Engineering-Issue to Client(R1)(Early Finish Date) | Engineering-Issue to Client(R1)(Late Finish Date) | Engineering-Issue to Client(R2)(Planned Finish Date) | Engineering-Issue to Client(R2)(Forecasted Finish Date) | Engineering-Issue to Client(R2)(Schedule Code) | Engineering-Issue to Client(R2)(Percentage) | Engineering-Issue to Client(R2)(Actual Finish Date) | Engineering-Issue to Client(R2)(Early Finish Date) | Engineering-Issue to Client(R2)(Late Finish Date) | Engineering-Client Review (R2)(Planned Finish Date) | Engineering-Client Review (R2)(Forecasted Finish Date) | Engineering-Client Review (R2)(Schedule Code) | Engineering-Client Review (R2)(Percentage) | Engineering-Client Review (R2)(Actual Finish Date) | Engineering-Client Review (R2)(Early Finish Date) | Engineering-Client Review (R2)(Late Finish Date) | Engineering-Issue to Client (R3)(Planned Finish Date) | Engineering-Issue to Client (R3)(Forecasted Finish Date) | Engineering-Issue to Client (R3)(Schedule Code) | Engineering-Issue to Client (R3)(Percentage) | Engineering-Issue to Client (R3)(Actual Finish Date) | Engineering-Issue to Client (R3)(Early Finish Date) | Engineering-Issue to Client (R3)(Late Finish Date) | Engineering-Client Review (R3)(Planned Finish Date) | Engineering-Client Review (R3)(Forecasted Finish Date) | Engineering-Client Review (R3)(Schedule Code) | Engineering-Client Review (R3)(Percentage) | Engineering-Client Review (R3)(Actual Finish Date) | Engineering-Client Review (R3)(Early Finish Date) | Engineering-Client Review (R3)(Late Finish Date) | Engineering-Issue to Client (R4)(Planned Finish Date) | Engineering-Issue to Client (R4)(Forecasted Finish Date) | Engineering-Issue to Client (R4)(Schedule Code) | Engineering-Issue to Client (R4)(Percentage) | Engineering-Issue to Client (R4)(Actual Finish Date) | Engineering-Issue to Client (R4)(Early Finish Date) | Engineering-Issue to Client (R4)(Late Finish Date) | Engineering-Client Review (R4)(Planned Finish Date) | Engineering-Client Review (R4)(Forecasted Finish Date) | Engineering-Client Review (R4)(Schedule Code) | Engineering-Client Review (R4)(Percentage) | Engineering-Client Review (R4)(Actual Finish Date) | Engineering-Client Review (R4)(Early Finish Date) | Engineering-Client Review (R4)(Late Finish Date) | Engineering-Final Release/GFC(Planned Finish Date) | Engineering-Final Release/GFC(Forecasted Finish Date) | Engineering-Final Release/GFC(Schedule Code) | Engineering-Final Release/GFC(Percentage) | Engineering-Final Release/GFC(Actual Finish Date) | Engineering-Final Release/GFC(Early Finish Date) | Engineering-Final Release/GFC(Late Finish Date) | Internal-Draftsman submission(Planned Finish Date) | Internal-Draftsman submission(Forecasted Finish Date) | Internal-Draftsman submission(Schedule Code) | Internal-Draftsman submission(Percentage) | Internal-Draftsman submission(Actual Finish Date) | Internal-Draftsman submission(Early Finish Date) | Internal-Draftsman submission(Late Finish Date) | Internal-Discipline Review(Planned Finish Date) | Internal-Discipline Review(Forecasted Finish Date) | Internal-Discipline Review(Schedule Code) | Internal-Discipline Review(Percentage) | Internal-Discipline Review(Actual Finish Date) | Internal-Discipline Review(Early Finish Date) | Internal-Discipline Review(Late Finish Date) | Internal-IDC Review(Planned Finish Date) | Internal-IDC Review(Forecasted Finish Date) | Internal-IDC Review(Schedule Code) | Internal-IDC Review(Percentage) | Internal-IDC Review(Actual Finish Date) | Internal-IDC Review(Early Finish Date) | Internal-IDC Review(Late Finish Date) | Internal-Final Release(Planned Finish Date) | Internal-Final Release(Forecasted Finish Date) | Internal-Final Release(Schedule Code) | Internal-Final Release(Percentage) | Internal-Final Release(Actual Finish Date) | Internal-Final Release(Early Finish Date) | Internal-Final Release(Late Finish Date) | Vendor-Vendor Submission(Planned Finish Date) | Vendor-Vendor Submission(Forecasted Finish Date) | Vendor-Vendor Submission(Schedule Code) | Vendor-Vendor Submission(Percentage) | Vendor-Vendor Submission(Actual Finish Date) | Vendor-Vendor Submission(Early Finish Date) | Vendor-Vendor Submission(Late Finish Date) | Vendor-Discipline Review(Planned Finish Date) | Vendor-Discipline Review(Forecasted Finish Date) | Vendor-Discipline Review(Schedule Code) | Vendor-Discipline Review(Percentage) | Vendor-Discipline Review(Actual Finish Date) | Vendor-Discipline Review(Early Finish Date) | Vendor-Discipline Review(Late Finish Date) | Vendor-IDC Review(Planned Finish Date) | Vendor-IDC Review(Forecasted Finish Date) | Vendor-IDC Review(Schedule Code) | Vendor-IDC Review(Percentage) | Vendor-IDC Review(Actual Finish Date) | Vendor-IDC Review(Early Finish Date) | Vendor-IDC Review(Late Finish Date) | Vendor-Issue to Client(Planned Finish Date) | Vendor-Issue to Client(Forecasted Finish Date) | Vendor-Issue to Client(Schedule Code) | Vendor-Issue to Client(Percentage) | Vendor-Issue to Client(Actual Finish Date) | Vendor-Issue to Client(Early Finish Date) | Vendor-Issue to Client(Late Finish Date) | Vendor-Client Review(Planned Finish Date) | Vendor-Client Review(Forecasted Finish Date) | Vendor-Client Review(Schedule Code) | Vendor-Client Review(Percentage) | Vendor-Client Review(Actual Finish Date) | Vendor-Client Review(Early Finish Date) | Vendor-Client Review(Late Finish Date) | Vendor-Final Release(Planned Finish Date) | Vendor-Final Release(Forecasted Finish Date) | Vendor-Final Release(Schedule Code) | Vendor-Final Release(Percentage) | Vendor-Final Release(Actual Finish Date) | Vendor-Final Release(Early Finish Date) | Vendor-Final Release(Late Finish Date) | PR STANDARD-Started(Planned Finish Date) | PR STANDARD-Started(Forecasted Finish Date) | PR STANDARD-Started(Schedule Code) | PR STANDARD-Started(Percentage) | PR STANDARD-Started(Actual Finish Date) | PR STANDARD-Started(Early Finish Date) | PR STANDARD-Started(Late Finish Date) | PR STANDARD-Issued for Inter-disciplinary Check (IDC)(Planned Finish Date) | PR STANDARD-Issued for Inter-disciplinary Check (IDC)(Forecasted Finish Date) | PR STANDARD-Issued for Inter-disciplinary Check (IDC)(Schedule Code) | PR STANDARD-Issued for Inter-disciplinary Check (IDC)(Percentage) | PR STANDARD-Issued for Inter-disciplinary Check (IDC)(Actual Finish Date) | PR STANDARD-Issued for Inter-disciplinary Check (IDC)(Early Finish Date) | PR STANDARD-Issued for Inter-disciplinary Check (IDC)(Late Finish Date) | PR STANDARD-Final Release to Buiseness Unit (FRB)(Planned Finish Date) | PR STANDARD-Final Release to Buiseness Unit (FRB)(Forecasted Finish Date) | PR STANDARD-Final Release to Buiseness Unit (FRB)(Schedule Code) | PR STANDARD-Final Release to Buiseness Unit (FRB)(Percentage) | PR STANDARD-Final Release to Buiseness Unit (FRB)(Actual Finish Date) | PR STANDARD-Final Release to Buiseness Unit (FRB)(Early Finish Date) | PR STANDARD-Final Release to Buiseness Unit (FRB)(Late Finish Date) | PR STANDARD-RFQ Release(Planned Finish Date) | PR STANDARD-RFQ Release(Forecasted Finish Date) | PR STANDARD-RFQ Release(Schedule Code) | PR STANDARD-RFQ Release(Percentage) | PR STANDARD-RFQ Release(Actual Finish Date) | PR STANDARD-RFQ Release(Early Finish Date) | PR STANDARD-RFQ Release(Late Finish Date) | PR STANDARD-Technical Evaluation(Planned Finish Date) | PR STANDARD-Technical Evaluation(Forecasted Finish Date) | PR STANDARD-Technical Evaluation(Schedule Code) | PR STANDARD-Technical Evaluation(Percentage) | PR STANDARD-Technical Evaluation(Actual Finish Date) | PR STANDARD-Technical Evaluation(Early Finish Date) | PR STANDARD-Technical Evaluation(Late Finish Date) | PR STANDARD-Offer Evaluation(Planned Finish Date) | PR STANDARD-Offer Evaluation(Forecasted Finish Date) | PR STANDARD-Offer Evaluation(Schedule Code) | PR STANDARD-Offer Evaluation(Percentage) | PR STANDARD-Offer Evaluation(Actual Finish Date) | PR STANDARD-Offer Evaluation(Early Finish Date) | PR STANDARD-Offer Evaluation(Late Finish Date) | PR STANDARD-PO Release(Planned Finish Date) | PR STANDARD-PO Release(Forecasted Finish Date) | PR STANDARD-PO Release(Schedule Code) | PR STANDARD-PO Release(Percentage) | PR STANDARD-PO Release(Actual Finish Date) | PR STANDARD-PO Release(Early Finish Date) | PR STANDARD-PO Release(Late Finish Date) | Authorized By | Category | Client Doc. Num. Without Rev. No. | Client Submission Date | Construction Activity | Discipline Category | Document Category | Document code | Document No.Without Rev. No. | Document Owner | Document Type | Funtional Unit | O19045 Document Category | O19045 Sub Category | Outotec Document Designation Number | Plan IFC Date | PO Number | Procube Code | Procube ID | Procube project ID | Qty in Document | RFQ Status | Serial | Size | UOM | Weight in kg | TASK_ID
1 | Task(Task)-->E (Engineering) | NTPC's CHP KERENDARI | 1 |  | Work In Progress | No | No | 2019-08-01 18:00 | 2021-09-27 18:00 | 2019-08-01 18:00 | 2022-04-19 18:00 |  |  | 2019-09-27 10:57 |  |  |  | 59.0241 | 21.9822 | [15 empty] | 0 | 100 | 100 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2279 | 0 | 0 | High | [7 empty] | 0 | 0 | [244 empty] | 1017691
2 | Task(Task)-->E (Engineering) | RECEIPT OF NOA (ZERO DATE OF THE PROJECT) |  | 1 | Completed | No | No | 2019-09-27 09:00 | 2019-09-27 18:00 | 2019-09-27 09:00 | 2019-09-27 18:00 |  |  | 2020-07-23 17:44 | 2020-07-23 17:44 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | Yes | No | 2280 | 0 | 1 | High | [7 empty] | 0 | 0 | [244 empty] | 1017692
3 | Task(Task)-->C (Construction) | SURVEY, GEO-TECHNICAL INVESTIGATION, TEMPORARY STRUCTURE & APPROACH | 1.2 | 1 | Work In Progress | No | No | 2019-09-27 09:00 | 2020-06-14 23:59 | 2019-09-27 09:00 | 2020-12-01 18:00 |  |  | 2019-09-27 12:40 |  |  |  | 100 | 100 | [15 empty] | 0.2658 | 0.2658 | 26.14 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5596 | 0 | 1 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017693
4 | Task(Task)-->C (Construction) | ROUTE SURVEY (TOPOGRAPHY) |  | 1.2 | Completed | No | No | 2019-10-21 09:00 | 2019-11-13 18:00 | 2019-10-21 09:00 | 2019-11-13 18:00 |  |  | 2019-10-21 12:24 | 2019-11-13 12:24 |  |  | 100 | 100 | [15 empty] | 100 | 0.2658 | 26.14 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5579 | 0 | 2 | Low | Santosh Anand | [6 empty] | 0 | 0 | [244 empty] | 1017694
5 | Task(Task)-->C (Construction) | GEO TECHNICAL INVESTIGATION WORK & SUBMISSION OF REPORT BY AGENCY |  | 1.2 | Completed | No | No | 2020-01-28 09:00 | 2020-03-27 18:00 | 2020-01-22 09:00 | 2020-07-20 18:00 |  |  | 2020-01-22 12:25 | 2020-07-20 12:25 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5574 | 0 | 2 | Low | Niharendu Kamle,Santosh Anand | [6 empty] | 0 | 0 | [244 empty] | 1017695
6 | Task(Task)-->C (Construction) | CONSTRUCTION/ ESTABLISHMENT OF SITE OFFICE |  | 1.2 | Unscheduled | No | No | 2019-10-19 09:00 | 2020-01-16 18:00 | 2020-01-01 09:00 | 2020-12-01 18:00 |  |  | 2020-01-01 10:18 |  |  |  | 100 | 70 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5580 | 0 | 2 | Low | Niharendu Kamle | [6 empty] | 0 | 0 | [244 empty] | 1017696
7 | Task(Task)-->C (Construction) | FINALIZATION OF SUB-CONTRACTOR FOR CIVIL WORK |  | 1.2 | Completed | No | No | 2019-09-27 09:00 | 2019-10-26 18:00 | 2019-09-27 09:00 | 2020-02-04 18:00 |  |  | 2019-09-27 12:40 | 2020-02-04 12:38 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5582 | 0 | 2 | Low | Santosh Anand | [6 empty] | 0 | 0 | [244 empty] | 1017697
8 | Task(Task)-->C (Construction) | LAND ACQUISITION FOR TEMPORARY STRUCTURE |  | 1.2 | Unscheduled | No | No | 2020-01-17 09:00 | 2020-04-15 18:00 | 2020-01-01 09:00 | 2020-10-15 18:00 |  |  | 2020-01-01 10:15 |  |  |  | 100 | 75 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5604 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017698
9 | Task(Task)-->C (Construction) | ESTABLISHMENT OF BATCHING PLANT/ CEMENT GODOWN/ CONSTRUCTION WATER & QUALITY LAB |  | 1.2 | Unscheduled | No | No | 2020-02-16 | 2020-05-15 18:00 | 2020-04-10 09:00 | 2020-09-23 18:00 |  |  | 2020-04-10 10:16 |  |  |  | 100 | 80 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5584 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017699
10 | Task(Task)-->C (Construction) | CONSTRUCTION OF LABOUR CAMP ( CAPACITY FOR 450 LABOUR ) |  | 1.2 | Unscheduled | No | No | 2020-02-16 | 2020-06-14 23:59 | 2020-08-01 09:00 | 2020-11-28 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5583 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017700
11 | Task(Task)-->C (Construction) | CONSTRUCTION OF STORAGE SPACE/ SHEDS |  | 1.2 | Unscheduled | No | No | 2020-02-16 | 2020-06-14 23:59 | 2020-01-01 09:00 | 2020-11-30 18:00 |  |  | 2020-01-01 10:20 |  |  |  | 100 | 50 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5589 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017701
12 | Task(Task)-->E (Engineering) | DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP | 1.3 | 1 | Work In Progress | No | No | 2019-09-27 09:00 | 2021-09-13 18:00 | 2019-09-27 09:00 | 2022-04-09 18:00 |  |  | 2019-09-27 10:57 |  |  |  | 57.7159 | 23.9296 | [15 empty] | 9.4645 | 9.4645 | 930.77 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2281 | 0 | 1 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017702
13 | Task(Task)-->E (Engineering) | ENGINEERING | 1.3.1 | 1.3 | Work In Progress | No | No | 2019-10-26 18:00 | 2020-07-13 17:40 | 2019-11-30 18:00 | 2020-09-14 18:00 |  |  | 2019-10-31 17:40 |  |  |  | 100 | 98.0957 | [15 empty] | 3.0587 | 0.28949 | 28.47 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2282 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017703
14 | Task(Task)-->E (Engineering) | Mechanical | 1.3.1.1 | 1.3.1 | Work In Progress | No | No | 2019-10-26 18:00 | 2020-05-11 17:40 | 2019-11-30 18:00 | 2020-09-14 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 94.7067 | [15 empty] | 8.3275 | 0.024107 | 2.37 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No | 2283 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036070
15 | Task(Task)-->E (Engineering) | G.A. OF TYP. CHUTE & SKIRT |  | 1.3.1.1 | Unscheduled | No | No | 2020-01-04 18:00 | 2020-02-21 17:40 | 2020-03-28 18:00 | 2020-05-08 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-0029 |  | 2020-02-13 10:26 | 7012-155-PVM-B-029 |  |  |  | I |  |  |  | 9.205 | 0.002219 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 80 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2290 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-04 18:00 | 2020-03-28 18:00 |  | 10 | 2020-03-28 23:31 |  |  | 2020-01-13 17:40 | 2020-04-12 23:59 |  | 30 | 2020-04-12 23:31 |  |  | 2020-01-18 17:40 | 2020-04-17 18:00 |  | 35 | 2020-04-17 23:31 |  |  | 2020-01-24 23:59 | 2020-04-17 18:00 |  | 65 | 2020-04-14 23:31 |  |  | 2020-01-30 17:40 | 2020-05-08 18:00 |  | 80 | 2020-05-08 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-02-21 17:40 | 2020-05-08 18:00 |  | 100 | [122 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 29 |  |  |  | 101043
16 | Task(Task)-->E (Engineering) | G.A OF GEARBOX FOR TROUGH BELT CONVEYORS |  | 1.3.1.1 | Completed | No | No | 2020-03-21 18:00 | 2020-05-11 17:40 | 2020-06-13 09:00 | 2020-06-30 18:00 |  |  | 2020-02-21 14:04 | 2020-07-02 11:13 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1002 |  | 2020-02-13 10:26 | 7012-155-PVM-B-102 |  |  |  | A |  |  |  | 13.3891 | 0.003228 | 0.32 | Plan & Actual | Date |  | 0 | 0 | 0 | 120 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2288 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-21 18:00 | 2020-05-18 18:00 |  | 10 | 2020-05-08 23:31 |  |  | 2020-03-31 17:40 | 2020-06-01 18:00 |  | 30 | 2020-05-23 23:31 |  |  | 2020-04-06 17:40 | 2020-06-08 18:00 |  | 35 | 2020-05-19 16:11 |  |  | 2020-04-11 23:59 | 2020-06-08 18:00 |  | 65 | 2020-05-19 16:18 |  |  | 2020-04-17 17:40 | 2020-06-29 18:00 |  | 80 | 2020-05-19 16:20 | [5 empty] | 80 | 2020-06-10 16:59 | [5 empty] | 80 | 2020-06-10 16:59 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-11 17:40 | 2020-06-29 18:00 |  | 100 | 2020-07-02 11:14 | [121 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 32 |  |  |  | 101046
17 | Task(Task)-->E (Engineering) | GA, BOM, WIRING AND TERMINAL DIAGRAM OF LOCAL CONTROL PANEL FOR LUBRICAION OF PRIMARY & SECONDARY SIZER |  | 1.3.1.1 | Unscheduled | No | No | 2020-03-11 18:00 | 2020-04-23 17:40 | 2020-05-30 18:00 | 2020-09-14 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-406 |  | 2020-02-13 11:47 | 7012-155-PVE-W-142 |  |  |  | A |  |  |  | 4.6025 | 0.00111 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2286 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-11 18:00 | 2020-05-30 18:00 |  | 10 |  |  |  | 2020-03-12 17:40 | 2020-06-06 18:00 |  | 30 |  |  |  | 2020-03-19 17:40 | 2020-06-13 18:00 |  | 35 |  |  |  | 2020-03-25 23:59 | 2020-06-13 18:00 |  | 65 | 2020-09-23 13:36 |  |  | 2020-04-01 17:40 | 2020-07-04 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-23 17:40 | 2020-07-04 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 377 |  |  |  | 101388
18 | Task(Task)-->E (Engineering) | G.A & LOAD DATA OF DUMP HOPPER STATION (DH-1, DH-2, DH-3 & DH-4) |  | 1.3.1.1 | Unscheduled | No | No | 2019-10-26 18:00 | 2019-12-30 17:40 | 2020-02-21 18:00 | 2020-05-04 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-0007 |  | 2020-02-13 10:26 | 7012-155-PVM-B-007 |  |  |  | A |  |  |  | 45.1883 | 0.010894 | 1.08 | Plan & Actual | Date |  | 0 | 0 | 0 | 400 | 0 | 100.31 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2284 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-10-26 18:00 | 2020-02-21 18:00 |  | 10 | 2020-02-21 23:31 |  |  | 2019-11-21 17:40 | 2020-03-20 18:00 |  | 30 | 2020-03-20 23:31 |  |  | 2019-11-27 17:40 | 2020-03-23 18:00 |  | 35 | 2020-03-23 23:31 |  |  | 2019-12-03 23:59 | 2020-03-30 18:00 |  | 65 | 2020-03-30 23:31 |  |  | 2019-12-09 17:40 | 2020-04-20 18:00 |  | 80 | 2020-04-20 23:31 | [5 empty] | 80 | 2020-08-21 17:37 | [5 empty] | 80 | 2020-08-21 17:37 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2019-12-30 17:40 | 2020-05-04 18:00 |  | 100 | 2020-04-23 23:31 | [121 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 7 |  |  |  | 101021
19 | Task(Task)-->E (Engineering) | G.A OF DRIBBLE CONVEYORS DF-1,DF-2, DF-3 & DF-4 |  | 1.3.1.1 | Unscheduled | No | No | 2020-01-13 18:00 | 2020-02-29 17:40 | 2019-11-30 18:00 | 2020-01-17 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-0028 |  | 2020-02-13 10:26 | 7012-155-PVM-B-028 |  |  |  | A |  |  |  | 9.205 | 0.002219 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 80 | 0 | 5.05 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2289 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-13 18:00 | 2019-11-30 18:00 |  | 10 | 2019-11-30 23:31 |  |  | 2020-01-20 17:40 | 2019-12-12 18:00 |  | 30 | 2019-12-12 23:31 |  |  | 2020-01-25 17:40 | 2019-12-15 23:59 |  | 35 | 2019-12-15 23:31 |  |  | 2020-01-31 23:59 | 2019-12-18 18:00 |  | 65 | 2019-12-18 23:31 |  |  | 2020-02-06 17:40 | 2020-01-03 18:00 |  | 80 | 2020-01-03 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-02-29 17:40 | 2020-01-17 18:00 |  | 100 | [122 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 28 |  |  |  | 101042
20 | Task(Task)-->E (Engineering) | GA OF APRON FEEDERS AF-1,AF-2, AF-3 & AF-4 |  | 1.3.1.1 | Completed | No | No | 2019-10-31 18:00 | 2019-12-12 17:40 | 2020-01-30 09:00 | 2020-02-21 18:00 |  |  | 2020-02-21 14:04 | 2020-08-24 20:07 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1001 |  | 2020-02-13 10:26 | 7012-155-PVM-B-101 |  |  |  | A |  |  |  | 9.205 | 0.002219 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 80 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2287 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-10-31 18:00 | 2020-01-15 18:00 |  | 10 | 2020-01-15 23:31 |  |  | 2019-11-04 17:40 | 2020-01-22 18:00 |  | 30 | 2020-01-22 23:31 |  |  | 2019-11-09 17:40 | 2020-01-25 18:00 |  | 35 | 2020-01-25 23:31 |  |  | 2019-11-15 23:59 | 2020-01-30 18:00 |  | 65 | 2020-01-30 23:31 |  |  | 2019-11-21 17:40 | 2020-02-21 18:00 |  | 80 | 2020-02-21 23:31 | [5 empty] | 80 | 2020-08-19 18:17 | [5 empty] | 80 | 2020-08-19 11:03 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2019-12-12 17:40 | 2020-02-21 18:00 |  | 100 | 2020-08-24 20:08 | [121 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 31 |  |  |  | 101045
21 | Task(Task)-->E (Engineering) | GA OF PRIMARY SIZERS PS-1, PS-2, PS-3 & PS-4 |  | 1.3.1.1 | Completed | No | No | 2019-10-27 23:59 | 2019-12-21 17:40 | 2020-03-30 09:00 | 2020-06-10 18:00 |  |  | 2020-02-21 14:04 | 2020-06-29 19:15 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1006 |  | 2020-02-13 10:27 | 7012-155-PVM-B-106 |  |  |  | A |  |  |  | 9.205 | 0.002219 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 80 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2285 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-10-27 23:59 | 2020-03-18 18:00 |  | 10 | 2020-03-18 23:31 |  |  | 2019-11-13 17:40 | 2020-03-23 18:00 |  | 30 | 2020-03-23 23:31 |  |  | 2019-11-19 17:40 | 2020-03-28 18:00 |  | 35 | 2020-03-28 23:31 |  |  | 2019-11-25 23:59 | 2020-03-30 18:00 |  | 65 | 2020-03-30 23:31 |  |  | 2019-11-30 17:40 | 2020-04-20 18:00 |  | 80 | 2020-04-23 23:31 | [5 empty] | 80 | 2020-06-22 18:44 | [5 empty] | 80 | 2020-06-10 18:01 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2019-12-21 17:40 | 2020-05-04 18:00 |  | 100 | 2020-06-29 19:16 | [121 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 36 |  |  |  | 101050
22 | Task(Task)-->E (Engineering) | Civil | 1.3.1.2 | 1.3.1 | Completed | No | No | 2019-10-31 17:40 | 2020-05-29 17:40 | 2020-01-04 09:00 | 2020-09-10 18:00 |  |  | 2019-10-31 17:40 | 2020-09-10 23:38 |  |  | 100 | 100 | [15 empty] | 79.2691 | 0.22948 | 22.56 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No | 2293 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036071
23 | Task(Task)-->E (Engineering) | DUMP HOPPER STATION (DH-1, DH-2, DH-3 & DH-4) - DESIGN CALCULATION FOR SUPER STRUCTURE |  | 1.3.1.2 | Completed | No | No | 2020-01-21 18:00 | 2020-03-21 17:40 | 2020-05-29 09:00 | 2020-07-03 18:00 |  |  | 2020-02-21 15:30 | 2020-07-04 23:05 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0003 |  | 2020-02-13 11:41 | 7012-155-PVC-U-009 |  |  |  | A |  |  |  | 8.7284 | 0.02003 | 1.97 | Plan & Actual | Date |  | 0 | 0 | 0 | 733.13 | 0 | 38 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2297 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-21 18:00 | 2020-03-30 18:00 |  | 10 | 2020-03-30 23:31 |  |  | 2020-02-10 17:40 | 2020-05-01 18:00 |  | 30 | 2020-05-16 23:31 |  |  | 2020-02-15 17:40 | 2020-05-04 18:00 |  | 35 | 2020-05-20 23:31 |  |  | 2020-02-21 23:59 | 2020-05-11 18:00 |  | 65 | 2020-05-29 23:31 |  |  | 2020-02-28 17:40 | 2020-06-01 18:00 |  | 80 | 2020-07-04 23:03 | [5 empty] | 80 | 2020-07-04 23:03 | [5 empty] | 80 | 2020-07-04 22:58 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-21 17:40 | 2020-06-15 18:00 |  | 100 | 2020-07-04 23:06 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 110 |  |  |  | 101124
24 | Task(Task)-->E (Engineering) | DUMP HOPPER STATION (DH-1, DH-2, DH-3 & DH-4) - DESIGN CALCULATION FOR SUB STRUCTURE |  | 1.3.1.2 | Completed | No | No | 2020-02-29 18:00 | 2020-04-29 17:40 | 2020-06-29 09:00 | 2020-07-13 18:00 |  |  | 2020-02-21 15:30 | 2020-08-03 23:54 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0004 |  | 2020-02-13 11:41 | 7012-155-PVC-U-010 |  |  |  | A |  |  |  | 1.9052 | 0.004372 | 0.43 | Plan & Actual | Date |  | 0 | 0 | 0 | 158.06 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2298 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-29 18:00 | 2020-05-01 18:00 |  | 10 | 2020-05-01 23:31 |  |  | 2020-03-18 17:40 | 2020-06-02 18:00 |  | 30 |  |  |  | 2020-03-24 17:40 | 2020-06-05 18:00 |  | 35 |  |  |  | 2020-03-31 23:59 | 2020-06-12 18:00 |  | 65 | 2020-07-07 21:16 |  |  | 2020-04-06 17:40 | 2020-07-03 18:00 |  | 80 | 2020-07-07 21:22 | [5 empty] | 80 | 2020-08-03 23:50 | [5 empty] | 80 | 2020-08-03 23:50 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-29 17:40 | 2020-07-17 18:00 |  | 100 | 2020-08-03 23:54 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 111 |  |  |  | 101125
25 | Task(Task)-->E (Engineering) | DUMP HOPPER STATION (DH-1, DH-2, DH-3 & DH-4) - DESIGN CALCULATION FOR RETAINING WALL |  | 1.3.1.2 | Completed | No | No | 2020-02-29 18:00 | 2020-04-29 17:40 | 2020-06-17 09:00 | 2020-07-03 18:00 |  |  | 2020-07-04 22:52 | 2020-07-04 22:52 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0005 |  | 2020-02-13 11:41 | 7012-155-PVC-U-011 |  |  |  | A |  |  |  | 42.8002 | 0.098217 | 9.66 | Plan & Actual | Date |  | 0 | 0 | 0 | 3586.04 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2299 | 1 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-29 18:00 | 2020-04-16 18:00 |  | 10 | 2020-04-16 23:31 |  |  | 2020-03-18 17:40 | 2020-05-18 18:00 |  | 30 | 2020-05-12 23:31 |  |  | 2020-03-24 17:40 | 2020-05-21 18:00 |  | 35 |  |  |  | 2020-03-31 23:59 | 2020-05-28 18:00 |  | 65 | 2020-07-04 22:30 |  |  | 2020-04-06 17:40 | 2020-06-18 18:00 |  | 80 | 2020-07-04 22:37 | [5 empty] | 80 | 2020-07-04 22:53 | [5 empty] | 80 | 2020-07-04 22:53 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-29 17:40 | 2020-07-02 18:00 |  | 100 | 2020-07-04 22:40 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 112 |  |  |  | 101126
26 | Task(Task)-->E (Engineering) | DUMP HOPPER STATION (DH-1, DH-2, DH-3 & DH-4) - NUM & RC DETAILS OF FDN |  | 1.3.1.2 | Completed | No | No | 2020-02-29 18:00 | 2020-04-29 17:40 | 2020-06-29 09:00 | 2020-07-13 18:00 |  |  | 2020-02-21 15:37 | 2020-09-10 23:38 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-NR-0002 |  | 2020-02-13 11:41 | 7012-155-PVC-C-013 |  |  |  | A |  |  |  | 1.9052 | 0.004372 | 0.43 | Plan & Actual | Date |  | 0 | 0 | 0 | 158.06 | 0 | 52.15 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2294 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-29 18:00 | 2020-05-01 18:00 |  | 10 |  |  |  | 2020-03-18 17:40 | 2020-06-02 18:00 |  | 30 |  |  |  | 2020-03-24 17:40 | 2020-06-05 18:00 |  | 35 | 2020-06-29 15:58 |  |  | 2020-03-31 23:59 | 2020-06-12 18:00 |  | 65 | 2020-07-07 21:14 |  |  | 2020-04-06 17:40 | 2020-07-03 18:00 |  | 80 | 2020-07-07 21:21 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | 2020-09-10 23:23 | [5 empty] | 80 | 2020-09-10 23:23 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-29 17:40 | 2020-07-17 18:00 |  | 100 | 2020-09-10 23:39 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 114 |  |  |  | 101128
27 | Task(Task)-->E (Engineering) | DUMP HOPPER STATION (DH-1, DH-2, DH-3 & DH-4) - NUM & RC DETAILS OF GRADE SLAB |  | 1.3.1.2 | Completed | No | No | 2020-03-30 18:00 | 2020-05-29 17:40 | 2020-08-14 09:00 | 2020-09-10 18:00 |  |  | 2020-02-21 15:37 | 2020-09-10 23:14 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-NR-0003 |  | 2020-02-13 11:41 | 7012-155-PVC-C-014 |  |  |  | A |  |  |  | 0.88613 | 0.002033 | 0.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 74.27 | 0 | 49.1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2295 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-30 18:00 | 2020-05-31 23:59 |  | 10 |  |  |  | 2020-04-17 17:40 | 2020-07-02 18:00 |  | 30 |  |  |  | 2020-04-23 17:40 | 2020-07-05 23:59 |  | 35 | 2020-08-14 23:25 |  |  | 2020-04-30 23:59 | 2020-07-12 23:59 |  | 65 | 2020-08-14 23:30 |  |  | 2020-05-06 17:40 | 2020-08-02 23:59 |  | 80 | 2020-09-10 22:17 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-29 17:40 | 2020-08-16 23:59 |  | 100 | 2020-09-10 23:15 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 115 |  |  |  | 101129
28 | Task(Task)-->E (Engineering) | DUMP HOPPER STATION (DH-1, DH-2, DH-3 & DH-4) - NUM & RC DETAILS OF RETAINING WALL |  | 1.3.1.2 | Completed | No | No | 2020-02-29 18:00 | 2020-04-29 17:40 | 2020-06-17 09:00 | 2020-07-03 18:00 |  |  | 2020-07-04 22:41 | 2020-07-04 22:41 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-NR-0004 |  | 2020-02-13 11:41 | 7012-155-PVC-C-015 |  |  |  | A |  |  |  | 42.8002 | 0.098217 | 9.66 | Plan & Actual | Date |  | 0 | 0 | 0 | 3586.04 | 0 | 53.1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2296 | 1 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-29 18:00 | 2020-04-16 18:00 |  | 10 | 2020-04-16 23:31 |  |  | 2020-03-18 17:40 | 2020-05-18 18:00 |  | 30 |  |  |  | 2020-03-24 17:40 | 2020-05-21 18:00 |  | 35 | 2020-06-11 12:23 |  |  | 2020-03-31 23:59 | 2020-05-28 18:00 |  | 65 | 2020-07-04 22:23 |  |  | 2020-04-06 17:40 | 2020-06-18 18:00 |  | 80 | 2020-07-04 22:36 | [5 empty] | 80 | 2020-07-04 22:42 | [5 empty] | 80 | 2020-07-04 22:42 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-29 17:40 | 2020-07-02 18:00 |  | 100 | 2020-07-04 22:38 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 116 |  |  |  | 101130
29 | Task(Task)-->E (Engineering) | MANUAL POWER AND TENSION CALCULATION FOR TROUGH CONVEYOR SC 1A/B AND SC 2A/B |  | 1.3.1.2 | Completed | No | No | 2019-10-31 17:40 | 2019-12-09 17:40 | 2020-01-04 09:00 | 2020-02-25 18:00 |  |  | 2019-10-31 17:40 | 2020-03-02 10:56 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-CS-DC-0003 |  | 2020-02-13 10:26 | 7012-155-PVM-U-003 |  |  |  | A |  |  |  | 0.97475 | 0.002237 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3056 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-10-19 18:00 | 2019-12-11 18:00 |  | 10 | 2019-12-11 23:31 |  |  | 2019-10-31 17:40 | 2020-01-01 18:00 |  | 30 | 2020-01-01 23:31 |  |  | 2019-11-06 17:40 | 2020-01-04 18:00 |  | 35 | 2020-01-04 23:31 |  |  | 2019-11-12 23:59 | 2020-01-04 18:00 |  | 65 | 2020-01-04 23:31 |  |  | 2019-11-18 17:40 | 2020-02-03 18:00 |  | 80 | 2020-02-03 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2019-12-09 17:40 | 2020-02-25 18:00 |  | 100 | 2020-02-25 23:31 | [121 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 3 |  |  |  | 101017
30 | Task(Task)-->E (Engineering) | Structural | 1.3.1.3 | 1.3.1 | Work In Progress | No | No | 2020-01-21 18:00 | 2020-07-13 17:40 | 2020-05-29 09:00 | 2020-08-31 18:00 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 98.1489 | [15 empty] | 7.3085 | 0.021158 | 2.08 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No | 2300 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036072
31 | Task(Task)-->E (Engineering) | DUMP HOPPER STATION (DH-1, DH-2, DH-3 & DH-4) - STRUCTURAL GA |  | 1.3.1.3 | Completed | No | No | 2020-01-21 18:00 | 2020-03-21 17:40 | 2020-05-29 09:00 | 2020-07-03 18:00 |  |  | 2020-02-21 15:37 | 2020-07-04 23:07 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-GA-0004 |  | 2020-02-13 11:41 | 7012-155-PVC-B-012 |  |  |  | A |  |  |  | 94.7115 | 0.020039 | 1.97 | Plan & Actual | Date |  | 0 | 0 | 0 | 733.13 | 0 | 86 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2301 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-21 18:00 | 2020-03-30 18:00 |  | 10 | 2020-03-30 23:31 |  |  | 2020-02-10 17:40 | 2020-05-01 18:00 |  | 30 | 2020-05-16 23:31 |  |  | 2020-02-15 17:40 | 2020-05-04 18:00 |  | 35 | 2020-05-20 23:31 |  |  | 2020-02-21 23:59 | 2020-05-11 18:00 |  | 65 | 2020-05-29 23:31 |  |  | 2020-02-28 17:40 | 2020-06-01 18:00 |  | 80 | 2020-07-04 23:04 | [5 empty] | 80 | 2020-07-04 23:04 | [5 empty] | 80 | 2020-07-04 22:59 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-21 17:40 | 2020-06-15 18:00 |  | 100 | 2020-07-04 23:08 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 113 |  |  |  | 101127
32 | Task(Task)-->E (Engineering) | ARCHITECTURAL GA OF DUMP HOPPER STATION (DH-1, DH-2, DH-3 & DH-4) |  | 1.3.1.3 | Unscheduled | No | No | 2020-05-14 18:00 | 2020-07-13 17:40 | 2020-06-22 18:00 | 2020-08-31 18:00 |  |  | 2020-02-21 15:39 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-AR-0001 |  | 2020-02-13 11:43 | 7012-155-PVC-C-107 |  |  |  | I |  |  |  | 5.2885 | 0.001119 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 40.52 | 0 | 56 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2302 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-05-14 18:00 | 2020-06-22 18:00 |  | 10 |  |  |  | 2020-06-02 17:40 | 2020-07-17 18:00 |  | 30 |  |  |  | 2020-06-08 17:40 | 2020-07-20 18:00 |  | 35 | 2020-10-14 16:46 |  |  | 2020-06-14 23:59 | 2020-07-27 18:00 |  | 65 | 2020-10-14 17:37 |  |  | 2020-06-19 17:40 | 2020-08-17 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-07-13 17:40 | 2020-08-31 18:00 |  | 100 | [122 empty] | Chetan Khodke |  |  |  |  | A - Architecture | [16 empty] | 208 |  |  |  | 101218
33 | Task(Task)-->E (Engineering) | ELECTRICAL | 1.3.1.4 | 1.3.1 | Unscheduled | No | No | 2019-12-25 18:00 | 2020-04-21 17:40 | 2020-04-12 23:59 | 2020-08-18 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 73.9304 | [15 empty] | 5.0949 | 0.014749 | 1.45 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No | 2305 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036073
34 | Task(Task)-->E (Engineering) | GA, DATA SHEET, TERMINAL BOX ARRANGEMET & CHARACTERISTICS CURVES OF LT MOTOR (CONVEYING SYSTEM) |  | 1.3.1.4 | Unscheduled | No | No | 2020-02-15 17:40 | 2020-03-27 17:40 | 2020-05-31 23:59 | 2020-08-18 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-162 |  | 2020-02-13 11:46 | 7012-155-PVE-W-107 |  |  |  | A |  |  |  | 7.5862 | 0.001119 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2308 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-15 18:00 | 2020-05-31 23:59 |  | 10 |  |  |  | 2020-02-15 17:40 | 2020-06-07 23:59 |  | 30 |  |  |  | 2020-02-21 17:40 | 2020-06-13 18:00 |  | 35 |  |  |  | 2020-02-28 23:59 | 2020-06-13 18:00 |  | 65 |  |  |  | 2020-03-05 17:40 | 2020-07-04 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-27 17:40 | 2020-07-04 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 342 |  |  |  | 101353
35 | Task(Task)-->E (Engineering) | EQUIPMENT, CABLE ROUTING, EARTHING & LIGHTNING LAYOUT WITH PLAN, SECTIONAL VIEWS & BOM OF DUMP HOPPER |  | 1.3.1.4 | Unscheduled | No | No | 2019-12-25 18:00 | 2020-02-19 17:40 | 2020-04-12 23:59 | 2020-05-31 23:59 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5052 |  | 2020-02-13 11:44 | 7012-155-PVE-F-014 |  |  |  | A |  |  |  | 46.2069 | 0.006815 | 0.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 248.42 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2306 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-12-25 18:00 | 2020-04-12 23:59 |  | 10 | 2020-04-12 23:31 |  |  | 2020-01-10 17:40 | 2020-04-26 23:59 |  | 30 | 2020-04-20 23:31 |  |  | 2020-01-16 17:40 | 2020-05-03 23:59 |  | 35 | 2020-04-27 23:31 |  |  | 2020-01-22 23:59 | 2020-05-10 23:59 |  | 65 | 2020-04-30 23:31 |  |  | 2020-01-28 17:40 | 2020-05-31 23:59 |  | 80 | 2020-05-11 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-02-19 17:40 | 2020-05-31 23:59 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 249 |  |  |  | 101260
36 | Task(Task)-->E (Engineering) | LIGHTING LAYOUT PLAN WITH POWER DISTRIBUTION ARRANGEMENT, SECTIONAL VIEW, BOM OF DUMP HOPPER |  | 1.3.1.4 | Unscheduled | No | No | 2020-03-02 18:00 | 2020-04-21 17:40 | 2020-04-24 18:00 | 2020-06-05 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5063 |  | 2020-02-13 11:44 | 7012-155-PVE-G-025 |  |  |  | A |  |  |  | 46.2069 | 0.006815 | 0.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 248.42 | 0 | 24.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2307 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-02 18:00 | 2020-04-24 18:00 |  | 10 | 2020-04-24 23:31 |  |  | 2020-03-10 17:40 | 2020-05-01 18:00 |  | 30 | 2020-04-28 23:31 |  |  | 2020-03-17 17:40 | 2020-05-08 18:00 |  | 35 | 2020-04-28 23:31 |  |  | 2020-03-23 23:59 | 2020-05-15 18:00 |  | 65 | 2020-04-30 23:31 |  |  | 2020-03-30 17:40 | 2020-06-05 18:00 |  | 80 | 2020-05-11 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-21 17:40 | 2020-06-05 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 260 |  |  |  | 101271
37 | Task(Task)-->P (Procurement) | PROCUREMENT | 1.3.2 | 1.3 | Work In Progress | No | No | 2019-09-27 09:00 | 2021-02-28 23:59 | 2019-09-27 09:00 | 2021-05-13 18:00 |  |  | 2019-09-27 10:57 |  |  |  | 84.9997 | 44.352 | [15 empty] | 47.1465 | 4.4622 | 438.83 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2310 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017708
38 | Task(Task)-->P (Procurement) | PURCHASE REQUISITION | 1.3.2.1 | 1.3.2 | Completed | No | No | 2019-09-27 09:00 | 2020-05-19 18:00 | 2019-09-27 09:00 | 2020-05-29 18:00 |  |  | 2019-09-27 10:57 | 2020-05-31 18:44 |  |  | 100 | 100 | [15 empty] | 4.9952 | 0.2229 | 21.92 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2311 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017709
39 | Task(Task)-->P (Procurement) | Apron Feeder |  | 1.3.2.1 | Completed | No | No | 2019-09-27 09:00 | 2019-09-27 18:00 | 2019-09-27 09:00 | 2019-09-27 18:00 |  |  | 2019-09-27 10:57 | 2019-09-27 10:57 |  |  | 100 | 100 | [15 empty] | 19.1062 | 0.042587 | 4.19 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2312 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017710
40 | Task(Task)-->P (Procurement) | Gear Box for Apron Feeder |  | 1.3.2.1 | Completed | No | No | 2019-11-13 09:00 | 2019-11-13 18:00 | 2020-01-20 09:00 | 2020-01-20 18:00 |  |  | 2020-01-20 11:17 | 2020-01-20 11:17 |  |  | 100 | 100 | [15 empty] | 0.91199 | 0.002033 | 0.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2313 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017711
41 | Task(Task)-->P (Procurement) | Geared Coupling for Apron Feeder |  | 1.3.2.1 | Completed | No | No | 2019-11-21 09:00 | 2019-11-21 18:00 | 2020-04-04 09:00 | 2020-04-04 18:00 |  |  | 2020-04-04 10:57 | 2020-04-04 10:57 |  |  | 100 | 100 | [15 empty] | 0.1824 | 0.000407 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2314 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017712
42 | Task(Task)-->P (Procurement) | Primary Sizer |  | 1.3.2.1 | Completed | No | No | 2019-09-27 09:00 | 2019-09-27 18:00 | 2019-09-27 09:00 | 2019-09-27 18:00 |  |  | 2019-09-27 10:57 | 2019-09-27 10:57 |  |  | 100 | 100 | [15 empty] | 37.8477 | 0.084361 | 8.3 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2315 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017713
43 | Task(Task)-->P (Procurement) | Pulley for Dribble Conveyor |  | 1.3.2.1 | Completed | No | No | 2019-09-27 09:00 | 2019-09-27 18:00 | 2020-02-05 09:00 | 2020-02-05 18:00 |  |  | 2020-02-05 16:16 | 2020-02-05 16:16 |  |  | 100 | 100 | [15 empty] | 1.0032 | 0.002236 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2316 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017714
44 | Task(Task)-->P (Procurement) | Idler for Dribble Conveyor |  | 1.3.2.1 | Completed | No | No | 2019-12-19 09:00 | 2019-12-19 18:00 | 2020-02-13 09:00 | 2020-02-13 18:00 |  |  | 2020-02-13 14:52 | 2020-02-13 14:52 |  |  | 100 | 100 | [15 empty] | 0.228 | 0.000508 | 0.05 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2317 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017715
45 | Task(Task)-->P (Procurement) | Plummer Block for Dribble Conveyor |  | 1.3.2.1 | Completed | No | No | 2020-05-17 | 2020-05-17 23:59 | 2020-02-10 09:00 | 2020-02-10 18:00 |  |  | 2020-02-10 09:26 | 2020-02-10 09:26 |  |  | 100 | 100 | [15 empty] | 0.091199 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2318 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017716
46 | Task(Task)-->P (Procurement) | Bearing for Dribble Conveyor |  | 1.3.2.1 | Completed | No | No | 2020-05-17 | 2020-05-17 23:59 | 2020-02-10 09:00 | 2020-02-10 18:00 |  |  | 2020-02-10 09:36 | 2020-02-10 09:36 |  |  | 100 | 100 | [15 empty] | 0.1368 | 0.000305 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2319 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017717
47 | Task(Task)-->P (Procurement) | Belting for Dribble Conveyor |  | 1.3.2.1 | Completed | No | No | 2019-11-07 09:00 | 2019-11-07 18:00 | 2020-01-20 09:00 | 2020-01-20 18:00 |  |  | 2020-01-20 15:54 | 2020-01-20 15:54 |  |  | 100 | 100 | [15 empty] | 0.2736 | 0.00061 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2320 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017718
48 | Task(Task)-->P (Procurement) | Scrapper for Dribble Conveyor |  | 1.3.2.1 | Completed | No | No | 2019-11-17 | 2019-11-17 23:59 | 2020-03-11 09:00 | 2020-03-11 18:00 |  |  | 2020-03-11 10:57 | 2020-03-11 10:57 |  |  | 100 | 100 | [15 empty] | 0.1824 | 0.000407 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2321 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017719
49 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.3.2.1 | Completed | No | No | 2020-03-10 09:00 | 2020-03-10 18:00 | 2020-03-11 09:00 | 2020-03-11 18:00 |  |  | 2020-03-11 12:41 | 2020-03-11 12:41 |  |  | 100 | 100 | [15 empty] | 0.86639 | 0.001931 | 0.19 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2322 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017720
50 | Task(Task)-->P (Procurement) | Chute & Skirt |  | 1.3.2.1 | Completed | No | No | 2020-03-10 09:00 | 2020-03-10 18:00 | 2020-03-11 09:00 | 2020-03-11 18:00 |  |  | 2020-03-11 10:57 | 2020-03-11 10:57 |  |  | 100 | 100 | [15 empty] | 3.9672 | 0.008843 | 0.87 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2323 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017721
51 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.3.2.1 | Completed | No | No | 2020-05-19 09:00 | 2020-05-19 18:00 | 2020-04-16 09:00 | 2020-04-16 18:00 |  |  | 2020-04-16 10:57 | 2020-04-16 10:57 |  |  | 100 | 100 | [15 empty] | 0.0456 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2324 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017722
52 | Task(Task)-->P (Procurement) | Gear Box for Dribble Conveyor |  | 1.3.2.1 | Completed | No | No | 2019-11-13 09:00 | 2019-11-13 18:00 | 2020-01-20 09:00 | 2020-01-20 18:00 |  |  | 2020-01-20 11:17 | 2020-01-20 11:17 |  |  | 100 | 100 | [15 empty] | 0.91199 | 0.002033 | 0.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2325 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017723
53 | Task(Task)-->P (Procurement) | Geared Coupling for Dribble Conveyor |  | 1.3.2.1 | Completed | No | No | 2019-11-21 09:00 | 2019-11-21 18:00 | 2020-01-22 09:00 | 2020-01-22 18:00 |  |  | 2020-01-22 10:41 | 2020-01-22 10:41 |  |  | 100 | 100 | [15 empty] | 0.228 | 0.000508 | 0.05 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2326 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017724
54 | Task(Task)-->P (Procurement) | Building Structure |  | 1.3.2.1 | Completed | No | No | 2020-02-21 09:00 | 2020-02-21 18:00 | 2020-05-29 09:00 | 2020-05-29 18:00 |  |  | 2020-05-31 18:44 | 2020-05-31 18:44 |  |  | 100 | 100 | [15 empty] | 31.2358 | 0.069623 | 6.85 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2327 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017725
55 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR CONVEYING SYSTEM |  | 1.3.2.1 | Completed | No | No | 2019-12-16 09:00 | 2019-12-16 18:00 | 2020-01-13 09:00 | 2020-01-13 18:00 |  |  | 2020-01-13 10:57 | 2020-01-13 10:57 |  |  | 100 | 100 | [15 empty] | 0.72959 | 0.001626 | 0.16 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2328 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017726
56 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.3.2.1 | Completed | No | No | 2020-03-10 09:00 | 2020-03-10 18:00 | 2020-03-16 09:00 | 2020-03-16 18:00 |  |  | 2020-03-16 10:57 | 2020-03-16 10:57 |  |  | 100 | 100 | [15 empty] | 1.2312 | 0.002744 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2329 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017727
57 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.3.2.1 | Completed | No | No | 2020-03-27 09:00 | 2020-03-27 18:00 | 2020-04-30 09:00 | 2020-04-30 18:00 |  |  | 2020-04-30 10:57 | 2020-04-30 10:57 |  |  | 100 | 100 | [15 empty] | 0.5472 | 0.00122 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2330 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017728
58 | Task(Task)-->P (Procurement) | LPBS |  | 1.3.2.1 | Completed | No | No | 2020-03-20 09:00 | 2020-03-20 18:00 | 2020-04-14 09:00 | 2020-04-14 18:00 |  |  | 2020-04-14 16:52 | 2020-04-14 16:52 |  |  | 100 | 100 | [15 empty] | 0.091199 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2331 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017729
59 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.3.2.1 | Completed | No | No | 2020-01-08 09:00 | 2020-01-08 18:00 | 2020-01-08 09:00 | 2020-01-08 18:00 |  |  | 2020-01-08 10:57 | 2020-01-08 10:57 |  |  | 100 | 100 | [15 empty] | 0.0456 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2334 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017730
60 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.3.2.1 | Completed | No | No | 2019-12-30 09:00 | 2019-12-30 18:00 | 2019-12-30 09:00 | 2019-12-30 18:00 |  |  | 2019-12-30 10:57 | 2019-12-30 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2335 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017731
61 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.3.2.1 | Completed | No | No | 2020-01-03 09:00 | 2020-01-03 18:00 | 2020-01-03 09:00 | 2020-01-03 18:00 |  |  | 2020-01-03 10:57 | 2020-01-03 10:57 |  |  | 100 | 100 | [15 empty] | 0.0456 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2336 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017732
62 | Task(Task)-->P (Procurement) | CONTROL JUNCTION BOX |  | 1.3.2.1 | Completed | No | No | 2020-03-05 09:00 | 2020-03-05 18:00 | 2020-04-18 09:00 | 2020-04-18 18:00 |  |  | 2020-04-18 10:57 | 2020-04-18 10:57 |  |  | 100 | 100 | [15 empty] | 0.091199 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2337 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017733
63 | Task(Task)-->P (Procurement) | TECHNICAL CLEARANCE | 1.3.2.2 | 1.3.2 | Completed | No | No | 2019-09-28 09:00 | 2020-06-18 18:00 | 2019-09-27 09:00 | 2020-06-12 18:00 |  |  | 2019-10-31 10:57 | 2020-06-12 16:53 |  |  | 100 | 100 | [15 empty] | 4.9998 | 0.2231 | 21.94 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2338 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017734
64 | Task(Task)-->P (Procurement) | Apron Feeder |  | 1.3.2.2 | Completed | No | No | 2019-09-28 09:00 | 2019-10-11 18:00 | 2019-09-27 09:00 | 2019-10-31 18:00 |  |  | 2019-10-31 10:57 | 2019-10-31 10:57 |  |  | 100 | 100 | [15 empty] | 19.0888 | 0.042587 | 4.19 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2339 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017735
65 | Task(Task)-->P (Procurement) | Gear Box for Apron Feeder |  | 1.3.2.2 | Completed | No | No | 2019-11-14 09:00 | 2020-02-26 18:00 | 2020-01-20 09:00 | 2020-03-20 18:00 |  |  | 2020-01-22 11:19 | 2020-03-20 11:19 |  |  | 100 | 100 | [15 empty] | 0.91116 | 0.002033 | 0.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2340 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017736
66 | Task(Task)-->P (Procurement) | Geared Coupling for Apron Feeder |  | 1.3.2.2 | Completed | No | No | 2019-11-22 09:00 | 2020-03-19 18:00 | 2020-04-04 09:00 | 2020-04-09 18:00 |  |  | 2020-04-09 10:57 | 2020-04-09 10:57 |  |  | 100 | 100 | [15 empty] | 0.18223 | 0.000407 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2341 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017737
67 | Task(Task)-->P (Procurement) | Primary Sizer |  | 1.3.2.2 | Completed | No | No | 2019-09-28 09:00 | 2019-10-16 18:00 | 2019-09-27 09:00 | 2019-11-07 18:00 |  |  | 2019-11-07 10:57 | 2019-11-07 10:57 |  |  | 100 | 100 | [15 empty] | 37.8132 | 0.084361 | 8.3 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2342 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017738
68 | Task(Task)-->P (Procurement) | Pulley for Dribble Conveyor |  | 1.3.2.2 | Completed | No | No | 2019-09-28 09:00 | 2020-01-04 18:00 | 2020-02-05 09:00 | 2020-02-10 18:00 |  |  | 2020-02-06 16:19 | 2020-02-10 16:19 |  |  | 100 | 100 | [15 empty] | 1.0023 | 0.002236 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2343 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017739
69 | Task(Task)-->P (Procurement) | Idler for Dribble Conveyor |  | 1.3.2.2 | Completed | No | No | 2019-12-20 09:00 | 2020-02-01 18:00 | 2020-02-13 09:00 | 2020-03-26 18:00 |  |  | 2020-02-14 14:56 | 2020-03-26 14:56 |  |  | 100 | 100 | [15 empty] | 0.22779 | 0.000508 | 0.05 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2344 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017740
70 | Task(Task)-->P (Procurement) | Plummer Block for Dribble Conveyor |  | 1.3.2.2 | Completed | No | No | 2020-05-18 09:00 | 2020-06-01 18:00 | 2020-02-10 09:00 | 2020-02-10 18:00 |  |  | 2020-02-10 09:28 | 2020-02-10 09:28 |  |  | 100 | 100 | [15 empty] | 0.091116 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2345 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017741
71 | Task(Task)-->P (Procurement) | Bearing for Dribble Conveyor |  | 1.3.2.2 | Completed | No | No | 2020-05-18 09:00 | 2020-06-16 18:00 | 2020-02-10 09:00 | 2020-02-10 18:00 |  |  | 2020-02-10 09:37 | 2020-02-10 09:37 |  |  | 100 | 100 | [15 empty] | 0.13667 | 0.000305 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2346 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017742
72 | Task(Task)-->P (Procurement) | Belting for Dribble Conveyor |  | 1.3.2.2 | Completed | No | No | 2019-11-08 09:00 | 2020-01-06 18:00 | 2020-01-20 09:00 | 2020-05-16 18:00 |  |  | 2020-05-16 10:57 | 2020-05-16 10:57 |  |  | 100 | 100 | [15 empty] | 0.27335 | 0.00061 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2347 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017743
73 | Task(Task)-->P (Procurement) | Scrapper for Dribble Conveyor |  | 1.3.2.2 | Completed | No | No | 2019-11-18 09:00 | 2020-03-16 18:00 | 2020-03-11 09:00 | 2020-03-26 18:00 |  |  | 2020-03-26 10:57 | 2020-03-26 10:57 |  |  | 100 | 100 | [15 empty] | 0.18223 | 0.000407 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2348 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017744
74 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.3.2.2 | Completed | No | No | 2020-03-11 09:00 | 2020-03-20 18:00 | 2020-03-11 09:00 | 2020-03-17 18:00 |  |  | 2020-03-12 12:43 | 2020-03-17 12:43 |  |  | 100 | 100 | [15 empty] | 0.8656 | 0.001931 | 0.19 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2349 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017745
75 | Task(Task)-->P (Procurement) | Chute & Skirt |  | 1.3.2.2 | Completed | No | No | 2020-03-11 09:00 | 2020-03-20 18:00 | 2020-03-11 09:00 | 2020-03-17 18:00 |  |  | 2020-03-17 10:57 | 2020-03-17 10:57 |  |  | 100 | 100 | [15 empty] | 3.9636 | 0.008843 | 0.87 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2350 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017746
76 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.3.2.2 | Completed | No | No | 2020-05-20 09:00 | 2020-06-18 18:00 | 2020-04-16 09:00 | 2020-04-16 18:00 |  |  | 2020-04-16 10:57 | 2020-04-16 10:57 |  |  | 100 | 100 | [15 empty] | 0.045558 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2351 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017747
77 | Task(Task)-->P (Procurement) | Gear Box for Dribble Conveyor |  | 1.3.2.2 | Completed | No | No | 2019-11-14 09:00 | 2020-02-26 18:00 | 2020-01-20 09:00 | 2020-03-20 18:00 |  |  | 2020-01-22 11:19 | 2020-03-20 11:19 |  |  | 100 | 100 | [15 empty] | 0.91116 | 0.002033 | 0.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2352 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017748
78 | Task(Task)-->P (Procurement) | Geared Coupling for Dribble Conveyor |  | 1.3.2.2 | Completed | No | No | 2019-11-22 09:00 | 2020-03-19 18:00 | 2020-01-22 09:00 | 2020-04-13 18:00 |  |  | 2020-04-13 10:46 | 2020-04-13 10:46 |  |  | 100 | 100 | [15 empty] | 0.22779 | 0.000508 | 0.05 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2353 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017749
79 | Task(Task)-->P (Procurement) | Building Structure |  | 1.3.2.2 | Completed | No | No | 2020-02-22 09:00 | 2020-02-28 18:00 | 2020-05-29 09:00 | 2020-05-29 18:00 |  |  | 2020-05-29 17:31 | 2020-05-29 17:31 |  |  | 100 | 100 | [15 empty] | 31.2073 | 0.069623 | 6.85 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2354 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017750
80 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR CONVEYING SYSTEM |  | 1.3.2.2 | Completed | No | No | 2019-12-17 09:00 | 2019-12-31 18:00 | 2020-01-13 09:00 | 2020-04-11 18:00 |  |  | 2020-04-11 10:57 | 2020-04-11 10:57 |  |  | 100 | 100 | [15 empty] | 0.72893 | 0.001626 | 0.16 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2355 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017751
81 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.3.2.2 | Completed | No | No | 2020-03-11 09:00 | 2020-03-25 18:00 | 2020-03-16 09:00 | 2020-06-02 18:00 |  |  | 2020-06-02 10:57 | 2020-06-02 10:57 |  |  | 100 | 100 | [15 empty] | 1.2301 | 0.002744 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2356 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017752
82 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.3.2.2 | Completed | No | No | 2020-03-28 09:00 | 2020-05-11 18:00 | 2020-04-30 09:00 | 2020-06-03 18:00 |  |  | 2020-06-03 10:57 | 2020-06-03 10:57 |  |  | 100 | 100 | [15 empty] | 0.5467 | 0.00122 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2357 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017753
83 | Task(Task)-->P (Procurement) | LPBS |  | 1.3.2.2 | Completed | No | No | 2020-03-21 09:00 | 2020-04-04 18:00 | 2020-04-14 09:00 | 2020-06-12 18:00 |  |  | 2020-04-14 16:53 | 2020-06-12 16:53 |  |  | 100 | 100 | [15 empty] | 0.091116 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2358 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017754
84 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.3.2.2 | Completed | No | No | 2020-01-09 09:00 | 2020-01-22 18:00 | 2020-01-08 09:00 | 2020-03-10 18:00 |  |  | 2020-03-10 10:57 | 2020-03-10 10:57 |  |  | 100 | 100 | [15 empty] | 0.13667 | 0.000305 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2361 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017755
85 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.3.2.2 | Completed | No | No | 2019-12-31 09:00 | 2020-01-14 18:00 | 2019-12-30 09:00 | 2020-03-07 18:00 |  |  | 2020-03-07 10:57 | 2020-03-07 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2362 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017756
86 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.3.2.2 | Completed | No | No | 2020-01-04 09:00 | 2020-01-18 18:00 | 2020-01-03 09:00 | 2020-01-16 18:00 |  |  | 2020-01-16 10:57 | 2020-01-16 10:57 |  |  | 100 | 100 | [15 empty] | 0.045558 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2363 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017757
87 | Task(Task)-->P (Procurement) | CONTROL JUNCTION BOX |  | 1.3.2.2 | Completed | No | No | 2020-03-06 09:00 | 2020-03-13 18:00 | 2020-04-18 09:00 | 2020-06-02 18:00 |  |  | 2020-06-02 10:57 | 2020-06-02 10:57 |  |  | 100 | 100 | [15 empty] | 0.091116 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2364 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017758
88 | Task(Task)-->P (Procurement) | ORDERING | 1.3.2.3 | 1.3.2 | Work In Progress | No | No | 2019-10-12 09:00 | 2020-07-18 18:00 | 2019-10-31 09:00 | 2020-09-04 18:00 |  |  | 2020-01-05 08:00 |  |  |  | 100 | 99.9545 | [15 empty] | 9.9995 | 0.4462 | 43.88 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2365 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017759
89 | Task(Task)-->P (Procurement) | Apron Feeder |  | 1.3.2.3 | Completed | No | No | 2019-10-12 09:00 | 2019-11-10 23:59 | 2019-10-31 09:00 | 2020-01-29 18:00 |  |  | 2020-01-29 10:57 | 2020-01-29 10:57 |  |  | 100 | 100 | [15 empty] | 19.0975 | 0.085213 | 8.38 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2366 | 0 | 4 | Low | ADMINISTRATOR | [6 empty] | 0 | 0 | [244 empty] | 1017760
90 | Task(Task)-->P (Procurement) | Gear Box for Apron Feeder |  | 1.3.2.3 | Completed | No | No | 2020-02-27 09:00 | 2020-03-27 18:00 | 2020-03-20 09:00 | 2020-04-30 18:00 |  |  | 2020-03-21 11:21 | 2020-04-30 11:21 |  |  | 100 | 100 | [15 empty] | 0.91158 | 0.004067 | 0.4 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2367 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017761
91 | Task(Task)-->P (Procurement) | Geared Coupling for Apron Feeder |  | 1.3.2.3 | Completed | No | No | 2020-03-20 09:00 | 2020-04-18 18:00 | 2020-04-09 09:00 | 2020-04-30 18:00 |  |  | 2020-04-30 10:57 | 2020-04-30 10:57 |  |  | 100 | 100 | [15 empty] | 0.15953 | 0.000712 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2368 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017762
92 | Task(Task)-->P (Procurement) | Primary Sizer |  | 1.3.2.3 | Completed | No | No | 2019-10-17 09:00 | 2019-11-20 18:00 | 2019-11-07 09:00 | 2020-02-25 18:00 |  |  | 2020-02-25 10:57 | 2020-02-25 10:57 |  |  | 100 | 100 | [15 empty] | 37.8532 | 0.1689 | 16.61 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2369 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017763
93 | Task(Task)-->P (Procurement) | Pulley for Dribble Conveyor |  | 1.3.2.3 | Completed | No | No | 2020-01-05 | 2020-02-03 18:00 | 2020-02-10 09:00 | 2020-03-21 18:00 |  |  | 2020-01-05 08:00 | 2020-03-21 16:05 |  |  | 100 | 100 | [15 empty] | 1.0255 | 0.004576 | 0.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2370 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017764
94 | Task(Task)-->P (Procurement) | Idler for Dribble Conveyor |  | 1.3.2.3 | Completed | No | No | 2020-02-02 | 2020-03-02 18:00 | 2020-03-26 09:00 | 2020-04-30 18:00 |  |  | 2020-03-27 14:58 | 2020-04-30 14:57 |  |  | 100 | 100 | [15 empty] | 0.2051 | 0.000915 | 0.09 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2371 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017765
95 | Task(Task)-->P (Procurement) | Plummer Block for Dribble Conveyor |  | 1.3.2.3 | Completed | No | No | 2020-06-02 09:00 | 2020-07-01 18:00 | 2020-02-10 09:00 | 2020-03-24 18:00 |  |  | 2020-02-11 09:32 | 2020-03-24 09:32 |  |  | 100 | 100 | [15 empty] | 0.068368 | 0.000305 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2372 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017766
96 | Task(Task)-->P (Procurement) | Bearing for Dribble Conveyor |  | 1.3.2.3 | Completed | No | No | 2020-06-17 09:00 | 2020-07-16 18:00 | 2020-02-10 09:00 | 2020-03-24 18:00 |  |  | 2020-02-11 09:40 | 2020-03-24 09:40 |  |  | 100 | 100 | [15 empty] | 0.13674 | 0.00061 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2373 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017767
97 | Task(Task)-->P (Procurement) | Belting for Dribble Conveyor |  | 1.3.2.3 | Completed | No | No | 2020-01-07 09:00 | 2020-02-20 18:00 | 2020-05-16 09:00 | 2020-09-04 18:00 |  |  | 2020-05-16 16:24 | 2020-09-04 16:24 |  |  | 100 | 100 | [15 empty] | 0.27347 | 0.00122 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2374 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017768
98 | Task(Task)-->P (Procurement) | Scrapper for Dribble Conveyor |  | 1.3.2.3 | Completed | No | No | 2020-03-17 09:00 | 2020-04-15 18:00 | 2020-03-26 09:00 | 2020-05-30 18:00 |  |  | 2020-05-30 10:57 | 2020-05-30 10:57 |  |  | 100 | 100 | [15 empty] | 0.15953 | 0.000712 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2375 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017769
99 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.3.2.3 | Completed | No | No | 2020-03-21 09:00 | 2020-04-19 23:59 | 2020-03-17 09:00 | 2020-07-06 18:00 |  |  | 2020-03-18 12:44 | 2020-07-06 12:44 |  |  | 100 | 100 | [15 empty] | 0.866 | 0.003864 | 0.38 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2376 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017770
100 | Task(Task)-->P (Procurement) | Chute & Skirt |  | 1.3.2.3 | Completed | No | No | 2020-03-21 09:00 | 2020-04-19 23:59 | 2020-03-17 09:00 | 2020-07-06 18:00 |  |  | 2020-03-18 12:49 | 2020-07-06 12:49 |  |  | 100 | 100 | [15 empty] | 3.9426 | 0.017592 | 1.73 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2377 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017771
101 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.3.2.3 | Unscheduled | No | No | 2020-06-19 09:00 | 2020-07-18 18:00 | 2020-04-16 09:00 | 2020-08-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.045579 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2378 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017772
102 | Task(Task)-->P (Procurement) | Gear Box for Dribble Conveyor |  | 1.3.2.3 | Completed | No | No | 2020-02-27 09:00 | 2020-03-27 18:00 | 2020-03-20 09:00 | 2020-04-30 18:00 |  |  | 2020-03-21 11:21 | 2020-04-30 11:21 |  |  | 100 | 100 | [15 empty] | 0.91158 | 0.004067 | 0.4 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2379 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017773
103 | Task(Task)-->P (Procurement) | Geared Coupling for Dribble Conveyor |  | 1.3.2.3 | Completed | No | No | 2020-03-20 09:00 | 2020-04-18 18:00 | 2020-04-13 09:00 | 2020-04-30 18:00 |  |  | 2020-04-14 11:11 | 2020-04-30 11:11 |  |  | 100 | 100 | [15 empty] | 0.22789 | 0.001017 | 0.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2380 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017774
104 | Task(Task)-->P (Procurement) | Building Structure |  | 1.3.2.3 | Completed | No | No | 2020-02-29 09:00 | 2020-03-29 23:59 | 2020-05-29 09:00 | 2020-05-31 23:59 |  |  | 2020-05-31 18:49 | 2020-05-31 18:49 |  |  | 100 | 100 | [15 empty] | 31.2443 | 0.13941 | 13.71 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2381 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017775
105 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR CONVEYING SYSTEM |  | 1.3.2.3 | Completed | No | No | 2020-01-01 09:00 | 2020-01-16 18:00 | 2020-04-11 09:00 | 2020-07-20 18:00 |  |  | 2020-04-12 15:47 | 2020-06-20 15:47 |  |  | 100 | 100 | [15 empty] | 0.75205 | 0.003356 | 0.33 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2382 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017776
106 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.3.2.3 | Completed | No | No | 2020-03-26 09:00 | 2020-04-10 18:00 | 2020-06-02 09:00 | 2020-07-31 18:00 |  |  | 2020-06-03 15:51 | 2020-06-29 15:51 |  |  | 100 | 100 | [15 empty] | 1.2078 | 0.005389 | 0.53 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2383 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017777
107 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.3.2.3 | Completed | No | No | 2020-05-12 09:00 | 2020-06-25 18:00 | 2020-06-03 09:00 | 2020-06-24 18:00 |  |  | 2020-06-15 10:57 | 2020-06-15 10:57 |  |  | 100 | 100 | [15 empty] | 0.54695 | 0.00244 | 0.24 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2384 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017778
108 | Task(Task)-->P (Procurement) | LPBS |  | 1.3.2.3 | Completed | No | No | 2020-04-05 | 2020-04-20 18:00 | 2020-06-12 09:00 | 2020-08-19 18:00 |  |  | 2020-06-12 16:55 | 2020-08-19 16:55 |  |  | 100 | 100 | [15 empty] | 0.091158 | 0.000407 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2385 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017779
109 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.3.2.3 | Completed | No | No | 2020-01-23 09:00 | 2020-02-05 18:00 | 2020-03-10 09:00 | 2020-08-17 18:00 |  |  | 2020-03-10 16:54 | 2020-08-17 16:54 |  |  | 100 | 100 | [15 empty] | 0.13674 | 0.00061 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2388 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017780
110 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.3.2.3 | Completed | No | No | 2020-01-15 09:00 | 2020-02-01 18:00 | 2020-03-07 09:00 | 2020-08-01 18:00 |  |  | 2020-03-07 16:55 | 2020-08-01 16:55 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2389 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017781
111 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.3.2.3 | Completed | No | No | 2020-01-19 | 2020-01-31 18:00 | 2020-01-16 09:00 | 2020-02-01 18:00 |  |  | 2020-02-01 10:57 | 2020-02-01 10:57 |  |  | 100 | 100 | [15 empty] | 0.022789 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2390 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017782
112 | Task(Task)-->P (Procurement) | CONTROL JUNCTION BOX |  | 1.3.2.3 | Completed | No | No | 2020-03-14 09:00 | 2020-03-21 18:00 | 2020-06-02 09:00 | 2020-08-19 18:00 |  |  | 2020-06-02 16:56 | 2020-08-19 16:56 |  |  | 100 | 100 | [15 empty] | 0.11395 | 0.000508 | 0.05 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2391 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017783
113 | Task(Task)-->P (Procurement) | ITP APPROVAL | 1.3.2.4 | 1.3.2 | Work In Progress | No | No | 2019-11-11 09:00 | 2020-08-27 18:00 | 2020-01-29 09:00 | 2020-10-30 18:00 |  |  | 2020-01-29 01:52 |  |  |  | 100 | 24.0094 | [15 empty] | 4.9998 | 0.2231 | 21.94 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2392 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017784
114 | Task(Task)-->P (Procurement) | Apron Feeder |  | 1.3.2.4 | Completed | No | No | 2019-11-11 09:00 | 2019-12-20 18:00 | 2020-01-29 09:00 | 2020-06-11 18:00 |  |  | 2020-01-29 01:52 | 2020-06-11 01:52 |  |  | 100 | 100 | [15 empty] | 19.0888 | 0.042587 | 4.19 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2393 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017785
115 | Task(Task)-->P (Procurement) | Gear Box for Apron Feeder |  | 1.3.2.4 | Completed | No | No | 2020-03-28 09:00 | 2020-05-06 18:00 | 2020-04-30 09:00 | 2020-06-22 18:00 |  |  | 2020-04-30 16:57 | 2020-06-22 16:57 |  |  | 100 | 100 | [15 empty] | 0.91116 | 0.002033 | 0.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2394 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017786
116 | Task(Task)-->P (Procurement) | Geared Coupling for Apron Feeder |  | 1.3.2.4 | Completed | No | No | 2020-04-19 | 2020-05-28 18:00 | 2020-04-30 09:00 | 2020-08-28 18:00 |  |  | 2020-04-30 01:54 | 2020-06-18 17:30 |  |  | 100 | 100 | [15 empty] | 0.18223 | 0.000407 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2395 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017787
117 | Task(Task)-->P (Procurement) | Primary Sizer |  | 1.3.2.4 | Unscheduled | No | No | 2019-11-21 09:00 | 2019-12-30 18:00 | 2020-02-25 09:00 | 2020-10-15 18:00 | [6 empty] | 100 | 0 | [15 empty] | 37.8132 | 0.084361 | 8.3 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2396 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017788
118 | Task(Task)-->P (Procurement) | Pulley for Dribble Conveyor |  | 1.3.2.4 | Unscheduled | No | No | 2020-02-04 09:00 | 2020-03-14 18:00 | 2020-03-21 09:00 | 2020-05-11 18:00 | [6 empty] | 100 | 0 | [15 empty] | 1.0023 | 0.002236 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2397 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017789
119 | Task(Task)-->P (Procurement) | Idler for Dribble Conveyor |  | 1.3.2.4 | Completed | No | No | 2020-03-03 09:00 | 2020-04-11 18:00 | 2020-04-30 09:00 | 2020-05-19 18:00 |  |  | 2020-04-13 16:20 | 2020-05-19 16:20 |  |  | 100 | 100 | [15 empty] | 0.22779 | 0.000508 | 0.05 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2398 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017790
120 | Task(Task)-->P (Procurement) | Plummer Block for Dribble Conveyor |  | 1.3.2.4 | Unscheduled | No | No | 2020-07-02 09:00 | 2020-08-10 18:00 | 2020-03-24 09:00 | 2020-08-13 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.091116 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2399 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017791
121 | Task(Task)-->P (Procurement) | Bearing for Dribble Conveyor |  | 1.3.2.4 | Unscheduled | No | No | 2020-07-17 09:00 | 2020-08-25 18:00 | 2020-03-24 09:00 | 2020-03-29 23:59 | [6 empty] | 100 | 0 | [15 empty] | 0.13667 | 0.000305 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2400 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017792
122 | Task(Task)-->P (Procurement) | Belting for Dribble Conveyor |  | 1.3.2.4 | Completed | No | No | 2020-02-21 09:00 | 2020-03-31 18:00 | 2020-09-04 09:00 | 2020-09-30 18:00 |  |  | 2020-09-04 16:30 | 2020-09-30 16:30 |  |  | 100 | 100 | [15 empty] | 0.27335 | 0.00061 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2401 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017793
123 | Task(Task)-->P (Procurement) | Scrapper for Dribble Conveyor |  | 1.3.2.4 | Completed | No | No | 2020-04-16 09:00 | 2020-05-25 18:00 | 2020-05-30 09:00 | 2020-06-25 18:00 |  |  | 2020-05-13 16:26 | 2020-06-25 16:26 |  |  | 100 | 100 | [15 empty] | 0.18223 | 0.000407 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2402 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017794
124 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.3.2.4 | Unscheduled | No | No | 2020-04-20 09:00 | 2020-05-29 18:00 | 2020-07-06 09:00 | 2020-07-16 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.8656 | 0.001931 | 0.19 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2403 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017795
125 | Task(Task)-->P (Procurement) | Chute & Skirt |  | 1.3.2.4 | Unscheduled | No | No | 2020-04-20 09:00 | 2020-05-29 18:00 | 2020-07-06 09:00 | 2020-07-16 18:00 | [6 empty] | 100 | 0 | [15 empty] | 3.9636 | 0.008843 | 0.87 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2404 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017796
126 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.3.2.4 | Unscheduled | No | No | 2020-07-19 | 2020-08-27 18:00 | 2020-06-25 09:00 | 2020-06-25 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.045558 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2405 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017797
127 | Task(Task)-->P (Procurement) | Gear Box for Dribble Conveyor |  | 1.3.2.4 | Completed | No | No | 2020-03-28 09:00 | 2020-05-06 18:00 | 2020-04-30 09:00 | 2020-06-22 18:00 |  |  | 2020-04-30 16:57 | 2020-06-22 16:57 |  |  | 100 | 100 | [15 empty] | 0.91116 | 0.002033 | 0.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2406 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017798
128 | Task(Task)-->P (Procurement) | Geared Coupling for Dribble Conveyor |  | 1.3.2.4 | Completed | No | No | 2020-04-19 | 2020-05-28 18:00 | 2020-04-30 09:00 | 2020-06-18 18:00 |  |  | 2020-04-30 01:54 | 2020-06-18 17:31 |  |  | 100 | 100 | [15 empty] | 0.22779 | 0.000508 | 0.05 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2407 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017799
129 | Task(Task)-->P (Procurement) | Building Structure |  | 1.3.2.4 | Unscheduled | No | No | 2020-03-30 09:00 | 2020-04-05 23:59 | 2020-05-31 | 2020-08-04 18:00 |  |  | 2020-06-25 19:04 |  |  |  | 100 | 0 | [15 empty] | 31.2073 | 0.069623 | 6.85 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2408 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017800
130 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR CONVEYING SYSTEM |  | 1.3.2.4 | Unscheduled | No | No | 2020-01-17 09:00 | 2020-02-25 18:00 | 2020-09-08 09:00 | 2020-10-10 18:00 |  |  | 2020-09-08 16:58 |  |  |  | 100 | 0 | [15 empty] | 0.72893 | 0.001626 | 0.16 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2409 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017801
131 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.3.2.4 | Completed | No | No | 2020-04-11 09:00 | 2020-05-20 18:00 | 2020-07-28 09:00 | 2020-09-08 18:00 |  |  | 2020-07-08 17:23 | 2020-09-08 17:23 |  |  | 100 | 100 | [15 empty] | 1.2301 | 0.002744 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2410 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017802
132 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.3.2.4 | Completed | No | No | 2020-06-26 09:00 | 2020-08-04 18:00 | 2020-06-23 09:00 | 2020-09-08 18:00 |  |  | 2020-06-23 17:21 | 2020-09-08 17:05 |  |  | 100 | 100 | [15 empty] | 0.5467 | 0.00122 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2411 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017803
133 | Task(Task)-->P (Procurement) | LPBS |  | 1.3.2.4 | Completed | No | No | 2020-04-21 09:00 | 2020-05-30 18:00 | 2020-07-29 09:00 | 2020-08-21 18:00 |  |  | 2020-07-29 14:54 | 2020-08-22 12:53 |  |  | 100 | 100 | [15 empty] | 0.091116 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2412 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017804
134 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.3.2.4 | Unscheduled | No | No | 2020-02-06 09:00 | 2020-03-16 18:00 | 2020-09-24 09:00 | 2020-10-30 18:00 |  |  | 2020-09-24 09:58 |  |  |  | 100 | 0 | [15 empty] | 0.13667 | 0.000305 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2415 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017805
135 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.3.2.4 | Unscheduled | No | No | 2020-02-02 | 2020-03-12 18:00 | 2020-08-02 | 2020-09-10 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2416 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017806
136 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.3.2.4 | Completed | No | No | 2020-02-01 09:00 | 2020-03-11 18:00 | 2020-07-02 09:00 | 2020-08-04 18:00 |  |  | 2020-07-02 16:57 | 2020-08-04 16:57 |  |  | 100 | 100 | [15 empty] | 0.045558 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2417 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017807
137 | Task(Task)-->P (Procurement) | CONTROL JUNCTION BOX |  | 1.3.2.4 | Completed | No | No | 2020-03-22 | 2020-04-30 18:00 | 2020-07-29 09:00 | 2020-09-21 18:00 |  |  | 2020-07-29 14:51 | 2020-09-22 16:57 |  |  | 100 | 100 | [15 empty] | 0.091116 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2418 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017808
138 | Task(Task)-->P (Procurement) | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE | 1.3.2.5 | 1.3.2 | Work In Progress | No | No | 2019-11-11 09:00 | 2020-09-16 18:00 | 2020-01-29 09:00 | 2020-10-21 18:00 |  |  | 2020-01-30 12:41 |  |  |  | 100 | 67.2489 | [15 empty] | 15.0016 | 0.6694 | 65.83 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2419 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017809
139 | Task(Task)-->P (Procurement) | Apron Feeder |  | 1.3.2.5 | Completed | No | No | 2019-11-11 09:00 | 2020-02-08 18:00 | 2020-01-29 09:00 | 2020-03-16 18:00 |  |  | 2020-01-30 12:41 | 2020-03-16 10:57 |  |  | 100 | 100 | [15 empty] | 19.0946 | 0.12782 | 12.57 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2420 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017810
140 | Task(Task)-->P (Procurement) | Gear Box for Apron Feeder |  | 1.3.2.5 | Completed | No | No | 2020-03-28 09:00 | 2020-05-26 18:00 | 2020-04-30 09:00 | 2020-07-01 18:00 |  |  | 2020-04-30 19:12 | 2020-07-01 19:12 |  |  | 100 | 100 | [15 empty] | 0.91144 | 0.006101 | 0.6 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2421 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017811
141 | Task(Task)-->P (Procurement) | Geared Coupling for Apron Feeder |  | 1.3.2.5 | Completed | No | No | 2020-04-19 | 2020-06-17 18:00 | 2020-04-30 09:00 | 2020-07-23 18:00 |  |  | 2020-04-30 01:56 | 2020-07-23 01:57 |  |  | 100 | 100 | [15 empty] | 0.1671 | 0.001119 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2422 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017812
142 | Task(Task)-->P (Procurement) | Primary Sizer |  | 1.3.2.5 | Completed | No | No | 2019-11-21 09:00 | 2020-02-18 18:00 | 2020-02-25 09:00 | 2020-06-22 18:00 |  |  | 2020-02-26 14:48 | 2020-06-22 14:48 |  |  | 100 | 100 | [15 empty] | 37.8399 | 0.2533 | 24.91 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2423 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017813
143 | Task(Task)-->P (Procurement) | Pulley for Dribble Conveyor |  | 1.3.2.5 | Completed | No | No | 2020-02-04 09:00 | 2020-03-29 23:59 | 2020-03-21 09:00 | 2020-03-25 18:00 |  |  | 2020-03-22 18:03 | 2020-03-25 18:03 |  |  | 100 | 100 | [15 empty] | 1.0178 | 0.006813 | 0.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2424 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017814
144 | Task(Task)-->P (Procurement) | Idler for Dribble Conveyor |  | 1.3.2.5 | Completed | No | No | 2020-03-03 09:00 | 2020-05-01 18:00 | 2020-04-30 09:00 | 2020-06-25 18:00 |  |  | 2020-05-04 14:59 | 2020-06-25 15:00 |  |  | 100 | 100 | [15 empty] | 0.21267 | 0.001424 | 0.14 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2425 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017815
145 | Task(Task)-->P (Procurement) | Plummer Block for Dribble Conveyor |  | 1.3.2.5 | Completed | No | No | 2020-07-02 09:00 | 2020-08-30 23:59 | 2020-03-24 09:00 | 2020-06-29 18:00 |  |  | 2020-05-14 10:06 | 2020-06-29 10:06 |  |  | 100 | 100 | [15 empty] | 0.075953 | 0.000508 | 0.05 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2426 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017816
146 | Task(Task)-->P (Procurement) | Bearing for Dribble Conveyor |  | 1.3.2.5 | Completed | No | No | 2020-07-17 09:00 | 2020-07-17 18:00 | 2020-03-24 09:00 | 2020-03-24 18:00 |  |  | 2020-03-24 10:05 | 2020-03-24 10:05 |  |  | 100 | 100 | [15 empty] | 0.12153 | 0.000813 | 0.08 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2427 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017817
147 | Task(Task)-->P (Procurement) | Belting for Dribble Conveyor |  | 1.3.2.5 | Unscheduled | No | No | 2020-02-21 09:00 | 2020-04-20 18:00 | 2020-09-04 09:00 | 2020-10-15 18:00 |  |  | 2020-09-04 16:36 |  |  |  | 100 | 50 | [15 empty] | 0.27343 | 0.00183 | 0.18 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2428 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017818
148 | Task(Task)-->P (Procurement) | Scrapper for Dribble Conveyor |  | 1.3.2.5 | Completed | No | No | 2020-04-16 09:00 | 2020-06-14 23:59 | 2020-05-30 09:00 | 2020-07-30 18:00 |  |  | 2020-05-30 16:33 | 2020-07-30 16:33 |  |  | 100 | 100 | [15 empty] | 0.1671 | 0.001119 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2429 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017819
149 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.3.2.5 | Completed | No | No | 2020-04-20 09:00 | 2020-09-16 18:00 | 2020-07-06 09:00 | 2020-07-06 18:00 |  |  | 2020-07-06 12:45 | 2020-07-06 12:45 |  |  | 100 | 100 | [15 empty] | 0.86587 | 0.005796 | 0.57 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2430 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017820
150 | Task(Task)-->P (Procurement) | Chute & Skirt |  | 1.3.2.5 | Completed | No | No | 2020-04-20 09:00 | 2020-09-16 18:00 | 2020-07-06 09:00 | 2020-07-06 18:00 |  |  | 2020-07-06 12:51 | 2020-07-06 12:51 |  |  | 100 | 100 | [15 empty] | 3.9496 | 0.026438 | 2.6 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2431 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017821
151 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.3.2.5 | Unscheduled | No | No | 2020-07-19 | 2020-08-27 18:00 | 2020-08-04 09:00 | 2020-08-04 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.045572 | 0.000305 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2432 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017822
152 | Task(Task)-->P (Procurement) | Gear Box for Dribble Conveyor |  | 1.3.2.5 | Completed | No | No | 2020-03-28 09:00 | 2020-05-26 18:00 | 2020-04-30 09:00 | 2020-07-01 18:00 |  |  | 2020-04-30 19:12 | 2020-07-01 19:12 |  |  | 100 | 100 | [15 empty] | 0.91144 | 0.006101 | 0.6 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2433 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017823
153 | Task(Task)-->P (Procurement) | Geared Coupling for Dribble Conveyor |  | 1.3.2.5 | Completed | No | No | 2020-04-19 | 2020-06-17 18:00 | 2020-04-30 09:00 | 2020-07-30 18:00 |  |  | 2020-04-30 10:09 | 2020-07-07 10:10 |  |  | 100 | 100 | [15 empty] | 0.22786 | 0.001525 | 0.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2434 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017824
154 | Task(Task)-->P (Procurement) | Building Structure |  | 1.3.2.5 | Unscheduled | No | No | 2020-03-28 09:00 | 2020-04-03 18:00 | 2020-05-31 | 2020-07-11 18:00 | [6 empty] | 100 | 0 | [15 empty] | 31.232 | 0.20907 | 20.56 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2435 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017825
155 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR CONVEYING SYSTEM |  | 1.3.2.5 | Completed | No | No | 2020-01-17 09:00 | 2020-03-01 23:59 | 2020-07-07 09:00 | 2020-09-29 18:00 |  |  | 2020-07-07 10:15 | 2020-09-21 12:52 |  |  | 100 | 100 | [15 empty] | 0.74434 | 0.004983 | 0.49 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2436 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017826
156 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.3.2.5 | Unscheduled | No | No | 2020-04-11 09:00 | 2020-05-25 18:00 | 2020-07-10 09:00 | 2020-10-16 18:00 |  |  | 2020-07-14 10:44 |  |  |  | 100 | 0 | [15 empty] | 1.2153 | 0.008135 | 0.8 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2437 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017827
157 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.3.2.5 | Completed | No | No | 2020-06-26 09:00 | 2020-08-09 23:59 | 2020-05-30 09:00 | 2020-08-08 18:00 |  |  | 2020-06-18 | 2020-08-07 15:00 |  |  | 100 | 100 | [15 empty] | 0.54686 | 0.003661 | 0.36 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2438 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017828
158 | Task(Task)-->P (Procurement) | LPBS |  | 1.3.2.5 | Completed | No | No | 2020-04-21 09:00 | 2020-06-04 18:00 | 2020-07-25 09:00 | 2020-08-22 18:00 |  |  | 2020-07-24 18:32 | 2020-08-22 12:56 |  |  | 100 | 100 | [15 empty] | 0.091144 | 0.00061 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2439 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017829
159 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.3.2.5 | Completed | No | No | 2020-02-06 09:00 | 2020-03-21 18:00 | 2020-08-11 09:00 | 2020-09-19 18:00 |  |  | 2020-08-11 13:11 | 2020-09-19 12:57 |  |  | 100 | 100 | [15 empty] | 0.13672 | 0.000915 | 0.09 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2442 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017830
160 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.3.2.5 | Unscheduled | No | No | 2020-02-02 | 2020-03-17 18:00 | 2020-08-09 | 2020-10-20 18:00 |  |  | 2020-08-09 13:13 |  |  |  | 100 | 0 | [15 empty] | 0.015191 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2443 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017831
161 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.3.2.5 | Completed | No | No | 2020-02-01 09:00 | 2020-03-16 18:00 | 2020-02-01 09:00 | 2020-07-15 18:00 |  |  | 2020-02-11 21:24 | 2020-07-15 21:24 |  |  | 100 | 100 | [15 empty] | 0.030381 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2444 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017832
162 | Task(Task)-->P (Procurement) | CONTROL JUNCTION BOX |  | 1.3.2.5 | Unscheduled | No | No | 2020-03-22 | 2020-05-05 18:00 | 2020-07-25 09:00 | 2020-10-21 18:00 |  |  | 2020-07-25 12:12 |  |  |  | 100 | 0 | [15 empty] | 0.10633 | 0.000712 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2445 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017833
163 | Task(Task)-->P (Procurement) | MANUFACTURING & RECEIPT AT SITE (MRN) | 1.3.2.6 | 1.3.2 | Unscheduled | No | No | 2020-02-09 | 2021-02-28 23:59 | 2020-03-16 09:00 | 2021-05-13 18:00 |  |  | 2020-03-16 02:00 |  |  |  | 75.0012 | 21.7872 | [15 empty] | 60.0041 | 2.6775 | 263.31 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2446 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017834
164 | Task(Task)-->P (Procurement) | Apron Feeder |  | 1.3.2.6 | Unscheduled | No | No | 2020-02-09 | 2021-02-03 18:00 | 2020-03-16 09:00 | 2020-12-31 18:00 |  |  | 2020-03-16 02:00 |  |  |  | 67.036 | 40 | [15 empty] | 19.0954 | 0.51128 | 50.28 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2447 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017835
165 | Task(Task)-->P (Procurement) | Gear Box for Apron Feeder |  | 1.3.2.6 | Unscheduled | No | No | 2020-05-27 09:00 | 2020-12-22 18:00 | 2020-07-01 09:00 | 2020-12-31 18:00 |  |  | 2020-07-01 17:25 |  |  |  | 63.8095 | 30 | [15 empty] | 0.91527 | 0.024506 | 2.41 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2448 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017836
166 | Task(Task)-->P (Procurement) | Geared Coupling for Apron Feeder |  | 1.3.2.6 | Unscheduled | No | No | 2020-06-18 09:00 | 2020-12-15 18:00 | 2020-07-23 09:00 | 2020-10-05 18:00 |  |  | 2020-07-30 17:44 |  |  |  | 61.8785 | 90 | [15 empty] | 0.1671 | 0.004474 | 0.44 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2449 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017837
167 | Task(Task)-->P (Procurement) | Primary Sizer |  | 1.3.2.6 | Unscheduled | No | No | 2020-02-19 09:00 | 2021-02-28 23:59 | 2020-06-22 09:00 | 2021-02-28 23:59 |  |  | 2020-06-22 01:48 |  |  |  | 61.7021 | 35 | [15 empty] | 37.8413 | 1.0132 | 99.64 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2450 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017838
168 | Task(Task)-->P (Procurement) | Pulley for Dribble Conveyor |  | 1.3.2.6 | Unscheduled | No | No | 2020-03-30 09:00 | 2020-11-20 18:00 | 2020-03-25 09:00 | 2020-11-30 18:00 |  |  | 2020-03-25 18:05 |  |  |  | 81.3559 | 0 | [15 empty] | 1.014 | 0.02715 | 2.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2451 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017839
169 | Task(Task)-->P (Procurement) | Idler for Dribble Conveyor |  | 1.3.2.6 | Unscheduled | No | No | 2020-05-02 09:00 | 2020-11-13 18:00 | 2020-06-25 09:00 | 2020-12-31 18:00 | [6 empty] | 81.1225 | 0 | [15 empty] | 0.21268 | 0.005694 | 0.56 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2452 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017840
170 | Task(Task)-->P (Procurement) | Plummer Block for Dribble Conveyor |  | 1.3.2.6 | Unscheduled | No | No | 2020-08-31 09:00 | 2020-12-23 18:00 | 2020-06-29 09:00 | 2020-12-31 18:00 | [6 empty] | 33.0435 | 0 | [15 empty] | 0.075956 | 0.002034 | 0.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2453 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017841
171 | Task(Task)-->P (Procurement) | Bearing for Dribble Conveyor |  | 1.3.2.6 | Unscheduled | No | No | 2020-08-26 09:00 | 2020-12-23 18:00 | 2020-03-24 09:00 | 2020-09-09 18:00 | [6 empty] | 35.8333 | 0 | [15 empty] | 0.12533 | 0.003356 | 0.33 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2454 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017842
172 | Task(Task)-->P (Procurement) | Belting for Dribble Conveyor |  | 1.3.2.6 | Unscheduled | No | No | 2020-04-21 09:00 | 2020-11-16 18:00 | 2020-10-16 09:00 | 2021-05-13 18:00 | [6 empty] | 80.9524 | 0 | [15 empty] | 0.28104 | 0.007525 | 0.74 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2455 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017843
173 | Task(Task)-->P (Procurement) | Scrapper for Dribble Conveyor |  | 1.3.2.6 | Unscheduled | No | No | 2020-06-15 09:00 | 2020-12-11 18:00 | 2020-07-30 09:00 | 2020-12-31 18:00 | [6 empty] | 63.8889 | 0 | [15 empty] | 0.1671 | 0.004474 | 0.44 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2456 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017844
174 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.3.2.6 | Unscheduled | No | No | 2020-06-19 09:00 | 2021-02-13 18:00 | 2020-07-06 09:00 | 2021-01-31 23:59 | [6 empty] | 46.25 | 0 | [15 empty] | 0.8621 | 0.023083 | 2.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2457 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017845
175 | Task(Task)-->P (Procurement) | Chute & Skirt |  | 1.3.2.6 | Unscheduled | No | No | 2020-06-19 09:00 | 2021-02-13 18:00 | 2020-07-06 09:00 | 2021-01-31 23:59 | [6 empty] | 46.25 | 0 | [15 empty] | 3.9535 | 0.10586 | 10.41 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2458 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017846
176 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.3.2.6 | Unscheduled | No | No | 2020-08-28 09:00 | 2020-12-25 18:00 | 2020-08-04 09:00 | 2020-12-25 18:00 | [6 empty] | 34.1667 | 0 | [15 empty] | 0.049371 | 0.001322 | 0.13 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2459 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017847
177 | Task(Task)-->P (Procurement) | Gear Box for Dribble Conveyor |  | 1.3.2.6 | Unscheduled | No | No | 2020-05-27 09:00 | 2020-12-22 18:00 | 2020-07-01 09:00 | 2020-12-31 18:00 |  |  | 2020-07-01 17:25 |  |  |  | 63.8095 | 30 | [15 empty] | 0.91527 | 0.024506 | 2.41 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2460 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017848
178 | Task(Task)-->P (Procurement) | Geared Coupling for Dribble Conveyor |  | 1.3.2.6 | Unscheduled | No | No | 2020-06-18 09:00 | 2020-12-15 18:00 | 2020-07-30 09:00 | 2020-10-05 18:00 |  |  | 2020-07-30 17:44 |  |  |  | 61.8785 | 90 | [15 empty] | 0.22787 | 0.006101 | 0.6 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2461 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017849
179 | Task(Task)-->P (Procurement) | Building Structure |  | 1.3.2.6 | Unscheduled | No | No | 2020-04-06 09:00 | 2020-10-05 18:00 | 2020-07-11 09:00 | 2021-03-31 18:00 | [6 empty] | 100 | 0 | [15 empty] | 31.2293 | 0.83616 | 82.23 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2462 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017850
180 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR CONVEYING SYSTEM |  | 1.3.2.6 | Unscheduled | No | No | 2020-03-02 09:00 | 2020-09-26 18:00 | 2020-10-11 | 2021-05-07 18:00 |  |  | 2020-09-22 12:54 |  |  |  | 100 | 0 | [15 empty] | 0.74437 | 0.01993 | 1.96 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2463 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017851
181 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.3.2.6 | Unscheduled | No | No | 2020-05-26 09:00 | 2020-10-21 18:00 | 2020-10-17 09:00 | 2021-03-14 23:59 | [6 empty] | 90.604 | 0 | [15 empty] | 1.2115 | 0.032438 | 3.19 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2464 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017852
182 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.3.2.6 | Unscheduled | No | No | 2020-08-10 09:00 | 2020-11-07 18:00 | 2020-09-09 09:00 | 2020-12-07 18:00 |  |  | 2020-08-07 15:47 |  |  |  | 65.5556 | 0 | [15 empty] | 0.55068 | 0.014744 | 1.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2465 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017853
183 | Task(Task)-->P (Procurement) | LPBS |  | 1.3.2.6 | Unscheduled | No | No | 2020-06-05 09:00 | 2020-09-16 18:00 | 2020-08-23 | 2020-12-04 18:00 |  |  | 2020-08-22 12:56 |  |  |  | 100 | 0 | [15 empty] | 0.08735 | 0.002339 | 0.23 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2466 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017854
184 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.3.2.6 | Unscheduled | No | No | 2020-03-22 | 2020-08-05 18:00 | 2020-10-31 09:00 | 2021-03-16 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.13672 | 0.003661 | 0.36 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2469 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017855
185 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.3.2.6 | Unscheduled | No | No | 2020-03-18 09:00 | 2020-07-27 18:00 | 2020-10-21 09:00 | 2021-03-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.011393 | 0.000305 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2470 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017856
186 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.3.2.6 | Unscheduled | No | No | 2020-03-17 09:00 | 2020-07-31 18:00 | 2020-07-02 09:00 | 2020-11-15 23:59 |  |  | 2020-07-15 21:33 |  |  |  | 100 | 0 | [15 empty] | 0.022787 | 0.00061 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2471 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017857
187 | Task(Task)-->P (Procurement) | CONTROL JUNCTION BOX |  | 1.3.2.6 | Unscheduled | No | No | 2020-05-06 09:00 | 2020-09-16 18:00 | 2020-10-22 09:00 | 2021-03-04 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.10254 | 0.002746 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2472 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017858
188 | Task(Task)-->C (Construction) | CONSTRUCTION | 1.3.3 | 1.3 | Unscheduled | No | No | 2019-10-11 | 2021-09-13 18:00 | 2020-04-26 | 2022-04-09 18:00 |  |  | 2020-04-26 14:54 |  |  |  | 29.2859 | 0.03749 | [15 empty] | 49.7948 | 4.7128 | 463.48 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2473 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017859
189 | Task(Task)-->C (Construction) | CIVIL WORKS | 1.3.3.1 | 1.3.3 | Unscheduled | No | No | 2019-10-11 | 2021-06-04 18:00 | 2020-04-26 | 2021-12-29 18:00 |  |  | 2020-04-26 14:54 |  |  |  | 30.3732 | 0.04899 | [15 empty] | 76.5276 | 3.6066 | 354.69 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2474 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017860
190 | Task(Task)-->C (Construction) | AVAILABILITY OF FRONT BY NTPC |  | 1.3.3.1 | Unscheduled | No | No | 2020-04-14 09:00 | 2020-04-14 18:00 | 2020-07-11 09:00 | 2020-10-31 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2475 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017861
191 | Task(Task)-->C (Construction) | APPROACH TO DUMP HOPPER |  | 1.3.3.1 | Unscheduled | No | No | 2020-04-15 09:00 | 2020-07-13 18:00 | 2020-04-26 | 2020-11-15 23:59 |  |  | 2020-04-26 14:54 |  |  |  | 100 | 34 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5608 | 0 | 4 | Low | Niharendu Kamle | [6 empty] | 0 | 0 | [244 empty] | 1017862
192 | Task(Task)-->C (Construction) | EXCAVATION |  | 1.3.3.1 | Unscheduled | No | No | 2020-04-21 09:00 | 2020-05-06 18:00 | 2020-07-13 09:00 | 2020-11-30 18:00 |  |  | 2020-07-13 14:55 |  |  |  | 100 | 7.4576 | [15 empty] | 0.65689 | 0.023692 | 2.33 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 8716 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2476 | 0 | 4 | Low | Niharendu Kamle | [6 empty] | 0 | 0 | [244 empty] | 1017863
193 | Task(Task)-->C (Construction) | PCC |  | 1.3.3.1 | Unscheduled | No | No | 2019-10-11 | 2020-05-13 18:00 | 2020-11-22 | 2020-12-07 18:00 | [6 empty] | 100 | 0 | [15 empty] | 2.8729 | 0.10361 | 10.19 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 1127 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | Weekly | Cumulative | 0 | No | No | 2477 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | PCC | [21 empty] | 1017864
194 | Task(Task)-->C (Construction) | RAFT |  | 1.3.3.1 | Unscheduled | No | No | 2020-05-06 09:00 | 2020-06-06 18:00 | 2020-11-30 09:00 | 2020-12-31 18:00 | [6 empty] | 100 | 0 | [15 empty] | 2.0581 | 0.074227 | 7.3 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 275 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2478 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017865
195 | Task(Task)-->C (Construction) | PEDESTALS FOR DHS STR. |  | 1.3.3.1 | Unscheduled | No | No | 2020-05-26 09:00 | 2020-07-03 18:00 | 2020-12-20 | 2021-01-27 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.89089 | 0.032131 | 3.16 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 119 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2479 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017866
196 | Task(Task)-->C (Construction) | PRIMARY SIZER FLOOR (WITH CONNECTED RETAINING WALL) |  | 1.3.3.1 | Unscheduled | No | No | 2021-03-29 09:00 | 2021-04-28 18:00 | 2021-10-23 09:00 | 2021-11-22 18:00 | [6 empty] | 0 | 0 | [15 empty] | 1.607 | 0.057958 | 5.7 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 215 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2480 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017867
197 | Task(Task)-->C (Construction) | APPRON FEEDER FLOOR (WITH CONNECTED RETAINING WALL) |  | 1.3.3.1 | Unscheduled | No | No | 2021-04-14 09:00 | 2021-05-14 18:00 | 2021-11-08 09:00 | 2021-12-08 18:00 | [6 empty] | 0 | 0 | [15 empty] | 1.607 | 0.057958 | 5.7 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 215 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2482 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017868
198 | Task(Task)-->C (Construction) | SC 1A, SC 1B, SC 2A & SC 2B TAIL PULLEY FLOOR (GRADE SLAB) |  | 1.3.3.1 | Unscheduled | No | No | 2021-03-29 09:00 | 2021-06-04 18:00 | 2021-10-23 09:00 | 2021-12-29 18:00 | [6 empty] | 0 | 0 | [15 empty] | 11.6972 | 0.42187 | 41.49 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 2216 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2483 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017869
199 | Task(Task)-->C (Construction) | RCC FOR BALANCE RETAINING WALL |  | 1.3.3.1 | Unscheduled | No | No | 2020-06-14 | 2021-06-01 18:00 | 2021-01-08 09:00 | 2021-12-26 23:59 | [6 empty] | 32.8612 | 0 | [15 empty] | 47.5359 | 1.7144 | 168.61 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 6355 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2484 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | RCC | [21 empty] | 1017870
200 | Task(Task)-->C (Construction) | RAMP (FILLING WITH EARTH) |  | 1.3.3.1 | Unscheduled | No | No | 2020-07-14 09:00 | 2021-06-01 18:00 | 2021-02-07 | 2021-12-26 23:59 | [6 empty] | 26.6254 | 0 | [15 empty] | 31.0741 | 1.1207 | 110.22 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 249100 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2485 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017871
201 | Task(Task)-->C (Construction) | STRUCTURAL WORKS | 1.3.3.2 | 1.3.3 | Unscheduled | No | No | 2020-08-01 09:00 | 2021-03-28 23:59 | 2021-02-25 09:00 | 2021-10-22 18:00 | [6 empty] | 41.8025 | 0 | [15 empty] | 14.4537 | 0.68118 | 66.99 |  | Quantity | Metric Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 1035 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2486 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017872
202 | Task(Task)-->C (Construction) | STRL. ERECTION FOR RCC CASTING OF PRIMARY SIZER FLOOR & FOUNDATION |  | 1.3.3.2 | Unscheduled | No | No | 2020-08-01 09:00 | 2020-09-29 18:00 | 2021-02-25 09:00 | 2021-04-25 23:59 | [6 empty] | 100 | 0 | [15 empty] | 38.713 | 0.2637 | 25.93 | Plan & Actual | Quantity | Metric Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2487 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017873
203 | Task(Task)-->C (Construction) | STRL. ERECTION FOR APPRON FEEDERS RCC FLOOR |  | 1.3.3.2 | Unscheduled | No | No | 2020-09-30 09:00 | 2020-12-13 23:59 | 2021-04-26 09:00 | 2021-07-09 18:00 | [6 empty] | 10.6667 | 0 | [15 empty] | 28.9639 | 0.19729 | 19.4 | Plan & Actual | Quantity | Metric Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5585 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017874
204 | Task(Task)-->C (Construction) | STRL. ERECTION FOR DUMP HOPPER STEEL FLOOR |  | 1.3.3.2 | Unscheduled | No | No | 2020-12-14 09:00 | 2021-01-27 18:00 | 2021-07-10 09:00 | 2021-08-23 18:00 | [6 empty] | 0 | 0 | [15 empty] | 24.1266 | 0.16434 | 16.16 | Plan & Actual | Quantity | Metric Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2489 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017875
205 | Task(Task)-->C (Construction) | BALANCE STRUCTURAL ERECTION |  | 1.3.3.2 | Unscheduled | No | No | 2021-01-28 09:00 | 2021-03-28 23:59 | 2021-08-24 09:00 | 2021-10-22 18:00 | [6 empty] | 0 | 0 | [15 empty] | 8.1965 | 0.055833 | 5.49 | Plan & Actual | Quantity | Metric Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2490 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017876
206 | Task(Task)-->C (Construction) | MECHANICAL EQUIPMENT WORKS | 1.3.3.3 | 1.3.3 | Unscheduled | No | No | 2021-05-27 09:00 | 2021-09-13 18:00 | 2021-12-21 09:00 | 2022-04-09 18:00 | [6 empty] | 0 | 0 | [15 empty] | 7.2042 | 0.33952 | 33.39 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5447 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017877
207 | Task(Task)-->C (Construction) | ERECTION OF PRIMARY SIZER |  | 1.3.3.3 | Unscheduled | No | No | 2021-05-27 09:00 | 2021-07-05 18:00 | 2021-12-21 09:00 | 2022-01-29 18:00 | [6 empty] | 0 | 0 | [15 empty] | 21.018 | 0.07136 | 7.02 | Plan & Actual | Quantity | Metric Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 191 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2491 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017878
208 | Task(Task)-->C (Construction) | ERECTION OF APRRON FEEDERS |  | 1.3.3.3 | Unscheduled | No | No | 2021-06-05 09:00 | 2021-07-19 18:00 | 2021-12-30 09:00 | 2022-02-12 18:00 | [6 empty] | 0 | 0 | [15 empty] | 10.5689 | 0.035884 | 3.53 | Plan & Actual | Quantity | Metric Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2492 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017879
209 | Task(Task)-->C (Construction) | ERECTION OF STEEL DUMP HOPPER |  | 1.3.3.3 | Unscheduled | No | No | 2021-07-20 09:00 | 2021-09-07 18:00 | 2022-02-13 | 2022-04-03 23:59 | [6 empty] | 0 | 0 | [15 empty] | 52.5749 | 0.1785 | 17.56 | Plan & Actual | Quantity | Metric Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 478 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2493 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017880
210 | Task(Task)-->C (Construction) | ERECTION OF DRIBBLE CONVEYOR |  | 1.3.3.3 | Unscheduled | No | No | 2021-06-20 | 2021-08-03 18:00 | 2022-01-14 09:00 | 2022-02-27 23:59 | [6 empty] | 0 | 0 | [15 empty] | 10.5689 | 0.035884 | 3.53 | Plan & Actual | Quantity | Metric Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2494 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017881
211 | Task(Task)-->C (Construction) | ERECTION OF CHUTES/ HOODS & SUPPORTS |  | 1.3.3.3 | Unscheduled | No | No | 2021-07-06 09:00 | 2021-09-13 18:00 | 2022-01-30 | 2022-04-09 18:00 | [6 empty] | 0 | 0 | [15 empty] | 5.2695 | 0.017891 | 1.76 | Plan & Actual | Quantity | Metric Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2495 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017882
212 | Task(Task)-->C (Construction) | BELTING WORKS |  | 1.3.3 | Unscheduled | No | No | 2021-07-29 09:00 | 2021-08-28 18:00 | 2022-02-22 09:00 | 2022-03-24 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0.034521 | 0.001627 | 0.16 | Plan & Actual | Quantity | Meter | 0 | 0 | 0 | 0 | 0 | 0 | 104 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2498 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017883
213 | Task(Task)-->C (Construction) | ELECTRICAL & INSTRUMENTATION WORKS | 1.3.3.5 | 1.3.3 | Unscheduled | No | No | 2021-01-19 09:00 | 2021-08-25 18:00 | 2021-08-15 | 2022-03-17 18:00 | [6 empty] | 0 | 0 | [15 empty] | 1.4477 | 0.06823 | 6.71 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2499 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017884
214 | Task(Task)-->C (Construction) | CABLE TRAY |  | 1.3.3.5 | Unscheduled | No | No | 2021-01-19 09:00 | 2021-02-17 18:00 | 2021-08-15 | 2021-09-13 18:00 | [6 empty] | 0 | 0 | [15 empty] | 7.0149 | 0.004786 | 0.47 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 1100 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2500 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017885
215 | Task(Task)-->C (Construction) | POWER CABLE |  | 1.3.3.5 | Unscheduled | No | No | 2021-08-04 09:00 | 2021-08-07 18:00 | 2022-02-28 09:00 | 2022-03-03 18:00 | [6 empty] | 0 | 0 | [15 empty] | 15.5224 | 0.010591 | 1.04 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 7366 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2501 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017886
216 | Task(Task)-->C (Construction) | C&I CABLE |  | 1.3.3.5 | Unscheduled | No | No | 2021-08-05 09:00 | 2021-08-07 18:00 | 2022-03-01 09:00 | 2022-03-03 18:00 | [6 empty] | 0 | 0 | [15 empty] | 22.8358 | 0.015581 | 1.53 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 10800 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5276 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017887
217 | Task(Task)-->C (Construction) | EARTHING |  | 1.3.3.5 | Unscheduled | No | No | 2021-08-03 09:00 | 2021-08-07 18:00 | 2022-02-27 | 2022-03-03 18:00 | [6 empty] | 0 | 0 | [15 empty] | 2.8358 | 0.001935 | 0.19 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 850 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5277 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017888
218 | Task(Task)-->C (Construction) | EARTH PIT |  | 1.3.3.5 | Unscheduled | No | No | 2021-05-30 | 2021-06-01 18:00 | 2021-12-24 09:00 | 2021-12-26 23:59 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5278 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017889
219 | Task(Task)-->C (Construction) | LIGHTING |  | 1.3.3.5 | Unscheduled | No | No | 2021-03-23 09:00 | 2021-04-07 18:00 | 2021-10-17 | 2021-11-01 18:00 | [6 empty] | 0 | 0 | [15 empty] | 27.9104 | 0.019043 | 1.87 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 192 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5279 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017890
220 | Task(Task)-->C (Construction) | FIELD INSTRUMENTS |  | 1.3.3.5 | Unscheduled | No | No | 2021-08-06 09:00 | 2021-08-08 23:59 | 2022-03-02 09:00 | 2022-03-04 18:00 | [6 empty] | 0 | 0 | [15 empty] | 13.5821 | 0.009267 | 0.91 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5280 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017891
221 | Task(Task)-->C (Construction) | MOTOR TERMINATION |  | 1.3.3.5 | Unscheduled | No | No | 2021-08-04 09:00 | 2021-08-10 18:00 | 2022-02-28 09:00 | 2022-03-06 23:59 | [6 empty] | 0 | 0 | [15 empty] | 10.2985 | 0.007027 | 0.69 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5281 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017892
222 | Task(Task)-->C (Construction) | NO LOAD RUN OF MOTOR |  | 1.3.3.5 | Unscheduled | No | No | 2021-08-22 | 2021-08-25 18:00 | 2022-03-14 09:00 | 2022-03-17 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5282 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017893
223 | Task(Task)-->C (Construction) | NO LOAD COMMISSIONING & SYSTEM READYNESS FOR LOAD & TRIAL OPERATION |  | 1.3.3 | Unscheduled | No | No | 2021-08-19 09:00 | 2021-09-01 18:00 | 2022-03-11 09:00 | 2022-03-24 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0.33227 | 0.015659 | 1.54 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2502 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017894
224 | Task(Task)-->E (Engineering) | KDTP-1 | 1.4 | 1 | Work In Progress | No | No | 2019-09-27 09:00 | 2021-08-28 18:00 | 2019-09-27 09:00 | 2022-03-20 23:59 |  |  | 2019-09-27 10:57 |  |  |  | 70.4217 | 33.0673 | [15 empty] | 4.0727 | 4.0727 | 400.52 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2504 | 0 | 1 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017895
225 | Task(Task)-->E (Engineering) | ENGINEERING | 1.4.1 | 1.4 | Work In Progress | No | No | 2019-10-27 23:59 | 2020-07-07 17:40 | 2020-03-02 09:00 | 2020-10-15 18:00 |  |  | 2020-02-17 17:40 |  |  |  | 100 | 82.6272 | [15 empty] | 1.9075 | 0.077687 | 7.64 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2505 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017896
226 | Task(Task)-->E (Engineering) | MECHANICAL | 1.4.1.1 | 1.4.1 | Work In Progress | No | No | 2019-10-27 23:59 | 2020-06-04 17:40 | 2020-03-02 09:00 | 2020-08-21 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 61.9442 | [15 empty] | 29.6199 | 0.023011 | 2.26 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No | 2506 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036074
227 | Task(Task)-->E (Engineering) | GA OF FLAP GATE |  | 1.4.1.1 | Unscheduled | No | No | 2020-04-04 18:00 | 2020-06-04 17:40 | 2020-05-20 18:00 | 2020-08-21 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1021 |  | 2020-02-13 10:27 | 7012-155-PVM-B-121 |  |  |  | A |  |  |  | 25 | 0.005753 | 0.54 | Plan & Actual | Date |  | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2510 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-04 18:00 | 2020-05-20 18:00 |  | 10 |  |  |  | 2020-04-23 17:40 | 2020-06-10 18:00 |  | 30 |  |  |  | 2020-04-30 17:40 | 2020-06-16 18:00 |  | 35 |  |  |  | 2020-05-06 23:59 | 2020-06-21 23:59 |  | 65 |  |  |  | 2020-05-13 17:40 | 2020-07-12 23:59 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-04 17:40 | 2020-07-12 23:59 |  | 100 | [122 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 51 |  |  |  | 101065
228 | Task(Task)-->E (Engineering) | THRUST & ACTUATOR SELECTION FOR FLAP GATE ACTUATOR |  | 1.4.1.1 | Unscheduled | No | No | 2020-04-04 18:00 | 2020-06-04 17:40 | 2020-05-20 18:00 | 2020-08-21 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-DC-1022 |  | 2020-02-13 10:27 | 7012-155-PVM-B-122 |  |  |  | A |  |  |  | 5.0926 | 0.001172 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2511 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-04 18:00 | 2020-05-20 18:00 |  | 10 |  |  |  | 2020-04-23 17:40 | 2020-06-10 18:00 |  | 30 |  |  |  | 2020-04-30 17:40 | 2020-06-16 18:00 |  | 35 |  |  |  | 2020-05-06 23:59 | 2020-06-21 23:59 |  | 65 |  |  |  | 2020-05-13 17:40 | 2020-07-12 23:59 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-04 17:40 | 2020-07-12 23:59 |  | 100 | [122 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 52 |  |  |  | 101066
229 | Task(Task)-->E (Engineering) | G.A & LOAD DATA OF TRANSFER POINT KDTP-1 |  | 1.4.1.1 | Unscheduled | No | No | 2019-10-29 18:00 | 2020-01-02 17:40 | 2020-03-07 18:00 | 2020-05-19 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-0008 |  | 2020-02-13 10:26 | 7012-155-PVM-B-008 |  |  |  | A |  |  |  | 39.8148 | 0.009162 | 0.86 | Plan & Actual | Date |  | 0 | 0 | 0 | 320 | 0 | 149.1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2507 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-10-29 18:00 | 2020-03-07 18:00 |  | 10 | 2020-03-07 23:31 |  |  | 2019-11-25 17:40 | 2020-04-04 18:00 |  | 30 | 2020-04-04 23:31 |  |  | 2019-11-30 17:40 | 2020-04-07 18:00 |  | 35 | 2020-04-07 23:31 |  |  | 2019-12-06 23:59 | 2020-04-14 18:00 |  | 65 | 2020-04-14 23:31 |  |  | 2019-12-12 17:40 | 2020-05-05 18:00 |  | 80 | 2020-05-08 23:31 | [5 empty] | 80 | 2020-09-17 15:51 | [5 empty] | 80 | 2020-09-17 15:51 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-01-02 17:40 | 2020-05-19 18:00 |  | 100 | [122 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 8 |  |  |  | 101022
230 | Task(Task)-->E (Engineering) | GA OF SECONDARY SIZERS SS-1, SS-2, SS-3 & SS-4 |  | 1.4.1.1 | Completed | No | No | 2019-10-27 23:59 | 2019-12-21 17:40 | 2020-03-30 09:00 | 2020-06-10 18:00 |  |  | 2020-02-21 14:04 | 2020-06-29 19:15 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1007 |  | 2020-02-13 10:27 | 7012-155-PVM-B-107 |  |  |  | A |  |  |  | 10.1852 | 0.002344 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 80 | 0 | 13.2 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2508 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-10-27 23:59 | 2020-03-18 18:00 |  | 10 | 2020-03-18 23:31 |  |  | 2019-11-13 17:40 | 2020-03-22 23:59 |  | 30 | 2020-03-22 23:31 |  |  | 2019-11-19 17:40 | 2020-03-28 18:00 |  | 35 | 2020-03-28 23:31 |  |  | 2019-11-25 23:59 | 2020-03-30 18:00 |  | 65 | 2020-03-30 23:31 |  |  | 2019-11-30 17:40 | 2020-04-20 18:00 |  | 80 | 2020-04-23 23:31 | [5 empty] | 80 | 2020-06-22 18:44 | [5 empty] | 80 | 2020-06-10 18:01 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2019-12-21 17:40 | 2020-05-04 18:00 |  | 100 | 2020-06-29 19:16 | [121 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 37 |  |  |  | 101051
231 | Task(Task)-->E (Engineering) | GA OF INLINE MAGNETIC SEPERATOR |  | 1.4.1.1 | Completed | No | No | 2020-01-30 18:00 | 2020-03-25 17:40 | 2020-03-02 09:00 | 2020-04-11 18:00 |  |  | 2020-02-21 14:04 | 2020-06-19 15:47 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1030 |  | 2020-02-13 10:27 | 7012-155-PVM-B-130 |  |  |  | A |  |  |  | 19.9074 | 0.004581 | 0.43 | Plan & Actual | Date |  | 0 | 0 | 0 | 160 | 0 | 8.1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2512 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-30 18:00 | 2020-02-06 18:00 |  | 10 | 2020-02-06 23:31 |  |  | 2020-02-13 17:40 | 2020-02-19 18:00 |  | 30 | 2020-02-19 23:31 |  |  | 2020-02-19 17:40 | 2020-02-24 18:00 |  | 35 | 2020-02-24 23:31 |  |  | 2020-02-26 23:59 | 2020-03-02 18:00 |  | 65 | 2020-03-02 23:31 |  |  | 2020-03-03 17:40 | 2020-03-20 18:00 |  | 80 | 2020-03-20 23:31 | [5 empty] | 80 | 2020-06-10 19:07 | [5 empty] | 80 | 2020-06-10 19:07 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-25 17:40 | 2020-04-25 18:00 |  | 100 | 2020-04-23 23:31 | [121 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 60 |  |  |  | 101074
232 | Task(Task)-->E (Engineering) | CIVIL | 1.4.1.2 | 1.4.1 | Work In Progress | No | No | 2020-01-19 23:59 | 2020-05-25 17:40 | 2020-06-26 18:00 | 2020-09-23 18:00 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 98.0715 | [15 empty] | 33.2896 | 0.025862 | 2.54 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No | 2515 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036075
233 | Task(Task)-->E (Engineering) | TRANSFER POINT KDTP-1 - DESIGN CALCULATION OF SUPER STRUCTURE |  | 1.4.1.2 | Completed | No | No | 2020-01-19 23:59 | 2020-03-19 17:40 | 2020-06-30 09:00 | 2020-07-15 18:00 |  |  | 2020-02-21 15:37 | 2020-07-15 15:00 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-DC-0006 |  | 2020-02-13 11:41 | 7012-155-PVC-U-016 |  |  |  | A |  |  |  | 45.6693 | 0.011811 | 1.16 | Plan & Actual | Date |  | 0 | 0 | 0 | 431.02 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2519 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-19 23:59 | 2020-04-17 18:00 |  | 10 | 2020-05-05 23:31 |  |  | 2020-02-06 17:40 | 2020-05-07 18:00 |  | 30 |  |  |  | 2020-02-13 17:40 | 2020-05-10 23:59 |  | 35 |  |  |  | 2020-02-19 23:59 | 2020-05-17 23:59 |  | 65 | 2020-07-15 14:52 |  |  | 2020-02-26 17:40 | 2020-06-07 23:59 |  | 80 | 2020-07-15 14:55 | [5 empty] | 80 | 2020-07-15 15:00 | [5 empty] | 80 | 2020-07-15 15:00 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-19 17:40 | 2020-06-21 23:59 |  | 100 | 2020-07-15 15:01 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 117 |  |  |  | 101131
234 | Task(Task)-->E (Engineering) | TRANSFER POINT KDTP-1 - DESIGN CALCULATION OF SUB STRUCTURE |  | 1.4.1.2 | Completed | No | No | 2020-02-23 23:59 | 2020-04-23 17:40 | 2020-07-11 09:00 | 2020-08-04 18:00 |  |  | 2020-02-21 15:37 | 2020-08-04 20:42 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-DC-0007 |  | 2020-02-13 11:41 | 7012-155-PVC-U-017 |  |  |  | A |  |  |  | 27.1654 | 0.007026 | 0.69 | Plan & Actual | Date |  | 0 | 0 | 0 | 257.12 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2520 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-23 23:59 | 2020-05-22 18:00 |  | 10 |  |  |  | 2020-03-12 17:40 | 2020-06-11 18:00 |  | 30 |  |  |  | 2020-03-19 17:40 | 2020-06-14 23:59 |  | 35 |  |  |  | 2020-03-25 23:59 | 2020-06-21 23:59 |  | 65 | 2020-08-04 20:23 |  |  | 2020-04-01 17:40 | 2020-07-12 23:59 |  | 80 | 2020-08-04 20:37 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-23 17:40 | 2020-07-26 23:59 |  | 100 | 2020-08-04 20:42 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 118 |  |  |  | 101132
235 | Task(Task)-->E (Engineering) | TRANSFER POINT KDTP-1 - NUM & RC DETAILS OF FDN |  | 1.4.1.2 | Completed | No | No | 2020-02-23 23:59 | 2020-04-23 17:40 | 2020-07-11 09:00 | 2020-08-04 18:00 |  |  | 2020-02-21 15:37 | 2020-08-04 20:41 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-NR-0005 |  | 2020-02-13 11:41 | 7012-155-PVC-C-019 |  |  |  | A |  |  |  | 16.1417 | 0.004175 | 0.41 | Plan & Actual | Date |  | 0 | 0 | 0 | 154.22 | 0 | 8.15 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2516 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-23 23:59 | 2020-05-22 18:00 |  | 10 |  |  |  | 2020-03-12 17:40 | 2020-06-11 18:00 |  | 30 |  |  |  | 2020-03-19 17:40 | 2020-06-14 23:59 |  | 35 | 2020-07-11 16:17 |  |  | 2020-03-25 23:59 | 2020-06-21 23:59 |  | 65 | 2020-08-04 20:24 |  |  | 2020-04-01 17:40 | 2020-07-12 23:59 |  | 80 | 2020-08-04 20:38 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-23 17:40 | 2020-07-26 23:59 |  | 100 | 2020-08-04 20:41 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 120 |  |  |  | 101134
236 | Task(Task)-->E (Engineering) | TRANSFER POINT KDTP-1 - NUM & RC DETAILS OF FLOOR SLABS |  | 1.4.1.2 | Unscheduled | No | No | 2020-03-24 18:00 | 2020-05-25 17:40 | 2020-06-26 18:00 | 2020-09-23 18:00 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-NR-0006 |  | 2020-02-13 11:41 | 7012-155-PVC-C-020 |  |  |  | A |  |  |  | 5.5118 | 0.001425 | 0.14 | Plan & Actual | Date |  | 0 | 0 | 0 | 51.26 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2517 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-24 18:00 | 2020-06-26 18:00 |  | 10 |  |  |  | 2020-04-13 17:40 | 2020-07-16 18:00 |  | 30 |  |  |  | 2020-04-18 17:40 | 2020-07-19 23:59 |  | 35 | 2020-08-30 20:44 |  |  | 2020-04-24 23:59 | 2020-07-26 23:59 |  | 65 | 2020-08-31 23:46 |  |  | 2020-05-01 17:40 | 2020-08-16 23:59 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-25 17:40 | 2020-08-30 23:59 |  | 100 | [122 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 121 |  |  |  | 101135
237 | Task(Task)-->E (Engineering) | TRANSFER POINT KDTP-1 - NUM & RC DETAILS OF GRADE SLAB |  | 1.4.1.2 | Completed | No | No | 2020-03-24 18:00 | 2020-05-25 17:40 | 2020-08-06 09:00 | 2020-08-17 18:00 |  |  | 2020-02-21 15:37 | 2020-08-17 22:47 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-NR-0007 |  | 2020-02-13 11:41 | 7012-155-PVC-C-021 |  |  |  | A |  |  |  | 5.5118 | 0.001425 | 0.14 | Plan & Actual | Date |  | 0 | 0 | 0 | 51.26 | 0 | 40.1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2518 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-24 18:00 | 2020-07-16 18:00 |  | 10 |  |  |  | 2020-04-13 17:40 | 2020-08-05 18:00 |  | 30 |  |  |  | 2020-04-18 17:40 | 2020-08-08 18:00 |  | 35 | 2020-08-06 08:51 |  |  | 2020-04-24 23:59 | 2020-08-15 18:00 |  | 65 | 2020-08-13 19:52 |  |  | 2020-05-01 17:40 | 2020-09-05 18:00 |  | 80 | 2020-08-17 22:42 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-25 17:40 | 2020-09-19 18:00 |  | 100 | 2020-08-17 22:48 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 122 |  |  |  | 101136
238 | Task(Task)-->E (Engineering) | STRUCTURAL | 1.4.1.3 | 1.4.1 | Work In Progress | No | No | 2020-01-19 23:59 | 2020-07-07 17:40 | 2020-07-01 09:00 | 2020-10-15 18:00 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 96.9685 | [15 empty] | 16.6448 | 0.012931 | 1.27 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No | 2521 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036076
239 | Task(Task)-->E (Engineering) | TRANSFER POINT KDTP-1 - STRUCTURAL GA |  | 1.4.1.3 | Completed | No | No | 2020-01-19 23:59 | 2020-03-19 17:40 | 2020-07-01 09:00 | 2020-07-15 18:00 |  |  | 2020-02-21 15:37 | 2020-07-15 20:59 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-GA-0005 |  | 2020-02-13 11:41 | 7012-155-PVC-B-018 |  |  |  | A |  |  |  | 91.3386 | 0.011811 | 1.16 | Plan & Actual | Date |  | 0 | 0 | 0 | 431.02 | 0 | 38.3 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2523 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-19 23:59 | 2020-04-17 18:00 |  | 10 | 2020-05-05 23:31 |  |  | 2020-02-06 17:40 | 2020-05-07 18:00 |  | 30 |  |  |  | 2020-02-13 17:40 | 2020-05-10 23:59 |  | 35 | 2020-06-29 10:36 |  |  | 2020-02-19 23:59 | 2020-05-17 23:59 |  | 65 | 2020-07-15 20:46 |  |  | 2020-02-26 17:40 | 2020-06-07 23:59 |  | 80 | 2020-07-15 20:54 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-19 17:40 | 2020-06-21 23:59 |  | 100 | 2020-07-15 21:00 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 119 |  |  |  | 101133
240 | Task(Task)-->E (Engineering) | ARCHITECTURAL GA OF TRANSFER POINT KDTP-1 |  | 1.4.1.3 | Unscheduled | No | No | 2020-05-08 18:00 | 2020-07-07 17:40 | 2020-07-01 18:00 | 2020-10-15 18:00 |  |  | 2020-02-21 15:39 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-AR-0002 |  | 2020-02-13 11:43 | 7012-155-PVC-C-108 |  |  |  | I |  |  |  | 8.6614 | 0.00112 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 40.52 | 0 | 73 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2522 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-05-08 18:00 | 2020-07-01 18:00 |  | 10 |  |  |  | 2020-05-27 17:40 | 2020-07-26 23:59 |  | 30 |  |  |  | 2020-06-02 17:40 | 2020-07-29 18:00 |  | 35 | 2020-09-16 19:09 |  |  | 2020-06-08 23:59 | 2020-08-05 18:00 |  | 65 | 2020-09-19 20:58 |  |  | 2020-06-15 17:40 | 2020-08-26 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-07-07 17:40 | 2020-09-09 18:00 |  | 100 | [122 empty] | Chetan Khodke |  |  |  |  | A - Architecture | [16 empty] | 209 |  |  |  | 101219
241 | Task(Task)-->E (Engineering) | ELECTRICAL | 1.4.1.4 | 1.4.1 | Work In Progress | No | No | 2020-01-09 18:00 | 2020-06-10 17:40 | 2020-03-02 09:00 | 2020-08-21 18:00 |  |  | 2020-02-17 17:40 |  |  |  | 100 | 75.7693 | [15 empty] | 20.4456 | 0.015884 | 1.56 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No | 2526 | 1 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036077
242 | Task(Task)-->E (Engineering) | GA,SLD,WIRING & BOM OF ILMS |  | 1.4.1.4 | Completed | No | No | 2020-02-17 17:40 | 2020-03-30 17:40 | 2020-03-02 09:00 | 2020-04-02 18:00 |  |  | 2020-02-17 17:40 | 2020-04-18 12:40 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-401 |  | 2020-02-13 11:47 | 7012-155-PVE-W-137 |  |  |  | A |  |  |  | 7.0513 | 0.00112 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2529 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-16 23:59 | 2020-02-18 18:00 |  | 10 | 2020-02-18 23:31 |  |  | 2020-02-17 17:40 | 2020-02-25 18:00 |  | 30 | 2020-02-25 23:31 |  |  | 2020-02-24 17:40 | 2020-02-29 18:00 |  | 35 | 2020-02-29 23:31 |  |  | 2020-02-29 23:59 | 2020-03-02 18:00 |  | 65 | 2020-03-02 23:31 |  |  | 2020-03-06 17:40 | 2020-03-17 18:00 |  | 80 | 2020-03-17 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-30 17:40 | 2020-04-09 18:00 |  | 100 | 2020-04-09 23:31 | [121 empty] | Varun Parihari | [21 empty] | 372 |  |  |  | 101383
243 | Task(Task)-->E (Engineering) | DATASHEET & TERMINAL WIRING DIAGRAM FOR FLAP GATE |  | 1.4.1.4 | Unscheduled | No | No | 2020-04-30 17:40 | 2020-06-10 17:40 | 2020-05-15 18:00 | 2020-08-21 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-405 |  | 2020-02-13 11:47 | 7012-155-PVE-W-141 |  |  |  | A |  |  |  | 7.0513 | 0.00112 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2530 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-30 18:00 | 2020-05-15 18:00 |  | 10 |  |  |  | 2020-04-30 17:40 | 2020-05-22 18:00 |  | 30 |  |  |  | 2020-05-06 17:40 | 2020-05-28 18:00 |  | 35 |  |  |  | 2020-05-13 23:59 | 2020-05-28 18:00 |  | 65 |  |  |  | 2020-05-19 17:40 | 2020-06-18 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-10 17:40 | 2020-06-18 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 376 |  |  |  | 101387
244 | Task(Task)-->E (Engineering) | EQUIPMENT, CABLE ROUTING, EARTHING & LIGHTNING LAYOUT WITH PLAN, SECTIONAL VIEWS & BOM OF KDTP-1 |  | 1.4.1.4 | Unscheduled | No | No | 2020-01-09 18:00 | 2020-03-06 17:40 | 2020-04-18 18:00 | 2020-06-08 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5054 |  | 2020-02-13 11:44 | 7012-155-PVE-F-016 |  |  |  | A |  |  |  | 42.9487 | 0.006822 | 0.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 248.42 | 0 | 38.33 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2527 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-09 18:00 | 2020-04-18 18:00 |  | 10 | 2020-04-18 23:31 |  |  | 2020-01-25 17:40 | 2020-05-02 18:00 |  | 30 | 2020-05-12 23:31 |  |  | 2020-01-31 17:40 | 2020-05-09 18:00 |  | 35 | 2020-05-19 23:31 |  |  | 2020-02-06 23:59 | 2020-05-16 18:00 |  | 65 | 2020-05-29 23:31 |  |  | 2020-02-13 17:40 | 2020-06-06 18:00 |  | 80 | 2020-07-28 17:52 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-06 17:40 | 2020-06-06 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 251 |  |  |  | 101262
245 | Task(Task)-->E (Engineering) | LIGHTING LAYOUT PLAN WITH POWER DISTRIBUTION ARRANGEMENT, SECTIONAL VIEW, BOM OF KDTP-1 |  | 1.4.1.4 | Unscheduled | No | No | 2020-03-16 18:00 | 2020-05-05 17:40 | 2020-04-29 18:00 | 2020-06-10 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5065 |  | 2020-02-13 11:44 | 7012-155-PVE-G-027 |  |  |  | A |  |  |  | 42.9487 | 0.006822 | 0.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 248.42 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2528 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-16 18:00 | 2020-04-29 18:00 |  | 10 | 2020-04-29 23:31 |  |  | 2020-03-24 17:40 | 2020-05-06 18:00 |  | 30 | 2020-05-02 23:31 |  |  | 2020-03-31 17:40 | 2020-05-13 18:00 |  | 35 | 2020-05-04 23:31 |  |  | 2020-04-06 23:59 | 2020-05-20 18:00 |  | 65 | 2020-05-05 23:31 |  |  | 2020-04-13 17:40 | 2020-06-10 18:00 |  | 80 | 2020-05-19 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-05 17:40 | 2020-06-10 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 262 |  |  |  | 101273
246 | Task(Task)-->P (Procurement) | PROCUREMENT | 1.4.2 | 1.4 | Work In Progress | No | No | 2019-09-27 09:00 | 2021-03-20 18:00 | 2019-09-27 09:00 | 2021-05-13 18:00 |  |  | 2019-09-27 10:57 |  |  |  | 83.2527 | 42.8427 | [15 empty] | 73.3172 | 2.986 | 293.65 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2532 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017901
247 | Task(Task)-->P (Procurement) | PURCHASE REQUISITION | 1.4.2.1 | 1.4.2 | Work In Progress | No | No | 2019-09-27 09:00 | 2020-03-27 18:00 | 2019-09-27 09:00 | 2020-05-29 18:00 |  |  | 2019-09-27 10:57 |  |  |  | 100 | 99.9321 | [15 empty] | 5.03 | 0.15019 | 14.77 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2533 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017902
248 | Task(Task)-->P (Procurement) | Secondary Sizer |  | 1.4.2.1 | Completed | No | No | 2019-09-27 09:00 | 2019-09-27 18:00 | 2019-09-27 09:00 | 2019-09-27 18:00 |  |  | 2019-09-27 10:57 | 2019-09-27 10:57 |  |  | 100 | 100 | [15 empty] | 56.157 | 0.084344 | 8.3 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2534 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017903
249 | Task(Task)-->P (Procurement) | ILMS |  | 1.4.2.1 | Completed | No | No | 2019-09-27 09:00 | 2019-09-27 18:00 | 2019-09-27 09:00 | 2019-09-27 18:00 |  |  | 2019-09-27 10:57 | 2019-09-27 10:57 |  |  | 100 | 100 | [15 empty] | 6.157 | 0.009247 | 0.91 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2535 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017904
250 | Task(Task)-->P (Procurement) | Flap Gate |  | 1.4.2.1 | Completed | No | No | 2020-02-06 09:00 | 2020-02-06 18:00 | 2020-03-20 09:00 | 2020-03-20 18:00 |  |  | 2020-03-20 10:57 | 2020-03-20 10:57 |  |  | 100 | 100 | [15 empty] | 1.9621 | 0.002947 | 0.29 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2536 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017905
251 | Task(Task)-->P (Procurement) | Chute & Skirt |  | 1.4.2.1 | Completed | No | No | 2020-03-10 09:00 | 2020-03-10 18:00 | 2020-03-11 09:00 | 2020-03-11 18:00 |  |  | 2020-03-11 10:57 | 2020-03-11 10:57 |  |  | 100 | 100 | [15 empty] | 5.8863 | 0.008841 | 0.87 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2537 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017906
252 | Task(Task)-->P (Procurement) | Building Structure |  | 1.4.2.1 | Completed | No | No | 2020-02-19 09:00 | 2020-02-19 18:00 | 2020-05-29 09:00 | 2020-05-29 18:00 |  |  | 2020-05-31 18:44 | 2020-05-31 18:44 |  |  | 100 | 100 | [15 empty] | 26.387 | 0.039631 | 3.9 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2538 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017907
253 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR CONVEYING SYSTEM |  | 1.4.2.1 | Completed | No | No | 2019-12-16 09:00 | 2019-12-16 18:00 | 2020-01-13 09:00 | 2020-01-13 18:00 |  |  | 2020-01-13 10:57 | 2020-01-13 10:57 |  |  | 100 | 100 | [15 empty] | 0.54127 | 0.000813 | 0.08 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2539 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017908
254 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.4.2.1 | Completed | No | No | 2020-03-10 09:00 | 2020-03-10 18:00 | 2020-03-16 09:00 | 2020-03-16 18:00 |  |  | 2020-03-16 10:57 | 2020-03-16 10:57 |  |  | 100 | 100 | [15 empty] | 1.8268 | 0.002744 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2540 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017909
255 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.4.2.1 | Completed | No | No | 2020-03-27 09:00 | 2020-03-27 18:00 | 2020-04-30 09:00 | 2020-04-30 18:00 |  |  | 2020-04-30 10:57 | 2020-04-30 10:57 |  |  | 100 | 100 | [15 empty] | 0.81191 | 0.001219 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2541 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017910
256 | Task(Task)-->P (Procurement) | LPBS |  | 1.4.2.1 | Unscheduled | No | No | 2020-03-20 09:00 | 2020-03-20 18:00 | 2020-04-14 09:00 | 2020-04-14 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.067659 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2542 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017911
257 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.4.2.1 | Completed | No | No | 2020-01-03 09:00 | 2020-01-03 18:00 | 2020-01-03 09:00 | 2020-01-03 18:00 |  |  | 2020-01-03 10:57 | 2020-01-03 10:57 |  |  | 100 | 100 | [15 empty] | 0.067659 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2545 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017912
258 | Task(Task)-->P (Procurement) | CONTROL JUNCTION BOX |  | 1.4.2.1 | Completed | No | No | 2020-03-05 09:00 | 2020-03-05 18:00 | 2020-04-18 09:00 | 2020-04-18 18:00 |  |  | 2020-04-18 10:57 | 2020-04-18 10:57 |  |  | 100 | 100 | [15 empty] | 0.13532 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2546 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017913
259 | Task(Task)-->P (Procurement) | TECHNICAL CLEARANCE | 1.4.2.2 | 1.4.2 | Work In Progress | No | No | 2019-09-28 09:00 | 2020-05-11 18:00 | 2019-09-27 09:00 | 2020-06-12 18:00 |  |  | 2019-11-07 10:57 |  |  |  | 100 | 99.9225 | [15 empty] | 4.4068 | 0.13158 | 12.94 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2547 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017914
260 | Task(Task)-->P (Procurement) | Secondary Sizer |  | 1.4.2.2 | Completed | No | No | 2019-09-28 09:00 | 2019-10-16 18:00 | 2019-09-27 09:00 | 2019-11-07 18:00 |  |  | 2019-11-07 10:57 | 2019-11-07 10:57 |  |  | 100 | 100 | [15 empty] | 49.9614 | 0.065741 | 6.47 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2548 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017915
261 | Task(Task)-->P (Procurement) | ILMS |  | 1.4.2.2 | Completed | No | No | 2019-09-28 09:00 | 2020-01-07 18:00 | 2019-09-27 09:00 | 2019-12-04 18:00 |  |  | 2019-12-04 10:57 | 2019-12-04 10:57 |  |  | 100 | 100 | [15 empty] | 7.027 | 0.009246 | 0.91 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2549 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017916
262 | Task(Task)-->P (Procurement) | Flap Gate |  | 1.4.2.2 | Completed | No | No | 2020-02-07 09:00 | 2020-03-22 23:59 | 2020-03-20 09:00 | 2020-04-28 18:00 |  |  | 2020-04-28 10:57 | 2020-04-28 10:57 |  |  | 100 | 100 | [15 empty] | 2.2394 | 0.002947 | 0.29 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2550 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017917
263 | Task(Task)-->P (Procurement) | Chute & Skirt |  | 1.4.2.2 | Completed | No | No | 2020-03-11 09:00 | 2020-03-20 18:00 | 2020-03-11 09:00 | 2020-03-17 18:00 |  |  | 2020-03-17 10:57 | 2020-03-17 10:57 |  |  | 100 | 100 | [15 empty] | 6.7181 | 0.00884 | 0.87 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2551 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017918
264 | Task(Task)-->P (Procurement) | Building Structure |  | 1.4.2.2 | Completed | No | No | 2020-02-20 09:00 | 2020-02-26 18:00 | 2020-05-29 09:00 | 2020-05-29 18:00 |  |  | 2020-05-29 17:31 | 2020-05-29 17:31 |  |  | 100 | 100 | [15 empty] | 30.1158 | 0.039628 | 3.9 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2552 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017919
265 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR CONVEYING SYSTEM |  | 1.4.2.2 | Completed | No | No | 2019-12-17 09:00 | 2019-12-31 18:00 | 2020-01-13 09:00 | 2020-04-11 18:00 |  |  | 2020-04-11 10:57 | 2020-04-11 10:57 |  |  | 100 | 100 | [15 empty] | 0.61776 | 0.000813 | 0.08 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2553 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017920
266 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.4.2.2 | Completed | No | No | 2020-03-11 09:00 | 2020-03-25 18:00 | 2020-03-16 09:00 | 2020-06-02 18:00 |  |  | 2020-06-02 10:57 | 2020-06-02 10:57 |  |  | 100 | 100 | [15 empty] | 2.0849 | 0.002743 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2554 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017921
267 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.4.2.2 | Completed | No | No | 2020-03-28 09:00 | 2020-05-11 18:00 | 2020-04-30 09:00 | 2020-06-03 18:00 |  |  | 2020-06-03 10:57 | 2020-06-03 10:57 |  |  | 100 | 100 | [15 empty] | 0.92664 | 0.001219 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2555 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017922
268 | Task(Task)-->P (Procurement) | LPBS |  | 1.4.2.2 | Unscheduled | No | No | 2020-03-21 09:00 | 2020-04-04 18:00 | 2020-04-14 09:00 | 2020-06-12 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.07722 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2556 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017923
269 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.4.2.2 | Completed | No | No | 2020-01-04 09:00 | 2020-01-18 18:00 | 2020-01-03 09:00 | 2020-01-16 18:00 |  |  | 2020-01-16 10:57 | 2020-01-16 10:57 |  |  | 100 | 100 | [15 empty] | 0.07722 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2559 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017924
270 | Task(Task)-->P (Procurement) | CONTROL JUNCTION BOX |  | 1.4.2.2 | Completed | No | No | 2020-03-06 09:00 | 2020-03-13 18:00 | 2020-04-18 09:00 | 2020-06-02 18:00 |  |  | 2020-06-02 10:57 | 2020-06-02 10:57 |  |  | 100 | 100 | [15 empty] | 0.15444 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2560 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017925
271 | Task(Task)-->P (Procurement) | ORDERING | 1.4.2.3 | 1.4.2 | Work In Progress | No | No | 2019-10-17 09:00 | 2020-06-25 18:00 | 2019-11-07 09:00 | 2020-08-28 18:00 |  |  | 2020-02-01 10:57 |  |  |  | 100 | 99.7294 | [15 empty] | 10.0633 | 0.30049 | 29.55 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2561 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017926
272 | Task(Task)-->P (Procurement) | Secondary Sizer |  | 1.4.2.3 | Completed | No | No | 2019-10-17 09:00 | 2019-11-20 18:00 | 2019-11-07 09:00 | 2020-02-25 18:00 |  |  | 2020-02-25 10:57 | 2020-02-25 10:57 |  |  | 100 | 100 | [15 empty] | 56.2098 | 0.1689 | 16.61 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2562 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017927
273 | Task(Task)-->P (Procurement) | ILMS |  | 1.4.2.3 | Completed | No | No | 2020-01-08 09:00 | 2020-02-06 18:00 | 2019-12-04 09:00 | 2020-02-03 18:00 |  |  | 2020-02-03 10:57 | 2020-02-03 10:57 |  |  | 100 | 100 | [15 empty] | 6.1591 | 0.018507 | 1.82 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2563 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017928
274 | Task(Task)-->P (Procurement) | Flap Gate |  | 1.4.2.3 | Completed | No | No | 2020-03-23 09:00 | 2020-04-21 18:00 | 2020-04-28 09:00 | 2020-08-28 18:00 |  |  | 2020-04-28 16:11 | 2020-08-22 16:11 |  |  | 100 | 100 | [15 empty] | 1.9289 | 0.005796 | 0.57 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2564 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017929
275 | Task(Task)-->P (Procurement) | Chute & Skirt |  | 1.4.2.3 | Completed | No | No | 2020-03-21 09:00 | 2020-04-19 23:59 | 2020-03-17 09:00 | 2020-07-06 18:00 |  |  | 2020-03-18 12:49 | 2020-07-06 12:49 |  |  | 100 | 100 | [15 empty] | 5.8545 | 0.017592 | 1.73 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2565 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017930
276 | Task(Task)-->P (Procurement) | Building Structure |  | 1.4.2.3 | Completed | No | No | 2020-02-27 09:00 | 2020-03-27 18:00 | 2020-05-29 09:00 | 2020-05-31 23:59 |  |  | 2020-05-31 18:49 | 2020-05-31 18:49 |  |  | 100 | 100 | [15 empty] | 26.3959 | 0.079317 | 7.8 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2566 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017931
277 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR CONVEYING SYSTEM |  | 1.4.2.3 | Completed | No | No | 2020-01-01 09:00 | 2020-01-16 18:00 | 2020-04-11 09:00 | 2020-07-20 18:00 |  |  | 2020-04-12 15:47 | 2020-06-20 15:47 |  |  | 100 | 100 | [15 empty] | 0.54146 | 0.001627 | 0.16 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2567 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017932
278 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.4.2.3 | Completed | No | No | 2020-03-26 09:00 | 2020-04-10 18:00 | 2020-06-02 09:00 | 2020-07-31 18:00 |  |  | 2020-06-03 15:51 | 2020-06-29 15:51 |  |  | 100 | 100 | [15 empty] | 1.7936 | 0.005389 | 0.53 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2568 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017933
279 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.4.2.3 | Completed | No | No | 2020-05-12 09:00 | 2020-06-25 18:00 | 2020-06-03 09:00 | 2020-06-24 18:00 |  |  | 2020-06-15 10:57 | 2020-06-15 10:57 |  |  | 100 | 100 | [15 empty] | 0.81218 | 0.002441 | 0.24 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2569 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017934
280 | Task(Task)-->P (Procurement) | LPBS |  | 1.4.2.3 | Unscheduled | No | No | 2020-04-05 | 2020-04-20 18:00 | 2020-06-12 09:00 | 2020-08-19 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.10152 | 0.000305 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2570 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017935
281 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.4.2.3 | Completed | No | No | 2020-01-19 | 2020-01-31 18:00 | 2020-01-16 09:00 | 2020-02-01 18:00 |  |  | 2020-02-01 10:57 | 2020-02-01 10:57 |  |  | 100 | 100 | [15 empty] | 0.033841 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5611 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017936
282 | Task(Task)-->P (Procurement) | CONTROL JUNCTION BOX |  | 1.4.2.3 | Unscheduled | No | No | 2020-03-14 09:00 | 2020-03-21 18:00 | 2020-06-02 09:00 | 2020-08-19 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.1692 | 0.000508 | 0.05 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2574 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017937
283 | Task(Task)-->P (Procurement) | ITP APPROVAL | 1.4.2.4 | 1.4.2 | Work In Progress | No | No | 2019-09-27 09:00 | 2020-08-04 18:00 | 2020-02-03 09:00 | 2020-10-30 18:00 |  |  | 2020-02-03 15:18 |  |  |  | 100 | 8.0516 | [15 empty] | 5.03 | 0.15019 | 14.77 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2575 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017938
284 | Task(Task)-->P (Procurement) | Secondary Sizer |  | 1.4.2.4 | Unscheduled | No | No | 2019-11-21 09:00 | 2019-12-30 18:00 | 2020-02-25 09:00 | 2020-10-15 18:00 | [6 empty] | 100 | 0 | [15 empty] | 56.157 | 0.084344 | 8.3 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2576 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017939
285 | Task(Task)-->P (Procurement) | ILMS |  | 1.4.2.4 | Completed | No | No | 2020-02-07 09:00 | 2020-03-17 18:00 | 2020-02-03 09:00 | 2020-02-24 18:00 |  |  | 2020-02-03 15:18 | 2020-02-24 15:18 |  |  | 100 | 100 | [15 empty] | 6.157 | 0.009247 | 0.91 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2577 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017940
286 | Task(Task)-->P (Procurement) | Flap Gate |  | 1.4.2.4 | Unscheduled | No | No | 2020-04-22 09:00 | 2020-05-31 23:59 | 2020-08-22 09:00 | 2020-10-30 18:00 |  |  | 2020-08-22 16:15 |  |  |  | 100 | 0 | [15 empty] | 1.9621 | 0.002947 | 0.29 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2578 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017941
287 | Task(Task)-->P (Procurement) | Chute & Skirt |  | 1.4.2.4 | Unscheduled | No | No | 2020-04-20 09:00 | 2020-05-29 18:00 | 2020-07-06 09:00 | 2020-07-16 18:00 | [6 empty] | 100 | 0 | [15 empty] | 5.8863 | 0.008841 | 0.87 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2579 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017942
288 | Task(Task)-->P (Procurement) | Building Structure |  | 1.4.2.4 | Unscheduled | No | No | 2020-03-28 09:00 | 2020-04-03 18:00 | 2020-05-31 | 2020-08-04 18:00 |  |  | 2020-06-25 19:04 |  |  |  | 100 | 0 | [15 empty] | 26.387 | 0.039631 | 3.9 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2580 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017943
289 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR CONVEYING SYSTEM |  | 1.4.2.4 | Unscheduled | No | No | 2020-01-17 09:00 | 2020-02-25 18:00 | 2020-09-08 09:00 | 2020-10-11 23:59 | [6 empty] | 100 | 0 | [15 empty] | 0.54127 | 0.000813 | 0.08 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2581 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017944
290 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.4.2.4 | Completed | No | No | 2020-04-11 09:00 | 2020-05-20 18:00 | 2020-07-28 09:00 | 2020-09-08 18:00 |  |  | 2020-07-08 17:23 | 2020-09-08 17:23 |  |  | 100 | 100 | [15 empty] | 1.8268 | 0.002744 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2582 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017945
291 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.4.2.4 | Unscheduled | No | No | 2020-06-26 09:00 | 2020-08-04 18:00 | 2020-06-23 09:00 | 2020-09-08 18:00 |  |  | 2020-06-23 17:26 |  |  |  | 100 | 0 | [15 empty] | 0.81191 | 0.001219 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2583 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017946
292 | Task(Task)-->P (Procurement) | LPBS |  | 1.4.2.4 | Completed | No | No | 2020-04-21 09:00 | 2020-05-30 18:00 | 2020-07-29 09:00 | 2020-08-21 18:00 |  |  | 2020-07-29 14:56 | 2020-08-22 12:53 |  |  | 100 | 100 | [15 empty] | 0.067659 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2584 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017947
293 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.4.2.4 | Unscheduled | No | No | 2019-09-27 09:00 | 2019-11-05 18:00 | 2020-07-02 09:00 | 2020-08-04 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.067659 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2587 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017948
294 | Task(Task)-->P (Procurement) | CONTROL JUNCTION BOX |  | 1.4.2.4 | Unscheduled | No | No | 2020-03-22 | 2020-04-30 18:00 | 2020-07-29 09:00 | 2020-09-21 18:00 |  |  | 2020-07-29 14:52 |  |  |  | 100 | 0 | [15 empty] | 0.13532 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2588 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017949
295 | Task(Task)-->P (Procurement) | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE | 1.4.2.5 | 1.4.2 | Work In Progress | No | No | 2019-09-27 09:00 | 2020-09-16 18:00 | 2020-02-01 09:00 | 2020-10-21 18:00 |  |  | 2020-02-04 12:46 |  |  |  | 100 | 69.9956 | [15 empty] | 15.0933 | 0.45068 | 44.32 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2589 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017950
296 | Task(Task)-->P (Procurement) | Secondary Sizer |  | 1.4.2.5 | Completed | No | No | 2019-11-21 09:00 | 2020-02-18 18:00 | 2020-02-25 09:00 | 2020-06-22 18:00 |  |  | 2020-02-26 14:50 | 2020-06-22 14:50 |  |  | 100 | 100 | [15 empty] | 56.1922 | 0.25325 | 24.91 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2590 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017951
297 | Task(Task)-->P (Procurement) | ILMS |  | 1.4.2.5 | Completed | No | No | 2020-02-07 09:00 | 2020-04-06 18:00 | 2020-02-03 09:00 | 2020-04-24 18:00 |  |  | 2020-02-04 12:46 | 2020-04-24 10:57 |  |  | 100 | 100 | [15 empty] | 6.1584 | 0.027755 | 2.73 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2591 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017952
298 | Task(Task)-->P (Procurement) | Flap Gate |  | 1.4.2.5 | Unscheduled | No | No | 2020-04-22 09:00 | 2020-06-20 18:00 | 2020-08-22 09:00 | 2020-10-15 18:00 |  |  | 2020-08-22 16:13 |  |  |  | 100 | 15 | [15 empty] | 1.94 | 0.008743 | 0.86 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2592 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017953
299 | Task(Task)-->P (Procurement) | Chute & Skirt |  | 1.4.2.5 | Completed | No | No | 2020-04-20 09:00 | 2020-09-16 18:00 | 2020-07-06 09:00 | 2020-07-06 18:00 |  |  | 2020-07-06 12:51 | 2020-07-06 12:51 |  |  | 100 | 100 | [15 empty] | 5.8651 | 0.026433 | 2.6 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2593 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017954
300 | Task(Task)-->P (Procurement) | Building Structure |  | 1.4.2.5 | Unscheduled | No | No | 2020-03-26 09:00 | 2020-04-01 18:00 | 2020-05-31 | 2020-07-25 18:00 | [6 empty] | 100 | 0 | [15 empty] | 26.393 | 0.11895 | 11.7 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2594 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017955
301 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR CONVEYING SYSTEM |  | 1.4.2.5 | Completed | No | No | 2020-01-17 09:00 | 2020-03-01 23:59 | 2020-07-07 09:00 | 2020-09-29 18:00 |  |  | 2020-07-07 10:15 | 2020-09-21 12:52 |  |  | 100 | 100 | [15 empty] | 0.54139 | 0.00244 | 0.24 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2595 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017956
302 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.4.2.5 | Unscheduled | No | No | 2020-04-11 09:00 | 2020-05-25 18:00 | 2020-07-10 09:00 | 2020-10-16 18:00 |  |  | 2020-07-14 10:44 |  |  |  | 100 | 0 | [15 empty] | 1.8046 | 0.008133 | 0.8 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2596 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017957
303 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.4.2.5 | Completed | No | No | 2020-06-26 09:00 | 2020-08-09 23:59 | 2020-05-30 09:00 | 2020-08-08 18:00 |  |  | 2020-06-18 17:04 | 2020-08-07 15:00 |  |  | 100 | 100 | [15 empty] | 0.81209 | 0.00366 | 0.36 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2597 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017958
304 | Task(Task)-->P (Procurement) | LPBS |  | 1.4.2.5 | Completed | No | No | 2020-04-21 09:00 | 2020-06-04 18:00 | 2020-07-25 09:00 | 2020-08-22 18:00 |  |  | 2020-07-24 18:37 | 2020-08-22 12:57 |  |  | 100 | 100 | [15 empty] | 0.090232 | 0.000407 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2598 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017959
305 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.4.2.5 | Completed | No | No | 2019-09-27 09:00 | 2019-11-10 23:59 | 2020-02-01 09:00 | 2020-07-15 18:00 |  |  | 2020-02-11 21:25 | 2020-07-15 21:25 |  |  | 100 | 100 | [15 empty] | 0.045116 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2601 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017960
306 | Task(Task)-->P (Procurement) | CONTROL JUNCTION BOX |  | 1.4.2.5 | Unscheduled | No | No | 2020-03-22 | 2020-05-05 18:00 | 2020-07-25 09:00 | 2020-10-21 18:00 |  |  | 2020-07-25 12:52 |  |  |  | 100 | 0 | [15 empty] | 0.15791 | 0.000712 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2602 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017961
307 | Task(Task)-->P (Procurement) | MANUFACTURING & RECEIPT AT SITE (MRN) | 1.4.2.6 | 1.4.2 | Unscheduled | No | No | 2019-11-11 09:00 | 2021-03-20 18:00 | 2020-04-24 09:00 | 2021-05-13 18:00 |  |  | 2020-04-24 15:19 |  |  |  | 72.262 | 20.5494 | [15 empty] | 60.3767 | 1.8028 | 177.29 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2603 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017962
308 | Task(Task)-->P (Procurement) | Secondary Sizer |  | 1.4.2.6 | Unscheduled | No | No | 2020-02-19 09:00 | 2021-03-20 18:00 | 2020-06-22 09:00 | 2021-03-20 18:00 |  |  | 2020-06-22 01:45 |  |  |  | 58.5859 | 30 | [15 empty] | 56.2017 | 1.0132 | 99.64 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2604 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017963
309 | Task(Task)-->P (Procurement) | ILMS |  | 1.4.2.6 | Unscheduled | No | No | 2020-04-07 09:00 | 2020-10-03 18:00 | 2020-04-24 09:00 | 2020-11-15 23:59 |  |  | 2020-04-24 15:19 |  |  |  | 100 | 60 | [15 empty] | 6.1481 | 0.11084 | 10.9 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2605 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017964
310 | Task(Task)-->P (Procurement) | Flap Gate |  | 1.4.2.6 | Unscheduled | No | No | 2020-06-21 | 2021-01-01 18:00 | 2020-10-31 09:00 | 2021-05-13 18:00 | [6 empty] | 55.8974 | 0 | [15 empty] | 1.9403 | 0.034981 | 3.44 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2606 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017965
311 | Task(Task)-->P (Procurement) | Chute & Skirt |  | 1.4.2.6 | Unscheduled | No | No | 2020-06-19 09:00 | 2021-02-13 18:00 | 2020-07-06 09:00 | 2021-01-31 23:59 | [6 empty] | 46.25 | 0 | [15 empty] | 5.8717 | 0.10586 | 10.41 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2607 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017966
312 | Task(Task)-->P (Procurement) | Building Structure |  | 1.4.2.6 | Unscheduled | No | No | 2020-04-04 09:00 | 2020-10-05 18:00 | 2020-07-25 09:00 | 2020-12-31 18:00 | [6 empty] | 100 | 0 | [15 empty] | 26.3974 | 0.4759 | 46.8 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2608 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017967
313 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR CONVEYING SYSTEM |  | 1.4.2.6 | Unscheduled | No | No | 2020-03-02 09:00 | 2020-09-26 18:00 | 2020-10-12 09:00 | 2021-05-08 18:00 |  |  | 2020-09-22 12:54 |  |  |  | 100 | 0 | [15 empty] | 0.55277 | 0.009965 | 0.98 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2609 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017968
314 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.4.2.6 | Unscheduled | No | No | 2020-05-26 09:00 | 2020-10-21 18:00 | 2020-10-17 09:00 | 2021-03-14 23:59 | [6 empty] | 90.604 | 0 | [15 empty] | 1.7993 | 0.032438 | 3.19 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2610 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017969
315 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.4.2.6 | Unscheduled | No | No | 2020-08-10 09:00 | 2020-11-07 18:00 | 2020-09-09 09:00 | 2020-12-07 18:00 |  |  | 2020-08-07 15:00 |  |  |  | 65.5556 | 0 | [15 empty] | 0.81787 | 0.014745 | 1.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2611 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017970
316 | Task(Task)-->P (Procurement) | LPBS |  | 1.4.2.6 | Unscheduled | No | No | 2020-06-05 09:00 | 2020-09-16 18:00 | 2020-08-23 | 2020-12-04 18:00 |  |  | 2020-08-22 13:00 |  |  |  | 100 | 0 | [15 empty] | 0.084607 | 0.001525 | 0.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2612 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017971
317 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.4.2.6 | Unscheduled | No | No | 2019-11-11 09:00 | 2020-03-09 18:00 | 2020-07-02 09:00 | 2020-10-29 18:00 |  |  | 2020-07-15 21:33 |  |  |  | 100 | 0 | [15 empty] | 0.033843 | 0.00061 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2615 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017972
318 | Task(Task)-->P (Procurement) | CONTROL JUNCTION BOX |  | 1.4.2.6 | Unscheduled | No | No | 2020-05-06 09:00 | 2020-09-16 18:00 | 2020-10-22 09:00 | 2021-03-04 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.15229 | 0.002746 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2616 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017973
319 | Task(Task)-->C (Construction) | CONSTRUCTION | 1.4.3 | 1.4 | Unscheduled | No | No | 2020-04-08 09:00 | 2021-08-28 18:00 | 2020-09-08 09:00 | 2022-03-20 23:59 |  |  | 2020-09-07 15:50 |  |  |  | 30.1737 | 0.32322 | [15 empty] | 24.7753 | 1.009 | 99.23 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2617 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017974
320 | Task(Task)-->C (Construction) | CIVIL | 1.4.3.1 | 1.4.3 | Unscheduled | No | No | 2020-04-08 09:00 | 2021-03-21 23:59 | 2020-09-08 09:00 | 2021-08-26 18:00 |  |  | 2020-09-07 15:50 |  |  |  | 32.4949 | 0.74728 | [15 empty] | 43.253 | 0.43643 | 42.92 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2618 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017975
321 | Task(Task)-->C (Construction) | AVAILABILITY OF FRONT BY NTPC |  | 1.4.3.1 | Unscheduled | No | No | 2020-04-08 09:00 | 2020-04-08 18:00 | 2020-09-08 09:00 | 2020-10-10 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2619 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017976
322 | Task(Task)-->C (Construction) | EXCAVATION |  | 1.4.3.1 | Unscheduled | No | No | 2020-04-15 09:00 | 2020-04-29 18:00 | 2020-10-11 | 2020-10-25 23:59 |  |  | 2020-09-07 15:50 |  |  |  | 100 | 13.7096 | [15 empty] | 5.4507 | 0.023789 | 2.34 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 8753 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2620 | 0 | 4 | Low | Niharendu Kamle | [6 empty] | 0 | 0 | [244 empty] | 1017977
323 | Task(Task)-->C (Construction) | PCC |  | 1.4.3.1 | Unscheduled | No | No | 2020-05-16 09:00 | 2020-05-21 18:00 | 2020-10-21 09:00 | 2020-10-26 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.76869 | 0.003355 | 0.33 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2621 | 0 | 4 | Low | ADMINISTRATOR | [6 empty] | 0 | 0 | [222 empty] | PCC | [21 empty] | 1017978
324 | Task(Task)-->C (Construction) | RAFT |  | 1.4.3.1 | Unscheduled | No | No | 2020-05-22 09:00 | 2020-06-03 18:00 | 2020-10-27 09:00 | 2020-11-08 23:59 | [6 empty] | 100 | 0 | [15 empty] | 21.6399 | 0.094443 | 9.29 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2622 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017979
325 | Task(Task)-->C (Construction) | PADESTALS FOR KDTP-1 STR. |  | 1.4.3.1 | Unscheduled | No | No | 2020-06-04 09:00 | 2020-06-24 18:00 | 2020-11-09 09:00 | 2020-11-29 23:59 | [6 empty] | 100 | 0 | [15 empty] | 4.6355 | 0.020231 | 1.99 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2623 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017980
326 | Task(Task)-->C (Construction) | SECONDARY SIZER FOUNDATION WITH SLAB |  | 1.4.3.1 | Unscheduled | No | No | 2020-10-21 09:00 | 2020-11-05 18:00 | 2021-03-28 | 2021-04-12 18:00 | [6 empty] | 0 | 0 | [15 empty] | 3.7037 | 0.016164 | 1.59 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2625 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017981
327 | Task(Task)-->C (Construction) | HEAD PULLEY FLOOR OF SC 1A/B & SC 2A/B |  | 1.4.3.1 | Unscheduled | No | No | 2021-01-19 09:00 | 2021-01-29 18:00 | 2021-06-26 09:00 | 2021-07-06 18:00 | [6 empty] | 0 | 0 | [15 empty] | 3.7037 | 0.016164 | 1.59 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2626 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017982
328 | Task(Task)-->C (Construction) | GRADE SLAB FOR TAIL PULLEY OF SC 3 A/B |  | 1.4.3.1 | Unscheduled | No | No | 2021-01-30 09:00 | 2021-03-21 23:59 | 2021-07-07 09:00 | 2021-08-26 18:00 | [6 empty] | 0 | 0 | [15 empty] | 60.0978 | 0.26228 | 25.8 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 1378 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2628 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017983
329 | Task(Task)-->C (Construction) | STRUCTURAL WORKS | 1.4.3.2 | 1.4.3 | Unscheduled | No | No | 2020-07-23 09:00 | 2021-03-04 18:00 | 2020-12-28 09:00 | 2021-08-09 18:00 | [6 empty] | 42.0467 | 0 | [15 empty] | 38.3352 | 0.38681 | 38.04 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2629 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017984
330 | Task(Task)-->C (Construction) | STRL. ERECTION FOR RCC CASTING UP TO SECONDARY SIZER FLOOR & FOUNDATION |  | 1.4.3.2 | Unscheduled | No | No | 2020-07-23 09:00 | 2020-10-20 18:00 | 2020-12-28 09:00 | 2021-03-27 18:00 | [6 empty] | 85.5556 | 0 | [15 empty] | 49.1454 | 0.1901 | 18.69 | Plan & Actual | Quantity | Metric Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 289 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2630 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017985
331 | Task(Task)-->C (Construction) | STRL. ERECTION FOR RCC CASTING UP TO HEAD PULLEY (SC 1A/B & SC 2A/B) FLOOR |  | 1.4.3.2 | Unscheduled | No | No | 2020-10-21 09:00 | 2021-01-18 18:00 | 2021-03-28 | 2021-06-25 18:00 | [6 empty] | 0 | 0 | [15 empty] | 39.3111 | 0.15206 | 14.95 | Plan & Actual | Quantity | Metric Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 231 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2631 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017986
332 | Task(Task)-->C (Construction) | BALANCE STRUCTURAL ERECTION |  | 1.4.3.2 | Unscheduled | No | No | 2021-01-19 09:00 | 2021-03-04 18:00 | 2021-06-26 09:00 | 2021-08-09 18:00 | [6 empty] | 0 | 0 | [15 empty] | 11.5435 | 0.044651 | 4.39 | Plan & Actual | Quantity | Metric Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2632 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017987
333 | Task(Task)-->C (Construction) | MECHANICAL EQUIPMENT WORKS | 1.4.3.3 | 1.4.3 | Unscheduled | No | No | 2021-03-05 09:00 | 2021-06-18 18:00 | 2021-05-11 09:00 | 2021-09-17 18:00 | [6 empty] | 0 | 0 | [15 empty] | 9.1404 | 0.092228 | 9.07 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5449 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017988
334 | Task(Task)-->C (Construction) | ERECTION OF SECONDARY SIZER |  | 1.4.3.3 | Unscheduled | No | No | 2021-03-21 | 2021-05-04 18:00 | 2021-05-11 09:00 | 2021-06-24 18:00 | [6 empty] | 0 | 0 | [15 empty] | 77.398 | 0.071383 | 7.02 | Plan & Actual | Quantity | Metric Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 191 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2633 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017989
335 | Task(Task)-->C (Construction) | ERECTION OF CHUTES/ HOODS & SUPPORTS |  | 1.4.3.3 | Unscheduled | No | No | 2021-05-05 09:00 | 2021-06-18 18:00 | 2021-08-04 09:00 | 2021-09-17 18:00 | [6 empty] | 0 | 0 | [15 empty] | 19.4046 | 0.017897 | 1.76 | Plan & Actual | Quantity | Metric Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2634 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017990
336 | Task(Task)-->C (Construction) | ERECTION OF ILMS |  | 1.4.3.3 | Unscheduled | No | No | 2021-03-05 09:00 | 2021-03-18 18:00 | 2021-08-10 09:00 | 2021-08-23 18:00 | [6 empty] | 0 | 0 | [15 empty] | 3.1974 | 0.002949 | 0.29 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5406 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017991
337 | Task(Task)-->C (Construction) | ELECTRICAL & INSTRUMENTATION WORKS | 1.4.3.4 | 1.4.3 | Unscheduled | No | No | 2021-02-25 09:00 | 2021-08-25 18:00 | 2021-08-02 09:00 | 2022-03-17 18:00 | [6 empty] | 0 | 0 | [15 empty] | 7.7194 | 0.07789 | 7.66 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2636 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017992
338 | Task(Task)-->C (Construction) | CABLE TRAY |  | 1.4.3.4 | Unscheduled | No | No | 2021-02-25 09:00 | 2021-03-11 18:00 | 2021-08-02 09:00 | 2021-08-16 18:00 | [6 empty] | 0 | 0 | [15 empty] | 8.366 | 0.006516 | 0.64 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2637 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017993
339 | Task(Task)-->C (Construction) | POWER CABLE |  | 1.4.3.4 | Unscheduled | No | No | 2021-03-12 09:00 | 2021-03-21 23:59 | 2021-08-17 09:00 | 2021-08-26 18:00 | [6 empty] | 0 | 0 | [15 empty] | 32.6797 | 0.025454 | 2.5 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 17687 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2638 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017994
340 | Task(Task)-->C (Construction) | C&I CABLE |  | 1.4.3.4 | Unscheduled | No | No | 2021-03-17 09:00 | 2021-03-21 23:59 | 2021-09-25 09:00 | 2021-09-29 18:00 | [6 empty] | 0 | 0 | [15 empty] | 30.719 | 0.023927 | 2.35 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 16600 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5283 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017995
341 | Task(Task)-->C (Construction) | EARTHING |  | 1.4.3.4 | Unscheduled | No | No | 2021-03-07 | 2021-03-11 18:00 | 2021-08-12 09:00 | 2021-08-16 18:00 | [6 empty] | 0 | 0 | [15 empty] | 2.4837 | 0.001935 | 0.19 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 873 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5284 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017996
342 | Task(Task)-->C (Construction) | EARTH PIT |  | 1.4.3.4 | Unscheduled | No | No | 2021-03-19 09:00 | 2021-03-21 23:59 | 2021-08-24 09:00 | 2021-08-26 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5285 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017997
343 | Task(Task)-->C (Construction) | LIGHTING |  | 1.4.3.4 | Unscheduled | No | No | 2021-02-28 | 2021-03-14 23:59 | 2021-08-05 09:00 | 2021-08-19 18:00 | [6 empty] | 0 | 0 | [15 empty] | 13.7255 | 0.010691 | 1.05 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 108 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5286 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017998
344 | Task(Task)-->C (Construction) | FIELD INTRUMENTS |  | 1.4.3.4 | Unscheduled | No | No | 2021-03-19 09:00 | 2021-03-22 18:00 | 2021-09-27 09:00 | 2021-09-30 18:00 | [6 empty] | 0 | 0 | [15 empty] | 12.0261 | 0.009367 | 0.92 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5287 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1017999
345 | Task(Task)-->C (Construction) | MOTOR TERMINATION |  | 1.4.3.4 | Unscheduled | No | No | 2021-05-19 09:00 | 2021-05-25 18:00 | 2021-12-03 09:00 | 2021-12-09 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5288 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018000
346 | Task(Task)-->C (Construction) | NO LOAD RUN OF MOTOR |  | 1.4.3.4 | Unscheduled | No | No | 2021-08-22 | 2021-08-25 18:00 | 2022-03-14 09:00 | 2022-03-17 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5450 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018001
347 | Task(Task)-->C (Construction) | NO LOAD COMMISSIONING & SYSTEM READYNESS FOR LOAD & TRIAL OPERATION |  | 1.4.3 | Unscheduled | No | No | 2021-08-13 09:00 | 2021-08-28 18:00 | 2022-03-05 09:00 | 2022-03-20 23:59 | [6 empty] | 0 | 0 | [15 empty] | 1.552 | 0.015659 | 1.54 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2639 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018002
348 | Task(Task)-->E (Engineering) | TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B | 1.5 | 1 | Work In Progress | No | No | 2019-09-27 09:00 | 2021-09-08 18:00 | 2019-09-27 09:00 | 2022-03-31 18:00 |  |  | 2019-09-27 10:57 |  |  |  | 71.5355 | 34.0164 | [15 empty] | 2.1555 | 2.1555 | 211.98 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2641 | 0 | 1 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018003
349 | Task(Task)-->E (Engineering) | ENGINEERING | 1.5.1 | 1.5 | Work In Progress | No | No | 2019-10-02 18:00 | 2020-08-14 17:40 | 2019-10-20 23:59 | 2020-10-08 18:00 |  |  | 2019-11-02 17:40 |  |  |  | 100 | 90.9886 | [15 empty] | 6.2792 | 0.13535 | 13.31 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2642 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018004
350 | Task(Task)-->E (Engineering) | MECHANICAL | 1.5.1.1 | 1.5.1 | Work In Progress | No | No | 2019-10-02 18:00 | 2020-08-14 17:40 | 2019-10-20 23:59 | 2020-10-08 18:00 |  |  | 2019-11-02 17:40 |  |  |  | 100 | 95.1065 | [15 empty] | 54.3077 | 0.073504 | 7.06 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No | 2643 | 3 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036078
351 | Task(Task)-->E (Engineering) | SELECTION OF BELT AND DRIVE COMPONENTS FOR TROUGH BELTS CONVEYORS |  | 1.5.1.1 | Completed | No | No | 2019-11-14 17:40 | 2019-12-23 17:40 | 2020-01-06 09:00 | 2020-02-17 18:00 |  |  | 2019-11-14 17:40 | 2020-03-04 10:30 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-CS-DC-0012 |  | 2020-02-13 10:26 | 7012-155-PVM-B-012 |  |  |  | A |  |  |  | 1.4589 | 0.001072 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2649 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-11-08 18:00 | 2019-12-19 18:00 |  | 10 | 2019-12-19 23:31 |  |  | 2019-11-14 17:40 | 2020-01-03 18:00 |  | 30 | 2020-01-03 23:31 |  |  | 2019-11-20 17:40 | 2020-01-03 18:00 |  | 35 | 2020-01-03 23:31 |  |  | 2019-11-26 23:59 | 2020-01-06 18:00 |  | 65 | 2020-01-06 23:31 |  |  | 2019-12-02 17:40 | 2020-02-17 18:00 |  | 80 | 2020-02-17 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2019-12-23 17:40 | 2020-02-17 18:00 |  | 100 | 2020-02-17 23:31 | [121 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 12 |  |  |  | 101026
352 | Task(Task)-->E (Engineering) | TROUGH BELT CONVEYOR PROFILES FOR SC 1A/B, SC 2A/B, SC 3A/B, SY 1A/B AND BELT FEEDER BF1/2 & BF3/4 |  | 1.5.1.1 | Completed | No | No | 2019-10-21 18:00 | 2019-12-05 17:40 | 2019-11-13 09:00 | 2020-01-03 18:00 |  |  | 2020-06-15 17:24 | 2020-06-19 15:47 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-CS-GA-0013 |  | 2020-02-13 10:26 | 7012-155-PVM-B-013 |  |  |  | A |  |  |  | 1.4589 | 0.001072 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 40 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2644 | 1 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-10-21 18:00 | 2019-10-26 18:00 |  | 10 | 2019-10-26 23:31 |  |  | 2019-10-28 17:40 | 2019-11-10 23:59 |  | 30 | 2019-11-10 23:31 |  |  | 2019-11-02 17:40 | 2019-11-10 23:59 |  | 35 | 2019-11-10 23:31 |  |  | 2019-11-08 23:59 | 2019-11-13 18:00 |  | 65 | 2019-11-13 23:31 |  |  | 2019-11-14 17:40 | 2019-12-23 18:00 |  | 80 | 2019-12-23 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | 2020-06-15 17:24 | [5 empty] | 80 | 2020-06-15 17:24 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2019-12-05 17:40 | 2020-01-20 18:00 |  | 100 | 2020-01-20 23:31 | [121 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 13 |  |  |  | 101027
353 | Task(Task)-->E (Engineering) | COASTING TIME CALCULATION AND BRAKE REQUIREMENT FOR TROUGH BELT CONVEYORS |  | 1.5.1.1 | Unscheduled | No | No | 2019-11-07 18:00 | 2019-12-23 17:40 | 2020-04-07 18:00 | 2020-05-19 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-DC-0027 |  | 2020-02-13 10:26 | 7012-155-PVM-U-027 |  |  |  | A |  |  |  | 1.4589 | 0.001072 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 40 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2661 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-11-07 18:00 | 2020-04-07 18:00 |  | 10 | 2020-04-07 23:31 |  |  | 2019-11-14 17:40 | 2020-04-21 18:00 |  | 30 | 2020-04-21 23:31 |  |  | 2019-11-20 17:40 | 2020-04-26 23:59 |  | 35 | 2020-04-26 23:31 |  |  | 2019-11-26 23:59 | 2020-04-26 23:59 |  | 65 | 2020-04-28 23:31 |  |  | 2019-12-02 17:40 | 2020-05-17 23:59 |  | 80 | 2020-05-19 23:31 | [5 empty] | 80 | 2020-09-17 17:15 | [5 empty] | 80 | 2020-09-17 17:15 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2019-12-23 17:40 | 2020-05-17 23:59 |  | 100 | [122 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 27 |  |  |  | 101041
354 | Task(Task)-->E (Engineering) | G.A OF FLUID COUPLING WITH PERFORMANCE CURVES |  | 1.5.1.1 | Completed | No | No | 2020-03-19 18:00 | 2020-05-15 17:40 | 2020-07-31 09:00 | 2020-08-21 18:00 |  |  | 2020-02-21 14:04 | 2020-08-25 17:43 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1004 |  | 2020-02-13 10:27 | 7012-155-PVM-B-104 |  |  |  | A |  |  |  | 5.7029 | 0.004192 | 0.43 | Plan & Actual | Date |  | 0 | 0 | 0 | 160 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2664 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-19 18:00 | 2020-05-20 18:00 |  | 10 | 2020-05-29 23:31 |  |  | 2020-04-03 17:40 | 2020-06-03 18:00 |  | 30 |  |  |  | 2020-04-09 17:40 | 2020-06-10 18:00 |  | 35 |  |  |  | 2020-04-16 23:59 | 2020-06-17 18:00 |  | 65 | 2020-07-31 21:54 |  |  | 2020-04-22 17:40 | 2020-07-08 18:00 |  | 80 | 2020-08-25 11:16 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-15 17:40 | 2020-07-08 18:00 |  | 100 | 2020-08-25 17:44 | [121 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 34 |  |  |  | 101048
355 | Task(Task)-->E (Engineering) | SECTION VIEW, P&ID AND GA OF FLUID COUPLING |  | 1.5.1.1 | Completed | No | No | 2020-03-19 18:00 | 2020-05-15 17:40 | 2020-07-31 09:00 | 2020-08-21 18:00 |  |  | 2020-02-21 14:04 | 2020-08-25 17:43 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1005 |  | 2020-02-13 10:27 | 7012-155-PVM-B-105 |  |  |  | I |  |  |  | 5.7029 | 0.004192 | 0.43 | Plan & Actual | Date |  | 0 | 0 | 0 | 160 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2665 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-19 18:00 | 2020-05-20 18:00 |  | 10 | 2020-05-29 23:31 |  |  | 2020-04-03 17:40 | 2020-06-03 18:00 |  | 30 |  |  |  | 2020-04-09 17:40 | 2020-06-10 18:00 |  | 35 |  |  |  | 2020-04-16 23:59 | 2020-06-17 18:00 |  | 65 | 2020-07-31 21:54 |  |  | 2020-04-22 17:40 | 2020-07-08 18:00 |  | 80 | 2020-08-25 11:17 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-15 17:40 | 2020-07-08 18:00 |  | 100 | 2020-08-25 17:44 | [121 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 35 |  |  |  | 101049
356 | Task(Task)-->E (Engineering) | GA & DIMENSION SHEET FOR TROUGHING IDLERS OF TROUGH BELT CONVEYOR |  | 1.5.1.1 | Completed | No | No | 2020-02-20 18:00 | 2020-04-16 17:40 | 2020-05-29 09:00 | 2020-06-22 18:00 |  |  | 2020-02-21 14:04 | 2020-06-29 19:15 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1008 |  | 2020-02-13 10:27 | 7012-155-PVM-B-108 |  |  |  | I |  |  |  | 9.9469 | 0.007311 | 0.75 | Plan & Actual | Date |  | 0 | 0 | 0 | 280 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2650 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-20 18:00 | 2020-05-15 18:00 |  | 10 | 2020-05-11 23:31 |  |  | 2020-03-05 17:40 | 2020-06-05 18:00 |  | 30 | 2020-05-15 23:31 |  |  | 2020-03-11 17:40 | 2020-06-11 18:00 |  | 35 | 2020-05-18 23:31 |  |  | 2020-03-18 23:59 | 2020-06-11 18:00 |  | 65 | 2020-05-29 23:31 |  |  | 2020-03-24 17:40 | 2020-07-02 18:00 |  | 80 | 2020-06-24 06:47 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-16 17:40 | 2020-07-02 18:00 |  | 100 | 2020-06-29 19:16 | [121 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 38 |  |  |  | 101052
357 | Task(Task)-->E (Engineering) | GA & DIMENSION SHEET FOR IMPACT IDLER FOR TROUGH BELT CONVEYORS |  | 1.5.1.1 | Completed | No | No | 2020-02-20 18:00 | 2020-04-16 17:40 | 2020-06-06 09:00 | 2020-06-22 18:00 |  |  | 2020-02-21 14:04 | 2020-06-29 19:15 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1010 |  | 2020-02-13 10:27 | 7012-155-PVM-B-110 |  |  |  | I |  |  |  | 2.9178 | 0.002145 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 80 | 0 | 11.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2651 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-20 18:00 | 2020-05-18 18:00 |  | 10 | 2020-05-11 23:31 |  |  | 2020-03-05 17:40 | 2020-06-08 18:00 |  | 30 | 2020-05-23 23:31 |  |  | 2020-03-11 17:40 | 2020-06-14 23:59 |  | 35 | 2020-05-31 23:31 |  |  | 2020-03-18 23:59 | 2020-06-14 23:59 |  | 65 | 2020-06-08 18:43 |  |  | 2020-03-24 17:40 | 2020-07-05 23:59 |  | 80 | 2020-06-24 06:45 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-16 17:40 | 2020-07-05 23:59 |  | 100 | 2020-06-29 19:16 | [121 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 40 |  |  |  | 101054
358 | Task(Task)-->E (Engineering) | GA & DIMENSION SHEET FOR FLAT RETURN IDLER FOR TROUGH BELT CONVEYORS |  | 1.5.1.1 | Unscheduled | No | No | 2020-02-20 18:00 | 2020-04-16 17:40 | 2020-05-20 18:00 | 2020-07-07 18:00 |  |  | 2020-08-28 17:04 |  |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1012 |  | 2020-02-13 10:27 | 7012-155-PVM-B-112 |  |  |  | I |  |  |  | 2.9178 | 0.002145 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 80 | 0 | 9.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2652 | 1 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-20 18:00 | 2020-05-20 18:00 |  | 10 | 2020-05-11 23:31 |  |  | 2020-03-05 17:40 | 2020-06-10 18:00 |  | 30 | 2020-05-23 23:31 |  |  | 2020-03-11 17:40 | 2020-06-16 18:00 |  | 35 | 2020-05-31 23:31 |  |  | 2020-03-18 23:59 | 2020-06-16 18:00 |  | 65 | 2020-06-08 18:43 |  |  | 2020-03-24 17:40 | 2020-07-07 18:00 |  | 80 | 2020-06-24 06:47 | [5 empty] | 80 | 2020-08-28 17:04 | [5 empty] | 80 | 2020-08-28 17:04 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-16 17:40 | 2020-07-07 18:00 |  | 100 | 2020-06-29 19:16 | [121 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 42 |  |  |  | 101056
359 | Task(Task)-->E (Engineering) | GA & DIMENSION SHEET FOR V-RETURN IDLERS FOR TROUGH BELT CONVEYORS |  | 1.5.1.1 | Completed | No | No | 2020-02-20 18:00 | 2020-04-16 17:40 | 2020-06-15 09:00 | 2020-07-03 18:00 |  |  | 2020-02-21 14:04 | 2020-07-04 14:55 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1013 |  | 2020-02-13 10:27 | 7012-155-PVM-B-113 |  |  |  | I |  |  |  | 2.9178 | 0.002145 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 80 | 0 | 2.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2653 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-20 18:00 | 2020-05-26 18:00 |  | 10 | 2020-05-14 23:31 |  |  | 2020-03-05 17:40 | 2020-06-16 18:00 |  | 30 | 2020-05-23 23:31 |  |  | 2020-03-11 17:40 | 2020-06-22 18:00 |  | 35 | 2020-05-31 23:31 |  |  | 2020-03-18 23:59 | 2020-06-22 18:00 |  | 65 | 2020-06-15 18:11 |  |  | 2020-03-24 17:40 | 2020-07-13 18:00 |  | 80 | 2020-07-03 15:34 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-16 17:40 | 2020-07-13 18:00 |  | 100 | 2020-07-04 14:56 | [121 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 43 |  |  |  | 101057
360 | Task(Task)-->E (Engineering) | GA & DIMENSION SHEET FOR RUBBER DISC RETURN IDLER FOR BELT CONVEYORS |  | 1.5.1.1 | Completed | No | No | 2020-02-20 18:00 | 2020-04-16 17:40 | 2020-06-06 09:00 | 2020-06-29 18:00 |  |  | 2020-02-21 14:04 | 2020-07-07 18:40 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1014 |  | 2020-02-13 10:27 | 7012-155-PVM-B-114 |  |  |  | I |  |  |  | 2.9178 | 0.002145 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 80 | 0 | 7.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2663 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-20 18:00 | 2020-05-15 18:00 |  | 10 | 2020-05-14 23:31 |  |  | 2020-03-05 17:40 | 2020-06-05 18:00 |  | 30 | 2020-05-23 23:31 |  |  | 2020-03-11 17:40 | 2020-06-11 18:00 |  | 35 | 2020-05-31 23:31 |  |  | 2020-03-18 23:59 | 2020-06-11 18:00 |  | 65 | 2020-06-08 18:43 |  |  | 2020-03-24 17:40 | 2020-07-02 18:00 |  | 80 | 2020-06-24 06:46 | [5 empty] | 80 | 2020-06-29 18:35 | [5 empty] | 80 | 2020-06-29 18:35 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-16 17:40 | 2020-07-02 18:00 |  | 100 | 2020-07-07 18:41 | [121 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 44 |  |  |  | 101058
361 | Task(Task)-->E (Engineering) | GA & DIMENSION SHEET FOR S.A CARRAYING AND S.A RETURN IDLER FOR TROUGH BELT CONVEYORS |  | 1.5.1.1 | Completed | No | No | 2020-02-20 18:00 | 2020-04-16 17:40 | 2020-06-15 09:00 | 2020-07-03 18:00 |  |  | 2020-02-21 14:04 | 2020-07-04 14:55 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1016 |  | 2020-02-13 10:27 | 7012-155-PVM-B-116 |  |  |  | I |  |  |  | 2.9178 | 0.002145 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 80 | 0 | 2.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2654 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-20 18:00 | 2020-05-22 18:00 |  | 10 | 2020-05-11 23:31 |  |  | 2020-03-05 17:40 | 2020-06-12 18:00 |  | 30 | 2020-05-23 23:31 |  |  | 2020-03-11 17:40 | 2020-06-18 18:00 |  | 35 | 2020-05-31 23:31 |  |  | 2020-03-18 23:59 | 2020-06-18 18:00 |  | 65 | 2020-06-15 18:11 |  |  | 2020-03-24 17:40 | 2020-07-09 18:00 |  | 80 | 2020-07-03 15:33 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-16 17:40 | 2020-07-09 18:00 |  | 100 | 2020-07-04 14:56 | [121 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 46 |  |  |  | 101060
362 | Task(Task)-->E (Engineering) | GA & DIMENSION SHEET FOR TROUGHING TRANSITION IDLER FOR TROUGH BELT CONVEYORS |  | 1.5.1.1 | Completed | No | No | 2020-02-20 18:00 | 2020-04-16 17:40 | 2020-06-06 09:00 | 2020-06-29 18:00 |  |  | 2020-02-21 14:04 | 2020-07-07 18:40 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1018 |  | 2020-02-13 10:27 | 7012-155-PVM-B-118 |  |  |  | I |  |  |  | 2.9178 | 0.002145 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 80 | 0 | 7.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2655 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-20 18:00 | 2020-05-26 18:00 |  | 10 | 2020-05-11 23:31 |  |  | 2020-03-05 17:40 | 2020-06-16 18:00 |  | 30 | 2020-05-23 23:31 |  |  | 2020-03-11 17:40 | 2020-06-22 18:00 |  | 35 | 2020-05-31 23:31 |  |  | 2020-03-18 23:59 | 2020-06-22 18:00 |  | 65 | 2020-06-08 18:43 |  |  | 2020-03-24 17:40 | 2020-07-13 18:00 |  | 80 | 2020-06-25 08:20 | [5 empty] | 80 | 2020-06-29 18:46 | [5 empty] | 80 | 2020-06-29 18:46 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-16 17:40 | 2020-07-13 18:00 |  | 100 | 2020-07-07 18:41 | [121 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 48 |  |  |  | 101062
363 | Task(Task)-->E (Engineering) | BELT DATA SHEET WITH SCHEDULE FOR TROUGH BELT CONVEYORS |  | 1.5.1.1 | Unscheduled | No | No | 2020-02-07 18:00 | 2020-04-04 17:40 | 2020-05-10 23:59 | 2020-10-08 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-DC-1024 |  | 2020-02-13 10:27 | 7012-155-PVM-Y-124 |  |  |  | A |  |  |  | 1.4589 | 0.001072 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 40 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2662 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-07 18:00 | 2020-05-10 23:59 |  | 10 |  |  |  | 2020-02-24 17:40 | 2020-05-31 23:59 |  | 30 |  |  |  | 2020-02-29 17:40 | 2020-06-07 23:59 |  | 35 |  |  |  | 2020-03-06 23:59 | 2020-06-07 23:59 |  | 65 | 2020-09-19 13:18 |  |  | 2020-03-12 17:40 | 2020-06-28 23:59 |  | 80 | 2020-10-14 15:22 | [5 empty] | 80 | 2020-10-16 19:16 | [5 empty] | 80 | 2020-10-16 19:16 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-04 17:40 | 2020-06-28 23:59 |  | 100 | [122 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 54 |  |  |  | 101068
364 | Task(Task)-->E (Engineering) | SCHEDULE OF DRIVE AND NON DRIVE PULLEY FOR TROUGH BELT CONVEYORS |  | 1.5.1.1 | Completed | No | No | 2020-01-11 18:00 | 2020-03-07 17:40 | 2020-02-18 09:00 | 2020-03-27 18:00 |  |  | 2020-02-21 14:04 | 2020-06-19 18:48 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1026 |  | 2020-02-13 10:27 | 7012-155-PVM-H-126 |  |  |  | A |  |  |  | 4.244 | 0.00312 | 0.32 | Plan & Actual | Date |  | 0 | 0 | 0 | 120 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2659 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-11 18:00 | 2020-01-25 18:00 |  | 10 | 2020-01-25 23:31 |  |  | 2020-01-28 17:40 | 2020-02-15 18:00 |  | 30 | 2020-02-15 23:31 |  |  | 2020-02-03 17:40 | 2020-02-18 18:00 |  | 35 | 2020-02-18 23:31 |  |  | 2020-02-08 23:59 | 2020-02-18 18:00 |  | 65 | 2020-02-18 23:31 |  |  | 2020-02-14 17:40 | 2020-03-19 18:00 |  | 80 | 2020-03-19 23:31 | [5 empty] | 80 | 2020-06-13 12:03 | [5 empty] | 80 | 2020-06-13 12:03 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-07 17:40 | 2020-03-27 18:00 |  | 100 | 2020-04-19 23:31 | [121 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 56 |  |  |  | 101070
365 | Task(Task)-->E (Engineering) | G.A OF BRAKES FOR TROUGH BELT CONVEYORS |  | 1.5.1.1 | Completed | No | No | 2020-03-25 18:00 | 2020-05-22 17:40 | 2020-07-21 09:00 | 2020-08-12 18:00 |  |  | 2020-02-21 14:04 | 2020-08-24 20:07 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1028 |  | 2020-02-13 10:27 | 7012-155-PVM-B-128 |  |  |  | I |  |  |  | 2.9178 | 0.002145 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 80 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2656 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-25 18:00 | 2020-05-25 18:00 |  | 10 |  |  |  | 2020-04-10 17:40 | 2020-06-15 18:00 |  | 30 |  |  |  | 2020-04-17 17:40 | 2020-06-18 18:00 |  | 35 |  |  |  | 2020-04-23 23:59 | 2020-06-23 18:00 |  | 65 | 2020-07-29 00:16 |  |  | 2020-04-30 17:40 | 2020-07-14 18:00 |  | 80 | 2020-08-19 18:23 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-22 17:40 | 2020-07-14 18:00 |  | 100 | 2020-08-24 20:08 | [121 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 58 |  |  |  | 101072
366 | Task(Task)-->E (Engineering) | GA OF SCRAPPERS- INTERNAL & EXTERNAL FOR BOTH TROUGH BELT & PIPE CONVEYOR |  | 1.5.1.1 | Completed | No | No | 2020-04-12 23:59 | 2020-05-29 17:40 | 2020-07-08 09:00 | 2020-07-28 18:00 |  |  | 2020-02-21 14:04 | 2020-07-30 19:53 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1033 |  | 2020-02-13 10:27 | 7012-155-PVM-B-133 |  |  |  | I |  |  |  | 14.3236 | 0.010528 | 1.08 | Plan & Actual | Date |  | 0 | 0 | 0 | 400 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2646 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-12 23:59 | 2020-05-10 23:59 |  | 10 |  |  |  | 2020-04-17 17:40 | 2020-05-25 18:00 |  | 30 |  |  |  | 2020-04-23 17:40 | 2020-05-28 18:00 |  | 35 |  |  |  | 2020-04-30 23:59 | 2020-05-28 18:00 |  | 65 | 2020-07-08 17:20 |  |  | 2020-05-06 17:40 | 2020-06-18 18:00 |  | 80 | 2020-07-28 10:14 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-29 17:40 | 2020-06-18 18:00 |  | 100 | 2020-07-30 19:53 | [121 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 63 |  |  |  | 101077
367 | Task(Task)-->E (Engineering) | G.A OF PLUMMER BLOCKS FOR BELT FEEDER, TROUGH & PIPE CONVEYOR |  | 1.5.1.1 | Completed | No | No | 2020-06-28 23:59 | 2020-08-14 17:40 | 2020-06-09 09:00 | 2020-06-24 18:00 |  |  | 2020-02-21 14:04 | 2020-06-29 19:15 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1040 |  | 2020-02-13 10:27 | 7012-155-PVM-B-140 |  |  |  | I |  |  |  | 2.9178 | 0.002145 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 80 | 0 | 6.15 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2647 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-06-28 23:59 | 2020-06-15 18:00 |  | 10 |  |  |  | 2020-07-03 17:40 | 2020-06-30 18:00 |  | 30 |  |  |  | 2020-07-09 17:40 | 2020-07-03 18:00 |  | 35 |  |  |  | 2020-07-16 23:59 | 2020-07-03 18:00 |  | 65 | 2020-06-13 12:14 |  |  | 2020-07-22 17:40 | 2020-07-24 18:00 |  | 80 | 2020-06-25 08:23 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-08-14 17:40 | 2020-07-24 18:00 |  | 100 | 2020-06-29 19:16 | [121 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 70 |  |  |  | 101084
368 | Task(Task)-->E (Engineering) | G.A OF GEAR COUPLING FOR TROUGH CONVEYORS |  | 1.5.1.1 | Completed | No | No | 2020-04-20 18:00 | 2020-06-06 17:40 | 2020-06-15 09:00 | 2020-07-04 18:00 |  |  | 2020-02-21 14:04 | 2020-07-30 19:53 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1043 |  | 2020-02-13 10:27 | 7012-155-PVM-B-143 |  |  |  | I |  |  |  | 1.4589 | 0.001072 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 40 | 0 | 16.3 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2657 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-20 18:00 | 2020-05-18 18:00 |  | 10 | 2020-05-04 23:31 |  |  | 2020-04-27 17:40 | 2020-06-02 18:00 |  | 30 | 2020-05-23 23:31 |  |  | 2020-05-02 17:40 | 2020-06-05 18:00 |  | 35 | 2020-05-31 23:31 |  |  | 2020-05-08 23:59 | 2020-06-05 18:00 |  | 65 | 2020-07-06 12:27 |  |  | 2020-05-15 17:40 | 2020-06-26 18:00 |  | 80 | 2020-07-06 12:28 | [5 empty] | 80 | 2020-07-14 10:32 | [5 empty] | 80 | 2020-07-14 10:32 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-06 17:40 | 2020-06-26 18:00 |  | 100 | 2020-07-30 19:53 | [121 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 73 |  |  |  | 101087
369 | Task(Task)-->E (Engineering) | GA, DATA SHEET, TERMINAL BOX ARRANGEMET & CHARACTERISTICS CURVES OF HT MOTOR FOR CONVEYING SYSTEM |  | 1.5.1.1 | Unscheduled | No | No | 2020-03-27 17:40 | 2020-05-08 17:40 | 2020-05-31 23:59 | 2020-09-01 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-161 |  | 2020-02-13 11:46 | 7012-155-PVE-W-106 |  |  |  | A |  |  |  | 1.4589 | 0.001072 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2669 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-28 18:00 | 2020-05-31 23:59 |  | 10 |  |  |  | 2020-03-27 17:40 | 2020-06-07 23:59 |  | 30 |  |  |  | 2020-04-03 17:40 | 2020-06-12 18:00 |  | 35 |  |  |  | 2020-04-09 23:59 | 2020-06-12 18:00 |  | 65 |  |  |  | 2020-04-16 17:40 | 2020-07-03 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-08 17:40 | 2020-07-03 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 341 |  |  |  | 101352
370 | Task(Task)-->E (Engineering) | GA, DATA SHEET, BOM, WIRING AND TERMINAL DIAGRAM OF LOCAL CONTROL PANEL FOR SCOOP COUPLING |  | 1.5.1.1 | Unscheduled | No | No | 2020-04-04 17:40 | 2020-05-16 17:40 | 2020-05-20 18:00 | 2020-08-21 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-400 |  | 2020-02-13 11:47 | 7012-155-PVE-W-136 |  |  |  | A |  |  |  | 0.79576 | 0.000585 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2670 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-05 23:59 | 2020-05-20 18:00 |  | 10 |  |  |  | 2020-04-04 17:40 | 2020-05-27 18:00 |  | 30 |  |  |  | 2020-04-10 17:40 | 2020-06-01 18:00 |  | 35 |  |  |  | 2020-04-17 23:59 | 2020-06-01 18:00 |  | 65 | 2020-08-03 10:41 |  |  | 2020-04-23 17:40 | 2020-06-22 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-16 17:40 | 2020-06-22 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 371 |  |  |  | 101382
371 | Task(Task)-->E (Engineering) | G.A & MARKING OF CONV. SC 1A /B AND SC 2A/B |  | 1.5.1.1 | Unscheduled | No | No | 2019-11-18 18:00 | 2020-01-08 17:40 | 2020-01-27 18:00 | 2020-04-09 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-0019 |  | 2020-02-13 10:26 | 7012-155-PVM-B-019 |  |  |  | A |  |  |  | 8.6207 | 0.006337 | 0.65 | Plan & Actual | Date |  | 0 | 0 | 0 | 240 | 0 | 24.15 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2645 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-11-18 18:00 | 2020-01-27 18:00 |  | 10 | 2020-01-27 23:31 |  |  | 2019-11-30 17:40 | 2020-02-11 18:00 |  | 30 | 2020-02-11 23:31 |  |  | 2019-12-06 17:40 | 2020-02-13 18:00 |  | 35 | 2020-02-13 23:31 |  |  | 2019-12-12 23:59 | 2020-02-20 18:00 |  | 65 | 2020-02-20 23:31 |  |  | 2019-12-18 17:40 | 2020-03-19 18:00 |  | 80 | 2020-03-19 23:31 | [5 empty] | 80 | 2020-03-23 11:08 | [5 empty] | 80 | 2020-03-23 11:08 | [5 empty] | 80 | 2020-09-21 11:08 | [5 empty] | 80 | 2020-09-21 11:08 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-01-08 17:40 | 2020-04-09 18:00 |  | 100 | [122 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 19 |  |  |  | 101033
372 | Task(Task)-->E (Engineering) | GA OF BELT WEIGH SCALE |  | 1.5.1.1 | Completed | No | No | 2020-03-05 17:40 | 2020-04-16 17:40 | 2020-04-14 09:00 | 2020-05-08 18:00 |  |  | 2020-02-21 14:04 | 2020-06-29 19:15 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1023 |  | 2020-02-13 10:27 | 7012-155-PVM-B-123 |  |  |  | A |  |  |  | 1.4589 | 0.001072 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 40 | 0 | 3.3 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2666 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-08 23:59 | 2020-04-10 18:00 |  | 10 | 2020-04-10 23:31 |  |  | 2020-03-05 17:40 | 2020-04-17 18:00 |  | 30 | 2020-04-11 23:31 |  |  | 2020-03-11 17:40 | 2020-04-20 18:00 |  | 35 | 2020-04-14 23:31 |  |  | 2020-03-18 23:59 | 2020-04-20 18:00 |  | 65 | 2020-04-14 23:31 |  |  | 2020-03-24 17:40 | 2020-05-11 18:00 |  | 80 | 2020-05-08 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | 2020-06-09 12:33 | [5 empty] | 80 | 2020-06-22 18:45 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-16 17:40 | 2020-05-11 18:00 |  | 100 | 2020-06-01 23:31 | [121 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 53 |  |  |  | 101067
373 | Task(Task)-->E (Engineering) | GA OF SUSPENDED MAGNET |  | 1.5.1.1 | Completed | No | No | 2020-01-30 18:00 | 2020-03-25 17:40 | 2020-03-02 09:00 | 2020-04-11 18:00 |  |  | 2020-02-21 14:04 | 2020-06-19 22:44 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1031 |  | 2020-02-13 10:27 | 7012-155-PVM-B-131 |  |  |  | A |  |  |  | 5.7029 | 0.004192 | 0.43 | Plan & Actual | Date |  | 0 | 0 | 0 | 160 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2667 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-30 18:00 | 2020-02-06 18:00 |  | 10 | 2020-02-06 23:31 |  |  | 2020-02-13 17:40 | 2020-02-19 18:00 |  | 30 | 2020-02-19 23:31 |  |  | 2020-02-19 17:40 | 2020-02-24 18:00 |  | 35 | 2020-02-24 23:31 |  |  | 2020-02-26 23:59 | 2020-03-02 18:00 |  | 65 | 2020-03-02 23:31 |  |  | 2020-03-03 17:40 | 2020-03-20 18:00 |  | 80 | 2020-03-20 23:31 | [5 empty] | 80 | 2020-06-10 19:01 | [5 empty] | 80 | 2020-06-10 19:01 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-25 17:40 | 2020-04-25 18:00 |  | 100 | 2020-04-19 23:31 | [121 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 61 |  |  |  | 101075
374 | Task(Task)-->E (Engineering) | GA OF METAL DETECTOR |  | 1.5.1.1 | Completed | No | No | 2020-01-28 18:00 | 2020-03-20 17:40 | 2020-07-08 09:00 | 2020-07-24 18:00 |  |  | 2020-02-21 14:04 | 2020-07-30 19:52 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1032 |  | 2020-02-13 10:27 | 7012-155-PVM-B-132 |  |  |  | A |  |  |  | 5.7029 | 0.004192 | 0.43 | Plan & Actual | Date |  | 0 | 0 | 0 | 160 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2668 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-28 18:00 | 2020-05-14 18:00 |  | 10 | 2020-05-29 23:31 |  |  | 2020-02-07 17:40 | 2020-05-29 18:00 |  | 30 |  |  |  | 2020-02-14 17:40 | 2020-06-01 18:00 |  | 35 |  |  |  | 2020-02-20 23:59 | 2020-06-06 18:00 |  | 65 | 2020-07-08 17:20 |  |  | 2020-02-27 17:40 | 2020-06-27 18:00 |  | 80 | 2020-07-27 18:45 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-20 17:40 | 2020-06-27 18:00 |  | 100 | 2020-07-30 19:53 | [121 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 62 |  |  |  | 101076
375 | Task(Task)-->E (Engineering) | POWER AND TENSION CALCULATION FOR TROUGH BELT CONVEYORS (COMPUTERISED) |  | 1.5.1.1 | Completed | No | No | 2019-11-02 17:40 | 2019-12-11 17:40 | 2020-01-04 09:00 | 2020-02-25 18:00 |  |  | 2019-11-02 17:40 | 2020-03-04 10:30 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-CS-DC-0004 |  | 2020-02-13 10:26 | 7012-155-PVM-U-004 |  |  |  | A |  |  |  | 1.4589 | 0.001072 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2660 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-10-21 18:00 | 2019-12-11 18:00 |  | 10 | 2019-12-11 23:31 |  |  | 2019-11-02 17:40 | 2020-01-01 18:00 |  | 30 | 2020-01-01 23:31 |  |  | 2019-11-08 17:40 | 2020-01-04 18:00 |  | 35 | 2020-01-04 23:31 |  |  | 2019-11-14 23:59 | 2020-01-04 18:00 |  | 65 | 2020-01-04 23:31 |  |  | 2019-11-20 17:40 | 2020-02-17 18:00 |  | 80 | 2020-02-17 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2019-12-11 17:40 | 2020-02-25 18:00 |  | 100 | 2020-02-25 23:31 | [121 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 4 |  |  |  | 101018
376 | Task(Task)-->E (Engineering) | TYP. CROSS SECTION DETAILS OF TROUGH CONV. GALLERY |  | 1.5.1.1 | Unscheduled | No | No | 2019-10-02 18:00 | 2019-11-21 17:40 | 2019-10-20 23:59 | 2019-12-23 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-CS-GA-0005 |  | 2020-02-13 10:26 | 7012-155-PVM-B-005 |  |  |  | A |  |  |  | 4.244 | 0.00312 | 0.32 | Plan & Actual | Date |  | 0 | 0 | 0 | 120 | 0 | 10.15 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2648 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-10-02 18:00 | 2019-10-20 23:59 |  | 10 | 2019-10-20 23:31 |  |  | 2019-10-14 17:40 | 2019-11-04 18:00 |  | 30 | 2019-11-04 23:31 |  |  | 2019-10-19 17:40 | 2019-11-09 18:00 |  | 35 | 2019-11-09 23:31 |  |  | 2019-10-25 23:59 | 2019-11-12 18:00 |  | 65 | 2019-11-12 23:31 |  |  | 2019-10-31 17:40 | 2019-12-11 18:00 |  | 80 | 2019-12-11 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2019-11-21 17:40 | 2019-12-23 18:00 |  | 100 | [122 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 5 |  |  |  | 101019
377 | Task(Task)-->E (Engineering) | CIVIL | 1.5.1.2 | 1.5.1 | Completed | No | No | 2020-01-20 18:00 | 2020-06-02 17:40 | 2020-05-30 09:00 | 2020-07-15 18:00 |  |  | 2020-02-21 15:37 | 2020-07-15 20:57 |  |  | 100 | 100 | [15 empty] | 8.1538 | 0.011036 | 1.06 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No | 2671 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036079
378 | Task(Task)-->E (Engineering) | CONV. SC 1A/B : DESIGN CALCULATION OF SUPER STRUCTURE |  | 1.5.1.2 | Completed | No | No | 2020-01-20 18:00 | 2020-03-20 17:40 | 2020-05-31 | 2020-07-03 18:00 |  |  | 2020-07-03 22:30 | 2020-07-03 22:30 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0016 |  | 2020-02-13 11:42 | 7012-155-PVC-U-058 |  |  |  | A |  |  |  | 29.6296 | 0.00327 | 0.32 | Plan & Actual | Date |  | 0 | 0 | 0 | 117.35 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2672 | 1 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-20 18:00 | 2020-03-24 18:00 |  | 10 | 2020-03-24 23:31 |  |  | 2020-02-07 17:40 | 2020-04-28 18:00 |  | 30 | 2020-05-25 23:31 |  |  | 2020-02-14 17:40 | 2020-05-01 18:00 |  | 35 | 2020-05-28 23:31 |  |  | 2020-02-20 23:59 | 2020-05-08 18:00 |  | 65 | 2020-05-31 23:31 |  |  | 2020-02-27 17:40 | 2020-05-29 18:00 |  | 80 | 2020-07-03 22:23 | [5 empty] | 80 | 2020-07-03 22:31 | [5 empty] | 80 | 2020-07-03 22:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-20 17:40 | 2020-06-12 18:00 |  | 100 | 2020-07-03 22:27 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 159 |  |  |  | 101171
379 | Task(Task)-->E (Engineering) | CONV. SC 1A/B : DESIGN CALCULATION OF SUB STRUCTURE |  | 1.5.1.2 | Completed | No | No | 2020-02-19 18:00 | 2020-04-20 17:40 | 2020-07-02 09:00 | 2020-07-15 18:00 |  |  | 2020-02-21 15:37 | 2020-07-15 20:56 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0017 |  | 2020-02-13 11:42 | 7012-155-PVC-U-059 |  |  |  | A |  |  |  | 10.1852 | 0.001124 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 38.49 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2673 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-19 18:00 | 2020-04-23 18:00 |  | 10 | 2020-04-23 23:31 |  |  | 2020-03-09 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-03-16 17:40 | 2020-05-31 23:59 |  | 35 |  |  |  | 2020-03-21 23:59 | 2020-06-07 23:59 |  | 65 | 2020-07-15 20:47 |  |  | 2020-03-27 17:40 | 2020-06-28 23:59 |  | 80 | 2020-07-15 20:55 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-20 17:40 | 2020-07-12 23:59 |  | 100 | 2020-07-15 20:57 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 160 |  |  |  | 101172
380 | Task(Task)-->E (Engineering) | CONV. SC 1A/B : NUM & RC DETAILS OF FDN |  | 1.5.1.2 | Completed | No | No | 2020-02-19 18:00 | 2020-04-20 17:40 | 2020-07-02 09:00 | 2020-07-15 18:00 |  |  | 2020-02-21 15:37 | 2020-07-15 20:57 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-NR-0021 |  | 2020-02-13 11:42 | 7012-155-PVC-C-061 |  |  |  | A |  |  |  | 10.1852 | 0.001124 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 38.49 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2676 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-19 18:00 | 2020-04-23 18:00 |  | 10 | 2020-04-23 23:31 |  |  | 2020-03-09 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-03-16 17:40 | 2020-05-31 23:59 |  | 35 |  |  |  | 2020-03-21 23:59 | 2020-06-07 23:59 |  | 65 | 2020-07-15 20:49 |  |  | 2020-03-27 17:40 | 2020-06-28 23:59 |  | 80 | 2020-07-15 20:55 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-20 17:40 | 2020-07-12 23:59 |  | 100 | 2020-07-15 20:58 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 162 |  |  |  | 101174
381 | Task(Task)-->E (Engineering) | CONV. SC 2A/B : DESIGN CALCULATION OF SUPER STRUCTURE |  | 1.5.1.2 | Completed | No | No | 2020-03-23 17:40 | 2020-05-04 17:40 | 2020-05-30 09:00 | 2020-06-16 18:00 |  |  | 2020-02-21 15:37 | 2020-06-16 22:21 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0018 |  | 2020-02-13 11:42 | 7012-155-PVC-U-062 |  |  |  | A |  |  |  | 29.6296 | 0.00327 | 0.32 | Plan & Actual | Date |  | 0 | 0 | 0 | 117.35 | 0 | 56 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2674 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-04 18:00 | 2020-03-24 18:00 |  | 10 | 2020-03-24 23:31 |  |  | 2020-03-23 17:40 | 2020-04-28 18:00 |  | 30 | 2020-05-25 23:31 |  |  | 2020-03-30 17:40 | 2020-05-01 18:00 |  | 35 | 2020-05-28 23:31 |  |  | 2020-04-04 23:59 | 2020-05-08 18:00 |  | 65 | 2020-05-30 23:31 |  |  | 2020-04-10 17:40 | 2020-05-29 18:00 |  | 80 | 2020-06-16 22:19 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-04 17:40 | 2020-06-12 18:00 |  | 100 | 2020-06-16 22:22 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 163 |  |  |  | 101175
382 | Task(Task)-->E (Engineering) | CONV. SC 2A/B : DESIGN CALCULATION OF SUB STRUCTURE |  | 1.5.1.2 | Completed | No | No | 2020-04-03 18:00 | 2020-06-02 17:40 | 2020-06-30 09:00 | 2020-07-13 18:00 |  |  | 2020-02-21 15:37 | 2020-07-13 23:03 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0019 |  | 2020-02-13 11:42 | 7012-155-PVC-U-063 |  |  |  | A |  |  |  | 10.1852 | 0.001124 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 38.49 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2675 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-03 18:00 | 2020-04-23 18:00 |  | 10 | 2020-04-23 23:31 |  |  | 2020-04-21 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-04-28 17:40 | 2020-05-31 23:59 |  | 35 |  |  |  | 2020-05-04 23:59 | 2020-06-07 23:59 |  | 65 | 2020-07-13 22:53 |  |  | 2020-05-11 17:40 | 2020-06-28 23:59 |  | 80 | 2020-07-13 23:01 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-02 17:40 | 2020-07-12 23:59 |  | 100 | 2020-07-13 23:04 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 164 |  |  |  | 101176
383 | Task(Task)-->E (Engineering) | CONV. SC 2A/B : NUM & RC DETAILS OF FDN |  | 1.5.1.2 | Completed | No | No | 2020-04-03 18:00 | 2020-06-02 17:40 | 2020-07-01 09:00 | 2020-07-13 18:00 |  |  | 2020-02-21 15:37 | 2020-07-13 23:04 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-NR-0022 |  | 2020-02-13 11:42 | 7012-155-PVC-C-065 |  |  |  | A |  |  |  | 10.1852 | 0.001124 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 38.49 | 0 | 5.15 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2677 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-03 18:00 | 2020-04-23 18:00 |  | 10 | 2020-04-23 23:31 |  |  | 2020-04-21 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-04-28 17:40 | 2020-05-31 23:59 |  | 35 | 2020-07-01 20:59 |  |  | 2020-05-04 23:59 | 2020-06-07 23:59 |  | 65 | 2020-07-13 22:54 |  |  | 2020-05-11 17:40 | 2020-06-28 23:59 |  | 80 | 2020-07-13 23:00 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-02 17:40 | 2020-07-12 23:59 |  | 100 | 2020-07-13 23:05 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 166 |  |  |  | 101178
384 | Task(Task)-->E (Engineering) | STRUCTURAL | 1.5.1.3 | 1.5.1 | Completed | No | No | 2020-01-20 18:00 | 2020-05-04 17:40 | 2020-05-30 09:00 | 2020-07-03 18:00 |  |  | 2020-02-21 15:37 | 2020-07-03 22:31 |  |  | 100 | 100 | [15 empty] | 4.9231 | 0.006663 | 0.64 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No | 2678 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036080
385 | Task(Task)-->E (Engineering) | CONV. SC 1A/B : STRUCTURAL GA |  | 1.5.1.3 | Completed | No | No | 2020-01-20 18:00 | 2020-03-20 17:40 | 2020-05-31 | 2020-07-03 18:00 |  |  | 2020-07-03 22:31 | 2020-07-03 22:31 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-GA-0019 |  | 2020-02-13 11:42 | 7012-155-PVC-B-060 |  |  |  | A |  |  |  | 50 | 0.003332 | 0.32 | Plan & Actual | Date |  | 0 | 0 | 0 | 117.35 | 0 | 176.3 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2679 | 1 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-20 18:00 | 2020-03-24 18:00 |  | 10 | 2020-03-24 23:31 |  |  | 2020-02-07 17:40 | 2020-04-28 18:00 |  | 30 | 2020-05-25 23:31 |  |  | 2020-02-14 17:40 | 2020-05-01 18:00 |  | 35 | 2020-05-28 23:31 |  |  | 2020-02-20 23:59 | 2020-05-08 18:00 |  | 65 | 2020-05-31 23:31 |  |  | 2020-02-27 17:40 | 2020-05-29 18:00 |  | 80 | 2020-07-03 22:22 | [5 empty] | 80 | 2020-07-03 22:32 | [5 empty] | 80 | 2020-07-03 22:32 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-20 17:40 | 2020-06-12 18:00 |  | 100 | 2020-07-03 22:26 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 161 |  |  |  | 101173
386 | Task(Task)-->E (Engineering) | CONV. SC 2A/B : STRUCTURAL GA |  | 1.5.1.3 | Completed | No | No | 2020-03-23 17:40 | 2020-05-04 17:40 | 2020-05-30 09:00 | 2020-06-16 18:00 |  |  | 2020-02-21 15:37 | 2020-06-16 22:20 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-GA-0020 |  | 2020-02-13 11:42 | 7012-155-PVC-B-064 |  |  |  | A |  |  |  | 50 | 0.003332 | 0.32 | Plan & Actual | Date |  | 0 | 0 | 0 | 117.35 | 0 | 56 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2680 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-04 18:00 | 2020-03-24 18:00 |  | 10 | 2020-03-24 23:31 |  |  | 2020-03-23 17:40 | 2020-04-28 18:00 |  | 30 | 2020-05-25 23:31 |  |  | 2020-03-30 17:40 | 2020-05-01 18:00 |  | 35 | 2020-05-28 23:31 |  |  | 2020-04-04 23:59 | 2020-05-08 18:00 |  | 65 | 2020-05-30 23:31 |  |  | 2020-04-10 17:40 | 2020-05-29 18:00 |  | 80 | 2020-06-16 22:18 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-04 17:40 | 2020-06-12 18:00 |  | 100 | 2020-06-16 22:21 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 165 |  |  |  | 101177
387 | Task(Task)-->E (Engineering) | ELECTRICAL | 1.5.1.4 | 1.5.1 | Work In Progress | No | No | 2020-02-11 17:40 | 2020-06-23 17:40 | 2020-03-02 09:00 | 2020-07-01 18:00 |  |  | 2020-02-24 17:40 |  |  |  | 100 | 80.5188 | [15 empty] | 32.6154 | 0.044144 | 4.24 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No | 2683 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036081
388 | Task(Task)-->E (Engineering) | LIGHTING LAYOUT PLAN WITH POWER DISTRIBUTION ARRANGEMENT, SECTIONAL VIEW, BOM OF CONVEYOR CONV. SC 1A /B |  | 1.5.1.4 | Unscheduled | No | No | 2020-05-01 18:00 | 2020-06-20 17:40 | 2020-04-17 09:00 | 2020-06-14 23:59 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5079 |  | 2020-02-13 11:45 | 7012-155-PVE-G-041 |  |  |  | A |  |  |  | 47.4057 | 0.020927 | 2.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 746.44 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2684 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-05-01 18:00 | 2020-05-03 23:59 |  | 10 | 2020-04-11 23:31 |  |  | 2020-05-11 17:40 | 2020-05-10 23:59 |  | 30 | 2020-04-15 23:31 |  |  | 2020-05-16 17:40 | 2020-05-17 23:59 |  | 35 | 2020-04-17 23:31 |  |  | 2020-05-22 23:59 | 2020-05-24 23:59 |  | 65 | 2020-04-17 23:31 |  |  | 2020-05-29 17:40 | 2020-06-14 23:59 |  | 80 | 2020-04-23 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-20 17:40 | 2020-06-14 23:59 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 276 |  |  |  | 101287
389 | Task(Task)-->E (Engineering) | LIGHTING LAYOUT PLAN WITH POWER DISTRIBUTION ARRANGEMENT, SECTIONAL VIEW, BOM OF CONVEYOR CONV. SC 2A/B |  | 1.5.1.4 | Unscheduled | No | No | 2020-05-05 18:00 | 2020-06-23 17:40 | 2020-04-17 09:00 | 2020-06-18 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5080 |  | 2020-02-13 11:45 | 7012-155-PVE-G-042 |  |  |  | A |  |  |  | 47.4057 | 0.020927 | 2.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 746.44 | 0 | 24.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2685 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-05-05 18:00 | 2020-05-07 18:00 |  | 10 | 2020-04-12 23:31 |  |  | 2020-05-13 17:40 | 2020-05-14 18:00 |  | 30 | 2020-04-14 23:31 |  |  | 2020-05-19 17:40 | 2020-05-21 18:00 |  | 35 | 2020-04-17 23:31 |  |  | 2020-05-26 23:59 | 2020-05-28 18:00 |  | 65 | 2020-04-17 23:31 |  |  | 2020-06-01 17:40 | 2020-06-18 18:00 |  | 80 | 2020-04-23 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-23 17:40 | 2020-06-18 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 277 |  |  |  | 101288
390 | Task(Task)-->E (Engineering) | GA,SLD,WIRING & BOM OF SUSPENDED MAGNET |  | 1.5.1.4 | Completed | No | No | 2020-02-24 17:40 | 2020-04-04 17:40 | 2020-03-02 09:00 | 2020-04-02 18:00 |  |  | 2020-02-24 17:40 | 2020-04-18 12:40 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-402 |  | 2020-02-13 11:47 | 7012-155-PVE-W-138 |  |  |  | A |  |  |  | 2.5943 | 0.001145 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2686 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-22 18:00 | 2020-02-22 18:00 |  | 10 | 2020-02-22 23:31 |  |  | 2020-02-24 17:40 | 2020-02-29 18:00 |  | 30 | 2020-02-29 23:31 |  |  | 2020-02-29 17:40 | 2020-03-02 18:00 |  | 35 | 2020-03-02 23:31 |  |  | 2020-03-06 23:59 | 2020-03-02 18:00 |  | 65 | 2020-03-02 23:31 |  |  | 2020-03-12 17:40 | 2020-03-17 18:00 |  | 80 | 2020-03-17 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-04 17:40 | 2020-04-09 18:00 |  | 100 | 2020-04-09 23:31 | [121 empty] | Varun Parihari | [21 empty] | 373 |  |  |  | 101384
391 | Task(Task)-->E (Engineering) | GA,SLD,WIRING & BOM OF METAL DETECTOR |  | 1.5.1.4 | Unscheduled | No | No | 2020-02-11 17:40 | 2020-03-23 17:40 | 2020-05-14 18:00 | 2020-07-01 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-403 |  | 2020-02-13 11:47 | 7012-155-PVE-W-139 |  |  |  | A |  |  |  | 2.5943 | 0.001145 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2687 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-13 18:00 | 2020-05-14 18:00 |  | 10 |  |  |  | 2020-02-11 17:40 | 2020-05-21 18:00 |  | 30 |  |  |  | 2020-02-17 17:40 | 2020-05-25 18:00 |  | 35 |  |  |  | 2020-02-24 23:59 | 2020-05-25 18:00 |  | 65 | 2020-07-28 15:44 |  |  | 2020-02-29 17:40 | 2020-06-15 18:00 |  | 80 | 2020-07-28 17:46 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-23 17:40 | 2020-06-15 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 374 |  |  |  | 101385
392 | Task(Task)-->P (Procurement) | PROCUREMENT | 1.5.2 | 1.5 | Work In Progress | No | No | 2019-09-27 09:00 | 2021-02-13 18:00 | 2019-09-27 09:00 | 2021-05-13 18:00 |  |  | 2019-09-27 10:57 |  |  |  | 90.2357 | 40.6629 | [15 empty] | 69.6042 | 1.5003 | 147.54 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2688 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018009
393 | Task(Task)-->P (Procurement) | PURCHASE REQUISITION | 1.5.2.1 | 1.5.2 | Work In Progress | No | No | 2019-09-27 09:00 | 2020-05-19 18:00 | 2019-09-27 09:00 | 2020-05-29 18:00 |  |  | 2019-09-27 10:57 |  |  |  | 100 | 99.8654 | [15 empty] | 5.002 | 0.075047 | 7.38 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2689 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018010
394 | Task(Task)-->P (Procurement) | Suspended Magnet |  | 1.5.2.1 | Completed | No | No | 2019-09-27 09:00 | 2019-09-27 18:00 | 2019-09-27 09:00 | 2019-09-27 18:00 |  |  | 2019-09-27 10:57 | 2019-09-27 10:57 |  |  | 100 | 100 | [15 empty] | 10.4054 | 0.007809 | 0.77 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2690 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018011
395 | Task(Task)-->P (Procurement) | Belt Scale |  | 1.5.2.1 | Completed | No | No | 2019-09-27 09:00 | 2019-09-27 18:00 | 2019-09-27 09:00 | 2019-09-27 18:00 |  |  | 2019-09-27 14:37 | 2019-09-27 14:37 |  |  | 100 | 100 | [15 empty] | 2.027 | 0.001521 | 0.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2691 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018012
396 | Task(Task)-->P (Procurement) | Metal Detector |  | 1.5.2.1 | Completed | No | No | 2019-09-27 09:00 | 2019-09-27 18:00 | 2019-09-27 09:00 | 2019-09-27 18:00 |  |  | 2019-09-27 10:57 | 2019-09-27 10:57 |  |  | 100 | 100 | [15 empty] | 2.027 | 0.001521 | 0.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2692 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018013
397 | Task(Task)-->P (Procurement) | Pulley |  | 1.5.2.1 | Completed | No | No | 2019-09-27 09:00 | 2019-09-27 18:00 | 2020-02-05 09:00 | 2020-02-05 18:00 |  |  | 2020-02-05 16:16 | 2020-02-05 16:16 |  |  | 100 | 100 | [15 empty] | 12.027 | 0.009026 | 0.89 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2693 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018014
398 | Task(Task)-->P (Procurement) | Idler |  | 1.5.2.1 | Completed | No | No | 2019-12-19 09:00 | 2019-12-19 18:00 | 2020-02-13 09:00 | 2020-02-13 18:00 |  |  | 2020-02-13 15:44 | 2020-02-13 15:44 |  |  | 100 | 100 | [15 empty] | 8.5135 | 0.006389 | 0.63 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2694 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018015
399 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.5.2.1 | Completed | No | No | 2020-05-17 | 2020-05-17 23:59 | 2020-02-10 09:00 | 2020-02-10 18:00 |  |  | 2020-02-10 09:26 | 2020-02-10 09:26 |  |  | 100 | 100 | [15 empty] | 0.94595 | 0.00071 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2695 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018016
400 | Task(Task)-->P (Procurement) | Bearing |  | 1.5.2.1 | Completed | No | No | 2020-05-17 | 2020-05-17 23:59 | 2020-02-10 09:00 | 2020-02-10 18:00 |  |  | 2020-02-10 09:36 | 2020-02-10 09:36 |  |  | 100 | 100 | [15 empty] | 1.4865 | 0.001116 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2696 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018017
401 | Task(Task)-->P (Procurement) | Belting |  | 1.5.2.1 | Completed | No | No | 2019-11-07 09:00 | 2019-11-07 18:00 | 2020-01-20 09:00 | 2020-01-20 18:00 |  |  | 2020-01-20 15:54 | 2020-01-20 15:54 |  |  | 100 | 100 | [15 empty] | 8.7838 | 0.006592 | 0.65 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2697 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018018
402 | Task(Task)-->P (Procurement) | Scrapper |  | 1.5.2.1 | Completed | No | No | 2019-11-17 | 2019-11-17 23:59 | 2020-03-11 09:00 | 2020-03-11 18:00 |  |  | 2020-03-11 10:57 | 2020-03-11 10:57 |  |  | 100 | 100 | [15 empty] | 0.54054 | 0.000406 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2698 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018019
403 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.5.2.1 | Completed | No | No | 2020-03-10 09:00 | 2020-03-10 18:00 | 2020-03-11 09:00 | 2020-03-11 18:00 |  |  | 2020-03-11 12:41 | 2020-03-11 12:41 |  |  | 100 | 100 | [15 empty] | 2.5676 | 0.001927 | 0.19 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2699 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018020
404 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.5.2.1 | Completed | No | No | 2020-05-19 09:00 | 2020-05-19 18:00 | 2020-04-16 09:00 | 2020-04-16 18:00 |  |  | 2020-04-16 10:57 | 2020-04-16 10:57 |  |  | 100 | 100 | [15 empty] | 0.13514 | 0.000101 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2700 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018021
405 | Task(Task)-->P (Procurement) | Gear Box |  | 1.5.2.1 | Completed | No | No | 2019-11-13 09:00 | 2019-11-13 18:00 | 2020-01-20 09:00 | 2020-01-20 18:00 |  |  | 2020-01-20 11:17 | 2020-01-20 11:17 |  |  | 100 | 100 | [15 empty] | 2.7027 | 0.002028 | 0.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2701 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018022
406 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.5.2.1 | Completed | No | No | 2019-11-21 09:00 | 2019-11-21 18:00 | 2020-01-22 09:00 | 2020-01-22 18:00 |  |  | 2020-01-22 10:41 | 2020-01-22 10:41 |  |  | 100 | 100 | [15 empty] | 0.40541 | 0.000304 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2702 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018023
407 | Task(Task)-->P (Procurement) | Fluid Coupling |  | 1.5.2.1 | Completed | No | No | 2019-11-25 09:00 | 2019-11-25 18:00 | 2020-01-22 09:00 | 2020-01-22 18:00 |  |  | 2020-01-22 09:54 | 2020-01-22 09:54 |  |  | 100 | 100 | [15 empty] | 2.8378 | 0.00213 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2703 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018024
408 | Task(Task)-->P (Procurement) | Brake |  | 1.5.2.1 | Completed | No | No | 2019-12-18 09:00 | 2019-12-18 18:00 | 2020-04-04 09:00 | 2020-04-04 18:00 |  |  | 2020-04-04 11:33 | 2020-04-04 11:33 |  |  | 100 | 100 | [15 empty] | 0.27027 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2704 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018025
409 | Task(Task)-->P (Procurement) | Building Structure |  | 1.5.2.1 | Completed | No | No | 2020-04-04 09:00 | 2020-04-04 18:00 | 2020-05-29 09:00 | 2020-05-29 18:00 |  |  | 2020-05-31 18:44 | 2020-05-31 18:44 |  |  | 100 | 100 | [15 empty] | 29.7297 | 0.022311 | 2.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2705 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018026
410 | Task(Task)-->P (Procurement) | HT AC MOTORS |  | 1.5.2.1 | Completed | No | No | 2020-01-07 09:00 | 2020-01-07 18:00 | 2020-01-17 09:00 | 2020-01-17 18:00 |  |  | 2020-01-17 10:57 | 2020-01-17 10:57 |  |  | 100 | 100 | [15 empty] | 7.8378 | 0.005882 | 0.58 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2706 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018027
411 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.5.2.1 | Completed | No | No | 2020-03-10 09:00 | 2020-03-10 18:00 | 2020-03-16 09:00 | 2020-03-16 18:00 |  |  | 2020-03-16 10:57 | 2020-03-16 10:57 |  |  | 100 | 100 | [15 empty] | 3.6486 | 0.002738 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2707 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018028
412 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.5.2.1 | Completed | No | No | 2020-03-27 09:00 | 2020-03-27 18:00 | 2020-04-30 09:00 | 2020-04-30 18:00 |  |  | 2020-04-30 10:57 | 2020-04-30 10:57 |  |  | 100 | 100 | [15 empty] | 1.6216 | 0.001217 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2708 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018029
413 | Task(Task)-->P (Procurement) | LPBS |  | 1.5.2.1 | Unscheduled | No | No | 2020-03-20 09:00 | 2020-03-20 18:00 | 2020-04-14 09:00 | 2020-04-14 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.13514 | 0.000101 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2709 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018030
414 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.5.2.1 | Completed | No | No | 2020-01-08 09:00 | 2020-01-08 18:00 | 2020-01-08 09:00 | 2020-01-08 18:00 |  |  | 2020-01-08 10:57 | 2020-01-08 10:57 |  |  | 100 | 100 | [15 empty] | 1.3514 | 0.001014 | 0.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2711 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018031
415 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.5.2.1 | Completed | No | No | 2019-12-30 09:00 | 2019-12-30 18:00 | 2019-12-30 09:00 | 2019-12-30 18:00 |  |  | 2019-12-30 10:57 | 2019-12-30 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2712 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018032
416 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.5.2.1 | Completed | No | No | 2020-01-03 09:00 | 2020-01-03 18:00 | 2020-01-03 09:00 | 2020-01-03 18:00 |  |  | 2020-01-03 10:57 | 2020-01-03 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2713 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018033
417 | Task(Task)-->P (Procurement) | TECHNICAL CLEARANCE | 1.5.2.2 | 1.5.2 | Work In Progress | No | No | 2019-09-28 09:00 | 2020-06-18 18:00 | 2019-09-27 09:00 | 2020-06-12 18:00 |  |  | 2019-09-30 14:37 |  |  |  | 100 | 99.8654 | [15 empty] | 5.002 | 0.075047 | 7.38 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2714 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018034
418 | Task(Task)-->P (Procurement) | Suspended Magnet |  | 1.5.2.2 | Completed | No | No | 2019-09-28 09:00 | 2020-01-07 18:00 | 2019-09-27 09:00 | 2019-12-04 18:00 |  |  | 2019-12-04 10:57 | 2019-12-04 10:57 |  |  | 100 | 100 | [15 empty] | 10.4054 | 0.007809 | 0.77 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2715 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018035
419 | Task(Task)-->P (Procurement) | Belt Scale |  | 1.5.2.2 | Completed | No | No | 2019-09-28 09:00 | 2020-02-02 23:59 | 2019-09-27 09:00 | 2019-12-17 18:00 |  |  | 2019-09-30 14:37 | 2019-12-17 14:38 |  |  | 100 | 100 | [15 empty] | 2.027 | 0.001521 | 0.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2716 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018036
420 | Task(Task)-->P (Procurement) | Metal Detector |  | 1.5.2.2 | Completed | No | No | 2019-09-28 09:00 | 2020-01-06 18:00 | 2019-09-27 09:00 | 2019-12-27 18:00 |  |  | 2019-12-27 10:57 | 2019-12-27 10:57 |  |  | 100 | 100 | [15 empty] | 2.027 | 0.001521 | 0.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2717 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018037
421 | Task(Task)-->P (Procurement) | Pulley |  | 1.5.2.2 | Completed | No | No | 2019-09-28 09:00 | 2020-01-04 18:00 | 2020-02-05 09:00 | 2020-02-10 18:00 |  |  | 2020-02-06 16:19 | 2020-02-10 16:19 |  |  | 100 | 100 | [15 empty] | 12.027 | 0.009026 | 0.89 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2718 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018038
422 | Task(Task)-->P (Procurement) | Idler |  | 1.5.2.2 | Completed | No | No | 2019-12-20 09:00 | 2020-02-01 18:00 | 2020-02-13 09:00 | 2020-03-26 18:00 |  |  | 2020-02-14 10:57 | 2020-03-26 10:57 |  |  | 100 | 100 | [15 empty] | 8.5135 | 0.006389 | 0.63 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2719 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018039
423 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.5.2.2 | Completed | No | No | 2020-05-18 09:00 | 2020-06-01 18:00 | 2020-02-10 09:00 | 2020-02-10 18:00 |  |  | 2020-02-10 09:28 | 2020-02-10 09:28 |  |  | 100 | 100 | [15 empty] | 0.94595 | 0.00071 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2720 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018040
424 | Task(Task)-->P (Procurement) | Bearing |  | 1.5.2.2 | Completed | No | No | 2020-05-18 09:00 | 2020-06-16 18:00 | 2020-02-10 09:00 | 2020-02-10 18:00 |  |  | 2020-02-10 09:37 | 2020-02-10 09:37 |  |  | 100 | 100 | [15 empty] | 1.4865 | 0.001116 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2721 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018041
425 | Task(Task)-->P (Procurement) | Belting |  | 1.5.2.2 | Completed | No | No | 2019-11-08 09:00 | 2020-01-06 18:00 | 2020-01-20 09:00 | 2020-05-16 18:00 |  |  | 2020-05-16 10:57 | 2020-05-16 10:57 |  |  | 100 | 100 | [15 empty] | 8.7838 | 0.006592 | 0.65 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2722 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018042
426 | Task(Task)-->P (Procurement) | Scrapper |  | 1.5.2.2 | Completed | No | No | 2019-11-18 09:00 | 2020-03-16 18:00 | 2020-03-11 09:00 | 2020-03-26 18:00 |  |  | 2020-03-26 10:57 | 2020-03-26 10:57 |  |  | 100 | 100 | [15 empty] | 0.54054 | 0.000406 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2723 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018043
427 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.5.2.2 | Completed | No | No | 2020-03-11 09:00 | 2020-03-20 18:00 | 2020-03-11 09:00 | 2020-03-17 18:00 |  |  | 2020-03-12 12:43 | 2020-03-17 12:43 |  |  | 100 | 100 | [15 empty] | 2.5676 | 0.001927 | 0.19 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2724 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018044
428 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.5.2.2 | Completed | No | No | 2020-05-20 09:00 | 2020-06-18 18:00 | 2020-04-16 09:00 | 2020-04-16 18:00 |  |  | 2020-04-16 10:57 | 2020-04-16 10:57 |  |  | 100 | 100 | [15 empty] | 0.13514 | 0.000101 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2725 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018045
429 | Task(Task)-->P (Procurement) | Gear Box |  | 1.5.2.2 | Completed | No | No | 2019-11-14 09:00 | 2020-02-26 18:00 | 2020-01-20 09:00 | 2020-03-20 18:00 |  |  | 2020-01-22 11:19 | 2020-03-20 11:19 |  |  | 100 | 100 | [15 empty] | 2.7027 | 0.002028 | 0.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2726 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018046
430 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.5.2.2 | Completed | No | No | 2019-11-22 09:00 | 2020-03-19 18:00 | 2020-01-22 09:00 | 2020-04-13 18:00 |  |  | 2020-04-13 10:46 | 2020-04-13 10:46 |  |  | 100 | 100 | [15 empty] | 0.40541 | 0.000304 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2727 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018047
431 | Task(Task)-->P (Procurement) | Fluid Coupling |  | 1.5.2.2 | Completed | No | No | 2019-11-26 09:00 | 2020-03-01 23:59 | 2020-01-22 09:00 | 2020-04-13 18:00 |  |  | 2020-01-23 09:54 | 2020-04-13 09:54 |  |  | 100 | 100 | [15 empty] | 2.8378 | 0.00213 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2728 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018048
432 | Task(Task)-->P (Procurement) | Brake |  | 1.5.2.2 | Completed | No | No | 2019-12-19 09:00 | 2020-03-09 18:00 | 2020-04-04 09:00 | 2020-04-22 18:00 |  |  | 2020-04-05 11:34 | 2020-04-22 11:34 |  |  | 100 | 100 | [15 empty] | 0.27027 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2729 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018049
433 | Task(Task)-->P (Procurement) | Building Structure |  | 1.5.2.2 | Completed | No | No | 2020-04-05 | 2020-04-11 18:00 | 2020-05-29 09:00 | 2020-05-29 18:00 |  |  | 2020-05-29 17:31 | 2020-05-29 17:31 |  |  | 100 | 100 | [15 empty] | 29.7297 | 0.022311 | 2.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2730 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018050
434 | Task(Task)-->P (Procurement) | HT AC MOTORS |  | 1.5.2.2 | Completed | No | No | 2020-01-08 09:00 | 2020-02-06 18:00 | 2020-01-17 09:00 | 2020-04-11 18:00 |  |  | 2020-04-11 10:57 | 2020-04-11 10:57 |  |  | 100 | 100 | [15 empty] | 7.8378 | 0.005882 | 0.58 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2731 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018051
435 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.5.2.2 | Completed | No | No | 2020-03-11 09:00 | 2020-03-25 18:00 | 2020-03-16 09:00 | 2020-06-02 18:00 |  |  | 2020-06-02 10:57 | 2020-06-02 10:57 |  |  | 100 | 100 | [15 empty] | 3.6486 | 0.002738 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2732 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018052
436 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.5.2.2 | Completed | No | No | 2020-03-28 09:00 | 2020-05-11 18:00 | 2020-04-30 09:00 | 2020-06-03 18:00 |  |  | 2020-06-03 10:57 | 2020-06-03 10:57 |  |  | 100 | 100 | [15 empty] | 1.6216 | 0.001217 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2733 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018053
437 | Task(Task)-->P (Procurement) | LPBS |  | 1.5.2.2 | Unscheduled | No | No | 2020-03-21 09:00 | 2020-04-04 18:00 | 2020-04-14 09:00 | 2020-06-12 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.13514 | 0.000101 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2734 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018054
438 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.5.2.2 | Completed | No | No | 2020-01-09 09:00 | 2020-01-22 18:00 | 2020-01-08 09:00 | 2020-03-10 18:00 |  |  | 2020-03-10 10:57 | 2020-03-10 10:57 |  |  | 100 | 100 | [15 empty] | 1.3514 | 0.001014 | 0.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2736 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018055
439 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.5.2.2 | Completed | No | No | 2019-12-31 09:00 | 2020-01-16 18:00 | 2019-12-30 09:00 | 2020-03-07 18:00 |  |  | 2020-03-07 10:57 | 2020-03-07 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2737 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018056
440 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.5.2.2 | Completed | No | No | 2020-01-04 09:00 | 2020-01-18 18:00 | 2020-01-03 09:00 | 2020-01-16 18:00 |  |  | 2020-01-16 10:57 | 2020-01-16 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2738 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018057
441 | Task(Task)-->P (Procurement) | ORDERING | 1.5.2.3 | 1.5.2 | Work In Progress | No | No | 2020-01-05 | 2020-07-18 18:00 | 2019-12-04 09:00 | 2020-09-04 18:00 |  |  | 2020-01-05 08:00 |  |  |  | 100 | 98.4406 | [15 empty] | 9.9973 | 0.14999 | 14.75 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2739 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018058
442 | Task(Task)-->P (Procurement) | Suspended Magnet |  | 1.5.2.3 | Completed | No | No | 2020-01-08 09:00 | 2020-02-06 18:00 | 2019-12-04 09:00 | 2020-02-03 18:00 |  |  | 2020-02-03 10:57 | 2020-02-03 10:57 |  |  | 100 | 100 | [15 empty] | 10.4407 | 0.01566 | 1.54 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2740 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018059
443 | Task(Task)-->P (Procurement) | Belt Scale |  | 1.5.2.3 | Completed | No | No | 2020-02-03 09:00 | 2020-03-03 18:00 | 2019-12-17 09:00 | 2020-02-03 18:00 |  |  | 2020-02-03 08:00 | 2020-02-03 16:05 |  |  | 100 | 100 | [15 empty] | 2.0339 | 0.003051 | 0.3 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2741 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018060
444 | Task(Task)-->P (Procurement) | Metal Detector |  | 1.5.2.3 | Completed | No | No | 2020-01-07 09:00 | 2020-02-05 18:00 | 2019-12-27 09:00 | 2020-03-20 18:00 |  |  | 2020-03-20 10:57 | 2020-03-20 10:57 |  |  | 100 | 100 | [15 empty] | 2.0339 | 0.003051 | 0.3 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2742 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018061
445 | Task(Task)-->P (Procurement) | Pulley |  | 1.5.2.3 | Completed | No | No | 2020-01-05 | 2020-02-03 18:00 | 2020-02-10 09:00 | 2020-03-21 18:00 |  |  | 2020-01-05 08:00 | 2020-03-21 16:05 |  |  | 100 | 100 | [15 empty] | 12.0678 | 0.018101 | 1.78 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2743 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018062
446 | Task(Task)-->P (Procurement) | Idler |  | 1.5.2.3 | Completed | No | No | 2020-02-02 | 2020-03-02 18:00 | 2020-03-26 09:00 | 2020-04-30 18:00 |  |  | 2020-02-02 08:00 | 2020-04-29 16:05 |  |  | 100 | 100 | [15 empty] | 8.4746 | 0.012711 | 1.25 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2744 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018063
447 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.5.2.3 | Completed | No | No | 2020-06-02 09:00 | 2020-07-01 18:00 | 2020-02-10 09:00 | 2020-03-24 18:00 |  |  | 2020-02-11 09:32 | 2020-03-24 09:32 |  |  | 100 | 100 | [15 empty] | 0.88136 | 0.001322 | 0.13 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2745 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018064
448 | Task(Task)-->P (Procurement) | Bearing |  | 1.5.2.3 | Completed | No | No | 2020-06-17 09:00 | 2020-07-16 18:00 | 2020-02-10 09:00 | 2020-03-24 18:00 |  |  | 2020-02-11 09:40 | 2020-03-24 09:40 |  |  | 100 | 100 | [15 empty] | 1.4915 | 0.002237 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2746 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018065
449 | Task(Task)-->P (Procurement) | Belting |  | 1.5.2.3 | Completed | No | No | 2020-01-07 09:00 | 2020-02-20 18:00 | 2020-05-16 09:00 | 2020-09-04 18:00 |  |  | 2020-05-16 16:24 | 2020-09-04 16:24 |  |  | 100 | 100 | [15 empty] | 8.8136 | 0.01322 | 1.3 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2747 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018066
450 | Task(Task)-->P (Procurement) | Scrapper |  | 1.5.2.3 | Completed | No | No | 2020-03-17 09:00 | 2020-04-15 18:00 | 2020-03-26 09:00 | 2020-05-30 18:00 |  |  | 2020-05-30 10:57 | 2020-05-30 10:57 |  |  | 100 | 100 | [15 empty] | 0.47458 | 0.000712 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2748 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018067
451 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.5.2.3 | Completed | No | No | 2020-03-21 09:00 | 2020-04-19 23:59 | 2020-03-17 09:00 | 2020-07-06 18:00 |  |  | 2020-03-18 12:44 | 2020-07-06 12:44 |  |  | 100 | 100 | [15 empty] | 2.5763 | 0.003864 | 0.38 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2749 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018068
452 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.5.2.3 | Unscheduled | No | No | 2020-06-19 09:00 | 2020-07-18 18:00 | 2020-04-16 09:00 | 2020-08-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.13559 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2750 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018069
453 | Task(Task)-->P (Procurement) | Gear Box |  | 1.5.2.3 | Completed | No | No | 2020-02-27 09:00 | 2020-03-27 18:00 | 2020-03-20 09:00 | 2020-04-30 18:00 |  |  | 2020-03-21 11:21 | 2020-04-30 11:21 |  |  | 100 | 100 | [15 empty] | 2.7119 | 0.004068 | 0.4 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2751 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018070
454 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.5.2.3 | Completed | No | No | 2020-03-20 09:00 | 2020-04-18 18:00 | 2020-04-13 09:00 | 2020-04-30 18:00 |  |  | 2020-04-14 11:11 | 2020-04-30 11:11 |  |  | 100 | 100 | [15 empty] | 0.33898 | 0.000508 | 0.05 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2752 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018071
455 | Task(Task)-->P (Procurement) | Fluid Coupling |  | 1.5.2.3 | Completed | No | No | 2020-03-02 09:00 | 2020-03-31 18:00 | 2020-04-13 09:00 | 2020-05-18 18:00 |  |  | 2020-04-14 09:54 | 2020-05-18 16:05 |  |  | 100 | 100 | [15 empty] | 2.8475 | 0.004271 | 0.42 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2753 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018072
456 | Task(Task)-->P (Procurement) | Brake |  | 1.5.2.3 | Completed | No | No | 2020-03-10 09:00 | 2020-04-08 18:00 | 2020-04-22 09:00 | 2020-05-18 18:00 |  |  | 2020-04-23 11:38 | 2020-05-18 16:05 |  |  | 100 | 100 | [15 empty] | 0.27119 | 0.000407 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2754 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018073
457 | Task(Task)-->P (Procurement) | Building Structure |  | 1.5.2.3 | Completed | No | No | 2020-04-12 | 2020-05-11 18:00 | 2020-05-29 09:00 | 2020-05-31 23:59 |  |  | 2020-05-31 18:49 | 2020-05-31 18:49 |  |  | 100 | 100 | [15 empty] | 29.8305 | 0.044743 | 4.4 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2755 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018074
458 | Task(Task)-->P (Procurement) | HT AC MOTORS |  | 1.5.2.3 | Completed | No | No | 2020-02-07 09:00 | 2020-03-07 18:00 | 2020-04-11 09:00 | 2020-06-25 18:00 |  |  | 2020-04-13 09:41 | 2020-06-25 09:41 |  |  | 100 | 100 | [15 empty] | 7.8644 | 0.011796 | 1.16 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2756 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018075
459 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.5.2.3 | Completed | No | No | 2020-03-26 09:00 | 2020-04-10 18:00 | 2020-06-02 09:00 | 2020-07-31 18:00 |  |  | 2020-06-03 15:51 | 2020-06-29 15:51 |  |  | 100 | 100 | [15 empty] | 3.5932 | 0.00539 | 0.53 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2757 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018076
460 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.5.2.3 | Completed | No | No | 2020-05-12 09:00 | 2020-06-25 18:00 | 2020-06-03 09:00 | 2020-06-24 18:00 |  |  | 2020-06-15 10:57 | 2020-06-15 10:57 |  |  | 100 | 100 | [15 empty] | 1.6271 | 0.002441 | 0.24 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2758 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018077
461 | Task(Task)-->P (Procurement) | LPBS |  | 1.5.2.3 | Unscheduled | No | No | 2020-04-05 | 2020-04-20 18:00 | 2020-06-12 09:00 | 2020-08-19 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.067797 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2759 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018078
462 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.5.2.3 | Unscheduled | No | No | 2020-01-23 09:00 | 2020-02-05 18:00 | 2020-03-10 09:00 | 2020-08-17 18:00 | [6 empty] | 100 | 0 | [15 empty] | 1.3559 | 0.002034 | 0.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2761 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018079
463 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.5.2.3 | Unscheduled | No | No | 2020-01-17 09:00 | 2020-02-01 18:00 | 2020-03-07 09:00 | 2020-08-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2762 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018080
464 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.5.2.3 | Completed | No | No | 2020-01-19 | 2020-01-31 18:00 | 2020-01-16 09:00 | 2020-02-01 18:00 |  |  | 2020-02-01 10:57 | 2020-02-01 10:57 |  |  | 100 | 100 | [15 empty] | 0.067797 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2763 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018081
465 | Task(Task)-->P (Procurement) | ITP APPROVAL | 1.5.2.4 | 1.5.2 | Work In Progress | No | No | 2020-02-01 09:00 | 2020-08-25 18:00 | 2020-02-03 09:00 | 2020-10-30 18:00 |  |  | 2020-02-03 15:21 |  |  |  | 100 | 38.1746 | [15 empty] | 5.002 | 0.075047 | 7.38 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2764 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018082
466 | Task(Task)-->P (Procurement) | Suspended Magnet |  | 1.5.2.4 | Completed | No | No | 2020-02-07 09:00 | 2020-03-17 18:00 | 2020-02-03 09:00 | 2020-02-24 18:00 |  |  | 2020-02-03 15:21 | 2020-02-24 15:21 |  |  | 100 | 100 | [15 empty] | 10.4054 | 0.007809 | 0.77 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2765 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018083
467 | Task(Task)-->P (Procurement) | Belt Scale |  | 1.5.2.4 | Unscheduled | No | No | 2020-03-04 09:00 | 2020-04-12 23:59 | 2020-02-03 09:00 | 2020-09-09 18:00 |  |  | 2020-02-03 15:27 |  |  |  | 100 | 50 | [15 empty] | 2.027 | 0.001521 | 0.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2766 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018084
468 | Task(Task)-->P (Procurement) | Metal Detector |  | 1.5.2.4 | Completed | No | No | 2020-02-06 09:00 | 2020-03-16 18:00 | 2020-03-20 09:00 | 2020-09-02 18:00 |  |  | 2020-03-20 16:01 | 2020-09-02 16:01 |  |  | 100 | 100 | [15 empty] | 2.027 | 0.001521 | 0.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2767 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018085
469 | Task(Task)-->P (Procurement) | Pulley |  | 1.5.2.4 | Unscheduled | No | No | 2020-02-04 09:00 | 2020-03-14 18:00 | 2020-03-21 09:00 | 2020-05-11 18:00 | [6 empty] | 100 | 0 | [15 empty] | 12.027 | 0.009026 | 0.89 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2768 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018086
470 | Task(Task)-->P (Procurement) | Idler |  | 1.5.2.4 | Completed | No | No | 2020-03-03 09:00 | 2020-04-11 18:00 | 2020-04-30 09:00 | 2020-05-19 18:00 |  |  | 2020-04-13 16:20 | 2020-05-19 16:20 |  |  | 100 | 100 | [15 empty] | 8.5135 | 0.006389 | 0.63 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2769 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018087
471 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.5.2.4 | Unscheduled | No | No | 2020-07-02 09:00 | 2020-08-10 18:00 | 2020-03-24 09:00 | 2020-08-13 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.94595 | 0.00071 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2770 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018088
472 | Task(Task)-->P (Procurement) | Bearing |  | 1.5.2.4 | Unscheduled | No | No | 2020-07-17 09:00 | 2020-08-25 18:00 | 2020-03-24 09:00 | 2020-03-29 23:59 | [6 empty] | 100 | 0 | [15 empty] | 1.4865 | 0.001116 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2771 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018089
473 | Task(Task)-->P (Procurement) | Belting |  | 1.5.2.4 | Completed | No | No | 2020-02-21 09:00 | 2020-03-31 18:00 | 2020-09-04 09:00 | 2020-09-30 18:00 |  |  | 2020-09-04 16:30 | 2020-09-30 16:30 |  |  | 100 | 100 | [15 empty] | 8.7838 | 0.006592 | 0.65 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2772 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018090
474 | Task(Task)-->P (Procurement) | Scrapper |  | 1.5.2.4 | Completed | No | No | 2020-04-16 09:00 | 2020-05-25 18:00 | 2020-05-30 09:00 | 2020-06-25 18:00 |  |  | 2020-05-30 16:31 | 2020-06-25 16:31 |  |  | 100 | 100 | [15 empty] | 0.54054 | 0.000406 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2773 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018091
475 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.5.2.4 | Unscheduled | No | No | 2020-04-20 09:00 | 2020-05-29 18:00 | 2020-07-06 09:00 | 2020-07-16 18:00 | [6 empty] | 100 | 0 | [15 empty] | 2.5676 | 0.001927 | 0.19 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2774 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018092
476 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.5.2.4 | Unscheduled | No | No | 2020-07-19 | 2020-08-17 18:00 | 2020-06-25 09:00 | 2020-06-25 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.13514 | 0.000101 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2775 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018093
477 | Task(Task)-->P (Procurement) | Gear Box |  | 1.5.2.4 | Completed | No | No | 2020-03-28 09:00 | 2020-05-06 18:00 | 2020-04-30 09:00 | 2020-06-22 18:00 |  |  | 2020-04-30 16:57 | 2020-06-22 16:57 |  |  | 100 | 100 | [15 empty] | 2.7027 | 0.002028 | 0.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2776 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018094
478 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.5.2.4 | Completed | No | No | 2020-04-19 | 2020-05-28 18:00 | 2020-04-30 09:00 | 2020-06-18 18:00 |  |  | 2020-04-30 01:54 | 2020-06-18 17:31 |  |  | 100 | 100 | [15 empty] | 0.40541 | 0.000304 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2777 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018095
479 | Task(Task)-->P (Procurement) | Fluid Coupling |  | 1.5.2.4 | Unscheduled | No | No | 2020-04-01 09:00 | 2020-05-10 23:59 | 2020-05-18 09:00 | 2020-08-18 18:00 | [6 empty] | 100 | 0 | [15 empty] | 2.8378 | 0.00213 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2778 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018096
480 | Task(Task)-->P (Procurement) | Brake |  | 1.5.2.4 | Unscheduled | No | No | 2020-04-09 09:00 | 2020-05-18 18:00 | 2020-05-18 09:00 | 2020-10-10 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.27027 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2779 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018097
481 | Task(Task)-->P (Procurement) | Building Structure |  | 1.5.2.4 | Unscheduled | No | No | 2020-05-12 09:00 | 2020-05-18 18:00 | 2020-05-31 | 2020-08-04 18:00 |  |  | 2020-06-25 19:04 |  |  |  | 100 | 0 | [15 empty] | 29.7297 | 0.022311 | 2.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2780 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018098
482 | Task(Task)-->P (Procurement) | HT AC MOTORS |  | 1.5.2.4 | Unscheduled | No | No | 2020-03-08 | 2020-04-16 18:00 | 2020-09-11 09:00 | 2020-10-20 18:00 | [6 empty] | 100 | 0 | [15 empty] | 7.8378 | 0.005882 | 0.58 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2781 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018099
483 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.5.2.4 | Completed | No | No | 2020-04-11 09:00 | 2020-05-20 18:00 | 2020-07-28 09:00 | 2020-09-08 18:00 |  |  | 2020-07-08 17:23 | 2020-09-08 17:23 |  |  | 100 | 100 | [15 empty] | 3.6486 | 0.002738 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2782 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018100
484 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.5.2.4 | Unscheduled | No | No | 2020-06-26 09:00 | 2020-08-04 18:00 | 2020-06-23 09:00 | 2020-09-08 18:00 |  |  | 2020-06-23 17:28 |  |  |  | 100 | 0 | [15 empty] | 1.6216 | 0.001217 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2783 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018101
485 | Task(Task)-->P (Procurement) | LPBS |  | 1.5.2.4 | Completed | No | No | 2020-04-21 09:00 | 2020-05-30 18:00 | 2020-07-29 09:00 | 2020-08-21 18:00 |  |  | 2020-07-29 14:57 | 2020-08-22 12:53 |  |  | 100 | 100 | [15 empty] | 0.13514 | 0.000101 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2784 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018102
486 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.5.2.4 | Unscheduled | No | No | 2020-02-06 09:00 | 2020-03-16 18:00 | 2020-09-24 09:00 | 2020-10-30 18:00 | [6 empty] | 100 | 0 | [15 empty] | 1.3514 | 0.001014 | 0.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2786 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018103
487 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.5.2.4 | Unscheduled | No | No | 2020-02-02 | 2020-02-22 18:00 | 2020-08-02 | 2020-08-22 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2787 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018104
488 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.5.2.4 | Unscheduled | No | No | 2020-02-01 09:00 | 2020-03-11 18:00 | 2020-07-02 09:00 | 2020-08-04 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2788 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018105
489 | Task(Task)-->P (Procurement) | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE | 1.5.2.5 | 1.5.2 | Work In Progress | No | No | 2020-02-01 09:00 | 2020-09-16 18:00 | 2020-02-01 09:00 | 2020-10-20 18:00 |  |  | 2020-02-04 12:47 |  |  |  | 100 | 88.9066 | [15 empty] | 14.9993 | 0.22504 | 22.13 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2789 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018106
490 | Task(Task)-->P (Procurement) | Suspended Magnet |  | 1.5.2.5 | Completed | No | No | 2020-02-07 09:00 | 2020-04-06 18:00 | 2020-02-03 09:00 | 2020-04-24 18:00 |  |  | 2020-02-04 12:47 | 2020-04-24 10:57 |  |  | 100 | 100 | [15 empty] | 10.4383 | 0.02349 | 2.31 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2790 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018107
491 | Task(Task)-->P (Procurement) | Belt Scale |  | 1.5.2.5 | Completed | No | No | 2020-03-04 09:00 | 2020-05-02 18:00 | 2020-02-03 09:00 | 2020-07-25 18:00 |  |  | 2020-06-16 15:39 | 2020-07-25 00:58 |  |  | 100 | 100 | [15 empty] | 2.0334 | 0.004576 | 0.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2791 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018108
492 | Task(Task)-->P (Procurement) | Metal Detector |  | 1.5.2.5 | Completed | No | No | 2020-02-06 09:00 | 2020-04-05 23:59 | 2020-03-20 09:00 | 2020-08-13 18:00 |  |  | 2020-07-03 15:41 | 2020-07-27 01:07 |  |  | 100 | 100 | [15 empty] | 2.0334 | 0.004576 | 0.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2792 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018109
493 | Task(Task)-->P (Procurement) | Pulley |  | 1.5.2.5 | Completed | No | No | 2020-02-04 09:00 | 2020-03-29 23:59 | 2020-03-21 09:00 | 2020-03-25 18:00 |  |  | 2020-03-22 18:03 | 2020-03-25 18:03 |  |  | 100 | 100 | [15 empty] | 12.0651 | 0.027151 | 2.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2793 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018110
494 | Task(Task)-->P (Procurement) | Idler |  | 1.5.2.5 | Completed | No | No | 2020-03-03 09:00 | 2020-05-01 18:00 | 2020-04-30 09:00 | 2020-06-25 18:00 |  |  | 2020-06-25 14:53 | 2020-06-25 14:53 |  |  | 100 | 100 | [15 empty] | 8.4953 | 0.019118 | 1.88 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2794 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018111
495 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.5.2.5 | Completed | No | No | 2020-07-02 09:00 | 2020-08-30 23:59 | 2020-03-24 09:00 | 2020-06-29 18:00 |  |  | 2020-05-14 14:59 | 2020-06-29 14:59 |  |  | 100 | 100 | [15 empty] | 0.90375 | 0.002034 | 0.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2795 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018112
496 | Task(Task)-->P (Procurement) | Bearing |  | 1.5.2.5 | Completed | No | No | 2020-07-17 09:00 | 2020-07-17 18:00 | 2020-03-24 09:00 | 2020-03-24 18:00 |  |  | 2020-03-24 10:05 | 2020-03-24 10:05 |  |  | 100 | 100 | [15 empty] | 1.4912 | 0.003356 | 0.33 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2796 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018113
497 | Task(Task)-->P (Procurement) | Belting |  | 1.5.2.5 | Unscheduled | No | No | 2020-02-21 09:00 | 2020-04-20 18:00 | 2020-09-04 09:00 | 2020-10-15 18:00 |  |  | 2020-09-04 16:36 |  |  |  | 100 | 50 | [15 empty] | 8.8116 | 0.019829 | 1.95 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2797 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018114
498 | Task(Task)-->P (Procurement) | Scrapper |  | 1.5.2.5 | Completed | No | No | 2020-04-16 09:00 | 2020-06-14 23:59 | 2020-05-30 09:00 | 2020-07-30 18:00 |  |  | 2020-05-30 16:36 | 2020-07-30 16:36 |  |  | 100 | 100 | [15 empty] | 0.49706 | 0.001119 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2798 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018115
499 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.5.2.5 | Completed | No | No | 2020-04-20 09:00 | 2020-09-16 18:00 | 2020-07-06 09:00 | 2020-07-06 18:00 |  |  | 2020-07-06 12:45 | 2020-07-06 12:45 |  |  | 100 | 100 | [15 empty] | 2.5757 | 0.005796 | 0.57 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2799 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018116
500 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.5.2.5 | Unscheduled | No | No | 2020-07-19 | 2020-08-27 18:00 | 2020-08-04 09:00 | 2020-08-04 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.13556 | 0.000305 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2800 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018117
501 | Task(Task)-->P (Procurement) | Gear Box |  | 1.5.2.5 | Completed | No | No | 2020-03-28 09:00 | 2020-05-26 18:00 | 2020-04-30 09:00 | 2020-07-01 18:00 |  |  | 2020-04-30 15:33 | 2020-07-01 15:33 |  |  | 100 | 100 | [15 empty] | 2.7113 | 0.006101 | 0.6 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2801 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018118
502 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.5.2.5 | Completed | No | No | 2020-04-19 | 2020-06-17 18:00 | 2020-04-30 09:00 | 2020-07-30 18:00 |  |  | 2020-04-30 15:31 | 2020-07-06 15:31 |  |  | 100 | 100 | [15 empty] | 0.3615 | 0.000814 | 0.08 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2802 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018119
503 | Task(Task)-->P (Procurement) | Fluid Coupling |  | 1.5.2.5 | Unscheduled | No | No | 2020-04-01 09:00 | 2020-05-30 18:00 | 2020-05-18 09:00 | 2020-08-21 18:00 | [6 empty] | 100 | 0 | [15 empty] | 2.8016 | 0.006305 | 0.62 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2803 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018120
504 | Task(Task)-->P (Procurement) | Brake |  | 1.5.2.5 | Unscheduled | No | No | 2020-04-09 09:00 | 2020-06-07 23:59 | 2020-05-18 09:00 | 2020-08-13 18:00 |  |  | 2020-06-18 17:35 |  |  |  | 100 | 50 | [15 empty] | 0.27113 | 0.00061 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2804 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018121
505 | Task(Task)-->P (Procurement) | Building Structure |  | 1.5.2.5 | Completed | No | No | 2020-05-10 | 2020-05-16 18:00 | 2020-05-31 | 2020-06-23 18:00 |  |  | 2020-05-31 18:54 | 2020-06-27 18:54 |  |  | 100 | 100 | [15 empty] | 29.7786 | 0.067013 | 6.59 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2805 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018122
506 | Task(Task)-->P (Procurement) | HT AC MOTORS |  | 1.5.2.5 | Completed | No | No | 2020-03-08 | 2020-05-21 18:00 | 2020-07-18 09:00 | 2020-09-28 18:00 |  |  | 2020-07-18 09:04 | 2020-09-28 10:23 |  |  | 100 | 100 | [15 empty] | 7.8626 | 0.017694 | 1.74 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2806 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018123
507 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.5.2.5 | Unscheduled | No | No | 2020-04-11 09:00 | 2020-05-25 18:00 | 2020-07-10 09:00 | 2020-10-16 18:00 |  |  | 2020-07-14 10:44 |  |  |  | 100 | 0 | [15 empty] | 3.615 | 0.008135 | 0.8 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2807 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018124
508 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.5.2.5 | Completed | No | No | 2020-06-26 09:00 | 2020-08-09 23:59 | 2020-05-30 09:00 | 2020-08-08 18:00 |  |  | 2020-06-18 17:06 | 2020-08-07 15:00 |  |  | 100 | 100 | [15 empty] | 1.6268 | 0.003661 | 0.36 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2808 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018125
509 | Task(Task)-->P (Procurement) | LPBS |  | 1.5.2.5 | Completed | No | No | 2020-04-21 09:00 | 2020-06-04 18:00 | 2020-07-25 09:00 | 2020-08-22 18:00 |  |  | 2020-07-24 18:42 | 2020-08-22 12:57 |  |  | 100 | 100 | [15 empty] | 0.090375 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2809 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018126
510 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.5.2.5 | Completed | No | No | 2020-02-06 09:00 | 2020-03-21 18:00 | 2020-08-11 09:00 | 2020-09-19 18:00 |  |  | 2020-08-11 13:11 | 2020-09-19 12:57 |  |  | 100 | 100 | [15 empty] | 1.3556 | 0.003051 | 0.3 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2811 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018127
511 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.5.2.5 | Unscheduled | No | No | 2020-02-02 | 2020-03-03 18:00 | 2020-08-09 | 2020-10-20 18:00 |  |  | 2020-08-09 13:14 |  |  |  | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2812 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018128
512 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.5.2.5 | Completed | No | No | 2020-02-01 09:00 | 2020-03-16 18:00 | 2020-02-01 09:00 | 2020-07-15 18:00 |  |  | 2020-02-11 21:26 | 2020-07-15 21:26 |  |  | 100 | 100 | [15 empty] | 0.045188 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2813 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018129
513 | Task(Task)-->P (Procurement) | MANUFACTURING & RECEIPT AT SITE (MRN) | 1.5.2.6 | 1.5.2 | Unscheduled | No | No | 2020-03-04 09:00 | 2021-02-13 18:00 | 2020-03-24 09:00 | 2021-05-13 18:00 |  |  | 2020-03-25 18:05 |  |  |  | 83.7255 | 9.3104 | [15 empty] | 59.9973 | 0.90015 | 88.52 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2814 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018130
514 | Task(Task)-->P (Procurement) | Suspended Magnet |  | 1.5.2.6 | Unscheduled | No | No | 2020-04-07 09:00 | 2020-10-03 18:00 | 2020-04-24 09:00 | 2020-10-31 18:00 |  |  | 2020-04-24 15:22 |  |  |  | 100 | 60 | [15 empty] | 10.4597 | 0.094154 | 9.26 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2815 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018131
515 | Task(Task)-->P (Procurement) | Belt Scale |  | 1.5.2.6 | Unscheduled | No | No | 2020-05-03 | 2020-10-29 18:00 | 2020-07-25 09:00 | 2020-10-31 18:00 |  |  | 2020-07-25 15:31 |  |  |  | 87.7778 | 70 | [15 empty] | 2.0106 | 0.018099 | 1.78 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2816 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018132
516 | Task(Task)-->P (Procurement) | Metal Detector |  | 1.5.2.6 | Unscheduled | No | No | 2020-04-06 09:00 | 2020-10-02 18:00 | 2020-08-13 09:00 | 2020-12-31 18:00 |  |  | 2020-08-13 16:02 |  |  |  | 100 | 25 | [15 empty] | 2.0219 | 0.0182 | 1.79 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2817 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018133
517 | Task(Task)-->P (Procurement) | Pulley |  | 1.5.2.6 | Unscheduled | No | No | 2020-03-30 09:00 | 2020-11-20 18:00 | 2020-03-25 09:00 | 2020-11-30 18:00 |  |  | 2020-03-25 18:05 |  |  |  | 81.3559 | 0 | [15 empty] | 12.0637 | 0.10859 | 10.68 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2818 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018134
518 | Task(Task)-->P (Procurement) | Idler |  | 1.5.2.6 | Unscheduled | No | No | 2020-05-02 09:00 | 2020-11-13 18:00 | 2020-06-25 09:00 | 2020-12-31 18:00 | [6 empty] | 81.1225 | 0 | [15 empty] | 8.5056 | 0.076563 | 7.53 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2819 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018135
519 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.5.2.6 | Unscheduled | No | No | 2020-08-31 09:00 | 2020-12-23 18:00 | 2020-06-29 09:00 | 2020-12-31 18:00 | [6 empty] | 33.0435 | 0 | [15 empty] | 0.88106 | 0.007931 | 0.78 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2820 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018136
520 | Task(Task)-->P (Procurement) | Bearing |  | 1.5.2.6 | Unscheduled | No | No | 2020-08-26 09:00 | 2020-12-23 18:00 | 2020-03-24 09:00 | 2020-09-09 18:00 | [6 empty] | 35.8333 | 0 | [15 empty] | 1.5023 | 0.013523 | 1.33 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2821 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018137
521 | Task(Task)-->P (Procurement) | Belting |  | 1.5.2.6 | Unscheduled | No | No | 2020-04-21 09:00 | 2020-11-16 18:00 | 2020-10-16 09:00 | 2021-05-13 18:00 | [6 empty] | 80.9524 | 0 | [15 empty] | 8.7993 | 0.079207 | 7.79 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2822 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018138
522 | Task(Task)-->P (Procurement) | Scrapper |  | 1.5.2.6 | Unscheduled | No | No | 2020-06-15 09:00 | 2020-12-11 18:00 | 2020-07-30 09:00 | 2020-12-31 18:00 | [6 empty] | 63.8889 | 0 | [15 empty] | 0.49701 | 0.004474 | 0.44 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2823 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018139
523 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.5.2.6 | Unscheduled | No | No | 2020-06-19 09:00 | 2021-02-13 18:00 | 2020-07-06 09:00 | 2021-01-31 23:59 | [6 empty] | 46.25 | 0 | [15 empty] | 2.5641 | 0.023081 | 2.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2824 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018140
524 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.5.2.6 | Unscheduled | No | No | 2020-08-28 09:00 | 2020-12-25 18:00 | 2020-08-04 09:00 | 2020-12-25 18:00 | [6 empty] | 34.1667 | 0 | [15 empty] | 0.14684 | 0.001322 | 0.13 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2825 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018141
525 | Task(Task)-->P (Procurement) | Gear Box |  | 1.5.2.6 | Unscheduled | No | No | 2020-05-27 09:00 | 2020-12-22 18:00 | 2020-07-01 09:00 | 2020-12-31 18:00 |  |  | 2020-07-01 17:25 |  |  |  | 63.8095 | 30 | [15 empty] | 2.7222 | 0.024504 | 2.41 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2826 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018142
526 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.5.2.6 | Unscheduled | No | No | 2020-06-18 09:00 | 2020-12-15 18:00 | 2020-07-30 09:00 | 2020-10-05 18:00 |  |  | 2020-07-30 17:44 |  |  |  | 61.8785 | 90 | [15 empty] | 0.33887 | 0.00305 | 0.3 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2827 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018143
527 | Task(Task)-->P (Procurement) | Fluid Coupling |  | 1.5.2.6 | Unscheduled | No | No | 2020-05-31 | 2020-12-26 18:00 | 2020-08-21 09:00 | 2021-01-31 23:59 | [6 empty] | 61.9048 | 0 | [15 empty] | 2.8126 | 0.025318 | 2.49 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2828 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018144
528 | Task(Task)-->P (Procurement) | Brake |  | 1.5.2.6 | Unscheduled | No | No | 2020-06-08 09:00 | 2020-12-04 18:00 | 2020-08-13 09:00 | 2020-10-31 18:00 | [6 empty] | 67.7778 | 0 | [15 empty] | 0.28239 | 0.002542 | 0.25 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2829 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018145
529 | Task(Task)-->P (Procurement) | Building Structure |  | 1.5.2.6 | Unscheduled | No | No | 2020-05-19 09:00 | 2020-10-19 18:00 | 2020-06-23 09:00 | 2021-03-31 18:00 | [6 empty] | 92.2078 | 0 | [15 empty] | 29.7978 | 0.26823 | 26.38 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2830 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018146
530 | Task(Task)-->P (Procurement) | HT AC MOTORS |  | 1.5.2.6 | Unscheduled | No | No | 2020-05-22 09:00 | 2020-11-17 18:00 | 2020-10-21 09:00 | 2021-04-18 23:59 |  |  | 2020-09-28 10:25 |  |  |  | 77.2222 | 0 | [15 empty] | 7.8504 | 0.070666 | 6.95 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2831 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018147
531 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.5.2.6 | Unscheduled | No | No | 2020-05-26 09:00 | 2020-10-21 18:00 | 2020-10-17 09:00 | 2021-03-14 23:59 | [6 empty] | 90.604 | 0 | [15 empty] | 3.6033 | 0.032435 | 3.19 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2832 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018148
532 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.5.2.6 | Unscheduled | No | No | 2020-08-10 09:00 | 2020-11-07 18:00 | 2020-09-09 09:00 | 2020-12-07 18:00 |  |  | 2020-08-07 15:00 |  |  |  | 65.5556 | 0 | [15 empty] | 1.6379 | 0.014743 | 1.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2833 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018149
533 | Task(Task)-->P (Procurement) | LPBS |  | 1.5.2.6 | Unscheduled | No | No | 2020-06-05 09:00 | 2020-09-16 18:00 | 2020-08-23 | 2020-12-04 18:00 |  |  | 2020-08-22 13:00 |  |  |  | 100 | 0 | [15 empty] | 0.090365 | 0.000813 | 0.08 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2834 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018150
534 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.5.2.6 | Unscheduled | No | No | 2020-03-22 | 2020-08-05 18:00 | 2020-10-31 09:00 | 2021-03-16 18:00 | [6 empty] | 100 | 0 | [15 empty] | 1.3668 | 0.012303 | 1.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2836 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018151
535 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.5.2.6 | Unscheduled | No | No | 2020-03-04 09:00 | 2020-07-02 18:00 | 2020-10-21 09:00 | 2021-02-18 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.011296 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2837 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018152
536 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.5.2.6 | Unscheduled | No | No | 2020-03-17 09:00 | 2020-07-31 18:00 | 2020-07-02 09:00 | 2020-11-15 23:59 |  |  | 2020-07-15 21:34 |  |  |  | 100 | 0 | [15 empty] | 0.033887 | 0.000305 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2838 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018153
537 | Task(Task)-->C (Construction) | CONSTRUCTION | 1.5.3 | 1.5 | Unscheduled | No | No | 2020-04-04 09:00 | 2021-09-08 18:00 | 2020-08-01 09:00 | 2022-03-31 18:00 | [6 empty] | 10.1526 | 0 | [15 empty] | 24.1166 | 0.51984 | 51.12 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2839 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018154
538 | Task(Task)-->C (Construction) | CIVIL | 1.5.3.1 | 1.5.3 | Unscheduled | No | No | 2020-04-04 09:00 | 2020-07-08 18:00 | 2020-08-01 09:00 | 2020-11-03 18:00 | [6 empty] | 100 | 0 | [15 empty] | 10.1526 | 0.052777 | 5.19 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2840 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018155
539 | Task(Task)-->C (Construction) | AVAILABILITY OF FRONT BY NTPC |  | 1.5.3.1 | Unscheduled | No | No | 2020-04-04 09:00 | 2020-04-04 18:00 | 2020-08-01 09:00 | 2020-08-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2841 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018156
540 | Task(Task)-->C (Construction) | EXCAVATION |  | 1.5.3.1 | Unscheduled | No | No | 2020-05-25 09:00 | 2020-06-06 18:00 | 2020-08-02 | 2020-08-14 18:00 | [6 empty] | 100 | 0 | [15 empty] | 12.3314 | 0.006508 | 0.64 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 2408 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2842 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | Excavation | [21 empty] | 1018157
541 | Task(Task)-->C (Construction) | PCC |  | 1.5.3.1 | Unscheduled | No | No | 2020-05-29 09:00 | 2020-06-08 18:00 | 2020-09-24 09:00 | 2020-10-04 23:59 | [6 empty] | 100 | 0 | [15 empty] | 3.8536 | 0.002034 | 0.2 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2843 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | PCC | [21 empty] | 1018158
542 | Task(Task)-->C (Construction) | FOUNDATIONS - RAFT |  | 1.5.3.1 | Unscheduled | No | No | 2020-06-05 09:00 | 2020-06-23 18:00 | 2020-10-01 09:00 | 2020-10-19 18:00 | [6 empty] | 100 | 0 | [15 empty] | 58.1888 | 0.03071 | 3.02 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 114 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2844 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018159
543 | Task(Task)-->C (Construction) | PADESTALS FOR SC-1A,SC-1B, SC-2A & SC-2B CONV. STR. |  | 1.5.3.1 | Unscheduled | No | No | 2020-06-15 09:00 | 2020-07-08 18:00 | 2020-10-11 | 2020-11-03 18:00 | [6 empty] | 100 | 0 | [15 empty] | 25.6262 | 0.013525 | 1.33 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2845 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018160
544 | Task(Task)-->C (Construction) | STRUCTURAL WORKS | 1.5.3.2 | 1.5.3 | Unscheduled | No | No | 2020-10-20 09:00 | 2021-03-18 18:00 | 2021-04-01 09:00 | 2021-08-28 18:00 | [6 empty] | 0 | 0 | [15 empty] | 41.784 | 0.21721 | 21.36 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2846 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018161
545 | Task(Task)-->C (Construction) | ERECTION OF STRUCTURAL STEEL |  | 1.5.3.2 | Unscheduled | No | No | 2020-10-20 09:00 | 2021-03-18 18:00 | 2021-04-01 09:00 | 2021-08-28 18:00 | [6 empty] | 0 | 0 | [15 empty] | 100 | 0.21721 | 21.36 | Plan & Actual | Quantity | Metric Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 330 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2847 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018162
546 | Task(Task)-->C (Construction) | MECHANICAL EQUIPMENT WORKS | 1.5.3.3 | 1.5.3 | Unscheduled | No | No | 2021-03-19 09:00 | 2021-07-28 18:00 | 2021-08-29 | 2022-01-07 18:00 | [6 empty] | 0 | 0 | [15 empty] | 21.2637 | 0.11054 | 10.87 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5451 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018163
547 | Task(Task)-->C (Construction) | ERECTION OF CONVEYOR SC 1A |  | 1.5.3.3 | Unscheduled | No | No | 2021-03-19 09:00 | 2021-05-17 18:00 | 2021-08-29 | 2021-10-27 18:00 | [6 empty] | 0 | 0 | [15 empty] | 23.6648 | 0.026158 | 2.57 | Plan & Actual | Quantity | Meter | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2848 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018164
548 | Task(Task)-->C (Construction) | ERECTION OF CONVEYOR SC 1B |  | 1.5.3.3 | Unscheduled | No | No | 2021-03-19 09:00 | 2021-05-17 18:00 | 2021-08-29 | 2021-10-27 18:00 | [6 empty] | 0 | 0 | [15 empty] | 23.6648 | 0.026158 | 2.57 | Plan & Actual | Quantity | Meter | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5407 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018165
549 | Task(Task)-->C (Construction) | ERECTION OF CONVEYOR SC 2A |  | 1.5.3.3 | Unscheduled | No | No | 2021-05-18 09:00 | 2021-07-16 18:00 | 2021-10-28 09:00 | 2021-12-26 23:59 | [6 empty] | 0 | 0 | [15 empty] | 23.6648 | 0.026158 | 2.57 | Plan & Actual | Quantity | Meter | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5408 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018166
550 | Task(Task)-->C (Construction) | ERECTION OF CONVEYOR SC 2B |  | 1.5.3.3 | Unscheduled | No | No | 2021-05-18 09:00 | 2021-07-16 18:00 | 2021-10-28 09:00 | 2021-12-26 23:59 | [6 empty] | 0 | 0 | [15 empty] | 23.6648 | 0.026158 | 2.57 | Plan & Actual | Quantity | Meter | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5409 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018167
551 | Task(Task)-->C (Construction) | ERECTION OF SUSPENDED MAGNET |  | 1.5.3.3 | Unscheduled | No | No | 2021-07-17 09:00 | 2021-07-28 18:00 | 2021-12-27 09:00 | 2022-01-07 18:00 | [6 empty] | 0 | 0 | [15 empty] | 2.0258 | 0.002239 | 0.22 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5411 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018168
552 | Task(Task)-->C (Construction) | ERECTION OF METAL DETECTOR |  | 1.5.3.3 | Unscheduled | No | No | 2021-07-17 09:00 | 2021-07-28 18:00 | 2021-12-27 09:00 | 2022-01-07 18:00 | [6 empty] | 0 | 0 | [15 empty] | 1.6575 | 0.001832 | 0.18 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5412 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018169
553 | Task(Task)-->C (Construction) | ERECTION OF BELT SCALE |  | 1.5.3.3 | Unscheduled | No | No | 2021-07-17 09:00 | 2021-07-28 18:00 | 2021-12-27 09:00 | 2022-01-07 18:00 | [6 empty] | 0 | 0 | [15 empty] | 1.6575 | 0.001832 | 0.18 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5410 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018170
554 | Task(Task)-->C (Construction) | BELT LAYING & JOINTING WORK |  | 1.5.3 | Unscheduled | No | No | 2021-06-02 09:00 | 2021-07-31 18:00 | 2021-11-12 09:00 | 2022-01-10 18:00 | [6 empty] | 0 | 0 | [15 empty] | 3.3451 | 0.017389 | 1.71 | Plan & Actual | Quantity | Meter | 0 | 0 | 0 | 0 | 0 | 0 | 1100 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5452 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018171
555 | Task(Task)-->C (Construction) | ELECTRICAL & INSTRUMENTATION | 1.5.3.5 | 1.5.3 | Unscheduled | No | No | 2021-03-14 | 2021-08-25 18:00 | 2021-08-24 09:00 | 2022-03-17 18:00 | [6 empty] | 0 | 0 | [15 empty] | 11.4241 | 0.059387 | 5.84 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2850 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018172
556 | Task(Task)-->C (Construction) | CABLE TRAY |  | 1.5.3.5 | Unscheduled | No | No | 2021-03-19 09:00 | 2021-03-23 18:00 | 2021-08-29 | 2021-09-02 18:00 | [6 empty] | 0 | 0 | [15 empty] | 5.4889 | 0.00326 | 0.32 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2851 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018173
557 | Task(Task)-->C (Construction) | POWER CABLE |  | 1.5.3.5 | Unscheduled | No | No | 2021-07-29 09:00 | 2021-08-01 23:59 | 2022-01-08 09:00 | 2022-01-11 18:00 | [6 empty] | 0 | 0 | [15 empty] | 15.4374 | 0.009168 | 0.9 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 6387 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2852 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018174
558 | Task(Task)-->C (Construction) | CONTROL CABLE |  | 1.5.3.5 | Unscheduled | No | No | 2021-07-31 09:00 | 2021-08-01 23:59 | 2022-01-10 09:00 | 2022-01-11 18:00 | [6 empty] | 0 | 0 | [15 empty] | 4.1166 | 0.002445 | 0.24 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 1700 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2853 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018175
559 | Task(Task)-->C (Construction) | EARTHING |  | 1.5.3.5 | Unscheduled | No | No | 2021-03-19 09:00 | 2021-03-23 18:00 | 2021-08-29 | 2021-09-02 18:00 | [6 empty] | 0 | 0 | [15 empty] | 6.6895 | 0.003973 | 0.39 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 1760 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2854 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018176
560 | Task(Task)-->C (Construction) | LIGHTING |  | 1.5.3.5 | Unscheduled | No | No | 2021-03-14 | 2021-03-28 23:59 | 2021-08-24 09:00 | 2021-09-07 18:00 | [6 empty] | 0 | 0 | [15 empty] | 18.6964 | 0.011103 | 1.09 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 112 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5290 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018177
561 | Task(Task)-->C (Construction) | FIELD INTRUMENTS |  | 1.5.3.5 | Unscheduled | No | No | 2021-07-27 09:00 | 2021-08-02 18:00 | 2022-01-06 09:00 | 2022-01-12 18:00 | [6 empty] | 0 | 0 | [15 empty] | 49.5712 | 0.029439 | 2.89 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5291 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018178
562 | Task(Task)-->C (Construction) | MOTOR TERMINATION |  | 1.5.3.5 | Unscheduled | No | No | 2021-08-02 09:00 | 2021-08-03 18:00 | 2022-01-12 09:00 | 2022-01-13 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5292 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018179
563 | Task(Task)-->C (Construction) | NO LOAD RUN OF MOTOR |  | 1.5.3.5 | Unscheduled | No | No | 2021-08-22 | 2021-08-25 18:00 | 2022-03-14 09:00 | 2022-03-17 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5453 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018180
564 | Task(Task)-->C (Construction) | NO LOAD COMMISSIONING & SYSTEM READYNESS FOR LOAD & TRIAL OPERATION |  | 1.5.3 | Unscheduled | No | No | 2021-08-26 09:00 | 2021-09-08 18:00 | 2022-03-18 09:00 | 2022-03-31 18:00 | [6 empty] | 0 | 0 | [15 empty] | 12.0305 | 0.062539 | 6.15 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5293 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018181
565 | Task(Task)-->E (Engineering) | SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2) | 1.6 | 1 | Work In Progress | No | No | 2019-09-27 09:00 | 2021-09-09 18:00 | 2019-12-30 09:00 | 2022-04-01 18:00 |  |  | 2019-12-30 10:57 |  |  |  | 61.8614 | 16.7491 | [15 empty] | 1.6884 | 1.6884 | 166.04 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2855 | 0 | 1 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018182
566 | Task(Task)-->E (Engineering) | ENGINEERING | 1.6.1 | 1.6 | Work In Progress | No | No | 2019-10-16 18:00 | 2020-06-19 17:40 | 2020-02-26 18:00 | 2020-10-04 23:59 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 72.3318 | [15 empty] | 3.3183 | 0.056025 | 5.51 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2856 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018183
567 | Task(Task)-->E (Engineering) | MECHANICAL | 1.6.1.1 | 1.6.1 | Work In Progress | No | No | 2019-10-16 18:00 | 2020-05-30 17:40 | 2020-02-26 18:00 | 2020-08-21 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 79.9976 | [15 empty] | 29.4011 | 0.016472 | 1.62 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No | 2857 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036082
568 | Task(Task)-->E (Engineering) | G.A & LOAD DATA OF SURGE HOPPER BUILDING |  | 1.6.1.1 | Unscheduled | No | No | 2019-10-16 18:00 | 2019-12-20 17:40 | 2020-02-26 18:00 | 2020-05-11 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-0009 |  | 2020-02-13 10:26 | 7012-155-PVM-B-009 |  |  |  | A |  |  |  | 66.2577 | 0.010914 | 1.08 | Plan & Actual | Date |  | 0 | 0 | 0 | 400 | 0 | 125.3 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2858 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-10-16 18:00 | 2020-02-26 18:00 |  | 10 | 2020-02-26 23:31 |  |  | 2019-11-12 17:40 | 2020-03-25 18:00 |  | 30 | 2020-03-25 23:31 |  |  | 2019-11-18 17:40 | 2020-03-28 18:00 |  | 35 | 2020-03-28 23:31 |  |  | 2019-11-23 23:59 | 2020-04-04 18:00 |  | 65 | 2020-04-04 23:31 |  |  | 2019-11-29 17:40 | 2020-04-25 18:00 |  | 80 | 2020-05-11 23:31 | [5 empty] | 80 | 2020-09-05 13:09 | [5 empty] | 80 | 2020-09-05 13:09 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2019-12-20 17:40 | 2020-05-09 18:00 |  | 100 | [122 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 9 |  |  |  | 101023
569 | Task(Task)-->E (Engineering) | G.A & MARKING OF BELT FEEDER BF-1 & BF-2 (INSIDE THE SURGE HOPPER BUILDING) |  | 1.6.1.1 | Unscheduled | No | No | 2019-12-28 18:00 | 2020-02-14 17:40 | 2020-03-15 23:59 | 2020-05-09 18:00 |  |  | 2020-09-21 12:14 |  |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-0022 |  | 2020-02-13 10:26 | 7012-155-PVM-B-022 |  |  |  | A |  |  |  | 13.4969 | 0.002223 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 80 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2859 | 1 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-12-28 18:00 | 2020-03-15 23:59 |  | 10 | 2020-03-15 23:31 |  |  | 2020-01-06 17:40 | 2020-03-30 18:00 |  | 30 | 2020-03-30 23:31 |  |  | 2020-01-11 17:40 | 2020-04-01 18:00 |  | 35 | 2020-04-01 23:31 |  |  | 2020-01-17 23:59 | 2020-04-04 18:00 |  | 65 | 2020-04-04 23:31 |  |  | 2020-01-23 17:40 | 2020-04-25 18:00 |  | 80 | 2020-04-23 23:31 | [5 empty] | 80 | 2020-09-21 12:14 | [5 empty] | 80 | 2020-09-21 12:14 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-02-14 17:40 | 2020-05-09 18:00 |  | 100 | 2020-04-23 23:31 | [121 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 22 |  |  |  | 101036
570 | Task(Task)-->E (Engineering) | G.A OF RACK & PINION GATE |  | 1.6.1.1 | Unscheduled | No | No | 2020-04-08 18:00 | 2020-05-30 17:40 | 2020-05-15 18:00 | 2020-08-21 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1037 |  | 2020-02-13 10:27 | 7012-155-PVM-B-137 |  |  |  | I |  |  |  | 6.7485 | 0.001112 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2865 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-08 18:00 | 2020-05-15 18:00 |  | 10 |  |  |  | 2020-04-18 17:40 | 2020-05-30 18:00 |  | 30 |  |  |  | 2020-04-24 17:40 | 2020-06-02 18:00 |  | 35 |  |  |  | 2020-05-01 23:59 | 2020-06-07 23:59 |  | 65 |  |  |  | 2020-05-07 17:40 | 2020-06-28 23:59 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-30 17:40 | 2020-06-28 23:59 |  | 100 | [122 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 67 |  |  |  | 101081
571 | Task(Task)-->E (Engineering) | G.A OF ROD GATE |  | 1.6.1.1 | Completed | No | No | 2020-02-01 17:40 | 2020-03-13 17:40 | 2020-08-18 09:00 | 2020-08-21 18:00 |  |  | 2020-02-21 14:04 | 2020-08-25 17:43 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1042 |  | 2020-02-13 10:27 | 7012-155-PVM-B-142 |  |  |  | I |  |  |  | 13.4969 | 0.002223 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2866 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-01 18:00 | 2020-04-17 18:00 |  | 10 | 2020-04-06 23:31 |  |  | 2020-02-01 17:40 | 2020-04-27 18:00 |  | 30 | 2020-04-11 23:31 |  |  | 2020-02-07 17:40 | 2020-04-30 18:00 |  | 35 | 2020-04-14 23:31 |  |  | 2020-02-14 23:59 | 2020-04-30 18:00 |  | 65 | 2020-08-19 18:58 |  |  | 2020-02-20 17:40 | 2020-05-21 18:00 |  | 80 | 2020-08-25 11:13 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-13 17:40 | 2020-05-21 18:00 |  | 100 | 2020-08-25 17:44 | [121 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 72 |  |  |  | 101086
572 | Task(Task)-->E (Engineering) | CIVIL | 1.6.1.2 | 1.6.1 | Work In Progress | No | No | 2020-01-01 18:00 | 2020-05-05 17:40 | 2020-04-05 23:59 | 2020-09-10 18:00 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 66.9322 | [15 empty] | 29.5826 | 0.016574 | 1.63 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No | 2868 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036083
573 | Task(Task)-->E (Engineering) | SURGE HOPPER BUILDING - DESIGN CALCULATION OF SUPER STRUCTURE |  | 1.6.1.2 | Unscheduled | No | No | 2020-01-01 18:00 | 2020-03-02 17:40 | 2020-04-05 23:59 | 2020-07-17 18:00 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-DC-0008 |  | 2020-02-13 11:41 | 7012-155-PVC-U-022 |  |  |  | A |  |  |  | 42.9448 | 0.007118 | 0.7 | Plan & Actual | Date |  | 0 | 0 | 0 | 259.05 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2869 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-01 18:00 | 2020-04-05 23:59 |  | 10 | 2020-04-07 23:31 |  |  | 2020-01-21 17:40 | 2020-05-01 18:00 |  | 30 | 2020-05-07 23:31 |  |  | 2020-01-27 17:40 | 2020-05-04 18:00 |  | 35 |  |  |  | 2020-02-01 23:59 | 2020-05-11 18:00 |  | 65 | 2020-08-13 20:01 |  |  | 2020-02-07 17:40 | 2020-06-01 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-02 17:40 | 2020-06-15 18:00 |  | 100 | [122 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 123 |  |  |  | 101137
574 | Task(Task)-->E (Engineering) | SURGE HOPPER BUILDING - DESIGN CALCULATION OF SUB STRUCTURE |  | 1.6.1.2 | Unscheduled | No | No | 2020-02-05 18:00 | 2020-04-06 17:40 | 2020-05-10 23:59 | 2020-07-29 18:00 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-DC-0009 |  | 2020-02-13 11:41 | 7012-155-PVC-U-023 |  |  |  | A |  |  |  | 28.8344 | 0.004779 | 0.47 | Plan & Actual | Date |  | 0 | 0 | 0 | 173.12 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2870 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-05 18:00 | 2020-05-10 23:59 |  | 10 |  |  |  | 2020-02-25 17:40 | 2020-06-05 18:00 |  | 30 |  |  |  | 2020-03-02 17:40 | 2020-06-08 18:00 |  | 35 |  |  |  | 2020-03-07 23:59 | 2020-06-15 18:00 |  | 65 | 2020-08-13 20:01 |  |  | 2020-03-13 17:40 | 2020-07-06 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-06 17:40 | 2020-07-20 18:00 |  | 100 | [122 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 124 |  |  |  | 101138
575 | Task(Task)-->E (Engineering) | SURGE HOPPER BUILDING - NUM & RC DETAILS OF FDN |  | 1.6.1.2 | Unscheduled | No | No | 2020-02-05 18:00 | 2020-04-06 17:40 | 2020-05-10 23:59 | 2020-07-29 18:00 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-NR-0008 |  | 2020-02-13 11:41 | 7012-155-PVC-C-025 |  |  |  | A |  |  |  | 17.1779 | 0.002847 | 0.28 | Plan & Actual | Date |  | 0 | 0 | 0 | 103.56 | 0 | 8.15 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2871 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-05 18:00 | 2020-05-10 23:59 |  | 10 |  |  |  | 2020-02-25 17:40 | 2020-06-05 18:00 |  | 30 |  |  |  | 2020-03-02 17:40 | 2020-06-08 18:00 |  | 35 | 2020-07-11 16:24 |  |  | 2020-03-07 23:59 | 2020-06-15 18:00 |  | 65 | 2020-08-13 20:01 |  |  | 2020-03-13 17:40 | 2020-07-06 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-06 17:40 | 2020-07-20 18:00 |  | 100 | [122 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 126 |  |  |  | 101140
576 | Task(Task)-->E (Engineering) | SURGE HOPPER BUILDING - NUM & RC DETAILS OF FLOOR SLABS |  | 1.6.1.2 | Unscheduled | No | No | 2020-03-06 18:00 | 2020-05-05 17:40 | 2020-06-14 23:59 | 2020-09-10 18:00 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-NR-0009 |  | 2020-02-13 11:41 | 7012-155-PVC-C-026 |  |  |  | A |  |  |  | 5.5215 | 0.000915 | 0.09 | Plan & Actual | Date |  | 0 | 0 | 0 | 34.39 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2872 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-06 18:00 | 2020-06-14 23:59 |  | 10 |  |  |  | 2020-03-24 17:40 | 2020-07-10 18:00 |  | 30 | 2020-08-24 15:19 |  |  | 2020-03-31 17:40 | 2020-07-13 18:00 |  | 35 | 2020-08-29 11:05 |  |  | 2020-04-06 23:59 | 2020-07-20 18:00 |  | 65 | 2020-08-30 19:30 |  |  | 2020-04-13 17:40 | 2020-08-10 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-05 17:40 | 2020-08-24 18:00 |  | 100 | [122 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 127 |  |  |  | 101141
577 | Task(Task)-->E (Engineering) | SURGE HOPPER BUILDING - NUM & RC DETAILS OF GRADE SLAB |  | 1.6.1.2 | Completed | No | No | 2020-03-06 18:00 | 2020-05-05 17:40 | 2020-08-06 09:00 | 2020-08-31 18:00 |  |  | 2020-02-21 15:37 | 2020-09-01 00:08 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-NR-0010 |  | 2020-02-13 11:41 | 7012-155-PVC-C-027 |  |  |  | A |  |  |  | 5.5215 | 0.000915 | 0.09 | Plan & Actual | Date |  | 0 | 0 | 0 | 34.39 | 0 | 28.11 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2873 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-06 18:00 | 2020-07-04 18:00 |  | 10 |  |  |  | 2020-03-24 17:40 | 2020-07-30 18:00 |  | 30 |  |  |  | 2020-03-31 17:40 | 2020-08-02 23:59 |  | 35 | 2020-08-05 16:50 |  |  | 2020-04-06 23:59 | 2020-08-09 23:59 |  | 65 | 2020-08-13 19:52 |  |  | 2020-04-13 17:40 | 2020-08-30 23:59 |  | 80 | 2020-09-01 00:06 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-05 17:40 | 2020-09-13 23:59 |  | 100 | 2020-09-01 00:09 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 128 |  |  |  | 101142
578 | Task(Task)-->E (Engineering) | STRUCTURAL | 1.6.1.3 | 1.6.1 | Unscheduled | No | No | 2020-01-01 18:00 | 2020-06-19 17:40 | 2020-04-05 23:59 | 2020-10-04 23:59 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 65 | [15 empty] | 14.7005 | 0.008236 | 0.81 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No | 2874 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036084
579 | Task(Task)-->E (Engineering) | SURGE HOPPER BUILDING - STRUCTURAL GA |  | 1.6.1.3 | Unscheduled | No | No | 2020-01-01 18:00 | 2020-03-02 17:40 | 2020-04-05 23:59 | 2020-07-17 18:00 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-GA-0006 |  | 2020-02-13 11:41 | 7012-155-PVC-B-024 |  |  |  | A |  |  |  | 86.4198 | 0.007118 | 0.7 | Plan & Actual | Date |  | 0 | 0 | 0 | 259.05 | 0 | 77.1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2875 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-01 18:00 | 2020-04-05 23:59 |  | 10 | 2020-04-07 23:31 |  |  | 2020-01-21 17:40 | 2020-05-01 18:00 |  | 30 | 2020-05-07 23:31 |  |  | 2020-01-27 17:40 | 2020-05-04 18:00 |  | 35 | 2020-06-26 13:23 |  |  | 2020-02-01 23:59 | 2020-05-11 18:00 |  | 65 | 2020-08-13 20:01 |  |  | 2020-02-07 17:40 | 2020-06-01 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-02 17:40 | 2020-06-15 18:00 |  | 100 | [122 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 125 |  |  |  | 101139
580 | Task(Task)-->E (Engineering) | ARCHITECTURAL GA OF SURGE HOPPER BUILDING |  | 1.6.1.3 | Unscheduled | No | No | 2020-04-20 18:00 | 2020-06-19 17:40 | 2020-06-25 18:00 | 2020-10-04 23:59 |  |  | 2020-02-21 15:39 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-AR-0003 |  | 2020-02-13 11:43 | 7012-155-PVC-C-109 |  |  |  | I |  |  |  | 13.5802 | 0.001118 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 40.52 | 0 | 89 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2876 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-20 18:00 | 2020-06-25 18:00 |  | 10 |  |  |  | 2020-05-08 17:40 | 2020-07-20 18:00 |  | 30 |  |  |  | 2020-05-15 17:40 | 2020-07-23 18:00 |  | 35 | 2020-09-23 17:59 |  |  | 2020-05-21 23:59 | 2020-07-30 18:00 |  | 65 | 2020-09-24 20:18 |  |  | 2020-05-28 17:40 | 2020-08-20 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-19 17:40 | 2020-09-03 18:00 |  | 100 | [122 empty] | Chetan Khodke |  |  |  |  | A - Architecture | [16 empty] | 210 |  |  |  | 101220
581 | Task(Task)-->E (Engineering) | ELECTRICAL | 1.6.1.4 | 1.6.1 | Unscheduled | No | No | 2019-12-13 18:00 | 2020-06-08 17:40 | 2020-04-14 18:00 | 2020-08-21 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 73.933 | [15 empty] | 26.3158 | 0.014743 | 1.45 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No | 2879 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036085
582 | Task(Task)-->E (Engineering) | DATASHEET & TERMINAL WIRING DIAGRAM FOR RACK & PINION GATE |  | 1.6.1.4 | Unscheduled | No | No | 2020-04-28 17:40 | 2020-06-08 17:40 | 2020-05-15 18:00 | 2020-08-21 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-404 |  | 2020-02-13 11:47 | 7012-155-PVE-W-140 |  |  |  | A |  |  |  | 7.5862 | 0.001118 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2882 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-28 18:00 | 2020-05-15 18:00 |  | 10 |  |  |  | 2020-04-28 17:40 | 2020-05-22 18:00 |  | 30 |  |  |  | 2020-05-04 17:40 | 2020-05-28 18:00 |  | 35 |  |  |  | 2020-05-11 23:59 | 2020-05-28 18:00 |  | 65 |  |  |  | 2020-05-16 17:40 | 2020-06-18 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-08 17:40 | 2020-06-18 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 375 |  |  |  | 101386
583 | Task(Task)-->E (Engineering) | EQUIPMENT, CABLE ROUTING, EARTHING & LIGHTNING LAYOUT WITH PLAN, SECTIONAL VIEWS & BOM OF SURGE HOPPER |  | 1.6.1.4 | Unscheduled | No | No | 2019-12-13 18:00 | 2020-02-06 17:40 | 2020-04-14 18:00 | 2020-06-04 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5053 |  | 2020-02-13 11:44 | 7012-155-PVE-F-015 |  |  |  | A |  |  |  | 46.2069 | 0.006812 | 0.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 248.42 | 0 | 24.16 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2880 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-12-13 18:00 | 2020-04-14 18:00 |  | 10 | 2020-04-14 23:31 |  |  | 2019-12-30 17:40 | 2020-04-28 18:00 |  | 30 | 2020-05-08 23:31 |  |  | 2020-01-04 17:40 | 2020-05-05 18:00 |  | 35 | 2020-05-11 23:31 |  |  | 2020-01-10 23:59 | 2020-05-12 18:00 |  | 65 | 2020-05-25 23:31 |  |  | 2020-01-16 17:40 | 2020-06-02 18:00 |  | 80 | 2020-07-28 17:08 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-02-06 17:40 | 2020-06-02 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 250 |  |  |  | 101261
584 | Task(Task)-->E (Engineering) | LIGHTING LAYOUT PLAN WITH POWER DISTRIBUTION ARRANGEMENT, SECTIONAL VIEW, BOM OF SURGE HOPPER |  | 1.6.1.4 | Unscheduled | No | No | 2020-02-18 18:00 | 2020-04-08 17:40 | 2020-04-27 18:00 | 2020-06-08 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5064 |  | 2020-02-13 11:44 | 7012-155-PVE-G-026 |  |  |  | A |  |  |  | 46.2069 | 0.006812 | 0.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 248.42 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2881 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-18 18:00 | 2020-04-27 18:00 |  | 10 | 2020-04-27 23:31 |  |  | 2020-02-27 17:40 | 2020-05-04 18:00 |  | 30 | 2020-05-03 23:31 |  |  | 2020-03-04 17:40 | 2020-05-11 18:00 |  | 35 | 2020-05-03 23:31 |  |  | 2020-03-10 23:59 | 2020-05-18 18:00 |  | 65 | 2020-05-05 23:31 |  |  | 2020-03-17 17:40 | 2020-06-08 18:00 |  | 80 | 2020-05-18 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-08 17:40 | 2020-06-08 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 261 |  |  |  | 101272
585 | Task(Task)-->P (Procurement) | PROCUREMENT | 1.6.2 | 1.6 | Work In Progress | No | No | 2019-09-27 09:00 | 2021-02-13 18:00 | 2019-12-30 09:00 | 2021-05-13 18:00 |  |  | 2019-12-30 10:57 |  |  |  | 88.7069 | 25.9292 | [15 empty] | 55.3388 | 0.93432 | 91.89 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2885 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018188
586 | Task(Task)-->P (Procurement) | PURCHASE REQUISITION | 1.6.2.1 | 1.6.2 | Work In Progress | No | No | 2019-09-27 09:00 | 2020-05-19 18:00 | 2019-12-30 09:00 | 2020-05-29 18:00 |  |  | 2019-12-30 10:57 |  |  |  | 100 | 94.1301 | [15 empty] | 4.9962 | 0.046681 | 4.59 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2886 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018189
587 | Task(Task)-->P (Procurement) | Rack & Pinion Gate |  | 1.6.2.1 | Completed | No | No | 2019-09-27 09:00 | 2019-09-27 18:00 | 2020-02-21 09:00 | 2020-02-21 18:00 |  |  | 2020-02-21 14:39 | 2020-02-21 14:39 |  |  | 100 | 100 | [15 empty] | 3.0435 | 0.001421 | 0.14 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2887 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018190
588 | Task(Task)-->P (Procurement) | Rod Gate |  | 1.6.2.1 | Completed | No | No | 2019-09-27 09:00 | 2019-09-27 18:00 | 2020-02-19 09:00 | 2020-02-19 18:00 |  |  | 2020-02-19 10:57 | 2020-02-19 10:57 |  |  | 100 | 100 | [15 empty] | 0.65217 | 0.000304 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2888 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018191
589 | Task(Task)-->P (Procurement) | Flap Gate |  | 1.6.2.1 | Completed | No | No | 2020-02-06 09:00 | 2020-02-06 18:00 | 2020-03-20 09:00 | 2020-03-20 18:00 |  |  | 2020-03-20 10:57 | 2020-03-20 10:57 |  |  | 100 | 100 | [15 empty] | 3.0435 | 0.001421 | 0.14 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2889 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018192
590 | Task(Task)-->P (Procurement) | Pulley |  | 1.6.2.1 | Completed | No | No | 2019-09-27 09:00 | 2019-09-27 18:00 | 2020-02-05 09:00 | 2020-02-05 18:00 |  |  | 2020-02-05 16:16 | 2020-02-05 16:16 |  |  | 100 | 100 | [15 empty] | 2.3913 | 0.001116 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2890 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018193
591 | Task(Task)-->P (Procurement) | Idler |  | 1.6.2.1 | Completed | No | No | 2019-12-19 09:00 | 2019-12-19 18:00 | 2020-02-13 09:00 | 2020-02-13 18:00 |  |  | 2020-02-13 15:44 | 2020-02-13 15:44 |  |  | 100 | 100 | [15 empty] | 0.86957 | 0.000406 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2891 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018194
592 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.6.2.1 | Completed | No | No | 2020-05-17 | 2020-05-17 23:59 | 2020-02-10 09:00 | 2020-02-10 18:00 |  |  | 2020-02-10 09:26 | 2020-02-10 09:26 |  |  | 100 | 100 | [15 empty] | 0.21739 | 0.000101 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2892 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018195
593 | Task(Task)-->P (Procurement) | Bearing |  | 1.6.2.1 | Completed | No | No | 2020-05-17 | 2020-05-17 23:59 | 2020-02-10 09:00 | 2020-02-10 18:00 |  |  | 2020-02-10 09:36 | 2020-02-10 09:36 |  |  | 100 | 100 | [15 empty] | 0.21739 | 0.000101 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2893 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018196
594 | Task(Task)-->P (Procurement) | Belting |  | 1.6.2.1 | Completed | No | No | 2019-11-07 09:00 | 2019-11-07 18:00 | 2020-01-20 09:00 | 2020-01-20 18:00 |  |  | 2020-01-20 15:54 | 2020-01-20 15:54 |  |  | 100 | 100 | [15 empty] | 0.86957 | 0.000406 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2894 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018197
595 | Task(Task)-->P (Procurement) | Scrapper |  | 1.6.2.1 | Completed | No | No | 2019-11-17 | 2019-11-17 23:59 | 2020-03-11 09:00 | 2020-03-11 18:00 |  |  | 2020-03-11 10:57 | 2020-03-11 10:57 |  |  | 100 | 100 | [15 empty] | 0.43478 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2895 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018198
596 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.6.2.1 | Completed | No | No | 2020-03-10 09:00 | 2020-03-10 18:00 | 2020-03-11 09:00 | 2020-03-11 18:00 |  |  | 2020-03-11 12:41 | 2020-03-11 12:41 |  |  | 100 | 100 | [15 empty] | 4.1304 | 0.001928 | 0.19 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2896 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018199
597 | Task(Task)-->P (Procurement) | Chute & Skirt |  | 1.6.2.1 | Completed | No | No | 2020-03-10 09:00 | 2020-03-10 18:00 | 2020-03-11 09:00 | 2020-03-11 18:00 |  |  | 2020-03-11 10:57 | 2020-03-11 10:57 |  |  | 100 | 100 | [15 empty] | 18.913 | 0.008829 | 0.87 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2897 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018200
598 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.6.2.1 | Completed | No | No | 2020-05-19 09:00 | 2020-05-19 18:00 | 2020-04-16 09:00 | 2020-04-16 18:00 |  |  | 2020-04-16 10:57 | 2020-04-16 10:57 |  |  | 100 | 100 | [15 empty] | 0.21739 | 0.000101 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2898 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018201
599 | Task(Task)-->P (Procurement) | Gear Box |  | 1.6.2.1 | Completed | No | No | 2019-11-13 09:00 | 2019-11-13 18:00 | 2020-01-20 09:00 | 2020-01-20 18:00 |  |  | 2020-01-20 11:17 | 2020-01-20 11:17 |  |  | 100 | 100 | [15 empty] | 2.1739 | 0.001015 | 0.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2899 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018202
600 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.6.2.1 | Completed | No | No | 2019-11-21 09:00 | 2019-11-21 18:00 | 2020-01-22 09:00 | 2020-01-22 18:00 |  |  | 2020-01-22 10:41 | 2020-01-22 10:41 |  |  | 100 | 100 | [15 empty] | 0.65217 | 0.000304 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2900 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018203
601 | Task(Task)-->P (Procurement) | Building Structure |  | 1.6.2.1 | Completed | No | No | 2020-02-01 09:00 | 2020-02-01 18:00 | 2020-05-29 09:00 | 2020-05-29 18:00 |  |  | 2020-05-31 18:44 | 2020-05-31 18:44 |  |  | 100 | 100 | [15 empty] | 52.6087 | 0.024558 | 2.42 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2901 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018204
602 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR CONVEYING SYSTEM |  | 1.6.2.1 | Completed | No | No | 2019-12-16 09:00 | 2019-12-16 18:00 | 2020-01-13 09:00 | 2020-01-13 18:00 |  |  | 2020-01-13 10:57 | 2020-01-13 10:57 |  |  | 100 | 100 | [15 empty] | 0.43478 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2902 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018205
603 | Task(Task)-->P (Procurement) | LIGHT & LIGHT F IXTURES |  | 1.6.2.1 | Unscheduled | No | No | 2020-03-10 09:00 | 2020-03-10 18:00 | 2020-03-16 09:00 | 2020-03-16 18:00 | [6 empty] | 100 | 0 | [15 empty] | 5.8696 | 0.00274 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2903 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018206
604 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.6.2.1 | Completed | No | No | 2020-03-27 09:00 | 2020-03-27 18:00 | 2020-04-30 09:00 | 2020-04-30 18:00 |  |  | 2020-04-30 10:57 | 2020-04-30 10:57 |  |  | 100 | 100 | [15 empty] | 2.6087 | 0.001218 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2904 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018207
605 | Task(Task)-->P (Procurement) | LPBS |  | 1.6.2.1 | Unscheduled | No | No | 2020-03-20 09:00 | 2020-03-20 18:00 | 2020-04-14 09:00 | 2020-04-14 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2905 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018208
606 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.6.2.1 | Completed | No | No | 2020-01-08 09:00 | 2020-01-08 18:00 | 2020-01-08 09:00 | 2020-01-08 18:00 |  |  | 2020-01-08 10:57 | 2020-01-08 10:57 |  |  | 100 | 100 | [15 empty] | 0.43478 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2908 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018209
607 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.6.2.1 | Completed | No | No | 2019-12-30 09:00 | 2019-12-30 18:00 | 2019-12-30 09:00 | 2019-12-30 18:00 |  |  | 2019-12-30 10:57 | 2019-12-30 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2909 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018210
608 | Task(Task)-->P (Procurement) | CONTROL JUNCTION BOX |  | 1.6.2.1 | Completed | No | No | 2020-03-05 09:00 | 2020-03-05 18:00 | 2020-04-18 09:00 | 2020-04-18 18:00 |  |  | 2020-04-18 10:57 | 2020-04-18 10:57 |  |  | 100 | 100 | [15 empty] | 0.21739 | 0.000101 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2910 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018211
609 | Task(Task)-->P (Procurement) | TECHNICAL CLEARANCE | 1.6.2.2 | 1.6.2 | Work In Progress | No | No | 2019-09-28 09:00 | 2020-06-18 18:00 | 2019-12-30 09:00 | 2020-06-12 18:00 |  |  | 2020-01-22 11:19 |  |  |  | 100 | 94.1301 | [15 empty] | 4.9962 | 0.046681 | 4.59 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2911 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018212
610 | Task(Task)-->P (Procurement) | Rack & Pinion Gate |  | 1.6.2.2 | Completed | No | No | 2019-09-28 09:00 | 2020-03-12 18:00 | 2020-02-21 09:00 | 2020-04-28 18:00 |  |  | 2020-02-24 14:39 | 2020-04-28 14:39 |  |  | 100 | 100 | [15 empty] | 3.0435 | 0.001421 | 0.14 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2912 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018213
611 | Task(Task)-->P (Procurement) | Rod Gate |  | 1.6.2.2 | Completed | No | No | 2019-09-28 09:00 | 2019-12-31 18:00 | 2020-02-19 09:00 | 2020-03-06 18:00 |  |  | 2020-03-06 10:57 | 2020-03-06 10:57 |  |  | 100 | 100 | [15 empty] | 0.65217 | 0.000304 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2913 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018214
612 | Task(Task)-->P (Procurement) | Flap Gate |  | 1.6.2.2 | Completed | No | No | 2020-02-07 09:00 | 2020-03-22 23:59 | 2020-03-20 09:00 | 2020-04-28 18:00 |  |  | 2020-04-28 10:57 | 2020-04-28 10:57 |  |  | 100 | 100 | [15 empty] | 3.0435 | 0.001421 | 0.14 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2914 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018215
613 | Task(Task)-->P (Procurement) | Pulley |  | 1.6.2.2 | Completed | No | No | 2019-09-28 09:00 | 2020-01-04 18:00 | 2020-02-05 09:00 | 2020-02-10 18:00 |  |  | 2020-02-06 16:19 | 2020-02-10 16:19 |  |  | 100 | 100 | [15 empty] | 2.3913 | 0.001116 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2915 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018216
614 | Task(Task)-->P (Procurement) | Idler |  | 1.6.2.2 | Completed | No | No | 2019-12-20 09:00 | 2020-02-01 18:00 | 2020-02-13 09:00 | 2020-03-26 18:00 |  |  | 2020-02-14 10:57 | 2020-03-26 10:57 |  |  | 100 | 100 | [15 empty] | 0.86957 | 0.000406 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2916 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018217
615 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.6.2.2 | Completed | No | No | 2020-05-18 09:00 | 2020-06-01 18:00 | 2020-02-10 09:00 | 2020-02-10 18:00 |  |  | 2020-02-10 09:28 | 2020-02-10 09:28 |  |  | 100 | 100 | [15 empty] | 0.21739 | 0.000101 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2917 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018218
616 | Task(Task)-->P (Procurement) | Bearing |  | 1.6.2.2 | Completed | No | No | 2020-05-18 09:00 | 2020-06-16 18:00 | 2020-02-10 09:00 | 2020-02-10 18:00 |  |  | 2020-02-10 09:37 | 2020-02-10 09:37 |  |  | 100 | 100 | [15 empty] | 0.21739 | 0.000101 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2918 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018219
617 | Task(Task)-->P (Procurement) | Belting |  | 1.6.2.2 | Completed | No | No | 2019-11-08 09:00 | 2020-01-06 18:00 | 2020-01-20 09:00 | 2020-05-16 18:00 |  |  | 2020-05-16 10:57 | 2020-05-16 10:57 |  |  | 100 | 100 | [15 empty] | 0.86957 | 0.000406 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2919 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018220
618 | Task(Task)-->P (Procurement) | Scrapper |  | 1.6.2.2 | Completed | No | No | 2019-11-18 09:00 | 2020-03-16 18:00 | 2020-03-11 09:00 | 2020-03-26 18:00 |  |  | 2020-03-26 10:57 | 2020-03-26 10:57 |  |  | 100 | 100 | [15 empty] | 0.43478 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2920 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018221
619 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.6.2.2 | Completed | No | No | 2020-03-11 09:00 | 2020-03-20 18:00 | 2020-03-11 09:00 | 2020-03-17 18:00 |  |  | 2020-03-12 12:43 | 2020-03-17 12:43 |  |  | 100 | 100 | [15 empty] | 4.1304 | 0.001928 | 0.19 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2921 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018222
620 | Task(Task)-->P (Procurement) | Chute & Skirt |  | 1.6.2.2 | Completed | No | No | 2020-03-11 09:00 | 2020-03-20 18:00 | 2020-03-11 09:00 | 2020-03-17 18:00 |  |  | 2020-03-17 10:57 | 2020-03-17 10:57 |  |  | 100 | 100 | [15 empty] | 18.913 | 0.008829 | 0.87 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2922 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018223
621 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.6.2.2 | Completed | No | No | 2020-05-20 09:00 | 2020-06-18 18:00 | 2020-04-16 09:00 | 2020-04-16 18:00 |  |  | 2020-04-16 10:57 | 2020-04-16 10:57 |  |  | 100 | 100 | [15 empty] | 0.21739 | 0.000101 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2923 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018224
622 | Task(Task)-->P (Procurement) | Gear Box |  | 1.6.2.2 | Completed | No | No | 2019-11-14 09:00 | 2020-02-26 18:00 | 2020-01-20 09:00 | 2020-03-20 18:00 |  |  | 2020-01-22 11:19 | 2020-03-20 11:19 |  |  | 100 | 100 | [15 empty] | 2.1739 | 0.001015 | 0.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2924 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018225
623 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.6.2.2 | Completed | No | No | 2019-11-22 09:00 | 2020-03-19 18:00 | 2020-01-22 09:00 | 2020-04-13 18:00 |  |  | 2020-04-13 10:46 | 2020-04-13 10:46 |  |  | 100 | 100 | [15 empty] | 0.65217 | 0.000304 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2925 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018226
624 | Task(Task)-->P (Procurement) | Building Structure |  | 1.6.2.2 | Completed | No | No | 2020-02-02 | 2020-02-08 18:00 | 2020-05-29 09:00 | 2020-05-29 18:00 |  |  | 2020-05-29 17:31 | 2020-05-29 17:31 |  |  | 100 | 100 | [15 empty] | 52.6087 | 0.024558 | 2.42 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2926 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018227
625 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR CONVEYING SYSTEM |  | 1.6.2.2 | Completed | No | No | 2019-12-17 09:00 | 2019-12-31 18:00 | 2020-01-13 09:00 | 2020-04-11 18:00 |  |  | 2020-04-11 10:57 | 2020-04-11 10:57 |  |  | 100 | 100 | [15 empty] | 0.43478 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2927 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018228
626 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.6.2.2 | Unscheduled | No | No | 2020-03-11 09:00 | 2020-03-25 18:00 | 2020-03-16 09:00 | 2020-06-02 18:00 | [6 empty] | 100 | 0 | [15 empty] | 5.8696 | 0.00274 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2928 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018229
627 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.6.2.2 | Completed | No | No | 2020-03-28 09:00 | 2020-05-11 18:00 | 2020-04-30 09:00 | 2020-06-03 18:00 |  |  | 2020-06-03 10:57 | 2020-06-03 10:57 |  |  | 100 | 100 | [15 empty] | 2.6087 | 0.001218 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2929 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018230
628 | Task(Task)-->P (Procurement) | LPBS |  | 1.6.2.2 | Unscheduled | No | No | 2020-03-21 09:00 | 2020-04-04 18:00 | 2020-04-14 09:00 | 2020-06-12 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2930 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018231
629 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.6.2.2 | Completed | No | No | 2020-01-09 09:00 | 2020-01-22 18:00 | 2020-01-08 09:00 | 2020-03-10 18:00 |  |  | 2020-03-10 10:57 | 2020-03-10 10:57 |  |  | 100 | 100 | [15 empty] | 0.43478 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2933 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018232
630 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.6.2.2 | Completed | No | No | 2019-12-31 09:00 | 2020-01-16 18:00 | 2019-12-30 09:00 | 2020-03-07 18:00 |  |  | 2020-03-07 10:57 | 2020-03-07 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2934 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018233
631 | Task(Task)-->P (Procurement) | CONTROL JUNCTION BOX |  | 1.6.2.2 | Completed | No | No | 2020-03-06 09:00 | 2020-03-13 18:00 | 2020-04-18 09:00 | 2020-06-02 18:00 |  |  | 2020-06-02 10:57 | 2020-06-02 10:57 |  |  | 100 | 100 | [15 empty] | 0.21739 | 0.000101 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2935 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018234
632 | Task(Task)-->P (Procurement) | ORDERING | 1.6.2.3 | 1.6.2 | Work In Progress | No | No | 2020-01-01 09:00 | 2020-07-18 18:00 | 2020-02-10 09:00 | 2020-09-04 18:00 |  |  | 2020-01-05 08:00 |  |  |  | 100 | 99.1301 | [15 empty] | 10.0033 | 0.093463 | 9.19 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2936 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018235
633 | Task(Task)-->P (Procurement) | Rack & Pinion Gate |  | 1.6.2.3 | Completed | No | No | 2020-03-13 09:00 | 2020-04-11 18:00 | 2020-04-28 09:00 | 2020-08-22 18:00 |  |  | 2020-04-28 15:39 | 2020-08-22 15:39 |  |  | 100 | 100 | [15 empty] | 3.0435 | 0.002845 | 0.28 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2937 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018236
634 | Task(Task)-->P (Procurement) | Rod Gate |  | 1.6.2.3 | Completed | No | No | 2020-01-01 09:00 | 2020-01-30 18:00 | 2020-03-06 09:00 | 2020-08-22 18:00 |  |  | 2020-03-06 16:47 | 2020-08-22 16:47 |  |  | 100 | 100 | [15 empty] | 0.65217 | 0.00061 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2938 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018237
635 | Task(Task)-->P (Procurement) | Flap Gate |  | 1.6.2.3 | Completed | No | No | 2020-03-23 09:00 | 2020-04-21 18:00 | 2020-04-28 09:00 | 2020-08-22 18:00 |  |  | 2020-04-28 16:12 | 2020-08-22 16:12 |  |  | 100 | 100 | [15 empty] | 3.1522 | 0.002946 | 0.29 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2939 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018238
636 | Task(Task)-->P (Procurement) | Pulley |  | 1.6.2.3 | Completed | No | No | 2020-01-05 | 2020-02-03 18:00 | 2020-02-10 09:00 | 2020-03-21 18:00 |  |  | 2020-01-05 08:00 | 2020-03-21 16:05 |  |  | 100 | 100 | [15 empty] | 2.3913 | 0.002235 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2940 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018239
637 | Task(Task)-->P (Procurement) | Idler |  | 1.6.2.3 | Completed | No | No | 2020-02-02 | 2020-03-02 18:00 | 2020-03-26 09:00 | 2020-04-30 18:00 |  |  | 2020-02-02 08:00 | 2020-04-29 16:05 |  |  | 100 | 100 | [15 empty] | 0.86957 | 0.000813 | 0.08 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2941 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018240
638 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.6.2.3 | Completed | No | No | 2020-06-02 09:00 | 2020-07-01 18:00 | 2020-02-10 09:00 | 2020-03-24 18:00 |  |  | 2020-02-11 09:32 | 2020-03-24 09:32 |  |  | 100 | 100 | [15 empty] | 0.21739 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2942 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018241
639 | Task(Task)-->P (Procurement) | Bearing |  | 1.6.2.3 | Completed | No | No | 2020-06-17 09:00 | 2020-07-16 18:00 | 2020-02-10 09:00 | 2020-03-24 18:00 |  |  | 2020-02-11 09:40 | 2020-03-24 09:40 |  |  | 100 | 100 | [15 empty] | 0.32609 | 0.000305 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2943 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018242
640 | Task(Task)-->P (Procurement) | Belting |  | 1.6.2.3 | Completed | No | No | 2020-01-07 09:00 | 2020-02-20 18:00 | 2020-05-16 09:00 | 2020-09-04 18:00 |  |  | 2020-05-16 16:24 | 2020-09-04 16:24 |  |  | 100 | 100 | [15 empty] | 0.86957 | 0.000813 | 0.08 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2944 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018243
641 | Task(Task)-->P (Procurement) | Scrapper |  | 1.6.2.3 | Completed | No | No | 2020-03-17 09:00 | 2020-04-15 18:00 | 2020-03-26 09:00 | 2020-05-30 18:00 |  |  | 2020-05-30 10:57 | 2020-05-30 10:57 |  |  | 100 | 100 | [15 empty] | 0.43478 | 0.000406 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2945 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018244
642 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.6.2.3 | Completed | No | No | 2020-03-21 09:00 | 2020-04-19 23:59 | 2020-03-17 09:00 | 2020-07-06 18:00 |  |  | 2020-03-18 12:44 | 2020-07-06 12:44 |  |  | 100 | 100 | [15 empty] | 4.1304 | 0.00386 | 0.38 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2946 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018245
643 | Task(Task)-->P (Procurement) | Chute & Skirt |  | 1.6.2.3 | Completed | No | No | 2020-03-21 09:00 | 2020-04-19 23:59 | 2020-03-17 09:00 | 2020-07-06 18:00 |  |  | 2020-03-18 12:49 | 2020-07-06 12:49 |  |  | 100 | 100 | [15 empty] | 18.8043 | 0.017575 | 1.73 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2947 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018246
644 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.6.2.3 | Unscheduled | No | No | 2020-06-19 09:00 | 2020-07-18 18:00 | 2020-04-16 09:00 | 2020-08-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.21739 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2948 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018247
645 | Task(Task)-->P (Procurement) | Gear Box |  | 1.6.2.3 | Completed | No | No | 2020-02-27 09:00 | 2020-03-27 18:00 | 2020-03-20 09:00 | 2020-04-30 18:00 |  |  | 2020-03-21 11:21 | 2020-04-30 11:21 |  |  | 100 | 100 | [15 empty] | 2.1739 | 0.002032 | 0.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2949 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018248
646 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.6.2.3 | Completed | No | No | 2020-03-20 09:00 | 2020-04-18 18:00 | 2020-04-13 09:00 | 2020-04-30 18:00 |  |  | 2020-04-14 11:11 | 2020-04-30 11:11 |  |  | 100 | 100 | [15 empty] | 0.54348 | 0.000508 | 0.05 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2950 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018249
647 | Task(Task)-->P (Procurement) | Building Structure |  | 1.6.2.3 | Completed | No | No | 2020-02-09 | 2020-03-09 18:00 | 2020-05-29 09:00 | 2020-05-31 23:59 |  |  | 2020-05-31 18:49 | 2020-05-31 18:49 |  |  | 100 | 100 | [15 empty] | 52.7174 | 0.049271 | 4.85 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2951 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018250
648 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR CONVEYING SYSTEM |  | 1.6.2.3 | Completed | No | No | 2020-01-01 09:00 | 2020-01-16 18:00 | 2020-04-11 09:00 | 2020-07-20 18:00 |  |  | 2020-04-12 15:47 | 2020-06-20 15:47 |  |  | 100 | 100 | [15 empty] | 0.43478 | 0.000406 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2952 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018251
649 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.6.2.3 | Completed | No | No | 2020-03-26 09:00 | 2020-04-10 18:00 | 2020-06-02 09:00 | 2020-07-31 18:00 |  |  | 2020-06-03 15:51 | 2020-06-29 15:51 |  |  | 100 | 100 | [15 empty] | 5.7609 | 0.005384 | 0.53 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2953 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018252
650 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.6.2.3 | Completed | No | No | 2020-05-12 09:00 | 2020-06-25 18:00 | 2020-06-03 09:00 | 2020-06-24 18:00 |  |  | 2020-06-15 10:57 | 2020-06-15 10:57 |  |  | 100 | 100 | [15 empty] | 2.6087 | 0.002438 | 0.24 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2954 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018253
651 | Task(Task)-->P (Procurement) | LPBS |  | 1.6.2.3 | Unscheduled | No | No | 2020-04-05 | 2020-04-20 18:00 | 2020-06-12 09:00 | 2020-08-19 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.1087 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2955 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018254
652 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.6.2.3 | Unscheduled | No | No | 2020-01-23 09:00 | 2020-02-05 18:00 | 2020-03-10 09:00 | 2020-08-17 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.32609 | 0.000305 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2958 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018255
653 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.6.2.3 | Unscheduled | No | No | 2020-01-17 09:00 | 2020-02-01 18:00 | 2020-03-07 09:00 | 2020-08-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2959 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018256
654 | Task(Task)-->P (Procurement) | CONTROL JUNCTION BOX |  | 1.6.2.3 | Unscheduled | No | No | 2020-03-14 09:00 | 2020-03-21 18:00 | 2020-06-02 09:00 | 2020-08-19 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.21739 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2960 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018257
655 | Task(Task)-->P (Procurement) | ITP APPROVAL | 1.6.2.4 | 1.6.2 | Work In Progress | No | No | 2020-01-17 09:00 | 2020-08-25 18:00 | 2020-03-21 09:00 | 2020-10-30 18:00 |  |  | 2020-04-13 16:21 |  |  |  | 100 | 11.5212 | [15 empty] | 4.9962 | 0.046681 | 4.59 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2961 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018258
656 | Task(Task)-->P (Procurement) | Rack & Pinion Gate |  | 1.6.2.4 | Unscheduled | No | No | 2020-04-12 | 2020-05-21 18:00 | 2020-08-22 09:00 | 2020-10-30 18:00 | [6 empty] | 100 | 0 | [15 empty] | 3.0435 | 0.001421 | 0.14 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2962 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018259
657 | Task(Task)-->P (Procurement) | Rod Gate |  | 1.6.2.4 | Completed | No | No | 2020-01-31 09:00 | 2020-03-10 18:00 | 2020-06-25 09:00 | 2020-06-25 18:00 |  |  | 2020-06-25 15:36 | 2020-06-25 15:36 |  |  | 100 | 100 | [15 empty] | 0.65217 | 0.000304 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2963 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018260
658 | Task(Task)-->P (Procurement) | Flap Gate |  | 1.6.2.4 | Unscheduled | No | No | 2020-04-22 09:00 | 2020-05-31 23:59 | 2020-08-22 09:00 | 2020-10-30 18:00 |  |  | 2020-08-22 16:16 |  |  |  | 100 | 0 | [15 empty] | 3.0435 | 0.001421 | 0.14 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2964 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018261
659 | Task(Task)-->P (Procurement) | Pulley |  | 1.6.2.4 | Unscheduled | No | No | 2020-02-04 09:00 | 2020-03-14 18:00 | 2020-03-21 09:00 | 2020-05-11 18:00 | [6 empty] | 100 | 0 | [15 empty] | 2.3913 | 0.001116 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2965 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018262
660 | Task(Task)-->P (Procurement) | Idler |  | 1.6.2.4 | Completed | No | No | 2020-03-03 09:00 | 2020-04-11 18:00 | 2020-04-30 09:00 | 2020-05-19 18:00 |  |  | 2020-04-13 16:21 | 2020-05-19 16:21 |  |  | 100 | 100 | [15 empty] | 0.86957 | 0.000406 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2966 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018263
661 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.6.2.4 | Unscheduled | No | No | 2020-07-02 09:00 | 2020-08-10 18:00 | 2020-03-24 09:00 | 2020-08-13 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.21739 | 0.000101 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2967 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018264
662 | Task(Task)-->P (Procurement) | Bearing |  | 1.6.2.4 | Unscheduled | No | No | 2020-07-17 09:00 | 2020-08-25 18:00 | 2020-03-24 09:00 | 2020-03-29 23:59 | [6 empty] | 100 | 0 | [15 empty] | 0.21739 | 0.000101 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2968 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018265
663 | Task(Task)-->P (Procurement) | Belting |  | 1.6.2.4 | Completed | No | No | 2020-02-21 09:00 | 2020-03-31 18:00 | 2020-09-04 09:00 | 2020-09-30 18:00 |  |  | 2020-09-04 16:30 | 2020-09-30 16:30 |  |  | 100 | 100 | [15 empty] | 0.86957 | 0.000406 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2969 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018266
664 | Task(Task)-->P (Procurement) | Scrapper |  | 1.6.2.4 | Completed | No | No | 2020-04-16 09:00 | 2020-05-25 18:00 | 2020-05-30 09:00 | 2020-06-25 18:00 |  |  | 2020-05-30 16:30 | 2020-06-25 16:31 |  |  | 100 | 100 | [15 empty] | 0.43478 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2970 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018267
665 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.6.2.4 | Unscheduled | No | No | 2020-04-20 09:00 | 2020-05-29 18:00 | 2020-07-06 09:00 | 2020-07-16 18:00 | [6 empty] | 100 | 0 | [15 empty] | 4.1304 | 0.001928 | 0.19 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2971 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018268
666 | Task(Task)-->P (Procurement) | Chute & Skirt |  | 1.6.2.4 | Unscheduled | No | No | 2020-04-20 09:00 | 2020-05-29 18:00 | 2020-07-06 09:00 | 2020-07-16 18:00 | [6 empty] | 100 | 0 | [15 empty] | 18.913 | 0.008829 | 0.87 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2972 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018269
667 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.6.2.4 | Unscheduled | No | No | 2020-07-19 | 2020-08-17 18:00 | 2020-06-25 09:00 | 2020-06-25 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.21739 | 0.000101 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2973 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018270
668 | Task(Task)-->P (Procurement) | Gear Box |  | 1.6.2.4 | Completed | No | No | 2020-03-28 09:00 | 2020-05-06 18:00 | 2020-04-30 09:00 | 2020-06-22 18:00 |  |  | 2020-04-30 16:57 | 2020-06-22 16:57 |  |  | 100 | 100 | [15 empty] | 2.1739 | 0.001015 | 0.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2974 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018271
669 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.6.2.4 | Completed | No | No | 2020-04-19 | 2020-05-28 18:00 | 2020-04-30 09:00 | 2020-06-18 18:00 |  |  | 2020-04-30 01:54 | 2020-06-18 17:31 |  |  | 100 | 100 | [15 empty] | 0.65217 | 0.000304 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2975 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018272
670 | Task(Task)-->P (Procurement) | Building Structure |  | 1.6.2.4 | Unscheduled | No | No | 2020-03-10 09:00 | 2020-03-16 18:00 | 2020-05-31 | 2020-08-04 18:00 |  |  | 2020-06-25 19:04 |  |  |  | 100 | 0 | [15 empty] | 52.6087 | 0.024558 | 2.42 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2976 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018273
671 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR CONVEYING SYSTEM |  | 1.6.2.4 | Unscheduled | No | No | 2020-01-17 09:00 | 2020-02-25 18:00 | 2020-09-08 09:00 | 2020-10-10 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.43478 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2977 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018274
672 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.6.2.4 | Completed | No | No | 2020-04-11 09:00 | 2020-05-20 18:00 | 2020-07-28 09:00 | 2020-09-08 18:00 |  |  | 2020-07-08 17:23 | 2020-09-08 17:23 |  |  | 100 | 100 | [15 empty] | 5.8696 | 0.00274 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2978 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018275
673 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.6.2.4 | Unscheduled | No | No | 2020-06-26 09:00 | 2020-08-04 18:00 | 2020-06-23 09:00 | 2020-09-08 18:00 |  |  | 2020-06-23 17:32 |  |  |  | 100 | 0 | [15 empty] | 2.6087 | 0.001218 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2979 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018276
674 | Task(Task)-->P (Procurement) | LPBS |  | 1.6.2.4 | Completed | No | No | 2020-04-21 09:00 | 2020-05-30 18:00 | 2020-07-29 09:00 | 2020-08-21 18:00 |  |  | 2020-07-29 14:58 | 2020-08-22 12:54 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2980 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018277
675 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.6.2.4 | Unscheduled | No | No | 2020-02-06 09:00 | 2020-03-16 18:00 | 2020-09-24 09:00 | 2020-10-30 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.43478 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2983 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018278
676 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.6.2.4 | Unscheduled | No | No | 2020-02-02 | 2020-02-22 18:00 | 2020-08-02 | 2020-08-22 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2984 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018279
677 | Task(Task)-->P (Procurement) | CONTROL JUNCTION BOX |  | 1.6.2.4 | Unscheduled | No | No | 2020-03-22 | 2020-04-30 18:00 | 2020-07-29 09:00 | 2020-09-21 18:00 |  |  | 2020-07-29 14:53 |  |  |  | 100 | 0 | [15 empty] | 0.21739 | 0.000101 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2985 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018280
678 | Task(Task)-->P (Procurement) | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE | 1.6.2.5 | 1.6.2 | Work In Progress | No | No | 2020-01-17 09:00 | 2020-09-16 18:00 | 2020-03-21 09:00 | 2020-10-21 18:00 |  |  | 2020-03-22 18:03 |  |  |  | 100 | 35.3592 | [15 empty] | 14.9995 | 0.14014 | 13.78 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2986 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018281
679 | Task(Task)-->P (Procurement) | Rack & Pinion Gate |  | 1.6.2.5 | Unscheduled | No | No | 2020-04-12 | 2020-06-10 18:00 | 2020-08-22 09:00 | 2020-10-15 18:00 |  |  | 2020-08-22 16:45 |  |  |  | 100 | 15 | [15 empty] | 3.0479 | 0.004271 | 0.42 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2987 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018282
680 | Task(Task)-->P (Procurement) | Rod Gate |  | 1.6.2.5 | Completed | No | No | 2020-01-31 09:00 | 2020-03-30 18:00 | 2020-08-22 09:00 | 2020-08-22 18:00 |  |  | 2020-08-22 15:37 | 2020-08-22 15:37 |  |  | 100 | 100 | [15 empty] | 0.65312 | 0.000915 | 0.09 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2988 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018283
681 | Task(Task)-->P (Procurement) | Flap Gate |  | 1.6.2.5 | Unscheduled | No | No | 2020-04-22 09:00 | 2020-06-20 18:00 | 2020-08-22 09:00 | 2020-10-15 18:00 |  |  | 2020-08-22 16:14 |  |  |  | 100 | 15 | [15 empty] | 3.1205 | 0.004373 | 0.43 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2989 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018284
682 | Task(Task)-->P (Procurement) | Pulley |  | 1.6.2.5 | Completed | No | No | 2020-02-04 09:00 | 2020-03-29 23:59 | 2020-03-21 09:00 | 2020-03-25 18:00 |  |  | 2020-03-22 18:03 | 2020-03-25 18:03 |  |  | 100 | 100 | [15 empty] | 2.3948 | 0.003356 | 0.33 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2990 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018285
683 | Task(Task)-->P (Procurement) | Idler |  | 1.6.2.5 | Completed | No | No | 2020-03-03 09:00 | 2020-05-01 18:00 | 2020-04-30 09:00 | 2020-06-25 18:00 |  |  | 2020-06-25 14:53 | 2020-06-25 14:53 |  |  | 100 | 100 | [15 empty] | 0.87083 | 0.00122 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2991 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018286
684 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.6.2.5 | Completed | No | No | 2020-07-02 09:00 | 2020-08-30 23:59 | 2020-03-24 09:00 | 2020-06-29 18:00 |  |  | 2020-05-14 14:59 | 2020-06-29 14:59 |  |  | 100 | 100 | [15 empty] | 0.14514 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2992 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018287
685 | Task(Task)-->P (Procurement) | Bearing |  | 1.6.2.5 | Completed | No | No | 2020-07-17 09:00 | 2020-07-17 18:00 | 2020-03-24 09:00 | 2020-03-24 18:00 |  |  | 2020-03-24 10:05 | 2020-03-24 10:05 |  |  | 100 | 100 | [15 empty] | 0.29028 | 0.000407 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2993 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018288
686 | Task(Task)-->P (Procurement) | Belting |  | 1.6.2.5 | Unscheduled | No | No | 2020-02-21 09:00 | 2020-04-20 18:00 | 2020-09-04 09:00 | 2020-10-15 18:00 |  |  | 2020-09-04 16:36 |  |  |  | 100 | 50 | [15 empty] | 0.79826 | 0.001119 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2994 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018289
687 | Task(Task)-->P (Procurement) | Scrapper |  | 1.6.2.5 | Completed | No | No | 2020-04-16 09:00 | 2020-06-14 23:59 | 2020-05-30 09:00 | 2020-07-30 18:00 |  |  | 2020-05-30 16:35 | 2020-07-30 16:35 |  |  | 100 | 100 | [15 empty] | 0.43541 | 0.00061 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2995 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018290
688 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.6.2.5 | Completed | No | No | 2020-04-20 09:00 | 2020-09-16 18:00 | 2020-07-06 09:00 | 2020-07-06 18:00 |  |  | 2020-07-06 12:45 | 2020-07-06 12:45 |  |  | 100 | 100 | [15 empty] | 4.1364 | 0.005797 | 0.57 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2996 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018291
689 | Task(Task)-->P (Procurement) | Chute & Skirt |  | 1.6.2.5 | Completed | No | No | 2020-04-20 09:00 | 2020-09-16 18:00 | 2020-07-06 09:00 | 2020-07-06 18:00 |  |  | 2020-07-06 12:51 | 2020-07-06 12:51 |  |  | 100 | 100 | [15 empty] | 18.8679 | 0.026442 | 2.6 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2997 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018292
690 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.6.2.5 | Unscheduled | No | No | 2020-07-19 | 2020-08-27 18:00 | 2020-08-04 09:00 | 2020-08-04 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.21771 | 0.000305 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2998 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018293
691 | Task(Task)-->P (Procurement) | Gear Box |  | 1.6.2.5 | Completed | No | No | 2020-03-28 09:00 | 2020-05-26 18:00 | 2020-04-30 09:00 | 2020-07-01 18:00 |  |  | 2020-04-30 15:33 | 2020-07-01 15:33 |  |  | 100 | 100 | [15 empty] | 2.1771 | 0.003051 | 0.3 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2999 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018294
692 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.6.2.5 | Completed | No | No | 2020-04-19 | 2020-06-17 18:00 | 2020-04-30 09:00 | 2020-07-30 18:00 |  |  | 2020-04-30 15:31 | 2020-07-06 15:31 |  |  | 100 | 100 | [15 empty] | 0.58055 | 0.000814 | 0.08 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3000 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018295
693 | Task(Task)-->P (Procurement) | Building Structure |  | 1.6.2.5 | Unscheduled | No | No | 2020-03-08 | 2020-03-14 18:00 | 2020-05-31 | 2020-07-29 18:00 | [6 empty] | 100 | 0 | [15 empty] | 52.7576 | 0.073936 | 7.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3001 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018296
694 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR CONVEYING SYSTEM |  | 1.6.2.5 | Completed | No | No | 2020-01-17 09:00 | 2020-03-01 23:59 | 2020-07-07 09:00 | 2020-09-29 18:00 |  |  | 2020-07-07 10:15 | 2020-09-21 12:52 |  |  | 100 | 100 | [15 empty] | 0.43541 | 0.00061 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3002 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018297
695 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.6.2.5 | Unscheduled | No | No | 2020-04-11 09:00 | 2020-05-25 18:00 | 2020-07-10 09:00 | 2020-10-16 18:00 |  |  | 2020-07-14 10:44 |  |  |  | 100 | 0 | [15 empty] | 5.8055 | 0.008136 | 0.8 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3003 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018298
696 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.6.2.5 | Completed | No | No | 2020-06-26 09:00 | 2020-08-09 23:59 | 2020-05-30 09:00 | 2020-08-08 18:00 |  |  | 2020-06-18 17:08 | 2020-08-07 15:00 |  |  | 100 | 100 | [15 empty] | 2.6125 | 0.003661 | 0.36 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3004 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018299
697 | Task(Task)-->P (Procurement) | LPBS |  | 1.6.2.5 | Completed | No | No | 2020-04-21 09:00 | 2020-06-04 18:00 | 2020-07-25 09:00 | 2020-08-22 18:00 |  |  | 2020-07-24 18:43 | 2020-08-22 12:57 |  |  | 100 | 100 | [15 empty] | 0.072569 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3005 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018300
698 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.6.2.5 | Completed | No | No | 2020-02-06 09:00 | 2020-03-21 18:00 | 2020-08-11 09:00 | 2020-09-19 18:00 |  |  | 2020-08-11 13:11 | 2020-09-19 12:57 |  |  | 100 | 100 | [15 empty] | 0.36284 | 0.000509 | 0.05 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3008 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018301
699 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.6.2.5 | Unscheduled | No | No | 2020-02-02 | 2020-03-03 18:00 | 2020-08-09 | 2020-10-20 18:00 |  |  | 2020-08-09 13:14 |  |  |  | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3009 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018302
700 | Task(Task)-->P (Procurement) | CONTROL JUNCTION BOX |  | 1.6.2.5 | Unscheduled | No | No | 2020-03-22 | 2020-05-05 18:00 | 2020-07-25 09:00 | 2020-10-21 18:00 |  |  | 2020-07-25 12:53 |  |  |  | 100 | 0 | [15 empty] | 0.21771 | 0.000305 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3010 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018303
701 | Task(Task)-->P (Procurement) | MANUFACTURING & RECEIPT AT SITE (MRN) | 1.6.2.6 | 1.6.2 | Unscheduled | No | No | 2020-03-02 09:00 | 2021-02-13 18:00 | 2020-03-24 09:00 | 2021-05-13 18:00 |  |  | 2020-03-25 18:05 |  |  |  | 81.1809 | 1.2128 | [15 empty] | 60.0087 | 0.56068 | 55.13 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3011 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018304
702 | Task(Task)-->P (Procurement) | Rack & Pinion Gate |  | 1.6.2.6 | Unscheduled | No | No | 2020-06-11 09:00 | 2020-12-07 18:00 | 2020-10-31 09:00 | 2021-04-28 18:00 | [6 empty] | 66.1111 | 0 | [15 empty] | 3.0276 | 0.016975 | 1.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3012 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018305
703 | Task(Task)-->P (Procurement) | Rod Gate |  | 1.6.2.6 | Unscheduled | No | No | 2020-06-11 09:00 | 2020-12-07 18:00 | 2020-08-22 09:00 | 2021-03-25 18:00 |  |  | 2020-08-22 15:38 |  |  |  | 66.1111 | 10 | [15 empty] | 0.65265 | 0.003659 | 0.36 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3013 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018306
704 | Task(Task)-->P (Procurement) | Flap Gate |  | 1.6.2.6 | Unscheduled | No | No | 2020-06-21 | 2021-01-01 18:00 | 2020-10-31 09:00 | 2021-05-13 18:00 | [6 empty] | 55.8974 | 0 | [15 empty] | 3.1182 | 0.017483 | 1.72 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3014 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018307
705 | Task(Task)-->P (Procurement) | Pulley |  | 1.6.2.6 | Unscheduled | No | No | 2020-03-30 09:00 | 2020-11-20 18:00 | 2020-03-25 09:00 | 2020-11-30 18:00 |  |  | 2020-03-25 18:05 |  |  |  | 81.3559 | 0 | [15 empty] | 2.4293 | 0.01362 | 1.34 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3015 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018308
706 | Task(Task)-->P (Procurement) | Idler |  | 1.6.2.6 | Unscheduled | No | No | 2020-05-02 09:00 | 2020-11-13 18:00 | 2020-06-25 09:00 | 2020-12-31 18:00 | [6 empty] | 81.1225 | 0 | [15 empty] | 0.8702 | 0.004879 | 0.48 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3016 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018309
707 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.6.2.6 | Unscheduled | No | No | 2020-08-31 09:00 | 2020-12-23 18:00 | 2020-06-29 09:00 | 2020-12-31 18:00 | [6 empty] | 33.0435 | 0 | [15 empty] | 0.18129 | 0.001016 | 0.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3017 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018310
708 | Task(Task)-->P (Procurement) | Bearing |  | 1.6.2.6 | Unscheduled | No | No | 2020-08-26 09:00 | 2020-12-23 18:00 | 2020-03-24 09:00 | 2020-09-09 18:00 | [6 empty] | 35.8333 | 0 | [15 empty] | 0.30819 | 0.001728 | 0.17 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3018 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018311
709 | Task(Task)-->P (Procurement) | Belting |  | 1.6.2.6 | Unscheduled | No | No | 2020-04-21 09:00 | 2020-11-16 18:00 | 2020-10-16 09:00 | 2021-05-13 18:00 | [6 empty] | 80.9524 | 0 | [15 empty] | 0.81581 | 0.004574 | 0.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3019 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018312
710 | Task(Task)-->P (Procurement) | Scrapper |  | 1.6.2.6 | Unscheduled | No | No | 2020-06-15 09:00 | 2020-12-11 18:00 | 2020-07-30 09:00 | 2020-12-31 18:00 | [6 empty] | 63.8889 | 0 | [15 empty] | 0.39884 | 0.002236 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3020 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018313
711 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.6.2.6 | Unscheduled | No | No | 2020-06-19 09:00 | 2021-02-13 18:00 | 2020-07-06 09:00 | 2021-01-31 23:59 | [6 empty] | 46.25 | 0 | [15 empty] | 4.1153 | 0.023073 | 2.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3021 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018314
712 | Task(Task)-->P (Procurement) | Chute & Skirt |  | 1.6.2.6 | Unscheduled | No | No | 2020-06-19 09:00 | 2021-02-13 18:00 | 2020-07-06 09:00 | 2021-01-31 23:59 | [6 empty] | 46.25 | 0 | [15 empty] | 18.8724 | 0.10581 | 10.41 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3022 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018315
713 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.6.2.6 | Unscheduled | No | No | 2020-08-28 09:00 | 2020-12-25 18:00 | 2020-08-04 09:00 | 2020-12-25 18:00 | [6 empty] | 34.1667 | 0 | [15 empty] | 0.23568 | 0.001321 | 0.13 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3023 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018316
714 | Task(Task)-->P (Procurement) | Gear Box |  | 1.6.2.6 | Unscheduled | No | No | 2020-05-27 09:00 | 2020-12-22 18:00 | 2020-07-01 09:00 | 2020-12-31 18:00 |  |  | 2020-07-01 17:25 |  |  |  | 63.8095 | 30 | [15 empty] | 2.1936 | 0.012299 | 1.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3024 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018317
715 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.6.2.6 | Unscheduled | No | No | 2020-06-18 09:00 | 2020-12-15 18:00 | 2020-07-30 09:00 | 2020-10-05 18:00 |  |  | 2020-07-30 17:44 |  |  |  | 61.8785 | 90 | [15 empty] | 0.54387 | 0.003049 | 0.3 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3025 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018318
716 | Task(Task)-->P (Procurement) | Building Structure |  | 1.6.2.6 | Unscheduled | No | No | 2020-03-17 09:00 | 2020-09-04 18:00 | 2020-07-29 09:00 | 2021-03-31 18:00 | [6 empty] | 100 | 0 | [15 empty] | 52.7194 | 0.29558 | 29.08 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3026 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018319
717 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR CONVEYING SYSTEM |  | 1.6.2.6 | Unscheduled | No | No | 2020-03-02 09:00 | 2020-09-26 18:00 | 2020-10-11 | 2021-05-07 18:00 |  |  | 2020-09-22 12:53 |  |  |  | 100 | 0 | [15 empty] | 0.4351 | 0.002439 | 0.24 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3027 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018320
718 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.6.2.6 | Unscheduled | No | No | 2020-05-26 09:00 | 2020-10-21 18:00 | 2020-10-17 09:00 | 2021-03-14 23:59 | [6 empty] | 90.604 | 0 | [15 empty] | 5.7832 | 0.032425 | 3.19 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3028 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018321
719 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.6.2.6 | Unscheduled | No | No | 2020-08-10 09:00 | 2020-11-07 18:00 | 2020-09-09 09:00 | 2020-12-07 18:00 |  |  | 2020-08-07 15:00 |  |  |  | 65.5556 | 0 | [15 empty] | 2.6287 | 0.014739 | 1.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3029 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018322
720 | Task(Task)-->P (Procurement) | LPBS |  | 1.6.2.6 | Unscheduled | No | No | 2020-06-05 09:00 | 2020-09-16 18:00 | 2020-08-23 | 2020-12-04 18:00 |  |  | 2020-08-22 13:00 |  |  |  | 100 | 0 | [15 empty] | 0.072516 | 0.000407 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3030 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018323
721 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.6.2.6 | Unscheduled | No | No | 2020-03-22 | 2020-08-05 18:00 | 2020-10-31 09:00 | 2021-03-16 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.32632 | 0.00183 | 0.18 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3033 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018324
722 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.6.2.6 | Unscheduled | No | No | 2020-03-04 09:00 | 2020-07-02 18:00 | 2020-10-21 09:00 | 2021-02-18 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.018129 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3034 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018325
723 | Task(Task)-->P (Procurement) | CONTROL JUNCTION BOX |  | 1.6.2.6 | Unscheduled | No | No | 2020-05-06 09:00 | 2020-09-16 18:00 | 2020-10-22 09:00 | 2021-03-04 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.25381 | 0.001423 | 0.14 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3035 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018326
724 | Task(Task)-->C (Construction) | CONSTRUCTION | 1.6.3 | 1.6 | Unscheduled | No | No | 2020-03-21 09:00 | 2021-09-09 18:00 | 2020-08-01 09:00 | 2022-04-01 18:00 | [6 empty] | 22.8669 | 0 | [15 empty] | 41.343 | 0.69802 | 68.65 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3036 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018327
725 | Task(Task)-->C (Construction) | CIVIL | 1.6.3.1 | 1.6.3 | Unscheduled | No | No | 2020-03-21 09:00 | 2021-02-04 18:00 | 2020-08-01 09:00 | 2021-06-15 18:00 | [6 empty] | 32.7997 | 0 | [15 empty] | 42.7677 | 0.29853 | 29.36 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3037 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018328
726 | Task(Task)-->C (Construction) | AVAILABILITY OF FRONT BY NTPC |  | 1.6.3.1 | Unscheduled | No | No | 2020-03-21 09:00 | 2020-03-21 18:00 | 2020-08-01 09:00 | 2020-08-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3038 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018329
727 | Task(Task)-->C (Construction) | EXCAVATION |  | 1.6.3.1 | Unscheduled | No | No | 2020-03-28 09:00 | 2020-04-09 18:00 | 2020-08-02 | 2020-08-14 18:00 | [6 empty] | 100 | 0 | [15 empty] | 5.4155 | 0.016167 | 1.59 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 5978 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3039 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | Excavation | [21 empty] | 1018330
728 | Task(Task)-->C (Construction) | PCC |  | 1.6.3.1 | Unscheduled | No | No | 2020-05-16 09:00 | 2020-05-20 18:00 | 2020-09-24 09:00 | 2020-09-28 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.81744 | 0.00244 | 0.24 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3040 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | PCC | [21 empty] | 1018331
729 | Task(Task)-->C (Construction) | RAFT |  | 1.6.3.1 | Unscheduled | No | No | 2020-05-20 09:00 | 2020-06-04 18:00 | 2020-09-28 09:00 | 2020-10-13 18:00 | [6 empty] | 100 | 0 | [15 empty] | 19.891 | 0.05938 | 5.84 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3041 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018332
730 | Task(Task)-->C (Construction) | PADESTALS FOR SURGE HOPPER BLDG. STR. |  | 1.6.3.1 | Unscheduled | No | No | 2020-06-05 09:00 | 2020-06-30 18:00 | 2020-10-14 09:00 | 2020-11-08 23:59 | [6 empty] | 100 | 0 | [15 empty] | 3.5082 | 0.010473 | 1.03 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3042 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018333
731 | Task(Task)-->C (Construction) | RCC FLOOR FOR TAIL PULLEY OF PC-1A/B |  | 1.6.3.1 | Unscheduled | No | No | 2020-09-12 09:00 | 2020-09-22 18:00 | 2021-01-21 09:00 | 2021-01-31 23:59 | [6 empty] | 100 | 0 | [15 empty] | 3.1676 | 0.009456 | 0.93 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3043 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | RCC | [21 empty] | 1018334
732 | Task(Task)-->C (Construction) | RCC FLOOR FOR BELT FEEDER |  | 1.6.3.1 | Unscheduled | No | No | 2020-10-12 09:00 | 2020-10-24 18:00 | 2021-02-20 09:00 | 2021-03-04 18:00 | [6 empty] | 0 | 0 | [15 empty] | 3.2698 | 0.009761 | 0.96 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3044 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | RCC | [21 empty] | 1018335
733 | Task(Task)-->C (Construction) | RCC FLOOR FOR SURGE HOPPER |  | 1.6.3.1 | Unscheduled | No | No | 2020-11-11 09:00 | 2020-11-26 18:00 | 2021-03-22 09:00 | 2021-04-06 18:00 | [6 empty] | 0 | 0 | [15 empty] | 3.3379 | 0.009964 | 0.98 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3045 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | RCC | [21 empty] | 1018336
734 | Task(Task)-->C (Construction) | GRADE SLAB FLOOR FOR TAIL END DRIVE OF PC-1A/B |  | 1.6.3.1 | Unscheduled | No | No | 2020-12-26 09:00 | 2021-02-04 18:00 | 2021-05-06 09:00 | 2021-06-15 18:00 | [6 empty] | 0 | 0 | [15 empty] | 60.5926 | 0.18089 | 17.79 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 950 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3046 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018337
735 | Task(Task)-->C (Construction) | STRUCTURAL WORKS | 1.6.3.2 | 1.6.3 | Unscheduled | No | No | 2020-07-29 09:00 | 2021-04-24 18:00 | 2020-12-07 09:00 | 2021-09-02 18:00 | [6 empty] | 25.6908 | 0 | [15 empty] | 34.4064 | 0.24016 | 23.62 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3047 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018338
736 | Task(Task)-->C (Construction) | ERECTION OF STRUCTURAL STEEL |  | 1.6.3.2 | Unscheduled | No | No | 2020-07-29 09:00 | 2020-12-25 18:00 | 2020-12-07 09:00 | 2021-05-05 18:00 | [6 empty] | 47.3333 | 0 | [15 empty] | 54.276 | 0.13035 | 12.82 | Plan & Actual | Quantity | Metric Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 198 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3048 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018339
737 | Task(Task)-->C (Construction) | ERECTION OF SURGE HOPPER |  | 1.6.3.2 | Unscheduled | No | No | 2020-11-26 09:00 | 2021-04-24 18:00 | 2021-04-06 09:00 | 2021-09-02 18:00 | [6 empty] | 0 | 0 | [15 empty] | 45.724 | 0.10981 | 10.8 | Plan & Actual | Quantity | Metric Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 168 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5413 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018340
738 | Task(Task)-->C (Construction) | MECHANICAL EQUIPMENT WORKS | 1.6.3.3 | 1.6.3 | Unscheduled | No | No | 2021-04-25 | 2021-05-24 18:00 | 2021-09-03 09:00 | 2021-10-02 18:00 | [6 empty] | 0 | 0 | [15 empty] | 8.5652 | 0.059787 | 5.88 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5456 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018341
739 | Task(Task)-->C (Construction) | ERECTION OF CHUTES/ HOODS & SUPPORTS |  | 1.6.3.3 | Unscheduled | No | No | 2021-04-25 | 2021-05-24 18:00 | 2021-09-03 09:00 | 2021-10-02 18:00 | [6 empty] | 0 | 0 | [15 empty] | 75.1278 | 0.044917 | 4.41 | Plan & Actual | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3049 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018342
740 | Task(Task)-->C (Construction) | ERECTION OF BF-1 |  | 1.6.3.3 | Unscheduled | No | No | 2021-04-25 | 2021-05-09 23:59 | 2021-09-03 09:00 | 2021-09-17 18:00 | [6 empty] | 0 | 0 | [15 empty] | 12.4361 | 0.007435 | 0.73 | Plan & Actual | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5414 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018343
741 | Task(Task)-->C (Construction) | ERECTION OF BF-2 |  | 1.6.3.3 | Unscheduled | No | No | 2021-05-10 09:00 | 2021-05-24 18:00 | 2021-09-18 09:00 | 2021-10-02 18:00 | [6 empty] | 0 | 0 | [15 empty] | 12.4361 | 0.007435 | 0.73 | Plan & Actual | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5415 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018344
742 | Task(Task)-->C (Construction) | ELECTRICAL & INSTRUMENTATION | 1.6.3.4 | 1.6.3 | Unscheduled | No | No | 2020-12-18 09:00 | 2021-08-25 18:00 | 2021-04-28 09:00 | 2022-03-17 18:00 | [6 empty] | 0 | 0 | [15 empty] | 12.0175 | 0.083885 | 8.25 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5268 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018345
743 | Task(Task)-->C (Construction) | CABLE TRAY |  | 1.6.3.4 | Unscheduled | No | No | 2020-12-18 09:00 | 2021-01-01 18:00 | 2021-04-28 09:00 | 2021-05-12 18:00 | [6 empty] | 0 | 0 | [15 empty] | 9.3333 | 0.007829 | 0.77 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3050 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018346
744 | Task(Task)-->C (Construction) | POWER CABLE LAYING |  | 1.6.3.4 | Unscheduled | No | No | 2021-05-25 09:00 | 2021-06-07 18:00 | 2021-10-03 | 2021-10-16 18:00 | [6 empty] | 0 | 0 | [15 empty] | 39.2727 | 0.032944 | 3.24 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 22891 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5269 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018347
745 | Task(Task)-->C (Construction) | CONTROL CABLE |  | 1.6.3.4 | Unscheduled | No | No | 2021-06-05 09:00 | 2021-06-07 18:00 | 2021-10-14 09:00 | 2021-10-16 18:00 | [6 empty] | 0 | 0 | [15 empty] | 28.3636 | 0.023793 | 2.34 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 16500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3051 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018348
746 | Task(Task)-->C (Construction) | EARTHING |  | 1.6.3.4 | Unscheduled | No | No | 2021-06-03 09:00 | 2021-06-07 18:00 | 2021-10-12 09:00 | 2021-10-16 18:00 | [6 empty] | 0 | 0 | [15 empty] | 2.1818 | 0.00183 | 0.18 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 827 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5296 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018349
747 | Task(Task)-->C (Construction) | EARTH PIT |  | 1.6.3.4 | Unscheduled | No | No | 2021-02-02 09:00 | 2021-02-04 18:00 | 2021-06-13 | 2021-06-15 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5297 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018350
748 | Task(Task)-->C (Construction) | LIGHTING |  | 1.6.3.4 | Unscheduled | No | No | 2020-12-21 09:00 | 2021-01-04 18:00 | 2021-05-01 09:00 | 2021-05-15 18:00 | [6 empty] | 0 | 0 | [15 empty] | 13.697 | 0.01149 | 1.13 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 116 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5298 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018351
749 | Task(Task)-->C (Construction) | FIELD INTRUMENTS |  | 1.6.3.4 | Unscheduled | No | No | 2021-06-04 09:00 | 2021-06-07 18:00 | 2021-10-13 09:00 | 2021-10-16 18:00 | [6 empty] | 0 | 0 | [15 empty] | 7.1515 | 0.005999 | 0.59 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5299 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018352
750 | Task(Task)-->C (Construction) | MOTOR TERMINATION |  | 1.6.3.4 | Unscheduled | No | No | 2021-06-06 | 2021-06-09 18:00 | 2021-12-03 09:00 | 2021-12-06 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5300 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018353
751 | Task(Task)-->C (Construction) | NO LOAD RUN OF MOTOR |  | 1.6.3.4 | Unscheduled | No | No | 2021-08-22 | 2021-08-25 18:00 | 2022-03-14 09:00 | 2022-03-17 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5457 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018354
752 | Task(Task)-->C (Construction) | NO LOAD COMMISSIONING & SYSTEM READYNESS FOR LOAD & TRIAL OPERATION |  | 1.6.3 | Unscheduled | No | No | 2021-08-26 09:00 | 2021-09-09 18:00 | 2022-03-18 09:00 | 2022-04-01 18:00 | [6 empty] | 0 | 0 | [15 empty] | 2.2433 | 0.015658 | 1.54 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5301 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018355
753 | Task(Task)-->E (Engineering) | TROUGH CONVEYOR SC 3A & SC 3B | 1.7 | 1 | Work In Progress | No | No | 2019-09-27 09:00 | 2021-08-25 18:00 | 2019-09-27 09:00 | 2022-03-17 18:00 |  |  | 2019-09-27 10:57 |  |  |  | 76.0538 | 30.0849 | [15 empty] | 1.0742 | 1.0742 | 105.64 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3052 | 0 | 1 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018356
754 | Task(Task)-->E (Engineering) | ENGINEERING | 1.7.1 | 1.7 | Work In Progress | No | No | 2019-12-06 18:00 | 2020-06-26 17:40 | 2020-01-13 18:00 | 2020-07-10 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 83.6683 | [15 empty] | 1.5998 | 0.017185 | 1.69 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3053 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018357
755 | Task(Task)-->E (Engineering) | MECHANICAL | 1.7.1.1 | 1.7.1 | Work In Progress | No | No | 2019-12-06 18:00 | 2020-03-23 17:40 | 2020-01-13 18:00 | 2020-04-09 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 86.7685 | [15 empty] | 38.4615 | 0.00661 | 0.65 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No | 3054 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036086
756 | Task(Task)-->E (Engineering) | PULLEY SHAFT DIAMETER, SHELL THICKNESS, DIAPHRAGM THICKNESS CALCULATION WITH BEARING SELECTION FOR TROUGH BELT CONVEYORS |  | 1.7.1.1 | Completed | No | No | 2020-01-20 18:00 | 2020-03-23 17:40 | 2020-02-18 09:00 | 2020-03-13 18:00 |  |  | 2020-02-21 14:04 | 2020-06-19 22:39 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-DC-0026 |  | 2020-02-13 10:26 | 7012-155-PVM-H-026 |  |  |  | A |  |  |  | 33.8462 | 0.002237 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 80 | 0 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2658 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-20 18:00 | 2020-01-14 18:00 |  | 10 | 2020-01-14 23:31 |  |  | 2020-02-11 17:40 | 2020-02-13 18:00 |  | 30 | 2020-02-13 23:31 |  |  | 2020-02-17 17:40 | 2020-02-18 18:00 |  | 35 | 2020-02-18 23:31 |  |  | 2020-02-24 23:59 | 2020-02-18 18:00 |  | 65 | 2020-02-18 23:31 |  |  | 2020-02-29 17:40 | 2020-03-13 18:00 |  | 80 | 2020-03-13 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-23 17:40 | 2020-03-13 18:00 |  | 100 | 2020-06-19 22:40 | [121 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 26 |  |  |  | 101040
757 | Task(Task)-->E (Engineering) | G.A & MARKING OF CONV. SC 3A/B |  | 1.7.1.1 | Unscheduled | No | No | 2019-12-06 18:00 | 2020-01-25 17:40 | 2020-01-13 18:00 | 2020-04-09 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-0020 |  | 2020-02-13 10:26 | 7012-155-PVM-B-020 |  |  |  | A |  |  |  | 66.1538 | 0.004373 | 0.43 | Plan & Actual | Date |  | 0 | 0 | 0 | 160 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3055 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-12-06 18:00 | 2020-01-13 18:00 |  | 10 | 2020-01-13 23:31 |  |  | 2019-12-18 17:40 | 2020-01-28 18:00 |  | 30 | 2020-01-28 23:31 |  |  | 2019-12-24 17:40 | 2020-01-30 18:00 |  | 35 | 2020-01-30 23:31 |  |  | 2019-12-30 23:59 | 2020-02-06 18:00 |  | 65 | 2020-02-06 23:31 |  |  | 2020-01-04 17:40 | 2020-02-26 18:00 |  | 80 | 2020-02-26 23:31 | [5 empty] | 80 | 2020-06-10 17:39 | [5 empty] | 80 | 2020-05-16 18:41 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-01-25 17:40 | 2020-04-09 18:00 |  | 100 | [122 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 20 |  |  |  | 101034
758 | Task(Task)-->E (Engineering) | CIVIL | 1.7.1.2 | 1.7.1 | Completed | No | No | 2020-03-03 17:40 | 2020-05-12 17:40 | 2020-04-11 09:00 | 2020-07-10 18:00 |  |  | 2020-02-21 15:37 | 2020-07-17 15:22 |  |  | 100 | 100 | [15 empty] | 5.3254 | 0.000915 | 0.09 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No | 3080 | 2 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036087
759 | Task(Task)-->E (Engineering) | CONV. SC 3A/B : NUM & RC DETAILS OF FDN |  | 1.7.1.2 | Completed | No | No | 2020-03-13 18:00 | 2020-05-12 17:40 | 2020-06-21 | 2020-07-10 18:00 |  |  | 2020-02-21 15:37 | 2020-07-17 15:22 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-NR-0023 |  | 2020-02-13 11:42 | 7012-155-PVC-C-069 |  |  |  | A |  |  |  | 19.5652 | 0.000179 | 0.09 | Plan & Actual | Date |  | 0 | 0 | 0 | 34.57 | 0 | 90.31 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3081 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-13 18:00 | 2020-03-27 18:00 |  | 10 | 2020-03-27 23:31 |  |  | 2020-03-31 17:40 | 2020-05-01 18:00 |  | 30 |  |  |  | 2020-04-06 17:40 | 2020-05-04 18:00 |  | 35 | 2020-06-19 10:27 |  |  | 2020-04-13 23:59 | 2020-05-11 18:00 |  | 65 | 2020-07-07 21:13 |  |  | 2020-04-18 17:40 | 2020-06-01 18:00 |  | 80 | 2020-07-07 21:25 | [5 empty] | 80 | 2020-07-17 15:07 | [5 empty] | 80 | 2020-07-17 15:07 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-12 17:40 | 2020-06-15 18:00 |  | 100 | 2020-07-17 15:14 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 170 |  |  |  | 101182
760 | Task(Task)-->E (Engineering) | CONV. SC 3A/B : DESIGN CALCULATION OF SUPER STRUCTURE |  | 1.7.1.2 | Completed | No | No | 2020-03-03 17:40 | 2020-04-13 17:40 | 2020-04-11 09:00 | 2020-05-01 18:00 |  |  | 2020-03-03 17:40 | 2020-05-16 17:38 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0020A |  | 2020-02-13 11:42 | 7012-155-PVC-U-066 |  |  |  | A |  |  |  | 60.8696 | 0.000557 | 0.28 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3082 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-12 18:00 | 2020-03-11 18:00 |  | 10 | 2020-03-11 23:31 |  |  | 2020-03-03 17:40 | 2020-04-01 18:00 |  | 30 | 2020-04-01 23:31 |  |  | 2020-03-09 17:40 | 2020-04-04 18:00 |  | 35 | 2020-04-04 23:31 |  |  | 2020-03-14 23:59 | 2020-04-11 18:00 |  | 65 | 2020-04-11 23:31 |  |  | 2020-03-20 17:40 | 2020-05-16 18:00 |  | 80 | 2020-05-01 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-13 17:40 | 2020-05-30 18:00 |  | 100 | 2020-05-16 17:38 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 167 |  |  |  | 101179
761 | Task(Task)-->E (Engineering) | CONV. SC 3A/B : DESIGN CALCULATION OF SUB STRUCTURE |  | 1.7.1.2 | Completed | No | No | 2020-03-13 18:00 | 2020-05-12 17:40 | 2020-06-21 | 2020-07-07 18:00 |  |  | 2020-02-21 15:37 | 2020-07-07 21:26 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0021A |  | 2020-02-13 11:42 | 7012-155-PVC-U-067 |  |  |  | A |  |  |  | 19.5652 | 0.000179 | 0.09 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3083 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-13 18:00 | 2020-03-27 18:00 |  | 10 | 2020-03-27 23:31 |  |  | 2020-03-31 17:40 | 2020-05-01 18:00 |  | 30 |  |  |  | 2020-04-06 17:40 | 2020-05-04 18:00 |  | 35 |  |  |  | 2020-04-13 23:59 | 2020-05-11 18:00 |  | 65 | 2020-07-07 21:11 |  |  | 2020-04-18 17:40 | 2020-06-01 18:00 |  | 80 | 2020-07-07 21:24 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-12 17:40 | 2020-06-15 18:00 |  | 100 | 2020-07-07 21:27 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 168 |  |  |  | 101180
762 | Task(Task)-->E (Engineering) | STRUCTURAL | 1.7.1.3 | 1.7.1 | Unscheduled | No | No | 2020-02-12 18:00 | 2020-04-13 17:40 | 2020-03-11 18:00 | 2020-05-30 18:00 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 80 | [15 empty] | 16.568 | 0.002847 | 0.28 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No | 3084 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036088
763 | Task(Task)-->E (Engineering) | CONV. SC 3A/B : STRUCTURAL GA |  | 1.7.1.3 | Unscheduled | No | No | 2020-02-12 18:00 | 2020-04-13 17:40 | 2020-03-11 18:00 | 2020-05-30 18:00 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-GA-0021 |  | 2020-02-13 11:42 | 7012-155-PVC-B-068 |  |  |  | A |  |  |  | 100 | 0.002847 | 0.28 | Plan & Actual | Date |  | 0 | 0 | 0 | 105.1 | 0 | 100.4 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3085 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-12 18:00 | 2020-03-11 18:00 |  | 10 | 2020-03-11 23:31 |  |  | 2020-03-03 17:40 | 2020-04-01 18:00 |  | 30 | 2020-04-01 23:31 |  |  | 2020-03-09 17:40 | 2020-04-04 18:00 |  | 35 | 2020-04-04 23:31 |  |  | 2020-03-14 23:59 | 2020-04-11 18:00 |  | 65 | 2020-04-11 23:31 |  |  | 2020-03-20 17:40 | 2020-05-16 18:00 |  | 80 | 2020-05-26 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | 2020-10-13 21:59 | [5 empty] | 80 | 2020-10-13 21:59 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-13 17:40 | 2020-05-30 18:00 |  | 100 | [122 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 169 |  |  |  | 101181
764 | Task(Task)-->E (Engineering) | ELECTRICAL | 1.7.1.4 | 1.7.1 | Unscheduled | No | No | 2020-05-08 18:00 | 2020-06-26 17:40 | 2020-04-12 | 2020-06-22 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 | [15 empty] | 39.645 | 0.006813 | 0.67 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No | 3088 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036089
765 | Task(Task)-->E (Engineering) | LIGHTING LAYOUT PLAN WITH POWER DISTRIBUTION ARRANGEMENT, SECTIONAL VIEW, BOM OF CONV. SC 3A/B |  | 1.7.1.4 | Unscheduled | No | No | 2020-05-08 18:00 | 2020-06-26 17:40 | 2020-04-12 | 2020-06-22 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5081 |  | 2020-02-13 11:45 | 7012-155-PVE-G-043 |  |  |  | A |  |  |  | 100 | 0.006813 | 0.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 248.42 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3089 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-05-08 18:00 | 2020-05-11 18:00 |  | 10 | 2020-04-06 23:31 |  |  | 2020-05-16 17:40 | 2020-05-18 18:00 |  | 30 | 2020-04-10 23:31 |  |  | 2020-05-22 17:40 | 2020-05-25 18:00 |  | 35 | 2020-04-12 23:31 |  |  | 2020-05-29 23:59 | 2020-06-01 18:00 |  | 65 | 2020-04-12 23:31 |  |  | 2020-06-04 17:40 | 2020-06-22 18:00 |  | 80 | 2020-04-23 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-26 17:40 | 2020-06-22 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 278 |  |  |  | 101289
766 | Task(Task)-->P (Procurement) | PROCUREMENT | 1.7.2 | 1.7 | Work In Progress | No | No | 2019-09-27 09:00 | 2021-02-13 18:00 | 2019-09-27 09:00 | 2021-05-13 18:00 |  |  | 2019-09-27 10:57 |  |  |  | 89.393 | 35.2419 | [15 empty] | 76.2779 | 0.81937 | 80.58 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3091 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018362
767 | Task(Task)-->P (Procurement) | PURCHASE REQUISITION | 1.7.2.1 | 1.7.2 | Work In Progress | No | No | 2019-09-27 09:00 | 2020-05-19 18:00 | 2019-09-27 09:00 | 2020-05-29 18:00 |  |  | 2019-09-27 10:57 |  |  |  | 100 | 100 | [15 empty] | 5.0006 | 0.040974 | 4.03 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3092 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018363
768 | Task(Task)-->P (Procurement) | Metal Detector |  | 1.7.2.1 | Completed | No | No | 2019-09-27 09:00 | 2019-09-27 18:00 | 2019-09-27 09:00 | 2019-09-27 18:00 |  |  | 2019-09-27 10:57 | 2019-09-27 10:57 |  |  | 100 | 100 | [15 empty] | 1.7413 | 0.000713 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3093 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018364
769 | Task(Task)-->P (Procurement) | Pulley |  | 1.7.2.1 | Completed | No | No | 2019-09-27 09:00 | 2019-09-27 18:00 | 2020-02-05 09:00 | 2020-02-05 18:00 |  |  | 2020-02-05 16:16 | 2020-02-05 16:16 |  |  | 100 | 100 | [15 empty] | 11.194 | 0.004587 | 0.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3094 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018365
770 | Task(Task)-->P (Procurement) | Idler |  | 1.7.2.1 | Completed | No | No | 2019-12-19 09:00 | 2019-12-19 18:00 | 2020-02-13 09:00 | 2020-02-13 18:00 |  |  | 2020-02-13 15:44 | 2020-02-13 15:44 |  |  | 100 | 100 | [15 empty] | 15.4229 | 0.006319 | 0.62 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3095 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018366
771 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.7.2.1 | Completed | No | No | 2020-05-17 | 2020-05-17 23:59 | 2020-02-10 09:00 | 2020-02-10 18:00 |  |  | 2020-02-10 09:26 | 2020-02-10 09:26 |  |  | 100 | 100 | [15 empty] | 0.74627 | 0.000306 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3096 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018367
772 | Task(Task)-->P (Procurement) | Bearing |  | 1.7.2.1 | Completed | No | No | 2020-05-17 | 2020-05-17 23:59 | 2020-02-10 09:00 | 2020-02-10 18:00 |  |  | 2020-02-10 09:36 | 2020-02-10 09:36 |  |  | 100 | 100 | [15 empty] | 1.4925 | 0.000612 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3097 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018368
773 | Task(Task)-->P (Procurement) | Belting |  | 1.7.2.1 | Completed | No | No | 2019-11-07 09:00 | 2019-11-07 18:00 | 2020-01-20 09:00 | 2020-01-20 18:00 |  |  | 2020-01-20 15:54 | 2020-01-20 15:54 |  |  | 100 | 100 | [15 empty] | 15.9204 | 0.006523 | 0.64 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3098 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018369
774 | Task(Task)-->P (Procurement) | Scrapper |  | 1.7.2.1 | Completed | No | No | 2019-11-17 | 2019-11-17 23:59 | 2020-03-11 09:00 | 2020-03-11 18:00 |  |  | 2020-03-11 10:57 | 2020-03-11 10:57 |  |  | 100 | 100 | [15 empty] | 0.49751 | 0.000204 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3099 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018370
775 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.7.2.1 | Completed | No | No | 2020-03-10 09:00 | 2020-03-10 18:00 | 2020-03-11 09:00 | 2020-03-11 18:00 |  |  | 2020-03-11 12:41 | 2020-03-11 12:41 |  |  | 100 | 100 | [15 empty] | 4.7264 | 0.001937 | 0.19 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3100 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018371
776 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.7.2.1 | Completed | No | No | 2020-05-19 09:00 | 2020-05-19 18:00 | 2020-04-16 09:00 | 2020-04-16 18:00 |  |  | 2020-04-16 10:57 | 2020-04-16 10:57 |  |  | 100 | 100 | [15 empty] | 0.24876 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3101 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018372
777 | Task(Task)-->P (Procurement) | Gear Box |  | 1.7.2.1 | Completed | No | No | 2019-11-13 09:00 | 2019-11-13 18:00 | 2020-01-20 09:00 | 2020-01-20 18:00 |  |  | 2020-01-20 11:17 | 2020-01-20 11:17 |  |  | 100 | 100 | [15 empty] | 2.4876 | 0.001019 | 0.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3102 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018373
778 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.7.2.1 | Completed | No | No | 2019-11-21 09:00 | 2019-11-21 18:00 | 2020-01-22 09:00 | 2020-01-22 18:00 |  |  | 2020-01-22 10:41 | 2020-01-22 10:41 |  |  | 100 | 100 | [15 empty] | 0.24876 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3103 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018374
779 | Task(Task)-->P (Procurement) | Fluid Coupling |  | 1.7.2.1 | Completed | No | No | 2019-11-25 09:00 | 2019-11-25 18:00 | 2020-01-22 09:00 | 2020-01-22 18:00 |  |  | 2020-01-22 09:54 | 2020-01-22 09:54 |  |  | 100 | 100 | [15 empty] | 2.4876 | 0.001019 | 0.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3104 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018375
780 | Task(Task)-->P (Procurement) | Brake |  | 1.7.2.1 | Completed | No | No | 2019-12-18 09:00 | 2019-12-18 18:00 | 2020-04-04 09:00 | 2020-04-04 18:00 |  |  | 2020-04-04 11:33 | 2020-04-04 11:33 |  |  | 100 | 100 | [15 empty] | 0.24876 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3105 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018376
781 | Task(Task)-->P (Procurement) | Building Structure |  | 1.7.2.1 | Completed | No | No | 2020-03-14 09:00 | 2020-03-14 18:00 | 2020-05-29 09:00 | 2020-05-29 18:00 |  |  | 2020-05-31 18:44 | 2020-05-31 18:44 |  |  | 100 | 100 | [15 empty] | 24.3781 | 0.009989 | 0.98 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3106 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018377
782 | Task(Task)-->P (Procurement) | HT AC MOTORS |  | 1.7.2.1 | Completed | No | No | 2020-01-07 09:00 | 2020-01-07 18:00 | 2020-01-17 09:00 | 2020-01-17 18:00 |  |  | 2020-01-17 10:57 | 2020-01-17 10:57 |  |  | 100 | 100 | [15 empty] | 7.2139 | 0.002956 | 0.29 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3107 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018378
783 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.7.2.1 | Completed | No | No | 2020-03-10 09:00 | 2020-03-10 18:00 | 2020-03-16 09:00 | 2020-03-16 18:00 |  |  | 2020-03-16 10:57 | 2020-03-16 10:57 |  |  | 100 | 100 | [15 empty] | 6.7164 | 0.002752 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3108 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018379
784 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.7.2.1 | Completed | No | No | 2020-03-27 09:00 | 2020-03-27 18:00 | 2020-04-30 09:00 | 2020-04-30 18:00 |  |  | 2020-04-30 10:57 | 2020-04-30 10:57 |  |  | 100 | 100 | [15 empty] | 2.9851 | 0.001223 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3109 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018380
785 | Task(Task)-->P (Procurement) | LPBS |  | 1.7.2.1 | Unscheduled | No | No | 2020-03-20 09:00 | 2020-03-20 18:00 | 2020-04-14 09:00 | 2020-04-14 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3110 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018381
786 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.7.2.1 | Completed | No | No | 2020-01-08 09:00 | 2020-01-08 18:00 | 2020-01-08 09:00 | 2020-01-08 18:00 |  |  | 2020-01-08 10:57 | 2020-01-08 10:57 |  |  | 100 | 100 | [15 empty] | 1.2438 | 0.00051 | 0.05 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3111 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018382
787 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.7.2.1 | Completed | No | No | 2019-12-30 09:00 | 2019-12-30 18:00 | 2019-12-30 09:00 | 2019-12-30 18:00 |  |  | 2019-12-30 10:57 | 2019-12-30 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3112 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018383
788 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.7.2.1 | Completed | No | No | 2020-01-03 09:00 | 2020-01-03 18:00 | 2020-01-03 09:00 | 2020-01-03 18:00 |  |  | 2020-01-03 10:57 | 2020-01-03 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3113 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018384
789 | Task(Task)-->P (Procurement) | TECHNICAL CLEARANCE | 1.7.2.2 | 1.7.2 | Work In Progress | No | No | 2019-09-28 09:00 | 2020-06-18 18:00 | 2019-09-27 09:00 | 2020-06-12 18:00 |  |  | 2019-12-27 10:57 |  |  |  | 100 | 100 | [15 empty] | 5.0006 | 0.040974 | 4.03 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3114 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018385
790 | Task(Task)-->P (Procurement) | Metal Detector |  | 1.7.2.2 | Completed | No | No | 2019-09-28 09:00 | 2020-01-06 18:00 | 2019-09-27 09:00 | 2019-12-27 18:00 |  |  | 2019-12-27 10:57 | 2019-12-27 10:57 |  |  | 100 | 100 | [15 empty] | 1.7413 | 0.000713 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3115 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018386
791 | Task(Task)-->P (Procurement) | Pulley |  | 1.7.2.2 | Completed | No | No | 2019-09-28 09:00 | 2020-01-04 18:00 | 2020-02-05 09:00 | 2020-02-10 18:00 |  |  | 2020-02-06 16:19 | 2020-02-10 16:19 |  |  | 100 | 100 | [15 empty] | 11.194 | 0.004587 | 0.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3116 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018387
792 | Task(Task)-->P (Procurement) | Idler |  | 1.7.2.2 | Completed | No | No | 2019-12-20 09:00 | 2020-02-01 18:00 | 2020-02-13 09:00 | 2020-03-26 18:00 |  |  | 2020-02-14 10:57 | 2020-03-26 10:57 |  |  | 100 | 100 | [15 empty] | 15.4229 | 0.006319 | 0.62 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3117 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018388
793 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.7.2.2 | Completed | No | No | 2020-05-18 09:00 | 2020-06-01 18:00 | 2020-02-10 09:00 | 2020-02-10 18:00 |  |  | 2020-02-10 09:28 | 2020-02-10 09:28 |  |  | 100 | 100 | [15 empty] | 0.74627 | 0.000306 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3118 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018389
794 | Task(Task)-->P (Procurement) | Bearing |  | 1.7.2.2 | Completed | No | No | 2020-05-18 09:00 | 2020-06-16 18:00 | 2020-02-10 09:00 | 2020-02-10 18:00 |  |  | 2020-02-10 09:37 | 2020-02-10 09:37 |  |  | 100 | 100 | [15 empty] | 1.4925 | 0.000612 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3119 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018390
795 | Task(Task)-->P (Procurement) | Belting |  | 1.7.2.2 | Completed | No | No | 2019-11-08 09:00 | 2020-01-06 18:00 | 2020-01-20 09:00 | 2020-05-16 18:00 |  |  | 2020-05-16 10:57 | 2020-05-16 10:57 |  |  | 100 | 100 | [15 empty] | 15.9204 | 0.006523 | 0.64 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3120 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018391
796 | Task(Task)-->P (Procurement) | Scrapper |  | 1.7.2.2 | Completed | No | No | 2019-11-18 09:00 | 2020-03-16 18:00 | 2020-03-11 09:00 | 2020-03-26 18:00 |  |  | 2020-03-26 10:57 | 2020-03-26 10:57 |  |  | 100 | 100 | [15 empty] | 0.49751 | 0.000204 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3121 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018392
797 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.7.2.2 | Completed | No | No | 2020-03-11 09:00 | 2020-03-20 18:00 | 2020-03-11 09:00 | 2020-03-17 18:00 |  |  | 2020-03-12 12:43 | 2020-03-17 12:43 |  |  | 100 | 100 | [15 empty] | 4.7264 | 0.001937 | 0.19 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3122 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018393
798 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.7.2.2 | Completed | No | No | 2020-05-20 09:00 | 2020-06-18 18:00 | 2020-04-16 09:00 | 2020-04-16 18:00 |  |  | 2020-04-16 10:57 | 2020-04-16 10:57 |  |  | 100 | 100 | [15 empty] | 0.24876 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3123 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018394
799 | Task(Task)-->P (Procurement) | Gear Box |  | 1.7.2.2 | Completed | No | No | 2019-11-14 09:00 | 2020-02-26 18:00 | 2020-01-20 09:00 | 2020-03-20 18:00 |  |  | 2020-01-22 11:19 | 2020-03-20 11:19 |  |  | 100 | 100 | [15 empty] | 2.4876 | 0.001019 | 0.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3124 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018395
800 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.7.2.2 | Completed | No | No | 2019-11-22 09:00 | 2020-03-19 18:00 | 2020-01-22 09:00 | 2020-04-13 18:00 |  |  | 2020-04-13 10:46 | 2020-04-13 10:46 |  |  | 100 | 100 | [15 empty] | 0.24876 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3125 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018396
801 | Task(Task)-->P (Procurement) | Fluid Coupling |  | 1.7.2.2 | Completed | No | No | 2019-11-26 09:00 | 2020-03-01 23:59 | 2020-01-22 09:00 | 2020-04-13 18:00 |  |  | 2020-01-23 09:54 | 2020-04-13 09:54 |  |  | 100 | 100 | [15 empty] | 2.4876 | 0.001019 | 0.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3126 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018397
802 | Task(Task)-->P (Procurement) | Brake |  | 1.7.2.2 | Completed | No | No | 2019-12-19 09:00 | 2020-03-09 18:00 | 2020-04-04 09:00 | 2020-04-22 18:00 |  |  | 2020-04-05 11:34 | 2020-04-22 11:34 |  |  | 100 | 100 | [15 empty] | 0.24876 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3127 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018398
803 | Task(Task)-->P (Procurement) | Building Structure |  | 1.7.2.2 | Completed | No | No | 2020-03-15 | 2020-03-21 18:00 | 2020-05-29 09:00 | 2020-05-29 18:00 |  |  | 2020-05-29 17:31 | 2020-05-29 17:31 |  |  | 100 | 100 | [15 empty] | 24.3781 | 0.009989 | 0.98 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3128 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018399
804 | Task(Task)-->P (Procurement) | HT AC MOTORS |  | 1.7.2.2 | Completed | No | No | 2020-01-08 09:00 | 2020-02-06 18:00 | 2020-01-17 09:00 | 2020-04-11 18:00 |  |  | 2020-04-11 10:57 | 2020-04-11 10:57 |  |  | 100 | 100 | [15 empty] | 7.2139 | 0.002956 | 0.29 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3129 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018400
805 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.7.2.2 | Completed | No | No | 2020-03-11 09:00 | 2020-03-25 18:00 | 2020-03-16 09:00 | 2020-06-02 18:00 |  |  | 2020-06-02 10:57 | 2020-06-02 10:57 |  |  | 100 | 100 | [15 empty] | 6.7164 | 0.002752 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3130 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018401
806 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.7.2.2 | Completed | No | No | 2020-03-28 09:00 | 2020-05-11 18:00 | 2020-04-30 09:00 | 2020-06-03 18:00 |  |  | 2020-06-03 10:57 | 2020-06-03 10:57 |  |  | 100 | 100 | [15 empty] | 2.9851 | 0.001223 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3131 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018402
807 | Task(Task)-->P (Procurement) | LPBS |  | 1.7.2.2 | Unscheduled | No | No | 2020-03-21 09:00 | 2020-04-04 18:00 | 2020-04-14 09:00 | 2020-06-12 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3132 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018403
808 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.7.2.2 | Completed | No | No | 2020-01-09 09:00 | 2020-01-22 18:00 | 2020-01-08 09:00 | 2020-03-10 18:00 |  |  | 2020-03-10 10:57 | 2020-03-10 10:57 |  |  | 100 | 100 | [15 empty] | 1.2438 | 0.00051 | 0.05 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3133 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018404
809 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.7.2.2 | Completed | No | No | 2019-12-31 09:00 | 2020-01-14 18:00 | 2019-12-30 09:00 | 2020-03-07 18:00 |  |  | 2020-03-07 10:57 | 2020-03-07 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3134 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018405
810 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.7.2.2 | Completed | No | No | 2020-01-04 09:00 | 2020-01-18 18:00 | 2020-01-03 09:00 | 2020-01-16 18:00 |  |  | 2020-01-16 10:57 | 2020-01-16 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3135 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018406
811 | Task(Task)-->P (Procurement) | ORDERING | 1.7.2.3 | 1.7.2 | Work In Progress | No | No | 2020-01-05 | 2020-07-18 18:00 | 2019-12-27 09:00 | 2020-09-04 18:00 |  |  | 2020-01-05 08:00 |  |  |  | 100 | 98.3916 | [15 empty] | 10.0012 | 0.081948 | 8.06 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3136 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018407
812 | Task(Task)-->P (Procurement) | Metal Detector |  | 1.7.2.3 | Completed | No | No | 2020-01-07 09:00 | 2020-02-05 18:00 | 2019-12-27 09:00 | 2020-03-20 18:00 |  |  | 2020-03-20 10:57 | 2020-03-20 10:57 |  |  | 100 | 100 | [15 empty] | 1.8564 | 0.001521 | 0.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3137 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018408
813 | Task(Task)-->P (Procurement) | Pulley |  | 1.7.2.3 | Completed | No | No | 2020-01-05 | 2020-02-03 18:00 | 2020-02-10 09:00 | 2020-03-21 18:00 |  |  | 2020-01-05 08:00 | 2020-03-21 16:05 |  |  | 100 | 100 | [15 empty] | 11.0149 | 0.009026 | 0.89 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3138 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018409
814 | Task(Task)-->P (Procurement) | Idler |  | 1.7.2.3 | Completed | No | No | 2020-02-02 | 2020-03-02 18:00 | 2020-03-26 09:00 | 2020-04-30 18:00 |  |  | 2020-02-02 08:00 | 2020-04-29 16:05 |  |  | 100 | 100 | [15 empty] | 15.3465 | 0.012576 | 1.24 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3139 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018410
815 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.7.2.3 | Completed | No | No | 2020-06-02 09:00 | 2020-07-01 18:00 | 2020-02-10 09:00 | 2020-03-24 18:00 |  |  | 2020-02-11 09:32 | 2020-03-24 09:32 |  |  | 100 | 100 | [15 empty] | 0.86634 | 0.00071 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3140 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018411
816 | Task(Task)-->P (Procurement) | Bearing |  | 1.7.2.3 | Completed | No | No | 2020-06-17 09:00 | 2020-07-16 18:00 | 2020-02-10 09:00 | 2020-03-24 18:00 |  |  | 2020-02-11 09:40 | 2020-03-24 09:40 |  |  | 100 | 100 | [15 empty] | 1.3614 | 0.001116 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3141 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018412
817 | Task(Task)-->P (Procurement) | Belting |  | 1.7.2.3 | Completed | No | No | 2020-01-07 09:00 | 2020-02-20 18:00 | 2020-05-16 09:00 | 2020-09-04 18:00 |  |  | 2020-05-16 16:24 | 2020-09-04 16:24 |  |  | 100 | 100 | [15 empty] | 15.9653 | 0.013083 | 1.29 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3142 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018413
818 | Task(Task)-->P (Procurement) | Scrapper |  | 1.7.2.3 | Completed | No | No | 2020-03-17 09:00 | 2020-04-15 18:00 | 2020-03-26 09:00 | 2020-05-30 18:00 |  |  | 2020-05-30 10:57 | 2020-05-30 10:57 |  |  | 100 | 100 | [15 empty] | 0.49505 | 0.000406 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3143 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018414
819 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.7.2.3 | Completed | No | No | 2020-03-21 09:00 | 2020-04-19 23:59 | 2020-03-17 09:00 | 2020-07-06 18:00 |  |  | 2020-03-18 12:44 | 2020-07-06 12:44 |  |  | 100 | 100 | [15 empty] | 4.703 | 0.003854 | 0.38 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3144 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018415
820 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.7.2.3 | Unscheduled | No | No | 2020-06-19 09:00 | 2020-07-18 18:00 | 2020-04-16 09:00 | 2020-08-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.24752 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3145 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018416
821 | Task(Task)-->P (Procurement) | Gear Box |  | 1.7.2.3 | Completed | No | No | 2020-02-27 09:00 | 2020-03-27 18:00 | 2020-03-20 09:00 | 2020-04-30 18:00 |  |  | 2020-03-21 11:21 | 2020-04-30 11:21 |  |  | 100 | 100 | [15 empty] | 2.4752 | 0.002028 | 0.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3146 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018417
822 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.7.2.3 | Completed | No | No | 2020-03-20 09:00 | 2020-04-18 18:00 | 2020-04-13 09:00 | 2020-04-30 18:00 |  |  | 2020-04-14 11:11 | 2020-04-30 11:11 |  |  | 100 | 100 | [15 empty] | 0.37129 | 0.000304 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3147 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018418
823 | Task(Task)-->P (Procurement) | Fluid Coupling |  | 1.7.2.3 | Completed | No | No | 2020-03-02 09:00 | 2020-03-31 18:00 | 2020-04-13 09:00 | 2020-05-18 18:00 |  |  | 2020-04-14 09:54 | 2020-05-18 16:05 |  |  | 100 | 100 | [15 empty] | 2.599 | 0.00213 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3148 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018419
824 | Task(Task)-->P (Procurement) | Brake |  | 1.7.2.3 | Completed | No | No | 2020-03-10 09:00 | 2020-04-08 18:00 | 2020-04-22 09:00 | 2020-05-18 18:00 |  |  | 2020-04-23 11:38 | 2020-05-18 16:05 |  |  | 100 | 100 | [15 empty] | 0.24752 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3149 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018420
825 | Task(Task)-->P (Procurement) | Building Structure |  | 1.7.2.3 | Completed | No | No | 2020-03-22 | 2020-04-20 18:00 | 2020-05-29 09:00 | 2020-05-31 23:59 |  |  | 2020-05-31 18:49 | 2020-05-31 18:49 |  |  | 100 | 100 | [15 empty] | 24.2574 | 0.019878 | 1.96 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3150 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018421
826 | Task(Task)-->P (Procurement) | HT AC MOTORS |  | 1.7.2.3 | Completed | No | No | 2020-02-07 09:00 | 2020-03-07 18:00 | 2020-04-11 09:00 | 2020-06-25 18:00 |  |  | 2020-04-13 09:41 | 2020-06-25 09:41 |  |  | 100 | 100 | [15 empty] | 7.1782 | 0.005882 | 0.58 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3151 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018422
827 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.7.2.3 | Completed | No | No | 2020-03-26 09:00 | 2020-04-10 18:00 | 2020-06-02 09:00 | 2020-07-31 18:00 |  |  | 2020-06-03 15:51 | 2020-06-29 15:51 |  |  | 100 | 100 | [15 empty] | 6.5594 | 0.005375 | 0.53 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3152 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018423
828 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.7.2.3 | Completed | No | No | 2020-05-12 09:00 | 2020-06-25 18:00 | 2020-06-03 09:00 | 2020-06-24 18:00 |  |  | 2020-06-15 10:57 | 2020-06-15 10:57 |  |  | 100 | 100 | [15 empty] | 2.9703 | 0.002434 | 0.24 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3153 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018424
829 | Task(Task)-->P (Procurement) | LPBS |  | 1.7.2.3 | Unscheduled | No | No | 2020-04-05 | 2020-04-20 18:00 | 2020-06-12 09:00 | 2020-08-19 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.12376 | 0.000101 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3154 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018425
830 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.7.2.3 | Unscheduled | No | No | 2020-01-23 09:00 | 2020-02-05 18:00 | 2020-03-10 09:00 | 2020-08-17 18:00 | [6 empty] | 100 | 0 | [15 empty] | 1.2376 | 0.001014 | 0.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3155 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018426
831 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.7.2.3 | Unscheduled | No | No | 2020-01-15 09:00 | 2020-02-01 18:00 | 2020-03-07 09:00 | 2020-08-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3156 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018427
832 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.7.2.3 | Completed | No | No | 2020-01-19 | 2020-01-31 18:00 | 2020-01-16 09:00 | 2020-02-01 18:00 |  |  | 2020-02-01 10:57 | 2020-02-01 10:57 |  |  | 100 | 100 | [15 empty] | 0.12376 | 0.000101 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3157 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018428
833 | Task(Task)-->P (Procurement) | ITP APPROVAL | 1.7.2.4 | 1.7.2 | Work In Progress | No | No | 2020-02-01 09:00 | 2020-08-25 18:00 | 2020-03-20 09:00 | 2020-10-30 18:00 |  |  | 2020-03-20 16:01 |  |  |  | 100 | 43.0311 | [15 empty] | 5.0006 | 0.040974 | 4.03 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3158 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018429
834 | Task(Task)-->P (Procurement) | Metal Detector |  | 1.7.2.4 | Completed | No | No | 2020-02-06 09:00 | 2020-03-16 18:00 | 2020-03-20 09:00 | 2020-09-02 18:00 |  |  | 2020-03-20 16:01 | 2020-09-02 16:01 |  |  | 100 | 100 | [15 empty] | 1.7413 | 0.000713 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3159 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018430
835 | Task(Task)-->P (Procurement) | Pulley |  | 1.7.2.4 | Unscheduled | No | No | 2020-02-04 09:00 | 2020-03-14 18:00 | 2020-03-21 09:00 | 2020-05-11 18:00 | [6 empty] | 100 | 0 | [15 empty] | 11.194 | 0.004587 | 0.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3160 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018431
836 | Task(Task)-->P (Procurement) | Idler |  | 1.7.2.4 | Completed | No | No | 2020-03-03 09:00 | 2020-04-11 18:00 | 2020-04-30 09:00 | 2020-05-19 18:00 |  |  | 2020-04-13 16:21 | 2020-05-19 16:21 |  |  | 100 | 100 | [15 empty] | 15.4229 | 0.006319 | 0.62 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3161 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018432
837 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.7.2.4 | Unscheduled | No | No | 2020-07-02 09:00 | 2020-08-10 18:00 | 2020-03-24 09:00 | 2020-08-13 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.74627 | 0.000306 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3162 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018433
838 | Task(Task)-->P (Procurement) | Bearing |  | 1.7.2.4 | Unscheduled | No | No | 2020-07-17 09:00 | 2020-08-25 18:00 | 2020-03-24 09:00 | 2020-03-29 23:59 | [6 empty] | 100 | 0 | [15 empty] | 1.4925 | 0.000612 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3163 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018434
839 | Task(Task)-->P (Procurement) | Belting |  | 1.7.2.4 | Completed | No | No | 2020-02-21 09:00 | 2020-03-31 18:00 | 2020-09-04 09:00 | 2020-09-30 18:00 |  |  | 2020-09-04 16:30 | 2020-09-30 16:30 |  |  | 100 | 100 | [15 empty] | 15.9204 | 0.006523 | 0.64 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3164 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018435
840 | Task(Task)-->P (Procurement) | Scrapper |  | 1.7.2.4 | Completed | No | No | 2020-04-16 09:00 | 2020-05-25 18:00 | 2020-05-30 09:00 | 2020-06-25 18:00 |  |  | 2020-05-30 16:29 | 2020-06-25 16:30 |  |  | 100 | 100 | [15 empty] | 0.49751 | 0.000204 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3165 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018436
841 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.7.2.4 | Unscheduled | No | No | 2020-04-20 09:00 | 2020-05-29 18:00 | 2020-07-06 09:00 | 2020-07-16 18:00 | [6 empty] | 100 | 0 | [15 empty] | 4.7264 | 0.001937 | 0.19 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3166 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018437
842 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.7.2.4 | Unscheduled | No | No | 2020-07-19 | 2020-08-17 18:00 | 2020-06-25 09:00 | 2020-06-25 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.24876 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3167 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018438
843 | Task(Task)-->P (Procurement) | Gear Box |  | 1.7.2.4 | Completed | No | No | 2020-03-28 09:00 | 2020-05-06 18:00 | 2020-04-30 09:00 | 2020-06-22 18:00 |  |  | 2020-04-30 16:57 | 2020-06-22 16:57 |  |  | 100 | 100 | [15 empty] | 2.4876 | 0.001019 | 0.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3168 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018439
844 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.7.2.4 | Completed | No | No | 2020-04-19 | 2020-05-28 18:00 | 2020-04-30 09:00 | 2020-06-18 18:00 |  |  | 2020-04-30 01:54 | 2020-06-18 17:31 |  |  | 100 | 100 | [15 empty] | 0.24876 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3169 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018440
845 | Task(Task)-->P (Procurement) | Fluid Coupling |  | 1.7.2.4 | Unscheduled | No | No | 2020-04-01 09:00 | 2020-05-10 23:59 | 2020-05-18 09:00 | 2020-08-18 18:00 | [6 empty] | 100 | 0 | [15 empty] | 2.4876 | 0.001019 | 0.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3170 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018441
846 | Task(Task)-->P (Procurement) | Brake |  | 1.7.2.4 | Unscheduled | No | No | 2020-04-09 09:00 | 2020-05-18 18:00 | 2020-05-18 09:00 | 2020-10-10 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.24876 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3171 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018442
847 | Task(Task)-->P (Procurement) | Building Structure |  | 1.7.2.4 | Unscheduled | No | No | 2020-04-21 09:00 | 2020-04-27 18:00 | 2020-05-31 | 2020-08-04 18:00 |  |  | 2020-06-25 19:04 |  |  |  | 100 | 0 | [15 empty] | 24.3781 | 0.009989 | 0.98 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3172 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018443
848 | Task(Task)-->P (Procurement) | HT AC MOTORS |  | 1.7.2.4 | Unscheduled | No | No | 2020-03-08 | 2020-04-16 18:00 | 2020-09-11 09:00 | 2020-10-20 18:00 | [6 empty] | 100 | 0 | [15 empty] | 7.2139 | 0.002956 | 0.29 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3173 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018444
849 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.7.2.4 | Completed | No | No | 2020-04-11 09:00 | 2020-05-20 18:00 | 2020-07-28 09:00 | 2020-09-08 18:00 |  |  | 2020-07-08 17:23 | 2020-09-08 17:23 |  |  | 100 | 100 | [15 empty] | 6.7164 | 0.002752 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3174 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018445
850 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.7.2.4 | Unscheduled | No | No | 2020-06-26 09:00 | 2020-08-04 18:00 | 2020-06-23 09:00 | 2020-09-08 18:00 |  |  | 2020-06-23 17:33 |  |  |  | 100 | 0 | [15 empty] | 2.9851 | 0.001223 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3175 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018446
851 | Task(Task)-->P (Procurement) | LPBS |  | 1.7.2.4 | Completed | No | No | 2020-04-21 09:00 | 2020-05-30 18:00 | 2020-07-29 09:00 | 2020-08-21 18:00 |  |  | 2020-07-29 14:59 | 2020-08-22 12:54 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3176 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018447
852 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.7.2.4 | Unscheduled | No | No | 2020-02-06 09:00 | 2020-03-16 18:00 | 2020-09-24 09:00 | 2020-10-30 18:00 | [6 empty] | 100 | 0 | [15 empty] | 1.2438 | 0.00051 | 0.05 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3177 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018448
853 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.7.2.4 | Unscheduled | No | No | 2020-02-02 | 2020-03-12 18:00 | 2020-08-02 | 2020-09-10 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3178 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018449
854 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.7.2.4 | Unscheduled | No | No | 2020-02-01 09:00 | 2020-03-11 18:00 | 2020-07-02 09:00 | 2020-08-04 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3179 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018450
855 | Task(Task)-->P (Procurement) | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE | 1.7.2.5 | 1.7.2 | Work In Progress | No | No | 2020-02-01 09:00 | 2020-09-16 18:00 | 2020-02-01 09:00 | 2020-10-20 18:00 |  |  | 2020-02-11 21:29 |  |  |  | 100 | 82.3555 | [15 empty] | 15.0019 | 0.12292 | 12.09 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3180 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018451
856 | Task(Task)-->P (Procurement) | Metal Detector |  | 1.7.2.5 | Completed | No | No | 2020-02-06 09:00 | 2020-04-05 23:59 | 2020-03-20 09:00 | 2020-08-13 18:00 |  |  | 2020-07-03 15:41 | 2020-07-27 01:06 |  |  | 100 | 100 | [15 empty] | 1.8182 | 0.002235 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3181 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018452
857 | Task(Task)-->P (Procurement) | Pulley |  | 1.7.2.5 | Completed | No | No | 2020-02-04 09:00 | 2020-03-29 23:59 | 2020-03-21 09:00 | 2020-03-25 18:00 |  |  | 2020-03-22 18:03 | 2020-03-25 18:03 |  |  | 100 | 100 | [15 empty] | 11.0744 | 0.013613 | 1.34 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3182 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018453
858 | Task(Task)-->P (Procurement) | Idler |  | 1.7.2.5 | Completed | No | No | 2020-03-03 09:00 | 2020-05-01 18:00 | 2020-04-30 09:00 | 2020-06-25 18:00 |  |  | 2020-06-25 14:53 | 2020-06-25 14:53 |  |  | 100 | 100 | [15 empty] | 15.3719 | 0.018895 | 1.86 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3183 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018454
859 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.7.2.5 | Completed | No | No | 2020-07-02 09:00 | 2020-08-30 23:59 | 2020-03-24 09:00 | 2020-06-29 18:00 |  |  | 2020-05-14 14:59 | 2020-06-29 14:59 |  |  | 100 | 100 | [15 empty] | 0.82645 | 0.001016 | 0.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3184 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018455
860 | Task(Task)-->P (Procurement) | Bearing |  | 1.7.2.5 | Completed | No | No | 2020-07-17 09:00 | 2020-07-17 18:00 | 2020-03-24 09:00 | 2020-03-24 18:00 |  |  | 2020-03-24 10:05 | 2020-03-24 10:05 |  |  | 100 | 100 | [15 empty] | 1.405 | 0.001727 | 0.17 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3185 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018456
861 | Task(Task)-->P (Procurement) | Belting |  | 1.7.2.5 | Unscheduled | No | No | 2020-02-21 09:00 | 2020-04-20 18:00 | 2020-09-04 09:00 | 2020-10-15 18:00 |  |  | 2020-09-04 16:36 |  |  |  | 100 | 50 | [15 empty] | 15.9504 | 0.019606 | 1.93 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3186 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018457
862 | Task(Task)-->P (Procurement) | Scrapper |  | 1.7.2.5 | Completed | No | No | 2020-04-16 09:00 | 2020-06-14 23:59 | 2020-05-30 09:00 | 2020-07-30 18:00 |  |  | 2020-05-30 16:35 | 2020-07-30 16:35 |  |  | 100 | 100 | [15 empty] | 0.49587 | 0.00061 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3187 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018458
863 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.7.2.5 | Completed | No | No | 2020-04-20 09:00 | 2020-09-16 18:00 | 2020-07-06 09:00 | 2020-07-06 18:00 |  |  | 2020-07-06 12:45 | 2020-07-06 12:45 |  |  | 100 | 100 | [15 empty] | 4.7107 | 0.00579 | 0.57 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3188 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018459
864 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.7.2.5 | Unscheduled | No | No | 2020-07-19 | 2020-08-27 18:00 | 2020-08-04 09:00 | 2020-08-04 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.24793 | 0.000305 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3189 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018460
865 | Task(Task)-->P (Procurement) | Gear Box |  | 1.7.2.5 | Completed | No | No | 2020-03-28 09:00 | 2020-05-26 18:00 | 2020-04-30 09:00 | 2020-07-01 18:00 |  |  | 2020-04-30 15:33 | 2020-07-01 15:33 |  |  | 100 | 100 | [15 empty] | 2.4793 | 0.003048 | 0.3 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3190 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018461
866 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.7.2.5 | Completed | No | No | 2020-04-19 | 2020-06-17 18:00 | 2020-04-30 09:00 | 2020-07-30 18:00 |  |  | 2020-04-30 15:31 | 2020-07-06 15:31 |  |  | 100 | 100 | [15 empty] | 0.33058 | 0.000406 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3191 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018462
867 | Task(Task)-->P (Procurement) | Fluid Coupling |  | 1.7.2.5 | Unscheduled | No | No | 2020-04-01 09:00 | 2020-05-30 18:00 | 2020-05-18 09:00 | 2020-08-21 18:00 | [6 empty] | 100 | 0 | [15 empty] | 2.562 | 0.003149 | 0.31 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3192 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018463
868 | Task(Task)-->P (Procurement) | Brake |  | 1.7.2.5 | Unscheduled | No | No | 2020-04-09 09:00 | 2020-06-07 23:59 | 2020-05-18 09:00 | 2020-08-13 18:00 |  |  | 2020-06-16 17:39 |  |  |  | 100 | 0 | [15 empty] | 0.24793 | 0.000305 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3193 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018464
869 | Task(Task)-->P (Procurement) | Building Structure |  | 1.7.2.5 | Completed | No | No | 2020-04-19 | 2020-04-25 18:00 | 2020-05-31 | 2020-05-31 23:59 |  |  | 2020-05-31 18:54 | 2020-06-22 18:54 |  |  | 100 | 100 | [15 empty] | 24.2975 | 0.029867 | 2.94 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3194 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018465
870 | Task(Task)-->P (Procurement) | HT AC MOTORS |  | 1.7.2.5 | Completed | No | No | 2020-03-08 | 2020-05-21 18:00 | 2020-07-18 09:00 | 2020-09-28 18:00 |  |  | 2020-07-18 09:04 | 2020-09-28 10:23 |  |  | 100 | 100 | [15 empty] | 7.1901 | 0.008838 | 0.87 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3195 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018466
871 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.7.2.5 | Unscheduled | No | No | 2020-04-11 09:00 | 2020-05-25 18:00 | 2020-07-10 09:00 | 2020-10-16 18:00 |  |  | 2020-07-14 10:44 |  |  |  | 100 | 0 | [15 empty] | 6.6116 | 0.008127 | 0.8 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3196 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018467
872 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.7.2.5 | Completed | No | No | 2020-06-26 09:00 | 2020-08-09 23:59 | 2020-05-30 09:00 | 2020-08-08 18:00 |  |  | 2020-06-18 17:09 | 2020-08-07 15:00 |  |  | 100 | 100 | [15 empty] | 2.9752 | 0.003657 | 0.36 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3197 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018468
873 | Task(Task)-->P (Procurement) | LPBS |  | 1.7.2.5 | Completed | No | No | 2020-04-21 09:00 | 2020-06-04 18:00 | 2020-07-25 09:00 | 2020-08-22 18:00 |  |  | 2020-07-24 18:44 | 2020-08-22 12:57 |  |  | 100 | 100 | [15 empty] | 0.082645 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3198 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018469
874 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.7.2.5 | Completed | No | No | 2020-02-06 09:00 | 2020-03-21 18:00 | 2020-08-11 09:00 | 2020-09-19 18:00 |  |  | 2020-08-11 13:11 | 2020-09-19 12:58 |  |  | 100 | 100 | [15 empty] | 1.2397 | 0.001524 | 0.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3199 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018470
875 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.7.2.5 | Unscheduled | No | No | 2020-02-02 | 2020-03-17 18:00 | 2020-08-09 | 2020-10-20 18:00 |  |  | 2020-08-09 13:16 |  |  |  | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3200 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018471
876 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.7.2.5 | Completed | No | No | 2020-02-01 09:00 | 2020-03-16 18:00 | 2020-02-01 09:00 | 2020-07-15 18:00 |  |  | 2020-02-11 21:29 | 2020-07-15 21:29 |  |  | 100 | 100 | [15 empty] | 0.082645 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3201 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018472
877 | Task(Task)-->P (Procurement) | MANUFACTURING & RECEIPT AT SITE (MRN) | 1.7.2.6 | 1.7.2 | Unscheduled | No | No | 2020-03-17 09:00 | 2021-02-13 18:00 | 2020-03-24 09:00 | 2021-05-13 18:00 |  |  | 2020-03-25 18:05 |  |  |  | 82.3202 | 1.4895 | [15 empty] | 59.995 | 0.49158 | 48.35 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3202 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018473
878 | Task(Task)-->P (Procurement) | Metal Detector |  | 1.7.2.6 | Unscheduled | No | No | 2020-04-06 09:00 | 2020-10-02 18:00 | 2020-08-13 09:00 | 2020-12-31 18:00 |  |  | 2020-08-13 16:03 |  |  |  | 100 | 25 | [15 empty] | 1.84 | 0.009045 | 0.89 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3203 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018474
879 | Task(Task)-->P (Procurement) | Pulley |  | 1.7.2.6 | Unscheduled | No | No | 2020-03-30 09:00 | 2020-11-20 18:00 | 2020-03-25 09:00 | 2020-11-30 18:00 |  |  | 2020-03-25 18:05 |  |  |  | 81.3559 | 0 | [15 empty] | 11.0399 | 0.05427 | 5.34 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3204 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018475
880 | Task(Task)-->P (Procurement) | Idler |  | 1.7.2.6 | Unscheduled | No | No | 2020-05-02 09:00 | 2020-11-13 18:00 | 2020-06-25 09:00 | 2020-12-31 18:00 | [6 empty] | 81.1225 | 0 | [15 empty] | 15.3814 | 0.075613 | 7.44 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3205 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018476
881 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.7.2.6 | Unscheduled | No | No | 2020-08-31 09:00 | 2020-12-23 18:00 | 2020-06-29 09:00 | 2020-12-31 18:00 | [6 empty] | 33.0435 | 0 | [15 empty] | 0.80628 | 0.003964 | 0.39 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3206 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018477
882 | Task(Task)-->P (Procurement) | Bearing |  | 1.7.2.6 | Unscheduled | No | No | 2020-08-26 09:00 | 2020-12-23 18:00 | 2020-03-24 09:00 | 2020-09-09 18:00 | [6 empty] | 35.8333 | 0 | [15 empty] | 1.3852 | 0.006809 | 0.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3207 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018478
883 | Task(Task)-->P (Procurement) | Belting |  | 1.7.2.6 | Unscheduled | No | No | 2020-04-21 09:00 | 2020-11-16 18:00 | 2020-10-16 09:00 | 2021-05-13 18:00 | [6 empty] | 80.9524 | 0 | [15 empty] | 15.9603 | 0.078458 | 7.72 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3208 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018479
884 | Task(Task)-->P (Procurement) | Scrapper |  | 1.7.2.6 | Unscheduled | No | No | 2020-06-15 09:00 | 2020-12-11 18:00 | 2020-07-30 09:00 | 2020-12-31 18:00 | [6 empty] | 63.8889 | 0 | [15 empty] | 0.45483 | 0.002236 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3209 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018480
885 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.7.2.6 | Unscheduled | No | No | 2020-06-19 09:00 | 2021-02-13 18:00 | 2020-07-06 09:00 | 2021-01-31 23:59 | [6 empty] | 46.25 | 0 | [15 empty] | 4.693 | 0.02307 | 2.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3210 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018481
886 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.7.2.6 | Unscheduled | No | No | 2020-08-28 09:00 | 2020-12-25 18:00 | 2020-08-04 09:00 | 2020-12-25 18:00 | [6 empty] | 34.1667 | 0 | [15 empty] | 0.26876 | 0.001321 | 0.13 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3211 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018482
887 | Task(Task)-->P (Procurement) | Gear Box |  | 1.7.2.6 | Unscheduled | No | No | 2020-05-27 09:00 | 2020-12-22 18:00 | 2020-07-01 09:00 | 2020-12-31 18:00 |  |  | 2020-07-01 17:25 |  |  |  | 63.8095 | 30 | [15 empty] | 2.5016 | 0.012297 | 1.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3212 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018483
888 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.7.2.6 | Unscheduled | No | No | 2020-06-18 09:00 | 2020-12-15 18:00 | 2020-07-30 09:00 | 2020-10-05 18:00 |  |  | 2020-07-30 17:44 |  |  |  | 61.8785 | 90 | [15 empty] | 0.31011 | 0.001524 | 0.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3213 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018484
889 | Task(Task)-->P (Procurement) | Fluid Coupling |  | 1.7.2.6 | Unscheduled | No | No | 2020-05-31 | 2020-12-26 18:00 | 2020-08-21 09:00 | 2021-01-31 23:59 | [6 empty] | 61.9048 | 0 | [15 empty] | 2.5842 | 0.012704 | 1.25 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3214 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018485
890 | Task(Task)-->P (Procurement) | Brake |  | 1.7.2.6 | Unscheduled | No | No | 2020-06-08 09:00 | 2020-12-04 18:00 | 2020-08-13 09:00 | 2020-10-31 18:00 | [6 empty] | 67.7778 | 0 | [15 empty] | 0.26876 | 0.001321 | 0.13 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3215 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018486
891 | Task(Task)-->P (Procurement) | Building Structure |  | 1.7.2.6 | Unscheduled | No | No | 2020-04-28 09:00 | 2020-09-18 18:00 | 2020-05-31 | 2021-03-31 18:00 | [6 empty] | 100 | 0 | [15 empty] | 24.3126 | 0.11952 | 11.76 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3216 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018487
892 | Task(Task)-->P (Procurement) | HT AC MOTORS |  | 1.7.2.6 | Unscheduled | No | No | 2020-05-22 09:00 | 2020-11-17 18:00 | 2020-10-21 09:00 | 2021-04-18 23:59 |  |  | 2020-09-28 10:24 |  |  |  | 77.2222 | 0 | [15 empty] | 7.1945 | 0.035367 | 3.48 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3217 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018488
893 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.7.2.6 | Unscheduled | No | No | 2020-05-26 09:00 | 2020-10-21 18:00 | 2020-10-17 09:00 | 2021-03-14 23:59 | [6 empty] | 90.604 | 0 | [15 empty] | 6.595 | 0.03242 | 3.19 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3218 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018489
894 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.7.2.6 | Unscheduled | No | No | 2020-08-10 09:00 | 2020-11-07 18:00 | 2020-09-09 09:00 | 2020-12-07 18:00 |  |  | 2020-08-07 15:00 |  |  |  | 65.5556 | 0 | [15 empty] | 2.9977 | 0.014736 | 1.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3219 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018490
895 | Task(Task)-->P (Procurement) | LPBS |  | 1.7.2.6 | Unscheduled | No | No | 2020-06-05 09:00 | 2020-09-16 18:00 | 2020-08-23 | 2020-12-04 18:00 |  |  | 2020-08-22 13:00 |  |  |  | 100 | 0 | [15 empty] | 0.082696 | 0.000407 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3220 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018491
896 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.7.2.6 | Unscheduled | No | No | 2020-03-22 | 2020-08-05 18:00 | 2020-10-31 09:00 | 2021-03-16 18:00 | [6 empty] | 100 | 0 | [15 empty] | 1.2404 | 0.006098 | 0.6 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3221 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018492
897 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.7.2.6 | Unscheduled | No | No | 2020-03-18 09:00 | 2020-07-27 18:00 | 2020-10-21 09:00 | 2021-03-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.020674 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3222 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018493
898 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.7.2.6 | Unscheduled | No | No | 2020-03-17 09:00 | 2020-07-31 18:00 | 2020-07-02 09:00 | 2020-11-15 23:59 |  |  | 2020-07-15 21:36 |  |  |  | 100 | 0 | [15 empty] | 0.062022 | 0.000305 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3223 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018494
899 | Task(Task)-->C (Construction) | CONSTRUCTION | 1.7.3 | 1.7 | Unscheduled | No | No | 2020-04-27 09:00 | 2021-08-25 18:00 | 2020-07-14 09:00 | 2022-03-17 18:00 |  |  | 2020-07-15 14:57 |  |  |  | 28.3285 | 8.4286 | [15 empty] | 22.1223 | 0.23764 | 23.37 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3224 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018495
900 | Task(Task)-->C (Construction) | CIVIL | 1.7.3.1 | 1.7.3 | Unscheduled | No | No | 2020-04-27 09:00 | 2020-06-21 23:59 | 2020-07-14 09:00 | 2020-12-02 18:00 |  |  | 2020-07-15 14:57 |  |  |  | 100 | 74.1914 | [15 empty] | 11.3605 | 0.026997 | 2.48 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3225 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018496
901 | Task(Task)-->C (Construction) | AVAILABILITY OF FRONT BY NTPC |  | 1.7.3.1 | Unscheduled | No | No | 2020-04-27 09:00 | 2020-04-27 18:00 | 2020-07-14 09:00 | 2020-10-31 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3226 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018497
902 | Task(Task)-->C (Construction) | EXCAVATION |  | 1.7.3.1 | Unscheduled | No | No | 2020-05-04 09:00 | 2020-05-12 18:00 | 2020-07-15 09:00 | 2020-11-15 23:59 |  |  | 2020-07-15 14:57 |  |  |  | 100 | 97.1963 | [15 empty] | 17.3387 | 0.004681 | 0.43 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 1605 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3227 | 0 | 4 | Low | Niharendu Kamle | [6 empty] | 0 | 0 | [222 empty] | Excavation | [21 empty] | 1018498
903 | Task(Task)-->C (Construction) | PCC |  | 1.7.3.1 | Unscheduled | No | No | 2020-05-16 09:00 | 2020-05-22 18:00 | 2020-07-24 09:00 | 2020-11-17 18:00 | [6 empty] | 100 | 50 | [15 empty] | 3.629 | 0.00098 | 0.09 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3228 | 0 | 4 | Low | Niharendu Kamle | [6 empty] | 0 | 0 | [222 empty] | PCC | [21 empty] | 1018499
904 | Task(Task)-->C (Construction) | FOUNDATIONS - RAFT |  | 1.7.3.1 | Unscheduled | No | No | 2020-05-23 09:00 | 2020-06-06 18:00 | 2020-08-20 09:00 | 2020-12-02 18:00 | [6 empty] | 100 | 96.2963 | [15 empty] | 57.6613 | 0.015567 | 1.43 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3229 | 0 | 4 | Low | Niharendu Kamle | [6 empty] | 0 | 0 | [244 empty] | 1018500
905 | Task(Task)-->C (Construction) | PADESTALS FOR SC-1A,SC-1B, SC-2A & SC-2B CONV. STR. |  | 1.7.3.1 | Unscheduled | No | No | 2020-06-02 09:00 | 2020-06-21 23:59 | 2020-08-30 | 2020-09-18 18:00 | [6 empty] | 100 | 0 | [15 empty] | 21.371 | 0.00577 | 0.53 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3230 | 0 | 4 | Low | Niharendu Kamle | [6 empty] | 0 | 0 | [244 empty] | 1018501
906 | Task(Task)-->C (Construction) | STRUCTURAL WORKS | 1.7.3.2 | 1.7.3 | Unscheduled | No | No | 2020-07-27 09:00 | 2021-01-31 23:59 | 2020-10-17 09:00 | 2021-04-23 18:00 | [6 empty] | 38.6243 | 0 | [15 empty] | 43.9304 | 0.1044 | 9.59 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3231 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018502
907 | Task(Task)-->C (Construction) | ERECTION OF STRUCTURAL STEEL |  | 1.7.3.2 | Unscheduled | No | No | 2020-07-27 09:00 | 2021-01-31 23:59 | 2020-10-17 09:00 | 2021-04-23 18:00 | [6 empty] | 38.6243 | 0 | [15 empty] | 100 | 0.1044 | 9.59 | Plan & Actual | Quantity | Metric Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 148 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3232 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018503
908 | Task(Task)-->C (Construction) | MECHANICAL EQUIPMENT WORKS | 1.7.3.3 | 1.7.3 | Unscheduled | No | No | 2021-02-14 | 2021-06-15 18:00 | 2021-04-24 09:00 | 2021-07-17 18:00 | [6 empty] | 0 | 0 | [15 empty] | 17.3156 | 0.041148 | 3.78 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5458 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018504
909 | Task(Task)-->C (Construction) | ERECTION OF SC 3A |  | 1.7.3.3 | Unscheduled | No | No | 2021-02-14 | 2021-03-20 18:00 | 2021-04-24 09:00 | 2021-05-28 18:00 | [6 empty] | 0 | 0 | [15 empty] | 48.5488 | 0.019977 | 1.84 | Plan & Actual | Quantity | Meter | 0 | 0 | 0 | 0 | 0 | 0 | 130 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3233 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018505
910 | Task(Task)-->C (Construction) | ERECTION OF SC 3B |  | 1.7.3.3 | Unscheduled | No | No | 2021-03-21 | 2021-04-24 18:00 | 2021-05-29 09:00 | 2021-07-02 18:00 | [6 empty] | 0 | 0 | [15 empty] | 48.5488 | 0.019977 | 1.84 | Plan & Actual | Quantity | Meter | 0 | 0 | 0 | 0 | 0 | 0 | 130 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5417 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018506
911 | Task(Task)-->C (Construction) | ERECTION OF METAL DETECTOR |  | 1.7.3.3 | Unscheduled | No | No | 2021-06-01 09:00 | 2021-06-15 18:00 | 2021-07-03 09:00 | 2021-07-17 18:00 | [6 empty] | 0 | 0 | [15 empty] | 2.9024 | 0.001194 | 0.11 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5459 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018507
912 | Task(Task)-->C (Construction) | BELT LAYING & JOINTING WORK |  | 1.7.3 | Unscheduled | No | No | 2021-06-16 09:00 | 2021-08-13 18:00 | 2021-07-18 | 2021-09-14 18:00 | [6 empty] | 0 | 0 | [15 empty] | 7.7416 | 0.018397 | 1.69 | Plan & Actual | Quantity | Meter | 0 | 0 | 0 | 0 | 0 | 0 | 1090 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3234 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018508
913 | Task(Task)-->C (Construction) | ELECTRICAL & INSTRUMENTATION | 1.7.3.5 | 1.7.3 | Unscheduled | No | No | 2021-01-27 09:00 | 2021-08-25 18:00 | 2021-04-19 09:00 | 2022-03-17 18:00 | [6 empty] | 0 | 0 | [15 empty] | 19.6519 | 0.0467 | 4.29 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3235 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018509
914 | Task(Task)-->C (Construction) | CABLE TRAY |  | 1.7.3.5 | Unscheduled | No | No | 2021-02-01 09:00 | 2021-02-02 18:00 | 2021-04-24 09:00 | 2021-04-25 23:59 | [6 empty] | 0 | 0 | [15 empty] | 4.9065 | 0.002291 | 0.21 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3236 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018510
915 | Task(Task)-->C (Construction) | POWER CABLE |  | 1.7.3.5 | Unscheduled | No | No | 2021-06-16 09:00 | 2021-06-16 18:00 | 2021-07-25 | 2021-07-25 23:59 | [6 empty] | 0 | 0 | [15 empty] | 3.7383 | 0.001746 | 0.16 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 1158 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3237 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018511
916 | Task(Task)-->C (Construction) | CONTROL CABLE |  | 1.7.3.5 | Unscheduled | No | No | 2021-06-16 09:00 | 2021-06-16 18:00 | 2021-09-25 09:00 | 2021-09-25 18:00 | [6 empty] | 0 | 0 | [15 empty] | 5.3738 | 0.00251 | 0.23 | Plan & Actual | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 1608 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3238 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018512
917 | Task(Task)-->C (Construction) | EARTHING |  | 1.7.3.5 | Unscheduled | No | No | 2021-02-09 09:00 | 2021-02-13 18:00 | 2021-04-21 09:00 | 2021-04-25 23:59 | [6 empty] | 0 | 0 | [15 empty] | 3.972 | 0.001855 | 0.17 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 770 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3239 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018513
918 | Task(Task)-->C (Construction) | LIGHTING |  | 1.7.3.5 | Unscheduled | No | No | 2021-01-27 09:00 | 2021-02-10 18:00 | 2021-04-19 09:00 | 2021-05-03 18:00 | [6 empty] | 0 | 0 | [15 empty] | 30.8411 | 0.014403 | 1.32 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 135 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5302 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018514
919 | Task(Task)-->C (Construction) | FIELD INTRUMENTS |  | 1.7.3.5 | Unscheduled | No | No | 2021-06-14 09:00 | 2021-06-17 18:00 | 2021-09-23 09:00 | 2021-09-26 23:59 | [6 empty] | 0 | 0 | [15 empty] | 51.1682 | 0.023896 | 2.19 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 66 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5303 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018515
920 | Task(Task)-->C (Construction) | MOTOR TERMINATION |  | 1.7.3.5 | Unscheduled | No | No | 2021-06-17 09:00 | 2021-06-17 18:00 | 2021-12-03 09:00 | 2021-12-03 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5304 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018516
921 | Task(Task)-->C (Construction) | NO LOAD RUN OF MOTOR |  | 1.7.3.5 | Unscheduled | No | No | 2021-08-22 | 2021-08-25 18:00 | 2022-03-14 09:00 | 2022-03-17 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5460 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018517
922 | Task(Task)-->E (Engineering) | KDTP-2 & DRIVE HOUSE-1 | 1.8 | 1 | Work In Progress | No | No | 2019-11-16 18:00 | 2021-09-06 18:00 | 2020-03-11 09:00 | 2022-03-29 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 58.219 | 6.2451 | [15 empty] | 2.0678 | 2.0678 | 203.35 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3240 | 0 | 1 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018518
923 | Task(Task)-->E (Engineering) | ENGINEERING | 1.8.1 | 1.8 | Work In Progress | No | No | 2019-11-16 18:00 | 2020-07-20 17:40 | 2020-04-15 18:00 | 2020-10-21 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 74.233 | [15 empty] | 2.5275 | 0.052263 | 5.14 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3241 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018519
924 | Task(Task)-->E (Engineering) | MECHANICAL | 1.8.1.1 | 1.8.1 | Unscheduled | No | No | 2019-11-16 18:00 | 2020-01-20 17:40 | 2020-04-15 18:00 | 2020-05-26 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 80 | [15 empty] | 16.7641 | 0.008761 | 0.86 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No | 3242 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036090
925 | Task(Task)-->E (Engineering) | G.A & LOAD DATA OF TRANSFER POINT KDTP-2 |  | 1.8.1.1 | Unscheduled | No | No | 2019-11-16 18:00 | 2020-01-20 17:40 | 2020-04-15 18:00 | 2020-05-26 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-0010 |  | 2020-02-13 10:26 | 7012-155-PVM-B-010 |  |  |  | A |  |  |  | 100 | 0.008761 | 0.86 | Plan & Actual | Date |  | 0 | 0 | 0 | 320 | 0 | 186.1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3243 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-11-16 18:00 | 2020-04-15 18:00 |  | 10 | 2020-04-15 23:31 |  |  | 2019-12-12 17:40 | 2020-04-17 18:00 |  | 30 | 2020-04-21 23:31 |  |  | 2019-12-18 17:40 | 2020-04-19 23:59 |  | 35 | 2020-04-23 23:31 |  |  | 2019-12-24 23:59 | 2020-04-21 18:00 |  | 65 | 2020-04-25 23:31 |  |  | 2019-12-30 17:40 | 2020-05-12 18:00 |  | 80 | 2020-05-11 23:31 | [5 empty] | 80 | 2020-07-27 18:25 | [5 empty] | 80 | 2020-07-27 18:25 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-01-20 17:40 | 2020-05-26 18:00 |  | 100 | [122 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 10 |  |  |  | 101024
926 | Task(Task)-->E (Engineering) | CIVIL | 1.8.1.2 | 1.8.1 | Work In Progress | No | No | 2020-02-01 18:00 | 2020-06-05 17:40 | 2020-04-21 18:00 | 2020-10-21 18:00 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 76.8747 | [15 empty] | 40.7407 | 0.021292 | 2.09 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No | 3249 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036091
927 | Task(Task)-->E (Engineering) | TRANSFER POINT KDTP-2 - DESIGN CALCULATION OF SUPER STRUCTURE |  | 1.8.1.2 | Unscheduled | No | No | 2020-02-01 18:00 | 2020-04-01 17:40 | 2020-04-21 18:00 | 2020-09-03 18:00 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-DC-0010 |  | 2020-02-13 11:41 | 7012-155-PVC-U-028 |  |  |  | A |  |  |  | 45.6731 | 0.009725 | 0.95 | Plan & Actual | Date |  | 0 | 0 | 0 | 354.21 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3253 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-01 18:00 | 2020-04-21 18:00 |  | 10 | 2020-05-08 23:31 |  |  | 2020-02-19 17:40 | 2020-05-11 18:00 |  | 30 |  |  |  | 2020-02-26 17:40 | 2020-05-14 18:00 |  | 35 |  |  |  | 2020-03-03 23:59 | 2020-05-21 18:00 |  | 65 | 2020-08-13 19:54 |  |  | 2020-03-09 17:40 | 2020-06-11 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-01 17:40 | 2020-06-25 18:00 |  | 100 | [122 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 129 |  |  |  | 101143
928 | Task(Task)-->E (Engineering) | TRANSFER POINT KDTP-2 - DESIGN CALCULATION OF SUB STRUCTURE |  | 1.8.1.2 | Completed | No | No | 2020-03-07 18:00 | 2020-05-06 17:40 | 2020-08-19 09:00 | 2020-09-01 18:00 |  |  | 2020-02-21 15:37 | 2020-09-02 00:50 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-DC-0011 |  | 2020-02-13 11:41 | 7012-155-PVC-U-029 |  |  |  | A |  |  |  | 27.4038 | 0.005835 | 0.57 | Plan & Actual | Date |  | 0 | 0 | 0 | 212.29 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3254 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-07 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-25 17:40 | 2020-06-10 18:00 |  | 30 |  |  |  | 2020-04-01 17:40 | 2020-06-13 18:00 |  | 35 |  |  |  | 2020-04-07 23:59 | 2020-06-20 18:00 |  | 65 | 2020-08-19 21:24 |  |  | 2020-04-14 17:40 | 2020-07-11 18:00 |  | 80 | 2020-09-02 00:45 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-06 17:40 | 2020-07-25 18:00 |  | 100 | 2020-09-02 00:51 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 130 |  |  |  | 101144
929 | Task(Task)-->E (Engineering) | TRANSFER POINT KDTP-2 - NUM & RC DETAILS OF FDN |  | 1.8.1.2 | Completed | No | No | 2020-03-07 18:00 | 2020-05-06 17:40 | 2020-08-19 09:00 | 2020-09-01 18:00 |  |  | 2020-02-21 15:37 | 2020-09-02 00:50 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-NR-0011 |  | 2020-02-13 11:41 | 7012-155-PVC-C-031 |  |  |  | A |  |  |  | 16.3462 | 0.00348 | 0.34 | Plan & Actual | Date |  | 0 | 0 | 0 | 127.29 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3250 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-07 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-25 17:40 | 2020-06-10 18:00 |  | 30 |  |  |  | 2020-04-01 17:40 | 2020-06-13 18:00 |  | 35 | 2020-08-19 17:48 |  |  | 2020-04-07 23:59 | 2020-06-20 18:00 |  | 65 | 2020-08-19 21:24 |  |  | 2020-04-14 17:40 | 2020-07-11 18:00 |  | 80 | 2020-09-02 00:43 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-06 17:40 | 2020-07-25 18:00 |  | 100 | 2020-09-02 00:51 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 132 |  |  |  | 101146
930 | Task(Task)-->E (Engineering) | TRANSFER POINT KDTP-2 - NUM & RC DETAILS OF FLOOR SLABS |  | 1.8.1.2 | Unscheduled | No | No | 2020-04-06 18:00 | 2020-06-05 17:40 | 2020-06-25 18:00 | 2020-10-21 18:00 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-NR-0012 |  | 2020-02-13 11:41 | 7012-155-PVC-C-032 |  |  |  | A |  |  |  | 5.2885 | 0.001126 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 42.3 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3251 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-06 18:00 | 2020-06-25 18:00 |  | 10 |  |  |  | 2020-04-24 17:40 | 2020-07-15 18:00 |  | 30 |  |  |  | 2020-05-01 17:40 | 2020-07-18 18:00 |  | 35 | 2020-09-26 14:51 |  |  | 2020-05-07 23:59 | 2020-07-25 18:00 |  | 65 | 2020-09-27 11:10 |  |  | 2020-05-14 17:40 | 2020-08-15 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-05 17:40 | 2020-08-29 18:00 |  | 100 | [122 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 133 |  |  |  | 101147
931 | Task(Task)-->E (Engineering) | TRANSFER POINT KDTP-2 - NUM & RC DETAILS OF GRADE SLAB |  | 1.8.1.2 | Unscheduled | No | No | 2020-04-06 18:00 | 2020-06-05 17:40 | 2020-07-15 18:00 | 2020-09-18 18:00 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-NR-0013 |  | 2020-02-13 11:41 | 7012-155-PVC-C-033 |  |  |  | A |  |  |  | 5.2885 | 0.001126 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 42.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3252 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-06 18:00 | 2020-07-15 18:00 |  | 10 |  |  |  | 2020-04-24 17:40 | 2020-08-04 18:00 |  | 30 |  |  |  | 2020-05-01 17:40 | 2020-08-07 18:00 |  | 35 |  |  |  | 2020-05-07 23:59 | 2020-08-14 18:00 |  | 65 |  |  |  | 2020-05-14 17:40 | 2020-09-04 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-05 17:40 | 2020-09-18 18:00 |  | 100 | [122 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 134 |  |  |  | 101148
932 | Task(Task)-->E (Engineering) | STRUCTURAL | 1.8.1.3 | 1.8.1 | Unscheduled | No | No | 2020-02-01 18:00 | 2020-07-20 17:40 | 2020-04-21 18:00 | 2020-09-08 18:00 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 58.2526 | [15 empty] | 20.6628 | 0.010799 | 1.06 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No | 3255 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036092
933 | Task(Task)-->E (Engineering) | TRANSFER POINT KDTP-2 - STRUCTURAL GA |  | 1.8.1.3 | Unscheduled | No | No | 2020-02-01 18:00 | 2020-04-01 17:40 | 2020-04-21 18:00 | 2020-09-03 18:00 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-GA-0007 |  | 2020-02-13 11:41 | 7012-155-PVC-B-030 |  |  |  | A |  |  |  | 89.6226 | 0.009678 | 0.95 | Plan & Actual | Date |  | 0 | 0 | 0 | 354.21 | 0 | 131.4 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3257 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-01 18:00 | 2020-04-21 18:00 |  | 10 | 2020-05-08 23:31 |  |  | 2020-02-19 17:40 | 2020-05-11 18:00 |  | 30 |  |  |  | 2020-02-26 17:40 | 2020-05-14 18:00 |  | 35 | 2020-08-10 17:31 |  |  | 2020-03-03 23:59 | 2020-05-21 18:00 |  | 65 | 2020-08-13 19:54 |  |  | 2020-03-09 17:40 | 2020-06-11 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-01 17:40 | 2020-06-25 18:00 |  | 100 | [122 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 131 |  |  |  | 101145
934 | Task(Task)-->E (Engineering) | ARCHITECTURAL GA OF TRANSFER POINT KDTP-2 |  | 1.8.1.3 | Unscheduled | No | No | 2020-05-21 18:00 | 2020-07-20 17:40 | 2020-06-30 18:00 | 2020-09-08 18:00 |  |  | 2020-02-21 15:39 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-AR-0004 |  | 2020-02-13 11:43 | 7012-155-PVC-C-110 |  |  |  | I |  |  |  | 10.3774 | 0.001121 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 40.52 | 0 | 64 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3256 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-05-21 18:00 | 2020-06-30 18:00 |  | 10 |  |  |  | 2020-06-09 17:40 | 2020-07-25 18:00 |  | 30 |  |  |  | 2020-06-16 17:40 | 2020-07-28 18:00 |  | 35 |  |  |  | 2020-06-21 23:59 | 2020-08-04 18:00 |  | 65 |  |  |  | 2020-06-26 17:40 | 2020-08-25 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-07-20 17:40 | 2020-09-08 18:00 |  | 100 | [122 empty] | Chetan Khodke |  |  |  |  | A - Architecture | [16 empty] | 211 |  |  |  | 101221
935 | Task(Task)-->E (Engineering) | ELECTRICAL | 1.8.1.4 | 1.8.1 | Unscheduled | No | No | 2020-01-28 18:00 | 2020-05-22 17:40 | 2020-04-20 18:00 | 2020-06-14 23:59 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 | [15 empty] | 21.8324 | 0.01141 | 1.12 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No | 3260 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036093
936 | Task(Task)-->E (Engineering) | EQUIPMENT, CABLE ROUTING, EARTHING & LIGHTNING LAYOUT WITH PLAN, SECTIONAL VIEWS & BOM OF KDTP-2 |  | 1.8.1.4 | Unscheduled | No | No | 2020-01-28 18:00 | 2020-03-24 17:40 | 2020-04-20 18:00 | 2020-06-12 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5055 |  | 2020-02-13 11:44 | 7012-155-PVE-F-017 |  |  |  | A |  |  |  | 40.1786 | 0.004584 | 0.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 165.48 | 0 | 45.31 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3261 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-28 18:00 | 2020-04-20 18:00 |  | 10 | 2020-04-20 23:31 |  |  | 2020-02-12 17:40 | 2020-05-04 18:00 |  | 30 | 2020-05-30 23:31 |  |  | 2020-02-18 17:40 | 2020-05-11 18:00 |  | 35 | 2020-05-30 23:31 |  |  | 2020-02-25 23:59 | 2020-05-18 18:00 |  | 65 | 2020-07-20 12:39 |  |  | 2020-03-02 17:40 | 2020-06-08 18:00 |  | 80 | 2020-07-28 17:52 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-24 17:40 | 2020-06-08 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 252 |  |  |  | 101263
937 | Task(Task)-->E (Engineering) | LIGHTING LAYOUT PLAN WITH POWER DISTRIBUTION ARRANGEMENT, SECTIONAL VIEW, BOM OF KDTP-2 |  | 1.8.1.4 | Unscheduled | No | No | 2020-04-02 18:00 | 2020-05-22 17:40 | 2020-05-03 23:59 | 2020-06-14 23:59 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5066 |  | 2020-02-13 11:44 | 7012-155-PVE-G-028 |  |  |  | A |  |  |  | 59.8214 | 0.006826 | 0.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 248.42 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3262 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-02 18:00 | 2020-05-03 23:59 |  | 10 | 2020-05-03 23:31 |  |  | 2020-04-10 17:40 | 2020-05-10 23:59 |  | 30 | 2020-05-10 23:31 |  |  | 2020-04-17 17:40 | 2020-05-17 23:59 |  | 35 | 2020-05-17 23:31 |  |  | 2020-04-23 23:59 | 2020-05-24 23:59 |  | 65 | 2020-05-14 23:31 |  |  | 2020-04-30 17:40 | 2020-06-14 23:59 |  | 80 | 2020-05-22 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-22 17:40 | 2020-06-14 23:59 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 263 |  |  |  | 101274
938 | Task(Task)-->P (Procurement) | PROCUREMENT | 1.8.2 | 1.8 | Work In Progress | No | No | 2020-02-06 09:00 | 2021-02-13 18:00 | 2020-03-11 09:00 | 2021-05-13 18:00 |  |  | 2020-03-11 10:57 |  |  |  | 92.4024 | 9.4364 | [15 empty] | 46.2972 | 0.95731 | 94.15 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3265 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018524
939 | Task(Task)-->P (Procurement) | PURCHASE REQUISITION | 1.8.2.1 | 1.8.2 | Work In Progress | No | No | 2020-02-06 09:00 | 2020-03-27 18:00 | 2020-03-11 09:00 | 2020-05-29 18:00 |  |  | 2020-03-11 10:57 |  |  |  | 100 | 29.7237 | [15 empty] | 5.0027 | 0.047891 | 4.71 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3266 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018525
940 | Task(Task)-->P (Procurement) | Flap Gate |  | 1.8.2.1 | Completed | No | No | 2020-02-06 09:00 | 2020-02-06 18:00 | 2020-03-20 09:00 | 2020-03-20 18:00 |  |  | 2020-03-20 10:57 | 2020-03-20 10:57 |  |  | 100 | 100 | [15 empty] | 2.9724 | 0.001424 | 0.14 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3267 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018526
941 | Task(Task)-->P (Procurement) | Chute & Skirt |  | 1.8.2.1 | Completed | No | No | 2020-03-10 09:00 | 2020-03-10 18:00 | 2020-03-11 09:00 | 2020-03-11 18:00 |  |  | 2020-03-11 10:57 | 2020-03-11 10:57 |  |  | 100 | 100 | [15 empty] | 18.4713 | 0.008846 | 0.87 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3268 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018527
942 | Task(Task)-->P (Procurement) | Building Structure |  | 1.8.2.1 | Unscheduled | No | No | 2020-03-03 09:00 | 2020-03-03 18:00 | 2020-05-29 09:00 | 2020-05-29 18:00 | [6 empty] | 100 | 0 | [15 empty] | 70.276 | 0.033656 | 3.31 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3269 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018528
943 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.8.2.1 | Completed | No | No | 2020-03-10 09:00 | 2020-03-10 18:00 | 2020-03-16 09:00 | 2020-03-16 18:00 |  |  | 2020-03-16 10:57 | 2020-03-16 10:57 |  |  | 100 | 100 | [15 empty] | 5.7325 | 0.002745 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3270 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018529
944 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.8.2.1 | Completed | No | No | 2020-03-27 09:00 | 2020-03-27 18:00 | 2020-04-30 09:00 | 2020-04-30 18:00 |  |  | 2020-04-30 10:57 | 2020-04-30 10:57 |  |  | 100 | 100 | [15 empty] | 2.5478 | 0.00122 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3271 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018530
945 | Task(Task)-->P (Procurement) | TECHNICAL CLEARANCE | 1.8.2.2 | 1.8.2 | Work In Progress | No | No | 2020-02-07 09:00 | 2020-05-11 18:00 | 2020-03-11 09:00 | 2020-06-03 18:00 |  |  | 2020-03-17 10:57 |  |  |  | 100 | 29.7237 | [15 empty] | 5.0027 | 0.047891 | 4.71 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3274 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018531
946 | Task(Task)-->P (Procurement) | Flap Gate |  | 1.8.2.2 | Completed | No | No | 2020-02-07 09:00 | 2020-03-22 23:59 | 2020-03-21 09:00 | 2020-04-28 18:00 |  |  | 2020-04-28 10:57 | 2020-04-28 10:57 |  |  | 100 | 100 | [15 empty] | 2.9724 | 0.001424 | 0.14 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3275 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018532
947 | Task(Task)-->P (Procurement) | Chute & Skirt |  | 1.8.2.2 | Completed | No | No | 2020-03-11 09:00 | 2020-03-20 18:00 | 2020-03-11 09:00 | 2020-03-17 18:00 |  |  | 2020-03-17 10:57 | 2020-03-17 10:57 |  |  | 100 | 100 | [15 empty] | 18.4713 | 0.008846 | 0.87 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3276 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018533
948 | Task(Task)-->P (Procurement) | Building Structure |  | 1.8.2.2 | Unscheduled | No | No | 2020-03-04 09:00 | 2020-03-10 18:00 | 2020-05-29 09:00 | 2020-05-29 18:00 | [6 empty] | 100 | 0 | [15 empty] | 70.276 | 0.033656 | 3.31 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3277 | 1 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018534
949 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.8.2.2 | Completed | No | No | 2020-03-11 09:00 | 2020-03-25 18:00 | 2020-03-16 09:00 | 2020-06-02 18:00 |  |  | 2020-06-02 10:57 | 2020-06-02 10:57 |  |  | 100 | 100 | [15 empty] | 5.7325 | 0.002745 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3278 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018535
950 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.8.2.2 | Completed | No | No | 2020-03-28 09:00 | 2020-05-11 18:00 | 2020-04-30 09:00 | 2020-06-03 18:00 |  |  | 2020-06-03 10:57 | 2020-06-03 10:57 |  |  | 100 | 100 | [15 empty] | 2.5478 | 0.00122 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3279 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018536
951 | Task(Task)-->P (Procurement) | ORDERING | 1.8.2.3 | 1.8.2 | Work In Progress | No | No | 2020-03-11 09:00 | 2020-06-25 18:00 | 2020-03-17 09:00 | 2020-08-22 18:00 |  |  | 2020-03-18 12:49 |  |  |  | 100 | 29.6488 | [15 empty] | 9.9947 | 0.09568 | 9.41 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3282 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018537
952 | Task(Task)-->P (Procurement) | Flap Gate |  | 1.8.2.3 | Completed | No | No | 2020-03-23 09:00 | 2020-04-21 18:00 | 2020-04-28 09:00 | 2020-08-22 18:00 |  |  | 2020-04-28 16:12 | 2020-08-22 16:12 |  |  | 100 | 100 | [15 empty] | 3.0818 | 0.002949 | 0.29 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3283 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018538
953 | Task(Task)-->P (Procurement) | Chute & Skirt |  | 1.8.2.3 | Completed | No | No | 2020-03-21 09:00 | 2020-04-19 23:59 | 2020-03-17 09:00 | 2020-07-06 18:00 |  |  | 2020-03-18 12:49 | 2020-07-06 12:49 |  |  | 100 | 100 | [15 empty] | 18.3847 | 0.01759 | 1.73 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3284 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018539
954 | Task(Task)-->P (Procurement) | Building Structure |  | 1.8.2.3 | Unscheduled | No | No | 2020-03-11 09:00 | 2020-04-09 18:00 | 2020-05-29 09:00 | 2020-07-28 18:00 | [6 empty] | 100 | 0 | [15 empty] | 70.3507 | 0.067312 | 6.62 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3285 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018540
955 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.8.2.3 | Completed | No | No | 2020-03-26 09:00 | 2020-04-10 18:00 | 2020-06-02 09:00 | 2020-07-31 18:00 |  |  | 2020-06-03 15:51 | 2020-06-29 15:51 |  |  | 100 | 100 | [15 empty] | 5.6323 | 0.005389 | 0.53 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3286 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018541
956 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.8.2.3 | Completed | No | No | 2020-05-12 09:00 | 2020-06-25 18:00 | 2020-06-03 09:00 | 2020-06-24 18:00 |  |  | 2020-06-15 10:57 | 2020-06-15 10:57 |  |  | 100 | 100 | [15 empty] | 2.5505 | 0.00244 | 0.24 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3287 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018542
957 | Task(Task)-->P (Procurement) | ITP APPROVAL | 1.8.2.4 | 1.8.2 | Work In Progress | No | No | 2020-04-10 09:00 | 2020-08-04 18:00 | 2020-06-23 09:00 | 2020-10-30 18:00 |  |  | 2020-06-23 17:39 |  |  |  | 100 | 5.7318 | [15 empty] | 5.0027 | 0.047891 | 4.71 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3290 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018543
958 | Task(Task)-->P (Procurement) | Flap Gate |  | 1.8.2.4 | Unscheduled | No | No | 2020-04-22 09:00 | 2020-05-31 23:59 | 2020-08-22 09:00 | 2020-10-30 18:00 |  |  | 2020-08-22 16:16 |  |  |  | 100 | 0 | [15 empty] | 2.9724 | 0.001424 | 0.14 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3291 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018544
959 | Task(Task)-->P (Procurement) | Chute & Skirt |  | 1.8.2.4 | Unscheduled | No | No | 2020-04-20 09:00 | 2020-05-29 18:00 | 2020-07-06 09:00 | 2020-07-16 18:00 | [6 empty] | 100 | 0 | [15 empty] | 18.4713 | 0.008846 | 0.87 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3292 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018545
960 | Task(Task)-->P (Procurement) | Building Structure |  | 1.8.2.4 | Unscheduled | No | No | 2020-04-10 09:00 | 2020-04-16 18:00 | 2020-07-28 09:00 | 2020-08-03 18:00 | [6 empty] | 100 | 0 | [15 empty] | 70.276 | 0.033656 | 3.31 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3293 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018546
961 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.8.2.4 | Completed | No | No | 2020-04-11 09:00 | 2020-05-20 18:00 | 2020-07-28 09:00 | 2020-09-08 18:00 |  |  | 2020-07-08 17:23 | 2020-09-08 17:23 |  |  | 100 | 100 | [15 empty] | 5.7325 | 0.002745 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3294 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018547
962 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.8.2.4 | Unscheduled | No | No | 2020-06-26 09:00 | 2020-08-04 18:00 | 2020-06-23 09:00 | 2020-09-08 18:00 |  |  | 2020-06-23 17:39 |  |  |  | 100 | 0 | [15 empty] | 2.5478 | 0.00122 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3295 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018548
963 | Task(Task)-->P (Procurement) | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE | 1.8.2.5 | 1.8.2 | Work In Progress | No | No | 2020-04-08 09:00 | 2020-09-16 18:00 | 2020-05-30 09:00 | 2020-10-16 18:00 |  |  | 2020-06-18 17:10 |  |  |  | 100 | 21.4201 | [15 empty] | 14.9973 | 0.14357 | 14.12 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3298 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018549
964 | Task(Task)-->P (Procurement) | Flap Gate |  | 1.8.2.5 | Unscheduled | No | No | 2020-04-22 09:00 | 2020-06-20 18:00 | 2020-08-22 09:00 | 2020-10-15 18:00 |  |  | 2020-08-22 16:14 |  |  |  | 100 | 15 | [15 empty] | 3.0453 | 0.004372 | 0.43 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3299 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018550
965 | Task(Task)-->P (Procurement) | Chute & Skirt |  | 1.8.2.5 | Completed | No | No | 2020-04-20 09:00 | 2020-09-16 18:00 | 2020-07-06 09:00 | 2020-07-06 18:00 |  |  | 2020-07-06 12:51 | 2020-07-06 12:51 |  |  | 100 | 100 | [15 empty] | 18.4136 | 0.026437 | 2.6 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3300 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018551
966 | Task(Task)-->P (Procurement) | Building Structure |  | 1.8.2.5 | Unscheduled | No | No | 2020-04-08 09:00 | 2020-04-14 18:00 | 2020-07-28 09:00 | 2020-08-25 18:00 | [6 empty] | 100 | 0 | [15 empty] | 70.3258 | 0.10097 | 9.93 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3301 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018552
967 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.8.2.5 | Unscheduled | No | No | 2020-04-11 09:00 | 2020-05-25 18:00 | 2020-07-10 09:00 | 2020-10-16 18:00 |  |  | 2020-07-14 10:44 |  |  |  | 100 | 0 | [15 empty] | 5.6657 | 0.008134 | 0.8 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3302 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018553
968 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.8.2.5 | Completed | No | No | 2020-06-26 09:00 | 2020-08-09 23:59 | 2020-05-30 09:00 | 2020-08-08 18:00 |  |  | 2020-06-18 17:10 | 2020-08-07 15:00 |  |  | 100 | 100 | [15 empty] | 2.5496 | 0.00366 | 0.36 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3303 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018554
969 | Task(Task)-->P (Procurement) | MANUFACTURING & RECEIPT AT SITE (MRN) | 1.8.2.6 | 1.8.2 | Unscheduled | No | No | 2020-04-17 09:00 | 2021-02-13 18:00 | 2020-07-06 09:00 | 2021-05-13 18:00 |  |  | 2020-08-07 15:00 |  |  |  | 87.3374 | 0 | [15 empty] | 60 | 0.57439 | 56.49 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3306 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018555
970 | Task(Task)-->P (Procurement) | Flap Gate |  | 1.8.2.6 | Unscheduled | No | No | 2020-06-21 | 2021-01-01 18:00 | 2020-10-31 09:00 | 2021-05-13 18:00 | [6 empty] | 55.8974 | 0 | [15 empty] | 3.0448 | 0.017489 | 1.72 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3307 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018556
971 | Task(Task)-->P (Procurement) | Chute & Skirt |  | 1.8.2.6 | Unscheduled | No | No | 2020-06-19 09:00 | 2021-02-13 18:00 | 2020-07-06 09:00 | 2021-01-31 23:59 | [6 empty] | 46.25 | 0 | [15 empty] | 18.428 | 0.10585 | 10.41 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3308 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018557
972 | Task(Task)-->P (Procurement) | Building Structure |  | 1.8.2.6 | Unscheduled | No | No | 2020-04-17 09:00 | 2020-10-05 18:00 | 2020-08-25 09:00 | 2021-03-31 18:00 | [6 empty] | 100 | 0 | [15 empty] | 70.3133 | 0.40387 | 39.72 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3309 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018558
973 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.8.2.6 | Unscheduled | No | No | 2020-05-26 09:00 | 2020-10-21 18:00 | 2020-10-17 09:00 | 2021-03-14 23:59 | [6 empty] | 90.604 | 0 | [15 empty] | 5.647 | 0.032436 | 3.19 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3310 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018559
974 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.8.2.6 | Unscheduled | No | No | 2020-08-10 09:00 | 2020-11-07 18:00 | 2020-09-09 09:00 | 2020-12-07 18:00 |  |  | 2020-08-07 15:00 |  |  |  | 65.5556 | 0 | [15 empty] | 2.5668 | 0.014744 | 1.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3311 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018560
975 | Task(Task)-->C (Construction) | CONSTRUCTION | 1.8.3 | 1.8 | Unscheduled | No | No | 2020-04-21 09:00 | 2021-09-06 18:00 | 2020-08-26 09:00 | 2022-03-29 18:00 | [6 empty] | 25.2304 | 0 | [15 empty] | 51.1753 | 1.0582 | 104.07 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3314 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018561
976 | Task(Task)-->C (Construction) | CIVIL | 1.8.3.1 | 1.8.3 | Unscheduled | No | No | 2020-04-21 09:00 | 2021-05-02 23:59 | 2020-08-26 09:00 | 2021-09-07 18:00 | [6 empty] | 31.5727 | 0 | [15 empty] | 48.03 | 0.50824 | 49.98 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3315 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018562
977 | Task(Task)-->C (Construction) | AVAILABILITY OF FRONT BY NTPC |  | 1.8.3.1 | Unscheduled | No | No | 2020-04-21 09:00 | 2020-04-21 18:00 | 2020-08-26 09:00 | 2020-08-26 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3316 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018563
978 | Task(Task)-->C (Construction) | EXCAVATION |  | 1.8.3.1 | Unscheduled | No | No | 2020-04-28 09:00 | 2020-06-04 18:00 | 2020-09-02 09:00 | 2020-10-09 18:00 | [6 empty] | 100 | 0 | [15 empty] | 6.0224 | 0.030608 | 3.01 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 11270 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3317 | 0 | 4 | Low | ADMINISTRATOR | [6 empty] | 0 | 0 | [222 empty] | Excavation | [21 empty] | 1018564
979 | Task(Task)-->C (Construction) | PCC |  | 1.8.3.1 | Unscheduled | No | No | 2020-05-19 09:00 | 2020-05-28 18:00 | 2020-09-24 09:00 | 2020-10-03 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.7403 | 0.003763 | 0.37 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3318 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | PCC | [21 empty] | 1018565
980 | Task(Task)-->C (Construction) | RAFT |  | 1.8.3.1 | Unscheduled | No | No | 2020-05-29 09:00 | 2020-06-11 18:00 | 2020-10-04 | 2020-10-17 18:00 | [6 empty] | 100 | 0 | [15 empty] | 14.3257 | 0.07281 | 7.16 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 270 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3319 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018566
981 | Task(Task)-->C (Construction) | PADESTALS FOR KDTP-2 STR. |  | 1.8.3.1 | Unscheduled | No | No | 2020-06-12 09:00 | 2020-07-07 18:00 | 2020-10-18 | 2020-11-12 18:00 | [6 empty] | 100 | 0 | [15 empty] | 2.6611 | 0.013525 | 1.33 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3320 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018567
982 | Task(Task)-->C (Construction) | RCC FLOOR FOR TAIL PULLEY OF PC-2A/B |  | 1.8.3.1 | Unscheduled | No | No | 2020-10-04 | 2020-10-19 18:00 | 2021-02-09 09:00 | 2021-02-24 18:00 | [6 empty] | 25 | 0 | [15 empty] | 3.4414 | 0.017491 | 1.72 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3322 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | RCC | [21 empty] | 1018568
983 | Task(Task)-->C (Construction) | RCC FLOOR FOR HEAD PULLEY OF PC-1A/B |  | 1.8.3.1 | Unscheduled | No | No | 2020-11-03 09:00 | 2020-11-21 18:00 | 2021-03-11 09:00 | 2021-03-29 18:00 | [6 empty] | 0 | 0 | [15 empty] | 3.4414 | 0.017491 | 1.72 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3323 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | RCC | [21 empty] | 1018569
984 | Task(Task)-->C (Construction) | DRIVE HOUSE FOUNDATION |  | 1.8.3.1 | Unscheduled | No | No | 2020-06-12 09:00 | 2020-07-12 23:59 | 2020-10-18 | 2020-11-17 18:00 | [6 empty] | 100 | 0 | [15 empty] | 2.9812 | 0.015152 | 1.49 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3324 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018570
985 | Task(Task)-->C (Construction) | HGTU FOUNDATION |  | 1.8.3.1 | Unscheduled | No | No | 2020-06-26 09:00 | 2020-07-25 18:00 | 2020-11-01 | 2020-11-30 18:00 | [6 empty] | 100 | 0 | [15 empty] | 3.9816 | 0.020236 | 1.99 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5474 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018571
986 | Task(Task)-->C (Construction) | GRADE SLAB FLOOR |  | 1.8.3.1 | Unscheduled | No | No | 2021-04-02 09:00 | 2021-05-02 23:59 | 2021-08-08 | 2021-09-07 18:00 | [6 empty] | 0 | 0 | [15 empty] | 62.405 | 0.31717 | 31.19 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 1666 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3325 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018572
987 | Task(Task)-->C (Construction) | STRUCTURAL WORKS | 1.8.3.2 | 1.8.3 | Unscheduled | No | No | 2020-08-05 09:00 | 2021-04-01 18:00 | 2020-12-11 09:00 | 2021-08-07 18:00 | [6 empty] | 26.6667 | 0 | [15 empty] | 37.7475 | 0.39943 | 39.28 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3326 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018573
988 | Task(Task)-->C (Construction) | ERECTION OF STRUCTURAL STEEL |  | 1.8.3.2 | Unscheduled | No | No | 2020-08-05 09:00 | 2021-04-01 18:00 | 2020-12-11 09:00 | 2021-08-07 18:00 | [6 empty] | 26.6667 | 0 | [15 empty] | 100 | 0.39943 | 39.28 | Plan & Actual | Quantity | Metric Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 608 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3327 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018574
989 | Task(Task)-->C (Construction) | MECHANICAL EQUIPMENT WORKS | 1.8.3.3 | 1.8.3 | Unscheduled | No | No | 2021-05-03 09:00 | 2021-07-31 18:00 | 2021-09-08 09:00 | 2021-12-06 18:00 | [6 empty] | 0 | 0 | [15 empty] | 5.295 | 0.056031 | 5.51 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5461 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018575
990 | Task(Task)-->C (Construction) | ERECTION OF CHUTES/ HOODS & SUPPORTS |  | 1.8.3.3 | Unscheduled | No | No | 2021-05-03 09:00 | 2021-07-31 18:00 | 2021-09-08 09:00 | 2021-12-06 18:00 | [6 empty] | 0 | 0 | [15 empty] | 100 | 0.056031 | 5.51 | Plan & Actual | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3328 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018576
991 | Task(Task)-->C (Construction) | ELECTRICAL & INSTRUMENTATION (E&I) | 1.8.3.4 | 1.8.3 | Unscheduled | No | No | 2021-03-28 | 2021-08-30 18:00 | 2021-08-03 09:00 | 2022-03-22 18:00 | [6 empty] | 0 | 0 | [15 empty] | 7.4476 | 0.078809 | 7.75 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5247 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018577
992 | Task(Task)-->C (Construction) | CABLE TRAY |  | 1.8.3.4 | Unscheduled | No | No | 2021-03-28 | 2021-04-11 23:59 | 2021-08-03 09:00 | 2021-08-17 18:00 | [6 empty] | 0 | 0 | [15 empty] | 8.2474 | 0.0065 | 0.64 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3329 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018578
993 | Task(Task)-->C (Construction) | POWER CABLE |  | 1.8.3.4 | Unscheduled | No | No | 2021-07-25 | 2021-08-03 18:00 | 2021-11-30 09:00 | 2021-12-09 18:00 | [6 empty] | 0 | 0 | [15 empty] | 39.3041 | 0.030975 | 3.05 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 21520 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5248 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018579
994 | Task(Task)-->C (Construction) | CONTROL CABLE |  | 1.8.3.4 | Unscheduled | No | No | 2021-07-30 09:00 | 2021-08-03 18:00 | 2021-12-05 | 2021-12-09 18:00 | [6 empty] | 0 | 0 | [15 empty] | 27.0619 | 0.021327 | 2.1 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 14860 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3330 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018580
995 | Task(Task)-->C (Construction) | EARTHING |  | 1.8.3.4 | Unscheduled | No | No | 2021-04-05 09:00 | 2021-04-11 23:59 | 2021-08-11 09:00 | 2021-08-17 18:00 | [6 empty] | 0 | 0 | [15 empty] | 3.866 | 0.003047 | 0.3 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 1325 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5306 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018581
996 | Task(Task)-->C (Construction) | EARTH PIT |  | 1.8.3.4 | Unscheduled | No | No | 2021-04-28 09:00 | 2021-05-02 23:59 | 2021-09-03 09:00 | 2021-09-07 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5307 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018582
997 | Task(Task)-->C (Construction) | LIGHTING |  | 1.8.3.4 | Unscheduled | No | No | 2021-04-02 09:00 | 2021-04-16 18:00 | 2021-08-08 | 2021-08-22 23:59 | [6 empty] | 0 | 0 | [15 empty] | 12.6289 | 0.009953 | 0.98 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5308 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018583
998 | Task(Task)-->C (Construction) | FIELD INTRUMENTS |  | 1.8.3.4 | Unscheduled | No | No | 2021-07-31 09:00 | 2021-08-04 18:00 | 2021-12-06 09:00 | 2021-12-10 18:00 | [6 empty] | 0 | 0 | [15 empty] | 8.8918 | 0.007008 | 0.69 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5309 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018584
999 | Task(Task)-->C (Construction) | MOTOR TERMINATION |  | 1.8.3.4 | Unscheduled | No | No | 2021-08-04 09:00 | 2021-08-07 18:00 | 2021-12-10 09:00 | 2021-12-13 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5310 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018585
1000 | Task(Task)-->C (Construction) | NO LOAD RUN OF MOTOR |  | 1.8.3.4 | Unscheduled | No | No | 2021-08-27 09:00 | 2021-08-30 18:00 | 2022-03-19 09:00 | 2022-03-22 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5462 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018586
1001 | Task(Task)-->C (Construction) | NO LOAD COMMISSIONING & SYSTEM READYNESS FOR LOAD & TRIAL OPERATION |  | 1.8.3 | Unscheduled | No | No | 2021-08-31 09:00 | 2021-09-06 18:00 | 2022-03-23 09:00 | 2022-03-29 18:00 | [6 empty] | 0 | 0 | [15 empty] | 1.4799 | 0.01566 | 1.54 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5311 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018587
1002 | Task(Task)-->E (Engineering) | PIPE CONVEYOR PC 1A & PC 1B | 1.9 | 1 | Work In Progress | No | No | 2019-10-25 18:00 | 2021-09-13 18:00 | 2019-11-08 09:00 | 2022-04-05 18:00 |  |  | 2019-11-08 17:06 |  |  |  | 55.0286 | 23.9351 | [15 empty] | 23.0338 | 23.0338 | 2265.22 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3331 | 0 | 1 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018588
1003 | Task(Task)-->E (Engineering) | ENGINEERING | 1.9.1 | 1.9 | Work In Progress | No | No | 2019-10-25 18:00 | 2020-08-21 17:40 | 2020-01-13 18:00 | 2020-10-23 18:00 |  |  | 2020-02-11 17:40 |  |  |  | 100 | 78.8019 | [15 empty] | 1.7045 | 0.39261 | 38.61 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3332 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018589
1004 | Task(Task)-->E (Engineering) | MECHANICAL | 1.9.1.1 | 1.9.1 | Work In Progress | No | No | 2019-10-25 18:00 | 2020-08-10 17:40 | 2020-01-13 18:00 | 2020-10-23 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 48.744 | [15 empty] | 20.3574 | 0.079924 | 7.86 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3333 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036094
1005 | Task(Task)-->E (Engineering) | TYP. CROSS SECTION DETAILS OF PIPE CONV. GALLERY |  | 1.9.1.1 | Unscheduled | No | No | 2019-10-25 18:00 | 2019-12-26 17:40 | 2020-01-13 18:00 | 2020-03-03 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-CS-GA-0006 |  | 2020-02-13 10:26 | 7012-155-PVM-B-006 |  |  |  | A |  |  |  | 5.5917 | 0.004469 | 0.43 | Plan & Actual | Date |  | 0 | 0 | 0 | 160 | 0 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3352 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-10-25 18:00 | 2020-01-13 18:00 |  | 10 | 2020-01-13 23:31 |  |  | 2019-11-18 17:40 | 2020-02-03 18:00 |  | 30 | 2020-02-03 23:31 |  |  | 2019-11-23 17:40 | 2020-02-10 18:00 |  | 35 | 2020-02-10 23:31 |  |  | 2019-11-29 23:59 | 2020-02-17 18:00 |  | 65 | 2020-02-17 23:31 |  |  | 2019-12-05 17:40 | 2020-03-03 18:00 |  | 80 | 2020-03-03 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2019-12-26 17:40 | 2020-03-03 18:00 |  | 100 | [122 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 6 |  |  |  | 101020
1006 | Task(Task)-->E (Engineering) | PIPE CONVEYOR PROFILES FOR PC 1A/B |  | 1.9.1.1 | Completed | No | No | 2019-11-12 18:00 | 2020-01-22 17:40 | 2020-02-21 09:00 | 2020-04-04 18:00 |  |  | 2020-02-21 14:04 | 2020-06-19 14:55 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-CS-DC-0014 |  | 2020-02-13 10:26 | 7012-155-PVM-B-014 |  |  |  | A |  |  |  | 2.8609 | 0.002287 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 80 | 0 | 93 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3334 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-11-12 18:00 | 2020-01-08 18:00 |  | 10 | 2020-01-08 23:31 |  |  | 2019-12-14 17:40 | 2020-02-07 18:00 |  | 30 | 2020-02-07 23:31 |  |  | 2019-12-20 17:40 | 2020-02-14 18:00 |  | 35 | 2020-02-14 23:31 |  |  | 2019-12-26 23:59 | 2020-02-21 18:00 |  | 65 | 2020-02-21 23:31 |  |  | 2020-01-01 17:40 | 2020-03-19 18:00 |  | 80 | 2020-03-19 23:31 | [5 empty] | 80 | 2020-03-30 18:34 | [5 empty] | 80 | 2020-03-30 18:34 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-01-22 17:40 | 2020-04-18 18:00 |  | 100 | 2020-04-23 23:31 | [121 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 14 |  |  |  | 101028
1007 | Task(Task)-->E (Engineering) | POWER AND TENSION CALCULATION FOR PIPE CONVEYORS PC 1A/B |  | 1.9.1.1 | Completed | No | No | 2019-11-12 18:00 | 2020-01-22 17:40 | 2020-04-28 09:00 | 2020-06-10 18:00 |  |  | 2020-02-21 14:04 | 2020-06-29 19:15 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-CS-DC-0016 |  | 2020-02-13 10:26 | 7012-155-PVM-U-016 |  |  |  | I |  |  |  | 1.4304 | 0.001143 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 40 | 0 | 18.2 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3337 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-11-12 18:00 | 2020-03-18 18:00 |  | 10 | 2020-03-18 23:31 |  |  | 2019-12-14 17:40 | 2020-04-17 18:00 |  | 30 | 2020-04-17 23:31 |  |  | 2019-12-20 17:40 | 2020-04-17 18:00 |  | 35 | 2020-04-17 23:31 |  |  | 2019-12-26 23:59 | 2020-04-24 18:00 |  | 65 | 2020-04-28 23:31 |  |  | 2020-01-01 17:40 | 2020-05-15 18:00 |  | 80 | 2020-05-16 23:31 | [5 empty] | 80 | 2020-06-10 15:15 | [5 empty] | 80 | 2020-06-10 15:15 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-01-22 17:40 | 2020-05-15 18:00 |  | 100 | 2020-06-29 19:16 | [121 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 16 |  |  |  | 101030
1008 | Task(Task)-->E (Engineering) | SELECTION OF BELT AND DRIVE COMPONENTS FOR PIPE CONVEYORS (PC 1A/B AND PC 2A/B) |  | 1.9.1.1 | Unscheduled | No | No | 2019-12-14 17:40 | 2020-01-22 17:40 | 2020-04-18 18:00 | 2020-05-22 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-CS-DC-0018 |  | 2020-02-13 10:26 | 7012-155-PVM-H-018 |  |  |  | I |  |  |  | 1.4304 | 0.001143 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 40 | 0 | 29.1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3336 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-12-14 18:00 | 2020-04-18 18:00 |  | 10 | 2020-04-18 23:31 |  |  | 2019-12-14 17:40 | 2020-04-23 18:00 |  | 30 | 2020-04-23 23:31 |  |  | 2019-12-20 17:40 | 2020-04-25 18:00 |  | 35 | 2020-04-25 23:31 |  |  | 2019-12-26 23:59 | 2020-04-28 18:00 |  | 65 | 2020-05-02 23:31 |  |  | 2020-01-01 17:40 | 2020-05-19 18:00 |  | 80 | 2020-05-22 23:31 | [5 empty] | 80 | 2020-08-28 14:53 | [5 empty] | 80 | 2020-08-28 14:53 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-01-22 17:40 | 2020-05-19 18:00 |  | 100 | [122 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 18 |  |  |  | 101032
1009 | Task(Task)-->E (Engineering) | G.A AND MARKING OF PIPE CONV. PC 1A/B WITH ELEVATION AND PLAN DETAILS |  | 1.9.1.1 | Unscheduled | No | No | 2019-12-19 18:00 | 2020-03-04 17:40 | 2020-04-03 18:00 | 2020-06-24 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-0024 |  | 2020-02-13 10:26 | 7012-155-PVM-B-024 |  |  |  | A |  |  |  | 14.0442 | 0.011225 | 1.08 | Plan & Actual | Date |  | 0 | 0 | 0 | 400 | 0 | 82.3 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3335 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-12-19 18:00 | 2020-04-03 18:00 |  | 10 | 2020-04-03 23:31 |  |  | 2020-01-23 17:40 | 2020-05-08 18:00 |  | 30 | 2020-05-11 23:31 |  |  | 2020-01-29 17:40 | 2020-05-13 18:00 |  | 35 | 2020-05-11 23:31 |  |  | 2020-02-04 23:59 | 2020-05-20 18:00 |  | 65 | 2020-05-28 23:31 |  |  | 2020-02-11 17:40 | 2020-06-10 18:00 |  | 80 | 2020-06-23 22:16 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-04 17:40 | 2020-06-24 18:00 |  | 100 | [122 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 24 |  |  |  | 101038
1010 | Task(Task)-->E (Engineering) | G.A OF GEARBOX FOR PIPE BELT CONVEYORS |  | 1.9.1.1 | Unscheduled | No | No | 2020-06-03 18:00 | 2020-08-10 17:40 | 2020-06-13 18:00 | 2020-10-15 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1003 |  | 2020-02-13 10:27 | 7012-155-PVM-B-103 |  |  |  | A |  |  |  | 2.8609 | 0.002287 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 80 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3351 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-06-03 18:00 | 2020-06-13 18:00 |  | 10 |  |  |  | 2020-06-29 17:40 | 2020-07-03 18:00 |  | 30 |  |  |  | 2020-07-04 17:40 | 2020-07-10 18:00 |  | 35 |  |  |  | 2020-07-10 23:59 | 2020-07-20 18:00 |  | 65 | 2020-09-15 15:30 |  |  | 2020-07-17 17:40 | 2020-08-10 18:00 |  | 80 | 2020-10-07 10:33 | [5 empty] | 80 | 2020-10-07 18:01 | [5 empty] | 80 | 2020-10-07 18:01 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-08-10 17:40 | 2020-08-10 18:00 |  | 100 | [122 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 33 |  |  |  | 101047
1011 | Task(Task)-->E (Engineering) | GA & DIMENSION SHEET FOR TROUGHING IDLERS FOR PIPE CONVEYOR IDLER |  | 1.9.1.1 | Unscheduled | No | No | 2020-02-20 18:00 | 2020-04-16 17:40 | 2020-05-30 18:00 | 2020-08-21 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1009 |  | 2020-02-13 10:27 | 7012-155-PVM-B-109 |  |  |  | I |  |  |  | 9.7529 | 0.007795 | 0.75 | Plan & Actual | Date |  | 0 | 0 | 0 | 280 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3338 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-20 18:00 | 2020-05-30 18:00 |  | 10 |  |  |  | 2020-03-05 17:40 | 2020-06-20 18:00 |  | 30 |  |  |  | 2020-03-11 17:40 | 2020-06-26 18:00 |  | 35 |  |  |  | 2020-03-18 23:59 | 2020-06-26 18:00 |  | 65 |  |  |  | 2020-03-24 17:40 | 2020-07-17 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-16 17:40 | 2020-07-17 18:00 |  | 100 | [122 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 39 |  |  |  | 101053
1012 | Task(Task)-->E (Engineering) | GA & DIMENSION SHEET FOR IMPACT IDLER FOR PIPE CONVEYORS |  | 1.9.1.1 | Unscheduled | No | No | 2020-02-20 18:00 | 2020-04-16 17:40 | 2020-05-30 18:00 | 2020-08-21 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1011 |  | 2020-02-13 10:27 | 7012-155-PVM-B-111 |  |  |  | I |  |  |  | 2.8609 | 0.002287 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 80 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3339 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-20 18:00 | 2020-05-30 18:00 |  | 10 |  |  |  | 2020-03-05 17:40 | 2020-06-20 18:00 |  | 30 |  |  |  | 2020-03-11 17:40 | 2020-06-26 18:00 |  | 35 |  |  |  | 2020-03-18 23:59 | 2020-06-26 18:00 |  | 65 |  |  |  | 2020-03-24 17:40 | 2020-07-17 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-16 17:40 | 2020-07-17 18:00 |  | 100 | [122 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 41 |  |  |  | 101055
1013 | Task(Task)-->E (Engineering) | GA & DIMENSION SHEET FOR 2 ROLL FLAT RETURN IDLERS FOR PIPE CONVEYORS |  | 1.9.1.1 | Unscheduled | No | No | 2020-02-20 18:00 | 2020-04-16 17:40 | 2020-05-30 18:00 | 2020-08-21 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 35 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1015 |  | 2020-02-13 10:27 | 7012-155-PVM-B-115 |  |  |  | I |  |  |  | 2.8609 | 0.002287 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 80 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3340 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-20 18:00 | 2020-05-30 18:00 |  | 10 |  |  |  | 2020-03-05 17:40 | 2020-06-20 18:00 |  | 30 |  |  |  | 2020-03-11 17:40 | 2020-06-26 18:00 |  | 35 | 2020-05-31 23:31 |  |  | 2020-03-18 23:59 | 2020-06-26 18:00 |  | 65 |  |  |  | 2020-03-24 17:40 | 2020-07-17 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-16 17:40 | 2020-07-17 18:00 |  | 100 | [122 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 45 |  |  |  | 101059
1014 | Task(Task)-->E (Engineering) | GA & DIMENSION SHEET FOR S.A CARRAYING AND S.A RETURN IDLER FOR PIPE CONVEYORS |  | 1.9.1.1 | Unscheduled | No | No | 2020-02-20 18:00 | 2020-04-16 17:40 | 2020-05-30 18:00 | 2020-08-21 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1017 |  | 2020-02-13 10:27 | 7012-155-PVM-B-117 |  |  |  | I |  |  |  | 2.8609 | 0.002287 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3341 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-20 18:00 | 2020-05-30 18:00 |  | 10 |  |  |  | 2020-03-05 17:40 | 2020-06-20 18:00 |  | 30 |  |  |  | 2020-03-11 17:40 | 2020-06-26 18:00 |  | 35 |  |  |  | 2020-03-18 23:59 | 2020-06-26 18:00 |  | 65 |  |  |  | 2020-03-24 17:40 | 2020-07-17 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-16 17:40 | 2020-07-17 18:00 |  | 100 | [122 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 47 |  |  |  | 101061
1015 | Task(Task)-->E (Engineering) | GA & DIMENSION SHEET FOR TROUGHING TRANSITION IDLER FOR PIPE CONVEYORS |  | 1.9.1.1 | Unscheduled | No | No | 2020-02-20 18:00 | 2020-04-16 17:40 | 2020-05-30 18:00 | 2020-08-21 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1019 |  | 2020-02-13 10:27 | 7012-155-PVM-B-119 |  |  |  | I |  |  |  | 2.8609 | 0.002287 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3342 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-20 18:00 | 2020-05-30 18:00 |  | 10 |  |  |  | 2020-03-05 17:40 | 2020-06-20 18:00 |  | 30 |  |  |  | 2020-03-11 17:40 | 2020-06-26 18:00 |  | 35 |  |  |  | 2020-03-18 23:59 | 2020-06-26 18:00 |  | 65 |  |  |  | 2020-03-24 17:40 | 2020-07-17 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-16 17:40 | 2020-07-17 18:00 |  | 100 | [122 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 49 |  |  |  | 101063
1016 | Task(Task)-->E (Engineering) | GA & DIMENSION SHEET FOR PSK IDLERS FOR PIPE CONVEYOR |  | 1.9.1.1 | Unscheduled | No | No | 2020-02-20 18:00 | 2020-04-16 17:40 | 2020-06-15 18:00 | 2020-08-02 23:59 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1020A |  | 2020-02-13 10:27 | 7012-155-PVM-B-120 |  |  |  | I |  |  |  | 2.8609 | 0.002287 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 80 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3343 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-20 18:00 | 2020-06-15 18:00 |  | 10 |  |  |  | 2020-03-05 17:40 | 2020-07-06 18:00 |  | 30 |  |  |  | 2020-03-11 17:40 | 2020-07-12 23:59 |  | 35 |  |  |  | 2020-03-18 23:59 | 2020-07-12 23:59 |  | 65 |  |  |  | 2020-03-24 17:40 | 2020-08-02 23:59 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-16 17:40 | 2020-08-02 23:59 |  | 100 | [122 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 50 |  |  |  | 101064
1017 | Task(Task)-->E (Engineering) | BELT DATA SHEET WITH SCHEDULE FOR PIPE CONVEYORS |  | 1.9.1.1 | Unscheduled | No | No | 2020-04-13 18:00 | 2020-06-23 17:40 | 2020-06-15 18:00 | 2020-10-23 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-DC-1025 |  | 2020-02-13 10:27 | 7012-155-PVM-Y-125 |  |  |  | I |  |  |  | 1.4304 | 0.001143 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 40 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3350 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-13 18:00 | 2020-06-15 18:00 |  | 10 |  |  |  | 2020-05-13 17:40 | 2020-07-06 18:00 |  | 30 |  |  |  | 2020-05-19 17:40 | 2020-07-13 18:00 |  | 35 |  |  |  | 2020-05-26 23:59 | 2020-07-28 18:00 |  | 65 | 2020-09-22 11:28 |  |  | 2020-06-01 17:40 | 2020-08-18 18:00 |  | 80 | 2020-10-14 15:23 | [5 empty] | 80 | 2020-10-16 19:16 | [5 empty] | 80 | 2020-10-16 19:16 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-23 17:40 | 2020-08-18 18:00 |  | 100 | [122 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 55 |  |  |  | 101069
1018 | Task(Task)-->E (Engineering) | SCHEDULE OF DRIVE AND NON DRIVE PULLEY FOR PIPE CONVEYORS |  | 1.9.1.1 | Unscheduled | No | No | 2020-03-11 18:00 | 2020-05-07 17:40 | 2020-06-15 18:00 | 2020-08-03 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1027 |  | 2020-02-13 10:27 | 7012-155-PVM-H-127 |  |  |  | A |  |  |  | 5.5917 | 0.004469 | 0.43 | Plan & Actual | Date |  | 0 | 0 | 0 | 160 | 0 | 51 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3349 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-11 18:00 | 2020-06-15 18:00 |  | 10 |  |  |  | 2020-03-26 17:40 | 2020-07-06 18:00 |  | 30 |  |  |  | 2020-04-02 17:40 | 2020-07-13 18:00 |  | 35 |  |  |  | 2020-04-08 23:59 | 2020-07-13 18:00 |  | 65 | 2020-07-14 12:43 |  |  | 2020-04-15 17:40 | 2020-08-03 18:00 |  | 80 | 2020-08-19 18:20 | [5 empty] | 80 | 2020-08-19 18:33 | [5 empty] | 80 | 2020-08-19 18:33 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-07 17:40 | 2020-08-03 18:00 |  | 100 | [122 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 57 |  |  |  | 101071
1019 | Task(Task)-->E (Engineering) | G.A OF BRAKES FOR PIPE CONVEYORS |  | 1.9.1.1 | Unscheduled | No | No | 2020-04-21 18:00 | 2020-06-18 17:40 | 2020-06-30 18:00 | 2020-09-29 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1029 |  | 2020-02-13 10:27 | 7012-155-PVM-B-129 |  |  |  | I |  |  |  | 5.5917 | 0.004469 | 0.43 | Plan & Actual | Date |  | 0 | 0 | 0 | 160 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3344 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-21 18:00 | 2020-06-30 18:00 |  | 10 |  |  |  | 2020-05-07 17:40 | 2020-07-21 18:00 |  | 30 |  |  |  | 2020-05-14 17:40 | 2020-07-24 18:00 |  | 35 |  |  |  | 2020-05-20 23:59 | 2020-07-29 18:00 |  | 65 | 2020-09-09 10:01 |  |  | 2020-05-27 17:40 | 2020-08-19 18:00 |  | 80 | 2020-10-03 16:27 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-18 17:40 | 2020-08-19 18:00 |  | 100 | [122 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 59 |  |  |  | 101073
1020 | Task(Task)-->E (Engineering) | G.A OF MAINTENANCE TROLLEY |  | 1.9.1.1 | Unscheduled | No | No | 2019-12-28 18:00 | 2020-02-19 17:40 | 2020-05-20 18:00 | 2020-08-12 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1038 |  | 2020-02-13 10:27 | 7012-155-PVM-B-138 |  |  |  | I |  |  |  | 2.8609 | 0.002287 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 80 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3353 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-12-28 18:00 | 2020-05-20 18:00 |  | 10 |  |  |  | 2020-01-10 17:40 | 2020-06-04 18:00 |  | 30 |  |  |  | 2020-01-16 17:40 | 2020-06-07 23:59 |  | 35 |  |  |  | 2020-01-22 23:59 | 2020-06-14 23:59 |  | 65 | 2020-08-28 17:34 |  |  | 2020-01-28 17:40 | 2020-07-05 23:59 |  | 80 | 2020-08-28 17:42 | [5 empty] | 80 | 2020-08-28 17:45 | [5 empty] | 80 | 2020-08-28 17:45 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-02-19 17:40 | 2020-07-05 23:59 |  | 100 | [122 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 68 |  |  |  | 101082
1021 | Task(Task)-->E (Engineering) | G.A OF GEAR COUPLING FOR PIPE CONVEYORS |  | 1.9.1.1 | Unscheduled | No | No | 2020-04-20 18:00 | 2020-06-06 17:40 | 2020-06-15 18:00 | 2020-09-01 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1044 |  | 2020-02-13 10:27 | 7012-155-PVM-B-144 |  |  |  | I |  |  |  | 1.4304 | 0.001143 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 40 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3347 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-20 18:00 | 2020-06-15 18:00 |  | 10 |  |  |  | 2020-04-27 17:40 | 2020-06-30 18:00 |  | 30 |  |  |  | 2020-05-02 17:40 | 2020-07-03 18:00 |  | 35 |  |  |  | 2020-05-08 23:59 | 2020-07-03 18:00 |  | 65 | 2020-08-14 23:27 |  |  | 2020-05-15 17:40 | 2020-07-24 18:00 |  | 80 | 2020-09-02 16:10 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-06 17:40 | 2020-07-24 18:00 |  | 100 | [122 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 74 |  |  |  | 101088
1022 | Task(Task)-->E (Engineering) | GA & DIMENSION SHEET FOR SPECIAL IDLERS FOR PIPE CONVEYOR |  | 1.9.1.1 | Unscheduled | No | No | 2020-02-23 23:59 | 2020-04-16 17:40 | 2020-04-07 18:00 | 2020-08-21 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 35 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1045 |  | 2020-02-13 10:27 | 7012-155-PVM-B-145 |  |  |  | I |  |  |  | 30.8192 | 0.024632 | 2.37 | Plan & Actual | Date |  | 0 | 0 | 0 | 880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3348 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-23 23:59 | 2020-04-07 18:00 |  | 10 | 2020-04-07 23:31 |  |  | 2020-03-05 17:40 | 2020-04-28 18:00 |  | 30 | 2020-04-28 23:31 |  |  | 2020-03-11 17:40 | 2020-04-28 18:00 |  | 35 | 2020-04-28 23:31 |  |  | 2020-03-18 23:59 | 2020-04-28 18:00 |  | 65 |  |  |  | 2020-03-24 17:40 | 2020-05-19 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-16 17:40 | 2020-05-19 18:00 |  | 100 | [122 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 75 |  |  |  | 101089
1023 | Task(Task)-->E (Engineering) | CIVIL | 1.9.1.2 | 1.9.1 | Completed | No | No | 2020-04-03 18:00 | 2020-07-07 17:40 | 2020-05-31 | 2020-10-15 18:00 |  |  | 2020-02-21 15:37 | 2020-10-03 12:27 |  |  | 100 | 100 | [15 empty] | 14.1155 | 0.055418 | 5.45 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3356 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036095
1024 | Task(Task)-->E (Engineering) | PIPE CONVEYOR FOR PC 1A/B : NUM & RC DETAILS OF FDN (SHT 1) |  | 1.9.1.2 | Completed | No | No | 2020-05-27 17:40 | 2020-07-07 17:40 | 2020-05-31 | 2020-06-04 18:00 |  |  | 2020-05-27 17:40 | 2020-06-04 14:46 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-NR-0017 |  | 2020-02-13 11:42 | 7012-155-PVC-C-047 |  |  |  | A |  |  |  | 17.4552 | 0.009673 | 2.73 | Plan & Actual | Date |  | 0 | 0 | 0 | 1012.26 | 0 | 54 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3357 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-05-08 18:00 | 2020-04-21 18:00 |  | 10 | 2020-04-21 23:31 |  |  | 2020-05-27 17:40 | 2020-05-26 18:00 |  | 30 | 2020-05-24 23:31 |  |  | 2020-06-02 17:40 | 2020-05-29 18:00 |  | 35 | 2020-05-26 23:31 |  |  | 2020-06-08 23:59 | 2020-06-05 18:00 |  | 65 | 2020-05-31 23:31 |  |  | 2020-06-15 17:40 | 2020-06-26 18:00 |  | 80 | 2020-06-04 14:41 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-07-07 17:40 | 2020-07-10 18:00 |  | 100 | 2020-06-04 14:47 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 148 |  |  |  | 101162
1025 | Task(Task)-->E (Engineering) | PIPE CONVEYOR FOR PC 1A/B : NUM & RC DETAILS OF FDN (SHT 2) |  | 1.9.1.2 | Completed | No | No | 2020-05-08 18:00 | 2020-07-07 17:40 | 2020-07-24 09:00 | 2020-08-04 18:00 |  |  | 2020-02-21 15:37 | 2020-08-04 20:40 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-NR-0018 |  | 2020-02-13 11:42 | 7012-155-PVC-C-048 |  |  |  | A |  |  |  | 17.4552 | 0.009673 | 2.73 | Plan & Actual | Date |  | 0 | 0 | 0 | 1012.26 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3358 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-05-08 18:00 | 2020-06-19 18:00 |  | 10 |  |  |  | 2020-05-27 17:40 | 2020-07-24 18:00 |  | 30 |  |  |  | 2020-06-02 17:40 | 2020-07-27 18:00 |  | 35 |  |  |  | 2020-06-08 23:59 | 2020-08-03 18:00 |  | 65 | 2020-08-04 20:26 |  |  | 2020-06-15 17:40 | 2020-08-24 18:00 |  | 80 | 2020-08-04 20:37 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-07-07 17:40 | 2020-09-07 18:00 |  | 100 | 2020-08-04 20:40 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 149 |  |  |  | 101163
1026 | Task(Task)-->E (Engineering) | PIPE CONVEYOR FOR PC 1A/B : DESIGN CALCULATION OF SUPER STRUCTURE |  | 1.9.1.2 | Completed | No | No | 2020-04-03 18:00 | 2020-06-02 17:40 | 2020-09-03 09:00 | 2020-10-15 18:00 |  |  | 2020-02-21 15:37 | 2020-10-03 12:27 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0014A |  | 2020-02-13 11:41 | 7012-155-PVC-U-040 |  |  |  | A |  |  |  | 30.243 | 0.01676 | 4.73 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3359 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-03 18:00 | 2020-05-20 18:00 |  | 10 |  |  |  | 2020-04-21 17:40 | 2020-06-24 18:00 |  | 30 |  |  |  | 2020-04-28 17:40 | 2020-06-27 18:00 |  | 35 |  |  |  | 2020-05-04 23:59 | 2020-07-04 18:00 |  | 65 | 2020-09-06 17:32 |  |  | 2020-05-11 17:40 | 2020-07-25 18:00 |  | 80 | 2020-10-03 12:25 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-02 17:40 | 2020-08-08 18:00 |  | 100 | 2020-10-03 12:27 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 141 |  |  |  | 101155
1027 | Task(Task)-->E (Engineering) | PIPE CONVEYOR FOR PC 1A/B : DESIGN CALCULATION OF SUB STRUCTURE |  | 1.9.1.2 | Completed | No | No | 2020-05-27 17:40 | 2020-07-07 17:40 | 2020-05-31 | 2020-06-04 18:00 |  |  | 2020-05-27 17:40 | 2020-06-04 14:47 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0015A |  | 2020-02-13 11:41 | 7012-155-PVC-U-041 |  |  |  | A |  |  |  | 34.8465 | 0.019311 | 5.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 63 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3360 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-05-08 18:00 | 2020-04-21 18:00 |  | 10 | 2020-05-15 23:31 |  |  | 2020-05-27 17:40 | 2020-05-26 18:00 |  | 30 | 2020-05-24 23:31 |  |  | 2020-06-02 17:40 | 2020-05-29 18:00 |  | 35 | 2020-05-26 23:31 |  |  | 2020-06-08 23:59 | 2020-06-05 18:00 |  | 65 | 2020-05-31 23:31 |  |  | 2020-06-15 17:40 | 2020-06-26 18:00 |  | 80 | 2020-06-04 14:42 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-07-07 17:40 | 2020-07-10 18:00 |  | 100 | 2020-06-04 14:48 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 142 |  |  |  | 101156
1028 | Task(Task)-->E (Engineering) | STRUCTURAL | 1.9.1.3 | 1.9.1 | Work In Progress | No | No | 2020-02-11 17:40 | 2020-08-21 17:40 | 2020-04-13 09:00 | 2020-10-15 18:00 |  |  | 2020-02-11 17:40 |  |  |  | 100 | 85.8078 | [15 empty] | 60.0363 | 0.23571 | 23.18 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3361 | 3 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036096
1029 | Task(Task)-->E (Engineering) | GA. OF STANDARD GALLERY FOR PIPE CONV. |  | 1.9.1.3 | Completed | No | No | 2020-02-11 17:40 | 2020-03-21 17:40 | 2020-04-13 09:00 | 2020-07-28 18:00 |  |  | 2020-07-28 09:11 | 2020-07-28 09:11 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-GA-0002 |  | 2020-02-13 11:41 | 7012-155-PVC-B-005 |  |  |  | A |  |  |  | 31.6379 | 0.074573 | 7.34 | Plan & Actual | Date |  | 0 | 0 | 0 | 2724 | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3365 | 1 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-22 18:00 | 2020-03-15 23:59 |  | 10 | 2020-02-18 23:31 |  |  | 2020-02-11 17:40 | 2020-04-05 23:59 |  | 30 | 2020-04-03 23:31 |  |  | 2020-02-17 17:40 | 2020-04-08 18:00 |  | 35 | 2020-04-06 23:31 |  |  | 2020-02-22 23:59 | 2020-04-15 18:00 |  | 65 | 2020-04-13 23:31 |  |  | 2020-02-28 17:40 | 2020-05-04 18:00 |  | 80 | 2020-05-11 23:31 | [5 empty] | 80 | 2020-07-28 09:12 | [5 empty] | 80 | 2020-07-28 09:12 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-21 17:40 | 2020-05-18 18:00 |  | 100 | 2020-05-11 23:31 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 106 |  |  |  | 101120
1030 | Task(Task)-->E (Engineering) | GA. OF STANDARD TRESTLES SUPPORTING PIPE CONV.GALLERIES |  | 1.9.1.3 | Completed | No | No | 2020-03-07 17:40 | 2020-04-18 17:40 | 2020-04-13 09:00 | 2020-07-28 18:00 |  |  | 2020-03-07 17:40 | 2020-05-16 16:34 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-GA-0003 |  | 2020-02-13 11:41 | 7012-155-PVC-B-006 |  |  |  | A |  |  |  | 7.8879 | 0.018592 | 1.83 | Plan & Actual | Date |  | 0 | 0 | 0 | 681 | 0 | 113 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3366 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-18 18:00 | 2020-03-15 23:59 |  | 10 | 2020-02-23 23:31 |  |  | 2020-03-07 17:40 | 2020-04-05 23:59 |  | 30 | 2020-04-03 23:31 |  |  | 2020-03-13 17:40 | 2020-04-08 18:00 |  | 35 | 2020-04-06 23:31 |  |  | 2020-03-20 23:59 | 2020-04-15 18:00 |  | 65 | 2020-04-13 23:31 |  |  | 2020-03-26 17:40 | 2020-05-04 18:00 |  | 80 | 2020-05-11 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-18 17:40 | 2020-05-18 18:00 |  | 100 | 2020-05-11 23:31 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 107 |  |  |  | 101121
1031 | Task(Task)-->E (Engineering) | DESIGN CALCULATION FOR STANDARD PIPE CONV.GALLERIES |  | 1.9.1.3 | Completed | No | No | 2020-02-11 17:40 | 2020-03-21 17:40 | 2020-04-13 09:00 | 2020-07-21 18:00 |  |  | 2020-02-11 17:40 | 2020-05-16 17:27 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0001 |  | 2020-02-13 11:41 | 7012-155-PVC-U-007 |  |  |  | A |  |  |  | 31.6379 | 0.074573 | 7.34 | Plan & Actual | Date |  | 0 | 0 | 0 | 2724 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3362 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-22 18:00 | 2020-03-15 23:59 |  | 10 | 2020-02-18 23:31 |  |  | 2020-02-11 17:40 | 2020-04-05 23:59 |  | 30 | 2020-04-03 23:31 |  |  | 2020-02-17 17:40 | 2020-04-08 18:00 |  | 35 | 2020-04-06 23:31 |  |  | 2020-02-22 23:59 | 2020-04-15 18:00 |  | 65 | 2020-04-13 23:31 |  |  | 2020-02-28 17:40 | 2020-05-04 18:00 |  | 80 | 2020-05-11 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-21 17:40 | 2020-05-18 18:00 |  | 100 | 2020-05-11 23:31 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 108 |  |  |  | 101122
1032 | Task(Task)-->E (Engineering) | DESIGN CALCULATION FOR STANDARD PIPE CONV.GALLERIES SUPPORTING TRESTLES |  | 1.9.1.3 | Completed | No | No | 2020-02-18 18:00 | 2020-04-18 17:40 | 2020-04-13 09:00 | 2020-07-28 18:00 |  |  | 2020-02-21 15:30 | 2020-07-28 09:59 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0002 |  | 2020-02-13 11:41 | 7012-155-PVC-U-008 |  |  |  | A |  |  |  | 7.8879 | 0.018592 | 1.83 | Plan & Actual | Date |  | 0 | 0 | 0 | 681 | 0 | 59 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3363 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-18 18:00 | 2020-03-15 23:59 |  | 10 | 2020-02-23 23:31 |  |  | 2020-03-07 17:40 | 2020-04-05 23:59 |  | 30 | 2020-04-03 23:31 |  |  | 2020-03-13 17:40 | 2020-04-08 18:00 |  | 35 | 2020-04-06 23:31 |  |  | 2020-03-20 23:59 | 2020-04-15 18:00 |  | 65 | 2020-04-13 23:31 |  |  | 2020-03-26 17:40 | 2020-05-04 18:00 |  | 80 | 2020-05-25 23:31 | [5 empty] | 80 | 2020-07-28 09:20 | [5 empty] | 80 | 2020-07-28 09:20 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-18 17:40 | 2020-05-18 18:00 |  | 100 | 2020-07-28 10:00 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 109 |  |  |  | 101123
1033 | Task(Task)-->E (Engineering) | PIPE CONVEYOR FOR PC 1A/B : STRUCTURAL GA (SHT 1) |  | 1.9.1.3 | Unscheduled | No | No | 2020-04-03 18:00 | 2020-06-02 17:40 | 2020-05-20 18:00 | 2020-10-04 23:59 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-GA-0009 |  | 2020-02-13 11:42 | 7012-155-PVC-B-042 |  |  |  | A |  |  |  | 4.0948 | 0.009652 | 0.95 | Plan & Actual | Date |  | 0 | 0 | 0 | 351.15 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3367 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-03 18:00 | 2020-05-20 18:00 |  | 10 |  |  |  | 2020-04-21 17:40 | 2020-06-24 18:00 |  | 30 |  |  |  | 2020-04-28 17:40 | 2020-06-27 18:00 |  | 35 |  |  |  | 2020-05-04 23:59 | 2020-07-04 18:00 |  | 65 | 2020-09-25 22:40 |  |  | 2020-05-11 17:40 | 2020-07-25 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-02 17:40 | 2020-08-08 18:00 |  | 100 | [122 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 143 |  |  |  | 101157
1034 | Task(Task)-->E (Engineering) | PIPE CONVEYOR FOR PC 1A/B : STRUCTURAL GA (SHT 2) |  | 1.9.1.3 | Unscheduled | No | No | 2020-04-03 18:00 | 2020-06-02 17:40 | 2020-05-20 18:00 | 2020-08-21 18:00 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-GA-0010 |  | 2020-02-13 11:42 | 7012-155-PVC-B-043 |  |  |  | A |  |  |  | 4.0948 | 0.009652 | 0.95 | Plan & Actual | Date |  | 0 | 0 | 0 | 351.15 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3368 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-03 18:00 | 2020-05-20 18:00 |  | 10 |  |  |  | 2020-04-21 17:40 | 2020-06-24 18:00 |  | 30 |  |  |  | 2020-04-28 17:40 | 2020-06-27 18:00 |  | 35 |  |  |  | 2020-05-04 23:59 | 2020-07-04 18:00 |  | 65 |  |  |  | 2020-05-11 17:40 | 2020-07-25 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-02 17:40 | 2020-08-08 18:00 |  | 100 | [122 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 144 |  |  |  | 101158
1035 | Task(Task)-->E (Engineering) | PIPE CONVEYOR FOR PC 1A/B : STRUCTURAL GA (SHT 3) |  | 1.9.1.3 | Unscheduled | No | No | 2020-04-03 18:00 | 2020-06-02 17:40 | 2020-05-20 18:00 | 2020-08-21 18:00 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-GA-0011 |  | 2020-02-13 11:42 | 7012-155-PVC-B-044 |  |  |  | A |  |  |  | 4.0948 | 0.009652 | 0.95 | Plan & Actual | Date |  | 0 | 0 | 0 | 351.15 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3369 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-03 18:00 | 2020-05-20 18:00 |  | 10 |  |  |  | 2020-04-21 17:40 | 2020-06-24 18:00 |  | 30 |  |  |  | 2020-04-28 17:40 | 2020-06-27 18:00 |  | 35 |  |  |  | 2020-05-04 23:59 | 2020-07-04 18:00 |  | 65 |  |  |  | 2020-05-11 17:40 | 2020-07-25 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-02 17:40 | 2020-08-08 18:00 |  | 100 | [122 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 145 |  |  |  | 101159
1036 | Task(Task)-->E (Engineering) | PIPE CONVEYOR FOR PC 1A/B : STRUCTURAL GA (SHT 4) |  | 1.9.1.3 | Unscheduled | No | No | 2020-04-03 18:00 | 2020-06-02 17:40 | 2020-05-20 18:00 | 2020-08-21 18:00 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-GA-0012 |  | 2020-02-13 11:42 | 7012-155-PVC-B-045 |  |  |  | A |  |  |  | 4.0948 | 0.009652 | 0.95 | Plan & Actual | Date |  | 0 | 0 | 0 | 351.15 | 0 | 98 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3370 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-03 18:00 | 2020-05-20 18:00 |  | 10 |  |  |  | 2020-04-21 17:40 | 2020-06-24 18:00 |  | 30 |  |  |  | 2020-04-28 17:40 | 2020-06-27 18:00 |  | 35 |  |  |  | 2020-05-04 23:59 | 2020-07-04 18:00 |  | 65 |  |  |  | 2020-05-11 17:40 | 2020-07-25 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-02 17:40 | 2020-08-08 18:00 |  | 100 | [122 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 146 |  |  |  | 101160
1037 | Task(Task)-->E (Engineering) | PIPE CONVEYOR FOR PC 1A/B : STRUCTURAL GA (SHT 5) |  | 1.9.1.3 | Completed | No | No | 2020-04-03 18:00 | 2020-06-02 17:40 | 2020-05-20 18:00 | 2020-10-15 18:00 |  |  | 2020-02-21 15:37 | 2020-10-14 20:53 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-GA-0013 |  | 2020-02-13 11:42 | 7012-155-PVC-B-046 |  |  |  | A |  |  |  | 4.0948 | 0.009652 | 0.95 | Plan & Actual | Date |  | 0 | 0 | 0 | 351.15 | 0 | 94.1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3371 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-03 18:00 | 2020-05-20 18:00 |  | 10 |  |  |  | 2020-04-21 17:40 | 2020-06-24 18:00 |  | 30 |  |  |  | 2020-04-28 17:40 | 2020-06-27 18:00 |  | 35 | 2020-07-29 11:37 |  |  | 2020-05-04 23:59 | 2020-07-04 18:00 |  | 65 | 2020-09-06 17:32 |  |  | 2020-05-11 17:40 | 2020-07-25 18:00 |  | 80 | 2020-10-14 20:43 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-02 17:40 | 2020-08-08 18:00 |  | 100 | 2020-10-14 20:53 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 147 |  |  |  | 101161
1038 | Task(Task)-->E (Engineering) | ARCHITECTURAL GA OF PIPE CONVEYOR FOR PC 1A/B |  | 1.9.1.3 | Unscheduled | No | No | 2020-06-22 18:00 | 2020-08-21 17:40 | 2020-07-19 23:59 | 2020-09-27 23:59 |  |  | 2020-02-21 15:39 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-AR-0006 |  | 2020-02-13 11:43 | 7012-155-PVC-C-112 |  |  |  | I |  |  |  | 0.47414 | 0.001118 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 40.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3364 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-06-22 18:00 | 2020-07-19 23:59 |  | 10 |  |  |  | 2020-07-10 17:40 | 2020-08-13 18:00 |  | 30 |  |  |  | 2020-07-17 17:40 | 2020-08-16 23:59 |  | 35 |  |  |  | 2020-07-23 23:59 | 2020-08-23 23:59 |  | 65 |  |  |  | 2020-07-30 17:40 | 2020-09-13 23:59 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-08-21 17:40 | 2020-09-27 23:59 |  | 100 | [122 empty] | Chetan Khodke |  |  |  |  | A - Architecture | [16 empty] | 213 |  |  |  | 101223
1039 | Task(Task)-->E (Engineering) | ELECTRICAL | 1.9.1.4 | 1.9.1 | Unscheduled | No | No | 2020-03-27 17:40 | 2020-06-10 17:40 | 2020-04-24 18:00 | 2020-09-23 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 59.1446 | [15 empty] | 5.4908 | 0.021557 | 2.12 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3374 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036097
1040 | Task(Task)-->E (Engineering) | GAD, WIRING DIAGRAM, DATA SHEET & BOM OF 6.6kV MV VFD FOR CHP PIPE CONVEYORS |  | 1.9.1.4 | Unscheduled | No | No | 2020-04-16 18:00 | 2020-05-29 17:40 | 2020-06-05 18:00 | 2020-08-17 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-153 |  | 2020-02-13 11:46 | 7012-155-PVE-W-098 |  |  |  | A |  |  |  | 10.4265 | 0.002248 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 82.54 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3377 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-16 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-04-17 17:40 | 2020-06-12 18:00 |  | 30 |  |  |  | 2020-04-23 17:40 | 2020-06-19 18:00 |  | 35 |  |  |  | 2020-04-30 23:59 | 2020-06-19 18:00 |  | 65 |  |  |  | 2020-05-06 17:40 | 2020-07-10 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-29 17:40 | 2020-07-10 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 333 |  |  |  | 101344
1041 | Task(Task)-->E (Engineering) | GA, DATA SHEET, TERMINAL BOX ARRANGEMET & CHARACTERISTICS CURVES OF HT MOTOR FOR PIPE CONVEYING SYSTEM |  | 1.9.1.4 | Unscheduled | No | No | 2020-03-27 17:40 | 2020-05-08 17:40 | 2020-06-05 18:00 | 2020-09-11 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-160 |  | 2020-02-13 11:46 | 7012-155-PVE-W-105 |  |  |  | A |  |  |  | 10.4265 | 0.002248 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 82.54 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3378 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-27 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-03-27 17:40 | 2020-06-12 18:00 |  | 30 |  |  |  | 2020-04-03 17:40 | 2020-06-18 18:00 |  | 35 |  |  |  | 2020-04-09 23:59 | 2020-06-18 18:00 |  | 65 |  |  |  | 2020-04-16 17:40 | 2020-07-09 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-08 17:40 | 2020-07-09 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 340 |  |  |  | 101351
1042 | Task(Task)-->E (Engineering) | GA & FOUNDATION DRAWING , DATA SHEET,SLD , SCHEME DRAWING AND BOM OF 6.6kV APFC SYSTEM FOR CHP. |  | 1.9.1.4 | Unscheduled | No | No | 2020-04-09 18:00 | 2020-05-25 17:40 | 2020-06-21 23:59 | 2020-09-23 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-186 |  | 2020-02-13 11:47 | 7012-155-PVE-W-131 |  |  |  | A |  |  |  | 5.2133 | 0.001124 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3375 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-09 18:00 | 2020-06-21 23:59 |  | 10 |  |  |  | 2020-04-13 17:40 | 2020-06-28 23:59 |  | 30 |  |  |  | 2020-04-18 17:40 | 2020-07-06 18:00 |  | 35 |  |  |  | 2020-04-24 23:59 | 2020-07-06 18:00 |  | 65 |  |  |  | 2020-05-01 17:40 | 2020-07-27 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-25 17:40 | 2020-07-27 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 366 |  |  |  | 101377
1043 | Task(Task)-->E (Engineering) | LIGHTING LAYOUT PLAN WITH POWER DISTRIBUTION ARRANGEMENT, SECTIONAL VIEW, BOM OF PIPE CONVEYOR 1A/B |  | 1.9.1.4 | Unscheduled | No | No | 2020-04-22 18:00 | 2020-06-10 17:40 | 2020-04-24 18:00 | 2020-06-24 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5077 |  | 2020-02-13 11:45 | 7012-155-PVE-G-039 |  |  |  | A |  |  |  | 73.9336 | 0.015938 | 1.56 | Plan & Actual | Date |  | 0 | 0 | 0 | 580.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3376 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-22 18:00 | 2020-04-24 18:00 |  | 10 | 2020-05-30 23:31 |  |  | 2020-04-30 17:40 | 2020-05-01 18:00 |  | 30 |  |  |  | 2020-05-06 17:40 | 2020-05-08 18:00 |  | 35 |  |  |  | 2020-05-13 23:59 | 2020-05-15 18:00 |  | 65 | 2020-08-03 11:52 |  |  | 2020-05-19 17:40 | 2020-06-05 18:00 |  | 80 | 2020-08-03 12:05 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-10 17:40 | 2020-06-05 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 274 |  |  |  | 101285
1044 | Task(Task)-->P (Procurement) | PROCUREMENT | 1.9.2 | 1.9 | Work In Progress | No | No | 2019-11-07 09:00 | 2021-03-31 18:00 | 2019-11-08 09:00 | 2022-01-22 18:00 |  |  | 2019-11-08 17:06 |  |  |  | 65.5718 | 30.3191 | [15 empty] | 74.5141 | 17.1634 | 1687.9 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3379 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018594
1045 | Task(Task)-->P (Procurement) | PURCHASE REQUISITION | 1.9.2.1 | 1.9.2 | Work In Progress | No | No | 2019-11-07 09:00 | 2020-05-19 18:00 | 2019-11-08 09:00 | 2020-07-19 23:59 |  |  | 2019-11-08 17:06 |  |  |  | 100 | 99.4668 | [15 empty] | 5.0002 | 0.85821 | 84.4 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3380 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018595
1046 | Task(Task)-->P (Procurement) | Pulley |  | 1.9.2.1 | Completed | No | No | 2020-03-03 09:00 | 2020-03-03 18:00 | 2020-04-26 | 2020-04-26 23:59 |  |  | 2020-04-26 10:57 | 2020-04-26 10:57 |  |  | 100 | 100 | [15 empty] | 4.3133 | 0.037017 | 3.64 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3381 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018596
1047 | Task(Task)-->P (Procurement) | Idler |  | 1.9.2.1 | Completed | No | No | 2019-11-19 09:00 | 2019-11-19 18:00 | 2020-03-21 09:00 | 2020-03-21 18:00 |  |  | 2020-03-21 10:57 | 2020-03-21 10:57 |  |  | 100 | 100 | [15 empty] | 16.2579 | 0.13953 | 13.72 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3382 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018597
1048 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.9.2.1 | Completed | No | No | 2020-05-17 | 2020-05-17 23:59 | 2020-04-26 | 2020-04-26 23:59 |  |  | 2020-04-26 10:57 | 2020-04-26 10:57 |  |  | 100 | 100 | [15 empty] | 0.34364 | 0.002949 | 0.29 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3383 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018598
1049 | Task(Task)-->P (Procurement) | Bearing |  | 1.9.2.1 | Completed | No | No | 2020-05-17 | 2020-05-17 23:59 | 2020-04-26 | 2020-04-26 23:59 |  |  | 2020-04-26 10:57 | 2020-04-26 10:57 |  |  | 100 | 100 | [15 empty] | 0.78208 | 0.006712 | 0.66 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3384 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018599
1050 | Task(Task)-->P (Procurement) | Belting |  | 1.9.2.1 | Completed | No | No | 2019-11-07 09:00 | 2019-11-07 18:00 | 2020-02-21 09:00 | 2020-02-21 18:00 |  |  | 2020-02-21 16:00 | 2020-02-21 16:00 |  |  | 100 | 100 | [15 empty] | 28.9489 | 0.24844 | 24.43 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3385 | 1 | 4 | High | [7 empty] | 0 | 0 | [244 empty] | 1018600
1051 | Task(Task)-->P (Procurement) | Scrapper |  | 1.9.2.1 | Completed | No | No | 2019-11-17 | 2019-11-17 23:59 | 2020-03-11 09:00 | 2020-03-11 18:00 |  |  | 2020-03-11 10:57 | 2020-03-11 10:57 |  |  | 100 | 100 | [15 empty] | 0.023699 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3386 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018601
1052 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.9.2.1 | Completed | No | No | 2020-03-10 09:00 | 2020-03-10 18:00 | 2020-03-11 09:00 | 2020-03-11 18:00 |  |  | 2020-03-11 12:41 | 2020-03-11 12:41 |  |  | 100 | 100 | [15 empty] | 1.5049 | 0.012915 | 1.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3387 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018602
1053 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.9.2.1 | Unscheduled | No | No | 2020-05-19 09:00 | 2020-05-19 18:00 | 2020-06-08 09:00 | 2020-06-08 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.53324 | 0.004576 | 0.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3388 | 1 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018603
1054 | Task(Task)-->P (Procurement) | Gear Box |  | 1.9.2.1 | Completed | No | No | 2019-11-13 09:00 | 2019-11-13 18:00 | 2020-02-21 09:00 | 2020-02-21 18:00 |  |  | 2020-02-21 10:57 | 2020-02-21 10:57 |  |  | 100 | 100 | [15 empty] | 2.7017 | 0.023187 | 2.28 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3389 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018604
1055 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.9.2.1 | Completed | No | No | 2019-11-21 09:00 | 2019-11-21 18:00 | 2020-04-27 09:00 | 2020-04-27 18:00 |  |  | 2020-04-27 10:41 | 2020-04-27 10:41 |  |  | 100 | 100 | [15 empty] | 0.58064 | 0.004983 | 0.49 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3390 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018605
1056 | Task(Task)-->P (Procurement) | Brake |  | 1.9.2.1 | Completed | No | No | 2019-12-18 09:00 | 2019-12-18 18:00 | 2020-05-01 09:00 | 2020-05-01 18:00 |  |  | 2020-04-23 11:33 | 2020-04-23 11:33 |  |  | 100 | 100 | [15 empty] | 0.17775 | 0.001525 | 0.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3391 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018606
1057 | Task(Task)-->P (Procurement) | Maintenance Trolley |  | 1.9.2.1 | Completed | No | No | 2019-11-30 09:00 | 2019-11-30 18:00 | 2020-07-19 | 2020-07-19 23:59 |  |  | 2020-07-28 11:45 | 2020-07-28 11:45 |  |  | 100 | 100 | [15 empty] | 0.36734 | 0.003153 | 0.31 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3392 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018607
1058 | Task(Task)-->P (Procurement) | Building Structure |  | 1.9.2.1 | Completed | No | No | 2020-03-20 09:00 | 2020-03-20 18:00 | 2020-04-06 09:00 | 2020-04-06 18:00 |  |  | 2020-04-06 17:30 | 2020-04-06 17:30 |  |  | 100 | 100 | [15 empty] | 32.6579 | 0.28027 | 27.56 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3393 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018608
1059 | Task(Task)-->P (Procurement) | 6.6KV HT VFD with Motors |  | 1.9.2.1 | Completed | No | No | 2019-12-30 09:00 | 2019-12-30 18:00 | 2020-01-24 09:00 | 2020-01-24 18:00 |  |  | 2019-11-21 10:57 | 2019-11-21 10:57 |  |  | 100 | 100 | [15 empty] | 9.9064 | 0.085018 | 8.36 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3394 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018609
1060 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.9.2.1 | Completed | No | No | 2020-03-10 09:00 | 2020-03-10 18:00 | 2020-03-16 09:00 | 2020-03-16 18:00 |  |  | 2020-03-16 10:57 | 2020-03-16 10:57 |  |  | 100 | 100 | [15 empty] | 0.31994 | 0.002746 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3395 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018610
1061 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.9.2.1 | Completed | No | No | 2020-03-27 09:00 | 2020-03-27 18:00 | 2020-04-30 09:00 | 2020-04-30 18:00 |  |  | 2020-04-30 10:57 | 2020-04-30 10:57 |  |  | 100 | 100 | [15 empty] | 0.1422 | 0.00122 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3396 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018611
1062 | Task(Task)-->P (Procurement) | WELDING DISTRIBUTION BOARD |  | 1.9.2.1 | Completed | No | No | 2020-02-14 09:00 | 2020-02-14 18:00 | 2019-11-08 09:00 | 2019-11-08 18:00 |  |  | 2019-11-08 17:06 | 2019-11-08 17:06 |  |  | 100 | 100 | [15 empty] | 0.39104 | 0.003356 | 0.33 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3397 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018612
1063 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.9.2.1 | Completed | No | No | 2020-01-08 09:00 | 2020-01-08 18:00 | 2020-01-08 09:00 | 2020-01-08 18:00 |  |  | 2020-01-08 10:57 | 2020-01-08 10:57 |  |  | 100 | 100 | [15 empty] | 0.047399 | 0.000407 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3399 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018613
1064 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.9.2.1 | Completed | No | No | 2019-12-30 09:00 | 2019-12-30 18:00 | 2019-12-30 09:00 | 2019-12-30 18:00 |  |  | 2019-12-30 10:57 | 2019-12-30 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3400 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018614
1065 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.9.2.1 | Completed | No | No | 2020-01-03 09:00 | 2020-01-03 18:00 | 2020-01-03 09:00 | 2020-01-03 18:00 |  |  | 2020-01-03 10:57 | 2020-01-03 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3401 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018615
1066 | Task(Task)-->P (Procurement) | TECHNICAL CLEARANCE | 1.9.2.2 | 1.9.2 | Work In Progress | No | No | 2019-11-08 09:00 | 2020-06-18 18:00 | 2019-11-08 09:00 | 2020-10-15 18:00 |  |  | 2019-11-09 17:07 |  |  |  | 100 | 99.0994 | [15 empty] | 5.0002 | 0.85821 | 84.4 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3402 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018616
1067 | Task(Task)-->P (Procurement) | Pulley |  | 1.9.2.2 | Completed | No | No | 2020-03-04 09:00 | 2020-03-04 18:00 | 2020-04-26 | 2020-04-26 23:59 |  |  | 2020-04-26 10:57 | 2020-04-26 10:57 |  |  | 100 | 100 | [15 empty] | 4.3133 | 0.037017 | 3.64 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3403 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018617
1068 | Task(Task)-->P (Procurement) | Idler |  | 1.9.2.2 | Completed | No | No | 2019-11-20 09:00 | 2020-02-01 18:00 | 2020-03-21 09:00 | 2020-05-16 18:00 |  |  | 2020-03-23 15:48 | 2020-05-16 15:48 |  |  | 100 | 100 | [15 empty] | 16.2579 | 0.13953 | 13.72 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3404 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018618
1069 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.9.2.2 | Completed | No | No | 2020-05-18 09:00 | 2020-06-01 18:00 | 2020-04-26 | 2020-04-26 23:59 |  |  | 2020-04-26 10:57 | 2020-04-26 10:57 |  |  | 100 | 100 | [15 empty] | 0.34364 | 0.002949 | 0.29 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3405 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018619
1070 | Task(Task)-->P (Procurement) | Bearing |  | 1.9.2.2 | Completed | No | No | 2020-05-18 09:00 | 2020-06-16 18:00 | 2020-04-26 | 2020-04-26 23:59 |  |  | 2020-04-26 10:57 | 2020-04-26 10:57 |  |  | 100 | 100 | [15 empty] | 0.78208 | 0.006712 | 0.66 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3406 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018620
1071 | Task(Task)-->P (Procurement) | Belting |  | 1.9.2.2 | Completed | No | No | 2019-11-08 09:00 | 2020-03-27 18:00 | 2020-02-21 09:00 | 2020-05-16 18:00 |  |  | 2020-05-16 10:57 | 2020-05-16 10:57 |  |  | 100 | 100 | [15 empty] | 28.9489 | 0.24844 | 24.43 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3407 | 0 | 4 | High | [7 empty] | 0 | 0 | [244 empty] | 1018621
1072 | Task(Task)-->P (Procurement) | Scrapper |  | 1.9.2.2 | Completed | No | No | 2019-11-18 09:00 | 2020-03-16 18:00 | 2020-03-11 09:00 | 2020-03-26 18:00 |  |  | 2020-03-26 10:57 | 2020-03-26 10:57 |  |  | 100 | 100 | [15 empty] | 0.023699 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3408 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018622
1073 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.9.2.2 | Completed | No | No | 2020-03-11 09:00 | 2020-03-20 18:00 | 2020-03-11 09:00 | 2020-03-17 18:00 |  |  | 2020-03-12 12:43 | 2020-03-17 12:43 |  |  | 100 | 100 | [15 empty] | 1.5049 | 0.012915 | 1.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3409 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018623
1074 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.9.2.2 | Unscheduled | No | No | 2020-05-20 09:00 | 2020-06-18 18:00 | 2020-06-08 09:00 | 2020-08-13 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.53324 | 0.004576 | 0.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3410 | 1 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018624
1075 | Task(Task)-->P (Procurement) | Gear Box |  | 1.9.2.2 | Completed | No | No | 2019-11-14 09:00 | 2020-05-21 18:00 | 2020-02-21 09:00 | 2020-05-29 18:00 |  |  | 2020-02-22 11:19 | 2020-05-29 10:57 |  |  | 100 | 100 | [15 empty] | 2.7017 | 0.023187 | 2.28 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3411 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018625
1076 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.9.2.2 | Completed | No | No | 2019-11-22 09:00 | 2020-03-19 18:00 | 2020-04-27 09:00 | 2020-05-30 18:00 |  |  | 2020-05-30 10:46 | 2020-05-30 10:46 |  |  | 100 | 100 | [15 empty] | 0.58064 | 0.004983 | 0.49 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3412 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018626
1077 | Task(Task)-->P (Procurement) | Brake |  | 1.9.2.2 | Completed | No | No | 2019-12-19 09:00 | 2020-04-05 23:59 | 2020-05-01 09:00 | 2020-06-15 18:00 |  |  | 2020-04-24 11:34 | 2020-06-15 10:57 |  |  | 100 | 100 | [15 empty] | 0.17775 | 0.001525 | 0.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3413 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018627
1078 | Task(Task)-->P (Procurement) | Maintenance Trolley |  | 1.9.2.2 | Unscheduled | No | No | 2019-12-01 | 2019-12-18 18:00 | 2020-07-19 | 2020-10-15 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.36734 | 0.003153 | 0.31 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3414 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018628
1079 | Task(Task)-->P (Procurement) | Building Structure |  | 1.9.2.2 | Completed | No | No | 2020-03-21 09:00 | 2020-03-27 18:00 | 2020-04-06 09:00 | 2020-04-13 18:00 |  |  | 2020-04-07 17:31 | 2020-04-13 17:31 |  |  | 100 | 100 | [15 empty] | 32.6579 | 0.28027 | 27.56 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3415 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018629
1080 | Task(Task)-->P (Procurement) | 6.6KV HT VFD with Motors |  | 1.9.2.2 | Completed | No | No | 2019-12-31 09:00 | 2020-01-29 18:00 | 2020-01-24 09:00 | 2020-04-16 18:00 |  |  | 2020-02-26 10:57 | 2020-02-26 10:57 |  |  | 100 | 100 | [15 empty] | 9.9064 | 0.085018 | 8.36 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3416 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018630
1081 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.9.2.2 | Completed | No | No | 2020-03-11 09:00 | 2020-03-25 18:00 | 2020-03-16 09:00 | 2020-06-02 18:00 |  |  | 2020-06-02 10:57 | 2020-06-02 10:57 |  |  | 100 | 100 | [15 empty] | 0.31994 | 0.002746 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3417 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018631
1082 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.9.2.2 | Completed | No | No | 2020-03-28 09:00 | 2020-05-11 18:00 | 2020-04-30 09:00 | 2020-06-03 18:00 |  |  | 2020-06-03 10:57 | 2020-06-03 10:57 |  |  | 100 | 100 | [15 empty] | 0.1422 | 0.00122 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3418 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018632
1083 | Task(Task)-->P (Procurement) | WELDING DISTRIBUTION BOARD |  | 1.9.2.2 | Completed | No | No | 2020-02-15 09:00 | 2020-02-28 18:00 | 2019-11-08 09:00 | 2020-02-13 18:00 |  |  | 2019-11-09 17:07 | 2020-02-13 17:07 |  |  | 100 | 100 | [15 empty] | 0.39104 | 0.003356 | 0.33 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3419 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018633
1084 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.9.2.2 | Completed | No | No | 2020-01-09 09:00 | 2020-01-22 18:00 | 2020-01-08 09:00 | 2020-03-10 18:00 |  |  | 2020-03-10 10:57 | 2020-03-10 10:57 |  |  | 100 | 100 | [15 empty] | 0.047399 | 0.000407 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3421 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018634
1085 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.9.2.2 | Completed | No | No | 2019-12-31 09:00 | 2020-01-14 18:00 | 2019-12-30 09:00 | 2020-03-07 18:00 |  |  | 2020-03-07 10:57 | 2020-03-07 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3422 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018635
1086 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.9.2.2 | Completed | No | No | 2020-01-04 09:00 | 2020-01-18 18:00 | 2020-01-03 09:00 | 2020-01-16 18:00 |  |  | 2020-01-16 10:57 | 2020-01-16 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3423 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018636
1087 | Task(Task)-->P (Procurement) | ORDERING | 1.9.2.3 | 1.9.2 | Work In Progress | No | No | 2019-12-19 09:00 | 2020-07-18 18:00 | 2020-01-16 09:00 | 2020-11-04 18:00 |  |  | 2020-02-01 10:57 |  |  |  | 100 | 93.9458 | [15 empty] | 9.9999 | 1.7163 | 168.79 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3424 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018637
1088 | Task(Task)-->P (Procurement) | Pulley |  | 1.9.2.3 | Unscheduled | No | No | 2020-03-05 09:00 | 2020-04-03 18:00 | 2020-04-26 | 2020-07-16 18:00 | [6 empty] | 100 | 0 | [15 empty] | 4.3185 | 0.074119 | 7.29 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3425 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018638
1089 | Task(Task)-->P (Procurement) | Idler |  | 1.9.2.3 | Completed | No | No | 2020-02-02 | 2020-03-02 18:00 | 2020-05-16 09:00 | 2020-08-22 18:00 |  |  | 2020-05-16 16:18 | 2020-08-22 16:18 |  |  | 100 | 100 | [15 empty] | 16.255 | 0.27899 | 27.44 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3426 | 1 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018639
1090 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.9.2.3 | Completed | No | No | 2020-06-02 09:00 | 2020-07-01 18:00 | 2020-04-26 | 2020-07-07 18:00 |  |  | 2020-04-27 09:32 | 2020-07-07 09:32 |  |  | 100 | 100 | [15 empty] | 0.34951 | 0.005999 | 0.59 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3427 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018640
1091 | Task(Task)-->P (Procurement) | Bearing |  | 1.9.2.3 | Unscheduled | No | No | 2020-06-17 09:00 | 2020-07-16 18:00 | 2020-04-26 | 2020-08-22 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.78194 | 0.013421 | 1.32 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3428 | 1 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018641
1092 | Task(Task)-->P (Procurement) | Belting |  | 1.9.2.3 | Completed | No | No | 2020-03-28 09:00 | 2020-05-11 18:00 | 2020-05-16 09:00 | 2020-09-04 18:00 |  |  | 2020-05-16 16:24 | 2020-09-04 16:24 |  |  | 100 | 100 | [15 empty] | 28.9379 | 0.49667 | 48.85 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3429 | 0 | 4 | High | [7 empty] | 0 | 0 | [244 empty] | 1018642
1093 | Task(Task)-->P (Procurement) | Scrapper |  | 1.9.2.3 | Completed | No | No | 2020-03-17 09:00 | 2020-04-15 18:00 | 2020-03-26 09:00 | 2020-05-30 18:00 |  |  | 2020-05-30 10:57 | 2020-05-30 10:57 |  |  | 100 | 100 | [15 empty] | 0.023695 | 0.000407 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3430 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018643
1094 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.9.2.3 | Completed | No | No | 2020-03-21 09:00 | 2020-04-19 23:59 | 2020-03-17 09:00 | 2020-07-06 18:00 |  |  | 2020-03-18 12:44 | 2020-07-06 12:44 |  |  | 100 | 100 | [15 empty] | 1.4987 | 0.025723 | 2.53 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3431 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018644
1095 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.9.2.3 | Unscheduled | No | No | 2020-06-19 09:00 | 2020-07-18 18:00 | 2020-08-13 09:00 | 2020-10-10 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.53907 | 0.009252 | 0.91 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3432 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018645
1096 | Task(Task)-->P (Procurement) | Gear Box |  | 1.9.2.3 | Completed | No | No | 2020-05-22 09:00 | 2020-06-20 18:00 | 2020-05-29 09:00 | 2020-06-23 18:00 |  |  | 2020-05-30 11:21 | 2020-06-23 16:51 |  |  | 100 | 100 | [15 empty] | 2.6953 | 0.046261 | 4.55 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3433 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018646
1097 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.9.2.3 | Completed | No | No | 2020-03-20 09:00 | 2020-04-18 18:00 | 2020-05-30 09:00 | 2020-06-16 18:00 |  |  | 2020-06-01 11:11 | 2020-06-16 16:05 |  |  | 100 | 100 | [15 empty] | 0.58646 | 0.010065 | 0.99 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3434 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018647
1098 | Task(Task)-->P (Procurement) | Brake |  | 1.9.2.3 | Completed | No | No | 2020-04-06 09:00 | 2020-05-05 18:00 | 2020-06-15 09:00 | 2020-07-03 18:00 |  |  | 2020-06-16 11:39 | 2020-07-03 11:39 |  |  | 100 | 100 | [15 empty] | 0.18364 | 0.003152 | 0.31 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3435 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018648
1099 | Task(Task)-->P (Procurement) | Maintenance Trolley |  | 1.9.2.3 | Unscheduled | No | No | 2019-12-19 09:00 | 2020-01-07 18:00 | 2020-10-16 09:00 | 2020-11-04 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.3732 | 0.006405 | 0.63 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3436 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018649
1100 | Task(Task)-->P (Procurement) | Building Structure |  | 1.9.2.3 | Completed | No | No | 2020-03-28 09:00 | 2020-04-26 23:59 | 2020-04-13 09:00 | 2020-05-31 23:59 |  |  | 2020-05-31 18:49 | 2020-05-31 18:49 |  |  | 100 | 100 | [15 empty] | 32.6462 | 0.56031 | 55.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3437 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018650
1101 | Task(Task)-->P (Procurement) | 6.6KV HT VFD with Motors |  | 1.9.2.3 | Completed | No | No | 2020-01-30 09:00 | 2020-02-28 18:00 | 2020-04-16 09:00 | 2020-07-18 18:00 |  |  | 2020-04-29 10:57 | 2020-04-29 10:57 |  |  | 100 | 100 | [15 empty] | 9.9106 | 0.1701 | 16.73 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3438 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018651
1102 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.9.2.3 | Completed | No | No | 2020-03-26 09:00 | 2020-04-10 18:00 | 2020-06-02 09:00 | 2020-07-31 18:00 |  |  | 2020-06-03 15:51 | 2020-06-29 15:51 |  |  | 100 | 100 | [15 empty] | 0.31396 | 0.005389 | 0.53 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3439 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018652
1103 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.9.2.3 | Completed | No | No | 2020-05-12 09:00 | 2020-06-25 18:00 | 2020-06-03 09:00 | 2020-06-24 18:00 |  |  | 2020-06-15 10:57 | 2020-06-15 10:57 |  |  | 100 | 100 | [15 empty] | 0.14217 | 0.00244 | 0.24 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3440 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018653
1104 | Task(Task)-->P (Procurement) | WELDING DISTRIBUTION BOARD |  | 1.9.2.3 | Completed | No | No | 2020-02-29 09:00 | 2020-03-14 18:00 | 2020-02-13 09:00 | 2020-06-17 18:00 |  |  | 2020-02-29 08:00 | 2020-03-24 16:05 |  |  | 100 | 100 | [15 empty] | 0.3969 | 0.006812 | 0.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3441 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018654
1105 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.9.2.3 | Unscheduled | No | No | 2020-01-23 09:00 | 2020-02-05 18:00 | 2020-03-10 09:00 | 2020-08-17 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.041467 | 0.000712 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3443 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018655
1106 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.9.2.3 | Unscheduled | No | No | 2020-01-15 09:00 | 2020-02-01 18:00 | 2020-03-07 09:00 | 2020-08-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3444 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018656
1107 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.9.2.3 | Completed | No | No | 2020-01-19 | 2020-01-31 18:00 | 2020-01-16 09:00 | 2020-02-01 18:00 |  |  | 2020-02-01 10:57 | 2020-02-01 10:57 |  |  | 100 | 100 | [15 empty] | 0.0059238 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3445 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018657
1108 | Task(Task)-->P (Procurement) | ITP APPROVAL | 1.9.2.4 | 1.9.2 | Work In Progress | No | No | 2020-01-08 09:00 | 2020-08-27 18:00 | 2020-05-01 09:00 | 2020-12-14 18:00 |  |  | 2020-05-01 10:26 |  |  |  | 100 | 34.5918 | [15 empty] | 5.0002 | 0.85821 | 84.4 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3446 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018658
1109 | Task(Task)-->P (Procurement) | Pulley |  | 1.9.2.4 | Unscheduled | No | No | 2020-04-04 09:00 | 2020-05-13 18:00 | 2020-07-16 09:00 | 2020-07-16 18:00 | [6 empty] | 100 | 0 | [15 empty] | 4.3133 | 0.037017 | 3.64 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3447 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018659
1110 | Task(Task)-->P (Procurement) | Idler |  | 1.9.2.4 | Unscheduled | No | No | 2020-03-03 09:00 | 2020-04-11 18:00 | 2020-08-22 09:00 | 2020-10-10 18:00 |  |  | 2020-08-22 16:22 |  |  |  | 100 | 10 | [15 empty] | 16.2579 | 0.13953 | 13.72 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3448 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018660
1111 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.9.2.4 | Unscheduled | No | No | 2020-07-02 09:00 | 2020-08-10 18:00 | 2020-07-07 09:00 | 2020-08-13 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.34364 | 0.002949 | 0.29 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3449 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018661
1112 | Task(Task)-->P (Procurement) | Bearing |  | 1.9.2.4 | Unscheduled | No | No | 2020-07-17 09:00 | 2020-08-25 18:00 | 2020-05-18 09:00 | 2020-05-25 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.78208 | 0.006712 | 0.66 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3450 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018662
1113 | Task(Task)-->P (Procurement) | Belting |  | 1.9.2.4 | Completed | No | No | 2020-05-12 09:00 | 2020-06-20 18:00 | 2020-09-04 09:00 | 2020-10-15 18:00 |  |  | 2020-09-04 16:30 | 2020-09-30 16:30 |  |  | 100 | 100 | [15 empty] | 28.9489 | 0.24844 | 24.43 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3451 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018663
1114 | Task(Task)-->P (Procurement) | Scrapper |  | 1.9.2.4 | Completed | No | No | 2020-04-16 09:00 | 2020-05-25 18:00 | 2020-05-30 09:00 | 2020-06-25 18:00 |  |  | 2020-05-30 16:32 | 2020-06-25 16:32 |  |  | 100 | 100 | [15 empty] | 0.023699 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3452 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018664
1115 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.9.2.4 | Unscheduled | No | No | 2020-04-20 09:00 | 2020-05-29 18:00 | 2020-07-06 09:00 | 2020-07-16 18:00 | [6 empty] | 100 | 0 | [15 empty] | 1.5049 | 0.012915 | 1.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3453 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018665
1116 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.9.2.4 | Unscheduled | No | No | 2020-07-19 | 2020-08-27 18:00 | 2020-10-11 | 2020-11-19 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.53324 | 0.004576 | 0.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3454 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018666
1117 | Task(Task)-->P (Procurement) | Gear Box |  | 1.9.2.4 | Completed | No | No | 2020-06-21 | 2020-07-30 18:00 | 2020-06-23 09:00 | 2020-06-23 18:00 |  |  | 2020-06-22 16:57 | 2020-06-22 16:57 |  |  | 100 | 100 | [15 empty] | 2.7017 | 0.023187 | 2.28 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3455 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018667
1118 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.9.2.4 | Completed | No | No | 2020-04-19 | 2020-05-28 18:00 | 2020-06-16 09:00 | 2020-06-18 18:00 |  |  | 2020-06-16 17:31 | 2020-06-18 17:31 |  |  | 100 | 100 | [15 empty] | 0.58064 | 0.004983 | 0.49 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3456 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018668
1119 | Task(Task)-->P (Procurement) | Brake |  | 1.9.2.4 | Unscheduled | No | No | 2020-05-06 09:00 | 2020-06-14 23:59 | 2020-07-03 09:00 | 2020-10-30 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.17775 | 0.001525 | 0.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3457 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018669
1120 | Task(Task)-->P (Procurement) | Maintenance Trolley |  | 1.9.2.4 | Unscheduled | No | No | 2020-01-08 09:00 | 2020-02-16 23:59 | 2020-11-05 09:00 | 2020-12-14 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.36734 | 0.003153 | 0.31 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3458 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018670
1121 | Task(Task)-->P (Procurement) | Building Structure |  | 1.9.2.4 | Unscheduled | No | No | 2020-04-27 09:00 | 2020-05-03 23:59 | 2020-05-31 | 2020-08-04 18:00 |  |  | 2020-06-25 19:04 |  |  |  | 100 | 0 | [15 empty] | 32.6579 | 0.28027 | 27.56 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3459 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018671
1122 | Task(Task)-->P (Procurement) | 6.6KV HT VFD with Motors |  | 1.9.2.4 | Unscheduled | No | No | 2020-02-29 09:00 | 2020-04-08 18:00 | 2020-08-01 09:00 | 2020-09-09 18:00 | [6 empty] | 100 | 0 | [15 empty] | 9.9064 | 0.085018 | 8.36 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3460 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018672
1123 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.9.2.4 | Completed | No | No | 2020-04-11 09:00 | 2020-05-20 18:00 | 2020-07-28 09:00 | 2020-09-08 18:00 |  |  | 2020-07-08 17:23 | 2020-09-08 17:23 |  |  | 100 | 100 | [15 empty] | 0.31994 | 0.002746 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3461 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018673
1124 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.9.2.4 | Unscheduled | No | No | 2020-06-26 09:00 | 2020-08-04 18:00 | 2020-06-23 09:00 | 2020-09-08 18:00 |  |  | 2020-06-23 17:41 |  |  |  | 100 | 0 | [15 empty] | 0.1422 | 0.00122 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3462 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018674
1125 | Task(Task)-->P (Procurement) | WELDING DISTRIBUTION BOARD |  | 1.9.2.4 | Completed | No | No | 2020-03-15 | 2020-04-23 18:00 | 2020-05-01 09:00 | 2020-05-19 18:00 |  |  | 2020-05-01 10:26 | 2020-05-19 10:26 |  |  | 100 | 100 | [15 empty] | 0.39104 | 0.003356 | 0.33 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3463 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018675
1126 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.9.2.4 | Unscheduled | No | No | 2020-02-06 09:00 | 2020-03-16 18:00 | 2020-09-24 09:00 | 2020-10-30 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.047399 | 0.000407 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3465 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018676
1127 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.9.2.4 | Unscheduled | No | No | 2020-02-02 | 2020-03-12 18:00 | 2020-08-02 | 2020-09-10 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3466 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018677
1128 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.9.2.4 | Unscheduled | No | No | 2020-02-01 09:00 | 2020-03-11 18:00 | 2020-07-02 09:00 | 2020-08-04 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3467 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018678
1129 | Task(Task)-->P (Procurement) | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE | 1.9.2.5 | 1.9.2 | Work In Progress | No | No | 2020-01-08 09:00 | 2020-09-01 18:00 | 2020-02-01 09:00 | 2021-01-13 18:00 |  |  | 2020-02-11 21:31 |  |  |  | 100 | 61.0723 | [15 empty] | 15.0001 | 2.5745 | 253.19 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3468 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018679
1130 | Task(Task)-->P (Procurement) | Pulley |  | 1.9.2.5 | Unscheduled | No | No | 2020-04-04 09:00 | 2020-06-02 18:00 | 2020-07-16 09:00 | 2020-07-16 18:00 | [6 empty] | 100 | 0 | [15 empty] | 4.3167 | 0.11114 | 10.93 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3469 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018680
1131 | Task(Task)-->P (Procurement) | Idler |  | 1.9.2.5 | Unscheduled | No | No | 2020-03-03 09:00 | 2020-05-01 18:00 | 2020-08-22 09:00 | 2020-10-15 18:00 | [6 empty] | 100 | 0 | [15 empty] | 16.2559 | 0.41851 | 41.16 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3470 | 1 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018681
1132 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.9.2.5 | Unscheduled | No | No | 2020-07-02 09:00 | 2020-08-30 23:59 | 2020-07-07 09:00 | 2020-09-28 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.34755 | 0.008948 | 0.88 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3471 | 1 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018682
1133 | Task(Task)-->P (Procurement) | Bearing |  | 1.9.2.5 | Unscheduled | No | No | 2020-07-17 09:00 | 2020-07-17 18:00 | 2020-07-18 09:00 | 2020-08-22 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.78199 | 0.020133 | 1.98 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3472 | 1 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018683
1134 | Task(Task)-->P (Procurement) | Belting |  | 1.9.2.5 | Unscheduled | No | No | 2020-05-12 09:00 | 2020-07-20 18:00 | 2020-09-04 09:00 | 2020-10-15 18:00 |  |  | 2020-09-04 16:36 |  |  |  | 100 | 50 | [15 empty] | 28.9415 | 0.74511 | 73.28 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3473 | 0 | 4 | High | [7 empty] | 0 | 0 | [244 empty] | 1018684
1135 | Task(Task)-->P (Procurement) | Scrapper |  | 1.9.2.5 | Completed | No | No | 2020-04-16 09:00 | 2020-06-14 23:59 | 2020-05-30 09:00 | 2020-07-30 18:00 |  |  | 2020-05-30 16:35 | 2020-07-30 16:35 |  |  | 100 | 100 | [15 empty] | 0.023697 | 0.00061 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3474 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018685
1136 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.9.2.5 | Completed | No | No | 2020-04-20 09:00 | 2020-08-17 18:00 | 2020-07-06 09:00 | 2020-07-06 18:00 |  |  | 2020-07-06 12:45 | 2020-07-06 12:45 |  |  | 100 | 100 | [15 empty] | 1.5008 | 0.038638 | 3.8 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3475 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018686
1137 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.9.2.5 | Unscheduled | No | No | 2020-07-19 | 2020-09-01 18:00 | 2020-10-11 | 2020-11-24 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.53712 | 0.013828 | 1.36 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3476 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018687
1138 | Task(Task)-->P (Procurement) | Gear Box |  | 1.9.2.5 | Unscheduled | No | No | 2020-06-21 | 2020-08-19 18:00 | 2020-06-23 09:00 | 2020-10-16 18:00 |  |  | 2020-06-23 16:55 |  |  |  | 100 | 50 | [15 empty] | 2.6975 | 0.069447 | 6.83 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3477 | 1 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018688
1139 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.9.2.5 | Completed | No | No | 2020-04-19 | 2020-06-17 18:00 | 2020-06-16 09:00 | 2020-09-02 18:00 |  |  | 2020-06-16 17:31 | 2020-09-02 17:31 |  |  | 100 | 100 | [15 empty] | 0.58452 | 0.015049 | 1.48 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3478 | 1 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018689
1140 | Task(Task)-->P (Procurement) | Brake |  | 1.9.2.5 | Unscheduled | No | No | 2020-05-06 09:00 | 2020-07-04 18:00 | 2020-07-03 09:00 | 2020-10-10 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.18167 | 0.004677 | 0.46 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3479 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018690
1141 | Task(Task)-->P (Procurement) | Maintenance Trolley |  | 1.9.2.5 | Unscheduled | No | No | 2020-01-08 09:00 | 2020-03-17 18:00 | 2020-11-05 09:00 | 2021-01-13 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.37125 | 0.009558 | 0.94 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3480 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018691
1142 | Task(Task)-->P (Procurement) | Building Structure |  | 1.9.2.5 | Completed | No | No | 2020-04-25 09:00 | 2020-05-01 18:00 | 2020-05-31 | 2020-06-27 18:00 |  |  | 2020-05-31 18:54 | 2020-06-23 18:54 |  |  | 100 | 100 | [15 empty] | 32.6501 | 0.84059 | 82.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3481 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018692
1143 | Task(Task)-->P (Procurement) | 6.6KV HT VFD with Motors |  | 1.9.2.5 | Completed | No | No | 2020-02-29 09:00 | 2020-05-13 18:00 | 2020-08-08 09:00 | 2020-10-10 18:00 |  |  | 2020-07-28 11:51 | 2020-09-23 15:24 |  |  | 100 | 100 | [15 empty] | 9.9092 | 0.25511 | 25.09 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3482 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018693
1144 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.9.2.5 | Unscheduled | No | No | 2020-04-11 09:00 | 2020-05-25 18:00 | 2020-07-10 09:00 | 2020-10-16 18:00 |  |  | 2020-07-14 10:44 |  |  |  | 100 | 0 | [15 empty] | 0.31596 | 0.008134 | 0.8 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3483 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018694
1145 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.9.2.5 | Completed | No | No | 2020-06-26 09:00 | 2020-08-09 23:59 | 2020-05-30 09:00 | 2020-08-08 18:00 |  |  | 2020-06-18 17:11 | 2020-08-07 15:00 |  |  | 100 | 100 | [15 empty] | 0.14218 | 0.00366 | 0.36 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3484 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018695
1146 | Task(Task)-->P (Procurement) | WELDING DISTRIBUTION BOARD |  | 1.9.2.5 | Completed | No | No | 2020-03-15 | 2020-04-28 18:00 | 2020-04-25 09:00 | 2020-07-17 18:00 |  |  | 2020-04-25 10:24 | 2020-07-17 10:23 |  |  | 100 | 100 | [15 empty] | 0.39494 | 0.010168 | 1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3485 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018696
1147 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.9.2.5 | Completed | No | No | 2020-02-06 09:00 | 2020-03-21 18:00 | 2020-08-11 09:00 | 2020-09-19 18:00 |  |  | 2020-08-11 13:12 | 2020-09-19 12:58 |  |  | 100 | 100 | [15 empty] | 0.043444 | 0.001118 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3487 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018697
1148 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.9.2.5 | Unscheduled | No | No | 2020-02-02 | 2020-03-17 18:00 | 2020-08-09 | 2020-10-20 18:00 |  |  | 2020-08-09 13:16 |  |  |  | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3488 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018698
1149 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.9.2.5 | Completed | No | No | 2020-02-01 09:00 | 2020-03-16 18:00 | 2020-02-01 09:00 | 2020-07-15 18:00 |  |  | 2020-02-11 21:31 | 2020-07-15 21:31 |  |  | 100 | 100 | [15 empty] | 0.0039495 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3489 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018699
1150 | Task(Task)-->P (Procurement) | MANUFACTURING & RECEIPT AT SITE (MRN) | 1.9.2.6 | 1.9.2 | Unscheduled | No | No | 2020-03-17 09:00 | 2021-03-31 18:00 | 2020-06-27 09:00 | 2022-01-22 18:00 |  |  | 2020-07-15 21:37 |  |  |  | 42.619 | 0.17537 | [15 empty] | 59.9993 | 10.2979 | 1012.74 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3490 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018700
1151 | Task(Task)-->P (Procurement) | Pulley |  | 1.9.2.6 | Unscheduled | No | No | 2020-06-03 09:00 | 2021-03-31 18:00 | 2020-07-16 09:00 | 2021-03-31 18:00 | [6 empty] | 42.053 | 0 | [15 empty] | 4.318 | 0.44466 | 43.73 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3491 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018701
1152 | Task(Task)-->P (Procurement) | Idler |  | 1.9.2.6 | Unscheduled | No | No | 2020-05-02 09:00 | 2021-03-28 23:59 | 2020-10-16 09:00 | 2021-09-11 18:00 | [6 empty] | 48.0363 | 0 | [15 empty] | 16.2559 | 1.674 | 164.63 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3492 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018702
1153 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.9.2.6 | Unscheduled | No | No | 2020-08-31 09:00 | 2021-02-01 18:00 | 2020-09-28 09:00 | 2021-03-15 18:00 | [6 empty] | 24.5161 | 0 | [15 empty] | 0.34955 | 0.035996 | 3.54 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3493 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018703
1154 | Task(Task)-->P (Procurement) | Bearing |  | 1.9.2.6 | Unscheduled | No | No | 2020-08-26 09:00 | 2021-01-22 18:00 | 2020-08-22 09:00 | 2021-03-31 18:00 | [6 empty] | 28.6667 | 0 | [15 empty] | 0.78302 | 0.080635 | 7.93 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3494 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018704
1155 | Task(Task)-->P (Procurement) | Belting |  | 1.9.2.6 | Unscheduled | No | No | 2020-07-21 09:00 | 2021-03-31 18:00 | 2020-10-16 09:00 | 2021-06-26 18:00 | [6 empty] | 31.1024 | 0 | [15 empty] | 28.9413 | 2.9804 | 293.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3495 | 0 | 4 | High | [7 empty] | 0 | 0 | [244 empty] | 1018705
1156 | Task(Task)-->P (Procurement) | Scrapper |  | 1.9.2.6 | Unscheduled | No | No | 2020-06-15 09:00 | 2020-12-11 18:00 | 2020-07-30 09:00 | 2020-12-31 18:00 | [6 empty] | 63.8889 | 0 | [15 empty] | 0.021723 | 0.002237 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3496 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018706
1157 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.9.2.6 | Unscheduled | No | No | 2020-06-19 09:00 | 2021-03-15 18:00 | 2020-07-06 09:00 | 2021-01-31 23:59 | [6 empty] | 41.1111 | 0 | [15 empty] | 1.5009 | 0.15456 | 15.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3497 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018707
1158 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.9.2.6 | Unscheduled | No | No | 2020-09-02 09:00 | 2021-01-29 18:00 | 2020-11-25 09:00 | 2021-04-23 18:00 | [6 empty] | 24 | 0 | [15 empty] | 0.53814 | 0.055418 | 5.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3498 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018708
1159 | Task(Task)-->P (Procurement) | Gear Box |  | 1.9.2.6 | Unscheduled | No | No | 2020-08-20 09:00 | 2021-02-20 18:00 | 2020-10-17 09:00 | 2021-04-19 18:00 | [6 empty] | 26.4865 | 0 | [15 empty] | 2.6957 | 0.2776 | 27.3 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3499 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018709
1160 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.9.2.6 | Unscheduled | No | No | 2020-06-18 09:00 | 2020-12-15 18:00 | 2020-09-02 09:00 | 2021-02-09 18:00 |  |  | 2020-09-02 17:44 |  |  |  | 61.8785 | 30 | [15 empty] | 0.58455 | 0.060197 | 5.92 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3500 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018710
1161 | Task(Task)-->P (Procurement) | Brake |  | 1.9.2.6 | Unscheduled | No | No | 2020-07-05 | 2021-02-10 18:00 | 2020-10-31 09:00 | 2021-06-08 18:00 | [6 empty] | 42.9864 | 0 | [15 empty] | 0.18169 | 0.01871 | 1.84 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3501 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018711
1162 | Task(Task)-->P (Procurement) | Maintenance Trolley |  | 1.9.2.6 | Unscheduled | No | No | 2020-03-18 09:00 | 2021-03-26 18:00 | 2021-01-14 09:00 | 2022-01-22 18:00 | [6 empty] | 54.5455 | 0 | [15 empty] | 0.37028 | 0.038131 | 3.75 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3502 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018712
1163 | Task(Task)-->P (Procurement) | Building Structure |  | 1.9.2.6 | Unscheduled | No | No | 2020-05-04 09:00 | 2021-03-19 18:00 | 2020-06-27 09:00 | 2021-03-31 18:00 | [6 empty] | 49.0625 | 0 | [15 empty] | 32.651 | 3.3624 | 330.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3503 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018713
1164 | Task(Task)-->P (Procurement) | 6.6KV HT VFD with Motors |  | 1.9.2.6 | Unscheduled | No | No | 2020-05-14 09:00 | 2021-03-09 18:00 | 2020-10-11 | 2021-08-06 18:00 | [6 empty] | 49 | 0 | [15 empty] | 9.9107 | 1.0206 | 100.37 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3504 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018714
1165 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.9.2.6 | Unscheduled | No | No | 2020-05-26 09:00 | 2021-02-18 18:00 | 2020-10-17 09:00 | 2021-07-12 18:00 | [6 empty] | 50.1859 | 0 | [15 empty] | 0.31499 | 0.032437 | 3.19 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3505 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018715
1166 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.9.2.6 | Unscheduled | No | No | 2020-08-10 09:00 | 2020-11-07 18:00 | 2020-09-09 09:00 | 2020-12-07 18:00 |  |  | 2020-08-07 15:00 |  |  |  | 65.5556 | 0 | [15 empty] | 0.14318 | 0.014744 | 1.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3506 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018716
1167 | Task(Task)-->P (Procurement) | WELDING DISTRIBUTION BOARD |  | 1.9.2.6 | Unscheduled | No | No | 2020-04-29 09:00 | 2020-09-26 18:00 | 2020-07-18 09:00 | 2020-12-15 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.39398 | 0.040572 | 3.99 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3507 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018717
1168 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.9.2.6 | Unscheduled | No | No | 2020-03-22 | 2020-07-05 23:59 | 2020-10-31 09:00 | 2021-02-13 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.041472 | 0.004271 | 0.42 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3509 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018718
1169 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.9.2.6 | Unscheduled | No | No | 2020-03-18 09:00 | 2020-07-27 18:00 | 2020-10-21 09:00 | 2021-03-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.00098742 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3510 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018719
1170 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.9.2.6 | Unscheduled | No | No | 2020-03-17 09:00 | 2020-07-31 18:00 | 2020-07-02 09:00 | 2020-11-15 23:59 |  |  | 2020-07-15 21:37 |  |  |  | 100 | 0 | [15 empty] | 0.0029623 | 0.000305 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3511 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018720
1171 | Task(Task)-->C (Construction) | CONSTRUCTION | 1.9.3 | 1.9 | Unscheduled | No | No | 2020-05-30 09:00 | 2021-09-13 18:00 | 2020-08-01 09:00 | 2022-04-05 18:00 | [6 empty] | 18.7705 | 0 | [15 empty] | 23.7815 | 5.4778 | 538.7 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3512 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018721
1172 | Task(Task)-->C (Construction) | CIVIL | 1.9.3.1 | 1.9.3 | Unscheduled | No | No | 2020-05-30 09:00 | 2021-04-02 18:00 | 2020-08-01 09:00 | 2021-06-25 18:00 | [6 empty] | 36.1141 | 0 | [15 empty] | 25.0782 | 1.3737 | 134.71 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3513 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018722
1173 | Task(Task)-->C (Construction) | AVAILABILITY OF FRONT BY NTPC |  | 1.9.3.1 | Unscheduled | No | No | 2020-05-30 09:00 | 2020-05-30 18:00 | 2020-08-01 09:00 | 2020-08-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3514 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018723
1174 | Task(Task)-->C (Construction) | APPROACH IN PIPE CONVEYOR CORRIDOR |  | 1.9.3.1 | Unscheduled | No | No | 2020-05-31 | 2021-02-14 23:59 | 2020-08-02 | 2021-04-18 23:59 | [6 empty] | 50 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5609 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018724
1175 | Task(Task)-->C (Construction) | EXCAVATION |  | 1.9.3.1 | Unscheduled | No | No | 2020-06-29 09:00 | 2021-03-15 18:00 | 2020-08-05 09:00 | 2021-04-21 18:00 | [6 empty] | 38.8462 | 0 | [15 empty] | 9.6875 | 0.13308 | 13.05 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 48921 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3515 | 0 | 4 | Low | Niharendu Kamle | [6 empty] | 0 | 0 | [222 empty] | Excavation | [21 empty] | 1018725
1176 | Task(Task)-->C (Construction) | PCC |  | 1.9.3.1 | Unscheduled | No | No | 2020-07-02 09:00 | 2021-03-18 18:00 | 2020-09-24 09:00 | 2021-06-10 18:00 | [6 empty] | 37.6923 | 0 | [15 empty] | 5.8348 | 0.080154 | 7.86 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 870 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3516 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | PCC | [21 empty] | 1018726
1177 | Task(Task)-->C (Construction) | FOUNDATIONS - RAFT |  | 1.9.3.1 | Unscheduled | No | No | 2020-07-03 09:00 | 2021-03-19 18:00 | 2020-09-25 09:00 | 2021-06-11 18:00 | [6 empty] | 37.3077 | 0 | [15 empty] | 59.127 | 0.81224 | 79.65 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 3002 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3517 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018727
1178 | Task(Task)-->C (Construction) | PADESTALS FOR PC-1A & PC-1B CONV. STR. |  | 1.9.3.1 | Unscheduled | No | No | 2020-07-17 09:00 | 2021-04-02 18:00 | 2020-10-09 09:00 | 2021-06-25 18:00 | [6 empty] | 31.9231 | 0 | [15 empty] | 25.3508 | 0.34825 | 34.15 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 1287 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3518 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018728
1179 | Task(Task)-->C (Construction) | STRUCTURAL WORKS | 1.9.3.2 | 1.9.3 | Unscheduled | No | No | 2020-08-14 09:00 | 2021-04-30 18:00 | 2020-11-06 09:00 | 2021-07-23 18:00 | [6 empty] | 21.1538 | 0 | [15 empty] | 45.9193 | 2.5154 | 246.66 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3519 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018729
1180 | Task(Task)-->C (Construction) | ERECTION OF STRUCTURAL STEEL |  | 1.9.3.2 | Unscheduled | No | No | 2020-08-14 09:00 | 2021-04-30 18:00 | 2020-11-06 09:00 | 2021-07-23 18:00 | [6 empty] | 21.1538 | 0 | [15 empty] | 100 | 2.5154 | 246.66 | Plan & Actual | Quantity | Metric Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 3813 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3520 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018730
1181 | Task(Task)-->C (Construction) | MECHANICAL EQUIPMENT WORKS | 1.9.3.3 | 1.9.3 | Unscheduled | No | No | 2021-03-06 09:00 | 2021-06-04 18:00 | 2021-05-29 09:00 | 2021-09-05 23:59 | [6 empty] | 0 | 0 | [15 empty] | 8.7907 | 0.48153 | 47.22 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5463 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018731
1182 | Task(Task)-->C (Construction) | ERECTION OF TECHNOLOGICAL STR. & IDLERS |  | 1.9.3.3 | Unscheduled | No | No | 2021-03-06 09:00 | 2021-05-14 18:00 | 2021-05-29 09:00 | 2021-08-06 18:00 | [6 empty] | 0 | 0 | [15 empty] | 60.0042 | 0.28894 | 28.34 | Plan & Actual | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3521 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018732
1183 | Task(Task)-->C (Construction) | ERECTION OF PULLEYS WITH FRAME |  | 1.9.3.3 | Unscheduled | No | No | 2021-04-01 09:00 | 2021-04-21 18:00 | 2021-07-14 09:00 | 2021-08-03 18:00 | [6 empty] | 0 | 0 | [15 empty] | 10.3536 | 0.049856 | 4.89 | Plan & Actual | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5429 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018733
1184 | Task(Task)-->C (Construction) | ERECTION OF DRIVES (MOTOR, GEAR BOX, COUPLING) |  | 1.9.3.3 | Unscheduled | No | No | 2021-03-10 09:00 | 2021-04-08 18:00 | 2021-08-07 09:00 | 2021-09-05 23:59 | [6 empty] | 0 | 0 | [15 empty] | 11.751 | 0.056585 | 5.55 | Plan & Actual | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5427 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018734
1185 | Task(Task)-->C (Construction) | ERECTION OF TAKE-UP COMPONENTS |  | 1.9.3.3 | Unscheduled | No | No | 2021-05-01 09:00 | 2021-06-04 18:00 | 2021-07-24 09:00 | 2021-08-27 18:00 | [6 empty] | 0 | 0 | [15 empty] | 17.8912 | 0.086152 | 8.45 | Plan & Actual | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5428 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018735
1186 | Task(Task)-->C (Construction) | BELT LAYING & JOINTING WORK |  | 1.9.3 | Unscheduled | No | No | 2021-04-06 09:00 | 2021-08-03 18:00 | 2021-06-29 09:00 | 2021-10-26 18:00 | [6 empty] | 0 | 0 | [15 empty] | 8.8875 | 0.48684 | 47.74 | Plan & Actual | Quantity | Meter | 0 | 0 | 0 | 0 | 0 | 0 | 16400 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3522 | 0 | 3 | High | [7 empty] | 0 | 0 | [244 empty] | 1018736
1187 | Task(Task)-->C (Construction) | MAINTENANCE TROLLEY |  | 1.9.3 | Unscheduled | No | No | 2021-05-01 09:00 | 2021-05-14 18:00 | 2022-01-23 | 2022-02-05 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0.053988 | 0.002957 | 0.29 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5475 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018737
1188 | Task(Task)-->C (Construction) | ELECTRICAL & INSTRUMENTATION | 1.9.3.6 | 1.9.3 | Unscheduled | No | No | 2021-03-30 09:00 | 2021-08-30 18:00 | 2021-06-22 09:00 | 2022-03-22 18:00 | [6 empty] | 0 | 0 | [15 empty] | 11.2704 | 0.61737 | 60.54 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3523 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018738
1189 | Task(Task)-->C (Construction) | CABLE TRAY |  | 1.9.3.6 | Unscheduled | No | No | 2021-04-13 09:00 | 2021-05-14 18:00 | 2021-07-06 09:00 | 2021-08-06 18:00 | [6 empty] | 0 | 0 | [15 empty] | 22.0185 | 0.13594 | 13.33 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 31200 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3524 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018739
1190 | Task(Task)-->C (Construction) | POWER CABLE |  | 1.9.3.6 | Unscheduled | No | No | 2021-05-15 09:00 | 2021-05-31 18:00 | 2021-08-27 09:00 | 2021-09-12 23:59 | [6 empty] | 0 | 0 | [15 empty] | 16.0555 | 0.099121 | 9.72 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 68645 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3525 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018740
1191 | Task(Task)-->C (Construction) | CONTROL CABLE |  | 1.9.3.6 | Unscheduled | No | No | 2021-05-29 09:00 | 2021-05-31 18:00 | 2021-09-25 09:00 | 2021-09-27 18:00 | [6 empty] | 0 | 0 | [15 empty] | 5.3023 | 0.032734 | 3.21 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 22700 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3526 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018741
1192 | Task(Task)-->C (Construction) | EARTHING |  | 1.9.3.6 | Unscheduled | No | No | 2021-04-21 09:00 | 2021-05-14 18:00 | 2021-07-14 09:00 | 2021-08-06 18:00 | [6 empty] | 0 | 0 | [15 empty] | 8.6224 | 0.053232 | 5.22 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 23400 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3527 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018742
1193 | Task(Task)-->C (Construction) | EARTH PIT |  | 1.9.3.6 | Unscheduled | No | No | 2021-03-30 09:00 | 2021-04-02 18:00 | 2021-06-22 09:00 | 2021-06-25 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5313 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018743
1194 | Task(Task)-->C (Construction) | FIELD INTRUMENTS |  | 1.9.3.6 | Unscheduled | No | No | 2021-05-30 | 2021-06-01 18:00 | 2021-09-26 | 2021-09-28 18:00 | [6 empty] | 0 | 0 | [15 empty] | 45.1437 | 0.2787 | 27.33 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5315 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018744
1195 | Task(Task)-->C (Construction) | MOTOR TERMINATION |  | 1.9.3.6 | Unscheduled | No | No | 2021-05-29 09:00 | 2021-06-01 18:00 | 2021-09-10 09:00 | 2021-09-13 18:00 | [6 empty] | 0 | 0 | [15 empty] | 2.1308 | 0.013155 | 1.29 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5316 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018745
1196 | Task(Task)-->C (Construction) | NO LOAD RUN OF MOTOR |  | 1.9.3.6 | Unscheduled | No | No | 2021-08-27 09:00 | 2021-08-30 18:00 | 2022-03-19 09:00 | 2022-03-22 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0.72679 | 0.004487 | 0.44 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5464 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018746
1197 | Task(Task)-->C (Construction) | NO LOAD COMMISSIONING & SYSTEM READYNESS FOR LOAD & TRIAL OPERATION |  | 1.9.3 | Unscheduled | No | No | 2021-08-31 09:00 | 2021-09-13 18:00 | 2022-03-23 09:00 | 2022-04-05 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5317 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018747
1198 | Task(Task)-->E (Engineering) | KDTP-3 & DRIVE HOUSE-2 | 1.10 | 1 | Work In Progress | No | No | 2019-11-22 18:00 | 2021-09-08 18:00 | 2020-03-11 09:00 | 2022-03-06 23:59 |  |  | 2020-02-21 14:04 |  |  |  | 61.1841 | 6.6056 | [15 empty] | 2.0178 | 2.0178 | 198.44 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3528 | 0 | 1 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018748
1199 | Task(Task)-->E (Engineering) | ENGINEERING | 1.10.1 | 1.10 | Work In Progress | No | No | 2019-11-22 18:00 | 2020-07-14 17:40 | 2020-04-15 18:00 | 2020-09-27 23:59 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 86.9204 | [15 empty] | 2.575 | 0.051958 | 5.11 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3529 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018749
1200 | Task(Task)-->E (Engineering) | MECHANICAL | 1.10.1.1 | 1.10.1 | Unscheduled | No | No | 2019-11-22 18:00 | 2020-01-25 17:40 | 2020-04-15 18:00 | 2020-06-04 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 80 | [15 empty] | 8.3984 | 0.004364 | 0.43 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3530 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036098
1201 | Task(Task)-->E (Engineering) | G.A & LOAD DATA OF TRANSFER POINT KDTP-3 |  | 1.10.1.1 | Unscheduled | No | No | 2019-11-22 18:00 | 2020-01-25 17:40 | 2020-04-15 18:00 | 2020-06-04 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-0011 |  | 2020-02-13 10:26 | 7012-155-PVM-B-011 |  |  |  | A |  |  |  | 100 | 0.004364 | 0.43 | Plan & Actual | Date |  | 0 | 0 | 0 | 160 | 0 | 72 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3531 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-11-22 18:00 | 2020-04-15 18:00 |  | 10 | 2020-04-15 23:31 |  |  | 2019-12-18 17:40 | 2020-04-20 18:00 |  | 30 | 2020-04-22 23:31 |  |  | 2019-12-24 17:40 | 2020-04-23 18:00 |  | 35 | 2020-04-25 23:31 |  |  | 2019-12-30 23:59 | 2020-04-30 18:00 |  | 65 | 2020-05-02 23:31 |  |  | 2020-01-04 17:40 | 2020-05-21 18:00 |  | 80 | 2020-05-21 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-01-25 17:40 | 2020-06-04 18:00 |  | 100 | [122 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 11 |  |  |  | 101025
1202 | Task(Task)-->E (Engineering) | CIVIL | 1.10.1.2 | 1.10.1 | Work In Progress | No | No | 2020-02-07 18:00 | 2020-05-30 17:40 | 2020-07-04 18:00 | 2020-09-27 23:59 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 89.7666 | [15 empty] | 47.6562 | 0.024761 | 2.44 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3537 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036099
1203 | Task(Task)-->E (Engineering) | TRANSFER POINT KDTP-3 - DESIGN CALCULATION OF SUPER STRUCTURE |  | 1.10.1.2 | Completed | No | No | 2020-02-07 18:00 | 2020-04-07 17:40 | 2020-08-07 09:00 | 2020-09-01 18:00 |  |  | 2020-02-21 15:37 | 2020-09-02 00:38 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-DC-0012 |  | 2020-02-13 11:41 | 7012-155-PVC-U-034 |  |  |  | A |  |  |  | 47.4419 | 0.011747 | 1.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 377.29 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3541 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-07 18:00 | 2020-04-30 18:00 |  | 10 |  |  |  | 2020-02-26 17:40 | 2020-05-20 18:00 |  | 30 |  |  |  | 2020-03-03 17:40 | 2020-05-23 18:00 |  | 35 |  |  |  | 2020-03-09 23:59 | 2020-05-30 18:00 |  | 65 | 2020-08-13 19:54 |  |  | 2020-03-16 17:40 | 2020-06-20 18:00 |  | 80 | 2020-09-01 23:24 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-07 17:40 | 2020-07-04 18:00 |  | 100 | 2020-09-02 00:39 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 135 |  |  |  | 101149
1204 | Task(Task)-->E (Engineering) | TRANSFER POINT KDTP-3 - DESIGN CALCULATION OF SUB STRUCTURE |  | 1.10.1.2 | Completed | No | No | 2020-03-13 18:00 | 2020-05-12 17:40 | 2020-08-18 09:00 | 2020-09-08 18:00 |  |  | 2020-02-21 15:37 | 2020-09-10 23:14 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-DC-0013 |  | 2020-02-13 11:41 | 7012-155-PVC-U-035 |  |  |  | A |  |  |  | 26.5116 | 0.006565 | 0.57 | Plan & Actual | Date |  | 0 | 0 | 0 | 212.29 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3542 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-13 18:00 | 2020-05-30 18:00 |  | 10 |  |  |  | 2020-03-31 17:40 | 2020-06-19 18:00 |  | 30 |  |  |  | 2020-04-06 17:40 | 2020-06-22 18:00 |  | 35 |  |  |  | 2020-04-13 23:59 | 2020-06-29 18:00 |  | 65 | 2020-08-18 18:00 |  |  | 2020-04-18 17:40 | 2020-07-20 18:00 |  | 80 | 2020-09-10 22:45 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-12 17:40 | 2020-08-03 18:00 |  | 100 | 2020-09-10 23:15 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 136 |  |  |  | 101150
1205 | Task(Task)-->E (Engineering) | TRANSFER POINT KDTP-3 - NUM & RC DETAILS OF FDN |  | 1.10.1.2 | Completed | No | No | 2020-03-13 18:00 | 2020-05-12 17:40 | 2020-08-18 09:00 | 2020-09-09 18:00 |  |  | 2020-02-21 15:37 | 2020-09-10 23:14 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-NR-0014 |  | 2020-02-13 11:41 | 7012-155-PVC-C-037 |  |  |  | A |  |  |  | 15.814 | 0.003916 | 0.34 | Plan & Actual | Date |  | 0 | 0 | 0 | 127.29 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3538 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-13 18:00 | 2020-05-30 18:00 |  | 10 |  |  |  | 2020-03-31 17:40 | 2020-06-19 18:00 |  | 30 |  |  |  | 2020-04-06 17:40 | 2020-06-22 18:00 |  | 35 | 2020-08-17 18:46 |  |  | 2020-04-13 23:59 | 2020-06-29 18:00 |  | 65 | 2020-08-18 18:00 |  |  | 2020-04-18 17:40 | 2020-07-20 18:00 |  | 80 | 2020-09-10 22:41 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-12 17:40 | 2020-08-03 18:00 |  | 100 | 2020-09-10 23:15 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 138 |  |  |  | 101152
1206 | Task(Task)-->E (Engineering) | TRANSFER POINT KDTP-3 - NUM & RC DETAILS OF FLOOR SLABS |  | 1.10.1.2 | Unscheduled | No | No | 2020-03-31 18:00 | 2020-05-30 17:40 | 2020-07-04 18:00 | 2020-09-07 18:00 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-NR-0015 |  | 2020-02-13 11:41 | 7012-155-PVC-C-038 |  |  |  | A |  |  |  | 5.1163 | 0.001267 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 42.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3539 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-31 18:00 | 2020-07-04 18:00 |  | 10 |  |  |  | 2020-04-18 17:40 | 2020-07-24 18:00 |  | 30 |  |  |  | 2020-04-24 17:40 | 2020-07-27 18:00 |  | 35 |  |  |  | 2020-05-01 23:59 | 2020-08-03 18:00 |  | 65 |  |  |  | 2020-05-07 17:40 | 2020-08-24 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-30 17:40 | 2020-09-07 18:00 |  | 100 | [122 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 139 |  |  |  | 101153
1207 | Task(Task)-->E (Engineering) | TRANSFER POINT KDTP-3 - NUM & RC DETAILS OF GRADE SLAB |  | 1.10.1.2 | Unscheduled | No | No | 2020-03-31 18:00 | 2020-05-30 17:40 | 2020-07-24 18:00 | 2020-09-27 23:59 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-NR-0016 |  | 2020-02-13 11:41 | 7012-155-PVC-C-039 |  |  |  | A |  |  |  | 5.1163 | 0.001267 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 42.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3540 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-31 18:00 | 2020-07-24 18:00 |  | 10 |  |  |  | 2020-04-18 17:40 | 2020-08-13 18:00 |  | 30 |  |  |  | 2020-04-24 17:40 | 2020-08-16 23:59 |  | 35 |  |  |  | 2020-05-01 23:59 | 2020-08-23 23:59 |  | 65 |  |  |  | 2020-05-07 17:40 | 2020-09-13 23:59 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-30 17:40 | 2020-09-27 23:59 |  | 100 | [122 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 140 |  |  |  | 101154
1208 | Task(Task)-->E (Engineering) | STRUCTURAL | 1.10.1.3 | 1.10.1 | Work In Progress | No | No | 2020-02-07 18:00 | 2020-07-14 17:40 | 2020-07-09 18:00 | 2020-09-17 18:00 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 90.2677 | [15 empty] | 22.0703 | 0.011467 | 1.13 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3543 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036100
1209 | Task(Task)-->E (Engineering) | TRANSFER POINT KDTP-3 - STRUCTURAL GA |  | 1.10.1.3 | Completed | No | No | 2020-02-07 18:00 | 2020-04-07 17:40 | 2020-08-07 09:00 | 2020-09-01 18:00 |  |  | 2020-02-21 15:37 | 2020-09-02 00:38 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-GA-0008 |  | 2020-02-13 11:41 | 7012-155-PVC-B-036 |  |  |  | A |  |  |  | 90.2655 | 0.010351 | 1.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 377.29 | 0 | 35.3 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3545 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-07 18:00 | 2020-04-30 18:00 |  | 10 |  |  |  | 2020-02-26 17:40 | 2020-05-20 18:00 |  | 30 |  |  |  | 2020-03-03 17:40 | 2020-05-23 18:00 |  | 35 | 2020-08-06 10:50 |  |  | 2020-03-09 23:59 | 2020-05-30 18:00 |  | 65 | 2020-08-13 19:54 |  |  | 2020-03-16 17:40 | 2020-06-20 18:00 |  | 80 | 2020-09-01 23:25 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-07 17:40 | 2020-07-04 18:00 |  | 100 | 2020-09-02 00:39 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 137 |  |  |  | 101151
1210 | Task(Task)-->E (Engineering) | ARCHITECTURAL GA OF TRANSFER POINT KDTP-3 |  | 1.10.1.3 | Unscheduled | No | No | 2020-05-15 18:00 | 2020-07-14 17:40 | 2020-07-09 18:00 | 2020-09-17 18:00 |  |  | 2020-02-21 15:39 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-AR-0005 |  | 2020-02-13 11:43 | 7012-155-PVC-C-111 |  |  |  | I |  |  |  | 9.7345 | 0.001116 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 40.52 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3544 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-05-15 18:00 | 2020-07-09 18:00 |  | 10 |  |  |  | 2020-06-02 17:40 | 2020-08-03 18:00 |  | 30 |  |  |  | 2020-06-08 17:40 | 2020-08-06 18:00 |  | 35 |  |  |  | 2020-06-15 23:59 | 2020-08-13 18:00 |  | 65 |  |  |  | 2020-06-20 17:40 | 2020-09-03 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-07-14 17:40 | 2020-09-17 18:00 |  | 100 | [122 empty] | Chetan Khodke |  |  |  |  | A - Architecture | [16 empty] | 212 |  |  |  | 101222
1211 | Task(Task)-->E (Engineering) | ELECTRICAL | 1.10.1.4 | 1.10.1 | Unscheduled | No | No | 2020-02-06 18:00 | 2020-06-02 17:40 | 2020-04-22 18:00 | 2020-06-18 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 | [15 empty] | 21.875 | 0.011366 | 1.12 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3548 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036101
1212 | Task(Task)-->E (Engineering) | EQUIPMENT, CABLE ROUTING, EARTHING & LIGHTNING LAYOUT WITH PLAN, SECTIONAL VIEWS & BOM OF KDTP-3 |  | 1.10.1.4 | Unscheduled | No | No | 2020-02-06 18:00 | 2020-04-03 17:40 | 2020-04-22 18:00 | 2020-06-18 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5056 |  | 2020-02-13 11:44 | 7012-155-PVE-F-018 |  |  |  | A |  |  |  | 40.1786 | 0.004567 | 0.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 165.48 | 0 | 13.45 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3549 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-06 18:00 | 2020-04-22 18:00 |  | 10 | 2020-04-22 23:31 |  |  | 2020-02-21 17:40 | 2020-05-06 18:00 |  | 30 | 2020-06-02 23:31 |  |  | 2020-02-28 17:40 | 2020-05-13 18:00 |  | 35 | 2020-06-19 12:47 |  |  | 2020-03-05 23:59 | 2020-05-20 18:00 |  | 65 | 2020-08-03 11:16 |  |  | 2020-03-11 17:40 | 2020-06-10 18:00 |  | 80 | 2020-08-03 11:27 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-03 17:40 | 2020-06-10 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 253 |  |  |  | 101264
1213 | Task(Task)-->E (Engineering) | LIGHTING LAYOUT PLAN WITH POWER DISTRIBUTION ARRANGEMENT, SECTIONAL VIEW, BOM OF KDTP-3 |  | 1.10.1.4 | Unscheduled | No | No | 2020-04-13 18:00 | 2020-06-02 17:40 | 2020-05-07 18:00 | 2020-06-18 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5067 |  | 2020-02-13 11:44 | 7012-155-PVE-G-029 |  |  |  | A |  |  |  | 59.8214 | 0.006799 | 0.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 248.42 | 0 | 24.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3550 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-13 18:00 | 2020-05-07 18:00 |  | 10 | 2020-05-04 23:31 |  |  | 2020-04-21 17:40 | 2020-05-14 18:00 |  | 30 | 2020-05-14 23:31 |  |  | 2020-04-28 17:40 | 2020-05-21 18:00 |  | 35 | 2020-05-21 23:31 |  |  | 2020-05-04 23:59 | 2020-05-28 18:00 |  | 65 | 2020-05-22 23:31 |  |  | 2020-05-11 17:40 | 2020-06-18 18:00 |  | 80 | 2020-06-17 14:58 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-02 17:40 | 2020-06-18 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 264 |  |  |  | 101275
1214 | Task(Task)-->P (Procurement) | PROCUREMENT | 1.10.2 | 1.10 | Work In Progress | No | No | 2020-02-06 09:00 | 2021-02-13 18:00 | 2020-03-11 09:00 | 2021-05-13 18:00 |  |  | 2020-03-11 10:57 |  |  |  | 91.9309 | 9.018 | [15 empty] | 48.4303 | 0.97724 | 96.11 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3553 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018754
1215 | Task(Task)-->P (Procurement) | PURCHASE REQUISITION | 1.10.2.1 | 1.10.2 | Work In Progress | No | No | 2020-02-06 09:00 | 2020-03-27 18:00 | 2020-03-11 09:00 | 2020-05-29 18:00 |  |  | 2020-03-11 10:57 |  |  |  | 100 | 28.397 | [15 empty] | 5.0042 | 0.048903 | 4.81 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3554 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018755
1216 | Task(Task)-->P (Procurement) | Flap Gate |  | 1.10.2.1 | Completed | No | No | 2020-02-06 09:00 | 2020-02-06 18:00 | 2020-03-20 09:00 | 2020-03-20 18:00 |  |  | 2020-03-20 10:57 | 2020-03-20 10:57 |  |  | 100 | 100 | [15 empty] | 2.8398 | 0.001389 | 0.14 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3555 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018756
1217 | Task(Task)-->P (Procurement) | Chute & Skirt |  | 1.10.2.1 | Completed | No | No | 2020-03-10 09:00 | 2020-03-10 18:00 | 2020-03-11 09:00 | 2020-03-11 18:00 |  |  | 2020-03-11 10:57 | 2020-03-11 10:57 |  |  | 100 | 100 | [15 empty] | 17.6471 | 0.00863 | 0.87 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3556 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018757
1218 | Task(Task)-->P (Procurement) | Building Structure |  | 1.10.2.1 | Unscheduled | No | No | 2020-03-09 09:00 | 2020-03-09 18:00 | 2020-05-29 09:00 | 2020-05-29 18:00 | [6 empty] | 100 | 0 | [15 empty] | 71.6024 | 0.035016 | 3.53 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3557 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018758
1219 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.10.2.1 | Completed | No | No | 2020-03-10 09:00 | 2020-03-10 18:00 | 2020-03-16 09:00 | 2020-03-16 18:00 |  |  | 2020-03-16 10:57 | 2020-03-16 10:57 |  |  | 100 | 100 | [15 empty] | 5.4767 | 0.002678 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3558 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018759
1220 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.10.2.1 | Completed | No | No | 2020-03-27 09:00 | 2020-03-27 18:00 | 2020-04-30 09:00 | 2020-04-30 18:00 |  |  | 2020-04-30 10:57 | 2020-04-30 10:57 |  |  | 100 | 100 | [15 empty] | 2.4341 | 0.00119 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3559 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018760
1221 | Task(Task)-->P (Procurement) | TECHNICAL CLEARANCE | 1.10.2.2 | 1.10.2 | Work In Progress | No | No | 2020-02-07 09:00 | 2020-05-11 18:00 | 2020-03-11 09:00 | 2020-06-03 18:00 |  |  | 2020-03-17 10:57 |  |  |  | 100 | 28.397 | [15 empty] | 5.0042 | 0.048903 | 4.81 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3562 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018761
1222 | Task(Task)-->P (Procurement) | Flap Gate |  | 1.10.2.2 | Completed | No | No | 2020-02-07 09:00 | 2020-03-22 23:59 | 2020-03-20 09:00 | 2020-04-28 18:00 |  |  | 2020-04-28 10:57 | 2020-04-28 10:57 |  |  | 100 | 100 | [15 empty] | 2.8398 | 0.001389 | 0.14 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3563 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018762
1223 | Task(Task)-->P (Procurement) | Chute & Skirt |  | 1.10.2.2 | Completed | No | No | 2020-03-11 09:00 | 2020-03-20 18:00 | 2020-03-11 09:00 | 2020-03-17 18:00 |  |  | 2020-03-17 10:57 | 2020-03-17 10:57 |  |  | 100 | 100 | [15 empty] | 17.6471 | 0.00863 | 0.87 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3564 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018763
1224 | Task(Task)-->P (Procurement) | Building Structure |  | 1.10.2.2 | Unscheduled | No | No | 2020-03-10 09:00 | 2020-03-16 18:00 | 2020-05-29 09:00 | 2020-05-29 18:00 | [6 empty] | 100 | 0 | [15 empty] | 71.6024 | 0.035016 | 3.53 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3565 | 1 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018764
1225 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.10.2.2 | Completed | No | No | 2020-03-11 09:00 | 2020-03-25 18:00 | 2020-03-16 09:00 | 2020-06-02 18:00 |  |  | 2020-06-02 10:57 | 2020-06-02 10:57 |  |  | 100 | 100 | [15 empty] | 5.4767 | 0.002678 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3566 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018765
1226 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.10.2.2 | Completed | No | No | 2020-03-28 09:00 | 2020-05-11 18:00 | 2020-04-30 09:00 | 2020-06-03 18:00 |  |  | 2020-06-03 10:57 | 2020-06-03 10:57 |  |  | 100 | 100 | [15 empty] | 2.4341 | 0.00119 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3567 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018766
1227 | Task(Task)-->P (Procurement) | ORDERING | 1.10.2.3 | 1.10.2 | Work In Progress | No | No | 2020-03-17 09:00 | 2020-06-25 18:00 | 2020-03-17 09:00 | 2020-08-22 18:00 |  |  | 2020-03-18 12:49 |  |  |  | 100 | 28.3254 | [15 empty] | 9.9979 | 0.097704 | 9.61 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3570 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018767
1228 | Task(Task)-->P (Procurement) | Flap Gate |  | 1.10.2.3 | Completed | No | No | 2020-03-23 09:00 | 2020-04-21 18:00 | 2020-04-28 09:00 | 2020-08-22 18:00 |  |  | 2020-04-28 16:13 | 2020-08-22 16:13 |  |  | 100 | 100 | [15 empty] | 2.9442 | 0.002877 | 0.29 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3571 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018768
1229 | Task(Task)-->P (Procurement) | Chute & Skirt |  | 1.10.2.3 | Completed | No | No | 2020-03-21 09:00 | 2020-04-19 23:59 | 2020-03-17 09:00 | 2020-07-06 18:00 |  |  | 2020-03-18 12:49 | 2020-07-06 12:49 |  |  | 100 | 100 | [15 empty] | 17.5635 | 0.01716 | 1.73 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3572 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018769
1230 | Task(Task)-->P (Procurement) | Building Structure |  | 1.10.2.3 | Unscheduled | No | No | 2020-03-17 09:00 | 2020-04-15 18:00 | 2020-05-29 09:00 | 2020-07-28 18:00 | [6 empty] | 100 | 0 | [15 empty] | 71.6751 | 0.070029 | 7.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3573 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018770
1231 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.10.2.3 | Completed | No | No | 2020-03-26 09:00 | 2020-04-10 18:00 | 2020-06-02 09:00 | 2020-07-31 18:00 |  |  | 2020-06-03 15:51 | 2020-06-29 15:51 |  |  | 100 | 100 | [15 empty] | 5.3807 | 0.005257 | 0.53 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3574 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018771
1232 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.10.2.3 | Completed | No | No | 2020-05-12 09:00 | 2020-06-25 18:00 | 2020-06-03 09:00 | 2020-06-24 18:00 |  |  | 2020-06-15 10:57 | 2020-06-15 10:57 |  |  | 100 | 100 | [15 empty] | 2.4365 | 0.002381 | 0.24 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3575 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018772
1233 | Task(Task)-->P (Procurement) | ITP APPROVAL | 1.10.2.4 | 1.10.2 | Work In Progress | No | No | 2020-04-11 09:00 | 2020-08-04 18:00 | 2020-06-23 09:00 | 2020-10-30 18:00 |  |  | 2020-06-23 17:42 |  |  |  | 100 | 5.4761 | [15 empty] | 5.0042 | 0.048903 | 4.81 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3578 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018773
1234 | Task(Task)-->P (Procurement) | Flap Gate |  | 1.10.2.4 | Unscheduled | No | No | 2020-04-22 09:00 | 2020-05-31 23:59 | 2020-08-22 09:00 | 2020-10-30 18:00 |  |  | 2020-08-22 16:16 |  |  |  | 100 | 0 | [15 empty] | 2.8398 | 0.001389 | 0.14 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3579 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018774
1235 | Task(Task)-->P (Procurement) | Chute & Skirt |  | 1.10.2.4 | Unscheduled | No | No | 2020-04-20 09:00 | 2020-05-29 18:00 | 2020-07-06 09:00 | 2020-07-16 18:00 | [6 empty] | 100 | 0 | [15 empty] | 17.6471 | 0.00863 | 0.87 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3580 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018775
1236 | Task(Task)-->P (Procurement) | Building Structure |  | 1.10.2.4 | Unscheduled | No | No | 2020-04-16 09:00 | 2020-04-22 18:00 | 2020-07-28 09:00 | 2020-08-03 18:00 | [6 empty] | 100 | 0 | [15 empty] | 71.6024 | 0.035016 | 3.53 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3581 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018776
1237 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.10.2.4 | Completed | No | No | 2020-04-11 09:00 | 2020-05-20 18:00 | 2020-07-28 09:00 | 2020-09-08 18:00 |  |  | 2020-07-08 17:23 | 2020-09-08 17:23 |  |  | 100 | 100 | [15 empty] | 5.4767 | 0.002678 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3582 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018777
1238 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.10.2.4 | Unscheduled | No | No | 2020-06-26 09:00 | 2020-08-04 18:00 | 2020-06-23 09:00 | 2020-09-08 18:00 |  |  | 2020-06-23 17:42 |  |  |  | 100 | 0 | [15 empty] | 2.4341 | 0.00119 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3583 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018778
1239 | Task(Task)-->P (Procurement) | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE | 1.10.2.5 | 1.10.2 | Work In Progress | No | No | 2020-04-11 09:00 | 2020-09-16 18:00 | 2020-05-30 09:00 | 2020-10-16 18:00 |  |  | 2020-06-18 17:12 |  |  |  | 100 | 20.4637 | [15 empty] | 15.0021 | 0.14661 | 14.42 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3586 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018779
1240 | Task(Task)-->P (Procurement) | Flap Gate |  | 1.10.2.5 | Unscheduled | No | No | 2020-04-22 09:00 | 2020-06-20 18:00 | 2020-08-22 09:00 | 2020-10-15 18:00 |  |  | 2020-08-22 16:15 |  |  |  | 100 | 15 | [15 empty] | 2.9093 | 0.004265 | 0.43 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3587 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018780
1241 | Task(Task)-->P (Procurement) | Chute & Skirt |  | 1.10.2.5 | Completed | No | No | 2020-04-20 09:00 | 2020-09-16 18:00 | 2020-07-06 09:00 | 2020-07-06 18:00 |  |  | 2020-07-06 12:51 | 2020-07-06 12:51 |  |  | 100 | 100 | [15 empty] | 17.5913 | 0.02579 | 2.6 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3588 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018781
1242 | Task(Task)-->P (Procurement) | Building Structure |  | 1.10.2.5 | Unscheduled | No | No | 2020-04-14 09:00 | 2020-04-20 18:00 | 2020-07-28 09:00 | 2020-08-25 18:00 | [6 empty] | 100 | 0 | [15 empty] | 71.6509 | 0.10504 | 10.59 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3589 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018782
1243 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.10.2.5 | Unscheduled | No | No | 2020-04-11 09:00 | 2020-05-25 18:00 | 2020-07-10 09:00 | 2020-10-16 18:00 |  |  | 2020-07-14 10:44 |  |  |  | 100 | 0 | [15 empty] | 5.4127 | 0.007935 | 0.8 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3590 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018783
1244 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.10.2.5 | Completed | No | No | 2020-06-26 09:00 | 2020-08-09 23:59 | 2020-05-30 09:00 | 2020-08-08 18:00 |  |  | 2020-06-18 17:12 | 2020-08-07 15:00 |  |  | 100 | 100 | [15 empty] | 2.4357 | 0.003571 | 0.36 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3591 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018784
1245 | Task(Task)-->P (Procurement) | MANUFACTURING & RECEIPT AT SITE (MRN) | 1.10.2.6 | 1.10.2 | Unscheduled | No | No | 2020-04-23 09:00 | 2021-02-13 18:00 | 2020-07-06 09:00 | 2021-05-13 18:00 |  |  | 2020-08-07 15:02 |  |  |  | 86.5487 | 0 | [15 empty] | 59.9875 | 0.58622 | 57.66 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3594 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018785
1246 | Task(Task)-->P (Procurement) | Flap Gate |  | 1.10.2.6 | Unscheduled | No | No | 2020-06-21 | 2021-01-01 18:00 | 2020-10-31 09:00 | 2021-05-13 18:00 | [6 empty] | 55.8974 | 0 | [15 empty] | 2.9093 | 0.017055 | 1.72 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3595 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018786
1247 | Task(Task)-->P (Procurement) | Chute & Skirt |  | 1.10.2.6 | Unscheduled | No | No | 2020-07-19 | 2021-02-13 18:00 | 2020-07-06 09:00 | 2021-01-31 23:59 | [6 empty] | 38.5714 | 0 | [15 empty] | 17.6083 | 0.10322 | 10.41 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3596 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018787
1248 | Task(Task)-->P (Procurement) | Building Structure |  | 1.10.2.6 | Unscheduled | No | No | 2020-04-23 09:00 | 2020-10-05 18:00 | 2020-08-25 09:00 | 2021-03-31 18:00 | [6 empty] | 100 | 0 | [15 empty] | 71.634 | 0.41993 | 42.35 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3597 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018788
1249 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.10.2.6 | Unscheduled | No | No | 2020-05-26 09:00 | 2020-10-21 18:00 | 2020-10-17 09:00 | 2021-03-14 23:59 | [6 empty] | 90.604 | 0 | [15 empty] | 5.3958 | 0.031631 | 3.19 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3598 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018789
1250 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.10.2.6 | Unscheduled | No | No | 2020-08-10 09:00 | 2020-11-07 18:00 | 2020-09-09 09:00 | 2020-12-07 18:00 |  |  | 2020-08-07 15:02 |  |  |  | 65.5556 | 0 | [15 empty] | 2.4526 | 0.014378 | 1.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3599 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018790
1251 | Task(Task)-->C (Construction) | CONSTRUCTION | 1.10.3 | 1.10 | Unscheduled | No | No | 2020-04-27 09:00 | 2021-09-08 18:00 | 2020-09-03 09:00 | 2022-03-06 23:59 | [6 empty] | 28.7516 | 0 | [15 empty] | 48.9947 | 0.98863 | 97.23 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3602 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018791
1252 | Task(Task)-->C (Construction) | CIVIL | 1.10.3.1 | 1.10.3 | Unscheduled | No | No | 2020-04-27 09:00 | 2021-05-05 18:00 | 2020-09-03 09:00 | 2021-09-28 18:00 | [6 empty] | 34.0151 | 0 | [15 empty] | 44.7645 | 0.44255 | 43.52 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3603 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018792
1253 | Task(Task)-->C (Construction) | AVAILABILITY OF FRONT BY NTPC |  | 1.10.3.1 | Unscheduled | No | No | 2020-04-27 09:00 | 2020-04-27 18:00 | 2020-09-03 09:00 | 2020-09-03 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3604 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018793
1254 | Task(Task)-->C (Construction) | EXCAVATION |  | 1.10.3.1 | Unscheduled | No | No | 2020-05-04 09:00 | 2020-06-03 18:00 | 2020-09-10 09:00 | 2020-10-10 18:00 | [6 empty] | 100 | 0 | [15 empty] | 5.7228 | 0.025327 | 2.49 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 9335 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3605 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | Excavation | [21 empty] | 1018794
1255 | Task(Task)-->C (Construction) | PCC |  | 1.10.3.1 | Unscheduled | No | No | 2020-05-25 09:00 | 2020-05-29 18:00 | 2020-10-01 09:00 | 2020-10-05 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.85038 | 0.003763 | 0.37 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3606 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | PCC | [21 empty] | 1018795
1256 | Task(Task)-->C (Construction) | RAFT |  | 1.10.3.1 | Unscheduled | No | No | 2020-05-30 09:00 | 2020-06-14 23:59 | 2020-10-06 09:00 | 2020-10-21 18:00 | [6 empty] | 100 | 0 | [15 empty] | 15.7895 | 0.069877 | 6.87 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 259 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3607 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018796
1257 | Task(Task)-->C (Construction) | PADESTALS FOR KDTP-3 STR. |  | 1.10.3.1 | Unscheduled | No | No | 2020-06-15 09:00 | 2020-07-10 18:00 | 2020-10-22 09:00 | 2020-11-16 18:00 | [6 empty] | 100 | 0 | [15 empty] | 3.6543 | 0.016172 | 1.59 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3608 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018797
1258 | Task(Task)-->C (Construction) | RCC FLOOR FOR TAIL PULLEY OF SY-1A/B |  | 1.10.3.1 | Unscheduled | No | No | 2020-11-06 09:00 | 2020-11-21 18:00 | 2021-03-15 09:00 | 2021-03-30 18:00 | [6 empty] | 0 | 0 | [15 empty] | 3.9531 | 0.017495 | 1.72 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3610 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018798
1259 | Task(Task)-->C (Construction) | RCC FLOOR FOR HEAD PULLEY OF PC-2A/B |  | 1.10.3.1 | Unscheduled | No | No | 2021-02-04 09:00 | 2021-02-22 18:00 | 2021-06-30 09:00 | 2021-07-18 23:59 | [6 empty] | 0 | 0 | [15 empty] | 3.9531 | 0.017495 | 1.72 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3611 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018799
1260 | Task(Task)-->C (Construction) | DRIVE HOUSE FOUNDATION |  | 1.10.3.1 | Unscheduled | No | No | 2020-06-13 09:00 | 2020-07-13 18:00 | 2020-10-20 09:00 | 2020-11-19 18:00 | [6 empty] | 100 | 0 | [15 empty] | 3.4245 | 0.015155 | 1.49 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3612 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018800
1261 | Task(Task)-->C (Construction) | HGTU FOUNDATION OF PC-2A/B |  | 1.10.3.1 | Unscheduled | No | No | 2020-06-27 09:00 | 2020-07-27 18:00 | 2020-11-03 09:00 | 2020-12-03 18:00 | [6 empty] | 100 | 0 | [15 empty] | 4.5737 | 0.020241 | 1.99 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5470 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018801
1262 | Task(Task)-->C (Construction) | GRADE SLAB FLOOR |  | 1.10.3.1 | Unscheduled | No | No | 2021-04-05 09:00 | 2021-05-05 18:00 | 2021-08-29 | 2021-09-28 18:00 | [6 empty] | 0 | 0 | [15 empty] | 58.0786 | 0.25703 | 25.27 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 1350 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3613 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018802
1263 | Task(Task)-->C (Construction) | STRUCTURAL WORKS | 1.10.3.2 | 1.10.3 | Unscheduled | No | No | 2020-08-08 09:00 | 2021-04-04 23:59 | 2020-12-15 09:00 | 2021-08-28 18:00 | [6 empty] | 31.799 | 0 | [15 empty] | 42.5324 | 0.42049 | 41.35 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3614 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018803
1264 | Task(Task)-->C (Construction) | STRUCTURAL WORKS FOR TAIL PULLEY FLOOR OF SY-1A/B |  | 1.10.3.2 | Unscheduled | No | No | 2020-08-08 09:00 | 2020-11-05 18:00 | 2020-12-15 09:00 | 2021-03-14 23:59 | [6 empty] | 67.7778 | 0 | [15 empty] | 46.9166 | 0.19728 | 19.4 | Plan & Actual | Quantity | Metric Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3615 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018804
1265 | Task(Task)-->C (Construction) | STRUCTURAL WORKS FOR HEAD PULLEY FLOOR OF PCN-2A/B |  | 1.10.3.2 | Unscheduled | No | No | 2020-11-06 09:00 | 2021-02-03 18:00 | 2021-04-01 09:00 | 2021-06-29 18:00 | [6 empty] | 0 | 0 | [15 empty] | 46.9166 | 0.19728 | 19.4 | Plan & Actual | Quantity | Metric Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5466 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018805
1266 | Task(Task)-->C (Construction) | BALANCE STRUCTURAL WORKS |  | 1.10.3.2 | Unscheduled | No | No | 2021-02-04 09:00 | 2021-04-04 23:59 | 2021-06-30 09:00 | 2021-08-28 18:00 | [6 empty] | 0 | 0 | [15 empty] | 6.1669 | 0.025931 | 2.55 | Plan & Actual | Quantity | Metric Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5467 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018806
1267 | Task(Task)-->C (Construction) | MECHANICAL EQUIPMENT WORKS | 1.10.3.3 | 1.10.3 | Unscheduled | No | No | 2021-03-23 09:00 | 2021-06-20 23:59 | 2021-08-16 09:00 | 2021-11-13 18:00 | [6 empty] | 0 | 0 | [15 empty] | 4.5361 | 0.044845 | 4.41 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5465 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018807
1268 | Task(Task)-->C (Construction) | ERECTION OF CHUTES/ HOODS & SUPPORTS |  | 1.10.3.3 | Unscheduled | No | No | 2021-03-23 09:00 | 2021-06-20 23:59 | 2021-08-16 09:00 | 2021-11-13 18:00 | [6 empty] | 0 | 0 | [15 empty] | 100 | 0.044845 | 4.41 | Plan & Actual | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3616 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018808
1269 | Task(Task)-->C (Construction) | ELECTRICAL & INSTRUMENTATION | 1.10.3.4 | 1.10.3 | Unscheduled | No | No | 2021-03-31 09:00 | 2021-08-25 18:00 | 2021-08-24 09:00 | 2022-02-20 23:59 | [6 empty] | 0 | 0 | [15 empty] | 6.583 | 0.065081 | 6.4 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5249 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018809
1270 | Task(Task)-->C (Construction) | CABLE TRAY |  | 1.10.3.4 | Unscheduled | No | No | 2021-03-31 09:00 | 2021-04-09 18:00 | 2021-08-24 09:00 | 2021-09-02 18:00 | [6 empty] | 0 | 0 | [15 empty] | 5 | 0.003254 | 0.32 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3617 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018810
1271 | Task(Task)-->C (Construction) | POWER CABLE |  | 1.10.3.4 | Unscheduled | No | No | 2021-06-21 09:00 | 2021-06-27 23:59 | 2021-11-14 | 2021-11-20 18:00 | [6 empty] | 0 | 0 | [15 empty] | 30.3125 | 0.019728 | 1.94 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 13710 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5250 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018811
1272 | Task(Task)-->C (Construction) | CONTROL CABLE |  | 1.10.3.4 | Unscheduled | No | No | 2021-06-25 09:00 | 2021-06-27 23:59 | 2021-11-18 09:00 | 2021-11-20 18:00 | [6 empty] | 0 | 0 | [15 empty] | 23.5938 | 0.015355 | 1.51 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 10700 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3618 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018812
1273 | Task(Task)-->C (Construction) | EARTHING |  | 1.10.3.4 | Unscheduled | No | No | 2021-03-31 09:00 | 2021-04-09 18:00 | 2021-08-24 09:00 | 2021-09-02 18:00 | [6 empty] | 0 | 0 | [15 empty] | 4.5312 | 0.002949 | 0.29 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 1282 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5318 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018813
1274 | Task(Task)-->C (Construction) | EARTH PIT |  | 1.10.3.4 | Unscheduled | No | No | 2021-05-01 09:00 | 2021-05-05 18:00 | 2021-09-24 09:00 | 2021-09-28 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5319 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018814
1275 | Task(Task)-->C (Construction) | LIGHTING |  | 1.10.3.4 | Unscheduled | No | No | 2021-04-05 09:00 | 2021-04-19 18:00 | 2021-08-29 | 2021-09-12 23:59 | [6 empty] | 0 | 0 | [15 empty] | 26.875 | 0.017491 | 1.72 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 176 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5320 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018815
1276 | Task(Task)-->C (Construction) | FIELD INTRUMENTS |  | 1.10.3.4 | Unscheduled | No | No | 2021-06-28 09:00 | 2021-06-30 18:00 | 2021-11-21 | 2021-11-23 18:00 | [6 empty] | 0 | 0 | [15 empty] | 9.6875 | 0.006305 | 0.62 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5321 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018816
1277 | Task(Task)-->C (Construction) | MOTOR TERMINATION |  | 1.10.3.4 | Unscheduled | No | No | 2021-06-28 09:00 | 2021-07-01 18:00 | 2021-12-03 09:00 | 2021-12-06 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5322 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018817
1278 | Task(Task)-->C (Construction) | NO LOAD RUN OF MOTOR |  | 1.10.3.4 | Unscheduled | No | No | 2021-08-22 | 2021-08-25 18:00 | 2022-02-17 09:00 | 2022-02-20 23:59 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5468 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018818
1279 | Task(Task)-->C (Construction) | NO LOAD COMMISSIONING & SYSTEM READYNESS FOR LOAD & TRIAL OPERATION |  | 1.10.3 | Unscheduled | No | No | 2021-08-26 09:00 | 2021-09-08 18:00 | 2022-02-21 09:00 | 2022-03-06 23:59 | [6 empty] | 0 | 0 | [15 empty] | 1.584 | 0.01566 | 1.54 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5323 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018819
1280 | Task(Task)-->E (Engineering) | PIPE CONVEYOR PC 2A & PC 2B | 1.11 | 1 | Work In Progress | No | No | 2019-11-07 09:00 | 2021-09-13 18:00 | 2019-11-08 09:00 | 2022-04-05 18:00 |  |  | 2019-11-08 17:07 |  |  |  | 53.8755 | 22.4171 | [15 empty] | 28.6358 | 28.6358 | 2816.14 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3619 | 0 | 1 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018820
1281 | Task(Task)-->E (Engineering) | ENGINEERING | 1.11.1 | 1.11 | Work In Progress | No | No | 2019-11-12 18:00 | 2020-09-04 17:40 | 2020-02-21 09:00 | 2020-10-25 23:59 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 83.5273 | [15 empty] | 0.5298 | 0.15171 | 14.92 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3620 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018821
1282 | Task(Task)-->E (Engineering) | MECHANICAL | 1.11.1.1 | 1.11.1 | Work In Progress | No | No | 2019-11-12 18:00 | 2020-03-18 17:40 | 2020-02-21 09:00 | 2020-06-10 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 84.6811 | [15 empty] | 9.3834 | 0.014236 | 1.4 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3621 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036102
1283 | Task(Task)-->E (Engineering) | PIPE CONVEYOR PROFILES FOR PC 2A/B |  | 1.11.1.1 | Completed | No | No | 2019-11-12 18:00 | 2020-01-22 17:40 | 2020-02-21 09:00 | 2020-04-04 18:00 |  |  | 2020-02-21 14:04 | 2020-06-19 14:55 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-CS-DC-0015 |  | 2020-02-13 10:26 | 7012-155-PVM-B-015 |  |  |  | A |  |  |  | 15.6028 | 0.002221 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 80 | 0 | 69 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3622 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-11-12 18:00 | 2020-01-08 18:00 |  | 10 | 2020-01-08 23:31 |  |  | 2019-12-14 17:40 | 2020-02-07 18:00 |  | 30 | 2020-02-07 23:31 |  |  | 2019-12-20 17:40 | 2020-02-14 18:00 |  | 35 | 2020-02-14 23:31 |  |  | 2019-12-26 23:59 | 2020-02-21 18:00 |  | 65 | 2020-02-21 23:31 |  |  | 2020-01-01 17:40 | 2020-03-19 18:00 |  | 80 | 2020-03-19 23:31 | [5 empty] | 80 | 2020-03-30 18:45 | [5 empty] | 80 | 2020-03-30 18:45 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-01-22 17:40 | 2020-04-18 18:00 |  | 100 | 2020-04-23 23:31 | [121 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 15 |  |  |  | 101029
1284 | Task(Task)-->E (Engineering) | POWER AND TENSION CALCULATION FOR PIPE CONVEYORS PC 2A/B |  | 1.11.1.1 | Completed | No | No | 2019-11-12 18:00 | 2020-01-22 17:40 | 2020-04-28 09:00 | 2020-06-10 18:00 |  |  | 2020-02-21 14:04 | 2020-06-29 19:15 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-CS-DC-0017 |  | 2020-02-13 10:26 | 7012-155-PVM-U-017 |  |  |  | I |  |  |  | 7.8014 | 0.001111 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 40 | 0 | 21.12 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3624 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-11-12 18:00 | 2020-03-18 18:00 |  | 10 | 2020-03-18 23:31 |  |  | 2019-12-14 17:40 | 2020-04-17 18:00 |  | 30 | 2020-04-17 23:31 |  |  | 2019-12-20 17:40 | 2020-04-17 18:00 |  | 35 | 2020-04-17 23:31 |  |  | 2019-12-26 23:59 | 2020-04-24 18:00 |  | 65 | 2020-04-28 23:31 |  |  | 2020-01-01 17:40 | 2020-05-15 18:00 |  | 80 | 2020-05-16 23:31 | [5 empty] | 80 | 2020-06-10 15:19 | [5 empty] | 80 | 2020-06-10 15:19 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-01-22 17:40 | 2020-05-15 18:00 |  | 100 | 2020-06-29 19:16 | [121 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 17 |  |  |  | 101031
1285 | Task(Task)-->E (Engineering) | G.A AND MARKING OF PIPE CONV. PC 2A/B WITH ELEVATION AND PLAN DETAILS |  | 1.11.1.1 | Unscheduled | No | No | 2019-12-28 18:00 | 2020-03-18 17:40 | 2020-03-15 23:59 | 2020-06-10 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-0025 |  | 2020-02-13 10:26 | 7012-155-PVM-B-025 |  |  |  | A |  |  |  | 76.5957 | 0.010904 | 1.08 | Plan & Actual | Date |  | 0 | 0 | 0 | 400 | 0 | 103 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3623 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-12-28 18:00 | 2020-03-15 23:59 |  | 10 | 2020-03-15 23:31 |  |  | 2020-02-05 17:40 | 2020-04-24 18:00 |  | 30 | 2020-05-01 23:31 |  |  | 2020-02-12 17:40 | 2020-04-29 18:00 |  | 35 | 2020-05-09 23:31 |  |  | 2020-02-18 23:59 | 2020-05-06 18:00 |  | 65 | 2020-05-12 23:31 |  |  | 2020-02-25 17:40 | 2020-05-27 18:00 |  | 80 | 2020-06-10 17:36 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-18 17:40 | 2020-06-10 18:00 |  | 100 | [122 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 25 |  |  |  | 101039
1286 | Task(Task)-->E (Engineering) | CIVIL | 1.11.1.2 | 1.11.1 | Work In Progress | No | No | 2020-05-22 18:00 | 2020-07-21 17:40 | 2020-06-05 18:00 | 2020-10-25 23:59 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 90 | [15 empty] | 47.7212 | 0.072399 | 7.12 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3643 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036103
1287 | Task(Task)-->E (Engineering) | PIPE CONVEYOR FOR PC 2A/B : NUM & RC DETAILS OF FDN (SHT 1) |  | 1.11.1.2 | Completed | No | No | 2020-05-22 18:00 | 2020-07-21 17:40 | 2020-08-17 09:00 | 2020-09-01 18:00 |  |  | 2020-02-21 15:37 | 2020-09-02 00:50 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-NR-0019 |  | 2020-02-13 11:42 | 7012-155-PVC-C-056 |  |  |  | A |  |  |  | 50 | 0.0362 | 3.51 | Plan & Actual | Date |  | 0 | 0 | 0 | 1303.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3644 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-05-22 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-06-09 17:40 | 2020-07-10 18:00 |  | 30 |  |  |  | 2020-06-16 17:40 | 2020-07-13 18:00 |  | 35 |  |  |  | 2020-06-22 23:59 | 2020-07-20 18:00 |  | 65 | 2020-08-17 22:24 |  |  | 2020-06-29 17:40 | 2020-08-10 18:00 |  | 80 | 2020-09-02 00:43 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-07-21 17:40 | 2020-08-24 18:00 |  | 100 | 2020-09-02 00:51 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 157 |  |  |  | 101169
1288 | Task(Task)-->E (Engineering) | PIPE CONVEYOR FOR PC 2A/B : NUM & RC DETAILS OF FDN (SHT 2) |  | 1.11.1.2 | Unscheduled | No | No | 2020-05-22 18:00 | 2020-07-21 17:40 | 2020-06-05 18:00 | 2020-10-25 23:59 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-NR-0020 |  | 2020-02-13 11:42 | 7012-155-PVC-C-057 |  |  |  | A |  |  |  | 50 | 0.0362 | 3.51 | Plan & Actual | Date |  | 0 | 0 | 0 | 1303.33 | 0 | 208 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3645 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-05-22 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-06-09 17:40 | 2020-07-10 18:00 |  | 30 |  |  |  | 2020-06-16 17:40 | 2020-07-13 18:00 |  | 35 |  |  |  | 2020-06-22 23:59 | 2020-07-20 18:00 |  | 65 | 2020-10-01 19:38 |  |  | 2020-06-29 17:40 | 2020-08-10 18:00 |  | 80 | 2020-10-14 20:44 | [5 empty] | 80 | 2020-10-14 20:49 | [5 empty] | 80 | 2020-10-14 20:49 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-07-21 17:40 | 2020-08-24 18:00 |  | 100 | [122 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 158 |  |  |  | 101170
1289 | Task(Task)-->E (Engineering) | STRUCTURAL | 1.11.1.3 | 1.11.1 | Work In Progress | No | No | 2020-04-17 18:00 | 2020-09-04 17:40 | 2020-05-06 18:00 | 2020-09-13 23:59 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 74.8088 | [15 empty] | 32.4397 | 0.049215 | 4.84 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3648 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036104
1290 | Task(Task)-->E (Engineering) | PIPE CONVEYOR FOR PC 2A/B : STRUCTURAL GA (SHT 1) |  | 1.11.1.3 | Completed | No | No | 2020-04-17 18:00 | 2020-06-16 17:40 | 2020-08-02 | 2020-08-17 18:00 |  |  | 2020-02-21 15:37 | 2020-08-17 22:47 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-GA-0014 |  | 2020-02-13 11:42 | 7012-155-PVC-B-051 |  |  |  | A |  |  |  | 7.4045 | 0.003644 | 0.95 | Plan & Actual | Date |  | 0 | 0 | 0 | 351.15 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3656 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-17 18:00 | 2020-05-06 18:00 |  | 10 |  |  |  | 2020-05-05 17:40 | 2020-06-10 18:00 |  | 30 |  |  |  | 2020-05-12 17:40 | 2020-06-13 18:00 |  | 35 |  |  |  | 2020-05-18 23:59 | 2020-06-20 18:00 |  | 65 | 2020-08-13 19:57 |  |  | 2020-05-25 17:40 | 2020-07-11 18:00 |  | 80 | 2020-08-17 22:37 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-16 17:40 | 2020-07-25 18:00 |  | 100 | 2020-08-17 22:48 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 152 |  |  |  | 101164
1291 | Task(Task)-->E (Engineering) | PIPE CONVEYOR FOR PC 2A/B : STRUCTURAL GA (SHT 2) |  | 1.11.1.3 | Completed | No | No | 2020-04-17 18:00 | 2020-06-16 17:40 | 2020-08-21 09:00 | 2020-09-09 18:00 |  |  | 2020-02-21 15:37 | 2020-09-10 23:14 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-GA-0015 |  | 2020-02-13 11:42 | 7012-155-PVC-B-052 |  |  |  | A |  |  |  | 7.4045 | 0.003644 | 0.95 | Plan & Actual | Date |  | 0 | 0 | 0 | 351.15 | 0 | 58.3 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3657 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-17 18:00 | 2020-05-06 18:00 |  | 10 |  |  |  | 2020-05-05 17:40 | 2020-06-10 18:00 |  | 30 |  |  |  | 2020-05-12 17:40 | 2020-06-13 18:00 |  | 35 |  |  |  | 2020-05-18 23:59 | 2020-06-20 18:00 |  | 65 | 2020-08-21 21:30 |  |  | 2020-05-25 17:40 | 2020-07-11 18:00 |  | 80 | 2020-09-10 22:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-16 17:40 | 2020-07-25 18:00 |  | 100 | 2020-09-10 23:15 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 153 |  |  |  | 101165
1292 | Task(Task)-->E (Engineering) | PIPE CONVEYOR FOR PC 2A/B : STRUCTURAL GA (SHT 3) |  | 1.11.1.3 | Completed | No | No | 2020-04-17 18:00 | 2020-06-16 17:40 | 2020-08-21 09:00 | 2020-09-09 18:00 |  |  | 2020-02-21 15:37 | 2020-09-10 23:14 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-GA-0016 |  | 2020-02-13 11:42 | 7012-155-PVC-B-053 |  |  |  | A |  |  |  | 7.4045 | 0.003644 | 0.95 | Plan & Actual | Date |  | 0 | 0 | 0 | 351.15 | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3658 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-17 18:00 | 2020-05-06 18:00 |  | 10 |  |  |  | 2020-05-05 17:40 | 2020-06-10 18:00 |  | 30 |  |  |  | 2020-05-12 17:40 | 2020-06-13 18:00 |  | 35 |  |  |  | 2020-05-18 23:59 | 2020-06-20 18:00 |  | 65 | 2020-08-21 21:30 |  |  | 2020-05-25 17:40 | 2020-07-11 18:00 |  | 80 | 2020-09-10 22:38 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-16 17:40 | 2020-07-25 18:00 |  | 100 | 2020-09-10 23:15 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 154 |  |  |  | 101166
1293 | Task(Task)-->E (Engineering) | PIPE CONVEYOR FOR PC 2A/B : STRUCTURAL GA (SHT 4) |  | 1.11.1.3 | Completed | No | No | 2020-04-17 18:00 | 2020-06-16 17:40 | 2020-08-21 09:00 | 2020-09-09 18:00 |  |  | 2020-02-21 15:37 | 2020-09-10 23:14 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-GA-0017 |  | 2020-02-13 11:42 | 7012-155-PVC-B-054 |  |  |  | A |  |  |  | 7.4045 | 0.003644 | 0.95 | Plan & Actual | Date |  | 0 | 0 | 0 | 351.15 | 0 | 78.3 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3659 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-17 18:00 | 2020-05-06 18:00 |  | 10 |  |  |  | 2020-05-05 17:40 | 2020-06-10 18:00 |  | 30 |  |  |  | 2020-05-12 17:40 | 2020-06-13 18:00 |  | 35 |  |  |  | 2020-05-18 23:59 | 2020-06-20 18:00 |  | 65 | 2020-08-21 21:30 |  |  | 2020-05-25 17:40 | 2020-07-11 18:00 |  | 80 | 2020-09-10 22:39 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-16 17:40 | 2020-07-25 18:00 |  | 100 | 2020-09-10 23:15 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 155 |  |  |  | 101167
1294 | Task(Task)-->E (Engineering) | PIPE CONVEYOR FOR PC 2A/B : STRUCTURAL GA (SHT 5) |  | 1.11.1.3 | Unscheduled | No | No | 2020-04-17 18:00 | 2020-06-16 17:40 | 2020-05-06 18:00 | 2020-08-21 18:00 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-GA-0018 |  | 2020-02-13 11:42 | 7012-155-PVC-B-055 |  |  |  | A |  |  |  | 7.4045 | 0.003644 | 0.95 | Plan & Actual | Date |  | 0 | 0 | 0 | 351.15 | 0 | 139 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3660 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-17 18:00 | 2020-05-06 18:00 |  | 10 |  |  |  | 2020-05-05 17:40 | 2020-06-10 18:00 |  | 30 |  |  |  | 2020-05-12 17:40 | 2020-06-13 18:00 |  | 35 |  |  |  | 2020-05-18 23:59 | 2020-06-20 18:00 |  | 65 | 2020-10-16 22:35 |  |  | 2020-05-25 17:40 | 2020-07-11 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-16 17:40 | 2020-07-25 18:00 |  | 100 | [122 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 156 |  |  |  | 101168
1295 | Task(Task)-->E (Engineering) | ARCHITECTURAL GA OF PIPE CONVEYOR FOR PC 2A/B |  | 1.11.1.3 | Unscheduled | No | No | 2020-07-06 18:00 | 2020-09-04 17:40 | 2020-07-06 18:00 | 2020-09-13 23:59 |  |  | 2020-02-21 15:39 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-AR-0007 |  | 2020-02-13 11:43 | 7012-155-PVC-C-113 |  |  |  | I |  |  |  | 0.85737 | 0.000422 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 40.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3651 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-07-06 18:00 | 2020-07-06 18:00 |  | 10 |  |  |  | 2020-07-24 17:40 | 2020-07-30 18:00 |  | 30 |  |  |  | 2020-07-31 17:40 | 2020-08-02 23:59 |  | 35 |  |  |  | 2020-08-06 23:59 | 2020-08-09 23:59 |  | 65 |  |  |  | 2020-08-13 17:40 | 2020-08-30 23:59 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-09-04 17:40 | 2020-09-13 23:59 |  | 100 | [122 empty] | Chetan Khodke |  |  |  |  | A - Architecture | [16 empty] | 214 |  |  |  | 101224
1296 | Task(Task)-->E (Engineering) | PIPE CONVEYOR FOR PC 2A/B : DESIGN CALCULATION OF SUPER STRUCTURE |  | 1.11.1.3 | Unscheduled | No | No | 2020-05-05 17:40 | 2020-06-16 17:40 | 2020-06-05 18:00 | 2020-08-24 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0042 |  | 2020-02-13 12:42 | 7012-155-PVC-U-049 |  |  |  | A |  |  |  | 54.7155 | 0.026928 | 7.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3653 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-05-22 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-05-05 17:40 | 2020-07-10 18:00 |  | 30 |  |  |  | 2020-05-12 17:40 | 2020-07-13 18:00 |  | 35 |  |  |  | 2020-05-18 23:59 | 2020-07-20 18:00 |  | 65 | 2020-10-16 22:35 |  |  | 2020-05-25 17:40 | 2020-08-10 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-16 17:40 | 2020-08-24 18:00 |  | 100 | [122 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 150 |  |  |  | 101464
1297 | Task(Task)-->E (Engineering) | PIPE CONVEYOR FOR PC 2A/B : DESIGN CALCULATION OF SUB STRUCTURE |  | 1.11.1.3 | Unscheduled | No | No | 2020-04-17 18:00 | 2020-07-21 17:40 | 2020-05-06 18:00 | 2020-08-17 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0045 |  | 2020-02-13 12:42 | 7012-155-PVC-U-050 |  |  |  | A |  |  |  | 7.4045 | 0.003644 | 0.95 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3656 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-17 18:00 | 2020-05-06 18:00 |  | 10 |  |  |  | 2020-06-09 17:40 | 2020-06-10 18:00 |  | 30 |  |  |  | 2020-06-16 17:40 | 2020-06-13 18:00 |  | 35 |  |  |  | 2020-06-22 23:59 | 2020-06-20 18:00 |  | 65 | 2020-10-13 22:05 |  |  | 2020-06-29 17:40 | 2020-07-11 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-07-21 17:40 | 2020-07-25 18:00 |  | 100 | [122 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 151 |  |  |  | 101465
1298 | Task(Task)-->E (Engineering) | ELECTRICAL | 1.11.1.4 | 1.11.1 | Unscheduled | No | No | 2020-05-09 18:00 | 2020-06-29 17:40 | 2020-05-12 18:00 | 2020-06-24 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 | [15 empty] | 10.4558 | 0.015863 | 1.56 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3661 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036105
1299 | Task(Task)-->E (Engineering) | LIGHTING LAYOUT PLAN WITH POWER DISTRIBUTION ARRANGEMENT, SECTIONAL VIEW, BOM OF PIPE CONVEYOR 2A/B |  | 1.11.1.4 | Unscheduled | No | No | 2020-05-09 18:00 | 2020-06-29 17:40 | 2020-05-12 18:00 | 2020-06-24 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5078 |  | 2020-02-13 11:45 | 7012-155-PVE-G-040 |  |  |  | A |  |  |  | 100 | 0.015863 | 1.56 | Plan & Actual | Date |  | 0 | 0 | 0 | 580.17 | 0 | 24.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3663 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-05-09 18:00 | 2020-05-12 18:00 |  | 10 | 2020-05-12 23:31 |  |  | 2020-05-18 17:40 | 2020-05-19 18:00 |  | 30 |  |  |  | 2020-05-25 17:40 | 2020-05-26 18:00 |  | 35 |  |  |  | 2020-05-30 23:59 | 2020-06-02 18:00 |  | 65 | 2020-06-10 11:31 |  |  | 2020-06-05 17:40 | 2020-06-23 18:00 |  | 80 | 2020-08-03 10:00 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-29 17:40 | 2020-06-23 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 275 |  |  |  | 101286
1300 | Task(Task)-->P (Procurement) | PROCUREMENT | 1.11.2 | 1.11 | Work In Progress | No | No | 2019-11-07 09:00 | 2021-03-31 18:00 | 2019-11-08 09:00 | 2022-01-22 18:00 |  |  | 2019-11-08 17:07 |  |  |  | 65.4657 | 29.6513 | [15 empty] | 74.1058 | 21.2208 | 2086.93 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3666 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018826
1301 | Task(Task)-->P (Procurement) | PURCHASE REQUISITION | 1.11.2.1 | 1.11.2 | Work In Progress | No | No | 2019-11-07 09:00 | 2020-05-19 18:00 | 2019-11-08 09:00 | 2020-07-19 23:59 |  |  | 2019-11-08 17:07 |  |  |  | 100 | 99.5684 | [15 empty] | 4.9949 | 1.06 | 104.24 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3667 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018827
1302 | Task(Task)-->P (Procurement) | Pulley |  | 1.11.2.1 | Completed | No | No | 2020-03-03 09:00 | 2020-03-03 18:00 | 2020-04-26 | 2020-04-26 23:59 |  |  | 2020-04-26 10:57 | 2020-04-26 10:57 |  |  | 100 | 100 | [15 empty] | 3.1751 | 0.033654 | 3.31 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3668 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018828
1303 | Task(Task)-->P (Procurement) | Idler |  | 1.11.2.1 | Completed | No | No | 2019-11-19 09:00 | 2019-11-19 18:00 | 2020-03-21 09:00 | 2020-03-21 18:00 |  |  | 2020-03-21 10:57 | 2020-03-21 10:57 |  |  | 100 | 100 | [15 empty] | 17.2374 | 0.18271 | 17.97 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3669 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018829
1304 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.11.2.1 | Completed | No | No | 2020-05-17 | 2020-05-17 23:59 | 2020-04-26 | 2020-04-26 23:59 |  |  | 2020-04-26 10:57 | 2020-04-26 10:57 |  |  | 100 | 100 | [15 empty] | 0.25899 | 0.002745 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3670 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018830
1305 | Task(Task)-->P (Procurement) | Bearing |  | 1.11.2.1 | Completed | No | No | 2020-05-17 | 2020-05-17 23:59 | 2020-04-26 | 2020-04-26 23:59 |  |  | 2020-04-26 10:57 | 2020-04-26 10:57 |  |  | 100 | 100 | [15 empty] | 0.57554 | 0.0061 | 0.6 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3671 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018831
1306 | Task(Task)-->P (Procurement) | Belting |  | 1.11.2.1 | Completed | No | No | 2019-11-07 09:00 | 2019-11-07 18:00 | 2020-02-21 09:00 | 2020-02-21 18:00 |  |  | 2020-02-21 15:59 | 2020-02-21 15:59 |  |  | 100 | 100 | [15 empty] | 32.2878 | 0.34224 | 33.66 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3672 | 1 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018832
1307 | Task(Task)-->P (Procurement) | Scrapper |  | 1.11.2.1 | Completed | No | No | 2019-11-17 | 2019-11-17 23:59 | 2020-03-11 09:00 | 2020-03-11 18:00 |  |  | 2020-03-11 10:57 | 2020-03-11 10:57 |  |  | 100 | 100 | [15 empty] | 0.019185 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3673 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018833
1308 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.11.2.1 | Completed | No | No | 2020-03-10 09:00 | 2020-03-10 18:00 | 2020-03-11 09:00 | 2020-03-11 18:00 |  |  | 2020-03-11 12:41 | 2020-03-11 12:41 |  |  | 100 | 100 | [15 empty] | 1.2182 | 0.012913 | 1.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3674 | 0 | 4 | High | [7 empty] | 0 | 0 | [244 empty] | 1018834
1309 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.11.2.1 | Unscheduled | No | No | 2020-05-19 09:00 | 2020-05-19 18:00 | 2020-06-08 09:00 | 2020-06-08 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.43165 | 0.004575 | 0.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3675 | 1 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018835
1310 | Task(Task)-->P (Procurement) | Gear Box |  | 1.11.2.1 | Completed | No | No | 2019-11-13 09:00 | 2019-11-13 18:00 | 2020-02-21 09:00 | 2020-02-21 18:00 |  |  | 2020-02-21 10:57 | 2020-02-21 10:57 |  |  | 100 | 100 | [15 empty] | 1.6403 | 0.017386 | 1.71 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3676 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018836
1311 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.11.2.1 | Completed | No | No | 2019-11-21 09:00 | 2019-11-21 18:00 | 2020-04-27 09:00 | 2020-04-27 18:00 |  |  | 2020-04-27 10:41 | 2020-04-27 10:41 |  |  | 100 | 100 | [15 empty] | 0.35492 | 0.003762 | 0.37 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3677 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018837
1312 | Task(Task)-->P (Procurement) | Brake |  | 1.11.2.1 | Completed | No | No | 2019-12-18 09:00 | 2019-12-18 18:00 | 2020-05-01 09:00 | 2020-05-01 18:00 |  |  | 2020-04-23 11:33 | 2020-04-23 11:33 |  |  | 100 | 100 | [15 empty] | 0.11511 | 0.00122 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3678 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018838
1313 | Task(Task)-->P (Procurement) | Maintenance Trolley |  | 1.11.2.1 | Completed | No | No | 2019-11-30 09:00 | 2019-11-30 18:00 | 2020-07-19 | 2020-07-19 23:59 |  |  | 2020-07-28 11:45 | 2020-07-28 11:45 |  |  | 100 | 100 | [15 empty] | 0.29736 | 0.003152 | 0.31 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3679 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018839
1314 | Task(Task)-->P (Procurement) | Building Structure |  | 1.11.2.1 | Completed | No | No | 2020-03-20 09:00 | 2020-03-20 18:00 | 2020-04-06 09:00 | 2020-04-06 18:00 |  |  | 2020-04-06 17:30 | 2020-05-06 17:30 |  |  | 100 | 100 | [15 empty] | 35.6067 | 0.37742 | 37.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3680 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018840
1315 | Task(Task)-->P (Procurement) | 6.6KV HT VFD with Motors |  | 1.11.2.1 | Completed | No | No | 2019-12-30 09:00 | 2019-12-30 18:00 | 2020-01-24 09:00 | 2020-01-24 18:00 |  |  | 2019-11-21 10:57 | 2019-11-21 10:57 |  |  | 100 | 100 | [15 empty] | 6.0144 | 0.06375 | 6.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3681 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018841
1316 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.11.2.1 | Completed | No | No | 2020-03-10 09:00 | 2020-03-10 18:00 | 2020-03-16 09:00 | 2020-03-16 18:00 |  |  | 2020-03-16 10:57 | 2020-03-16 10:57 |  |  | 100 | 100 | [15 empty] | 0.25899 | 0.002745 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3682 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018842
1317 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.11.2.1 | Completed | No | No | 2020-03-27 09:00 | 2020-03-27 18:00 | 2020-04-30 09:00 | 2020-04-30 18:00 |  |  | 2020-04-30 10:57 | 2020-04-30 10:57 |  |  | 100 | 100 | [15 empty] | 0.11511 | 0.00122 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3683 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018843
1318 | Task(Task)-->P (Procurement) | WELDING DISTRIBUTION BOARD |  | 1.11.2.1 | Completed | No | No | 2020-02-14 09:00 | 2020-02-14 18:00 | 2019-11-08 09:00 | 2019-11-08 18:00 |  |  | 2019-11-08 17:07 | 2019-11-08 17:07 |  |  | 100 | 100 | [15 empty] | 0.35492 | 0.003762 | 0.37 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3684 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018844
1319 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.11.2.1 | Completed | No | No | 2020-01-08 09:00 | 2020-01-08 18:00 | 2020-01-08 09:00 | 2020-01-08 18:00 |  |  | 2020-01-08 10:57 | 2020-01-08 10:57 |  |  | 100 | 100 | [15 empty] | 0.038369 | 0.000407 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3686 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018845
1320 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.11.2.1 | Completed | No | No | 2019-12-30 09:00 | 2019-12-30 18:00 | 2019-12-30 09:00 | 2019-12-30 18:00 |  |  | 2019-12-30 10:57 | 2019-12-30 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3687 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018846
1321 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.11.2.1 | Completed | No | No | 2020-01-03 09:00 | 2020-01-03 18:00 | 2020-01-03 09:00 | 2020-01-03 18:00 |  |  | 2020-01-03 10:57 | 2020-01-03 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3688 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018847
1322 | Task(Task)-->P (Procurement) | TECHNICAL CLEARANCE | 1.11.2.2 | 1.11.2 | Work In Progress | No | No | 2019-11-08 09:00 | 2020-06-18 18:00 | 2019-11-08 09:00 | 2020-10-15 18:00 |  |  | 2019-11-09 17:08 |  |  |  | 100 | 99.271 | [15 empty] | 4.9949 | 1.06 | 104.24 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3689 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018848
1323 | Task(Task)-->P (Procurement) | Pulley |  | 1.11.2.2 | Completed | No | No | 2020-03-04 09:00 | 2020-03-04 18:00 | 2020-04-26 | 2020-04-26 23:59 |  |  | 2020-04-26 10:57 | 2020-04-26 10:57 |  |  | 100 | 100 | [15 empty] | 3.1751 | 0.033654 | 3.31 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3690 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018849
1324 | Task(Task)-->P (Procurement) | Idler |  | 1.11.2.2 | Completed | No | No | 2019-11-20 09:00 | 2020-02-01 18:00 | 2020-03-21 09:00 | 2020-05-16 18:00 |  |  | 2020-03-23 15:49 | 2020-05-16 15:49 |  |  | 100 | 100 | [15 empty] | 17.2374 | 0.18271 | 17.97 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3691 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018850
1325 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.11.2.2 | Completed | No | No | 2020-05-18 09:00 | 2020-06-01 18:00 | 2020-04-26 | 2020-04-26 23:59 |  |  | 2020-04-26 10:57 | 2020-04-26 10:57 |  |  | 100 | 100 | [15 empty] | 0.25899 | 0.002745 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3692 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018851
1326 | Task(Task)-->P (Procurement) | Bearing |  | 1.11.2.2 | Completed | No | No | 2020-05-18 09:00 | 2020-06-16 18:00 | 2020-04-26 | 2020-04-26 23:59 |  |  | 2020-04-26 10:57 | 2020-04-26 10:57 |  |  | 100 | 100 | [15 empty] | 0.57554 | 0.0061 | 0.6 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3693 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018852
1327 | Task(Task)-->P (Procurement) | Belting |  | 1.11.2.2 | Completed | No | No | 2019-11-08 09:00 | 2020-03-27 18:00 | 2020-02-21 09:00 | 2020-05-16 18:00 |  |  | 2020-05-16 10:57 | 2020-05-16 10:57 |  |  | 100 | 100 | [15 empty] | 32.2878 | 0.34224 | 33.66 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3694 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018853
1328 | Task(Task)-->P (Procurement) | Scrapper |  | 1.11.2.2 | Completed | No | No | 2019-11-18 09:00 | 2020-03-16 18:00 | 2020-03-11 09:00 | 2020-03-26 18:00 |  |  | 2020-03-26 10:57 | 2020-03-26 10:57 |  |  | 100 | 100 | [15 empty] | 0.019185 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3695 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018854
1329 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.11.2.2 | Completed | No | No | 2020-03-11 09:00 | 2020-03-20 18:00 | 2020-03-11 09:00 | 2020-03-17 18:00 |  |  | 2020-03-12 12:43 | 2020-03-17 12:43 |  |  | 100 | 100 | [15 empty] | 1.2182 | 0.012913 | 1.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3696 | 0 | 4 | High | [7 empty] | 0 | 0 | [244 empty] | 1018855
1330 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.11.2.2 | Unscheduled | No | No | 2020-05-20 09:00 | 2020-06-18 18:00 | 2020-06-08 09:00 | 2020-08-13 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.43165 | 0.004575 | 0.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3697 | 1 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018856
1331 | Task(Task)-->P (Procurement) | Gear Box |  | 1.11.2.2 | Completed | No | No | 2019-11-14 09:00 | 2020-05-21 18:00 | 2020-02-21 09:00 | 2020-05-29 18:00 |  |  | 2020-02-22 11:19 | 2020-05-29 10:57 |  |  | 100 | 100 | [15 empty] | 1.6403 | 0.017386 | 1.71 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3698 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018857
1332 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.11.2.2 | Completed | No | No | 2019-11-22 09:00 | 2020-03-19 18:00 | 2020-04-27 09:00 | 2020-05-30 18:00 |  |  | 2020-05-30 10:46 | 2020-05-30 10:46 |  |  | 100 | 100 | [15 empty] | 0.35492 | 0.003762 | 0.37 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3699 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018858
1333 | Task(Task)-->P (Procurement) | Brake |  | 1.11.2.2 | Completed | No | No | 2019-12-19 09:00 | 2020-04-05 23:59 | 2020-05-01 09:00 | 2020-06-15 18:00 |  |  | 2020-04-24 11:34 | 2020-06-15 10:57 |  |  | 100 | 100 | [15 empty] | 0.11511 | 0.00122 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3700 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018859
1334 | Task(Task)-->P (Procurement) | Maintenance Trolley |  | 1.11.2.2 | Unscheduled | No | No | 2019-12-01 | 2019-12-18 18:00 | 2020-07-19 | 2020-10-15 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.29736 | 0.003152 | 0.31 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3701 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018860
1335 | Task(Task)-->P (Procurement) | Building Structure |  | 1.11.2.2 | Completed | No | No | 2020-03-21 09:00 | 2020-03-27 18:00 | 2020-04-06 09:00 | 2020-04-13 18:00 |  |  | 2020-04-07 17:31 | 2020-04-13 17:31 |  |  | 100 | 100 | [15 empty] | 35.6067 | 0.37742 | 37.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3702 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018861
1336 | Task(Task)-->P (Procurement) | 6.6KV HT VFD with Motors |  | 1.11.2.2 | Completed | No | No | 2019-12-31 09:00 | 2020-01-29 18:00 | 2020-01-24 09:00 | 2020-04-16 18:00 |  |  | 2020-02-26 10:57 | 2020-02-26 10:57 |  |  | 100 | 100 | [15 empty] | 6.0144 | 0.06375 | 6.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3703 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018862
1337 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.11.2.2 | Completed | No | No | 2020-03-11 09:00 | 2020-03-25 18:00 | 2020-03-16 09:00 | 2020-06-02 18:00 |  |  | 2020-06-02 10:57 | 2020-06-02 10:57 |  |  | 100 | 100 | [15 empty] | 0.25899 | 0.002745 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3704 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018863
1338 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.11.2.2 | Completed | No | No | 2020-03-28 09:00 | 2020-05-11 18:00 | 2020-04-30 09:00 | 2020-06-03 18:00 |  |  | 2020-06-03 10:57 | 2020-06-03 10:57 |  |  | 100 | 100 | [15 empty] | 0.11511 | 0.00122 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3705 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018864
1339 | Task(Task)-->P (Procurement) | WELDING DISTRIBUTION BOARD |  | 1.11.2.2 | Completed | No | No | 2020-02-15 09:00 | 2020-02-28 18:00 | 2019-11-08 09:00 | 2020-02-13 18:00 |  |  | 2019-11-09 17:08 | 2020-02-13 17:08 |  |  | 100 | 100 | [15 empty] | 0.35492 | 0.003762 | 0.37 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3706 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018865
1340 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.11.2.2 | Completed | No | No | 2020-01-09 09:00 | 2020-01-22 18:00 | 2020-01-08 09:00 | 2020-03-10 18:00 |  |  | 2020-03-10 10:57 | 2020-03-10 10:57 |  |  | 100 | 100 | [15 empty] | 0.038369 | 0.000407 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3708 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018866
1341 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.11.2.2 | Completed | No | No | 2019-12-31 09:00 | 2020-01-14 18:00 | 2019-12-30 09:00 | 2020-03-07 18:00 |  |  | 2020-03-07 10:57 | 2020-03-07 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3709 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018867
1342 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.11.2.2 | Completed | No | No | 2020-01-04 09:00 | 2020-01-18 18:00 | 2020-01-03 09:00 | 2020-01-16 18:00 |  |  | 2020-01-16 10:57 | 2020-01-16 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3710 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018868
1343 | Task(Task)-->P (Procurement) | ORDERING | 1.11.2.3 | 1.11.2 | Work In Progress | No | No | 2019-12-19 09:00 | 2020-07-18 18:00 | 2020-01-16 09:00 | 2020-11-04 18:00 |  |  | 2020-02-01 10:57 |  |  |  | 100 | 95.4724 | [15 empty] | 9.9898 | 2.1199 | 208.48 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3711 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018869
1344 | Task(Task)-->P (Procurement) | Pulley |  | 1.11.2.3 | Unscheduled | No | No | 2020-03-05 09:00 | 2020-04-03 18:00 | 2020-04-26 | 2020-07-16 18:00 | [6 empty] | 100 | 0 | [15 empty] | 3.1799 | 0.06741 | 6.63 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3712 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018870
1345 | Task(Task)-->P (Procurement) | Idler |  | 1.11.2.3 | Completed | No | No | 2020-02-02 | 2020-03-02 18:00 | 2020-05-16 09:00 | 2020-08-22 18:00 |  |  | 2020-05-16 16:19 | 2020-08-22 16:19 |  |  | 100 | 100 | [15 empty] | 17.2374 | 0.36542 | 35.94 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3713 | 1 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018871
1346 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.11.2.3 | Completed | No | No | 2020-06-02 09:00 | 2020-07-01 18:00 | 2020-04-26 | 2020-07-07 18:00 |  |  | 2020-04-27 09:32 | 2020-07-07 09:32 |  |  | 100 | 100 | [15 empty] | 0.25899 | 0.00549 | 0.54 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3714 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018872
1347 | Task(Task)-->P (Procurement) | Bearing |  | 1.11.2.3 | Unscheduled | No | No | 2020-06-17 09:00 | 2020-07-16 18:00 | 2020-04-26 | 2020-08-22 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.57554 | 0.012201 | 1.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3715 | 1 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018873
1348 | Task(Task)-->P (Procurement) | Belting |  | 1.11.2.3 | Completed | No | No | 2020-03-28 09:00 | 2020-05-11 18:00 | 2020-05-16 09:00 | 2020-09-04 18:00 |  |  | 2020-05-16 16:24 | 2020-09-04 16:24 |  |  | 100 | 100 | [15 empty] | 32.2878 | 0.68447 | 67.32 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3716 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018874
1349 | Task(Task)-->P (Procurement) | Scrapper |  | 1.11.2.3 | Completed | No | No | 2020-03-17 09:00 | 2020-04-15 18:00 | 2020-03-26 09:00 | 2020-05-30 18:00 |  |  | 2020-05-30 10:57 | 2020-05-30 10:57 |  |  | 100 | 100 | [15 empty] | 0.019185 | 0.000407 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3717 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018875
1350 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.11.2.3 | Completed | No | No | 2020-03-21 09:00 | 2020-04-19 23:59 | 2020-03-17 09:00 | 2020-07-06 18:00 |  |  | 2020-03-18 12:44 | 2020-07-06 12:44 |  |  | 100 | 100 | [15 empty] | 1.2134 | 0.025724 | 2.53 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3718 | 0 | 4 | High | [7 empty] | 0 | 0 | [244 empty] | 1018876
1351 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.11.2.3 | Unscheduled | No | No | 2020-06-19 09:00 | 2020-07-18 18:00 | 2020-08-13 09:00 | 2020-10-10 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.43645 | 0.009252 | 0.91 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3719 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018877
1352 | Task(Task)-->P (Procurement) | Gear Box |  | 1.11.2.3 | Completed | No | No | 2020-05-22 09:00 | 2020-06-20 18:00 | 2020-05-29 09:00 | 2020-06-23 18:00 |  |  | 2020-05-30 11:21 | 2020-06-23 16:51 |  |  | 100 | 100 | [15 empty] | 1.6355 | 0.034671 | 3.41 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3720 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018878
1353 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.11.2.3 | Completed | No | No | 2020-03-20 09:00 | 2020-04-18 18:00 | 2020-05-30 09:00 | 2020-06-16 18:00 |  |  | 2020-06-01 11:11 | 2020-06-16 16:05 |  |  | 100 | 100 | [15 empty] | 0.35492 | 0.007524 | 0.74 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3721 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018879
1354 | Task(Task)-->P (Procurement) | Brake |  | 1.11.2.3 | Completed | No | No | 2020-04-06 09:00 | 2020-05-05 18:00 | 2020-06-15 09:00 | 2020-07-03 18:00 |  |  | 2020-06-16 11:40 | 2020-07-03 11:40 |  |  | 100 | 100 | [15 empty] | 0.11031 | 0.002339 | 0.23 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3722 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018880
1355 | Task(Task)-->P (Procurement) | Maintenance Trolley |  | 1.11.2.3 | Unscheduled | No | No | 2019-12-19 09:00 | 2020-01-07 18:00 | 2020-10-16 09:00 | 2020-11-04 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.30216 | 0.006406 | 0.63 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3723 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018881
1356 | Task(Task)-->P (Procurement) | Building Structure |  | 1.11.2.3 | Completed | No | No | 2020-03-28 09:00 | 2020-04-26 23:59 | 2020-04-13 09:00 | 2020-05-31 23:59 |  |  | 2020-05-31 18:49 | 2020-05-31 18:49 |  |  | 100 | 100 | [15 empty] | 35.6019 | 0.75473 | 74.23 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3724 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018882
1357 | Task(Task)-->P (Procurement) | 6.6KV HT VFD with Motors |  | 1.11.2.3 | Completed | No | No | 2020-01-30 09:00 | 2020-02-28 18:00 | 2020-04-16 09:00 | 2020-07-18 18:00 |  |  | 2020-04-29 10:57 | 2020-04-29 10:57 |  |  | 100 | 100 | [15 empty] | 6.0192 | 0.1276 | 12.55 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3725 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018883
1358 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.11.2.3 | Completed | No | No | 2020-03-26 09:00 | 2020-04-10 18:00 | 2020-06-02 09:00 | 2020-07-31 18:00 |  |  | 2020-06-03 15:51 | 2020-06-29 15:51 |  |  | 100 | 100 | [15 empty] | 0.2542 | 0.005389 | 0.53 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3726 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018884
1359 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.11.2.3 | Completed | No | No | 2020-05-12 09:00 | 2020-06-25 18:00 | 2020-06-03 09:00 | 2020-06-24 18:00 |  |  | 2020-06-15 10:57 | 2020-06-15 10:57 |  |  | 100 | 100 | [15 empty] | 0.11511 | 0.00244 | 0.24 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3727 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018885
1360 | Task(Task)-->P (Procurement) | WELDING DISTRIBUTION BOARD |  | 1.11.2.3 | Completed | No | No | 2020-02-29 09:00 | 2020-03-14 18:00 | 2020-02-13 09:00 | 2020-06-17 18:00 |  |  | 2020-02-29 08:00 | 2020-03-24 16:05 |  |  | 100 | 100 | [15 empty] | 0.35971 | 0.007626 | 0.75 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3728 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018886
1361 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.11.2.3 | Unscheduled | No | No | 2020-01-23 09:00 | 2020-02-05 18:00 | 2020-03-10 09:00 | 2020-08-17 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.033573 | 0.000712 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3730 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018887
1362 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.11.2.3 | Unscheduled | No | No | 2020-01-15 09:00 | 2020-02-01 18:00 | 2020-03-07 09:00 | 2020-08-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3731 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018888
1363 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.11.2.3 | Completed | No | No | 2020-01-19 | 2020-01-31 18:00 | 2020-01-16 09:00 | 2020-02-01 18:00 |  |  | 2020-02-01 10:57 | 2020-02-01 10:57 |  |  | 100 | 100 | [15 empty] | 0.0047962 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3732 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018889
1364 | Task(Task)-->P (Procurement) | ITP APPROVAL | 1.11.2.4 | 1.11.2 | Work In Progress | No | No | 2020-01-08 09:00 | 2020-08-27 18:00 | 2020-05-01 09:00 | 2020-12-14 18:00 |  |  | 2020-05-01 10:26 |  |  |  | 100 | 20.093 | [15 empty] | 5.0951 | 1.0812 | 106.33 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3733 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018890
1365 | Task(Task)-->P (Procurement) | Pulley |  | 1.11.2.4 | Unscheduled | No | No | 2020-04-04 09:00 | 2020-05-13 18:00 | 2020-07-16 09:00 | 2020-07-16 18:00 | [6 empty] | 100 | 0 | [15 empty] | 3.1127 | 0.033654 | 3.31 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3734 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018891
1366 | Task(Task)-->P (Procurement) | Idler |  | 1.11.2.4 | Unscheduled | No | No | 2020-03-03 09:00 | 2020-04-11 18:00 | 2020-08-22 09:00 | 2020-10-10 18:00 |  |  | 2020-08-22 16:23 |  |  |  | 100 | 10 | [15 empty] | 16.8986 | 0.18271 | 17.97 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3735 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018892
1367 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.11.2.4 | Unscheduled | No | No | 2020-07-02 09:00 | 2020-08-10 18:00 | 2020-07-07 09:00 | 2020-08-13 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.2539 | 0.002745 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3736 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018893
1368 | Task(Task)-->P (Procurement) | Bearing |  | 1.11.2.4 | Unscheduled | No | No | 2020-07-17 09:00 | 2020-08-25 18:00 | 2020-05-18 09:00 | 2020-05-25 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.56423 | 0.006101 | 0.6 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3737 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018894
1369 | Task(Task)-->P (Procurement) | Belting |  | 1.11.2.4 | Unscheduled | No | No | 2020-05-12 09:00 | 2020-06-20 18:00 | 2020-09-04 09:00 | 2020-10-15 18:00 |  |  | 2020-09-04 16:30 |  |  |  | 100 | 50 | [15 empty] | 31.6532 | 0.34224 | 33.66 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3738 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018895
1370 | Task(Task)-->P (Procurement) | Scrapper |  | 1.11.2.4 | Completed | No | No | 2020-04-16 09:00 | 2020-05-25 18:00 | 2020-05-30 09:00 | 2020-06-25 18:00 |  |  | 2020-05-30 16:32 | 2020-06-25 16:32 |  |  | 100 | 100 | [15 empty] | 0.018808 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3739 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018896
1371 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.11.2.4 | Unscheduled | No | No | 2020-04-20 09:00 | 2020-05-29 18:00 | 2020-07-06 09:00 | 2020-07-16 18:00 | [6 empty] | 100 | 0 | [15 empty] | 1.1943 | 0.012913 | 1.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3740 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018897
1372 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.11.2.4 | Unscheduled | No | No | 2020-07-19 | 2020-08-27 18:00 | 2020-10-11 | 2020-11-19 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.42317 | 0.004575 | 0.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3741 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018898
1373 | Task(Task)-->P (Procurement) | Gear Box |  | 1.11.2.4 | Completed | No | No | 2020-06-21 | 2020-07-30 18:00 | 2020-06-23 09:00 | 2020-06-23 18:00 |  |  | 2020-06-22 16:57 | 2020-06-22 16:57 |  |  | 100 | 100 | [15 empty] | 1.608 | 0.017386 | 1.71 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3742 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018899
1374 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.11.2.4 | Completed | No | No | 2020-04-19 | 2020-05-28 18:00 | 2020-06-16 09:00 | 2020-06-18 18:00 |  |  | 2020-06-16 17:31 | 2020-06-18 17:31 |  |  | 100 | 100 | [15 empty] | 0.34794 | 0.003762 | 0.37 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3743 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018900
1375 | Task(Task)-->P (Procurement) | Brake |  | 1.11.2.4 | Unscheduled | No | No | 2020-05-06 09:00 | 2020-06-14 23:59 | 2020-07-03 09:00 | 2020-10-30 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.11285 | 0.00122 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3744 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018901
1376 | Task(Task)-->P (Procurement) | Maintenance Trolley |  | 1.11.2.4 | Unscheduled | No | No | 2020-01-08 09:00 | 2020-02-16 23:59 | 2020-11-05 09:00 | 2020-12-14 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.29152 | 0.003152 | 0.31 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3745 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018902
1377 | Task(Task)-->P (Procurement) | Building Structure |  | 1.11.2.4 | Unscheduled | No | No | 2020-04-27 09:00 | 2020-05-03 23:59 | 2020-05-31 | 2020-08-04 18:00 |  |  | 2020-06-25 19:04 |  |  |  | 100 | 0 | [15 empty] | 34.9069 | 0.37742 | 37.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3746 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018903
1378 | Task(Task)-->P (Procurement) | 6.6KV HT VFD with Motors |  | 1.11.2.4 | Unscheduled | No | No | 2020-02-29 09:00 | 2020-04-08 18:00 | 2020-08-01 09:00 | 2020-09-09 18:00 | [6 empty] | 100 | 0 | [15 empty] | 7.8616 | 0.085 | 8.36 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3747 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018904
1379 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.11.2.4 | Completed | No | No | 2020-04-11 09:00 | 2020-05-20 18:00 | 2020-07-28 09:00 | 2020-09-08 18:00 |  |  | 2020-07-08 17:23 | 2020-09-08 17:23 |  |  | 100 | 100 | [15 empty] | 0.2539 | 0.002745 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3748 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018905
1380 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.11.2.4 | Unscheduled | No | No | 2020-06-26 09:00 | 2020-08-04 18:00 | 2020-06-23 09:00 | 2020-09-08 18:00 |  |  | 2020-06-23 17:44 |  |  |  | 100 | 0 | [15 empty] | 0.11285 | 0.00122 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3749 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018906
1381 | Task(Task)-->P (Procurement) | WELDING DISTRIBUTION BOARD |  | 1.11.2.4 | Completed | No | No | 2020-03-15 | 2020-04-23 18:00 | 2020-05-01 09:00 | 2020-05-19 18:00 |  |  | 2020-05-01 10:26 | 2020-05-19 10:26 |  |  | 100 | 100 | [15 empty] | 0.34794 | 0.003762 | 0.37 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3750 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018907
1382 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.11.2.4 | Unscheduled | No | No | 2020-02-06 09:00 | 2020-03-16 18:00 | 2020-09-24 09:00 | 2020-10-30 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.037615 | 0.000407 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3752 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018908
1383 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.11.2.4 | Unscheduled | No | No | 2020-02-02 | 2020-03-12 18:00 | 2020-08-02 | 2020-09-10 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3753 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018909
1384 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.11.2.4 | Unscheduled | No | No | 2020-02-01 09:00 | 2020-03-11 18:00 | 2020-07-02 09:00 | 2020-08-04 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3754 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018910
1385 | Task(Task)-->P (Procurement) | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE | 1.11.2.5 | 1.11.2 | Work In Progress | No | No | 2020-01-08 09:00 | 2020-09-01 18:00 | 2020-02-01 09:00 | 2021-01-13 18:00 |  |  | 2020-02-11 21:30 |  |  |  | 100 | 60.6881 | [15 empty] | 14.9852 | 3.18 | 312.73 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3755 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018911
1386 | Task(Task)-->P (Procurement) | Pulley |  | 1.11.2.5 | Unscheduled | No | No | 2020-04-04 09:00 | 2020-06-02 18:00 | 2020-07-16 09:00 | 2020-07-16 18:00 | [6 empty] | 100 | 0 | [15 empty] | 3.1785 | 0.10107 | 9.94 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3756 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018912
1387 | Task(Task)-->P (Procurement) | Idler |  | 1.11.2.5 | Unscheduled | No | No | 2020-03-03 09:00 | 2020-05-01 18:00 | 2020-08-22 09:00 | 2020-10-15 18:00 | [6 empty] | 100 | 0 | [15 empty] | 17.2385 | 0.54818 | 53.91 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3757 | 1 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018913
1388 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.11.2.5 | Unscheduled | No | No | 2020-07-02 09:00 | 2020-08-30 23:59 | 2020-07-07 09:00 | 2020-09-28 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.25581 | 0.008135 | 0.8 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3758 | 1 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018914
1389 | Task(Task)-->P (Procurement) | Bearing |  | 1.11.2.5 | Unscheduled | No | No | 2020-07-17 09:00 | 2020-07-17 18:00 | 2020-07-18 09:00 | 2020-08-22 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.57558 | 0.018303 | 1.8 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3759 | 1 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018915
1390 | Task(Task)-->P (Procurement) | Belting |  | 1.11.2.5 | Unscheduled | No | No | 2020-05-12 09:00 | 2020-07-20 18:00 | 2020-09-04 09:00 | 2020-10-15 18:00 |  |  | 2020-09-04 16:36 |  |  |  | 100 | 50 | [15 empty] | 32.2898 | 1.0268 | 100.98 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3760 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018916
1391 | Task(Task)-->P (Procurement) | Scrapper |  | 1.11.2.5 | Completed | No | No | 2020-04-16 09:00 | 2020-06-14 23:59 | 2020-05-30 09:00 | 2020-07-30 18:00 |  |  | 2020-05-30 16:34 | 2020-07-30 16:34 |  |  | 100 | 100 | [15 empty] | 0.019186 | 0.00061 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3761 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018917
1392 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.11.2.5 | Completed | No | No | 2020-04-20 09:00 | 2020-08-17 18:00 | 2020-07-06 09:00 | 2020-07-06 18:00 |  |  | 2020-07-06 12:45 | 2020-07-06 12:45 |  |  | 100 | 100 | [15 empty] | 1.2151 | 0.03864 | 3.8 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3762 | 0 | 4 | High | [7 empty] | 0 | 0 | [244 empty] | 1018918
1393 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.11.2.5 | Unscheduled | No | No | 2020-07-19 | 2020-09-01 18:00 | 2020-10-11 | 2020-11-24 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.43488 | 0.013829 | 1.36 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3763 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018919
1394 | Task(Task)-->P (Procurement) | Gear Box |  | 1.11.2.5 | Unscheduled | No | No | 2020-06-21 | 2020-08-19 18:00 | 2020-06-23 09:00 | 2020-10-16 18:00 |  |  | 2020-06-23 16:57 |  |  |  | 100 | 50 | [15 empty] | 1.6372 | 0.052063 | 5.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3764 | 1 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018920
1395 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.11.2.5 | Completed | No | No | 2020-04-19 | 2020-06-17 18:00 | 2020-06-16 09:00 | 2020-09-02 18:00 |  |  | 2020-06-16 17:31 | 2020-09-02 17:31 |  |  | 100 | 100 | [15 empty] | 0.35494 | 0.011287 | 1.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3765 | 1 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018921
1396 | Task(Task)-->P (Procurement) | Brake |  | 1.11.2.5 | Unscheduled | No | No | 2020-05-06 09:00 | 2020-07-04 18:00 | 2020-07-03 09:00 | 2020-10-10 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.10872 | 0.003457 | 0.34 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3766 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018922
1397 | Task(Task)-->P (Procurement) | Maintenance Trolley |  | 1.11.2.5 | Unscheduled | No | No | 2020-01-08 09:00 | 2020-03-17 18:00 | 2020-11-05 09:00 | 2021-01-13 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.30058 | 0.009558 | 0.94 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3767 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018923
1398 | Task(Task)-->P (Procurement) | Building Structure |  | 1.11.2.5 | Completed | No | No | 2020-04-25 09:00 | 2020-05-01 18:00 | 2020-05-31 | 2020-06-22 18:00 |  |  | 2020-05-31 18:54 | 2020-05-31 18:54 |  |  | 100 | 100 | [15 empty] | 35.6058 | 1.1323 | 111.35 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3768 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018924
1399 | Task(Task)-->P (Procurement) | 6.6KV HT VFD with Motors |  | 1.11.2.5 | Completed | No | No | 2020-02-29 09:00 | 2020-05-13 18:00 | 2020-08-08 09:00 | 2020-10-10 18:00 |  |  | 2020-07-28 11:51 | 2020-09-23 15:24 |  |  | 100 | 100 | [15 empty] | 6.018 | 0.19137 | 18.82 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3769 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018925
1400 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.11.2.5 | Unscheduled | No | No | 2020-04-11 09:00 | 2020-05-25 18:00 | 2020-07-10 09:00 | 2020-10-16 18:00 |  |  | 2020-07-14 10:44 |  |  |  | 100 | 0 | [15 empty] | 0.25581 | 0.008135 | 0.8 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3770 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018926
1401 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.11.2.5 | Completed | No | No | 2020-06-26 09:00 | 2020-08-09 23:59 | 2020-05-30 09:00 | 2020-08-08 18:00 |  |  | 2020-06-18 17:15 | 2020-08-07 15:00 |  |  | 100 | 100 | [15 empty] | 0.11512 | 0.003661 | 0.36 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3771 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018927
1402 | Task(Task)-->P (Procurement) | WELDING DISTRIBUTION BOARD |  | 1.11.2.5 | Completed | No | No | 2020-03-15 | 2020-04-28 18:00 | 2020-04-25 09:00 | 2020-07-17 18:00 |  |  | 2020-04-25 10:24 | 2020-07-17 10:24 |  |  | 100 | 100 | [15 empty] | 0.35814 | 0.011389 | 1.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3772 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018928
1403 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.11.2.5 | Completed | No | No | 2020-02-06 09:00 | 2020-03-21 18:00 | 2020-08-11 09:00 | 2020-09-19 18:00 |  |  | 2020-08-11 13:12 | 2020-09-19 12:58 |  |  | 100 | 100 | [15 empty] | 0.035174 | 0.001119 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3774 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018929
1404 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.11.2.5 | Unscheduled | No | No | 2020-02-02 | 2020-03-17 18:00 | 2020-08-09 | 2020-10-20 18:00 |  |  | 2020-08-09 13:17 |  |  |  | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3775 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018930
1405 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.11.2.5 | Completed | No | No | 2020-02-01 09:00 | 2020-03-16 18:00 | 2020-02-01 09:00 | 2020-07-15 18:00 |  |  | 2020-02-11 21:30 | 2020-07-15 21:31 |  |  | 100 | 100 | [15 empty] | 0.0031976 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3776 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018931
1406 | Task(Task)-->P (Procurement) | MANUFACTURING & RECEIPT AT SITE (MRN) | 1.11.2.6 | 1.11.2 | Unscheduled | No | No | 2020-03-17 09:00 | 2021-03-31 18:00 | 2020-06-22 09:00 | 2022-01-22 18:00 |  |  | 2020-07-15 21:39 |  |  |  | 42.3852 | 0.10648 | [15 empty] | 59.94 | 12.7197 | 1250.9 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3777 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018932
1407 | Task(Task)-->P (Procurement) | Pulley |  | 1.11.2.6 | Unscheduled | No | No | 2020-06-03 09:00 | 2021-03-31 18:00 | 2020-07-16 09:00 | 2021-03-31 18:00 | [6 empty] | 42.053 | 0 | [15 empty] | 3.1777 | 0.4042 | 39.75 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3778 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018933
1408 | Task(Task)-->P (Procurement) | Idler |  | 1.11.2.6 | Unscheduled | No | No | 2020-05-02 09:00 | 2021-03-28 23:59 | 2020-10-16 09:00 | 2021-09-11 18:00 | [6 empty] | 48.0363 | 0 | [15 empty] | 17.2381 | 2.1926 | 215.63 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3779 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018934
1409 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.11.2.6 | Unscheduled | No | No | 2020-08-31 09:00 | 2021-02-01 18:00 | 2020-09-28 09:00 | 2021-03-15 18:00 | [6 empty] | 24.5161 | 0 | [15 empty] | 0.25742 | 0.032743 | 3.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3780 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018935
1410 | Task(Task)-->P (Procurement) | Bearing |  | 1.11.2.6 | Unscheduled | No | No | 2020-08-26 09:00 | 2021-01-22 18:00 | 2020-08-22 09:00 | 2021-03-31 18:00 | [6 empty] | 28.6667 | 0 | [15 empty] | 0.57559 | 0.073214 | 7.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3781 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018936
1411 | Task(Task)-->P (Procurement) | Belting |  | 1.11.2.6 | Unscheduled | No | No | 2020-07-21 09:00 | 2021-03-31 18:00 | 2020-10-16 09:00 | 2021-06-26 18:00 | [6 empty] | 31.1024 | 0 | [15 empty] | 32.2898 | 4.1072 | 403.91 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3782 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018937
1412 | Task(Task)-->P (Procurement) | Scrapper |  | 1.11.2.6 | Unscheduled | No | No | 2020-06-15 09:00 | 2020-12-11 18:00 | 2020-07-30 09:00 | 2020-12-31 18:00 | [6 empty] | 63.8889 | 0 | [15 empty] | 0.017587 | 0.002237 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3783 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018938
1413 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.11.2.6 | Unscheduled | No | No | 2020-06-19 09:00 | 2021-03-15 18:00 | 2020-07-06 09:00 | 2021-01-31 23:59 | [6 empty] | 41.1111 | 0 | [15 empty] | 1.2151 | 0.15456 | 15.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3784 | 0 | 4 | High | [7 empty] | 0 | 0 | [244 empty] | 1018939
1414 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.11.2.6 | Unscheduled | No | No | 2020-09-02 09:00 | 2021-01-29 18:00 | 2020-11-25 09:00 | 2021-04-23 18:00 | [6 empty] | 24 | 0 | [15 empty] | 0.43569 | 0.055419 | 5.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3785 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018940
1415 | Task(Task)-->P (Procurement) | Gear Box |  | 1.11.2.6 | Unscheduled | No | No | 2020-08-20 09:00 | 2021-02-20 18:00 | 2020-10-17 09:00 | 2021-04-19 18:00 | [6 empty] | 26.4865 | 0 | [15 empty] | 1.6372 | 0.20825 | 20.48 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3786 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018941
1416 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.11.2.6 | Unscheduled | No | No | 2020-06-18 09:00 | 2020-12-15 18:00 | 2020-09-02 09:00 | 2021-02-09 18:00 |  |  | 2020-09-02 17:44 |  |  |  | 61.8785 | 30 | [15 empty] | 0.35495 | 0.045148 | 4.44 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3787 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018942
1417 | Task(Task)-->P (Procurement) | Brake |  | 1.11.2.6 | Unscheduled | No | No | 2020-07-05 | 2021-02-10 18:00 | 2020-10-31 09:00 | 2021-06-08 18:00 | [6 empty] | 42.9864 | 0 | [15 empty] | 0.11032 | 0.014033 | 1.38 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3788 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018943
1418 | Task(Task)-->P (Procurement) | Maintenance Trolley |  | 1.11.2.6 | Unscheduled | No | No | 2020-03-18 09:00 | 2021-03-26 18:00 | 2021-01-14 09:00 | 2022-01-22 18:00 | [6 empty] | 54.5455 | 0 | [15 empty] | 0.29979 | 0.038132 | 3.75 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3789 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018944
1419 | Task(Task)-->P (Procurement) | Building Structure |  | 1.11.2.6 | Unscheduled | No | No | 2020-05-04 09:00 | 2021-03-19 18:00 | 2020-06-22 09:00 | 2021-03-31 18:00 | [6 empty] | 49.0625 | 0 | [15 empty] | 35.6058 | 4.529 | 445.39 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3790 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018945
1420 | Task(Task)-->P (Procurement) | 6.6KV HT VFD with Motors |  | 1.11.2.6 | Unscheduled | No | No | 2020-05-14 09:00 | 2021-03-09 18:00 | 2020-10-11 | 2021-08-06 18:00 | [6 empty] | 49 | 0 | [15 empty] | 6.0181 | 0.76549 | 75.28 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3791 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018946
1421 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.11.2.6 | Unscheduled | No | No | 2020-05-26 09:00 | 2021-02-18 18:00 | 2020-10-17 09:00 | 2021-07-12 18:00 | [6 empty] | 50.1859 | 0 | [15 empty] | 0.25502 | 0.032438 | 3.19 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3792 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018947
1422 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.11.2.6 | Unscheduled | No | No | 2020-08-10 09:00 | 2020-11-07 18:00 | 2020-09-09 09:00 | 2020-12-07 18:00 |  |  | 2020-08-07 15:03 |  |  |  | 65.5556 | 0 | [15 empty] | 0.11592 | 0.014744 | 1.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3793 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018948
1423 | Task(Task)-->P (Procurement) | WELDING DISTRIBUTION BOARD |  | 1.11.2.6 | Unscheduled | No | No | 2020-04-29 09:00 | 2020-09-26 18:00 | 2020-07-18 09:00 | 2020-12-15 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.35894 | 0.045657 | 4.49 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3794 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018949
1424 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.11.2.6 | Unscheduled | No | No | 2020-03-22 | 2020-08-05 18:00 | 2020-10-31 09:00 | 2021-03-16 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.033576 | 0.004271 | 0.42 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3796 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018950
1425 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.11.2.6 | Unscheduled | No | No | 2020-03-18 09:00 | 2020-07-27 18:00 | 2020-10-21 09:00 | 2021-03-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.00079943 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3797 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018951
1426 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.11.2.6 | Unscheduled | No | No | 2020-03-17 09:00 | 2020-07-31 18:00 | 2020-07-02 09:00 | 2020-11-15 23:59 |  |  | 2020-07-15 21:39 |  |  |  | 100 | 0 | [15 empty] | 0.0023983 | 0.000305 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3798 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018952
1427 | Task(Task)-->C (Construction) | CONSTRUCTION | 1.11.3 | 1.11 | Unscheduled | No | No | 2020-05-22 | 2021-09-13 18:00 | 2020-08-26 09:00 | 2022-04-05 18:00 | [6 empty] | 19.0498 | 0.00506 | [15 empty] | 25.3644 | 7.2633 | 714.3 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3799 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018953
1428 | Task(Task)-->C (Construction) | CIVIL | 1.11.3.1 | 1.11.3 | Unscheduled | No | No | 2020-05-22 | 2021-05-26 18:00 | 2020-08-26 09:00 | 2021-09-08 18:00 | [6 empty] | 49.8634 | 0.02056 | [15 empty] | 24.6199 | 1.7882 | 175.86 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3800 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018954
1429 | Task(Task)-->C (Construction) | AVAILABILITY OF FRONT BY NTPC |  | 1.11.3.1 | Unscheduled | No | No | 2020-07-06 09:00 | 2020-07-06 18:00 | 2020-08-26 09:00 | 2020-08-26 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | Weekly | Cumulative | 0 | No | No | 3801 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018955
1430 | Task(Task)-->C (Construction) | APPROACH IN PIPE CONVEYOR CORRIDOR |  | 1.11.3.1 | Unscheduled | No | No | 2020-07-07 09:00 | 2021-05-02 23:59 | 2020-08-27 09:00 | 2021-06-22 18:00 | [6 empty] | 31 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5610 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018956
1431 | Task(Task)-->C (Construction) | EXCAVATION |  | 1.11.3.1 | Unscheduled | No | No | 2020-07-13 09:00 | 2021-05-08 18:00 | 2020-10-26 09:00 | 2021-08-21 18:00 | [6 empty] | 29 | 0 | [15 empty] | 11.1339 | 0.1991 | 19.58 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 73381 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | Weekly | Cumulative | 0 | No | No | 3802 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | Excavation | [21 empty] | 1018957
1432 | Task(Task)-->C (Construction) | PCC |  | 1.11.3.1 | Unscheduled | No | No | 2020-05-22 | 2021-05-11 18:00 | 2020-10-29 09:00 | 2021-08-24 18:00 | [6 empty] | 445.1065 | 0.36969 | [15 empty] | 5.5612 | 0.099447 | 9.78 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 1082 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | Weekly | Cumulative | 0 | No | No | 3803 | 0 | 4 | Low | ADMINISTRATOR | [6 empty] | 0 | 0 | [222 empty] | PCC | [21 empty] | 1018958
1433 | Task(Task)-->C (Construction) | RAFT OF FOUNDATIONS |  | 1.11.3.1 | Unscheduled | No | No | 2020-07-17 09:00 | 2021-05-12 18:00 | 2020-10-30 09:00 | 2021-08-25 18:00 | [6 empty] | 27.6667 | 0 | [15 empty] | 58.3077 | 1.0427 | 102.54 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 3865 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3804 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018959
1434 | Task(Task)-->C (Construction) | PEDESTALS |  | 1.11.3.1 | Unscheduled | No | No | 2020-07-31 09:00 | 2021-05-26 18:00 | 2020-11-13 09:00 | 2021-09-08 18:00 | [6 empty] | 23 | 0 | [15 empty] | 24.9972 | 0.447 | 43.96 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 1657 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3805 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018960
1435 | Task(Task)-->C (Construction) | STRUCTURAL WORKS | 1.11.3.2 | 1.11.3 | Unscheduled | No | No | 2020-08-28 09:00 | 2021-06-23 18:00 | 2020-12-11 09:00 | 2021-10-06 18:00 | [6 empty] | 13.6667 | 0 | [15 empty] | 47.5304 | 3.4523 | 339.51 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3806 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018961
1436 | Task(Task)-->C (Construction) | ERECTION OF STRUCTURAL STEEL |  | 1.11.3.2 | Unscheduled | No | No | 2020-08-28 09:00 | 2021-06-23 18:00 | 2020-12-11 09:00 | 2021-10-06 18:00 | [6 empty] | 13.6667 | 0 | [15 empty] | 100 | 3.4523 | 339.51 | Plan & Actual | Quantity | Metric Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 5250 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3807 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018962
1437 | Task(Task)-->C (Construction) | MECHANICAL EQUIPMENT WORKS | 1.11.3.3 | 1.11.3 | Unscheduled | No | No | 2020-09-17 09:00 | 2021-07-13 18:00 | 2021-01-14 09:00 | 2021-11-09 18:00 | [6 empty] | 4.2003 | 0 | [15 empty] | 6.6107 | 0.48015 | 47.22 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5469 | 0 | 3 | High | [7 empty] | 0 | 0 | [244 empty] | 1018963
1438 | Task(Task)-->C (Construction) | ERECTION OF TECHNOLOGICAL STR. & IDLERS |  | 1.11.3.3 | Unscheduled | No | No | 2020-09-17 09:00 | 2021-07-13 18:00 | 2021-01-14 09:00 | 2021-11-09 18:00 | [6 empty] | 7 | 0 | [15 empty] | 60.0042 | 0.28811 | 28.34 | Plan & Actual | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3808 | 0 | 4 | High | [7 empty] | 0 | 0 | [244 empty] | 1018964
1439 | Task(Task)-->C (Construction) | ERECTION OF PULLEYS WITH FRAME |  | 1.11.3.3 | Unscheduled | No | No | 2021-04-01 09:00 | 2021-05-30 23:59 | 2021-08-16 09:00 | 2021-10-14 18:00 | [6 empty] | 0 | 0 | [15 empty] | 10.3536 | 0.049713 | 4.89 | Plan & Actual | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5433 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018965
1440 | Task(Task)-->C (Construction) | ERECTION OF DRIVES (MOTOR, GEAR BOX, COUPLING) |  | 1.11.3.3 | Unscheduled | No | No | 2021-03-10 09:00 | 2021-05-08 18:00 | 2021-08-07 09:00 | 2021-10-05 18:00 | [6 empty] | 0 | 0 | [15 empty] | 11.751 | 0.056423 | 5.55 | Plan & Actual | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5434 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018966
1441 | Task(Task)-->C (Construction) | ERECTION OF TAKE-UP COMPONENTS |  | 1.11.3.3 | Unscheduled | No | No | 2021-01-30 09:00 | 2021-03-30 18:00 | 2021-04-24 09:00 | 2021-06-22 18:00 | [6 empty] | 0 | 0 | [15 empty] | 17.8912 | 0.085905 | 8.45 | Plan & Actual | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5435 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018967
1442 | Task(Task)-->C (Construction) | BELT LAYING & JOINTING WORK |  | 1.11.3 | Unscheduled | No | No | 2021-05-03 09:00 | 2021-08-30 18:00 | 2021-08-30 09:00 | 2021-12-27 18:00 | [6 empty] | 0 | 0 | [15 empty] | 9.2104 | 0.66898 | 65.79 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 22600 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3809 | 0 | 3 | High | [7 empty] | 0 | 0 | [244 empty] | 1018968
1443 | Task(Task)-->C (Construction) | MAINTENANCE TROLLEY |  | 1.11.3 | Unscheduled | No | No | 2021-06-24 09:00 | 2021-07-07 18:00 | 2022-01-23 | 2022-02-05 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0.046199 | 0.003356 | 0.33 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5472 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018969
1444 | Task(Task)-->C (Construction) | ELECTRICAL & INSTRUMENTATION | 1.11.3.6 | 1.11.3 | Unscheduled | No | No | 2021-05-23 | 2021-08-30 18:00 | 2021-09-05 | 2022-03-22 18:00 | [6 empty] | 0 | 0 | [15 empty] | 11.7668 | 0.85466 | 84.05 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3810 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018970
1445 | Task(Task)-->C (Construction) | CABLE TRAY |  | 1.11.3.6 | Unscheduled | No | No | 2021-06-03 09:00 | 2021-07-07 18:00 | 2021-09-16 09:00 | 2021-10-20 18:00 | [6 empty] | 0 | 0 | [15 empty] | 21.9564 | 0.18765 | 18.45 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 43200 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3811 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018971
1446 | Task(Task)-->C (Construction) | POWER CABLE |  | 1.11.3.6 | Unscheduled | No | No | 2021-07-08 09:00 | 2021-08-04 18:00 | 2021-10-21 09:00 | 2021-11-17 18:00 | [6 empty] | 0 | 0 | [15 empty] | 20.6593 | 0.17657 | 17.36 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 122676 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3812 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018972
1447 | Task(Task)-->C (Construction) | CONTROL CABLE |  | 1.11.3.6 | Unscheduled | No | No | 2021-07-26 09:00 | 2021-08-04 18:00 | 2021-11-08 09:00 | 2021-11-17 18:00 | [6 empty] | 0 | 0 | [15 empty] | 4.8792 | 0.0417 | 4.1 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 29000 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3813 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018973
1448 | Task(Task)-->C (Construction) | EARTHING |  | 1.11.3.6 | Unscheduled | No | No | 2021-06-05 09:00 | 2021-07-07 18:00 | 2021-09-18 09:00 | 2021-10-20 18:00 | [6 empty] | 0 | 0 | [15 empty] | 8.7588 | 0.074857 | 7.36 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 33000 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3814 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018974
1449 | Task(Task)-->C (Construction) | EARTH PIT |  | 1.11.3.6 | Unscheduled | No | No | 2021-05-23 | 2021-05-26 18:00 | 2021-09-05 | 2021-09-08 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5324 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018975
1450 | Task(Task)-->C (Construction) | LIGHTING |  | 1.11.3.6 | Unscheduled | No | No | 2021-05-23 | 2021-07-07 18:00 | 2021-09-05 | 2021-10-20 18:00 | [6 empty] | 0 | 0 | [15 empty] | 41.8184 | 0.3574 | 35.14 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5325 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018976
1451 | Task(Task)-->C (Construction) | FIELD INTRUMENTS |  | 1.11.3.6 | Unscheduled | No | No | 2021-08-03 09:00 | 2021-08-05 18:00 | 2021-11-16 09:00 | 2021-11-18 18:00 | [6 empty] | 0 | 0 | [15 empty] | 1.5352 | 0.01312 | 1.29 | Plan & Actual | Quantity | Lot | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5326 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018977
1452 | Task(Task)-->C (Construction) | MOTOR TERMINATION |  | 1.11.3.6 | Unscheduled | No | No | 2021-08-02 09:00 | 2021-08-05 18:00 | 2021-11-15 09:00 | 2021-11-18 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0.39272 | 0.003356 | 0.33 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5327 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018978
1453 | Task(Task)-->C (Construction) | NO LOAD RUN OF MOTOR |  | 1.11.3.6 | Unscheduled | No | No | 2021-08-27 09:00 | 2021-08-30 18:00 | 2022-03-19 09:00 | 2022-03-22 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5473 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018979
1454 | Task(Task)-->C (Construction) | NO LOAD COMMISSIONING & SYSTEM READYNESS FOR LOAD & TRIAL OPERATION |  | 1.11.3 | Unscheduled | No | No | 2021-08-31 09:00 | 2021-09-13 18:00 | 2022-03-23 09:00 | 2022-04-05 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0.2156 | 0.015659 | 1.54 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5328 | 0 | 3 | High | [7 empty] | 0 | 0 | [244 empty] | 1018980
1455 | Task(Task)-->E (Engineering) | TROUGH CONVEYOR SY 3A & SY 3B | 1.12 | 1 | Work In Progress | No | No | 2019-09-27 09:00 | 2021-09-08 18:00 | 2019-12-30 09:00 | 2022-03-06 23:59 |  |  | 2019-12-30 10:57 |  |  |  | 78.5609 | 25.4027 | [15 empty] | 0.82924 | 0.82924 | 81.55 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3815 | 0 | 1 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018981
1456 | Task(Task)-->E (Engineering) | ENGINEERING | 1.12.1 | 1.12 | Work In Progress | No | No | 2019-12-17 18:00 | 2020-06-29 17:40 | 2020-01-28 18:00 | 2020-09-03 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 81.2646 | [15 empty] | 1.9742 | 0.016371 | 1.61 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3816 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018982
1457 | Task(Task)-->E (Engineering) | MECHANICAL | 1.12.1.1 | 1.12.1 | Unscheduled | No | No | 2019-12-17 18:00 | 2020-02-06 17:40 | 2020-01-28 18:00 | 2020-04-19 23:59 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 80 | [15 empty] | 33.5404 | 0.005491 | 0.54 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3817 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036106
1458 | Task(Task)-->E (Engineering) | G.A & MARKING OF CONV. SY-1A / 1B |  | 1.12.1.1 | Unscheduled | No | No | 2019-12-17 18:00 | 2020-02-06 17:40 | 2020-01-28 18:00 | 2020-04-19 23:59 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-0021 |  | 2020-02-13 10:26 | 7012-155-PVM-B-021 |  |  |  | A |  |  |  | 100 | 0.005491 | 0.54 | Plan & Actual | Date |  | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3818 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-12-17 18:00 | 2020-01-28 18:00 |  | 10 | 2020-01-28 23:31 |  |  | 2019-12-30 17:40 | 2020-02-12 18:00 |  | 30 | 2020-02-12 23:31 |  |  | 2020-01-04 17:40 | 2020-02-14 18:00 |  | 35 | 2020-02-14 23:31 |  |  | 2020-01-10 23:59 | 2020-02-21 18:00 |  | 65 | 2020-02-21 23:31 |  |  | 2020-01-16 17:40 | 2020-04-05 23:59 |  | 80 | 2020-04-05 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-02-06 17:40 | 2020-04-19 23:59 |  | 100 | [122 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 21 |  |  |  | 101035
1459 | Task(Task)-->E (Engineering) | CIVIL | 1.12.1.2 | 1.12.1 | Work In Progress | No | No | 2020-02-23 23:59 | 2020-05-25 17:40 | 2020-05-05 18:00 | 2020-09-03 18:00 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 87.2716 | [15 empty] | 17.3913 | 0.002847 | 0.28 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3841 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036107
1460 | Task(Task)-->E (Engineering) | CONV. SY-1A / 1B : NUM & RC DETAILS OF FDN |  | 1.12.1.2 | Completed | No | No | 2020-03-24 18:00 | 2020-05-25 17:40 | 2020-08-12 09:00 | 2020-09-01 18:00 |  |  | 2020-02-21 15:37 | 2020-09-02 00:38 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-NR-0024 |  | 2020-02-13 11:42 | 7012-155-PVC-C-073 |  |  |  | A |  |  |  | 36.3636 | 0.001035 | 0.16 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 4.31 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3842 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-24 18:00 | 2020-05-05 18:00 |  | 10 |  |  |  | 2020-04-13 17:40 | 2020-06-24 18:00 |  | 30 |  |  |  | 2020-04-18 17:40 | 2020-06-27 18:00 |  | 35 | 2020-08-12 17:50 |  |  | 2020-04-24 23:59 | 2020-07-04 18:00 |  | 65 | 2020-08-13 19:57 |  |  | 2020-05-01 17:40 | 2020-07-25 18:00 |  | 80 | 2020-09-01 23:28 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-25 17:40 | 2020-08-08 18:00 |  | 100 | 2020-09-02 00:39 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 174 |  |  |  | 101184
1461 | Task(Task)-->E (Engineering) | CONV. SY-1A / 1B : DESIGN CALCULATION OF SUPER STRUCTURE |  | 1.12.1.2 | Completed | No | No | 2020-02-23 23:59 | 2020-04-23 17:40 | 2020-08-07 09:00 | 2020-09-01 18:00 |  |  | 2020-02-21 15:38 | 2020-09-02 00:38 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0020B |  | 2020-02-13 12:42 | 7012-155-PVC-U-070 |  |  |  | A |  |  |  | 27.2727 | 0.000776 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3843 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-23 23:59 | 2020-04-05 23:59 |  | 10 | 2020-04-05 23:31 |  |  | 2020-03-12 17:40 | 2020-05-25 18:00 |  | 30 |  |  |  | 2020-03-19 17:40 | 2020-05-28 18:00 |  | 35 |  |  |  | 2020-03-25 23:59 | 2020-06-04 18:00 |  | 65 | 2020-08-13 19:58 |  |  | 2020-04-01 17:40 | 2020-06-25 18:00 |  | 80 | 2020-09-01 23:27 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-23 17:40 | 2020-07-09 18:00 |  | 100 | 2020-09-02 00:39 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 171 |  |  |  | 101466
1462 | Task(Task)-->E (Engineering) | CONV. SY-1A / 1B : DESIGN CALCULATION OF SUB STRUCTURE |  | 1.12.1.2 | Unscheduled | No | No | 2020-03-24 18:00 | 2020-05-25 17:40 | 2020-05-05 18:00 | 2020-09-03 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0021B |  | 2020-02-13 12:42 | 7012-155-PVC-U-071 |  |  |  | A |  |  |  | 36.3636 | 0.001035 | 0.16 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3844 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-24 18:00 | 2020-05-05 18:00 |  | 10 | 2020-05-05 23:31 |  |  | 2020-04-13 17:40 | 2020-06-24 18:00 |  | 30 |  |  |  | 2020-04-18 17:40 | 2020-06-27 18:00 |  | 35 |  |  |  | 2020-04-24 23:59 | 2020-07-04 18:00 |  | 65 | 2020-08-13 19:58 |  |  | 2020-05-01 17:40 | 2020-07-25 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-25 17:40 | 2020-08-08 18:00 |  | 100 | [122 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 172 |  |  |  | 101467
1463 | Task(Task)-->E (Engineering) | STRUCTURAL | 1.12.1.3 | 1.12.1 | Unscheduled | No | No | 2020-02-23 23:59 | 2020-04-23 17:40 | 2020-04-05 23:59 | 2020-09-01 18:00 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 80 | [15 empty] | 7.4534 | 0.00122 | 0.12 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3845 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036108
1464 | Task(Task)-->E (Engineering) | CONV. SY-1A / 1B : STRUCTURAL GA |  | 1.12.1.3 | Unscheduled | No | No | 2020-02-23 23:59 | 2020-04-23 17:40 | 2020-04-05 23:59 | 2020-09-01 18:00 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-GA-0022 |  | 2020-02-13 11:42 | 7012-155-PVC-B-072 |  |  |  | A |  |  |  | 100 | 0.00122 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 43.49 | 0 | 31.1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3846 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-23 23:59 | 2020-04-05 23:59 |  | 10 | 2020-04-05 23:31 |  |  | 2020-03-12 17:40 | 2020-05-25 18:00 |  | 30 |  |  |  | 2020-03-19 17:40 | 2020-05-28 18:00 |  | 35 | 2020-07-31 22:52 |  |  | 2020-03-25 23:59 | 2020-06-04 18:00 |  | 65 | 2020-08-13 19:57 |  |  | 2020-04-01 17:40 | 2020-06-25 18:00 |  | 80 | 2020-09-01 23:30 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-23 17:40 | 2020-07-09 18:00 |  | 100 | [122 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 173 |  |  |  | 101183
1465 | Task(Task)-->E (Engineering) | ELECTRICAL | 1.12.1.4 | 1.12.1 | Unscheduled | No | No | 2020-05-09 18:00 | 2020-06-29 17:40 | 2020-04-28 09:00 | 2020-06-21 23:59 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 | [15 empty] | 41.6149 | 0.006813 | 0.67 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3849 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036109
1466 | Task(Task)-->E (Engineering) | LIGHTING LAYOUT PLAN WITH POWER DISTRIBUTION ARRANGEMENT, SECTIONAL VIEW, BOM OFCONV. SY-1A / 1B |  | 1.12.1.4 | Unscheduled | No | No | 2020-05-09 18:00 | 2020-06-29 17:40 | 2020-04-28 09:00 | 2020-06-21 23:59 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5082 |  | 2020-02-13 11:45 | 7012-155-PVE-G-044 |  |  |  | A |  |  |  | 100 | 0.006813 | 0.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 248.42 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3850 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-05-09 18:00 | 2020-05-10 23:59 |  | 10 | 2020-04-20 23:31 |  |  | 2020-05-18 17:40 | 2020-05-17 23:59 |  | 30 | 2020-04-25 23:31 |  |  | 2020-05-25 17:40 | 2020-05-24 23:59 |  | 35 | 2020-04-25 23:31 |  |  | 2020-05-30 23:59 | 2020-05-31 23:59 |  | 65 | 2020-04-28 23:31 |  |  | 2020-06-05 17:40 | 2020-06-21 23:59 |  | 80 | 2020-05-11 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-29 17:40 | 2020-06-21 23:59 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 279 |  |  |  | 101290
1467 | Task(Task)-->P (Procurement) | PROCUREMENT | 1.12.2 | 1.12 | Work In Progress | No | No | 2019-09-27 09:00 | 2021-02-13 18:00 | 2019-12-30 09:00 | 2021-05-13 18:00 |  |  | 2019-12-30 10:57 |  |  |  | 91.1009 | 29.1449 | [15 empty] | 81.6554 | 0.67712 | 66.59 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3851 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018987
1468 | Task(Task)-->P (Procurement) | PURCHASE REQUISITION | 1.12.2.1 | 1.12.2 | Work In Progress | No | No | 2019-09-27 09:00 | 2020-05-19 18:00 | 2019-12-30 09:00 | 2020-05-29 18:00 |  |  | 2019-12-30 10:57 |  |  |  | 100 | 100 | [15 empty] | 5.0008 | 0.033861 | 3.33 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3852 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018988
1469 | Task(Task)-->P (Procurement) | Pulley |  | 1.12.2.1 | Completed | No | No | 2019-09-27 09:00 | 2019-09-27 18:00 | 2020-02-05 09:00 | 2020-02-05 18:00 |  |  | 2020-02-05 16:16 | 2020-02-05 16:16 |  |  | 100 | 100 | [15 empty] | 15.015 | 0.005084 | 0.5 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3853 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018989
1470 | Task(Task)-->P (Procurement) | Idler |  | 1.12.2.1 | Completed | No | No | 2019-12-19 09:00 | 2019-12-19 18:00 | 2020-02-13 09:00 | 2020-02-13 18:00 |  |  | 2020-02-13 15:44 | 2020-02-13 15:44 |  |  | 100 | 100 | [15 empty] | 5.1051 | 0.001729 | 0.17 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3854 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018990
1471 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.12.2.1 | Completed | No | No | 2020-05-17 | 2020-05-17 23:59 | 2020-02-10 09:00 | 2020-02-10 18:00 |  |  | 2020-02-10 09:26 | 2020-02-10 09:26 |  |  | 100 | 100 | [15 empty] | 1.2012 | 0.000407 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3855 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018991
1472 | Task(Task)-->P (Procurement) | Bearing |  | 1.12.2.1 | Completed | No | No | 2020-05-17 | 2020-05-17 23:59 | 2020-02-10 09:00 | 2020-02-10 18:00 |  |  | 2020-02-10 09:36 | 2020-02-10 09:36 |  |  | 100 | 100 | [15 empty] | 1.8018 | 0.00061 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3856 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018992
1473 | Task(Task)-->P (Procurement) | Belting |  | 1.12.2.1 | Completed | No | No | 2019-11-07 09:00 | 2019-11-07 18:00 | 2020-01-20 09:00 | 2020-01-20 18:00 |  |  | 2020-01-20 15:54 | 2020-01-20 15:54 |  |  | 100 | 100 | [15 empty] | 6.006 | 0.002034 | 0.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3857 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018993
1474 | Task(Task)-->P (Procurement) | Scrapper |  | 1.12.2.1 | Completed | No | No | 2019-11-17 | 2019-11-17 23:59 | 2020-03-11 09:00 | 2020-03-11 18:00 |  |  | 2020-03-11 10:57 | 2020-03-11 10:57 |  |  | 100 | 100 | [15 empty] | 0.6006 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3858 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018994
1475 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.12.2.1 | Completed | No | No | 2020-03-10 09:00 | 2020-03-10 18:00 | 2020-03-11 09:00 | 2020-03-11 18:00 |  |  | 2020-03-11 12:41 | 2020-03-11 12:41 |  |  | 100 | 100 | [15 empty] | 5.7057 | 0.001932 | 0.19 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3859 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018995
1476 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.12.2.1 | Completed | No | No | 2020-05-19 09:00 | 2020-05-19 18:00 | 2020-04-16 09:00 | 2020-04-16 18:00 |  |  | 2020-04-16 10:57 | 2020-04-16 10:57 |  |  | 100 | 100 | [15 empty] | 0.3003 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3860 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018996
1477 | Task(Task)-->P (Procurement) | Gear Box |  | 1.12.2.1 | Completed | No | No | 2019-11-13 09:00 | 2019-11-13 18:00 | 2020-01-20 09:00 | 2020-01-20 18:00 |  |  | 2020-01-20 11:17 | 2020-01-20 11:17 |  |  | 100 | 100 | [15 empty] | 3.003 | 0.001017 | 0.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3861 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018997
1478 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.12.2.1 | Completed | No | No | 2019-11-21 09:00 | 2019-11-21 18:00 | 2020-01-22 09:00 | 2020-01-22 18:00 |  |  | 2020-01-22 10:41 | 2020-01-22 10:41 |  |  | 100 | 100 | [15 empty] | 0.3003 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3862 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018998
1479 | Task(Task)-->P (Procurement) | Fluid Coupling |  | 1.12.2.1 | Completed | No | No | 2019-11-25 09:00 | 2019-11-25 18:00 | 2020-01-22 09:00 | 2020-01-22 18:00 |  |  | 2020-01-22 09:54 | 2020-01-22 09:54 |  |  | 100 | 100 | [15 empty] | 3.003 | 0.001017 | 0.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3863 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1018999
1480 | Task(Task)-->P (Procurement) | Brake |  | 1.12.2.1 | Completed | No | No | 2019-12-18 09:00 | 2019-12-18 18:00 | 2020-04-04 09:00 | 2020-04-04 18:00 |  |  | 2020-04-04 11:33 | 2020-04-04 11:33 |  |  | 100 | 100 | [15 empty] | 0.3003 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3864 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019000
1481 | Task(Task)-->P (Procurement) | Building Structure |  | 1.12.2.1 | Completed | No | No | 2020-04-15 09:00 | 2020-04-15 18:00 | 2020-05-29 09:00 | 2020-05-29 18:00 |  |  | 2020-05-31 18:44 | 2020-05-31 18:44 |  |  | 100 | 100 | [15 empty] | 36.3363 | 0.012304 | 1.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3865 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019001
1482 | Task(Task)-->P (Procurement) | HT AC MOTORS |  | 1.12.2.1 | Completed | No | No | 2020-01-07 09:00 | 2020-01-07 18:00 | 2020-01-17 09:00 | 2020-01-17 18:00 |  |  | 2020-01-17 10:57 | 2020-01-17 10:57 |  |  | 100 | 100 | [15 empty] | 8.7087 | 0.002949 | 0.29 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3866 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019002
1483 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.12.2.1 | Completed | No | No | 2020-03-10 09:00 | 2020-03-10 18:00 | 2020-03-16 09:00 | 2020-03-16 18:00 |  |  | 2020-03-16 10:57 | 2020-03-16 10:57 |  |  | 100 | 100 | [15 empty] | 8.1081 | 0.002745 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3867 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019003
1484 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.12.2.1 | Completed | No | No | 2020-03-27 09:00 | 2020-03-27 18:00 | 2020-04-30 09:00 | 2020-04-30 18:00 |  |  | 2020-04-30 10:57 | 2020-04-30 10:57 |  |  | 100 | 100 | [15 empty] | 3.6036 | 0.00122 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3868 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019004
1485 | Task(Task)-->P (Procurement) | LPBS |  | 1.12.2.1 | Unscheduled | No | No | 2020-03-20 09:00 | 2020-03-20 18:00 | 2020-04-14 09:00 | 2020-04-14 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3869 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019005
1486 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.12.2.1 | Completed | No | No | 2020-01-08 09:00 | 2020-01-08 18:00 | 2020-01-08 09:00 | 2020-01-08 18:00 |  |  | 2020-01-08 10:57 | 2020-01-08 10:57 |  |  | 100 | 100 | [15 empty] | 0.9009 | 0.000305 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3871 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019006
1487 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.12.2.1 | Completed | No | No | 2019-12-30 09:00 | 2019-12-30 18:00 | 2019-12-30 09:00 | 2019-12-30 18:00 |  |  | 2019-12-30 10:57 | 2019-12-30 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3872 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019007
1488 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.12.2.1 | Completed | No | No | 2020-01-03 09:00 | 2020-01-03 18:00 | 2020-01-03 09:00 | 2020-01-03 18:00 |  |  | 2020-01-03 10:57 | 2020-01-03 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3873 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019008
1489 | Task(Task)-->P (Procurement) | TECHNICAL CLEARANCE | 1.12.2.2 | 1.12.2 | Work In Progress | No | No | 2019-09-28 09:00 | 2020-06-18 18:00 | 2019-12-30 09:00 | 2020-06-12 18:00 |  |  | 2020-01-16 10:57 |  |  |  | 100 | 100 | [15 empty] | 5.0008 | 0.033861 | 3.33 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3874 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019009
1490 | Task(Task)-->P (Procurement) | Pulley |  | 1.12.2.2 | Completed | No | No | 2019-09-28 09:00 | 2020-01-04 18:00 | 2020-02-05 09:00 | 2020-02-10 18:00 |  |  | 2020-02-06 16:19 | 2020-02-10 16:19 |  |  | 100 | 100 | [15 empty] | 15.015 | 0.005084 | 0.5 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3875 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019010
1491 | Task(Task)-->P (Procurement) | Idler |  | 1.12.2.2 | Completed | No | No | 2019-12-20 09:00 | 2020-02-01 18:00 | 2020-02-13 09:00 | 2020-03-26 18:00 |  |  | 2020-02-14 10:57 | 2020-03-26 10:57 |  |  | 100 | 100 | [15 empty] | 5.1051 | 0.001729 | 0.17 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3876 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019011
1492 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.12.2.2 | Completed | No | No | 2020-05-18 09:00 | 2020-06-01 18:00 | 2020-02-10 09:00 | 2020-02-10 18:00 |  |  | 2020-02-10 09:28 | 2020-02-10 09:28 |  |  | 100 | 100 | [15 empty] | 1.2012 | 0.000407 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3877 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019012
1493 | Task(Task)-->P (Procurement) | Bearing |  | 1.12.2.2 | Completed | No | No | 2020-05-18 09:00 | 2020-06-16 18:00 | 2020-02-10 09:00 | 2020-02-10 18:00 |  |  | 2020-02-10 09:37 | 2020-02-10 09:37 |  |  | 100 | 100 | [15 empty] | 1.8018 | 0.00061 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3878 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019013
1494 | Task(Task)-->P (Procurement) | Belting |  | 1.12.2.2 | Completed | No | No | 2019-11-08 09:00 | 2020-01-06 18:00 | 2020-01-20 09:00 | 2020-05-16 18:00 |  |  | 2020-05-16 10:57 | 2020-05-16 10:57 |  |  | 100 | 100 | [15 empty] | 6.006 | 0.002034 | 0.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3879 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019014
1495 | Task(Task)-->P (Procurement) | Scrapper |  | 1.12.2.2 | Completed | No | No | 2019-11-18 09:00 | 2020-03-16 18:00 | 2020-03-11 09:00 | 2020-03-26 18:00 |  |  | 2020-03-26 10:57 | 2020-03-26 10:57 |  |  | 100 | 100 | [15 empty] | 0.6006 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3880 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019015
1496 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.12.2.2 | Completed | No | No | 2020-03-11 09:00 | 2020-03-20 18:00 | 2020-03-11 09:00 | 2020-03-17 18:00 |  |  | 2020-03-12 12:43 | 2020-03-17 12:43 |  |  | 100 | 100 | [15 empty] | 5.7057 | 0.001932 | 0.19 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3881 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019016
1497 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.12.2.2 | Completed | No | No | 2020-05-20 09:00 | 2020-06-18 18:00 | 2020-04-16 09:00 | 2020-04-16 18:00 |  |  | 2020-04-16 10:57 | 2020-04-16 10:57 |  |  | 100 | 100 | [15 empty] | 0.3003 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3882 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019017
1498 | Task(Task)-->P (Procurement) | Gear Box |  | 1.12.2.2 | Completed | No | No | 2019-11-14 09:00 | 2020-02-26 18:00 | 2020-01-20 09:00 | 2020-03-20 18:00 |  |  | 2020-01-22 11:19 | 2020-03-20 11:19 |  |  | 100 | 100 | [15 empty] | 3.003 | 0.001017 | 0.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3883 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019018
1499 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.12.2.2 | Completed | No | No | 2019-11-22 09:00 | 2020-03-19 18:00 | 2020-01-22 09:00 | 2020-04-13 18:00 |  |  | 2020-04-13 10:46 | 2020-04-13 10:46 |  |  | 100 | 100 | [15 empty] | 0.3003 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3884 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019019
1500 | Task(Task)-->P (Procurement) | Fluid Coupling |  | 1.12.2.2 | Completed | No | No | 2019-11-26 09:00 | 2020-03-01 23:59 | 2020-01-22 09:00 | 2020-04-13 18:00 |  |  | 2020-01-23 09:54 | 2020-04-13 09:54 |  |  | 100 | 100 | [15 empty] | 3.003 | 0.001017 | 0.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3885 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019020
1501 | Task(Task)-->P (Procurement) | Brake |  | 1.12.2.2 | Completed | No | No | 2019-12-19 09:00 | 2020-03-09 18:00 | 2020-04-04 09:00 | 2020-04-22 18:00 |  |  | 2020-04-05 11:34 | 2020-04-22 11:34 |  |  | 100 | 100 | [15 empty] | 0.3003 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3886 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019021
1502 | Task(Task)-->P (Procurement) | Building Structure |  | 1.12.2.2 | Completed | No | No | 2020-04-16 09:00 | 2020-04-22 18:00 | 2020-05-29 09:00 | 2020-05-29 18:00 |  |  | 2020-05-29 17:31 | 2020-05-29 17:31 |  |  | 100 | 100 | [15 empty] | 36.3363 | 0.012304 | 1.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3887 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019022
1503 | Task(Task)-->P (Procurement) | HT AC MOTORS |  | 1.12.2.2 | Completed | No | No | 2020-01-08 09:00 | 2020-01-29 18:00 | 2020-01-17 09:00 | 2020-04-11 18:00 |  |  | 2020-04-11 10:57 | 2020-04-11 10:57 |  |  | 100 | 100 | [15 empty] | 8.7087 | 0.002949 | 0.29 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3888 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019023
1504 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.12.2.2 | Completed | No | No | 2020-03-11 09:00 | 2020-03-25 18:00 | 2020-03-16 09:00 | 2020-06-02 18:00 |  |  | 2020-06-02 10:57 | 2020-06-02 10:57 |  |  | 100 | 100 | [15 empty] | 8.1081 | 0.002745 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3889 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019024
1505 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.12.2.2 | Completed | No | No | 2020-03-28 09:00 | 2020-05-11 18:00 | 2020-04-30 09:00 | 2020-06-03 18:00 |  |  | 2020-06-03 10:57 | 2020-06-03 10:57 |  |  | 100 | 100 | [15 empty] | 3.6036 | 0.00122 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3890 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019025
1506 | Task(Task)-->P (Procurement) | LPBS |  | 1.12.2.2 | Unscheduled | No | No | 2020-03-21 09:00 | 2020-04-04 18:00 | 2020-04-14 09:00 | 2020-06-12 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3891 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019026
1507 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.12.2.2 | Completed | No | No | 2020-01-09 09:00 | 2020-01-22 18:00 | 2020-01-08 09:00 | 2020-03-10 18:00 |  |  | 2020-03-10 10:57 | 2020-03-10 10:57 |  |  | 100 | 100 | [15 empty] | 0.9009 | 0.000305 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3893 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019027
1508 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.12.2.2 | Completed | No | No | 2019-12-31 09:00 | 2020-01-14 18:00 | 2019-12-30 09:00 | 2020-03-07 18:00 |  |  | 2020-03-07 10:57 | 2020-03-07 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3894 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019028
1509 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.12.2.2 | Completed | No | No | 2020-01-04 09:00 | 2020-01-18 18:00 | 2020-01-03 09:00 | 2020-01-16 18:00 |  |  | 2020-01-16 10:57 | 2020-01-16 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3895 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019029
1510 | Task(Task)-->P (Procurement) | ORDERING | 1.12.2.3 | 1.12.2 | Work In Progress | No | No | 2020-01-05 | 2020-07-18 18:00 | 2020-01-16 09:00 | 2020-09-04 18:00 |  |  | 2020-01-05 08:00 |  |  |  | 100 | 98.6489 | [15 empty] | 10.0015 | 0.067722 | 6.66 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3896 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019030
1511 | Task(Task)-->P (Procurement) | Pulley |  | 1.12.2.3 | Completed | No | No | 2020-01-05 | 2020-02-03 18:00 | 2020-02-10 09:00 | 2020-03-21 18:00 |  |  | 2020-01-05 08:00 | 2020-03-21 16:05 |  |  | 100 | 100 | [15 empty] | 15.015 | 0.010168 | 1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3897 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019031
1512 | Task(Task)-->P (Procurement) | Idler |  | 1.12.2.3 | Completed | No | No | 2020-02-02 | 2020-03-02 18:00 | 2020-03-26 09:00 | 2020-04-30 18:00 |  |  | 2020-02-02 08:00 | 2020-04-29 16:05 |  |  | 100 | 100 | [15 empty] | 5.1051 | 0.003457 | 0.34 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3898 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019032
1513 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.12.2.3 | Completed | No | No | 2020-06-02 09:00 | 2020-07-01 18:00 | 2020-02-10 09:00 | 2020-03-24 18:00 |  |  | 2020-02-11 09:32 | 2020-03-24 09:32 |  |  | 100 | 100 | [15 empty] | 1.0511 | 0.000712 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3899 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019033
1514 | Task(Task)-->P (Procurement) | Bearing |  | 1.12.2.3 | Completed | No | No | 2020-06-17 09:00 | 2020-07-16 18:00 | 2020-02-10 09:00 | 2020-03-24 18:00 |  |  | 2020-02-11 09:40 | 2020-03-24 09:40 |  |  | 100 | 100 | [15 empty] | 1.952 | 0.001322 | 0.13 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3900 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019034
1515 | Task(Task)-->P (Procurement) | Belting |  | 1.12.2.3 | Completed | No | No | 2020-01-07 09:00 | 2020-02-20 18:00 | 2020-05-16 09:00 | 2020-09-04 18:00 |  |  | 2020-05-16 16:24 | 2020-09-04 16:24 |  |  | 100 | 100 | [15 empty] | 5.8559 | 0.003966 | 0.39 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3901 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019035
1516 | Task(Task)-->P (Procurement) | Scrapper |  | 1.12.2.3 | Completed | No | No | 2020-03-17 09:00 | 2020-04-15 18:00 | 2020-03-26 09:00 | 2020-05-30 18:00 |  |  | 2020-05-30 10:57 | 2020-05-30 10:57 |  |  | 100 | 100 | [15 empty] | 0.6006 | 0.000407 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3902 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019036
1517 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.12.2.3 | Completed | No | No | 2020-03-21 09:00 | 2020-04-19 23:59 | 2020-03-17 09:00 | 2020-07-06 18:00 |  |  | 2020-03-18 12:44 | 2020-07-06 12:44 |  |  | 100 | 100 | [15 empty] | 5.7057 | 0.003864 | 0.38 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3903 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019037
1518 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.12.2.3 | Unscheduled | No | No | 2020-06-19 09:00 | 2020-07-18 18:00 | 2020-04-16 09:00 | 2020-08-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.3003 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3904 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019038
1519 | Task(Task)-->P (Procurement) | Gear Box |  | 1.12.2.3 | Completed | No | No | 2020-02-27 09:00 | 2020-03-27 18:00 | 2020-03-20 09:00 | 2020-04-30 18:00 |  |  | 2020-03-21 11:21 | 2020-04-30 11:21 |  |  | 100 | 100 | [15 empty] | 3.003 | 0.002034 | 0.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3905 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019039
1520 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.12.2.3 | Completed | No | No | 2020-03-20 09:00 | 2020-04-18 18:00 | 2020-04-13 09:00 | 2020-04-30 18:00 |  |  | 2020-04-14 11:11 | 2020-04-30 11:11 |  |  | 100 | 100 | [15 empty] | 0.45045 | 0.000305 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3906 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019040
1521 | Task(Task)-->P (Procurement) | Fluid Coupling |  | 1.12.2.3 | Completed | No | No | 2020-03-02 09:00 | 2020-03-31 18:00 | 2020-04-13 09:00 | 2020-05-18 18:00 |  |  | 2020-04-14 09:54 | 2020-05-18 16:05 |  |  | 100 | 100 | [15 empty] | 3.1532 | 0.002135 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3907 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019041
1522 | Task(Task)-->P (Procurement) | Brake |  | 1.12.2.3 | Completed | No | No | 2020-03-10 09:00 | 2020-04-08 18:00 | 2020-04-22 09:00 | 2020-05-18 18:00 |  |  | 2020-04-23 11:37 | 2020-05-18 16:05 |  |  | 100 | 100 | [15 empty] | 0.3003 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3908 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019042
1523 | Task(Task)-->P (Procurement) | Building Structure |  | 1.12.2.3 | Completed | No | No | 2020-04-23 09:00 | 2020-05-22 18:00 | 2020-05-29 09:00 | 2020-05-31 23:59 |  |  | 2020-05-31 18:49 | 2020-05-31 18:49 |  |  | 100 | 100 | [15 empty] | 36.1862 | 0.024506 | 2.41 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3909 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019043
1524 | Task(Task)-->P (Procurement) | HT AC MOTORS |  | 1.12.2.3 | Completed | No | No | 2020-01-30 09:00 | 2020-02-20 18:00 | 2020-04-11 09:00 | 2020-06-25 18:00 |  |  | 2020-04-13 09:41 | 2020-06-25 09:41 |  |  | 100 | 100 | [15 empty] | 8.7087 | 0.005898 | 0.58 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3910 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019044
1525 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.12.2.3 | Completed | No | No | 2020-03-26 09:00 | 2020-04-10 18:00 | 2020-06-02 09:00 | 2020-07-31 18:00 |  |  | 2020-06-03 15:51 | 2020-06-29 15:51 |  |  | 100 | 100 | [15 empty] | 7.958 | 0.005389 | 0.53 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3911 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019045
1526 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.12.2.3 | Completed | No | No | 2020-05-12 09:00 | 2020-06-25 18:00 | 2020-06-03 09:00 | 2020-06-24 18:00 |  |  | 2020-06-15 10:57 | 2020-06-15 10:57 |  |  | 100 | 100 | [15 empty] | 3.6036 | 0.00244 | 0.24 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3912 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019046
1527 | Task(Task)-->P (Procurement) | LPBS |  | 1.12.2.3 | Unscheduled | No | No | 2020-04-05 | 2020-04-20 18:00 | 2020-06-12 09:00 | 2020-08-19 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.15015 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3913 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019047
1528 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.12.2.3 | Unscheduled | No | No | 2020-01-23 09:00 | 2020-02-05 18:00 | 2020-03-10 09:00 | 2020-08-17 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.9009 | 0.00061 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3915 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019048
1529 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.12.2.3 | Unscheduled | No | No | 2020-01-15 09:00 | 2020-01-31 18:00 | 2020-03-07 09:00 | 2020-08-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3916 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019049
1530 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.12.2.3 | Completed | No | No | 2020-01-19 | 2020-01-31 18:00 | 2020-01-16 09:00 | 2020-02-01 18:00 |  |  | 2020-02-01 10:57 | 2020-02-01 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3917 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019050
1531 | Task(Task)-->P (Procurement) | ITP APPROVAL | 1.12.2.4 | 1.12.2 | Work In Progress | No | No | 2020-02-01 09:00 | 2020-08-25 18:00 | 2020-03-21 09:00 | 2020-10-30 18:00 |  |  | 2020-04-13 16:22 |  |  |  | 100 | 23.1233 | [15 empty] | 5.0008 | 0.033861 | 3.33 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3918 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019051
1532 | Task(Task)-->P (Procurement) | Pulley |  | 1.12.2.4 | Unscheduled | No | No | 2020-02-04 09:00 | 2020-03-14 18:00 | 2020-03-21 09:00 | 2020-05-11 18:00 | [6 empty] | 100 | 0 | [15 empty] | 15.015 | 0.005084 | 0.5 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3919 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019052
1533 | Task(Task)-->P (Procurement) | Idler |  | 1.12.2.4 | Completed | No | No | 2020-03-03 09:00 | 2020-04-11 18:00 | 2020-04-30 09:00 | 2020-05-19 18:00 |  |  | 2020-04-13 16:22 | 2020-05-19 16:22 |  |  | 100 | 100 | [15 empty] | 5.1051 | 0.001729 | 0.17 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3920 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019053
1534 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.12.2.4 | Unscheduled | No | No | 2020-07-02 09:00 | 2020-08-10 18:00 | 2020-03-24 09:00 | 2020-08-13 18:00 | [6 empty] | 100 | 0 | [15 empty] | 1.2012 | 0.000407 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3921 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019054
1535 | Task(Task)-->P (Procurement) | Bearing |  | 1.12.2.4 | Unscheduled | No | No | 2020-07-17 09:00 | 2020-08-25 18:00 | 2020-03-24 09:00 | 2020-03-29 23:59 | [6 empty] | 100 | 0 | [15 empty] | 1.8018 | 0.00061 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3922 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019055
1536 | Task(Task)-->P (Procurement) | Belting |  | 1.12.2.4 | Completed | No | No | 2020-02-21 09:00 | 2020-03-31 18:00 | 2020-09-04 09:00 | 2020-09-30 18:00 |  |  | 2020-09-04 16:30 | 2020-09-30 17:07 |  |  | 100 | 100 | [15 empty] | 6.006 | 0.002034 | 0.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3923 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019056
1537 | Task(Task)-->P (Procurement) | Scrapper |  | 1.12.2.4 | Completed | No | No | 2020-04-16 09:00 | 2020-05-25 18:00 | 2020-05-30 09:00 | 2020-06-25 18:00 |  |  | 2020-05-30 16:32 | 2020-06-25 16:32 |  |  | 100 | 100 | [15 empty] | 0.6006 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3924 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019057
1538 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.12.2.4 | Unscheduled | No | No | 2020-04-20 09:00 | 2020-05-29 18:00 | 2020-07-06 09:00 | 2020-07-16 18:00 | [6 empty] | 100 | 0 | [15 empty] | 5.7057 | 0.001932 | 0.19 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3925 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019058
1539 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.12.2.4 | Unscheduled | No | No | 2020-07-19 | 2020-08-17 18:00 | 2020-06-25 09:00 | 2020-06-25 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.3003 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3926 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019059
1540 | Task(Task)-->P (Procurement) | Gear Box |  | 1.12.2.4 | Completed | No | No | 2020-03-28 09:00 | 2020-05-06 18:00 | 2020-04-30 09:00 | 2020-06-22 18:00 |  |  | 2020-04-30 16:54 | 2020-06-22 16:54 |  |  | 100 | 100 | [15 empty] | 3.003 | 0.001017 | 0.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3927 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019060
1541 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.12.2.4 | Completed | No | No | 2020-04-19 | 2020-05-28 18:00 | 2020-04-30 09:00 | 2020-06-18 18:00 |  |  | 2020-04-30 01:54 | 2020-06-18 17:31 |  |  | 100 | 100 | [15 empty] | 0.3003 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3928 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019061
1542 | Task(Task)-->P (Procurement) | Fluid Coupling |  | 1.12.2.4 | Unscheduled | No | No | 2020-04-01 09:00 | 2020-05-10 23:59 | 2020-05-18 09:00 | 2020-08-18 18:00 | [6 empty] | 100 | 0 | [15 empty] | 3.003 | 0.001017 | 0.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3929 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019062
1543 | Task(Task)-->P (Procurement) | Brake |  | 1.12.2.4 | Unscheduled | No | No | 2020-04-09 09:00 | 2020-05-18 18:00 | 2020-05-18 09:00 | 2020-10-11 23:59 | [6 empty] | 100 | 0 | [15 empty] | 0.3003 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3930 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019063
1544 | Task(Task)-->P (Procurement) | Building Structure |  | 1.12.2.4 | Unscheduled | No | No | 2020-05-23 09:00 | 2020-05-29 18:00 | 2020-05-31 | 2020-08-04 18:00 |  |  | 2020-06-25 19:04 |  |  |  | 100 | 0 | [15 empty] | 36.3363 | 0.012304 | 1.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3931 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019064
1545 | Task(Task)-->P (Procurement) | HT AC MOTORS |  | 1.12.2.4 | Unscheduled | No | No | 2020-02-21 09:00 | 2020-03-31 18:00 | 2020-09-11 09:00 | 2020-10-20 18:00 | [6 empty] | 100 | 0 | [15 empty] | 8.7087 | 0.002949 | 0.29 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3932 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019065
1546 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.12.2.4 | Completed | No | No | 2020-04-11 09:00 | 2020-05-20 18:00 | 2020-07-28 09:00 | 2020-09-08 18:00 |  |  | 2020-07-08 17:23 | 2020-09-08 17:23 |  |  | 100 | 100 | [15 empty] | 8.1081 | 0.002745 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3933 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019066
1547 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.12.2.4 | Unscheduled | No | No | 2020-06-26 09:00 | 2020-08-04 18:00 | 2020-06-23 09:00 | 2020-09-08 18:00 |  |  | 2020-06-23 17:45 |  |  |  | 100 | 0 | [15 empty] | 3.6036 | 0.00122 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3934 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019067
1548 | Task(Task)-->P (Procurement) | LPBS |  | 1.12.2.4 | Completed | No | No | 2020-04-21 09:00 | 2020-05-30 18:00 | 2020-07-29 09:00 | 2020-08-21 18:00 |  |  | 2020-07-29 15:00 | 2020-08-22 12:54 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3935 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019068
1549 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.12.2.4 | Unscheduled | No | No | 2020-02-06 09:00 | 2020-03-16 18:00 | 2020-09-24 09:00 | 2020-10-30 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.9009 | 0.000305 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3937 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019069
1550 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.12.2.4 | Unscheduled | No | No | 2020-02-01 09:00 | 2020-03-11 18:00 | 2020-08-02 | 2020-09-10 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3938 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019070
1551 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.12.2.4 | Unscheduled | No | No | 2020-02-01 09:00 | 2020-03-11 18:00 | 2020-07-02 09:00 | 2020-08-04 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3939 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019071
1552 | Task(Task)-->P (Procurement) | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE | 1.12.2.5 | 1.12.2 | Work In Progress | No | No | 2020-02-01 09:00 | 2020-09-16 18:00 | 2020-02-01 09:00 | 2020-10-20 18:00 |  |  | 2020-02-11 21:28 |  |  |  | 100 | 49.1485 | [15 empty] | 15.0023 | 0.10158 | 9.99 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3940 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019072
1553 | Task(Task)-->P (Procurement) | Pulley |  | 1.12.2.5 | Completed | No | No | 2020-02-04 09:00 | 2020-03-29 23:59 | 2020-03-21 09:00 | 2020-03-25 18:00 |  |  | 2020-03-22 18:03 | 2020-03-25 18:03 |  |  | 100 | 100 | [15 empty] | 15 | 0.015237 | 1.5 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3941 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019073
1554 | Task(Task)-->P (Procurement) | Idler |  | 1.12.2.5 | Completed | No | No | 2020-03-03 09:00 | 2020-05-01 18:00 | 2020-04-30 09:00 | 2020-06-25 18:00 |  |  | 2020-06-25 14:53 | 2020-06-25 14:53 |  |  | 100 | 100 | [15 empty] | 5.2 | 0.005282 | 0.52 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3942 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019074
1555 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.12.2.5 | Completed | No | No | 2020-07-02 09:00 | 2020-08-30 23:59 | 2020-03-24 09:00 | 2020-06-29 18:00 |  |  | 2020-05-14 14:59 | 2020-06-29 14:59 |  |  | 100 | 100 | [15 empty] | 1.1 | 0.001117 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3943 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019075
1556 | Task(Task)-->P (Procurement) | Bearing |  | 1.12.2.5 | Completed | No | No | 2020-07-17 09:00 | 2020-07-17 18:00 | 2020-03-24 09:00 | 2020-03-24 18:00 |  |  | 2020-03-24 10:05 | 2020-03-24 10:05 |  |  | 100 | 100 | [15 empty] | 1.9 | 0.00193 | 0.19 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3944 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019076
1557 | Task(Task)-->P (Procurement) | Belting |  | 1.12.2.5 | Unscheduled | No | No | 2020-02-21 09:00 | 2020-04-20 18:00 | 2020-09-04 09:00 | 2020-10-15 18:00 |  |  | 2020-09-04 16:36 |  |  |  | 100 | 50 | [15 empty] | 5.9 | 0.005993 | 0.59 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3945 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019077
1558 | Task(Task)-->P (Procurement) | Scrapper |  | 1.12.2.5 | Completed | No | No | 2020-04-16 09:00 | 2020-06-14 23:59 | 2020-05-30 09:00 | 2020-07-30 18:00 |  |  | 2020-05-30 16:34 | 2020-07-30 16:34 |  |  | 100 | 100 | [15 empty] | 0.6 | 0.000609 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3946 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019078
1559 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.12.2.5 | Completed | No | No | 2020-04-20 09:00 | 2020-09-16 18:00 | 2020-07-06 09:00 | 2020-07-06 18:00 |  |  | 2020-07-06 12:45 | 2020-07-06 12:45 |  |  | 100 | 100 | [15 empty] | 5.7 | 0.00579 | 0.57 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3947 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019079
1560 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.12.2.5 | Unscheduled | No | No | 2020-07-19 | 2020-08-27 18:00 | 2020-08-04 09:00 | 2020-08-04 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.3 | 0.000305 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3948 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019080
1561 | Task(Task)-->P (Procurement) | Gear Box |  | 1.12.2.5 | Completed | No | No | 2020-03-28 09:00 | 2020-05-26 18:00 | 2020-04-30 09:00 | 2020-07-01 18:00 |  |  | 2020-04-30 15:33 | 2020-07-01 15:33 |  |  | 100 | 100 | [15 empty] | 3 | 0.003047 | 0.3 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3949 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019081
1562 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.12.2.5 | Completed | No | No | 2020-04-19 | 2020-06-17 18:00 | 2020-04-30 09:00 | 2020-07-30 18:00 |  |  | 2020-04-30 15:31 | 2020-07-06 15:31 |  |  | 100 | 100 | [15 empty] | 0.4 | 0.000406 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3950 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019082
1563 | Task(Task)-->P (Procurement) | Fluid Coupling |  | 1.12.2.5 | Unscheduled | No | No | 2020-04-01 09:00 | 2020-05-30 18:00 | 2020-05-18 09:00 | 2020-08-21 18:00 | [6 empty] | 100 | 0 | [15 empty] | 3.1 | 0.003149 | 0.31 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3951 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019083
1564 | Task(Task)-->P (Procurement) | Brake |  | 1.12.2.5 | Unscheduled | No | No | 2020-04-09 09:00 | 2020-06-07 23:59 | 2020-05-18 09:00 | 2020-08-13 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.3 | 0.000305 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3952 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019084
1565 | Task(Task)-->P (Procurement) | Building Structure |  | 1.12.2.5 | Unscheduled | No | No | 2020-04-30 09:00 | 2020-05-06 18:00 | 2020-10-11 | 2020-10-17 18:00 | [6 empty] | 100 | 0 | [15 empty] | 36.2 | 0.036773 | 3.62 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3953 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019085
1566 | Task(Task)-->P (Procurement) | HT AC MOTORS |  | 1.12.2.5 | Completed | No | No | 2020-02-21 09:00 | 2020-05-05 18:00 | 2020-07-18 09:00 | 2020-09-28 18:00 |  |  | 2020-07-18 09:04 | 2020-09-28 10:23 |  |  | 100 | 100 | [15 empty] | 8.7 | 0.008838 | 0.87 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3954 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019086
1567 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.12.2.5 | Unscheduled | No | No | 2020-04-11 09:00 | 2020-05-25 18:00 | 2020-07-10 09:00 | 2020-10-16 18:00 |  |  | 2020-07-14 10:44 |  |  |  | 100 | 0 | [15 empty] | 8 | 0.008127 | 0.8 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3955 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019087
1568 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.12.2.5 | Completed | No | No | 2020-06-26 09:00 | 2020-08-09 23:59 | 2020-05-30 09:00 | 2020-08-08 18:00 |  |  | 2020-06-18 17:16 | 2020-08-07 15:00 |  |  | 100 | 100 | [15 empty] | 3.6 | 0.003657 | 0.36 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3956 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019088
1569 | Task(Task)-->P (Procurement) | LPBS |  | 1.12.2.5 | Completed | No | No | 2020-04-21 09:00 | 2020-06-04 18:00 | 2020-07-25 09:00 | 2020-08-22 18:00 |  |  | 2020-07-24 18:45 | 2020-08-22 12:58 |  |  | 100 | 100 | [15 empty] | 0.1 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3957 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019089
1570 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.12.2.5 | Completed | No | No | 2020-02-06 09:00 | 2020-03-21 18:00 | 2020-08-11 09:00 | 2020-09-19 18:00 |  |  | 2020-08-11 13:12 | 2020-09-19 12:58 |  |  | 100 | 100 | [15 empty] | 0.9 | 0.000914 | 0.09 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3959 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019090
1571 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.12.2.5 | Unscheduled | No | No | 2020-02-01 09:00 | 2020-03-16 18:00 | 2020-08-09 | 2020-10-20 18:00 |  |  | 2020-08-09 13:17 |  |  |  | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3960 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019091
1572 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.12.2.5 | Completed | No | No | 2020-02-01 09:00 | 2020-03-16 18:00 | 2020-02-01 09:00 | 2020-07-15 18:00 |  |  | 2020-02-11 21:28 | 2020-07-15 21:28 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3961 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019092
1573 | Task(Task)-->P (Procurement) | MANUFACTURING & RECEIPT AT SITE (MRN) | 1.12.2.6 | 1.12.2 | Unscheduled | No | No | 2020-03-17 09:00 | 2021-02-13 18:00 | 2020-03-24 09:00 | 2021-05-13 18:00 |  |  | 2020-03-25 18:05 |  |  |  | 85.1666 | 1.2456 | [15 empty] | 59.994 | 0.40623 | 39.95 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3962 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019093
1574 | Task(Task)-->P (Procurement) | Pulley |  | 1.12.2.6 | Unscheduled | No | No | 2020-03-30 09:00 | 2020-11-20 18:00 | 2020-03-25 09:00 | 2020-12-01 18:00 |  |  | 2020-03-25 18:05 |  |  |  | 81.3559 | 0 | [15 empty] | 15.0325 | 0.061067 | 6.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3963 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019094
1575 | Task(Task)-->P (Procurement) | Idler |  | 1.12.2.6 | Unscheduled | No | No | 2020-05-02 09:00 | 2020-11-13 18:00 | 2020-06-25 09:00 | 2020-12-31 18:00 | [6 empty] | 81.1225 | 0 | [15 empty] | 5.1526 | 0.020931 | 2.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3964 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019095
1576 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.12.2.6 | Unscheduled | No | No | 2020-08-31 09:00 | 2020-12-23 18:00 | 2020-06-29 09:00 | 2020-12-31 18:00 | [6 empty] | 33.0435 | 0 | [15 empty] | 1.1006 | 0.004471 | 0.44 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3965 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019096
1577 | Task(Task)-->P (Procurement) | Bearing |  | 1.12.2.6 | Unscheduled | No | No | 2020-08-26 09:00 | 2020-12-23 18:00 | 2020-03-24 09:00 | 2020-09-09 18:00 | [6 empty] | 35.8333 | 0 | [15 empty] | 1.8759 | 0.007621 | 0.75 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3966 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019097
1578 | Task(Task)-->P (Procurement) | Belting |  | 1.12.2.6 | Unscheduled | No | No | 2020-04-21 09:00 | 2020-11-16 18:00 | 2020-10-16 09:00 | 2021-05-13 18:00 | [6 empty] | 80.9524 | 0 | [15 empty] | 5.8779 | 0.023878 | 2.35 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3967 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019098
1579 | Task(Task)-->P (Procurement) | Scrapper |  | 1.12.2.6 | Unscheduled | No | No | 2020-06-15 09:00 | 2020-12-11 18:00 | 2020-07-30 09:00 | 2020-12-31 18:00 | [6 empty] | 63.8889 | 0 | [15 empty] | 0.55028 | 0.002235 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3968 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019099
1580 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.12.2.6 | Unscheduled | No | No | 2020-06-19 09:00 | 2021-02-13 18:00 | 2020-07-06 09:00 | 2021-01-31 23:59 | [6 empty] | 46.25 | 0 | [15 empty] | 5.6778 | 0.023065 | 2.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3969 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019100
1581 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.12.2.6 | Unscheduled | No | No | 2020-08-28 09:00 | 2020-12-25 18:00 | 2020-08-04 09:00 | 2020-12-25 18:00 | [6 empty] | 34.1667 | 0 | [15 empty] | 0.32516 | 0.001321 | 0.13 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3970 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019101
1582 | Task(Task)-->P (Procurement) | Gear Box |  | 1.12.2.6 | Unscheduled | No | No | 2020-05-27 09:00 | 2020-12-22 18:00 | 2020-07-01 09:00 | 2020-12-31 18:00 |  |  | 2020-07-01 17:25 |  |  |  | 63.8095 | 30 | [15 empty] | 3.0265 | 0.012295 | 1.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3971 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019102
1583 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.12.2.6 | Unscheduled | No | No | 2020-06-18 09:00 | 2020-12-15 18:00 | 2020-07-30 09:00 | 2020-10-05 18:00 |  |  | 2020-07-30 17:44 |  |  |  | 61.8785 | 90 | [15 empty] | 0.37519 | 0.001524 | 0.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3972 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019103
1584 | Task(Task)-->P (Procurement) | Fluid Coupling |  | 1.12.2.6 | Unscheduled | No | No | 2020-05-31 | 2020-12-26 18:00 | 2020-08-21 09:00 | 2021-01-31 23:59 | [6 empty] | 61.9048 | 0 | [15 empty] | 3.1266 | 0.012701 | 1.25 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3973 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019104
1585 | Task(Task)-->P (Procurement) | Brake |  | 1.12.2.6 | Unscheduled | No | No | 2020-06-08 09:00 | 2020-12-04 18:00 | 2020-08-13 09:00 | 2020-10-31 18:00 | [6 empty] | 67.7778 | 0 | [15 empty] | 0.32516 | 0.001321 | 0.13 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3974 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019105
1586 | Task(Task)-->P (Procurement) | Building Structure |  | 1.12.2.6 | Unscheduled | No | No | 2020-05-30 09:00 | 2020-09-30 18:00 | 2020-10-18 | 2021-02-18 18:00 | [6 empty] | 100 | 0 | [15 empty] | 36.1681 | 0.14693 | 14.46 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3975 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019106
1587 | Task(Task)-->P (Procurement) | HT AC MOTORS |  | 1.12.2.6 | Unscheduled | No | No | 2020-05-06 09:00 | 2020-09-30 18:00 | 2020-10-21 09:00 | 2021-03-17 18:00 |  |  | 2020-09-28 10:24 |  |  |  | 100 | 0 | [15 empty] | 8.7044 | 0.03536 | 3.48 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3976 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019107
1588 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.12.2.6 | Unscheduled | No | No | 2020-05-26 09:00 | 2020-10-21 18:00 | 2020-10-17 09:00 | 2021-03-14 23:59 | [6 empty] | 90.604 | 0 | [15 empty] | 7.979 | 0.032413 | 3.19 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3977 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019108
1589 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.12.2.6 | Unscheduled | No | No | 2020-08-10 09:00 | 2020-11-07 18:00 | 2020-09-09 09:00 | 2020-12-07 18:00 |  |  | 2020-08-07 15:03 |  |  |  | 65.5556 | 0 | [15 empty] | 3.6268 | 0.014733 | 1.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3978 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019109
1590 | Task(Task)-->P (Procurement) | LPBS |  | 1.12.2.6 | Unscheduled | No | No | 2020-06-05 09:00 | 2020-09-16 18:00 | 2020-08-23 | 2020-12-04 18:00 |  |  | 2020-08-22 13:01 |  |  |  | 100 | 0 | [15 empty] | 0.10005 | 0.000406 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3979 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019110
1591 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.12.2.6 | Unscheduled | No | No | 2020-03-22 | 2020-08-05 18:00 | 2020-10-31 09:00 | 2021-03-16 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.90045 | 0.003658 | 0.36 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3981 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019111
1592 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.12.2.6 | Unscheduled | No | No | 2020-03-17 09:00 | 2020-07-27 18:00 | 2020-10-21 09:00 | 2021-03-02 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.025013 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3982 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019112
1593 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.12.2.6 | Unscheduled | No | No | 2020-03-17 09:00 | 2020-07-31 18:00 | 2020-07-02 09:00 | 2020-11-15 23:59 |  |  | 2020-07-15 21:40 |  |  |  | 100 | 0 | [15 empty] | 0.050025 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3983 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019113
1594 | Task(Task)-->C (Construction) | CONSTRUCTION | 1.12.3 | 1.12 | Unscheduled | No | No | 2020-05-08 09:00 | 2021-09-08 18:00 | 2020-08-26 09:00 | 2022-03-06 23:59 | [6 empty] | 13.4261 | 0 | [15 empty] | 16.3703 | 0.13575 | 13.35 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3984 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019114
1595 | Task(Task)-->C (Construction) | CIVIL WORKS | 1.12.3.1 | 1.12.3 | Unscheduled | No | No | 2020-05-08 09:00 | 2020-09-11 18:00 | 2020-08-26 09:00 | 2020-12-30 18:00 | [6 empty] | 100 | 0 | [15 empty] | 9.9551 | 0.013514 | 1.33 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5477 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019115
1596 | Task(Task)-->C (Construction) | AVAILABILITY OF FRONT BY NTPC |  | 1.12.3.1 | Unscheduled | No | No | 2020-05-08 09:00 | 2020-05-08 18:00 | 2020-08-26 09:00 | 2020-08-26 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5476 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019116
1597 | Task(Task)-->C (Construction) | CIVIL |  | 1.12.3.1 | Unscheduled | No | No | 2020-05-15 09:00 | 2020-09-11 18:00 | 2020-09-02 09:00 | 2020-12-30 18:00 | [6 empty] | 100 | 0 | [15 empty] | 100 | 0.013514 | 1.33 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3985 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019117
1598 | Task(Task)-->C (Construction) | MECHANICAL | 1.12.3.2 | 1.12.3 | Unscheduled | No | No | 2020-10-01 09:00 | 2021-05-14 18:00 | 2021-02-19 09:00 | 2021-07-18 23:59 | [6 empty] | 6.0618 | 0 | [15 empty] | 57.2605 | 0.077731 | 7.65 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3986 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019118
1599 | Task(Task)-->C (Construction) | ERECTION OF STRUCTURAL STEEL |  | 1.12.3.2 | Unscheduled | No | No | 2020-10-01 09:00 | 2020-11-29 23:59 | 2021-02-19 09:00 | 2021-04-19 18:00 | [6 empty] | 11.6667 | 0 | [15 empty] | 51.9582 | 0.040388 | 3.98 | Plan & Actual | Quantity | Metric Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3987 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019119
1600 | Task(Task)-->C (Construction) | ERECTION OF SY 3A |  | 1.12.3.2 | Unscheduled | No | No | 2021-02-14 | 2021-03-30 18:00 | 2021-04-20 09:00 | 2021-06-03 18:00 | [6 empty] | 0 | 0 | [15 empty] | 24.0209 | 0.018672 | 1.84 | Plan & Actual | Quantity | Metric Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3988 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019120
1601 | Task(Task)-->C (Construction) | ERECTION OF SY 3B |  | 1.12.3.2 | Unscheduled | No | No | 2021-03-31 09:00 | 2021-05-14 18:00 | 2021-06-04 09:00 | 2021-07-18 23:59 | [6 empty] | 0 | 0 | [15 empty] | 24.0209 | 0.018672 | 1.84 | Plan & Actual | Quantity | Metric Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5436 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019121
1602 | Task(Task)-->C (Construction) | BELT LAYING & JOINTING WORK |  | 1.12.3 | Unscheduled | No | No | 2021-05-15 09:00 | 2021-06-14 18:00 | 2021-07-19 09:00 | 2021-08-18 18:00 | [6 empty] | 0 | 0 | [15 empty] | 3.8922 | 0.005284 | 0.52 | Plan & Actual | Quantity | Meter | 0 | 0 | 0 | 0 | 0 | 0 | 332 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3989 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019122
1603 | Task(Task)-->C (Construction) | ELECTRICAL & INSTRUMENTATION | 1.12.3.4 | 1.12.3 | Unscheduled | No | No | 2020-09-10 09:00 | 2021-08-25 18:00 | 2020-12-29 09:00 | 2022-02-20 23:59 | [6 empty] | 0 | 0 | [15 empty] | 17.3653 | 0.023573 | 2.32 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5266 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019123
1604 | Task(Task)-->C (Construction) | CABLE TRAY |  | 1.12.3.4 | Unscheduled | No | No | 2020-11-30 09:00 | 2020-12-02 18:00 | 2021-04-20 09:00 | 2021-04-22 18:00 | [6 empty] | 0 | 0 | [15 empty] | 9.0909 | 0.002143 | 0.21 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3990 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019124
1605 | Task(Task)-->C (Construction) | POWER CABLE |  | 1.12.3.4 | Unscheduled | No | No | 2021-05-15 09:00 | 2021-05-19 18:00 | 2021-07-25 | 2021-07-29 18:00 | [6 empty] | 0 | 0 | [15 empty] | 31.1688 | 0.007347 | 0.72 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 5080 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5267 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019125
1606 | Task(Task)-->C (Construction) | CONTROL CABLE |  | 1.12.3.4 | Unscheduled | No | No | 2021-05-19 09:00 | 2021-05-19 18:00 | 2021-09-25 09:00 | 2021-09-25 18:00 | [6 empty] | 0 | 0 | [15 empty] | 2.5974 | 0.000612 | 0.06 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 456 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3991 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019126
1607 | Task(Task)-->C (Construction) | EARTHING |  | 1.12.3.4 | Unscheduled | No | No | 2021-02-09 09:00 | 2021-02-11 18:00 | 2021-04-20 09:00 | 2021-04-22 18:00 | [6 empty] | 0 | 0 | [15 empty] | 3.4632 | 0.000816 | 0.08 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 369 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5329 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019127
1608 | Task(Task)-->C (Construction) | EARTH PIT |  | 1.12.3.4 | Unscheduled | No | No | 2020-09-10 09:00 | 2020-09-11 18:00 | 2020-12-29 09:00 | 2020-12-30 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5330 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019128
1609 | Task(Task)-->C (Construction) | LIGHTING |  | 1.12.3.4 | Unscheduled | No | No | 2020-11-30 09:00 | 2020-12-04 18:00 | 2021-04-20 09:00 | 2021-04-24 18:00 | [6 empty] | 0 | 0 | [15 empty] | 16.8831 | 0.00398 | 0.39 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5331 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019129
1610 | Task(Task)-->C (Construction) | FIELD INTRUMENTS |  | 1.12.3.4 | Unscheduled | No | No | 2021-05-18 09:00 | 2021-05-20 18:00 | 2021-09-24 09:00 | 2021-09-26 23:59 | [6 empty] | 0 | 0 | [15 empty] | 36.7965 | 0.008674 | 0.85 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5332 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019130
1611 | Task(Task)-->C (Construction) | MOTOR TERMINATION |  | 1.12.3.4 | Unscheduled | No | No | 2021-05-19 09:00 | 2021-05-20 18:00 | 2021-07-29 09:00 | 2021-07-30 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5333 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019131
1612 | Task(Task)-->C (Construction) | NO LOAD RUN OF MOTOR |  | 1.12.3.4 | Unscheduled | No | No | 2021-08-22 | 2021-08-25 18:00 | 2022-02-17 09:00 | 2022-02-20 23:59 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5478 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019132
1613 | Task(Task)-->C (Construction) | NO LOAD COMMISSIONING & SYSTEM READYNESS FOR LOAD & TRIAL OPERATION |  | 1.12.3 | Unscheduled | No | No | 2021-08-26 09:00 | 2021-09-08 18:00 | 2022-02-21 09:00 | 2022-03-06 23:59 | [6 empty] | 0 | 0 | [15 empty] | 11.5269 | 0.015648 | 1.54 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5334 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019133
1614 | Task(Task)-->E (Engineering) | SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER | 1.13 | 1 | Work In Progress | No | No | 2019-11-12 09:00 | 2021-08-21 18:00 | 2019-11-02 09:00 | 2022-03-13 23:59 |  |  | 2019-11-02 10:57 |  |  |  | 62.4769 | 14.1853 | [15 empty] | 3.5168 | 3.5168 | 345.85 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3992 | 0 | 1 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019134
1615 | Task(Task)-->E (Engineering) | ENGINEERING | 1.13.1 | 1.13 | Work In Progress | No | No | 2019-12-18 18:00 | 2020-07-02 17:40 | 2020-01-13 18:00 | 2020-11-04 18:00 |  |  | 2020-02-21 14:31 |  |  |  | 100 | 72.6329 | [15 empty] | 2.4461 | 0.086025 | 8.46 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3993 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019135
1616 | Task(Task)-->E (Engineering) | CIVIL | 1.13.1.1 | 1.13.1 | Work In Progress | No | No | 2020-03-04 18:00 | 2020-07-02 17:40 | 2020-03-31 18:00 | 2020-11-04 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 92.8786 | [15 empty] | 48.7334 | 0.041923 | 4.04 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No | 3994 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036113
1617 | Task(Task)-->E (Engineering) | SUBSTATION-1 CUM CONTROL ROOM (SS-KDTP-1) : DESIGN CALCULATION |  | 1.13.1.1 | Completed | No | No | 2020-03-23 17:40 | 2020-05-04 17:40 | 2020-05-02 09:00 | 2020-05-29 18:00 |  |  | 2020-03-23 17:40 | 2020-06-04 14:29 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0025 |  | 2020-02-13 11:42 | 7012-155-PVC-U-086 |  |  |  | A |  |  |  | 47.8908 | 0.020077 | 1.93 | Plan & Actual | Date |  | 0 | 0 | 0 | 717.2 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3999 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-04 18:00 | 2020-03-31 18:00 |  | 10 | 2020-03-31 23:31 |  |  | 2020-03-23 17:40 | 2020-04-25 18:00 |  | 30 | 2020-04-25 23:31 |  |  | 2020-03-30 17:40 | 2020-04-28 18:00 |  | 35 | 2020-04-28 23:31 |  |  | 2020-04-04 23:59 | 2020-05-05 18:00 |  | 65 | 2020-05-02 23:31 |  |  | 2020-04-10 17:40 | 2020-05-26 18:00 |  | 80 | 2020-05-22 23:31 | [5 empty] | 80 | 2020-05-29 23:06 | [5 empty] | 80 | 2020-05-29 22:57 | [5 empty] | 80 | 2020-06-04 14:26 | [5 empty] | 80 | 2020-06-04 14:26 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-04 17:40 | 2020-06-09 18:00 |  | 100 | 2020-06-04 14:30 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 187 |  |  |  | 101197
1618 | Task(Task)-->E (Engineering) | SUBSTATION-1 CUM CONTROL ROOM (SS-KDTP-1) : NUM & RC DETAILS (SHT 1) |  | 1.13.1.1 | Completed | No | No | 2020-03-23 17:40 | 2020-05-04 17:40 | 2020-05-02 09:00 | 2020-05-29 18:00 |  |  | 2020-03-23 17:40 | 2020-06-02 21:04 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-NR-0034 |  | 2020-02-13 11:42 | 7012-155-PVC-C-087 |  |  |  | A |  |  |  | 15.8809 | 0.006658 | 0.64 | Plan & Actual | Date |  | 0 | 0 | 0 | 239.46 | 0 | 20.4 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3995 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-04 18:00 | 2020-03-31 18:00 |  | 10 | 2020-03-31 23:31 |  |  | 2020-03-23 17:40 | 2020-04-25 18:00 |  | 30 | 2020-04-25 23:31 |  |  | 2020-03-30 17:40 | 2020-04-28 18:00 |  | 35 | 2020-04-28 23:31 |  |  | 2020-04-04 23:59 | 2020-05-05 18:00 |  | 65 | 2020-05-02 23:31 |  |  | 2020-04-10 17:40 | 2020-05-26 18:00 |  | 80 | 2020-05-22 23:31 | [5 empty] | 80 | 2020-05-29 23:05 | [5 empty] | 80 | 2020-05-29 22:59 | [5 empty] | 80 | 2020-06-02 20:50 | [5 empty] | 80 | 2020-06-02 20:50 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-04 17:40 | 2020-06-09 18:00 |  | 100 | 2020-06-02 21:05 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 188 |  |  |  | 101198
1619 | Task(Task)-->E (Engineering) | SUBSTATION-1 CUM CONTROL ROOM (SS-KDTP-1) : NUM & RC DETAILS (SHT 2) |  | 1.13.1.1 | Completed | No | No | 2020-03-04 18:00 | 2020-05-04 17:40 | 2020-07-08 09:00 | 2020-07-22 18:00 |  |  | 2020-02-21 15:38 | 2020-07-22 23:11 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-NR-0035 |  | 2020-02-13 11:43 | 7012-155-PVC-C-088 |  |  |  | A |  |  |  | 15.8809 | 0.006658 | 0.64 | Plan & Actual | Date |  | 0 | 0 | 0 | 239.46 | 0 | 10.05 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3996 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-04 18:00 | 2020-03-31 18:00 |  | 10 | 2020-04-26 23:31 |  |  | 2020-03-23 17:40 | 2020-04-25 18:00 |  | 30 | 2020-05-19 23:31 |  |  | 2020-03-30 17:40 | 2020-04-28 18:00 |  | 35 | 2020-05-27 12:13 |  |  | 2020-04-04 23:59 | 2020-05-05 18:00 |  | 65 | 2020-07-22 23:02 |  |  | 2020-04-10 17:40 | 2020-05-26 18:00 |  | 80 | 2020-07-22 23:09 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-04 17:40 | 2020-06-09 18:00 |  | 100 | 2020-07-22 23:12 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 189 |  |  |  | 101199
1620 | Task(Task)-->E (Engineering) | SUBSTATION-1 CUM CONTROL ROOM (SS-KDTP-1) : NUM & RC DETAILS (SHT 3) |  | 1.13.1.1 | Unscheduled | No | No | 2020-03-04 18:00 | 2020-05-04 17:40 | 2020-03-31 18:00 | 2020-11-04 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-NR-0036 |  | 2020-02-13 11:43 | 7012-155-PVC-C-089 |  |  |  | A |  |  |  | 15.8809 | 0.006658 | 0.64 | Plan & Actual | Date |  | 0 | 0 | 0 | 239.46 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3997 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-04 18:00 | 2020-03-31 18:00 |  | 10 |  |  |  | 2020-03-23 17:40 | 2020-04-25 18:00 |  | 30 |  |  |  | 2020-03-30 17:40 | 2020-04-28 18:00 |  | 35 | 2020-10-01 16:44 |  |  | 2020-04-04 23:59 | 2020-05-05 18:00 |  | 65 | 2020-10-01 17:16 |  |  | 2020-04-10 17:40 | 2020-05-26 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-04 17:40 | 2020-06-09 18:00 |  | 100 | [122 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 190 |  |  |  | 101200
1621 | Task(Task)-->E (Engineering) | ARCHITECTURAL GA OF SUBSTATION-1 CUM CONTROL ROOM (SS-KDTP-1) |  | 1.13.1.1 | Unscheduled | No | No | 2020-05-03 23:59 | 2020-07-02 17:40 | 2020-05-15 18:00 | 2020-09-28 18:00 |  |  | 2020-02-21 15:39 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-AR-0011 |  | 2020-02-13 11:43 | 7012-155-PVC-C-117 |  |  |  | A |  |  |  | 4.4665 | 0.001872 | 0.18 | Plan & Actual | Date |  | 0 | 0 | 0 | 68.01 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3998 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-05-03 23:59 | 2020-05-15 18:00 |  | 10 |  |  |  | 2020-05-21 17:40 | 2020-06-09 18:00 |  | 30 | 2020-08-28 09:01 |  |  | 2020-05-28 17:40 | 2020-06-12 18:00 |  | 35 | 2020-09-03 12:48 |  |  | 2020-06-03 23:59 | 2020-06-19 18:00 |  | 65 | 2020-09-03 16:24 |  |  | 2020-06-09 17:40 | 2020-07-10 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-07-02 17:40 | 2020-07-24 18:00 |  | 100 | [122 empty] | Chetan Khodke |  |  |  |  | A - Architecture | [16 empty] | 218 |  |  |  | 101228
1622 | Task(Task)-->E (Engineering) | ELECTRICAL | 1.13.1.2 | 1.13.1 | Unscheduled | No | No | 2019-12-18 18:00 | 2020-05-16 17:40 | 2020-01-13 18:00 | 2020-10-15 18:00 |  |  | 2020-02-21 14:31 |  |  |  | 100 | 53.3875 | [15 empty] | 51.2666 | 0.044102 | 4.25 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No | 4000 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036114
1623 | Task(Task)-->E (Engineering) | GA & CROSS SECTIONAL, FLOOR PLAN FOR 6.6 kV HT SWITCHGEAR FOR CHP |  | 1.13.1.2 | Unscheduled | No | No | 2020-02-28 18:00 | 2020-04-13 17:40 | 2020-05-21 18:00 | 2020-09-01 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-123 |  | 2020-02-13 11:45 | 7012-155-PVE-B-068 |  |  |  | A |  |  |  | 1.3921 | 0.000614 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4007 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-28 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-02 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-03-07 17:40 | 2020-06-04 18:00 |  | 35 |  |  |  | 2020-03-13 23:59 | 2020-06-04 18:00 |  | 65 | 2020-09-23 14:45 |  |  | 2020-03-20 17:40 | 2020-06-25 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-13 17:40 | 2020-06-25 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 303 |  |  |  | 101314
1624 | Task(Task)-->E (Engineering) | SINGLE LINE DIAGRAM FOR 6.6 kV HT SWITCHGEAR FOR CHP |  | 1.13.1.2 | Unscheduled | No | No | 2020-02-29 18:00 | 2020-04-13 17:40 | 2020-05-21 18:00 | 2020-09-22 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-126 |  | 2020-02-13 11:45 | 7012-155-PVE-P-071 |  |  |  | A |  |  |  | 1.3921 | 0.000614 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4028 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-29 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-02 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-03-07 17:40 | 2020-06-03 18:00 |  | 35 |  |  |  | 2020-03-13 23:59 | 2020-06-03 18:00 |  | 65 | 2020-09-23 14:49 |  |  | 2020-03-20 17:40 | 2020-06-24 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-13 17:40 | 2020-06-24 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 306 |  |  |  | 101317
1625 | Task(Task)-->E (Engineering) | SCHEME DIAGRAM FOR TIE INCOMER WITH LINE PT (TYPE-DE-IC) |  | 1.13.1.2 | Unscheduled | No | No | 2020-02-28 18:00 | 2020-04-13 17:40 | 2020-05-21 18:00 | 2020-09-17 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-127 |  | 2020-02-13 11:45 | 7012-155-PVE-L-072 |  |  |  | A |  |  |  | 1.3921 | 0.000614 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4016 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-28 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-02 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-03-07 17:40 | 2020-06-04 18:00 |  | 35 |  |  |  | 2020-03-13 23:59 | 2020-06-04 18:00 |  | 65 | 2020-09-23 16:58 |  |  | 2020-03-20 17:40 | 2020-06-25 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-13 17:40 | 2020-06-25 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 307 |  |  |  | 101318
1626 | Task(Task)-->E (Engineering) | SCHEME DIAGRAM FOR AUXILIARY INCOMER FEEDER WITH LINE PT (TYPE-DC) |  | 1.13.1.2 | Unscheduled | No | No | 2020-02-27 18:00 | 2020-04-13 17:40 | 2020-05-21 18:00 | 2020-09-17 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-128 |  | 2020-02-13 11:45 | 7012-155-PVE-L-073 |  |  |  | A |  |  |  | 1.3921 | 0.000614 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4017 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-27 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-02 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-03-07 17:40 | 2020-06-05 18:00 |  | 35 |  |  |  | 2020-03-13 23:59 | 2020-06-05 18:00 |  | 65 | 2020-09-23 17:35 |  |  | 2020-03-20 17:40 | 2020-06-26 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-13 17:40 | 2020-06-26 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 308 |  |  |  | 101319
1627 | Task(Task)-->E (Engineering) | SCHEME DIAGRAM FOR BUS COUPLER FEEDER (TYPE-DD) |  | 1.13.1.2 | Unscheduled | No | No | 2020-02-29 18:00 | 2020-04-13 17:40 | 2020-05-21 18:00 | 2020-09-17 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-129 |  | 2020-02-13 11:45 | 7012-155-PVE-L-074 |  |  |  | A |  |  |  | 1.3921 | 0.000614 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4018 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-29 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-02 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-03-07 17:40 | 2020-06-03 18:00 |  | 35 |  |  |  | 2020-03-13 23:59 | 2020-06-03 18:00 |  | 65 | 2020-09-23 17:35 |  |  | 2020-03-20 17:40 | 2020-06-24 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-13 17:40 | 2020-06-24 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 309 |  |  |  | 101320
1628 | Task(Task)-->E (Engineering) | SCHEME DIAGRAM FOR BUS PT FEEDER (TYPE-G) |  | 1.13.1.2 | Unscheduled | No | No | 2020-02-28 18:00 | 2020-04-13 17:40 | 2020-05-21 18:00 | 2020-09-17 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-130 |  | 2020-02-13 11:45 | 7012-155-PVE-L-075 |  |  |  | A |  |  |  | 1.3921 | 0.000614 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4019 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-28 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-02 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-03-07 17:40 | 2020-06-04 18:00 |  | 35 |  |  |  | 2020-03-13 23:59 | 2020-06-04 18:00 |  | 65 | 2020-09-23 17:36 |  |  | 2020-03-20 17:40 | 2020-06-25 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-13 17:40 | 2020-06-25 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 310 |  |  |  | 101321
1629 | Task(Task)-->E (Engineering) | SCHEME DIAGRAM FOR TRANSFORMER FEEDER WITHOUT DIFFERENTIAL (OIL TYPE) (TYPE-DB) |  | 1.13.1.2 | Unscheduled | No | No | 2020-02-27 18:00 | 2020-04-13 17:40 | 2020-05-21 18:00 | 2020-09-17 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-131 |  | 2020-02-13 11:45 | 7012-155-PVE-L-076 |  |  |  | A |  |  |  | 1.3921 | 0.000614 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4020 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-27 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-02 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-03-07 17:40 | 2020-06-05 18:00 |  | 35 |  |  |  | 2020-03-13 23:59 | 2020-06-05 18:00 |  | 65 | 2020-09-23 17:37 |  |  | 2020-03-20 17:40 | 2020-06-26 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-13 17:40 | 2020-06-26 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 311 |  |  |  | 101322
1630 | Task(Task)-->E (Engineering) | SCHEME DIAGRAM FOR TRANSFORMER FEEDER WITH DIFFERENTIAL (OIL TYPE) (TYPE-DBF) |  | 1.13.1.2 | Unscheduled | No | No | 2020-02-26 18:00 | 2020-04-13 17:40 | 2020-05-21 18:00 | 2020-09-17 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-132 |  | 2020-02-13 11:45 | 7012-155-PVE-L-077 |  |  |  | A |  |  |  | 1.3921 | 0.000614 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4021 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-26 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-02 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-03-07 17:40 | 2020-06-06 18:00 |  | 35 |  |  |  | 2020-03-13 23:59 | 2020-06-06 18:00 |  | 65 | 2020-09-23 17:38 |  |  | 2020-03-20 17:40 | 2020-06-27 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-13 17:40 | 2020-06-27 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 312 |  |  |  | 101323
1631 | Task(Task)-->E (Engineering) | SCHEME DIAGRAM FOR MOTOR FEEDER WITHOUT DIFFERENTIAL (TYPE-CC) |  | 1.13.1.2 | Unscheduled | No | No | 2020-03-01 23:59 | 2020-04-13 17:40 | 2020-05-21 18:00 | 2020-09-18 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-133 |  | 2020-02-13 11:45 | 7012-155-PVE-L-078 |  |  |  | A |  |  |  | 1.3921 | 0.000614 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4022 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-01 23:59 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-02 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-03-07 17:40 | 2020-06-02 18:00 |  | 35 |  |  |  | 2020-03-13 23:59 | 2020-06-02 18:00 |  | 65 | 2020-09-23 17:39 |  |  | 2020-03-20 17:40 | 2020-06-23 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-13 17:40 | 2020-06-23 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 313 |  |  |  | 101324
1632 | Task(Task)-->E (Engineering) | SCHEME DIAGRAM FOR TIE OUTGOING FEEDER (TYPE-DE) |  | 1.13.1.2 | Unscheduled | No | No | 2020-02-29 18:00 | 2020-04-13 17:40 | 2020-05-21 18:00 | 2020-09-18 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-134 |  | 2020-02-13 11:45 | 7012-155-PVE-L-079 |  |  |  | A |  |  |  | 1.3921 | 0.000614 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4023 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-29 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-02 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-03-07 17:40 | 2020-06-03 18:00 |  | 35 |  |  |  | 2020-03-13 23:59 | 2020-06-03 18:00 |  | 65 | 2020-09-23 17:40 |  |  | 2020-03-20 17:40 | 2020-06-24 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-13 17:40 | 2020-06-24 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 314 |  |  |  | 101325
1633 | Task(Task)-->E (Engineering) | SCHEME DIAGRAM FOR CAPACITOR FEEDER |  | 1.13.1.2 | Unscheduled | No | No | 2020-02-28 18:00 | 2020-04-13 17:40 | 2020-05-21 18:00 | 2020-09-18 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-135 |  | 2020-02-13 11:45 | 7012-155-PVE-L-080 |  |  |  | A |  |  |  | 1.3921 | 0.000614 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4024 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-28 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-02 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-03-07 17:40 | 2020-06-04 18:00 |  | 35 |  |  |  | 2020-03-13 23:59 | 2020-06-04 18:00 |  | 65 | 2020-09-23 17:44 |  |  | 2020-03-20 17:40 | 2020-06-25 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-13 17:40 | 2020-06-25 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 315 |  |  |  | 101326
1634 | Task(Task)-->E (Engineering) | SCHEME DIAGRAM FOR AUXILIARY PANEL |  | 1.13.1.2 | Unscheduled | No | No | 2020-02-26 18:00 | 2020-04-13 17:40 | 2020-05-21 18:00 | 2020-09-18 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-137 |  | 2020-02-13 11:45 | 7012-155-PVE-L-082 |  |  |  | A |  |  |  | 1.3921 | 0.000614 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4025 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-26 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-02 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-03-07 17:40 | 2020-06-06 18:00 |  | 35 |  |  |  | 2020-03-13 23:59 | 2020-06-06 18:00 |  | 65 | 2020-09-23 17:46 |  |  | 2020-03-20 17:40 | 2020-06-27 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-13 17:40 | 2020-06-27 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 317 |  |  |  | 101328
1635 | Task(Task)-->E (Engineering) | SCHEME DIAGRAM FOR EARTHING TRUCK |  | 1.13.1.2 | Unscheduled | No | No | 2020-02-28 18:00 | 2020-04-13 17:40 | 2020-05-21 18:00 | 2020-09-18 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-138 |  | 2020-02-13 11:46 | 7012-155-PVE-L-083 |  |  |  | A |  |  |  | 1.3921 | 0.000614 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4026 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-28 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-02 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-03-07 17:40 | 2020-06-04 18:00 |  | 35 |  |  |  | 2020-03-13 23:59 | 2020-06-04 18:00 |  | 65 | 2020-09-23 17:52 |  |  | 2020-03-20 17:40 | 2020-06-25 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-13 17:40 | 2020-06-25 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 318 |  |  |  | 101329
1636 | Task(Task)-->E (Engineering) | OIL TYPE POWER TRANSFORMER - GA DRAWINGS |  | 1.13.1.2 | Unscheduled | No | No | 2020-03-23 18:00 | 2020-05-06 17:40 | 2020-05-21 18:00 | 2020-07-28 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-139 |  | 2020-02-13 11:46 | 7012-155-PVE-B-084 |  |  |  | A |  |  |  | 2.5522 | 0.001126 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4008 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-23 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-25 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-04-01 17:40 | 2020-06-05 18:00 |  | 35 |  |  |  | 2020-04-07 23:59 | 2020-06-05 18:00 |  | 65 | 2020-07-20 11:44 |  |  | 2020-04-14 17:40 | 2020-06-26 18:00 |  | 80 | 2020-08-03 10:04 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-06 17:40 | 2020-06-26 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 319 |  |  |  | 101330
1637 | Task(Task)-->E (Engineering) | OIL TYPE POWER TRANSFORMER - RATING AND DIAGRAM PLATE |  | 1.13.1.2 | Unscheduled | No | No | 2020-03-25 17:40 | 2020-05-06 17:40 | 2020-05-21 18:00 | 2020-07-28 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-140 |  | 2020-02-13 11:46 | 7012-155-PVE-W-085 |  |  |  | A |  |  |  | 2.5522 | 0.001126 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4029 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-25 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-25 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-04-01 17:40 | 2020-06-03 18:00 |  | 35 |  |  |  | 2020-04-07 23:59 | 2020-06-03 18:00 |  | 65 | 2020-07-20 11:45 |  |  | 2020-04-14 17:40 | 2020-06-24 18:00 |  | 80 | 2020-07-28 17:55 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-06 17:40 | 2020-06-24 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 320 |  |  |  | 101331
1638 | Task(Task)-->E (Engineering) | OIL TYPE POWER TRANSFORMER - GA OF H.V. CABLE BOX |  | 1.13.1.2 | Unscheduled | No | No | 2020-03-23 18:00 | 2020-05-06 17:40 | 2020-05-21 18:00 | 2020-07-28 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-141 |  | 2020-02-13 11:46 | 7012-155-PVE-B-086 |  |  |  | A |  |  |  | 0.46404 | 0.000205 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 8.17 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4009 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-23 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-25 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-04-01 17:40 | 2020-06-05 18:00 |  | 35 |  |  |  | 2020-04-07 23:59 | 2020-06-05 18:00 |  | 65 | 2020-07-20 11:46 |  |  | 2020-04-14 17:40 | 2020-06-26 18:00 |  | 80 | 2020-08-03 10:04 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-06 17:40 | 2020-06-26 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 321 |  |  |  | 101332
1639 | Task(Task)-->E (Engineering) | OIL TYPE POWER TRANSFORMER - GA OF L.V. CABLE BOX |  | 1.13.1.2 | Unscheduled | No | No | 2020-03-25 17:40 | 2020-05-06 17:40 | 2020-05-21 18:00 | 2020-07-28 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-142 |  | 2020-02-13 11:46 | 7012-155-PVE-B-087 |  |  |  | A |  |  |  | 0.46404 | 0.000205 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 8.17 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4010 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-26 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-25 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-04-01 17:40 | 2020-06-02 18:00 |  | 35 |  |  |  | 2020-04-07 23:59 | 2020-06-02 18:00 |  | 65 | 2020-07-20 11:46 |  |  | 2020-04-14 17:40 | 2020-06-23 18:00 |  | 80 | 2020-08-03 10:03 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-06 17:40 | 2020-06-23 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 322 |  |  |  | 101333
1640 | Task(Task)-->E (Engineering) | OIL TYPE POWER TRANSFORMER - GA & SCHEMATIC OF MARSHALLING BOX |  | 1.13.1.2 | Unscheduled | No | No | 2020-03-23 18:00 | 2020-05-06 17:40 | 2020-05-21 18:00 | 2020-07-28 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-143 |  | 2020-02-13 11:46 | 7012-155-PVE-B-088 |  |  |  | A |  |  |  | 1.3921 | 0.000614 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4011 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-23 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-25 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-04-01 17:40 | 2020-06-05 18:00 |  | 35 |  |  |  | 2020-04-07 23:59 | 2020-06-05 18:00 |  | 65 | 2020-07-20 11:47 |  |  | 2020-04-14 17:40 | 2020-06-26 18:00 |  | 80 | 2020-08-03 10:03 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-06 17:40 | 2020-06-26 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 323 |  |  |  | 101334
1641 | Task(Task)-->E (Engineering) | OIL TYPE POWER TRANSFORMER - MANDATORY SPARES LIST |  | 1.13.1.2 | Unscheduled | No | No | 2020-03-25 17:40 | 2020-05-06 17:40 | 2020-05-21 18:00 | 2020-10-15 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-144 |  | 2020-02-13 11:46 | 7012-155-PVE-W-089 |  |  |  | A |  |  |  | 1.3921 | 0.000614 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4030 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-25 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-25 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-04-01 17:40 | 2020-06-03 18:00 |  | 35 |  |  |  | 2020-04-07 23:59 | 2020-06-03 18:00 |  | 65 |  |  |  | 2020-04-14 17:40 | 2020-06-24 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-06 17:40 | 2020-06-24 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 324 |  |  |  | 101335
1642 | Task(Task)-->E (Engineering) | OIL TYPE POWER TRANSFORMER - DATASHEET |  | 1.13.1.2 | Unscheduled | No | No | 2020-03-24 18:00 | 2020-05-06 17:40 | 2020-05-21 18:00 | 2020-07-20 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-145 |  | 2020-02-13 11:46 | 7012-155-PVE-Y-090 |  |  |  | A |  |  |  | 1.3921 | 0.000614 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4034 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-24 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-25 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-04-01 17:40 | 2020-06-04 18:00 |  | 35 |  |  |  | 2020-04-07 23:59 | 2020-06-04 18:00 |  | 65 | 2020-09-23 17:53 |  |  | 2020-04-14 17:40 | 2020-06-25 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-06 17:40 | 2020-06-25 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 325 |  |  |  | 101336
1643 | Task(Task)-->E (Engineering) | OIL TYPE DISTRIBUTION TRANSFORMER - GA DRAWINGS |  | 1.13.1.2 | Unscheduled | No | No | 2020-03-23 18:00 | 2020-05-06 17:40 | 2020-05-21 18:00 | 2020-08-06 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-146 |  | 2020-02-13 11:46 | 7012-155-PVE-B-091 |  |  |  | A |  |  |  | 1.3921 | 0.000614 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4012 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-23 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-25 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-04-01 17:40 | 2020-06-05 18:00 |  | 35 |  |  |  | 2020-04-07 23:59 | 2020-06-05 18:00 |  | 65 | 2020-09-23 17:54 |  |  | 2020-04-14 17:40 | 2020-06-26 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-06 17:40 | 2020-06-26 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 326 |  |  |  | 101337
1644 | Task(Task)-->E (Engineering) | OIL TYPE DISTRIBUTION TRANSFORMER - RATING AND DIAGRAM PLATE |  | 1.13.1.2 | Unscheduled | No | No | 2020-03-25 17:40 | 2020-05-06 17:40 | 2020-05-21 18:00 | 2020-08-07 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-147 |  | 2020-02-13 11:46 | 7012-155-PVE-W-092 |  |  |  | A |  |  |  | 0.46404 | 0.000205 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 8.17 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4031 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-26 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-25 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-04-01 17:40 | 2020-06-02 18:00 |  | 35 |  |  |  | 2020-04-07 23:59 | 2020-06-02 18:00 |  | 65 |  |  |  | 2020-04-14 17:40 | 2020-06-23 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-06 17:40 | 2020-06-23 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 327 |  |  |  | 101338
1645 | Task(Task)-->E (Engineering) | OIL TYPE DISTRIBUTION TRANSFORMER - GA OF H.V. CABLE BOX |  | 1.13.1.2 | Unscheduled | No | No | 2020-03-25 17:40 | 2020-05-06 17:40 | 2020-05-21 18:00 | 2020-08-07 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-148 |  | 2020-02-13 11:46 | 7012-155-PVE-B-093 |  |  |  | A |  |  |  | 0.46404 | 0.000205 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 8.17 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4013 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-27 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-25 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-04-01 17:40 | 2020-06-01 18:00 |  | 35 |  |  |  | 2020-04-07 23:59 | 2020-06-01 18:00 |  | 65 |  |  |  | 2020-04-14 17:40 | 2020-06-22 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-06 17:40 | 2020-06-22 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 328 |  |  |  | 101339
1646 | Task(Task)-->E (Engineering) | OIL TYPE DISTRIBUTION TRANSFORMER - GA OF L.V. BUS DUCT |  | 1.13.1.2 | Unscheduled | No | No | 2020-03-25 17:40 | 2020-05-06 17:40 | 2020-05-21 18:00 | 2020-08-07 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-149 |  | 2020-02-13 11:46 | 7012-155-PVE-B-094 |  |  |  | A |  |  |  | 0.46404 | 0.000205 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 8.17 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4014 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-25 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-25 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-04-01 17:40 | 2020-06-03 18:00 |  | 35 |  |  |  | 2020-04-07 23:59 | 2020-06-03 18:00 |  | 65 |  |  |  | 2020-04-14 17:40 | 2020-06-24 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-06 17:40 | 2020-06-24 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 329 |  |  |  | 101340
1647 | Task(Task)-->E (Engineering) | OIL TYPE DISTRIBUTION TRANSFORMER - GA & SCHEMATIC OF MARSHALLING BOX |  | 1.13.1.2 | Unscheduled | No | No | 2020-03-24 18:00 | 2020-05-06 17:40 | 2020-05-21 18:00 | 2020-08-12 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-150 |  | 2020-02-13 11:46 | 7012-155-PVE-B-095 |  |  |  | A |  |  |  | 1.3921 | 0.000614 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4015 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-24 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-25 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-04-01 17:40 | 2020-06-04 18:00 |  | 35 |  |  |  | 2020-04-07 23:59 | 2020-06-04 18:00 |  | 65 |  |  |  | 2020-04-14 17:40 | 2020-06-25 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-06 17:40 | 2020-06-25 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 330 |  |  |  | 101341
1648 | Task(Task)-->E (Engineering) | OIL TYPE DISTRIBUTION TRANSFORMER - MANDATORY SPARES LIST |  | 1.13.1.2 | Unscheduled | No | No | 2020-03-24 18:00 | 2020-05-06 17:40 | 2020-05-21 18:00 | 2020-08-21 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-151 |  | 2020-02-13 11:46 | 7012-155-PVE-W-096 |  |  |  | A |  |  |  | 1.3921 | 0.000614 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4032 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-24 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-25 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-04-01 17:40 | 2020-06-04 18:00 |  | 35 |  |  |  | 2020-04-07 23:59 | 2020-06-04 18:00 |  | 65 |  |  |  | 2020-04-14 17:40 | 2020-06-25 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-06 17:40 | 2020-06-25 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 331 |  |  |  | 101342
1649 | Task(Task)-->E (Engineering) | OIL TYPE DISTRIBUTION TRANSFORMER - DATASHEET |  | 1.13.1.2 | Unscheduled | No | No | 2020-03-23 18:00 | 2020-05-06 17:40 | 2020-05-21 18:00 | 2020-08-12 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-152 |  | 2020-02-13 11:46 | 7012-155-PVE-Y-097 |  |  |  | A |  |  |  | 1.3921 | 0.000614 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4035 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-23 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-25 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-04-01 17:40 | 2020-06-05 18:00 |  | 35 |  |  |  | 2020-04-07 23:59 | 2020-06-05 18:00 |  | 65 |  |  |  | 2020-04-14 17:40 | 2020-06-26 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-06 17:40 | 2020-06-26 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 332 |  |  |  | 101343
1650 | Task(Task)-->E (Engineering) | GAD, WIRING DIAGRAM, DATA SHEET & BOM OF 415V LV VFD FOR CHP. |  | 1.13.1.2 | Unscheduled | No | No | 2020-04-04 17:40 | 2020-05-16 17:40 | 2020-05-21 18:00 | 2020-07-12 23:59 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-154 |  | 2020-02-13 11:46 | 7012-155-PVE-W-099 |  |  |  | A |  |  |  | 5.1044 | 0.002251 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 82.54 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4005 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-05 23:59 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-04-04 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-04-10 17:40 | 2020-06-02 18:00 |  | 35 |  |  |  | 2020-04-17 23:59 | 2020-06-02 18:00 |  | 65 | 2020-08-03 10:44 |  |  | 2020-04-23 17:40 | 2020-06-23 18:00 |  | 80 | 2020-08-03 10:45 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-16 17:40 | 2020-06-23 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 334 |  |  |  | 101345
1651 | Task(Task)-->E (Engineering) | DATASHEET & TYPICAL SCHEME DIAGRAM OF 415V LT PMCC FOR CHP |  | 1.13.1.2 | Unscheduled | No | No | 2020-03-11 18:00 | 2020-04-23 17:40 | 2020-05-21 18:00 | 2020-09-22 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-158 |  | 2020-02-13 11:46 | 7012-155-PVE-L-103 |  |  |  | A |  |  |  | 12.993 | 0.00573 | 0.56 | Plan & Actual | Date |  | 0 | 0 | 0 | 207.15 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4027 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-11 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-12 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-03-19 17:40 | 2020-06-04 18:00 |  | 35 |  |  |  | 2020-03-25 23:59 | 2020-06-04 18:00 |  | 65 |  |  |  | 2020-04-01 17:40 | 2020-06-25 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-23 17:40 | 2020-06-25 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 338 |  |  |  | 101349
1652 | Task(Task)-->E (Engineering) | GA, DATA SHEETS, BOM & LAYOUT OF 415V LT (NSPBD) BUSDUCT |  | 1.13.1.2 | Unscheduled | No | No | 2020-03-20 17:40 | 2020-05-01 17:40 | 2020-05-21 18:00 | 2020-09-04 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-159 |  | 2020-02-13 11:46 | 7012-155-PVE-W-104 |  |  |  | A |  |  |  | 5.1044 | 0.002251 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 82.54 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4033 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-23 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-20 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-03-26 17:40 | 2020-05-31 23:59 |  | 35 |  |  |  | 2020-04-02 23:59 | 2020-05-31 23:59 |  | 65 |  |  |  | 2020-04-08 17:40 | 2020-06-21 23:59 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-01 17:40 | 2020-06-21 23:59 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 339 |  |  |  | 101350
1653 | Task(Task)-->E (Engineering) | SUBSTATION-1 (SS-1) NEAR KDTP-1 EQUIPMENT, CABLE ROUTING,EARTHING & LIGHTNING LAYOUT WITH PLAN & SECTIONAL VIEW & BOM. |  | 1.13.1.2 | Unscheduled | No | No | 2019-12-18 18:00 | 2020-02-12 17:40 | 2020-01-13 18:00 | 2020-05-06 18:00 |  |  | 2020-02-21 14:31 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5060 |  | 2020-02-13 11:44 | 7012-155-PVE-F-022 |  |  |  | A |  |  |  | 15.5452 | 0.006856 | 0.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 248.42 | 0 | 7.3 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4001 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-12-18 18:00 | 2020-01-13 18:00 |  | 10 | 2020-01-13 23:31 |  |  | 2020-01-03 17:40 | 2020-02-24 18:00 |  | 30 | 2020-02-24 23:31 |  |  | 2020-01-09 17:40 | 2020-03-09 18:00 |  | 35 | 2020-03-09 23:31 |  |  | 2020-01-15 23:59 | 2020-03-16 18:00 |  | 65 | 2020-03-16 23:31 |  |  | 2020-01-21 17:40 | 2020-04-06 18:00 |  | 80 | 2020-04-15 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-02-12 17:40 | 2020-05-06 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 257 |  |  |  | 101268
1654 | Task(Task)-->E (Engineering) | LIGHTING LAYOUT PLAN WITH POWER DISTRIBUTION ARRANGEMENT, SECTIONAL VIEW, BOM OF SS-1 |  | 1.13.1.2 | Unscheduled | No | No | 2020-02-10 18:00 | 2020-03-31 17:40 | 2020-05-15 09:00 | 2020-07-11 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5071 |  | 2020-02-13 11:44 | 7012-155-PVE-G-033 |  |  |  | A |  |  |  | 15.5452 | 0.006856 | 0.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 248.42 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4002 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-10 18:00 | 2020-05-30 18:00 |  | 10 | 2020-05-10 23:31 |  |  | 2020-02-18 17:40 | 2020-06-06 18:00 |  | 30 | 2020-05-12 23:31 |  |  | 2020-02-25 17:40 | 2020-06-13 18:00 |  | 35 | 2020-05-12 23:31 |  |  | 2020-03-02 23:59 | 2020-06-20 18:00 |  | 65 | 2020-05-15 23:31 |  |  | 2020-03-07 17:40 | 2020-07-11 18:00 |  | 80 | 2020-05-22 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-31 17:40 | 2020-07-11 18:00 |  | 100 | 2020-05-22 23:31 | [121 empty] | Varun Parihari | [21 empty] | 268 |  |  |  | 101279
1655 | Task(Task)-->E (Engineering) | GA & CROSS SECTIONAL, FLOOR PLAN FOR 33 kV HT SWITCHGEAR FOR CHP |  | 1.13.1.2 | Unscheduled | No | No | 2020-02-28 18:00 | 2020-04-13 17:40 | 2020-05-21 18:00 | 2020-09-18 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-121 |  | 2020-02-13 11:45 | 7012-155-PVE-B-066 |  |  |  | A |  |  |  | 1.3921 | 0.000614 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4003 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-28 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-02 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-03-07 17:40 | 2020-06-04 18:00 |  | 35 |  |  |  | 2020-03-13 23:59 | 2020-06-04 18:00 |  | 65 | 2020-09-23 14:43 |  |  | 2020-03-20 17:40 | 2020-06-25 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-13 17:40 | 2020-06-25 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 301 |  |  |  | 101312
1656 | Task(Task)-->E (Engineering) | SINGLE LINE DIAGRAM FOR 33 kV HT SWITCHGEAR FOR CHP |  | 1.13.1.2 | Unscheduled | No | No | 2020-02-27 18:00 | 2020-04-13 17:40 | 2020-05-21 18:00 | 2020-09-22 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-124 |  | 2020-02-13 11:45 | 7012-155-PVE-P-069 |  |  |  | A |  |  |  | 1.3921 | 0.000614 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4004 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-27 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-02 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-03-07 17:40 | 2020-06-05 18:00 |  | 35 |  |  |  | 2020-03-13 23:59 | 2020-06-05 18:00 |  | 65 | 2020-09-23 14:47 |  |  | 2020-03-20 17:40 | 2020-06-26 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-13 17:40 | 2020-06-26 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 304 |  |  |  | 101315
1657 | Task(Task)-->E (Engineering) | GA, SLD & BOM FOR 415V LT CHP PMCC-1 |  | 1.13.1.2 | Unscheduled | No | No | 2020-03-12 17:40 | 2020-04-23 17:40 | 2020-05-21 18:00 | 2020-09-22 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-155 |  | 2020-02-13 11:46 | 7012-155-PVE-W-100 |  |  |  | A |  |  |  | 7.6566 | 0.003377 | 0.33 | Plan & Actual | Date |  | 0 | 0 | 0 | 124.21 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4006 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-12 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-12 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-03-19 17:40 | 2020-06-03 18:00 |  | 35 |  |  |  | 2020-03-25 23:59 | 2020-06-03 18:00 |  | 65 |  |  |  | 2020-04-01 17:40 | 2020-06-24 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-23 17:40 | 2020-06-24 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 335 |  |  |  | 101346
1658 | Task(Task)-->P (Procurement) | PROCUREMENT | 1.13.2 | 1.13 | Work In Progress | No | No | 2019-11-12 09:00 | 2021-03-31 18:00 | 2019-11-02 09:00 | 2021-10-24 23:59 |  |  | 2019-11-02 10:57 |  |  |  | 77.9043 | 20.7092 | [15 empty] | 58.6757 | 2.0635 | 202.93 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4036 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019138
1659 | Task(Task)-->P (Procurement) | PURCHASE REQUISITION | 1.13.2.1 | 1.13.2 | Work In Progress | No | No | 2019-11-12 09:00 | 2020-05-26 18:00 | 2019-11-02 09:00 | 2020-04-18 18:00 |  |  | 2019-11-02 10:57 |  |  |  | 100 | 84.2681 | [15 empty] | 5.0015 | 0.10321 | 10.15 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4037 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019139
1660 | Task(Task)-->P (Procurement) | 33/6.9KV HT TRANSFORMER (ONAN TYPE) |  | 1.13.2.1 | Completed | No | No | 2019-11-28 09:00 | 2019-11-28 18:00 | 2020-01-17 09:00 | 2020-01-17 18:00 |  |  | 2020-01-22 10:57 | 2020-01-22 10:57 |  |  | 100 | 100 | [15 empty] | 10.0295 | 0.010351 | 1.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4038 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019140
1661 | Task(Task)-->P (Procurement) | HT SWITCHGEAR (33KV & 6.6KV) |  | 1.13.2.1 | Completed | No | No | 2019-11-13 09:00 | 2019-11-13 18:00 | 2019-11-02 09:00 | 2019-11-02 18:00 |  |  | 2019-11-02 10:57 | 2019-11-02 10:57 |  |  | 100 | 100 | [15 empty] | 31.2684 | 0.032271 | 3.18 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4039 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019141
1662 | Task(Task)-->P (Procurement) | 6.6KV HT VFD with Motors |  | 1.13.2.1 | Completed | No | No | 2019-12-30 09:00 | 2019-12-30 18:00 | 2020-01-24 09:00 | 2020-01-24 18:00 |  |  | 2019-11-21 10:57 | 2019-11-21 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4040 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019142
1663 | Task(Task)-->P (Procurement) | 415V LT VFD |  | 1.13.2.1 | Completed | No | No | 2019-12-18 09:00 | 2019-12-18 18:00 | 2019-11-21 09:00 | 2019-11-21 18:00 |  |  | 2019-11-21 10:57 | 2019-11-21 10:57 |  |  | 100 | 100 | [15 empty] | 4.6214 | 0.00477 | 0.47 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4041 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019143
1664 | Task(Task)-->P (Procurement) | 6.6KV HT APFC PANEL |  | 1.13.2.1 | Completed | No | No | 2020-01-24 09:00 | 2020-01-24 18:00 | 2020-02-13 09:00 | 2020-02-13 18:00 |  |  | 2020-02-13 10:57 | 2020-02-13 10:57 |  |  | 100 | 100 | [15 empty] | 1.1799 | 0.001218 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4042 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019144
1665 | Task(Task)-->P (Procurement) | 6.6KV/0.433V LT TRANSFORMER |  | 1.13.2.1 | Completed | No | No | 2019-11-25 09:00 | 2019-11-25 18:00 | 2020-01-22 09:00 | 2020-01-22 18:00 |  |  | 2020-01-22 15:37 | 2020-01-22 15:37 |  |  | 100 | 100 | [15 empty] | 10.0295 | 0.010351 | 1.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4043 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019145
1666 | Task(Task)-->P (Procurement) | LT BUSDUCT |  | 1.13.2.1 | Completed | No | No | 2019-12-02 09:00 | 2019-12-02 18:00 | 2019-12-11 09:00 | 2019-12-11 18:00 |  |  | 2019-12-11 10:57 | 2019-12-11 10:57 |  |  | 100 | 100 | [15 empty] | 1.5733 | 0.001624 | 0.16 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4044 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019146
1667 | Task(Task)-->P (Procurement) | 415V MCC |  | 1.13.2.1 | Unscheduled | No | No | 2019-11-28 09:00 | 2019-11-28 18:00 | 2019-11-14 09:00 | 2019-11-14 18:00 | [6 empty] | 100 | 0 | [15 empty] | 10.1278 | 0.010452 | 1.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4045 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019147
1668 | Task(Task)-->P (Procurement) | 110V DC BATTERY & BATTERY CHARGER SYSTEM |  | 1.13.2.1 | Completed | No | No | 2020-01-13 09:00 | 2020-01-13 18:00 | 2020-01-13 09:00 | 2020-01-13 18:00 |  |  | 2020-01-13 10:57 | 2020-01-13 10:57 |  |  | 100 | 100 | [15 empty] | 3.3432 | 0.00345 | 0.34 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4046 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019148
1669 | Task(Task)-->P (Procurement) | 6.6KV NEUTRAL GROUNDING RESISTOR |  | 1.13.2.1 | Completed | No | No | 2019-12-12 09:00 | 2019-12-12 18:00 | 2019-12-12 09:00 | 2019-12-12 18:00 |  |  | 2019-12-12 15:20 | 2019-12-12 15:21 |  |  | 100 | 100 | [15 empty] | 0.29499 | 0.000304 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4047 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019149
1670 | Task(Task)-->P (Procurement) | PLC SYSTEM |  | 1.13.2.1 | Completed | No | No | 2019-11-12 09:00 | 2019-11-12 18:00 | 2019-11-12 09:00 | 2019-11-12 18:00 |  |  | 2019-11-12 10:57 | 2019-11-12 10:57 |  |  | 100 | 100 | [15 empty] | 7.9646 | 0.00822 | 0.81 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4048 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019150
1671 | Task(Task)-->P (Procurement) | UPS SYSTEM |  | 1.13.2.1 | Completed | No | No | 2020-01-08 09:00 | 2020-01-08 18:00 | 2020-02-19 09:00 | 2020-02-19 18:00 |  |  | 2020-02-19 10:57 | 2020-02-19 10:57 |  |  | 100 | 100 | [15 empty] | 1.4749 | 0.001522 | 0.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4049 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019151
1672 | Task(Task)-->P (Procurement) | 24V DC BATTERY AND BATTERY CHARGER SYSTEM |  | 1.13.2.1 | Completed | No | No | 2020-01-27 09:00 | 2020-01-27 18:00 | 2020-02-26 09:00 | 2020-02-26 18:00 |  |  | 2020-02-26 10:57 | 2020-02-26 10:57 |  |  | 100 | 100 | [15 empty] | 0.6883 | 0.00071 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4050 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019152
1673 | Task(Task)-->P (Procurement) | FDA SYSTEM |  | 1.13.2.1 | Completed | No | No | 2020-02-14 09:00 | 2020-02-14 18:00 | 2020-02-17 09:00 | 2020-02-17 18:00 |  |  | 2020-02-17 10:57 | 2020-02-17 10:57 |  |  | 100 | 100 | [15 empty] | 4.8181 | 0.004973 | 0.49 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4051 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019153
1674 | Task(Task)-->P (Procurement) | SCADA |  | 1.13.2.1 | Completed | No | No | 2019-12-10 09:00 | 2019-12-10 18:00 | 2019-12-21 09:00 | 2019-12-21 18:00 |  |  | 2019-12-21 10:57 | 2019-12-21 10:57 |  |  | 100 | 100 | [15 empty] | 2.2616 | 0.002334 | 0.23 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4052 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019154
1675 | Task(Task)-->P (Procurement) | RUBBER MATS |  | 1.13.2.1 | Completed | No | No | 2020-05-26 09:00 | 2020-05-26 18:00 | 2020-04-18 09:00 | 2020-04-18 18:00 |  |  | 2020-04-18 10:57 | 2020-04-18 10:57 |  |  | 100 | 100 | [15 empty] | 0.098328 | 0.000101 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4055 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019155
1676 | Task(Task)-->P (Procurement) | MAIN LIGHTING DISTRIBUTION BOARD |  | 1.13.2.1 | Completed | No | No | 2020-02-04 09:00 | 2020-02-04 18:00 | 2020-04-02 09:00 | 2020-04-02 18:00 |  |  | 2020-04-02 17:08 | 2020-04-02 17:08 |  |  | 100 | 100 | [15 empty] | 0.49164 | 0.000507 | 0.05 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4056 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019156
1677 | Task(Task)-->P (Procurement) | LIGHTING PANELS |  | 1.13.2.1 | Unscheduled | No | No | 2020-02-28 09:00 | 2020-02-28 18:00 | 2020-04-02 09:00 | 2020-04-02 18:00 | [6 empty] | 100 | 0 | [15 empty] | 5.6047 | 0.005784 | 0.57 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4057 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019157
1678 | Task(Task)-->P (Procurement) | DCDB & DC FUSE BOARD |  | 1.13.2.1 | Completed | No | No | 2020-01-28 09:00 | 2020-01-28 18:00 | 2020-04-02 09:00 | 2020-04-02 18:00 |  |  | 2020-04-02 16:53 | 2020-04-02 16:53 |  |  | 100 | 100 | [15 empty] | 2.0649 | 0.002131 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4058 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019158
1679 | Task(Task)-->P (Procurement) | UPS DB,ACDB,MCBDB & AFB |  | 1.13.2.1 | Completed | No | No | 2020-03-18 09:00 | 2020-03-18 18:00 | 2020-04-02 09:00 | 2020-04-02 18:00 |  |  | 2020-04-02 17:01 | 2020-04-02 17:01 |  |  | 100 | 100 | [15 empty] | 2.0649 | 0.002131 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4059 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019159
1680 | Task(Task)-->P (Procurement) | TECHNICAL CLEARANCE | 1.13.2.2 | 1.13.2 | Work In Progress | No | No | 2019-11-13 09:00 | 2020-06-20 18:00 | 2019-11-02 09:00 | 2020-07-10 18:00 |  |  | 2019-11-04 14:46 |  |  |  | 100 | 83.5801 | [15 empty] | 5.0015 | 0.10321 | 10.15 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4060 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019160
1681 | Task(Task)-->P (Procurement) | 33/6.9KV HT TRANSFORMER (ONAN TYPE) |  | 1.13.2.2 | Completed | No | No | 2019-11-29 09:00 | 2019-12-22 23:59 | 2020-01-17 09:00 | 2020-02-17 18:00 |  |  | 2020-03-16 10:57 | 2020-03-16 10:57 |  |  | 100 | 100 | [15 empty] | 10.0295 | 0.010351 | 1.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4061 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019161
1682 | Task(Task)-->P (Procurement) | HT SWITCHGEAR (33KV & 6.6KV) |  | 1.13.2.2 | Completed | No | No | 2019-11-14 09:00 | 2019-12-13 18:00 | 2019-11-02 09:00 | 2020-03-10 18:00 |  |  | 2019-11-04 14:46 | 2020-03-10 14:46 |  |  | 100 | 100 | [15 empty] | 31.2684 | 0.032271 | 3.18 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4062 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019162
1683 | Task(Task)-->P (Procurement) | 6.6KV HT VFD with Motors |  | 1.13.2.2 | Completed | No | No | 2019-12-31 09:00 | 2020-01-29 18:00 | 2020-01-24 09:00 | 2020-04-16 18:00 |  |  | 2020-02-26 10:57 | 2020-02-26 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4063 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019163
1684 | Task(Task)-->P (Procurement) | 415V LT VFD |  | 1.13.2.2 | Completed | No | No | 2019-12-19 09:00 | 2020-01-17 18:00 | 2019-11-21 09:00 | 2020-02-26 18:00 |  |  | 2020-02-26 10:57 | 2020-02-26 10:57 |  |  | 100 | 100 | [15 empty] | 4.6214 | 0.00477 | 0.47 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4064 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019164
1685 | Task(Task)-->P (Procurement) | 6.6KV HT APFC PANEL |  | 1.13.2.2 | Completed | No | No | 2020-01-25 09:00 | 2020-02-16 23:59 | 2020-02-13 09:00 | 2020-04-28 18:00 |  |  | 2020-04-28 10:57 | 2020-04-28 10:57 |  |  | 100 | 100 | [15 empty] | 1.1799 | 0.001218 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4065 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019165
1686 | Task(Task)-->P (Procurement) | 6.6KV/0.433V LT TRANSFORMER |  | 1.13.2.2 | Completed | No | No | 2019-11-26 09:00 | 2019-12-20 18:00 | 2020-01-22 09:00 | 2020-03-16 18:00 |  |  | 2020-01-23 15:38 | 2020-03-16 15:38 |  |  | 100 | 100 | [15 empty] | 10.0295 | 0.010351 | 1.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4066 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019166
1687 | Task(Task)-->P (Procurement) | LT BUSDUCT |  | 1.13.2.2 | Completed | No | No | 2019-12-03 09:00 | 2020-01-03 18:00 | 2019-12-11 09:00 | 2020-03-10 18:00 |  |  | 2020-03-10 10:57 | 2020-03-10 10:57 |  |  | 100 | 100 | [15 empty] | 1.5733 | 0.001624 | 0.16 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4067 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019167
1688 | Task(Task)-->P (Procurement) | 415V MCC |  | 1.13.2.2 | Unscheduled | No | No | 2019-11-29 09:00 | 2020-01-11 18:00 | 2019-11-14 09:00 | 2020-03-11 18:00 | [6 empty] | 100 | 0 | [15 empty] | 10.1278 | 0.010452 | 1.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4068 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019168
1689 | Task(Task)-->P (Procurement) | 110V DC BATTERY & BATTERY CHARGER SYSTEM |  | 1.13.2.2 | Completed | No | No | 2020-01-14 09:00 | 2020-02-03 18:00 | 2020-01-13 09:00 | 2020-06-04 18:00 |  |  | 2020-01-14 17:10 | 2020-06-04 17:10 |  |  | 100 | 100 | [15 empty] | 3.3432 | 0.00345 | 0.34 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4069 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019169
1690 | Task(Task)-->P (Procurement) | 6.6KV NEUTRAL GROUNDING RESISTOR |  | 1.13.2.2 | Completed | No | No | 2019-12-13 09:00 | 2019-12-31 18:00 | 2019-12-12 09:00 | 2020-01-21 18:00 |  |  | 2019-12-13 15:22 | 2020-01-21 15:23 |  |  | 100 | 100 | [15 empty] | 0.29499 | 0.000304 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4070 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019170
1691 | Task(Task)-->P (Procurement) | PLC SYSTEM |  | 1.13.2.2 | Completed | No | No | 2019-11-13 09:00 | 2019-12-04 18:00 | 2019-11-12 09:00 | 2020-03-16 18:00 |  |  | 2020-03-16 10:57 | 2020-03-16 10:57 |  |  | 100 | 100 | [15 empty] | 7.9646 | 0.00822 | 0.81 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4071 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019171
1692 | Task(Task)-->P (Procurement) | UPS SYSTEM |  | 1.13.2.2 | Completed | No | No | 2020-01-09 09:00 | 2020-01-28 18:00 | 2020-02-19 09:00 | 2020-06-06 18:00 |  |  | 2020-06-06 10:57 | 2020-06-06 10:57 |  |  | 100 | 100 | [15 empty] | 1.4749 | 0.001522 | 0.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4072 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019172
1693 | Task(Task)-->P (Procurement) | 24V DC BATTERY AND BATTERY CHARGER SYSTEM |  | 1.13.2.2 | Unscheduled | No | No | 2020-01-28 09:00 | 2020-02-07 18:00 | 2020-02-26 09:00 | 2020-07-10 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.6883 | 0.00071 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4073 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019173
1694 | Task(Task)-->P (Procurement) | FDA SYSTEM |  | 1.13.2.2 | Completed | No | No | 2020-02-15 09:00 | 2020-03-12 18:00 | 2020-02-17 09:00 | 2020-06-10 18:00 |  |  | 2020-06-10 10:57 | 2020-06-10 10:57 |  |  | 100 | 100 | [15 empty] | 4.8181 | 0.004973 | 0.49 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4074 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019174
1695 | Task(Task)-->P (Procurement) | SCADA |  | 1.13.2.2 | Completed | No | No | 2019-12-11 09:00 | 2020-01-15 18:00 | 2019-12-21 09:00 | 2020-03-16 18:00 |  |  | 2020-03-16 10:57 | 2020-03-16 10:57 |  |  | 100 | 100 | [15 empty] | 2.2616 | 0.002334 | 0.23 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4075 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019175
1696 | Task(Task)-->P (Procurement) | RUBBER MATS |  | 1.13.2.2 | Completed | No | No | 2020-05-27 09:00 | 2020-06-20 18:00 | 2020-04-18 09:00 | 2020-04-20 18:00 |  |  | 2020-04-20 10:57 | 2020-04-20 10:57 |  |  | 100 | 100 | [15 empty] | 0.098328 | 0.000101 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4078 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019176
1697 | Task(Task)-->P (Procurement) | MAIN LIGHTING DISTRIBUTION BOARD |  | 1.13.2.2 | Completed | No | No | 2020-02-05 09:00 | 2020-04-02 18:00 | 2020-04-02 09:00 | 2020-07-01 18:00 |  |  | 2020-04-03 17:08 | 2020-07-01 17:08 |  |  | 100 | 100 | [15 empty] | 0.49164 | 0.000507 | 0.05 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4079 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019177
1698 | Task(Task)-->P (Procurement) | LIGHTING PANELS |  | 1.13.2.2 | Unscheduled | No | No | 2020-02-29 09:00 | 2020-05-11 18:00 | 2020-04-02 09:00 | 2020-07-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 5.6047 | 0.005784 | 0.57 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4080 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019178
1699 | Task(Task)-->P (Procurement) | DCDB & DC FUSE BOARD |  | 1.13.2.2 | Completed | No | No | 2020-01-29 09:00 | 2020-04-02 18:00 | 2020-04-02 09:00 | 2020-07-01 18:00 |  |  | 2020-04-03 16:59 | 2020-07-01 16:59 |  |  | 100 | 100 | [15 empty] | 2.0649 | 0.002131 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4081 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019179
1700 | Task(Task)-->P (Procurement) | UPS DB,ACDB,MCBDB & AFB |  | 1.13.2.2 | Completed | No | No | 2020-03-19 09:00 | 2020-04-02 18:00 | 2020-04-02 09:00 | 2020-07-01 18:00 |  |  | 2020-04-03 17:03 | 2020-07-01 17:03 |  |  | 100 | 100 | [15 empty] | 2.0649 | 0.002131 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4082 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019180
1701 | Task(Task)-->P (Procurement) | ORDERING | 1.13.2.3 | 1.13.2 | Work In Progress | No | No | 2019-12-05 09:00 | 2020-06-25 18:00 | 2020-01-21 09:00 | 2020-08-13 18:00 |  |  | 2020-03-11 14:48 |  |  |  | 100 | 77.3063 | [15 empty] | 9.998 | 0.20631 | 20.29 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4083 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019181
1702 | Task(Task)-->P (Procurement) | 33/6.9KV HT TRANSFORMER (ONAN TYPE) |  | 1.13.2.3 | Completed | No | No | 2019-12-23 09:00 | 2020-01-15 18:00 | 2020-02-17 09:00 | 2020-06-24 18:00 |  |  | 2020-07-16 22:27 | 2020-07-16 22:27 |  |  | 100 | 100 | [15 empty] | 10.0148 | 0.020661 | 2.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4084 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019182
1703 | Task(Task)-->P (Procurement) | HT SWITCHGEAR (33KV & 6.6KV) |  | 1.13.2.3 | Completed | No | No | 2019-12-14 09:00 | 2020-01-13 18:00 | 2020-03-10 09:00 | 2020-07-18 18:00 |  |  | 2020-03-11 14:48 | 2020-07-04 14:48 |  |  | 100 | 100 | [15 empty] | 31.3764 | 0.064732 | 6.36 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4085 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019183
1704 | Task(Task)-->P (Procurement) | 6.6KV HT VFD with Motors |  | 1.13.2.3 | Completed | No | No | 2020-01-30 09:00 | 2020-02-28 18:00 | 2020-04-16 09:00 | 2020-07-18 18:00 |  |  | 2020-04-29 10:57 | 2020-04-29 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4086 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019184
1705 | Task(Task)-->P (Procurement) | 415V LT VFD |  | 1.13.2.3 | Completed | No | No | 2020-01-18 09:00 | 2020-02-17 18:00 | 2020-02-26 09:00 | 2020-06-10 18:00 |  |  | 2020-04-29 10:57 | 2020-06-10 09:39 |  |  | 100 | 100 | [15 empty] | 4.6374 | 0.009567 | 0.94 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4087 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019185
1706 | Task(Task)-->P (Procurement) | 6.6KV HT APFC PANEL |  | 1.13.2.3 | Completed | No | No | 2020-02-17 09:00 | 2020-03-10 18:00 | 2020-04-28 09:00 | 2020-07-28 18:00 |  |  | 2020-05-04 15:15 | 2020-07-10 15:15 |  |  | 100 | 100 | [15 empty] | 1.184 | 0.002443 | 0.24 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4088 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019186
1707 | Task(Task)-->P (Procurement) | 6.6KV/0.433V LT TRANSFORMER |  | 1.13.2.3 | Completed | No | No | 2019-12-21 09:00 | 2020-01-15 18:00 | 2020-03-16 09:00 | 2020-06-23 18:00 |  |  | 2020-06-23 10:14 | 2020-06-23 10:14 |  |  | 100 | 100 | [15 empty] | 10.1135 | 0.020865 | 2.05 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4089 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019187
1708 | Task(Task)-->P (Procurement) | LT BUSDUCT |  | 1.13.2.3 | Completed | No | No | 2020-01-04 09:00 | 2020-02-04 18:00 | 2020-03-10 09:00 | 2020-06-11 18:00 |  |  | 2020-04-27 10:57 | 2020-04-27 10:57 |  |  | 100 | 100 | [15 empty] | 1.5294 | 0.003155 | 0.31 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4090 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019188
1709 | Task(Task)-->P (Procurement) | 415V MCC |  | 1.13.2.3 | Unscheduled | No | No | 2020-01-12 | 2020-02-25 18:00 | 2020-03-11 09:00 | 2020-07-04 18:00 | [6 empty] | 100 | 0 | [15 empty] | 10.2121 | 0.021068 | 2.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4091 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019189
1710 | Task(Task)-->P (Procurement) | 110V DC BATTERY & BATTERY CHARGER SYSTEM |  | 1.13.2.3 | Completed | No | No | 2020-02-04 09:00 | 2020-02-24 18:00 | 2020-06-04 09:00 | 2020-07-18 18:00 |  |  | 2020-06-05 17:10 | 2020-07-06 17:10 |  |  | 100 | 100 | [15 empty] | 3.3054 | 0.006819 | 0.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4092 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019190
1711 | Task(Task)-->P (Procurement) | 6.6KV NEUTRAL GROUNDING RESISTOR |  | 1.13.2.3 | Completed | No | No | 2020-01-01 09:00 | 2020-01-20 18:00 | 2020-01-21 09:00 | 2020-03-19 18:00 |  |  | 2020-03-19 10:19 | 2020-03-19 10:19 |  |  | 100 | 100 | [15 empty] | 0.296 | 0.000611 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4093 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019191
1712 | Task(Task)-->P (Procurement) | PLC SYSTEM |  | 1.13.2.3 | Completed | No | No | 2019-12-05 09:00 | 2019-12-27 18:00 | 2020-03-16 09:00 | 2020-07-07 18:00 |  |  | 2020-03-17 17:20 | 2020-06-04 17:20 |  |  | 100 | 100 | [15 empty] | 7.9921 | 0.016488 | 1.62 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4094 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019192
1713 | Task(Task)-->P (Procurement) | UPS SYSTEM |  | 1.13.2.3 | Unscheduled | No | No | 2020-01-29 09:00 | 2020-02-18 18:00 | 2020-06-06 09:00 | 2020-07-31 18:00 | [6 empty] | 100 | 0 | [15 empty] | 1.4307 | 0.002952 | 0.29 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4095 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019193
1714 | Task(Task)-->P (Procurement) | 24V DC BATTERY AND BATTERY CHARGER SYSTEM |  | 1.13.2.3 | Unscheduled | No | No | 2020-02-08 09:00 | 2020-02-19 18:00 | 2020-07-10 09:00 | 2020-08-07 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.69068 | 0.001425 | 0.14 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4096 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019194
1715 | Task(Task)-->P (Procurement) | FDA SYSTEM |  | 1.13.2.3 | Unscheduled | No | No | 2020-03-13 09:00 | 2020-04-08 18:00 | 2020-06-10 09:00 | 2020-08-06 18:00 | [6 empty] | 100 | 0 | [15 empty] | 4.7854 | 0.009873 | 0.97 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4097 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019195
1716 | Task(Task)-->P (Procurement) | SCADA |  | 1.13.2.3 | Completed | No | No | 2020-01-16 09:00 | 2020-02-20 18:00 | 2020-03-16 09:00 | 2020-06-24 18:00 |  |  | 2020-06-24 10:20 | 2020-06-24 10:20 |  |  | 100 | 100 | [15 empty] | 2.22 | 0.00458 | 0.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4098 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019196
1717 | Task(Task)-->P (Procurement) | RUBBER MATS |  | 1.13.2.3 | Completed | No | No | 2020-06-21 | 2020-06-25 18:00 | 2020-04-20 09:00 | 2020-06-06 18:00 |  |  | 2020-04-25 10:57 | 2020-04-25 10:57 |  |  | 100 | 100 | [15 empty] | 0.098668 | 0.000204 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4101 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019197
1718 | Task(Task)-->P (Procurement) | MAIN LIGHTING DISTRIBUTION BOARD |  | 1.13.2.3 | Completed | No | No | 2020-04-03 09:00 | 2020-04-18 18:00 | 2020-07-01 09:00 | 2020-08-13 18:00 |  |  | 2020-07-02 17:08 | 2020-07-07 17:08 |  |  | 100 | 100 | [15 empty] | 0.49334 | 0.001018 | 0.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4102 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019198
1719 | Task(Task)-->P (Procurement) | LIGHTING PANELS |  | 1.13.2.3 | Unscheduled | No | No | 2020-05-12 09:00 | 2020-06-25 18:00 | 2020-07-01 09:00 | 2020-08-13 18:00 | [6 empty] | 100 | 0 | [15 empty] | 5.5747 | 0.011501 | 1.13 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4103 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019199
1720 | Task(Task)-->P (Procurement) | DCDB & DC FUSE BOARD |  | 1.13.2.3 | Completed | No | No | 2020-04-03 09:00 | 2020-04-18 18:00 | 2020-07-01 09:00 | 2020-08-13 18:00 |  |  | 2020-07-02 17:00 | 2020-07-07 17:00 |  |  | 100 | 100 | [15 empty] | 2.0227 | 0.004173 | 0.41 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4104 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019200
1721 | Task(Task)-->P (Procurement) | UPS DB,ACDB,MCBDB & AFB |  | 1.13.2.3 | Completed | No | No | 2020-04-03 09:00 | 2020-04-18 18:00 | 2020-07-01 09:00 | 2020-08-13 18:00 |  |  | 2020-07-02 17:05 | 2020-07-07 17:05 |  |  | 100 | 100 | [15 empty] | 2.0227 | 0.004173 | 0.41 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4105 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019201
1722 | Task(Task)-->P (Procurement) | ITP APPROVAL | 1.13.2.4 | 1.13.2 | Work In Progress | No | No | 2019-12-28 09:00 | 2020-08-04 18:00 | 2020-06-05 09:00 | 2020-10-30 18:00 |  |  | 2020-06-05 08:53 |  |  |  | 100 | 10.3242 | [15 empty] | 5.0015 | 0.10321 | 10.15 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4106 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019202
1723 | Task(Task)-->P (Procurement) | 33/6.9KV HT TRANSFORMER (ONAN TYPE) |  | 1.13.2.4 | Completed | No | No | 2020-01-16 09:00 | 2020-02-24 18:00 | 2020-07-03 09:00 | 2020-07-15 18:00 |  |  | 2020-07-03 08:44 | 2020-07-15 08:45 |  |  | 100 | 100 | [15 empty] | 10.0295 | 0.010351 | 1.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4107 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019203
1724 | Task(Task)-->P (Procurement) | HT SWITCHGEAR (33KV & 6.6KV) |  | 1.13.2.4 | Unscheduled | No | No | 2020-01-14 09:00 | 2020-02-22 18:00 | 2020-08-06 09:00 | 2020-10-20 18:00 |  |  | 2020-07-13 10:49 |  |  |  | 100 | 0 | [15 empty] | 31.2684 | 0.032271 | 3.18 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4108 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019204
1725 | Task(Task)-->P (Procurement) | 6.6KV HT VFD with Motors |  | 1.13.2.4 | Unscheduled | No | No | 2020-02-29 09:00 | 2020-04-08 18:00 | 2020-08-01 09:00 | 2020-09-09 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4109 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019205
1726 | Task(Task)-->P (Procurement) | 415V LT VFD |  | 1.13.2.4 | Unscheduled | No | No | 2020-02-18 09:00 | 2020-03-28 18:00 | 2020-09-14 09:00 | 2020-10-15 18:00 |  |  | 2020-09-02 17:03 |  |  |  | 100 | 0 | [15 empty] | 4.6214 | 0.00477 | 0.47 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4110 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019206
1727 | Task(Task)-->P (Procurement) | 6.6KV HT APFC PANEL |  | 1.13.2.4 | Unscheduled | No | No | 2020-03-11 09:00 | 2020-04-19 23:59 | 2020-08-01 09:00 | 2020-09-09 18:00 | [6 empty] | 100 | 0 | [15 empty] | 1.1799 | 0.001218 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4111 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019207
1728 | Task(Task)-->P (Procurement) | 6.6KV/0.433V LT TRANSFORMER |  | 1.13.2.4 | Unscheduled | No | No | 2020-01-16 09:00 | 2020-02-24 18:00 | 2020-08-05 09:00 | 2020-10-10 18:00 | [6 empty] | 100 | 0 | [15 empty] | 10.0295 | 0.010351 | 1.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4112 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019208
1729 | Task(Task)-->P (Procurement) | LT BUSDUCT |  | 1.13.2.4 | Unscheduled | No | No | 2020-02-05 09:00 | 2020-03-15 23:59 | 2020-09-21 09:00 | 2020-10-20 18:00 |  |  | 2020-09-21 17:35 |  |  |  | 100 | 0 | [15 empty] | 1.5733 | 0.001624 | 0.16 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4113 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019209
1730 | Task(Task)-->P (Procurement) | 415V MCC |  | 1.13.2.4 | Unscheduled | No | No | 2020-02-26 09:00 | 2020-04-05 23:59 | 2020-08-01 09:00 | 2020-09-09 18:00 | [6 empty] | 100 | 0 | [15 empty] | 10.1278 | 0.010452 | 1.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4114 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019210
1731 | Task(Task)-->P (Procurement) | 110V DC BATTERY & BATTERY CHARGER SYSTEM |  | 1.13.2.4 | Unscheduled | No | No | 2020-02-25 09:00 | 2020-04-04 18:00 | 2020-07-07 09:00 | 2020-10-10 18:00 |  |  | 2020-07-07 10:31 |  |  |  | 100 | 0 | [15 empty] | 3.3432 | 0.00345 | 0.34 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4115 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019211
1732 | Task(Task)-->P (Procurement) | 6.6KV NEUTRAL GROUNDING RESISTOR |  | 1.13.2.4 | Completed | No | No | 2020-01-21 09:00 | 2020-02-29 18:00 | 2020-06-05 09:00 | 2020-07-15 18:00 |  |  | 2020-06-05 08:53 | 2020-07-15 08:53 |  |  | 100 | 100 | [15 empty] | 0.29499 | 0.000304 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4116 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019212
1733 | Task(Task)-->P (Procurement) | PLC SYSTEM |  | 1.13.2.4 | Unscheduled | No | No | 2019-12-28 09:00 | 2020-02-05 18:00 | 2020-08-27 09:00 | 2020-10-30 18:00 |  |  | 2020-08-27 17:07 |  |  |  | 100 | 0 | [15 empty] | 7.9646 | 0.00822 | 0.81 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4117 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019213
1734 | Task(Task)-->P (Procurement) | UPS SYSTEM |  | 1.13.2.4 | Unscheduled | No | No | 2020-02-19 09:00 | 2020-03-29 23:59 | 2020-09-01 09:00 | 2020-10-30 18:00 | [6 empty] | 100 | 0 | [15 empty] | 1.4749 | 0.001522 | 0.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4118 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019214
1735 | Task(Task)-->P (Procurement) | 24V DC BATTERY AND BATTERY CHARGER SYSTEM |  | 1.13.2.4 | Unscheduled | No | No | 2020-02-20 09:00 | 2020-03-30 18:00 | 2020-08-08 09:00 | 2020-10-30 18:00 |  |  | 2020-08-06 16:17 |  |  |  | 100 | 0 | [15 empty] | 0.6883 | 0.00071 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4119 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019215
1736 | Task(Task)-->P (Procurement) | FDA SYSTEM |  | 1.13.2.4 | Unscheduled | No | No | 2020-04-09 09:00 | 2020-05-18 18:00 | 2020-08-21 09:00 | 2020-10-30 18:00 | [6 empty] | 100 | 0 | [15 empty] | 4.8181 | 0.004973 | 0.49 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4120 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019216
1737 | Task(Task)-->P (Procurement) | SCADA |  | 1.13.2.4 | Unscheduled | No | No | 2020-02-21 09:00 | 2020-03-31 18:00 | 2020-09-17 09:00 | 2020-10-25 23:59 | [6 empty] | 100 | 0 | [15 empty] | 2.2616 | 0.002334 | 0.23 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4121 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019217
1738 | Task(Task)-->P (Procurement) | RUBBER MATS |  | 1.13.2.4 | Unscheduled | No | No | 2020-06-26 09:00 | 2020-08-04 18:00 | 2020-08-10 09:00 | 2020-08-10 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.098328 | 0.000101 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4124 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019218
1739 | Task(Task)-->P (Procurement) | MAIN LIGHTING DISTRIBUTION BOARD |  | 1.13.2.4 | Unscheduled | No | No | 2020-04-19 | 2020-05-28 18:00 | 2020-07-28 09:00 | 2020-10-10 18:00 |  |  | 2020-07-28 17:50 |  |  |  | 100 | 0 | [15 empty] | 0.49164 | 0.000507 | 0.05 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4125 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019219
1740 | Task(Task)-->P (Procurement) | LIGHTING PANELS |  | 1.13.2.4 | Unscheduled | No | No | 2020-06-26 09:00 | 2020-08-04 18:00 | 2020-07-28 09:00 | 2020-10-10 18:00 |  |  | 2020-07-28 17:39 |  |  |  | 100 | 0 | [15 empty] | 5.6047 | 0.005784 | 0.57 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4126 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019220
1741 | Task(Task)-->P (Procurement) | DCDB & DC FUSE BOARD |  | 1.13.2.4 | Unscheduled | No | No | 2020-04-19 | 2020-05-28 18:00 | 2020-07-28 09:00 | 2020-10-10 18:00 |  |  | 2020-07-28 14:24 |  |  |  | 100 | 0 | [15 empty] | 2.0649 | 0.002131 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4127 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019221
1742 | Task(Task)-->P (Procurement) | UPS DB,ACDB,MCBDB & AFB |  | 1.13.2.4 | Unscheduled | No | No | 2020-04-19 | 2020-05-28 18:00 | 2020-07-28 09:00 | 2020-10-10 18:00 |  |  | 2020-07-28 17:48 |  |  |  | 100 | 0 | [15 empty] | 2.0649 | 0.002131 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4128 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019222
1743 | Task(Task)-->P (Procurement) | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE | 1.13.2.5 | 1.13.2 | Work In Progress | No | No | 2019-12-28 09:00 | 2020-08-09 23:59 | 2020-03-19 09:00 | 2020-10-31 18:00 |  |  | 2020-03-20 15:24 |  |  |  | 100 | 27.1264 | [15 empty] | 14.9995 | 0.30951 | 30.44 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4129 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019223
1744 | Task(Task)-->P (Procurement) | 33/6.9KV HT TRANSFORMER (ONAN TYPE) |  | 1.13.2.5 | Completed | No | No | 2020-01-16 09:00 | 2020-03-15 23:59 | 2020-06-30 09:00 | 2020-09-22 18:00 |  |  | 2020-06-30 17:44 | 2020-09-22 12:23 |  |  | 100 | 100 | [15 empty] | 10.0164 | 0.031002 | 3.05 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4130 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019224
1745 | Task(Task)-->P (Procurement) | HT SWITCHGEAR (33KV & 6.6KV) |  | 1.13.2.5 | Unscheduled | No | No | 2020-01-14 09:00 | 2020-03-28 18:00 | 2020-07-30 09:00 | 2020-10-20 18:00 |  |  | 2020-07-30 10:50 |  |  |  | 100 | 0 | [15 empty] | 31.3629 | 0.097072 | 9.55 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4131 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019225
1746 | Task(Task)-->P (Procurement) | 6.6KV HT VFD with Motors |  | 1.13.2.5 | Completed | No | No | 2020-02-29 09:00 | 2020-05-13 18:00 | 2020-08-08 09:00 | 2020-10-10 18:00 |  |  | 2020-07-28 11:51 | 2020-09-23 15:24 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4132 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019226
1747 | Task(Task)-->P (Procurement) | 415V LT VFD |  | 1.13.2.5 | Completed | No | No | 2020-02-18 09:00 | 2020-05-02 18:00 | 2020-06-16 09:00 | 2020-09-23 18:00 |  |  | 2020-06-16 10:34 | 2020-09-22 17:02 |  |  | 100 | 100 | [15 empty] | 4.5977 | 0.01423 | 1.4 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4133 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019227
1748 | Task(Task)-->P (Procurement) | 6.6KV HT APFC PANEL |  | 1.13.2.5 | Unscheduled | No | No | 2020-03-11 09:00 | 2020-04-24 18:00 | 2020-07-22 09:00 | 2020-10-20 18:00 |  |  | 2020-07-22 08:56 |  |  |  | 100 | 0 | [15 empty] | 1.1823 | 0.003659 | 0.36 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4134 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019228
1749 | Task(Task)-->P (Procurement) | 6.6KV/0.433V LT TRANSFORMER |  | 1.13.2.5 | Completed | No | No | 2020-01-16 09:00 | 2020-03-15 23:59 | 2020-07-20 09:00 | 2020-09-17 18:00 |  |  | 2020-07-20 09:00 | 2020-09-17 12:32 |  |  | 100 | 100 | [15 empty] | 10.0821 | 0.031205 | 3.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4135 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019229
1750 | Task(Task)-->P (Procurement) | LT BUSDUCT |  | 1.13.2.5 | Unscheduled | No | No | 2020-02-05 09:00 | 2020-03-20 18:00 | 2020-06-12 09:00 | 2020-07-26 23:59 |  |  | 2020-09-16 17:36 |  |  |  | 100 | 0 | [15 empty] | 1.5435 | 0.004777 | 0.47 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4136 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019230
1751 | Task(Task)-->P (Procurement) | 415V MCC |  | 1.13.2.5 | Unscheduled | No | No | 2020-02-26 09:00 | 2020-05-10 23:59 | 2020-08-17 09:00 | 2020-10-31 18:00 |  |  | 2020-08-17 14:17 |  |  |  | 100 | 0 | [15 empty] | 10.1806 | 0.03151 | 3.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4137 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019231
1752 | Task(Task)-->P (Procurement) | 110V DC BATTERY & BATTERY CHARGER SYSTEM |  | 1.13.2.5 | Unscheduled | No | No | 2020-02-25 09:00 | 2020-04-19 23:59 | 2020-07-07 09:00 | 2020-10-31 18:00 |  |  | 2020-07-07 10:31 |  |  |  | 100 | 0 | [15 empty] | 3.3169 | 0.010266 | 1.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4138 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019232
1753 | Task(Task)-->P (Procurement) | 6.6KV NEUTRAL GROUNDING RESISTOR |  | 1.13.2.5 | Completed | No | No | 2020-01-21 09:00 | 2020-03-05 18:00 | 2020-03-19 09:00 | 2020-06-04 18:00 |  |  | 2020-03-20 15:24 | 2020-06-04 15:24 |  |  | 100 | 100 | [15 empty] | 0.29557 | 0.000915 | 0.09 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4139 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019233
1754 | Task(Task)-->P (Procurement) | PLC SYSTEM |  | 1.13.2.5 | Unscheduled | No | No | 2019-12-28 09:00 | 2020-03-11 18:00 | 2020-07-29 09:00 | 2020-10-15 18:00 |  |  | 2020-07-29 17:09 |  |  |  | 100 | 0 | [15 empty] | 7.9803 | 0.0247 | 2.43 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4140 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019234
1755 | Task(Task)-->P (Procurement) | UPS SYSTEM |  | 1.13.2.5 | Unscheduled | No | No | 2020-02-19 09:00 | 2020-04-03 18:00 | 2020-08-01 09:00 | 2020-09-14 18:00 |  |  | 2020-08-31 12:21 |  |  |  | 100 | 0 | [15 empty] | 1.445 | 0.004472 | 0.44 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4141 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019235
1756 | Task(Task)-->P (Procurement) | 24V DC BATTERY AND BATTERY CHARGER SYSTEM |  | 1.13.2.5 | Unscheduled | No | No | 2020-02-20 09:00 | 2020-04-14 18:00 | 2020-08-06 09:00 | 2020-10-20 18:00 |  |  | 2020-08-06 16:16 |  |  |  | 100 | 0 | [15 empty] | 0.68966 | 0.002135 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4142 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019236
1757 | Task(Task)-->P (Procurement) | FDA SYSTEM |  | 1.13.2.5 | Unscheduled | No | No | 2020-04-09 09:00 | 2020-06-22 18:00 | 2020-08-13 09:00 | 2020-10-15 18:00 | [6 empty] | 100 | 0 | [15 empty] | 4.7947 | 0.01484 | 1.46 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4143 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019237
1758 | Task(Task)-->P (Procurement) | SCADA |  | 1.13.2.5 | Unscheduled | No | No | 2020-02-21 09:00 | 2020-05-05 18:00 | 2020-08-15 09:00 | 2020-10-31 18:00 |  |  | 2020-07-06 17:05 |  |  |  | 100 | 0 | [15 empty] | 2.2332 | 0.006912 | 0.68 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4144 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019238
1759 | Task(Task)-->P (Procurement) | RUBBER MATS |  | 1.13.2.5 | Completed | No | No | 2020-06-26 09:00 | 2020-07-16 18:00 | 2020-06-30 09:00 | 2020-07-23 18:00 |  |  | 2020-06-11 21:15 | 2020-07-03 21:15 |  |  | 100 | 100 | [15 empty] | 0.098522 | 0.000305 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4147 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019239
1760 | Task(Task)-->P (Procurement) | MAIN LIGHTING DISTRIBUTION BOARD |  | 1.13.2.5 | Unscheduled | No | No | 2020-04-19 | 2020-06-02 18:00 | 2020-07-28 09:00 | 2020-10-31 18:00 |  |  | 2020-07-28 17:30 |  |  |  | 100 | 0 | [15 empty] | 0.52545 | 0.001626 | 0.16 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4148 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019240
1761 | Task(Task)-->P (Procurement) | LIGHTING PANELS |  | 1.13.2.5 | Unscheduled | No | No | 2020-06-26 09:00 | 2020-08-09 23:59 | 2020-07-28 09:00 | 2020-10-31 18:00 |  |  | 2020-07-28 17:40 |  |  |  | 100 | 0 | [15 empty] | 5.5829 | 0.01728 | 1.7 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4149 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019241
1762 | Task(Task)-->P (Procurement) | DCDB & DC FUSE BOARD |  | 1.13.2.5 | Unscheduled | No | No | 2020-04-19 | 2020-06-02 18:00 | 2020-07-28 09:00 | 2020-10-31 18:00 |  |  | 2020-07-28 14:22 |  |  |  | 100 | 0 | [15 empty] | 2.0361 | 0.006302 | 0.62 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4150 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019242
1763 | Task(Task)-->P (Procurement) | UPS DB,ACDB,MCBDB & AFB |  | 1.13.2.5 | Completed | No | No | 2020-04-19 | 2020-06-02 18:00 | 2020-07-28 09:00 | 2020-10-31 18:00 |  |  | 2020-07-28 17:47 | 2020-09-28 17:47 |  |  | 100 | 100 | [15 empty] | 2.0361 | 0.006302 | 0.62 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4151 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019243
1764 | Task(Task)-->P (Procurement) | MANUFACTURING & RECEIPT AT SITE (MRN) | 1.13.2.6 | 1.13.2 | Unscheduled | No | No | 2020-03-06 09:00 | 2021-03-31 18:00 | 2020-07-16 09:00 | 2021-10-24 23:59 |  |  | 2020-09-18 12:33 |  |  |  | 63.1726 | 0 | [15 empty] | 59.998 | 1.2381 | 121.76 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4152 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019244
1765 | Task(Task)-->P (Procurement) | 33/6.9KV HT TRANSFORMER (ONAN TYPE) |  | 1.13.2.6 | Unscheduled | No | No | 2020-03-16 09:00 | 2021-03-22 18:00 | 2020-09-23 09:00 | 2021-09-29 18:00 |  |  | 2020-09-23 09:26 |  |  |  | 55.3763 | 0 | [15 empty] | 10.0074 | 0.1239 | 12.18 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4153 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019245
1766 | Task(Task)-->P (Procurement) | HT SWITCHGEAR (33KV & 6.6KV) |  | 1.13.2.6 | Unscheduled | No | No | 2020-03-29 | 2021-03-22 18:00 | 2020-10-21 09:00 | 2021-10-14 18:00 | [6 empty] | 53.7604 | 0 | [15 empty] | 31.3696 | 0.38837 | 38.18 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4154 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019246
1767 | Task(Task)-->P (Procurement) | 6.6KV HT VFD with Motors |  | 1.13.2.6 | Unscheduled | No | No | 2020-05-14 09:00 | 2021-03-09 18:00 | 2020-10-11 | 2021-08-06 18:00 | [6 empty] | 49 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4155 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019247
1768 | Task(Task)-->P (Procurement) | 415V LT VFD |  | 1.13.2.6 | Unscheduled | No | No | 2020-05-03 | 2020-10-28 18:00 | 2020-10-16 09:00 | 2021-04-12 18:00 |  |  | 2020-09-23 09:02 |  |  |  | 88.2682 | 0 | [15 empty] | 4.6093 | 0.057066 | 5.61 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4156 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019248
1769 | Task(Task)-->P (Procurement) | 6.6KV HT APFC PANEL |  | 1.13.2.6 | Unscheduled | No | No | 2020-04-25 09:00 | 2020-11-04 18:00 | 2020-10-21 09:00 | 2021-05-02 23:59 | [6 empty] | 85.567 | 0 | [15 empty] | 1.1914 | 0.01475 | 1.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4157 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019249
1770 | Task(Task)-->P (Procurement) | 6.6KV/0.433V LT TRANSFORMER |  | 1.13.2.6 | Unscheduled | No | No | 2020-03-16 09:00 | 2021-03-29 18:00 | 2020-10-11 | 2021-10-24 23:59 |  |  | 2020-09-18 12:33 |  |  |  | 54.3536 | 0 | [15 empty] | 10.0978 | 0.12501 | 12.29 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4158 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019250
1771 | Task(Task)-->P (Procurement) | LT BUSDUCT |  | 1.13.2.6 | Unscheduled | No | No | 2020-03-21 09:00 | 2020-08-13 18:00 | 2020-10-21 09:00 | 2021-03-15 18:00 | [6 empty] | 100 | 0 | [15 empty] | 1.5364 | 0.019022 | 1.87 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4159 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019251
1772 | Task(Task)-->P (Procurement) | 415V MCC |  | 1.13.2.6 | Unscheduled | No | No | 2020-05-11 09:00 | 2021-03-31 18:00 | 2020-11-01 | 2021-09-21 18:00 | [6 empty] | 46.1538 | 0 | [15 empty] | 10.1964 | 0.12624 | 12.41 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4160 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019252
1773 | Task(Task)-->P (Procurement) | 110V DC BATTERY & BATTERY CHARGER SYSTEM |  | 1.13.2.6 | Unscheduled | No | No | 2020-04-20 09:00 | 2020-11-03 18:00 | 2020-11-01 | 2021-05-17 18:00 | [6 empty] | 86.3636 | 0 | [15 empty] | 3.3111 | 0.040994 | 4.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4161 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019253
1774 | Task(Task)-->P (Procurement) | 6.6KV NEUTRAL GROUNDING RESISTOR |  | 1.13.2.6 | Unscheduled | No | No | 2020-03-06 09:00 | 2020-09-02 18:00 | 2020-07-16 09:00 | 2021-01-12 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.304 | 0.003764 | 0.37 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4162 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019254
1775 | Task(Task)-->P (Procurement) | PLC SYSTEM |  | 1.13.2.6 | Unscheduled | No | No | 2020-03-12 09:00 | 2021-01-20 18:00 | 2020-10-31 09:00 | 2021-09-10 18:00 | [6 empty] | 66.6667 | 0 | [15 empty] | 7.9944 | 0.098975 | 9.73 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4163 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019255
1776 | Task(Task)-->P (Procurement) | UPS SYSTEM |  | 1.13.2.6 | Unscheduled | No | No | 2020-04-04 09:00 | 2020-11-03 18:00 | 2020-10-31 09:00 | 2021-06-01 18:00 | [6 empty] | 87.3832 | 0 | [15 empty] | 1.4378 | 0.017801 | 1.75 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4164 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019256
1777 | Task(Task)-->P (Procurement) | 24V DC BATTERY AND BATTERY CHARGER SYSTEM |  | 1.13.2.6 | Unscheduled | No | No | 2020-04-15 09:00 | 2020-10-18 23:59 | 2020-10-31 09:00 | 2021-05-05 18:00 | [6 empty] | 94.1176 | 0 | [15 empty] | 0.69838 | 0.008646 | 0.85 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4165 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019257
1778 | Task(Task)-->P (Procurement) | FDA SYSTEM |  | 1.13.2.6 | Unscheduled | No | No | 2020-06-23 09:00 | 2020-12-25 18:00 | 2020-10-31 09:00 | 2021-05-04 18:00 | [6 empty] | 57.5269 | 0 | [15 empty] | 4.7819 | 0.059202 | 5.82 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4166 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019258
1779 | Task(Task)-->P (Procurement) | SCADA |  | 1.13.2.6 | Unscheduled | No | No | 2020-05-06 09:00 | 2021-02-17 18:00 | 2020-11-01 | 2021-08-15 23:59 | [6 empty] | 53.8194 | 0 | [15 empty] | 2.2184 | 0.027465 | 2.7 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4167 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019259
1780 | Task(Task)-->P (Procurement) | RUBBER MATS |  | 1.13.2.6 | Unscheduled | No | No | 2020-08-05 09:00 | 2021-01-16 18:00 | 2020-08-07 09:00 | 2021-02-12 18:00 | [6 empty] | 38.7879 | 0 | [15 empty] | 0.098595 | 0.001221 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4170 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019260
1781 | Task(Task)-->P (Procurement) | MAIN LIGHTING DISTRIBUTION BOARD |  | 1.13.2.6 | Unscheduled | No | No | 2020-06-03 09:00 | 2020-09-16 18:00 | 2020-11-01 | 2021-02-14 23:59 | [6 empty] | 100 | 0 | [15 empty] | 0.50941 | 0.006307 | 0.62 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4171 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019261
1782 | Task(Task)-->P (Procurement) | LIGHTING PANELS |  | 1.13.2.6 | Unscheduled | No | No | 2020-08-10 09:00 | 2020-09-10 18:00 | 2020-11-01 | 2020-12-02 18:00 | [6 empty] | 100 | 0 | [15 empty] | 5.5788 | 0.069069 | 6.79 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4172 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019262
1783 | Task(Task)-->P (Procurement) | DCDB & DC FUSE BOARD |  | 1.13.2.6 | Unscheduled | No | No | 2020-06-03 09:00 | 2020-08-10 18:00 | 2020-11-01 | 2021-01-08 18:00 | [6 empty] | 100 | 0 | [15 empty] | 2.0294 | 0.025125 | 2.47 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4173 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019263
1784 | Task(Task)-->P (Procurement) | UPS DB,ACDB,MCBDB & AFB |  | 1.13.2.6 | Unscheduled | No | No | 2020-06-03 09:00 | 2020-11-28 18:00 | 2020-11-01 | 2021-04-28 18:00 |  |  | 2020-09-29 09:00 |  |  |  | 70.9497 | 0 | [15 empty] | 2.0294 | 0.025125 | 2.47 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4174 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019264
1785 | Task(Task)-->C (Construction) | CONSTRUCTION | 1.13.3 | 1.13 | Unscheduled | No | No | 2020-04-18 09:00 | 2021-08-21 18:00 | 2020-06-05 09:00 | 2022-03-13 23:59 |  |  | 2020-06-05 10:27 |  |  |  | 36.8327 | 0.66179 | [15 empty] | 38.8781 | 1.3673 | 134.46 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4175 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019265
1786 | Task(Task)-->C (Construction) | CIVIL | 1.13.3.1 | 1.13.3 | Unscheduled | No | No | 2020-04-18 09:00 | 2021-07-30 18:00 | 2020-06-05 09:00 | 2021-10-08 18:00 |  |  | 2020-06-05 10:27 |  |  |  | 43.9872 | 0.79034 | [15 empty] | 83.7349 | 1.1449 | 112.59 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4176 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019266
1787 | Task(Task)-->C (Construction) | AVAILABILITY OF FRONT BY NTPC |  | 1.13.3.1 | Unscheduled | No | No | 2020-04-18 09:00 | 2020-04-18 18:00 | 2020-06-05 09:00 | 2020-10-15 18:00 |  |  | 2020-06-05 10:27 |  |  |  | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4177 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019267
1788 | Task(Task)-->C (Construction) | EXCAVATION |  | 1.13.3.1 | Unscheduled | No | No | 2020-04-25 09:00 | 2020-05-19 18:00 | 2020-06-05 09:00 | 2020-11-15 23:59 |  |  | 2020-06-05 10:28 |  |  |  | 100 | 41.2715 | [15 empty] | 1.7586 | 0.020134 | 1.98 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 7424 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4178 | 0 | 4 | Low | Niharendu Kamle,Santosh Anand | [6 empty] | 0 | 0 | [222 empty] | Excavation | [21 empty] | 1019268
1789 | Task(Task)-->C (Construction) | PCC |  | 1.13.3.1 | Unscheduled | No | No | 2020-05-16 09:00 | 2020-06-09 18:00 | 2020-06-27 09:00 | 2020-11-22 23:59 |  |  | 2020-06-27 10:29 |  |  |  | 100 | 9.1954 | [15 empty] | 0.70166 | 0.008033 | 0.79 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 87 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4179 | 0 | 4 | Low | Niharendu Kamle,Santosh Anand | [6 empty] | 0 | 0 | [222 empty] | PCC | [21 empty] | 1019269
1790 | Task(Task)-->C (Construction) | RAFT |  | 1.13.3.1 | Unscheduled | No | No | 2020-05-23 09:00 | 2020-07-01 18:00 | 2020-08-01 09:00 | 2020-09-09 18:00 | [6 empty] | 100 | 0 | [15 empty] | 13.4293 | 0.15375 | 15.12 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 570 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4180 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019270
1791 | Task(Task)-->C (Construction) | PLINTH BEAM |  | 1.13.3.1 | Unscheduled | No | No | 2020-06-17 09:00 | 2020-08-15 18:00 | 2020-08-26 09:00 | 2020-10-24 18:00 | [6 empty] | 100 | 0 | [15 empty] | 2.3537 | 0.026946 | 2.65 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4181 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019271
1792 | Task(Task)-->C (Construction) | PULL PIT & GRADE SLAB OF GROUND FLOOR |  | 1.13.3.1 | Unscheduled | No | No | 2020-07-17 09:00 | 2020-08-30 23:59 | 2020-09-25 09:00 | 2020-11-08 23:59 | [6 empty] | 100 | 0 | [15 empty] | 16.3158 | 0.18679 | 18.37 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 981 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5498 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019272
1793 | Task(Task)-->C (Construction) | RCC COLUMN & SLAB FOR 1ST FLOOR |  | 1.13.3.1 | Unscheduled | No | No | 2020-08-16 | 2020-09-29 18:00 | 2020-10-25 | 2020-12-08 18:00 | [6 empty] | 100 | 0 | [15 empty] | 8.2512 | 0.094465 | 9.29 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5486 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019273
1794 | Task(Task)-->C (Construction) | RCC COLUMN & SLAB FOR 2ND (ROOF) FLOOR |  | 1.13.3.1 | Unscheduled | No | No | 2020-10-07 09:00 | 2020-12-05 18:00 | 2020-12-16 09:00 | 2021-02-13 18:00 | [6 empty] | 1.6667 | 0 | [15 empty] | 8.2512 | 0.094465 | 9.29 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5487 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019274
1795 | Task(Task)-->C (Construction) | RCC COLUMN & SLAB OF MUMTY & FOUNDATION OF FAN/ AC ETC |  | 1.13.3.1 | Unscheduled | No | No | 2020-12-06 | 2021-01-04 18:00 | 2021-02-14 | 2021-03-15 18:00 | [6 empty] | 0 | 0 | [15 empty] | 1.1813 | 0.013524 | 1.33 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5504 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019275
1796 | Task(Task)-->C (Construction) | BRICK WORK OF GROUND FLOOR |  | 1.13.3.1 | Unscheduled | No | No | 2020-10-28 09:00 | 2020-12-16 18:00 | 2021-01-06 09:00 | 2021-02-24 18:00 | [6 empty] | 0 | 0 | [15 empty] | 4.2011 | 0.048097 | 4.73 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4185 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019276
1797 | Task(Task)-->C (Construction) | PLASTERING OF GROUND FLOOR (IN SIDE) & HANDING OVER FOR ELECTRICAL WORKS |  | 1.13.3.1 | Unscheduled | No | No | 2020-11-07 09:00 | 2020-12-26 18:00 | 2021-01-16 09:00 | 2021-03-06 18:00 | [6 empty] | 0 | 0 | [15 empty] | 1.652 | 0.018913 | 1.86 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 3358 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4186 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019277
1798 | Task(Task)-->C (Construction) | BRICK WORK OF 1ST FLOOR |  | 1.13.3.1 | Unscheduled | No | No | 2021-01-03 | 2021-03-03 18:00 | 2021-03-14 | 2021-05-12 18:00 | [6 empty] | 0 | 0 | [15 empty] | 4.2011 | 0.048097 | 4.73 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5490 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019278
1799 | Task(Task)-->C (Construction) | PLASTERING OF 1ST FLOOR (IN SIDE) |  | 1.13.3.1 | Unscheduled | No | No | 2021-01-27 09:00 | 2021-03-17 18:00 | 2021-04-07 09:00 | 2021-05-26 18:00 | [6 empty] | 0 | 0 | [15 empty] | 1.652 | 0.018913 | 1.86 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 3358 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5489 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019279
1800 | Task(Task)-->C (Construction) | PAINTING OF CEILING OF ROOF SLAB (GRID 2 to 3) & HANDING OVER FOR ELECTRICAL WORKS |  | 1.13.3.1 | Unscheduled | No | No | 2021-03-08 09:00 | 2021-03-27 18:00 | 2021-05-17 09:00 | 2021-06-05 18:00 | [6 empty] | 0 | 0 | [15 empty] | 1.501 | 0.017185 | 1.69 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 3358 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5492 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019280
1801 | Task(Task)-->C (Construction) | INSIDE PAINTING & FALSE CEILING (GRID 1 TO 2) & HANDING OVER FOR ELECTRICAL WORKS |  | 1.13.3.1 | Unscheduled | No | No | 2021-03-18 09:00 | 2021-04-16 18:00 | 2021-05-27 09:00 | 2021-06-25 18:00 | [6 empty] | 0 | 0 | [15 empty] | 14.0687 | 0.16107 | 15.84 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 3358 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5495 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019281
1802 | Task(Task)-->C (Construction) | TRANSFORMER FOUNDATION, TRENCH, BRICK WORK & PLASTERING ETC & HANDING OVER TO ELECTRICAL |  | 1.13.3.1 | Unscheduled | No | No | 2020-08-16 | 2020-12-13 23:59 | 2020-10-25 | 2021-02-21 23:59 | [6 empty] | 44.1667 | 0 | [15 empty] | 2.3537 | 0.026946 | 2.65 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5497 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019282
1803 | Task(Task)-->C (Construction) | BALANCE BRICK WORK |  | 1.13.3.1 | Unscheduled | No | No | 2021-03-18 09:00 | 2021-04-16 18:00 | 2021-05-27 09:00 | 2021-06-25 18:00 | [6 empty] | 0 | 0 | [15 empty] | 1.1902 | 0.013626 | 1.34 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5501 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019283
1804 | Task(Task)-->C (Construction) | OUTSIDE PLASTERING |  | 1.13.3.1 | Unscheduled | No | No | 2021-04-17 09:00 | 2021-06-15 18:00 | 2021-06-26 09:00 | 2021-08-24 18:00 | [6 empty] | 0 | 0 | [15 empty] | 3.304 | 0.037827 | 3.72 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 6715 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5493 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019284
1805 | Task(Task)-->C (Construction) | DOOR , WINDOW, MONORAIL DOOR & ROLLING SHUTTER |  | 1.13.3.1 | Unscheduled | No | No | 2021-05-17 09:00 | 2021-06-23 18:00 | 2021-07-26 09:00 | 2021-09-01 18:00 | [6 empty] | 0 | 0 | [15 empty] | 3.0465 | 0.034878 | 3.43 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4187 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019285
1806 | Task(Task)-->C (Construction) | BALANCE PAINTING |  | 1.13.3.1 | Unscheduled | No | No | 2021-06-16 09:00 | 2021-07-30 18:00 | 2021-08-25 09:00 | 2021-10-08 18:00 | [6 empty] | 0 | 0 | [15 empty] | 3.0109 | 0.034471 | 3.39 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 6715 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5496 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019286
1807 | Task(Task)-->C (Construction) | ROOF WATER PROFING & RWDC PIPE |  | 1.13.3.1 | Unscheduled | No | No | 2021-02-02 09:00 | 2021-03-04 18:00 | 2021-04-13 09:00 | 2021-05-13 18:00 | [6 empty] | 0 | 0 | [15 empty] | 5.5245 | 0.063248 | 6.22 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 1296 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4189 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019287
1808 | Task(Task)-->C (Construction) | GARLAND DRAIN & PLINTH PROTECTION |  | 1.13.3.1 | Unscheduled | No | No | 2021-06-16 09:00 | 2021-07-30 18:00 | 2021-08-25 09:00 | 2021-10-08 18:00 | [6 empty] | 0 | 0 | [15 empty] | 2.0517 | 0.023489 | 2.31 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4190 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019288
1809 | Task(Task)-->C (Construction) | ELECTRICAL & INSTRUMENTATION | 1.13.3.2 | 1.13.3 | Unscheduled | No | No | 2020-12-27 | 2021-08-06 18:00 | 2021-03-07 | 2022-01-01 18:00 | [6 empty] | 0 | 0 | [15 empty] | 11.3565 | 0.15527 | 15.27 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5252 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019289
1810 | Task(Task)-->C (Construction) | TRANSFORMERS |  | 1.13.3.2 | Unscheduled | No | No | 2021-03-23 09:00 | 2021-04-12 18:00 | 2021-09-30 09:00 | 2021-10-20 18:00 | [6 empty] | 0 | 0 | [15 empty] | 15.1376 | 0.023504 | 2.31 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4194 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019290
1811 | Task(Task)-->C (Construction) | HT PANEL |  | 1.13.3.2 | Unscheduled | No | No | 2021-03-28 | 2021-04-16 18:00 | 2021-10-15 09:00 | 2021-11-03 18:00 | [6 empty] | 0 | 0 | [15 empty] | 8.0603 | 0.012515 | 1.23 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5253 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019291
1812 | Task(Task)-->C (Construction) | HT VFD |  | 1.13.3.2 | Unscheduled | No | No | 2021-04-17 09:00 | 2021-04-17 18:00 | 2021-11-04 09:00 | 2021-11-04 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4195 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019292
1813 | Task(Task)-->C (Construction) | HT APFC |  | 1.13.3.2 | Unscheduled | No | No | 2021-04-18 | 2021-04-18 23:59 | 2021-11-05 09:00 | 2021-11-05 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5335 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019293
1814 | Task(Task)-->C (Construction) | LT PANEL |  | 1.13.3.2 | Unscheduled | No | No | 2021-03-30 09:00 | 2021-04-23 18:00 | 2021-10-25 09:00 | 2021-11-18 18:00 | [6 empty] | 0 | 0 | [15 empty] | 2.2936 | 0.003561 | 0.35 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5336 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019294
1815 | Task(Task)-->C (Construction) | LT VFD |  | 1.13.3.2 | Unscheduled | No | No | 2021-04-18 | 2021-04-21 18:00 | 2021-11-05 09:00 | 2021-11-08 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5337 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019295
1816 | Task(Task)-->C (Construction) | BATTERY, BATTERY CHARGER & UPS |  | 1.13.3.2 | Unscheduled | No | No | 2021-07-31 09:00 | 2021-08-06 18:00 | 2021-10-09 09:00 | 2021-10-15 18:00 | [6 empty] | 0 | 0 | [15 empty] | 1.0485 | 0.001628 | 0.16 | Plan & Actual | Quantity | Set | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5509 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019296
1817 | Task(Task)-->C (Construction) | PLC PANEL & SCADA |  | 1.13.3.2 | Unscheduled | No | No | 2021-04-17 09:00 | 2021-04-23 18:00 | 2021-09-11 09:00 | 2021-09-17 18:00 | [6 empty] | 0 | 0 | [15 empty] | 28.7025 | 0.044567 | 4.38 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5507 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019297
1818 | Task(Task)-->C (Construction) | CABLE TRAY |  | 1.13.3.2 | Unscheduled | No | No | 2020-12-27 | 2021-01-05 18:00 | 2021-03-07 | 2021-03-16 18:00 | [6 empty] | 0 | 0 | [15 empty] | 5.5701 | 0.008649 | 0.85 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5338 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019298
1819 | Task(Task)-->C (Construction) | POWER CABLE |  | 1.13.3.2 | Unscheduled | No | No | 2021-04-24 09:00 | 2021-05-13 18:00 | 2021-11-19 09:00 | 2021-12-08 18:00 | [6 empty] | 0 | 0 | [15 empty] | 12.7785 | 0.019841 | 1.95 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 13795 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5339 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019299
1820 | Task(Task)-->C (Construction) | CONTROL CABLE |  | 1.13.3.2 | Unscheduled | No | No | 2021-04-24 09:00 | 2021-04-29 18:00 | 2021-11-19 09:00 | 2021-11-24 18:00 | [6 empty] | 0 | 0 | [15 empty] | 11.1402 | 0.017298 | 1.7 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5340 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019300
1821 | Task(Task)-->C (Construction) | EARTHING |  | 1.13.3.2 | Unscheduled | No | No | 2021-04-30 09:00 | 2021-05-13 18:00 | 2021-11-25 09:00 | 2021-12-08 18:00 | [6 empty] | 0 | 0 | [15 empty] | 2.0315 | 0.003154 | 0.31 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 1410 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5341 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019301
1822 | Task(Task)-->C (Construction) | EARTH PIT |  | 1.13.3.2 | Unscheduled | No | No | 2021-07-24 09:00 | 2021-07-30 18:00 | 2021-10-02 09:00 | 2021-10-08 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5342 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019302
1823 | Task(Task)-->C (Construction) | LIGHTING |  | 1.13.3.2 | Unscheduled | No | No | 2021-03-18 09:00 | 2021-05-01 18:00 | 2021-05-27 09:00 | 2021-07-10 18:00 | [6 empty] | 0 | 0 | [15 empty] | 13.2372 | 0.020554 | 2.02 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 207 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5343 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019303
1824 | Task(Task)-->C (Construction) | NON-MOTOR TERMINATION |  | 1.13.3.2 | Unscheduled | No | No | 2021-05-14 09:00 | 2021-06-06 23:59 | 2021-12-09 09:00 | 2022-01-01 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 237 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5346 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019304
1825 | Task(Task)-->C (Construction) | TESTING & CHARGING FOR LOAD & TRIAL OPERATION | 1.13.3.3 | 1.13.3 | Unscheduled | No | No | 2021-05-19 09:00 | 2021-08-21 18:00 | 2021-12-09 09:00 | 2022-03-13 23:59 | [6 empty] | 0 | 0 | [15 empty] | 4.9085 | 0.067112 | 6.6 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5347 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019305
1826 | Task(Task)-->C (Construction) | TRANSFORMERS (33KV/6.6KV) |  | 1.13.3.3 | Unscheduled | No | No | 2021-06-08 09:00 | 2021-06-17 18:00 | 2021-12-29 09:00 | 2022-01-07 18:00 | [6 empty] | 0 | 0 | [15 empty] | 7.5758 | 0.005084 | 0.5 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5512 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019306
1827 | Task(Task)-->C (Construction) | TRANSFORMERS (6.6KV/415V) |  | 1.13.3.3 | Unscheduled | No | No | 2021-07-08 09:00 | 2021-07-27 18:00 | 2022-01-28 09:00 | 2022-02-16 18:00 | [6 empty] | 0 | 0 | [15 empty] | 15 | 0.010067 | 0.99 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5590 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019307
1828 | Task(Task)-->C (Construction) | 33KV SWITCH BOARD |  | 1.13.3.3 | Unscheduled | No | No | 2021-05-19 09:00 | 2021-06-07 18:00 | 2021-12-09 09:00 | 2021-12-28 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5348 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019308
1829 | Task(Task)-->C (Construction) | 6.6. KV SWITCH BOARD |  | 1.13.3.3 | Unscheduled | No | No | 2021-06-18 09:00 | 2021-07-07 18:00 | 2022-01-08 09:00 | 2022-01-27 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5349 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019309
1830 | Task(Task)-->C (Construction) | PMCC-1A (LT SWITCH BOARD) |  | 1.13.3.3 | Unscheduled | No | No | 2021-07-28 09:00 | 2021-08-16 18:00 | 2022-02-17 09:00 | 2022-03-08 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5350 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019310
1831 | Task(Task)-->C (Construction) | PMCC-1B (LT SWITCH BOARD) |  | 1.13.3.3 | Unscheduled | No | No | 2021-08-02 09:00 | 2021-08-21 18:00 | 2022-02-22 09:00 | 2022-03-13 23:59 | [6 empty] | 0 | 0 | [15 empty] | 23.3333 | 0.015659 | 1.54 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5351 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019311
1832 | Task(Task)-->C (Construction) | BATTERY, BATTERY CHARGER & UPS |  | 1.13.3.3 | Unscheduled | No | No | 2021-08-07 09:00 | 2021-08-13 18:00 | 2021-12-09 09:00 | 2021-12-15 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Set | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5510 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019312
1833 | Task(Task)-->C (Construction) | PLC SYSTEM |  | 1.13.3.3 | Unscheduled | No | No | 2021-08-14 09:00 | 2021-08-20 18:00 | 2021-12-16 09:00 | 2021-12-22 18:00 | [6 empty] | 0 | 0 | [15 empty] | 54.0909 | 0.036301 | 3.57 | Plan & Actual | Quantity | Set | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5511 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019313
1834 | Task(Task)-->E (Engineering) | SUB STATION-2 NEAR KDTP-2 | 1.14 | 1 | Work In Progress | No | No | 2019-11-12 09:00 | 2021-08-26 18:00 | 2019-11-02 09:00 | 2022-03-18 18:00 |  |  | 2019-11-02 10:57 |  |  |  | 62.9867 | 11.8205 | [15 empty] | 2.7123 | 2.7123 | 266.74 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4196 | 0 | 1 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019314
1835 | Task(Task)-->E (Engineering) | ENGINEERING | 1.14.1 | 1.14 | Work In Progress | No | No | 2020-01-06 18:00 | 2020-07-21 17:40 | 2020-03-04 18:00 | 2020-11-04 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 84.976 | [15 empty] | 1.7733 | 0.048097 | 4.73 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4197 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019315
1836 | Task(Task)-->E (Engineering) | CIVIL | 1.14.1.1 | 1.14.1 | Work In Progress | No | No | 2020-03-23 18:00 | 2020-07-21 17:40 | 2020-04-30 18:00 | 2020-11-04 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 94.4031 | [15 empty] | 66.88 | 0.032167 | 4.18 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No | 4198 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036115
1837 | Task(Task)-->E (Engineering) | SUBSTATION-2 (SS-KDTP-2) : DESIGN CALCULATION |  | 1.14.1.1 | Completed | No | No | 2020-03-23 18:00 | 2020-05-22 17:40 | 2020-06-29 09:00 | 2020-07-15 18:00 |  |  | 2020-02-21 15:38 | 2020-07-15 14:58 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0026 |  | 2020-02-13 11:43 | 7012-155-PVC-U-090 |  |  |  | A |  |  |  | 47.7327 | 0.015354 | 2 | Plan & Actual | Date |  | 0 | 0 | 0 | 742.18 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4203 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-23 18:00 | 2020-04-30 18:00 |  | 10 |  |  |  | 2020-04-10 17:40 | 2020-05-25 18:00 |  | 30 |  |  |  | 2020-04-17 17:40 | 2020-05-28 18:00 |  | 35 |  |  |  | 2020-04-23 23:59 | 2020-06-04 18:00 |  | 65 | 2020-07-15 14:51 |  |  | 2020-04-30 17:40 | 2020-06-25 18:00 |  | 80 | 2020-07-15 14:55 | [5 empty] | 80 | 2020-07-15 14:57 | [5 empty] | 80 | 2020-07-15 14:57 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-22 17:40 | 2020-07-09 18:00 |  | 100 | 2020-07-15 14:59 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 191 |  |  |  | 101201
1838 | Task(Task)-->E (Engineering) | SUBSTATION-2 (SS-KDTP-2) : NUM & RC DETAILS (SHT 1) |  | 1.14.1.1 | Completed | No | No | 2020-03-23 18:00 | 2020-05-22 17:40 | 2020-06-29 09:00 | 2020-07-13 18:00 |  |  | 2020-02-21 15:38 | 2020-07-13 23:05 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-NR-0037 |  | 2020-02-13 11:43 | 7012-155-PVC-C-091 |  |  |  | A |  |  |  | 15.9905 | 0.005144 | 0.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 247.26 | 0 | 4.15 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4199 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-23 18:00 | 2020-04-30 18:00 |  | 10 |  |  |  | 2020-04-10 17:40 | 2020-05-25 18:00 |  | 30 |  |  |  | 2020-04-17 17:40 | 2020-05-28 18:00 |  | 35 | 2020-06-25 20:06 |  |  | 2020-04-23 23:59 | 2020-06-04 18:00 |  | 65 | 2020-07-13 22:48 |  |  | 2020-04-30 17:40 | 2020-06-25 18:00 |  | 80 | 2020-07-13 22:59 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-22 17:40 | 2020-07-09 18:00 |  | 100 | 2020-07-13 23:06 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 192 |  |  |  | 101202
1839 | Task(Task)-->E (Engineering) | SUBSTATION-2 (SS-KDTP-2) : NUM & RC DETAILS (SHT 2) |  | 1.14.1.1 | Completed | No | No | 2020-03-23 18:00 | 2020-05-22 17:40 | 2020-06-29 09:00 | 2020-07-13 18:00 |  |  | 2020-02-21 15:38 | 2020-07-13 23:06 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-NR-0038 |  | 2020-02-13 11:43 | 7012-155-PVC-C-092 |  |  |  | A |  |  |  | 15.9905 | 0.005144 | 0.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 247.26 | 0 | 2.35 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4200 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-23 18:00 | 2020-04-30 18:00 |  | 10 |  |  |  | 2020-04-10 17:40 | 2020-05-25 18:00 |  | 30 |  |  |  | 2020-04-17 17:40 | 2020-05-28 18:00 |  | 35 | 2020-06-26 11:25 |  |  | 2020-04-23 23:59 | 2020-06-04 18:00 |  | 65 | 2020-07-13 22:49 |  |  | 2020-04-30 17:40 | 2020-06-25 18:00 |  | 80 | 2020-07-13 23:00 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-22 17:40 | 2020-07-09 18:00 |  | 100 | 2020-07-13 23:07 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 193 |  |  |  | 101203
1840 | Task(Task)-->E (Engineering) | SUBSTATION-2 (SS-KDTP-2) : NUM & RC DETAILS (SHT 3) |  | 1.14.1.1 | Unscheduled | No | No | 2020-03-23 18:00 | 2020-05-22 17:40 | 2020-04-30 18:00 | 2020-11-04 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-NR-0039 |  | 2020-02-13 11:43 | 7012-155-PVC-C-093 |  |  |  | A |  |  |  | 15.9905 | 0.005144 | 0.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 247.26 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4201 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-23 18:00 | 2020-04-30 18:00 |  | 10 |  |  |  | 2020-04-10 17:40 | 2020-05-25 18:00 |  | 30 |  |  |  | 2020-04-17 17:40 | 2020-05-28 18:00 |  | 35 | 2020-09-30 12:05 |  |  | 2020-04-23 23:59 | 2020-06-04 18:00 |  | 65 | 2020-09-30 21:54 |  |  | 2020-04-30 17:40 | 2020-06-25 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-22 17:40 | 2020-07-09 18:00 |  | 100 | [122 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 194 |  |  |  | 101204
1841 | Task(Task)-->E (Engineering) | ARCHITECTURAL GA OF SUBSTATION-2 (SS-KDTP-2) |  | 1.14.1.1 | Completed | No | No | 2020-05-22 18:00 | 2020-07-21 17:40 | 2020-07-31 09:00 | 2020-08-31 18:00 |  |  | 2020-02-21 15:39 | 2020-09-01 00:08 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-AR-0012 |  | 2020-02-13 11:43 | 7012-155-PVC-C-118 |  |  |  | A |  |  |  | 4.2959 | 0.001382 | 0.18 | Plan & Actual | Date |  | 0 | 0 | 0 | 68.01 | 0 | 4.1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4202 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-05-22 18:00 | 2020-06-14 23:59 |  | 10 |  |  |  | 2020-06-09 17:40 | 2020-07-09 18:00 |  | 30 |  |  |  | 2020-06-16 17:40 | 2020-07-12 23:59 |  | 35 | 2020-07-31 22:57 |  |  | 2020-06-22 23:59 | 2020-07-19 23:59 |  | 65 | 2020-08-13 19:58 |  |  | 2020-06-29 17:40 | 2020-08-09 23:59 |  | 80 | 2020-09-01 00:04 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-07-21 17:40 | 2020-08-23 23:59 |  | 100 | 2020-09-01 00:09 | [121 empty] | Chetan Khodke |  |  |  |  | A - Architecture | [16 empty] | 219 |  |  |  | 101229
1842 | Task(Task)-->E (Engineering) | ELECTRICAL | 1.14.1.2 | 1.14.1 | Unscheduled | No | No | 2020-01-06 18:00 | 2020-04-23 17:40 | 2020-03-04 18:00 | 2020-10-15 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 65.94 | [15 empty] | 33.12 | 0.01593 | 2.07 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No | 4204 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036116
1843 | Task(Task)-->E (Engineering) | GA & CROSS SECTIONAL, FLOOR PLAN FOR 33 kV HT CICO PANEL FOR CHP |  | 1.14.1.2 | Unscheduled | No | No | 2020-02-29 18:00 | 2020-04-13 17:40 | 2020-05-21 18:00 | 2020-10-15 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-122 |  | 2020-02-13 11:45 | 7012-155-PVE-B-067 |  |  |  | A |  |  |  | 2.8986 | 0.000462 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4237 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-29 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-02 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-03-07 17:40 | 2020-06-03 18:00 |  | 35 |  |  |  | 2020-03-13 23:59 | 2020-06-03 18:00 |  | 65 | 2020-09-23 14:44 |  |  | 2020-03-20 17:40 | 2020-06-24 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-13 17:40 | 2020-06-24 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 302 |  |  |  | 101313
1844 | Task(Task)-->E (Engineering) | SINGLE LINE DIAGRAM FOR 33 kV HT CICO PANEL FOR CHP |  | 1.14.1.2 | Unscheduled | No | No | 2020-02-26 18:00 | 2020-04-13 17:40 | 2020-05-21 18:00 | 2020-09-22 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-125 |  | 2020-02-13 11:45 | 7012-155-PVE-P-070 |  |  |  | A |  |  |  | 2.8986 | 0.000462 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4239 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-26 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-02 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-03-07 17:40 | 2020-06-06 18:00 |  | 35 |  |  |  | 2020-03-13 23:59 | 2020-06-06 18:00 |  | 65 | 2020-09-23 14:48 |  |  | 2020-03-20 17:40 | 2020-06-27 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-13 17:40 | 2020-06-27 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 305 |  |  |  | 101316
1845 | Task(Task)-->E (Engineering) | SCHEME DIAGRAM FOR CICO FEEDER WITH LINE PT AND WITH DIFFERENTIAL (OIL TYPE) (TYPE-DBF1) |  | 1.14.1.2 | Unscheduled | No | No | 2020-02-27 18:00 | 2020-04-13 17:40 | 2020-05-21 18:00 | 2020-09-18 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-136 |  | 2020-02-13 11:45 | 7012-155-PVE-L-081 |  |  |  | A |  |  |  | 2.8986 | 0.000462 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4238 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-27 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-02 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-03-07 17:40 | 2020-06-05 18:00 |  | 35 |  |  |  | 2020-03-13 23:59 | 2020-06-05 18:00 |  | 65 | 2020-09-23 17:45 |  |  | 2020-03-20 17:40 | 2020-06-26 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-13 17:40 | 2020-06-26 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 316 |  |  |  | 101327
1846 | Task(Task)-->E (Engineering) | SUBSTATION-2 (SS-2) NEAR KDTP-2 EQUIPMENT, CABLE ROUTING,EARTHING & LIGHTNING LAYOUT WITH PLAN & SECTIONAL VIEW & BOM. |  | 1.14.1.2 | Unscheduled | No | No | 2020-01-06 18:00 | 2020-03-03 17:40 | 2020-03-04 18:00 | 2020-05-19 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5061 |  | 2020-02-13 11:44 | 7012-155-PVE-F-023 |  |  |  | A |  |  |  | 42.9952 | 0.006849 | 0.89 | Plan & Actual | Date |  | 0 | 0 | 0 | 331.35 | 0 | 39.11 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4205 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-06 18:00 | 2020-03-04 18:00 |  | 10 | 2020-03-04 23:31 |  |  | 2020-01-22 17:40 | 2020-04-01 18:00 |  | 30 | 2020-04-01 23:31 |  |  | 2020-01-28 17:40 | 2020-04-08 18:00 |  | 35 | 2020-04-08 23:31 |  |  | 2020-02-03 23:59 | 2020-04-15 18:00 |  | 65 | 2020-04-15 23:31 |  |  | 2020-02-10 17:40 | 2020-05-06 18:00 |  | 80 | 2020-04-28 23:31 | [5 empty] | 80 | 2020-07-07 14:38 | [5 empty] | 80 | 2020-07-07 14:38 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-03 17:40 | 2020-05-19 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 258 |  |  |  | 101269
1847 | Task(Task)-->E (Engineering) | LIGHTING LAYOUT PLAN WITH POWER DISTRIBUTION ARRANGEMENT, SECTIONAL VIEW, BOM OF SS-2 |  | 1.14.1.2 | Unscheduled | No | No | 2020-02-10 18:00 | 2020-04-07 17:40 | 2020-05-22 09:00 | 2020-07-13 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5072 |  | 2020-02-13 11:44 | 7012-155-PVE-G-034 |  |  |  | A |  |  |  | 32.3671 | 0.005156 | 0.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 248.42 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4206 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-10 18:00 | 2020-06-01 18:00 |  | 10 | 2020-05-15 23:31 |  |  | 2020-02-26 17:40 | 2020-06-08 18:00 |  | 30 | 2020-05-20 23:31 |  |  | 2020-03-03 17:40 | 2020-06-15 18:00 |  | 35 | 2020-05-20 23:31 |  |  | 2020-03-09 23:59 | 2020-06-22 18:00 |  | 65 | 2020-05-22 23:31 |  |  | 2020-03-16 17:40 | 2020-07-13 18:00 |  | 80 | 2020-06-01 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-07 17:40 | 2020-07-13 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 269 |  |  |  | 101280
1848 | Task(Task)-->E (Engineering) | GA, SLD & BOM FOR 415V LT CHP PMCC-2 |  | 1.14.1.2 | Unscheduled | No | No | 2020-03-12 17:40 | 2020-04-23 17:40 | 2020-05-21 18:00 | 2020-09-22 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-156 |  | 2020-02-13 11:46 | 7012-155-PVE-W-101 |  |  |  | A |  |  |  | 15.942 | 0.00254 | 0.33 | Plan & Actual | Date |  | 0 | 0 | 0 | 124.21 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4236 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-14 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-12 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-03-19 17:40 | 2020-06-01 18:00 |  | 35 |  |  |  | 2020-03-25 23:59 | 2020-06-01 18:00 |  | 65 |  |  |  | 2020-04-01 17:40 | 2020-06-22 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-23 17:40 | 2020-06-22 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 336 |  |  |  | 101347
1849 | Task(Task)-->P (Procurement) | PROCUREMENT | 1.14.2 | 1.14 | Work In Progress | No | No | 2019-11-12 09:00 | 2021-03-31 18:00 | 2019-11-02 09:00 | 2021-10-24 23:59 |  |  | 2019-11-02 10:57 |  |  |  | 78.6964 | 18.9741 | [15 empty] | 54.3563 | 1.4743 | 144.99 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4240 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019318
1850 | Task(Task)-->P (Procurement) | PURCHASE REQUISITION | 1.14.2.1 | 1.14.2 | Work In Progress | No | No | 2019-11-12 09:00 | 2020-06-25 18:00 | 2019-11-02 09:00 | 2020-04-18 18:00 |  |  | 2019-11-02 10:57 |  |  |  | 100 | 78.0225 | [15 empty] | 5.0003 | 0.073721 | 7.25 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4241 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019319
1851 | Task(Task)-->P (Procurement) | 33/6.9KV HT TRANSFORMER (ONAN TYPE) |  | 1.14.2.1 | Completed | No | No | 2019-11-28 09:00 | 2019-11-28 18:00 | 2020-01-17 09:00 | 2020-01-17 18:00 |  |  | 2020-01-22 10:57 | 2020-01-22 10:57 |  |  | 100 | 100 | [15 empty] | 14.011 | 0.010329 | 1.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4242 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019320
1852 | Task(Task)-->P (Procurement) | HT SWITCHGEAR (33KV & 6.6KV) |  | 1.14.2.1 | Completed | No | No | 2019-11-13 09:00 | 2019-11-13 18:00 | 2019-11-02 09:00 | 2019-11-02 18:00 |  |  | 2019-11-02 10:57 | 2019-11-02 10:57 |  |  | 100 | 100 | [15 empty] | 18.544 | 0.013671 | 1.35 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4243 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019321
1853 | Task(Task)-->P (Procurement) | 6.6KV HT VFD with Motors |  | 1.14.2.1 | Completed | No | No | 2019-12-30 09:00 | 2019-12-30 18:00 | 2020-01-24 09:00 | 2020-01-24 18:00 |  |  | 2019-11-21 10:57 | 2019-11-21 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4244 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019322
1854 | Task(Task)-->P (Procurement) | 6.6KV HT APFC PANEL |  | 1.14.2.1 | Completed | No | No | 2020-01-24 09:00 | 2020-01-24 18:00 | 2020-02-13 09:00 | 2020-02-13 18:00 |  |  | 2020-02-13 10:57 | 2020-02-13 10:57 |  |  | 100 | 100 | [15 empty] | 1.6484 | 0.001215 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4245 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019323
1855 | Task(Task)-->P (Procurement) | 6.6KV/0.433V LT TRANSFORMER |  | 1.14.2.1 | Completed | No | No | 2019-11-25 09:00 | 2019-11-25 18:00 | 2020-01-22 09:00 | 2020-01-22 18:00 |  |  | 2020-01-22 15:37 | 2020-01-22 15:37 |  |  | 100 | 100 | [15 empty] | 7.0055 | 0.005165 | 0.51 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4246 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019324
1856 | Task(Task)-->P (Procurement) | LT BUSDUCT |  | 1.14.2.1 | Completed | No | No | 2019-12-02 09:00 | 2019-12-02 18:00 | 2019-12-11 09:00 | 2019-12-11 18:00 |  |  | 2019-12-11 15:44 | 2019-12-11 15:44 |  |  | 100 | 100 | [15 empty] | 2.1978 | 0.00162 | 0.16 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4247 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019325
1857 | Task(Task)-->P (Procurement) | 415V MCC |  | 1.14.2.1 | Unscheduled | No | No | 2019-11-28 09:00 | 2019-11-28 18:00 | 2019-11-14 09:00 | 2019-11-14 18:00 | [6 empty] | 100 | 0 | [15 empty] | 14.1484 | 0.01043 | 1.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4248 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019326
1858 | Task(Task)-->P (Procurement) | 110V DC BATTERY & BATTERY CHARGER SYSTEM |  | 1.14.2.1 | Completed | No | No | 2020-01-13 09:00 | 2020-01-13 18:00 | 2020-01-13 09:00 | 2020-01-13 18:00 |  |  | 2020-01-13 10:57 | 2020-01-13 10:57 |  |  | 100 | 100 | [15 empty] | 4.6703 | 0.003443 | 0.34 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4249 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019327
1859 | Task(Task)-->P (Procurement) | 6.6KV NEUTRAL GROUNDING RESISTOR |  | 1.14.2.1 | Completed | No | No | 2019-12-12 09:00 | 2019-12-12 18:00 | 2019-12-12 09:00 | 2019-12-12 18:00 |  |  | 2019-12-12 15:21 | 2019-12-12 15:21 |  |  | 100 | 100 | [15 empty] | 0.41209 | 0.000304 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4250 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019328
1860 | Task(Task)-->P (Procurement) | PLC SYSTEM |  | 1.14.2.1 | Completed | No | No | 2019-11-12 09:00 | 2019-11-12 18:00 | 2019-11-12 09:00 | 2019-11-12 18:00 |  |  | 2019-11-12 10:57 | 2019-11-12 10:57 |  |  | 100 | 100 | [15 empty] | 10.0275 | 0.007392 | 0.73 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4251 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019329
1861 | Task(Task)-->P (Procurement) | UPS SYSTEM |  | 1.14.2.1 | Completed | No | No | 2020-01-08 09:00 | 2020-01-08 18:00 | 2020-02-19 09:00 | 2020-02-19 18:00 |  |  | 2020-02-19 10:57 | 2020-02-19 10:57 |  |  | 100 | 100 | [15 empty] | 2.0604 | 0.001519 | 0.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4252 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019330
1862 | Task(Task)-->P (Procurement) | 24V DC BATTERY AND BATTERY CHARGER SYSTEM |  | 1.14.2.1 | Completed | No | No | 2020-01-27 09:00 | 2020-01-27 18:00 | 2020-02-26 09:00 | 2020-02-26 18:00 |  |  | 2020-02-26 10:57 | 2020-02-26 10:57 |  |  | 100 | 100 | [15 empty] | 0.96154 | 0.000709 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4253 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019331
1863 | Task(Task)-->P (Procurement) | FDA SYSTEM |  | 1.14.2.1 | Completed | No | No | 2020-02-14 09:00 | 2020-02-14 18:00 | 2020-02-17 09:00 | 2020-02-17 18:00 |  |  | 2020-02-17 10:57 | 2020-02-17 10:57 |  |  | 100 | 100 | [15 empty] | 6.7308 | 0.004962 | 0.49 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4254 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019332
1864 | Task(Task)-->P (Procurement) | SCADA |  | 1.14.2.1 | Completed | No | No | 2019-12-10 09:00 | 2019-12-10 18:00 | 2019-12-21 09:00 | 2019-12-21 18:00 |  |  | 2019-12-21 10:57 | 2019-12-21 10:57 |  |  | 100 | 100 | [15 empty] | 3.1593 | 0.002329 | 0.23 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4255 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019333
1865 | Task(Task)-->P (Procurement) | RUBBER MATS |  | 1.14.2.1 | Completed | No | No | 2020-06-25 09:00 | 2020-06-25 18:00 | 2020-04-18 09:00 | 2020-04-18 18:00 |  |  | 2020-04-18 10:57 | 2020-04-18 10:57 |  |  | 100 | 100 | [15 empty] | 0.13736 | 0.000101 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4258 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019334
1866 | Task(Task)-->P (Procurement) | MAIN LIGHTING DISTRIBUTION BOARD |  | 1.14.2.1 | Completed | No | No | 2020-02-04 09:00 | 2020-02-04 18:00 | 2020-04-02 09:00 | 2020-04-02 18:00 |  |  | 2020-04-02 17:08 | 2020-04-02 17:08 |  |  | 100 | 100 | [15 empty] | 0.68681 | 0.000506 | 0.05 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4259 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019335
1867 | Task(Task)-->P (Procurement) | LIGHTING PANELS |  | 1.14.2.1 | Unscheduled | No | No | 2020-02-28 09:00 | 2020-02-28 18:00 | 2020-04-02 09:00 | 2020-04-02 18:00 | [6 empty] | 100 | 0 | [15 empty] | 7.8297 | 0.005772 | 0.57 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4260 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019336
1868 | Task(Task)-->P (Procurement) | DCDB & DC FUSE BOARD |  | 1.14.2.1 | Completed | No | No | 2020-01-28 09:00 | 2020-01-28 18:00 | 2020-04-02 09:00 | 2020-04-02 18:00 |  |  | 2020-04-02 16:53 | 2020-04-02 16:53 |  |  | 100 | 100 | [15 empty] | 2.8846 | 0.002127 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4261 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019337
1869 | Task(Task)-->P (Procurement) | UPS DB,ACDB,MCBDB & AFB |  | 1.14.2.1 | Completed | No | No | 2020-03-18 09:00 | 2020-03-18 18:00 | 2020-04-02 09:00 | 2020-04-02 18:00 |  |  | 2020-04-02 17:02 | 2020-04-02 17:02 |  |  | 100 | 100 | [15 empty] | 2.8846 | 0.002127 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4262 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019338
1870 | Task(Task)-->P (Procurement) | TECHNICAL CLEARANCE | 1.14.2.2 | 1.14.2 | Work In Progress | No | No | 2019-11-13 09:00 | 2020-07-20 18:00 | 2019-11-02 09:00 | 2020-07-10 18:00 |  |  | 2019-11-04 14:47 |  |  |  | 100 | 77.0608 | [15 empty] | 5.0003 | 0.073721 | 7.25 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4263 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019339
1871 | Task(Task)-->P (Procurement) | 33/6.9KV HT TRANSFORMER (ONAN TYPE) |  | 1.14.2.2 | Completed | No | No | 2019-11-29 09:00 | 2019-12-22 23:59 | 2020-01-17 09:00 | 2020-02-17 18:00 |  |  | 2020-03-16 10:57 | 2020-03-16 10:57 |  |  | 100 | 100 | [15 empty] | 14.011 | 0.010329 | 1.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4264 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019340
1872 | Task(Task)-->P (Procurement) | HT SWITCHGEAR (33KV & 6.6KV) |  | 1.14.2.2 | Completed | No | No | 2019-11-14 09:00 | 2019-12-13 18:00 | 2019-11-02 09:00 | 2020-03-10 18:00 |  |  | 2019-11-04 14:47 | 2020-03-10 14:47 |  |  | 100 | 100 | [15 empty] | 18.544 | 0.013671 | 1.35 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4265 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019341
1873 | Task(Task)-->P (Procurement) | 6.6KV HT VFD with Motors |  | 1.14.2.2 | Completed | No | No | 2019-12-31 09:00 | 2020-01-29 18:00 | 2020-01-24 09:00 | 2020-04-16 18:00 |  |  | 2020-02-26 10:57 | 2020-02-26 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4266 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019342
1874 | Task(Task)-->P (Procurement) | 6.6KV HT APFC PANEL |  | 1.14.2.2 | Completed | No | No | 2020-01-25 09:00 | 2020-02-16 23:59 | 2020-02-13 09:00 | 2020-04-28 18:00 |  |  | 2020-04-28 10:57 | 2020-04-28 10:57 |  |  | 100 | 100 | [15 empty] | 1.6484 | 0.001215 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4267 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019343
1875 | Task(Task)-->P (Procurement) | 6.6KV/0.433V LT TRANSFORMER |  | 1.14.2.2 | Completed | No | No | 2019-11-26 09:00 | 2019-12-20 18:00 | 2020-01-22 09:00 | 2020-03-16 18:00 |  |  | 2020-01-23 15:38 | 2020-03-16 15:38 |  |  | 100 | 100 | [15 empty] | 7.0055 | 0.005165 | 0.51 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4268 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019344
1876 | Task(Task)-->P (Procurement) | LT BUSDUCT |  | 1.14.2.2 | Completed | No | No | 2019-12-03 09:00 | 2020-01-03 18:00 | 2019-12-11 09:00 | 2020-03-10 18:00 |  |  | 2019-12-12 15:45 | 2020-03-10 15:45 |  |  | 100 | 100 | [15 empty] | 2.1978 | 0.00162 | 0.16 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4269 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019345
1877 | Task(Task)-->P (Procurement) | 415V MCC |  | 1.14.2.2 | Unscheduled | No | No | 2019-11-29 09:00 | 2020-01-11 18:00 | 2019-11-14 09:00 | 2020-03-11 18:00 | [6 empty] | 100 | 0 | [15 empty] | 14.1484 | 0.01043 | 1.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4270 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019346
1878 | Task(Task)-->P (Procurement) | 110V DC BATTERY & BATTERY CHARGER SYSTEM |  | 1.14.2.2 | Completed | No | No | 2020-01-14 09:00 | 2020-02-03 18:00 | 2020-01-13 09:00 | 2020-06-04 18:00 |  |  | 2020-01-14 17:10 | 2020-06-04 17:10 |  |  | 100 | 100 | [15 empty] | 4.6703 | 0.003443 | 0.34 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4271 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019347
1879 | Task(Task)-->P (Procurement) | 6.6KV NEUTRAL GROUNDING RESISTOR |  | 1.14.2.2 | Completed | No | No | 2019-12-13 09:00 | 2019-12-31 18:00 | 2019-12-12 09:00 | 2020-01-21 18:00 |  |  | 2019-12-13 15:23 | 2020-01-21 15:23 |  |  | 100 | 100 | [15 empty] | 0.41209 | 0.000304 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4272 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019348
1880 | Task(Task)-->P (Procurement) | PLC SYSTEM |  | 1.14.2.2 | Completed | No | No | 2019-11-13 09:00 | 2019-12-04 18:00 | 2019-11-12 09:00 | 2020-03-16 18:00 |  |  | 2020-03-16 10:57 | 2020-03-16 10:57 |  |  | 100 | 100 | [15 empty] | 10.0275 | 0.007392 | 0.73 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4273 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019349
1881 | Task(Task)-->P (Procurement) | UPS SYSTEM |  | 1.14.2.2 | Completed | No | No | 2020-01-09 09:00 | 2020-01-28 18:00 | 2020-02-19 09:00 | 2020-06-06 18:00 |  |  | 2020-06-06 10:57 | 2020-06-06 10:57 |  |  | 100 | 100 | [15 empty] | 2.0604 | 0.001519 | 0.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4274 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019350
1882 | Task(Task)-->P (Procurement) | 24V DC BATTERY AND BATTERY CHARGER SYSTEM |  | 1.14.2.2 | Unscheduled | No | No | 2020-01-28 09:00 | 2020-02-07 18:00 | 2020-02-26 09:00 | 2020-07-10 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.96154 | 0.000709 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4275 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019351
1883 | Task(Task)-->P (Procurement) | FDA SYSTEM |  | 1.14.2.2 | Completed | No | No | 2020-02-15 09:00 | 2020-03-12 18:00 | 2020-02-17 09:00 | 2020-06-10 18:00 |  |  | 2020-06-10 10:57 | 2020-06-10 10:57 |  |  | 100 | 100 | [15 empty] | 6.7308 | 0.004962 | 0.49 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4276 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019352
1884 | Task(Task)-->P (Procurement) | SCADA |  | 1.14.2.2 | Completed | No | No | 2019-12-11 09:00 | 2020-01-15 18:00 | 2019-12-21 09:00 | 2020-03-16 18:00 |  |  | 2020-03-16 10:57 | 2020-03-16 10:57 |  |  | 100 | 100 | [15 empty] | 3.1593 | 0.002329 | 0.23 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4277 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019353
1885 | Task(Task)-->P (Procurement) | RUBBER MATS |  | 1.14.2.2 | Completed | No | No | 2020-06-26 09:00 | 2020-07-20 18:00 | 2020-04-18 09:00 | 2020-04-20 18:00 |  |  | 2020-04-20 10:57 | 2020-04-20 10:57 |  |  | 100 | 100 | [15 empty] | 0.13736 | 0.000101 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4280 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019354
1886 | Task(Task)-->P (Procurement) | MAIN LIGHTING DISTRIBUTION BOARD |  | 1.14.2.2 | Completed | No | No | 2020-02-05 09:00 | 2020-04-02 18:00 | 2020-04-02 09:00 | 2020-07-01 18:00 |  |  | 2020-04-03 17:08 | 2020-07-01 17:08 |  |  | 100 | 100 | [15 empty] | 0.68681 | 0.000506 | 0.05 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4281 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019355
1887 | Task(Task)-->P (Procurement) | LIGHTING PANELS |  | 1.14.2.2 | Unscheduled | No | No | 2020-02-29 09:00 | 2020-05-11 18:00 | 2020-04-02 09:00 | 2020-07-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 7.8297 | 0.005772 | 0.57 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4282 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019356
1888 | Task(Task)-->P (Procurement) | DCDB & DC FUSE BOARD |  | 1.14.2.2 | Completed | No | No | 2020-01-29 09:00 | 2020-04-02 18:00 | 2020-04-02 09:00 | 2020-07-01 18:00 |  |  | 2020-04-03 16:59 | 2020-07-01 16:59 |  |  | 100 | 100 | [15 empty] | 2.8846 | 0.002127 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4283 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019357
1889 | Task(Task)-->P (Procurement) | UPS DB,ACDB,MCBDB & AFB |  | 1.14.2.2 | Completed | No | No | 2020-03-19 09:00 | 2020-04-02 18:00 | 2020-04-02 09:00 | 2020-07-01 18:00 |  |  | 2020-04-03 17:03 | 2020-07-01 17:03 |  |  | 100 | 100 | [15 empty] | 2.8846 | 0.002127 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4284 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019358
1890 | Task(Task)-->P (Procurement) | ORDERING | 1.14.2.3 | 1.14.2 | Work In Progress | No | No | 2019-12-05 09:00 | 2020-07-25 18:00 | 2020-01-21 09:00 | 2020-08-13 18:00 |  |  | 2020-01-04 08:00 |  |  |  | 100 | 68.232 | [15 empty] | 10.0007 | 0.14744 | 14.5 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4285 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019359
1891 | Task(Task)-->P (Procurement) | 33/6.9KV HT TRANSFORMER (ONAN TYPE) |  | 1.14.2.3 | Completed | No | No | 2019-12-23 09:00 | 2020-01-15 18:00 | 2020-02-17 09:00 | 2020-06-24 18:00 |  |  | 2020-07-16 22:28 | 2020-07-16 22:28 |  |  | 100 | 100 | [15 empty] | 14.0193 | 0.020671 | 2.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4286 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019360
1892 | Task(Task)-->P (Procurement) | HT SWITCHGEAR (33KV & 6.6KV) |  | 1.14.2.3 | Completed | No | No | 2019-12-14 09:00 | 2020-01-13 18:00 | 2020-03-10 09:00 | 2020-07-18 18:00 |  |  | 2020-03-11 14:48 | 2020-07-04 14:48 |  |  | 100 | 100 | [15 empty] | 18.6464 | 0.027493 | 2.7 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4287 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019361
1893 | Task(Task)-->P (Procurement) | 6.6KV HT VFD with Motors |  | 1.14.2.3 | Completed | No | No | 2020-01-30 09:00 | 2020-02-28 18:00 | 2020-04-16 09:00 | 2020-07-18 18:00 |  |  | 2020-04-29 10:57 | 2020-04-29 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4288 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019362
1894 | Task(Task)-->P (Procurement) | 6.6KV HT APFC PANEL |  | 1.14.2.3 | Completed | No | No | 2020-02-17 09:00 | 2020-03-10 18:00 | 2020-04-28 09:00 | 2020-07-28 18:00 |  |  | 2020-05-04 15:17 | 2020-07-10 15:17 |  |  | 100 | 100 | [15 empty] | 1.6575 | 0.002444 | 0.24 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4289 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019363
1895 | Task(Task)-->P (Procurement) | 6.6KV/0.433V LT TRANSFORMER |  | 1.14.2.3 | Completed | No | No | 2019-12-21 09:00 | 2020-01-15 18:00 | 2020-03-16 09:00 | 2020-06-23 18:00 |  |  | 2020-06-23 10:14 | 2020-06-23 10:14 |  |  | 100 | 100 | [15 empty] | 7.0442 | 0.010386 | 1.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4290 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019364
1896 | Task(Task)-->P (Procurement) | LT BUSDUCT |  | 1.14.2.3 | Completed | No | No | 2020-01-04 09:00 | 2020-02-04 18:00 | 2020-03-10 09:00 | 2020-06-11 18:00 |  |  | 2020-01-04 08:00 | 2020-04-27 15:46 |  |  | 100 | 100 | [15 empty] | 2.1409 | 0.003157 | 0.31 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4291 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019365
1897 | Task(Task)-->P (Procurement) | 415V MCC |  | 1.14.2.3 | Unscheduled | No | No | 2020-01-12 | 2020-02-25 18:00 | 2020-03-11 09:00 | 2020-07-04 18:00 | [6 empty] | 100 | 0 | [15 empty] | 14.2956 | 0.021078 | 2.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4292 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019366
1898 | Task(Task)-->P (Procurement) | 110V DC BATTERY & BATTERY CHARGER SYSTEM |  | 1.14.2.3 | Completed | No | No | 2020-02-04 09:00 | 2020-02-24 18:00 | 2020-06-04 09:00 | 2020-07-18 18:00 |  |  | 2020-06-05 17:10 | 2020-07-06 17:10 |  |  | 100 | 100 | [15 empty] | 4.6271 | 0.006822 | 0.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4293 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019367
1899 | Task(Task)-->P (Procurement) | 6.6KV NEUTRAL GROUNDING RESISTOR |  | 1.14.2.3 | Completed | No | No | 2020-01-01 09:00 | 2020-01-20 18:00 | 2020-01-21 09:00 | 2020-03-19 18:00 |  |  | 2020-03-19 10:20 | 2020-03-19 10:20 |  |  | 100 | 100 | [15 empty] | 0.41436 | 0.000611 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4294 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019368
1900 | Task(Task)-->P (Procurement) | PLC SYSTEM |  | 1.14.2.3 | Completed | No | No | 2019-12-05 09:00 | 2019-12-27 18:00 | 2020-03-16 09:00 | 2020-07-07 18:00 |  |  | 2020-03-16 17:20 | 2020-06-04 17:20 |  |  | 100 | 100 | [15 empty] | 10.0829 | 0.014866 | 1.46 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4295 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019369
1901 | Task(Task)-->P (Procurement) | UPS SYSTEM |  | 1.14.2.3 | Unscheduled | No | No | 2020-01-29 09:00 | 2020-02-18 18:00 | 2020-06-06 09:00 | 2020-07-31 18:00 | [6 empty] | 100 | 0 | [15 empty] | 2.0028 | 0.002953 | 0.29 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4296 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019370
1902 | Task(Task)-->P (Procurement) | 24V DC BATTERY AND BATTERY CHARGER SYSTEM |  | 1.14.2.3 | Unscheduled | No | No | 2020-02-08 09:00 | 2020-02-19 18:00 | 2020-07-10 09:00 | 2020-08-07 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.96685 | 0.001426 | 0.14 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4297 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019371
1903 | Task(Task)-->P (Procurement) | FDA SYSTEM |  | 1.14.2.3 | Unscheduled | No | No | 2020-03-13 09:00 | 2020-04-08 18:00 | 2020-06-10 09:00 | 2020-08-06 18:00 | [6 empty] | 100 | 0 | [15 empty] | 6.6989 | 0.009877 | 0.97 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4298 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019372
1904 | Task(Task)-->P (Procurement) | SCADA |  | 1.14.2.3 | Completed | No | No | 2020-01-16 09:00 | 2020-02-20 18:00 | 2020-03-16 09:00 | 2020-06-24 18:00 |  |  | 2020-06-24 10:20 | 2020-06-24 10:20 |  |  | 100 | 100 | [15 empty] | 3.1077 | 0.004582 | 0.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4299 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019373
1905 | Task(Task)-->P (Procurement) | RUBBER MATS |  | 1.14.2.3 | Completed | No | No | 2020-07-21 09:00 | 2020-07-25 18:00 | 2020-04-20 09:00 | 2020-06-06 18:00 |  |  | 2020-04-25 10:57 | 2020-04-25 10:57 |  |  | 100 | 100 | [15 empty] | 0.13812 | 0.000204 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4302 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019374
1906 | Task(Task)-->P (Procurement) | MAIN LIGHTING DISTRIBUTION BOARD |  | 1.14.2.3 | Completed | No | No | 2020-04-03 09:00 | 2020-04-18 18:00 | 2020-07-01 09:00 | 2020-08-13 18:00 |  |  | 2020-07-02 17:08 | 2020-07-07 17:08 |  |  | 100 | 100 | [15 empty] | 0.69061 | 0.001018 | 0.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4303 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019375
1907 | Task(Task)-->P (Procurement) | LIGHTING PANELS |  | 1.14.2.3 | Unscheduled | No | No | 2020-05-12 09:00 | 2020-06-25 18:00 | 2020-07-01 09:00 | 2020-08-13 18:00 | [6 empty] | 100 | 0 | [15 empty] | 7.8039 | 0.011506 | 1.13 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4304 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019376
1908 | Task(Task)-->P (Procurement) | DCDB & DC FUSE BOARD |  | 1.14.2.3 | Completed | No | No | 2020-04-03 09:00 | 2020-04-18 18:00 | 2020-07-01 09:00 | 2020-08-13 18:00 |  |  | 2020-07-02 17:00 | 2020-07-07 17:00 |  |  | 100 | 100 | [15 empty] | 2.8315 | 0.004175 | 0.41 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4305 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019377
1909 | Task(Task)-->P (Procurement) | UPS DB,ACDB,MCBDB & AFB |  | 1.14.2.3 | Completed | No | No | 2020-04-03 09:00 | 2020-04-18 18:00 | 2020-07-01 09:00 | 2020-08-13 18:00 |  |  | 2020-07-02 17:05 | 2020-07-07 17:05 |  |  | 100 | 100 | [15 empty] | 2.8315 | 0.004175 | 0.41 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4306 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019378
1910 | Task(Task)-->P (Procurement) | ITP APPROVAL | 1.14.2.4 | 1.14.2 | Work In Progress | No | No | 2019-12-28 09:00 | 2020-09-03 18:00 | 2020-06-05 09:00 | 2020-10-30 18:00 |  |  | 2020-06-05 08:52 |  |  |  | 100 | 14.4233 | [15 empty] | 5.0003 | 0.073721 | 7.25 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4307 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019379
1911 | Task(Task)-->P (Procurement) | 33/6.9KV HT TRANSFORMER (ONAN TYPE) |  | 1.14.2.4 | Completed | No | No | 2020-01-16 09:00 | 2020-02-24 18:00 | 2020-07-03 09:00 | 2020-07-15 18:00 |  |  | 2020-07-03 08:46 | 2020-07-15 08:46 |  |  | 100 | 100 | [15 empty] | 14.011 | 0.010329 | 1.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4308 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019380
1912 | Task(Task)-->P (Procurement) | HT SWITCHGEAR (33KV & 6.6KV) |  | 1.14.2.4 | Unscheduled | No | No | 2020-01-14 09:00 | 2020-02-22 18:00 | 2020-08-06 09:00 | 2020-10-20 18:00 |  |  | 2020-07-13 10:49 |  |  |  | 100 | 0 | [15 empty] | 18.544 | 0.013671 | 1.35 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4309 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019381
1913 | Task(Task)-->P (Procurement) | 6.6KV HT VFD with Motors |  | 1.14.2.4 | Unscheduled | No | No | 2020-02-29 09:00 | 2020-04-08 18:00 | 2020-08-01 09:00 | 2020-09-09 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4310 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019382
1914 | Task(Task)-->P (Procurement) | 6.6KV HT APFC PANEL |  | 1.14.2.4 | Unscheduled | No | No | 2020-03-11 09:00 | 2020-04-19 23:59 | 2020-08-01 09:00 | 2020-09-09 18:00 | [6 empty] | 100 | 0 | [15 empty] | 1.6484 | 0.001215 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4311 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019383
1915 | Task(Task)-->P (Procurement) | 6.6KV/0.433V LT TRANSFORMER |  | 1.14.2.4 | Unscheduled | No | No | 2020-01-16 09:00 | 2020-02-24 18:00 | 2020-08-05 09:00 | 2020-10-10 18:00 | [6 empty] | 100 | 0 | [15 empty] | 7.0055 | 0.005165 | 0.51 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4312 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019384
1916 | Task(Task)-->P (Procurement) | LT BUSDUCT |  | 1.14.2.4 | Unscheduled | No | No | 2020-02-05 09:00 | 2020-03-15 23:59 | 2020-09-21 09:00 | 2020-10-20 18:00 |  |  | 2020-09-21 17:35 |  |  |  | 100 | 0 | [15 empty] | 2.1978 | 0.00162 | 0.16 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4313 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019385
1917 | Task(Task)-->P (Procurement) | 415V MCC |  | 1.14.2.4 | Unscheduled | No | No | 2020-02-26 09:00 | 2020-04-05 23:59 | 2020-08-01 09:00 | 2020-09-09 18:00 | [6 empty] | 100 | 0 | [15 empty] | 14.1484 | 0.01043 | 1.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4314 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019386
1918 | Task(Task)-->P (Procurement) | 110V DC BATTERY & BATTERY CHARGER SYSTEM |  | 1.14.2.4 | Unscheduled | No | No | 2020-02-25 09:00 | 2020-04-04 18:00 | 2020-07-07 09:00 | 2020-10-10 18:00 |  |  | 2020-07-07 10:31 |  |  |  | 100 | 0 | [15 empty] | 4.6703 | 0.003443 | 0.34 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4315 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019387
1919 | Task(Task)-->P (Procurement) | 6.6KV NEUTRAL GROUNDING RESISTOR |  | 1.14.2.4 | Completed | No | No | 2020-01-21 09:00 | 2020-02-29 18:00 | 2020-06-05 09:00 | 2020-07-15 18:00 |  |  | 2020-06-05 08:52 | 2020-07-15 08:52 |  |  | 100 | 100 | [15 empty] | 0.41209 | 0.000304 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4316 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019388
1920 | Task(Task)-->P (Procurement) | PLC SYSTEM |  | 1.14.2.4 | Unscheduled | No | No | 2019-12-28 09:00 | 2020-02-05 18:00 | 2020-08-27 09:00 | 2020-10-30 18:00 |  |  | 2020-08-27 17:08 |  |  |  | 100 | 0 | [15 empty] | 10.0275 | 0.007392 | 0.73 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4317 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019389
1921 | Task(Task)-->P (Procurement) | UPS SYSTEM |  | 1.14.2.4 | Unscheduled | No | No | 2020-02-19 09:00 | 2020-03-29 23:59 | 2020-09-01 09:00 | 2020-10-30 18:00 | [6 empty] | 100 | 0 | [15 empty] | 2.0604 | 0.001519 | 0.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4318 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019390
1922 | Task(Task)-->P (Procurement) | 24V DC BATTERY AND BATTERY CHARGER SYSTEM |  | 1.14.2.4 | Unscheduled | No | No | 2020-02-20 09:00 | 2020-03-30 18:00 | 2020-08-08 09:00 | 2020-10-30 18:00 |  |  | 2020-08-06 16:17 |  |  |  | 100 | 0 | [15 empty] | 0.96154 | 0.000709 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4319 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019391
1923 | Task(Task)-->P (Procurement) | FDA SYSTEM |  | 1.14.2.4 | Unscheduled | No | No | 2020-04-09 09:00 | 2020-05-18 18:00 | 2020-08-21 09:00 | 2020-10-30 18:00 | [6 empty] | 100 | 0 | [15 empty] | 6.7308 | 0.004962 | 0.49 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4320 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019392
1924 | Task(Task)-->P (Procurement) | SCADA |  | 1.14.2.4 | Unscheduled | No | No | 2020-02-21 09:00 | 2020-03-31 18:00 | 2020-09-17 09:00 | 2020-10-25 23:59 | [6 empty] | 100 | 0 | [15 empty] | 3.1593 | 0.002329 | 0.23 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4321 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019393
1925 | Task(Task)-->P (Procurement) | RUBBER MATS |  | 1.14.2.4 | Unscheduled | No | No | 2020-07-26 | 2020-09-03 18:00 | 2020-08-10 09:00 | 2020-08-10 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.13736 | 0.000101 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4324 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019394
1926 | Task(Task)-->P (Procurement) | MAIN LIGHTING DISTRIBUTION BOARD |  | 1.14.2.4 | Unscheduled | No | No | 2020-04-19 | 2020-05-28 18:00 | 2020-07-28 09:00 | 2020-10-10 18:00 |  |  | 2020-07-28 17:50 |  |  |  | 100 | 0 | [15 empty] | 0.68681 | 0.000506 | 0.05 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4325 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019395
1927 | Task(Task)-->P (Procurement) | LIGHTING PANELS |  | 1.14.2.4 | Unscheduled | No | No | 2020-06-26 09:00 | 2020-08-04 18:00 | 2020-07-28 09:00 | 2020-10-10 18:00 |  |  | 2020-07-28 17:39 |  |  |  | 100 | 0 | [15 empty] | 7.8297 | 0.005772 | 0.57 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4326 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019396
1928 | Task(Task)-->P (Procurement) | DCDB & DC FUSE BOARD |  | 1.14.2.4 | Unscheduled | No | No | 2020-04-19 | 2020-05-28 18:00 | 2020-07-28 09:00 | 2020-10-10 18:00 |  |  | 2020-07-28 14:24 |  |  |  | 100 | 0 | [15 empty] | 2.8846 | 0.002127 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4327 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019397
1929 | Task(Task)-->P (Procurement) | UPS DB,ACDB,MCBDB & AFB |  | 1.14.2.4 | Unscheduled | No | No | 2020-04-19 | 2020-05-28 18:00 | 2020-07-28 09:00 | 2020-10-10 18:00 |  |  | 2020-07-28 17:48 |  |  |  | 100 | 0 | [15 empty] | 2.8846 | 0.002127 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4328 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019398
1930 | Task(Task)-->P (Procurement) | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE | 1.14.2.5 | 1.14.2 | Work In Progress | No | No | 2019-12-28 09:00 | 2020-08-15 18:00 | 2020-03-19 09:00 | 2020-10-31 18:00 |  |  | 2020-03-20 15:25 |  |  |  | 100 | 24.4949 | [15 empty] | 15.001 | 0.22116 | 21.75 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4329 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019399
1931 | Task(Task)-->P (Procurement) | 33/6.9KV HT TRANSFORMER (ONAN TYPE) |  | 1.14.2.5 | Completed | No | No | 2020-01-16 09:00 | 2020-03-15 23:59 | 2020-06-30 09:00 | 2020-09-22 18:00 |  |  | 2020-06-30 08:48 | 2020-09-22 12:23 |  |  | 100 | 100 | [15 empty] | 14.0165 | 0.031 | 3.05 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4330 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019400
1932 | Task(Task)-->P (Procurement) | HT SWITCHGEAR (33KV & 6.6KV) |  | 1.14.2.5 | Unscheduled | No | No | 2020-01-14 09:00 | 2020-03-28 18:00 | 2020-07-30 09:00 | 2020-10-20 18:00 |  |  | 2020-07-30 10:50 |  |  |  | 100 | 0 | [15 empty] | 18.5662 | 0.041062 | 4.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4331 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019401
1933 | Task(Task)-->P (Procurement) | 6.6KV HT VFD with Motors |  | 1.14.2.5 | Completed | No | No | 2020-02-29 09:00 | 2020-05-13 18:00 | 2020-08-08 09:00 | 2020-10-10 18:00 |  |  | 2020-07-28 11:51 | 2020-09-23 15:24 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4332 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019402
1934 | Task(Task)-->P (Procurement) | 6.6KV HT APFC PANEL |  | 1.14.2.5 | Unscheduled | No | No | 2020-03-11 09:00 | 2020-04-24 18:00 | 2020-07-22 09:00 | 2020-10-20 18:00 |  |  | 2020-07-22 08:56 |  |  |  | 100 | 0 | [15 empty] | 1.6544 | 0.003659 | 0.36 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4333 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019403
1935 | Task(Task)-->P (Procurement) | 6.6KV/0.433V LT TRANSFORMER |  | 1.14.2.5 | Completed | No | No | 2020-01-16 09:00 | 2020-03-15 23:59 | 2020-07-20 09:00 | 2020-09-17 18:00 |  |  | 2020-07-20 09:00 | 2020-09-17 12:32 |  |  | 100 | 100 | [15 empty] | 7.0772 | 0.015652 | 1.54 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4334 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019404
1936 | Task(Task)-->P (Procurement) | LT BUSDUCT |  | 1.14.2.5 | Unscheduled | No | No | 2020-02-05 09:00 | 2020-03-20 18:00 | 2020-06-12 09:00 | 2020-07-26 23:59 |  |  | 2020-09-16 17:36 |  |  |  | 100 | 0 | [15 empty] | 2.1599 | 0.004777 | 0.47 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4335 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019405
1937 | Task(Task)-->P (Procurement) | 415V MCC |  | 1.14.2.5 | Unscheduled | No | No | 2020-02-26 09:00 | 2020-05-10 23:59 | 2020-08-17 09:00 | 2020-10-31 18:00 |  |  | 2020-08-17 14:17 |  |  |  | 100 | 0 | [15 empty] | 14.2463 | 0.031508 | 3.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4336 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019406
1938 | Task(Task)-->P (Procurement) | 110V DC BATTERY & BATTERY CHARGER SYSTEM |  | 1.14.2.5 | Unscheduled | No | No | 2020-02-25 09:00 | 2020-04-19 23:59 | 2020-07-07 09:00 | 2020-10-31 18:00 |  |  | 2020-07-07 10:31 |  |  |  | 100 | 0 | [15 empty] | 4.6415 | 0.010265 | 1.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4337 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019407
1939 | Task(Task)-->P (Procurement) | 6.6KV NEUTRAL GROUNDING RESISTOR |  | 1.14.2.5 | Completed | No | No | 2020-01-21 09:00 | 2020-03-05 18:00 | 2020-03-19 09:00 | 2020-06-04 18:00 |  |  | 2020-03-20 15:25 | 2020-06-04 15:25 |  |  | 100 | 100 | [15 empty] | 0.4136 | 0.000915 | 0.09 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4338 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019408
1940 | Task(Task)-->P (Procurement) | PLC SYSTEM |  | 1.14.2.5 | Unscheduled | No | No | 2019-12-28 09:00 | 2020-03-11 18:00 | 2020-07-29 09:00 | 2020-10-15 18:00 |  |  | 2020-07-29 17:09 |  |  |  | 100 | 0 | [15 empty] | 10.0184 | 0.022157 | 2.18 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4339 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019409
1941 | Task(Task)-->P (Procurement) | UPS SYSTEM |  | 1.14.2.5 | Unscheduled | No | No | 2020-02-19 09:00 | 2020-04-03 18:00 | 2020-08-01 09:00 | 2020-09-14 18:00 |  |  | 2020-08-31 12:21 |  |  |  | 100 | 0 | [15 empty] | 2.0221 | 0.004472 | 0.44 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4340 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019410
1942 | Task(Task)-->P (Procurement) | 24V DC BATTERY AND BATTERY CHARGER SYSTEM |  | 1.14.2.5 | Unscheduled | No | No | 2020-02-20 09:00 | 2020-04-14 18:00 | 2020-08-06 09:00 | 2020-10-20 18:00 |  |  | 2020-08-06 16:16 |  |  |  | 100 | 0 | [15 empty] | 0.96507 | 0.002134 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4341 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019411
1943 | Task(Task)-->P (Procurement) | FDA SYSTEM |  | 1.14.2.5 | Unscheduled | No | No | 2020-04-09 09:00 | 2020-06-22 18:00 | 2020-08-13 09:00 | 2020-10-15 18:00 | [6 empty] | 100 | 0 | [15 empty] | 6.7096 | 0.014839 | 1.46 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4342 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019412
1944 | Task(Task)-->P (Procurement) | SCADA |  | 1.14.2.5 | Unscheduled | No | No | 2020-02-21 09:00 | 2020-05-05 18:00 | 2020-08-15 09:00 | 2020-10-31 18:00 |  |  | 2020-07-06 17:05 |  |  |  | 100 | 0 | [15 empty] | 3.125 | 0.006911 | 0.68 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4343 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019413
1945 | Task(Task)-->P (Procurement) | RUBBER MATS |  | 1.14.2.5 | Completed | No | No | 2020-07-26 | 2020-08-15 18:00 | 2020-06-30 09:00 | 2020-07-23 18:00 |  |  | 2020-06-11 21:16 | 2020-07-03 21:16 |  |  | 100 | 100 | [15 empty] | 0.13787 | 0.000305 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4346 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019414
1946 | Task(Task)-->P (Procurement) | MAIN LIGHTING DISTRIBUTION BOARD |  | 1.14.2.5 | Unscheduled | No | No | 2020-04-19 | 2020-06-02 18:00 | 2020-07-28 09:00 | 2020-10-31 18:00 |  |  | 2020-07-28 17:30 |  |  |  | 100 | 0 | [15 empty] | 0.73529 | 0.001626 | 0.16 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4347 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019415
1947 | Task(Task)-->P (Procurement) | LIGHTING PANELS |  | 1.14.2.5 | Unscheduled | No | No | 2020-06-26 09:00 | 2020-08-09 23:59 | 2020-07-28 09:00 | 2020-10-31 18:00 |  |  | 2020-07-28 17:40 |  |  |  | 100 | 0 | [15 empty] | 7.8125 | 0.017278 | 1.7 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4348 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019416
1948 | Task(Task)-->P (Procurement) | DCDB & DC FUSE BOARD |  | 1.14.2.5 | Unscheduled | No | No | 2020-04-19 | 2020-06-02 18:00 | 2020-07-28 09:00 | 2020-10-31 18:00 |  |  | 2020-07-28 14:23 |  |  |  | 100 | 0 | [15 empty] | 2.8493 | 0.006302 | 0.62 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4349 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019417
1949 | Task(Task)-->P (Procurement) | UPS DB,ACDB,MCBDB & AFB |  | 1.14.2.5 | Completed | No | No | 2020-04-19 | 2020-06-02 18:00 | 2020-07-28 09:00 | 2020-10-31 18:00 |  |  | 2020-07-28 17:47 | 2020-09-28 17:47 |  |  | 100 | 100 | [15 empty] | 2.8493 | 0.006302 | 0.62 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4350 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019418
1950 | Task(Task)-->P (Procurement) | MANUFACTURING & RECEIPT AT SITE (MRN) | 1.14.2.6 | 1.14.2 | Unscheduled | No | No | 2020-03-06 09:00 | 2021-03-31 18:00 | 2020-07-16 09:00 | 2021-10-24 23:59 |  |  | 2020-09-18 12:33 |  |  |  | 64.4923 | 0 | [15 empty] | 59.9972 | 0.88455 | 86.99 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4351 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019419
1951 | Task(Task)-->P (Procurement) | 33/6.9KV HT TRANSFORMER (ONAN TYPE) |  | 1.14.2.6 | Unscheduled | No | No | 2020-03-16 09:00 | 2021-03-22 18:00 | 2020-09-23 09:00 | 2021-09-29 18:00 |  |  | 2020-09-23 09:25 |  |  |  | 55.3763 | 0 | [15 empty] | 14.0064 | 0.1239 | 12.18 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4352 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019420
1952 | Task(Task)-->P (Procurement) | HT SWITCHGEAR (33KV & 6.6KV) |  | 1.14.2.6 | Unscheduled | No | No | 2020-03-29 | 2021-03-22 18:00 | 2020-10-21 09:00 | 2021-10-14 18:00 | [6 empty] | 53.7604 | 0 | [15 empty] | 18.6063 | 0.16458 | 16.18 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4353 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019421
1953 | Task(Task)-->P (Procurement) | 6.6KV HT VFD with Motors |  | 1.14.2.6 | Unscheduled | No | No | 2020-05-14 09:00 | 2021-03-09 18:00 | 2020-10-11 | 2021-08-06 18:00 | [6 empty] | 49 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4354 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019422
1954 | Task(Task)-->P (Procurement) | 6.6KV HT APFC PANEL |  | 1.14.2.6 | Unscheduled | No | No | 2020-04-25 09:00 | 2020-11-04 18:00 | 2020-10-21 09:00 | 2021-05-02 23:59 | [6 empty] | 85.567 | 0 | [15 empty] | 1.6674 | 0.014749 | 1.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4355 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019423
1955 | Task(Task)-->P (Procurement) | 6.6KV/0.433V LT TRANSFORMER |  | 1.14.2.6 | Unscheduled | No | No | 2020-03-16 09:00 | 2021-03-29 18:00 | 2020-10-11 | 2021-10-24 23:59 |  |  | 2020-09-18 12:33 |  |  |  | 54.3536 | 0 | [15 empty] | 7.0722 | 0.062558 | 6.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4356 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019424
1956 | Task(Task)-->P (Procurement) | LT BUSDUCT |  | 1.14.2.6 | Unscheduled | No | No | 2020-03-21 09:00 | 2020-08-13 18:00 | 2020-10-21 09:00 | 2021-03-15 18:00 | [6 empty] | 100 | 0 | [15 empty] | 2.1504 | 0.019022 | 1.87 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4357 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019425
1957 | Task(Task)-->P (Procurement) | 415V MCC |  | 1.14.2.6 | Unscheduled | No | No | 2020-05-11 09:00 | 2021-03-31 18:00 | 2020-11-01 | 2021-09-21 18:00 | [6 empty] | 46.1538 | 0 | [15 empty] | 14.2709 | 0.12623 | 12.41 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4358 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019426
1958 | Task(Task)-->P (Procurement) | 110V DC BATTERY & BATTERY CHARGER SYSTEM |  | 1.14.2.6 | Unscheduled | No | No | 2020-04-20 09:00 | 2020-11-03 18:00 | 2020-11-01 | 2021-05-17 18:00 | [6 empty] | 86.3636 | 0 | [15 empty] | 4.6343 | 0.040993 | 4.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4359 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019427
1959 | Task(Task)-->P (Procurement) | 6.6KV NEUTRAL GROUNDING RESISTOR |  | 1.14.2.6 | Unscheduled | No | No | 2020-03-06 09:00 | 2020-09-02 18:00 | 2020-07-16 09:00 | 2021-01-12 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.42548 | 0.003764 | 0.37 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4360 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019428
1960 | Task(Task)-->P (Procurement) | PLC SYSTEM |  | 1.14.2.6 | Unscheduled | No | No | 2020-03-12 09:00 | 2021-01-20 18:00 | 2020-10-31 09:00 | 2021-09-10 18:00 | [6 empty] | 66.6667 | 0 | [15 empty] | 10.0391 | 0.088801 | 8.73 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4361 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019429
1961 | Task(Task)-->P (Procurement) | UPS SYSTEM |  | 1.14.2.6 | Unscheduled | No | No | 2020-04-04 09:00 | 2020-11-03 18:00 | 2020-10-31 09:00 | 2021-06-01 18:00 | [6 empty] | 87.3832 | 0 | [15 empty] | 2.0124 | 0.017801 | 1.75 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4362 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019430
1962 | Task(Task)-->P (Procurement) | 24V DC BATTERY AND BATTERY CHARGER SYSTEM |  | 1.14.2.6 | Unscheduled | No | No | 2020-04-15 09:00 | 2020-10-18 23:59 | 2020-10-31 09:00 | 2021-05-05 18:00 | [6 empty] | 94.1176 | 0 | [15 empty] | 0.97746 | 0.008646 | 0.85 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4363 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019431
1963 | Task(Task)-->P (Procurement) | FDA SYSTEM |  | 1.14.2.6 | Unscheduled | No | No | 2020-06-23 09:00 | 2020-12-25 18:00 | 2020-10-31 09:00 | 2021-05-04 18:00 | [6 empty] | 57.5269 | 0 | [15 empty] | 6.6927 | 0.059201 | 5.82 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4364 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019432
1964 | Task(Task)-->P (Procurement) | SCADA |  | 1.14.2.6 | Unscheduled | No | No | 2020-05-06 09:00 | 2021-02-17 18:00 | 2020-11-01 | 2021-08-15 23:59 | [6 empty] | 53.8194 | 0 | [15 empty] | 3.1049 | 0.027464 | 2.7 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4365 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019433
1965 | Task(Task)-->P (Procurement) | RUBBER MATS |  | 1.14.2.6 | Unscheduled | No | No | 2020-09-04 09:00 | 2021-02-15 18:00 | 2020-08-11 09:00 | 2021-01-22 18:00 | [6 empty] | 20.6061 | 0 | [15 empty] | 0.13799 | 0.001221 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4368 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019434
1966 | Task(Task)-->P (Procurement) | MAIN LIGHTING DISTRIBUTION BOARD |  | 1.14.2.6 | Unscheduled | No | No | 2020-06-03 09:00 | 2020-09-16 18:00 | 2020-11-01 | 2021-02-14 23:59 | [6 empty] | 100 | 0 | [15 empty] | 0.71297 | 0.006307 | 0.62 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4369 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019435
1967 | Task(Task)-->P (Procurement) | LIGHTING PANELS |  | 1.14.2.6 | Unscheduled | No | No | 2020-08-10 09:00 | 2020-09-10 18:00 | 2020-11-01 | 2020-12-02 18:00 | [6 empty] | 100 | 0 | [15 empty] | 7.8082 | 0.069068 | 6.79 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4370 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019436
1968 | Task(Task)-->P (Procurement) | DCDB & DC FUSE BOARD |  | 1.14.2.6 | Unscheduled | No | No | 2020-06-03 09:00 | 2020-08-10 18:00 | 2020-11-01 | 2021-01-08 18:00 | [6 empty] | 100 | 0 | [15 empty] | 2.8404 | 0.025125 | 2.47 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4371 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019437
1969 | Task(Task)-->P (Procurement) | UPS DB,ACDB,MCBDB & AFB |  | 1.14.2.6 | Unscheduled | No | No | 2020-06-03 09:00 | 2020-11-28 18:00 | 2020-11-01 | 2021-04-28 18:00 |  |  | 2020-09-29 09:00 |  |  |  | 70.9497 | 0 | [15 empty] | 2.8404 | 0.025125 | 2.47 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4372 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019438
1970 | Task(Task)-->C (Construction) | CONSTRUCTION | 1.14.3 | 1.14 | Unscheduled | No | No | 2020-05-07 09:00 | 2021-08-26 18:00 | 2020-08-01 09:00 | 2022-03-18 18:00 | [6 empty] | 42.026 | 0 | [15 empty] | 43.8704 | 1.1899 | 117.02 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4373 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019439
1971 | Task(Task)-->C (Construction) | CIVIL | 1.14.3.1 | 1.14.3 | Unscheduled | No | No | 2020-05-07 09:00 | 2021-08-04 18:00 | 2020-08-01 09:00 | 2022-01-26 18:00 | [6 empty] | 46.1469 | 0 | [15 empty] | 91.0699 | 1.0837 | 106.57 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4374 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019440
1972 | Task(Task)-->C (Construction) | AVAILABILITY OF FRONT BY NTPC |  | 1.14.3.1 | Unscheduled | No | No | 2020-05-07 09:00 | 2020-05-07 18:00 | 2020-08-01 09:00 | 2020-08-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4375 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019441
1973 | Task(Task)-->C (Construction) | EXCAVATION |  | 1.14.3.1 | Unscheduled | No | No | 2020-05-14 09:00 | 2020-06-02 18:00 | 2020-11-05 09:00 | 2021-01-28 18:00 | [6 empty] | 100 | 0 | [15 empty] | 1.6232 | 0.01759 | 1.73 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 6500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4376 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | Excavation | [21 empty] | 1019442
1974 | Task(Task)-->C (Construction) | PCC |  | 1.14.3.1 | Unscheduled | No | No | 2020-05-21 09:00 | 2020-06-09 18:00 | 2020-11-12 09:00 | 2020-12-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.76938 | 0.008337 | 0.82 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 91 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4377 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | PCC | [21 empty] | 1019443
1975 | Task(Task)-->C (Construction) | RAFT |  | 1.14.3.1 | Unscheduled | No | No | 2020-05-28 09:00 | 2020-07-01 18:00 | 2020-11-19 09:00 | 2020-12-23 18:00 | [6 empty] | 100 | 0 | [15 empty] | 15.4813 | 0.16776 | 16.5 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 622 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4378 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019444
1976 | Task(Task)-->C (Construction) | PLINTH BEAM |  | 1.14.3.1 | Unscheduled | No | No | 2020-06-22 09:00 | 2020-08-10 18:00 | 2020-12-14 09:00 | 2021-02-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 2.4864 | 0.026944 | 2.65 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4379 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019445
1977 | Task(Task)-->C (Construction) | PULL PIT & GRADE SLAB FOR GROUND FLOOR |  | 1.14.3.1 | Unscheduled | No | No | 2020-07-22 09:00 | 2020-08-30 23:59 | 2021-01-13 09:00 | 2021-02-21 23:59 | [6 empty] | 100 | 0 | [15 empty] | 15.5282 | 0.16827 | 16.55 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 884 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5514 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019446
1978 | Task(Task)-->C (Construction) | COLUMN AND SLAB OF 1ST FLOOR |  | 1.14.3.1 | Unscheduled | No | No | 2020-08-21 09:00 | 2020-10-04 23:59 | 2021-02-12 09:00 | 2021-03-28 23:59 | [6 empty] | 100 | 0 | [15 empty] | 8.7165 | 0.094456 | 9.29 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5516 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019447
1979 | Task(Task)-->C (Construction) | COLUMN AND ROOF SLAB (2ND FLOOR) |  | 1.14.3.1 | Unscheduled | No | No | 2020-10-12 09:00 | 2020-12-10 18:00 | 2021-04-05 09:00 | 2021-06-03 18:00 | [6 empty] | 0 | 0 | [15 empty] | 8.7165 | 0.094456 | 9.29 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4382 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019448
1980 | Task(Task)-->C (Construction) | RCC COLUMN & SLAB OF MUMTY & FOUNDATION OF FAN/ AC ETC |  | 1.14.3.1 | Unscheduled | No | No | 2020-12-11 09:00 | 2021-01-09 18:00 | 2021-06-04 09:00 | 2021-07-03 18:00 | [6 empty] | 0 | 0 | [15 empty] | 1.2479 | 0.013523 | 1.33 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5517 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019449
1981 | Task(Task)-->C (Construction) | BRICK WORK OF GROUND FLOOR |  | 1.14.3.1 | Unscheduled | No | No | 2020-11-02 09:00 | 2020-12-21 18:00 | 2021-04-26 09:00 | 2021-06-14 18:00 | [6 empty] | 0 | 0 | [15 empty] | 4.438 | 0.048092 | 4.73 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5518 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019450
1982 | Task(Task)-->C (Construction) | PLASTERING OF GROUND FLOOR (IN SIDE) & HANDING OVER FOR ELECTRICAL WORKS |  | 1.14.3.1 | Unscheduled | No | No | 2020-11-12 09:00 | 2020-12-31 18:00 | 2021-05-06 09:00 | 2021-06-24 18:00 | [6 empty] | 0 | 0 | [15 empty] | 1.9234 | 0.020843 | 2.05 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 3698 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5519 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019451
1983 | Task(Task)-->C (Construction) | BRICK WORK OF 1ST FLOOR |  | 1.14.3.1 | Unscheduled | No | No | 2021-01-08 09:00 | 2021-03-08 18:00 | 2021-07-02 09:00 | 2021-08-30 18:00 | [6 empty] | 0 | 0 | [15 empty] | 4.438 | 0.048092 | 4.73 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5520 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019452
1984 | Task(Task)-->C (Construction) | PLASTERING OF 1ST FLOOR (IN SIDE) |  | 1.14.3.1 | Unscheduled | No | No | 2021-02-01 09:00 | 2021-03-22 18:00 | 2021-07-26 09:00 | 2021-09-13 18:00 | [6 empty] | 0 | 0 | [15 empty] | 1.9234 | 0.020843 | 2.05 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 3698 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5521 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019453
1985 | Task(Task)-->C (Construction) | PAINTING OF CEILING OF ROOF SLAB (GRID 2 to 3) & HANDING OVER FOR ELECTRICAL WORKS |  | 1.14.3.1 | Unscheduled | No | No | 2021-03-13 09:00 | 2021-04-01 18:00 | 2021-09-04 09:00 | 2021-09-23 18:00 | [6 empty] | 0 | 0 | [15 empty] | 1.7546 | 0.019013 | 1.87 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 3698 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5522 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019454
1986 | Task(Task)-->C (Construction) | INSIDE PAINTING & FALSE CEILING (GRID 1 TO 2) & HANDING OVER FOR ELECTRICAL WORKS |  | 1.14.3.1 | Unscheduled | No | No | 2021-03-23 09:00 | 2021-04-21 18:00 | 2021-09-14 09:00 | 2021-10-13 18:00 | [6 empty] | 0 | 0 | [15 empty] | 6.5115 | 0.070562 | 6.94 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 3698 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5523 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019455
1987 | Task(Task)-->C (Construction) | TRANSFORMER FOUNDATION, TRENCH, BRICK WORK & PLASTERING ETC & HANDING OVER TO ELECTRICAL |  | 1.14.3.1 | Unscheduled | No | No | 2020-08-11 09:00 | 2020-11-08 23:59 | 2021-02-02 09:00 | 2021-05-02 23:59 | [6 empty] | 64.4444 | 0 | [15 empty] | 2.3926 | 0.025927 | 2.55 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5524 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019456
1988 | Task(Task)-->C (Construction) | BALANCE BRICK WORK |  | 1.14.3.1 | Unscheduled | No | No | 2021-03-23 09:00 | 2021-04-21 18:00 | 2021-09-14 09:00 | 2021-10-13 18:00 | [6 empty] | 0 | 0 | [15 empty] | 3.481 | 0.037721 | 3.71 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 235 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5525 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019457
1989 | Task(Task)-->C (Construction) | OUTSIDE PLASTERING |  | 1.14.3.1 | Unscheduled | No | No | 2021-04-22 09:00 | 2021-06-20 23:59 | 2021-10-14 09:00 | 2021-12-12 23:59 | [6 empty] | 0 | 0 | [15 empty] | 3.8469 | 0.041687 | 4.1 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 7395 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5526 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019458
1990 | Task(Task)-->C (Construction) | DOOR , WINDOW, MONORAIL DOOR & ROLLING SHUTTER |  | 1.14.3.1 | Unscheduled | No | No | 2021-05-22 09:00 | 2021-06-28 18:00 | 2021-11-13 09:00 | 2021-12-20 18:00 | [6 empty] | 0 | 0 | [15 empty] | 3.2182 | 0.034875 | 3.43 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5527 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019459
1991 | Task(Task)-->C (Construction) | BALANCE PAINTING |  | 1.14.3.1 | Unscheduled | No | No | 2021-06-21 09:00 | 2021-08-04 18:00 | 2021-12-13 09:00 | 2022-01-26 18:00 | [6 empty] | 0 | 0 | [15 empty] | 3.4997 | 0.037925 | 3.73 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 7395 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5528 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019460
1992 | Task(Task)-->C (Construction) | ROOF WATER PROFING & RWDC PIPE |  | 1.14.3.1 | Unscheduled | No | No | 2021-02-07 | 2021-03-09 18:00 | 2021-08-01 | 2021-08-31 18:00 | [6 empty] | 0 | 0 | [15 empty] | 5.836 | 0.063242 | 6.22 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 1296 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5529 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019461
1993 | Task(Task)-->C (Construction) | GARLAND DRAIN & PLINTH PROTECTION |  | 1.14.3.1 | Unscheduled | No | No | 2021-06-21 09:00 | 2021-08-04 18:00 | 2021-12-13 09:00 | 2022-01-26 18:00 | [6 empty] | 0 | 0 | [15 empty] | 2.1674 | 0.023487 | 2.31 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5530 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019462
1994 | Task(Task)-->C (Construction) | ELECTRICAL & INSTRUMENTATION | 1.14.3.2 | 1.14.3 | Unscheduled | No | No | 2021-01-01 09:00 | 2021-08-04 18:00 | 2021-06-25 09:00 | 2022-01-26 18:00 | [6 empty] | 0 | 0 | [15 empty] | 6.7681 | 0.080534 | 7.92 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5254 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019463
1995 | Task(Task)-->C (Construction) | TRANSFORMERS |  | 1.14.3.2 | Unscheduled | No | No | 2021-03-23 09:00 | 2021-04-05 18:00 | 2021-09-30 09:00 | 2021-10-13 18:00 | [6 empty] | 0 | 0 | [15 empty] | 19.4444 | 0.015659 | 1.54 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4392 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019464
1996 | Task(Task)-->C (Construction) | HT PANEL |  | 1.14.3.2 | Unscheduled | No | No | 2021-04-02 09:00 | 2021-04-16 18:00 | 2021-10-15 09:00 | 2021-10-29 18:00 | [6 empty] | 0 | 0 | [15 empty] | 8.5859 | 0.006915 | 0.68 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5255 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019465
1997 | Task(Task)-->C (Construction) | HT VFD |  | 1.14.3.2 | Unscheduled | No | No | 2021-04-22 09:00 | 2021-04-23 18:00 | 2021-10-30 09:00 | 2021-10-31 23:59 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4393 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019466
1998 | Task(Task)-->C (Construction) | HT APFC |  | 1.14.3.2 | Unscheduled | No | No | 2021-04-24 09:00 | 2021-04-24 18:00 | 2021-11-01 09:00 | 2021-11-01 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5352 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019467
1999 | Task(Task)-->C (Construction) | LT PANEL |  | 1.14.3.2 | Unscheduled | No | No | 2021-04-02 09:00 | 2021-04-21 18:00 | 2021-10-25 09:00 | 2021-11-13 18:00 | [6 empty] | 0 | 0 | [15 empty] | 2.5253 | 0.002034 | 0.2 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5353 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019468
2000 | Task(Task)-->C (Construction) | BATTERY, BATTERY CHARGER & UPS |  | 1.14.3.2 | Unscheduled | No | No | 2021-01-01 09:00 | 2021-01-07 18:00 | 2021-06-25 09:00 | 2021-07-01 18:00 | [6 empty] | 0 | 0 | [15 empty] | 2.0202 | 0.001627 | 0.16 | Plan & Actual | Quantity | Set | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5552 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019469
2001 | Task(Task)-->C (Construction) | CABLE TRAY |  | 1.14.3.2 | Unscheduled | No | No | 2021-01-01 09:00 | 2021-01-10 23:59 | 2021-06-25 09:00 | 2021-07-04 23:59 | [6 empty] | 0 | 0 | [15 empty] | 8.0808 | 0.006508 | 0.64 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5354 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019470
2002 | Task(Task)-->C (Construction) | POWRE CABLE |  | 1.14.3.2 | Unscheduled | No | No | 2021-04-25 | 2021-05-09 23:59 | 2021-11-14 | 2021-11-28 23:59 | [6 empty] | 0 | 0 | [15 empty] | 15.5303 | 0.012507 | 1.23 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 8710 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5355 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019471
2003 | Task(Task)-->C (Construction) | CONTROL CABLE |  | 1.14.3.2 | Unscheduled | No | No | 2021-05-05 09:00 | 2021-05-09 23:59 | 2021-11-24 09:00 | 2021-11-28 23:59 | [6 empty] | 0 | 0 | [15 empty] | 16.0354 | 0.012914 | 1.27 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 9000 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5356 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019472
2004 | Task(Task)-->C (Construction) | EARTHING |  | 1.14.3.2 | Unscheduled | No | No | 2021-05-03 09:00 | 2021-05-09 23:59 | 2021-11-22 09:00 | 2021-11-28 23:59 | [6 empty] | 0 | 0 | [15 empty] | 3.9141 | 0.003152 | 0.31 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 1377 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5357 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019473
2005 | Task(Task)-->C (Construction) | EARTH PIT |  | 1.14.3.2 | Unscheduled | No | No | 2021-07-22 09:00 | 2021-08-04 18:00 | 2022-01-13 09:00 | 2022-01-26 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5358 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019474
2006 | Task(Task)-->C (Construction) | LIGHTING |  | 1.14.3.2 | Unscheduled | No | No | 2021-04-02 09:00 | 2021-04-08 18:00 | 2021-09-24 09:00 | 2021-09-30 18:00 | [6 empty] | 0 | 0 | [15 empty] | 23.8636 | 0.019218 | 1.89 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 194 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5359 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019475
2007 | Task(Task)-->C (Construction) | NON-MOTOR TERMINATION |  | 1.14.3.2 | Unscheduled | No | No | 2021-05-10 09:00 | 2021-05-11 18:00 | 2021-11-29 09:00 | 2021-11-30 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 183 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5362 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019476
2008 | Task(Task)-->C (Construction) | TESTING & CHARGING FOR LOAD & TRIAL OPERATION | 1.14.3.3 | 1.14.3 | Unscheduled | No | No | 2021-05-10 09:00 | 2021-08-26 18:00 | 2021-11-29 09:00 | 2022-03-18 18:00 | [6 empty] | 0 | 0 | [15 empty] | 2.162 | 0.025726 | 2.53 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5363 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019477
2009 | Task(Task)-->C (Construction) | TRANSFORMERS (33KV/6.6KV) |  | 1.14.3.3 | Unscheduled | No | No | 2021-06-28 09:00 | 2021-07-07 18:00 | 2022-01-18 09:00 | 2022-01-27 18:00 | [6 empty] | 0 | 0 | [15 empty] | 19.685 | 0.005064 | 0.5 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5591 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019478
2010 | Task(Task)-->C (Construction) | TRANSFORMERS (6.6KV/415V) |  | 1.14.3.3 | Unscheduled | No | No | 2021-07-28 09:00 | 2021-08-06 18:00 | 2022-02-17 09:00 | 2022-02-26 18:00 | [6 empty] | 0 | 0 | [15 empty] | 19.685 | 0.005064 | 0.5 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5592 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019479
2011 | Task(Task)-->C (Construction) | 33KV SWBD |  | 1.14.3.3 | Unscheduled | No | No | 2021-06-08 09:00 | 2021-06-27 23:59 | 2021-12-29 09:00 | 2022-01-17 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5364 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019480
2012 | Task(Task)-->C (Construction) | 6.6. KV SWBD |  | 1.14.3.3 | Unscheduled | No | No | 2021-07-08 09:00 | 2021-07-27 18:00 | 2022-01-28 09:00 | 2022-02-16 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5365 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019481
2013 | Task(Task)-->C (Construction) | PMCC-2 |  | 1.14.3.3 | Unscheduled | No | No | 2021-08-07 09:00 | 2021-08-26 18:00 | 2022-02-27 | 2022-03-18 18:00 | [6 empty] | 0 | 0 | [15 empty] | 60.6299 | 0.015598 | 1.54 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5366 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019482
2014 | Task(Task)-->C (Construction) | BATTERY, BATTERY CHARGER & UPS |  | 1.14.3.3 | Unscheduled | No | No | 2021-05-10 09:00 | 2021-05-16 23:59 | 2021-11-29 09:00 | 2021-12-05 23:59 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Set | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5556 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019483
2015 | Task(Task)-->E (Engineering) | SUB STATION-3 NEAR KDTP-3 | 1.15 | 1 | Work In Progress | No | No | 2019-11-12 09:00 | 2021-08-29 23:59 | 2019-11-02 09:00 | 2022-02-16 18:00 |  |  | 2019-11-02 10:57 |  |  |  | 62.1273 | 13.5671 | [15 empty] | 2.7774 | 2.7774 | 273.14 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4394 | 0 | 1 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019484
2016 | Task(Task)-->E (Engineering) | ENGINEERING | 1.15.1 | 1.15 | Work In Progress | No | No | 2020-01-31 18:00 | 2020-08-15 17:40 | 2020-04-02 18:00 | 2020-11-04 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 84.6406 | [15 empty] | 4.1299 | 0.1147 | 11.28 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4395 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019485
2017 | Task(Task)-->E (Engineering) | CIVIL | 1.15.1.1 | 1.15.1 | Work In Progress | No | No | 2020-04-17 18:00 | 2020-08-15 17:40 | 2020-05-13 18:00 | 2020-11-04 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 92.8987 | [15 empty] | 71.2329 | 0.081707 | 4.16 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No | 4396 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036117
2018 | Task(Task)-->E (Engineering) | SUBSTATION-3 (SS-KDTP-3) : DESIGN CALCULATION |  | 1.15.1.1 | Completed | No | No | 2020-04-17 18:00 | 2020-06-16 17:40 | 2020-07-10 09:00 | 2020-07-30 18:00 |  |  | 2020-02-21 15:38 | 2020-07-30 20:23 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0027 |  | 2020-02-13 11:43 | 7012-155-PVC-U-094 |  |  |  | A |  |  |  | 47.8261 | 0.039077 | 1.98 | Plan & Actual | Date |  | 0 | 0 | 0 | 737.42 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4401 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-17 18:00 | 2020-05-13 18:00 |  | 10 |  |  |  | 2020-05-05 17:40 | 2020-06-07 23:59 |  | 30 |  |  |  | 2020-05-12 17:40 | 2020-06-10 18:00 |  | 35 |  |  |  | 2020-05-18 23:59 | 2020-06-17 18:00 |  | 65 | 2020-07-30 19:29 |  |  | 2020-05-25 17:40 | 2020-07-08 18:00 |  | 80 | 2020-07-30 20:20 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-16 17:40 | 2020-07-22 18:00 |  | 100 | 2020-07-30 20:23 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 195 |  |  |  | 101205
2019 | Task(Task)-->E (Engineering) | SUBSTATION-3 (SS-KDTP-3) : NUM & RC DETAILS (SHT 1) |  | 1.15.1.1 | Completed | No | No | 2020-04-17 18:00 | 2020-06-16 17:40 | 2020-07-10 09:00 | 2020-07-30 18:00 |  |  | 2020-02-21 15:38 | 2020-07-30 20:24 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-NR-0040 |  | 2020-02-13 11:43 | 7012-155-PVC-C-095 |  |  |  | A |  |  |  | 15.942 | 0.013026 | 0.66 | Plan & Actual | Date |  | 0 | 0 | 0 | 245.42 | 0 | 2.15 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4397 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-17 18:00 | 2020-05-13 18:00 |  | 10 |  |  |  | 2020-05-05 17:40 | 2020-06-07 23:59 |  | 30 |  |  |  | 2020-05-12 17:40 | 2020-06-10 18:00 |  | 35 | 2020-07-11 06:31 |  |  | 2020-05-18 23:59 | 2020-06-17 18:00 |  | 65 | 2020-07-30 19:30 |  |  | 2020-05-25 17:40 | 2020-07-08 18:00 |  | 80 | 2020-07-30 19:38 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-16 17:40 | 2020-07-22 18:00 |  | 100 | 2020-07-30 20:24 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 196 |  |  |  | 101206
2020 | Task(Task)-->E (Engineering) | SUBSTATION-3 (SS-KDTP-3) : NUM & RC DETAILS (SHT 2) |  | 1.15.1.1 | Completed | No | No | 2020-04-17 18:00 | 2020-06-16 17:40 | 2020-07-10 09:00 | 2020-07-30 18:00 |  |  | 2020-02-21 15:38 | 2020-07-30 20:25 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-NR-0041 |  | 2020-02-13 11:43 | 7012-155-PVC-C-096 |  |  |  | A |  |  |  | 15.942 | 0.013026 | 0.66 | Plan & Actual | Date |  | 0 | 0 | 0 | 245.42 | 0 | 2.1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4398 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-17 18:00 | 2020-05-13 18:00 |  | 10 |  |  |  | 2020-05-05 17:40 | 2020-06-07 23:59 |  | 30 |  |  |  | 2020-05-12 17:40 | 2020-06-10 18:00 |  | 35 | 2020-07-10 13:29 |  |  | 2020-05-18 23:59 | 2020-06-17 18:00 |  | 65 | 2020-07-11 08:03 |  |  | 2020-05-25 17:40 | 2020-07-08 18:00 |  | 80 | 2020-07-30 19:34 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-16 17:40 | 2020-07-22 18:00 |  | 100 | 2020-07-11 08:03 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 197 |  |  |  | 101207
2021 | Task(Task)-->E (Engineering) | SUBSTATION-3 (SS-KDTP-3) : NUM & RC DETAILS (SHT 3) |  | 1.15.1.1 | Unscheduled | No | No | 2020-04-17 18:00 | 2020-06-16 17:40 | 2020-05-13 18:00 | 2020-11-04 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-NR-0042 |  | 2020-02-13 11:43 | 7012-155-PVC-C-097 |  |  |  | A |  |  |  | 15.942 | 0.013026 | 0.66 | Plan & Actual | Date |  | 0 | 0 | 0 | 245.42 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4399 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-17 18:00 | 2020-05-13 18:00 |  | 10 |  |  |  | 2020-05-05 17:40 | 2020-06-07 23:59 |  | 30 |  |  |  | 2020-05-12 17:40 | 2020-06-10 18:00 |  | 35 | 2020-09-30 12:07 |  |  | 2020-05-18 23:59 | 2020-06-17 18:00 |  | 65 | 2020-09-30 21:53 |  |  | 2020-05-25 17:40 | 2020-07-08 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-16 17:40 | 2020-07-22 18:00 |  | 100 | [122 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 198 |  |  |  | 101208
2022 | Task(Task)-->E (Engineering) | ARCHITECTURAL GA OF SUBSTATION-3 (SS-KDTP-3) |  | 1.15.1.1 | Unscheduled | No | No | 2020-06-16 18:00 | 2020-08-15 17:40 | 2020-06-27 18:00 | 2020-10-05 18:00 |  |  | 2020-02-21 15:39 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-AR-0013 |  | 2020-02-13 11:43 | 7012-155-PVC-C-119 |  |  |  | A |  |  |  | 4.3478 | 0.003552 | 0.18 | Plan & Actual | Date |  | 0 | 0 | 0 | 68.01 | 0 | 74 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4400 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-06-16 18:00 | 2020-06-27 18:00 |  | 10 |  |  |  | 2020-07-04 17:40 | 2020-07-22 18:00 |  | 30 |  |  |  | 2020-07-10 17:40 | 2020-07-25 18:00 |  | 35 | 2020-09-14 13:24 |  |  | 2020-07-17 23:59 | 2020-08-01 18:00 |  | 65 | 2020-09-14 13:47 |  |  | 2020-07-23 17:40 | 2020-08-22 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-08-15 17:40 | 2020-09-05 18:00 |  | 100 | [122 empty] | Chetan Khodke |  |  |  |  | A - Architecture | [16 empty] | 220 |  |  |  | 101230
2023 | Task(Task)-->E (Engineering) | ELECTRICAL | 1.15.1.2 | 1.15.1 | Unscheduled | No | No | 2020-01-31 18:00 | 2020-04-23 17:40 | 2020-04-02 18:00 | 2020-09-22 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 64.192 | [15 empty] | 28.7671 | 0.032997 | 1.68 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No | 4402 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036118
2024 | Task(Task)-->E (Engineering) | SUBSTATION-3 (SS-3) NEAR KDTP-3 EQUIPMENT, CABLE ROUTING,EARTHING & LIGHTNING LAYOUT WITH PLAN & SECTIONAL VIEW & BOM. |  | 1.15.1.2 | Unscheduled | No | No | 2020-01-31 18:00 | 2020-03-27 17:40 | 2020-04-02 18:00 | 2020-05-22 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5062 |  | 2020-02-13 11:44 | 7012-155-PVE-F-024 |  |  |  | A |  |  |  | 40.1198 | 0.013238 | 0.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 248.42 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4403 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-31 18:00 | 2020-04-02 18:00 |  | 10 | 2020-04-02 23:31 |  |  | 2020-02-15 17:40 | 2020-04-16 18:00 |  | 30 | 2020-04-15 23:31 |  |  | 2020-02-21 17:40 | 2020-04-23 18:00 |  | 35 | 2020-04-21 23:31 |  |  | 2020-02-28 23:59 | 2020-04-30 18:00 |  | 65 | 2020-04-21 23:31 |  |  | 2020-03-05 17:40 | 2020-05-21 18:00 |  | 80 | 2020-05-01 23:31 | [5 empty] | 80 | 2020-08-27 18:50 | [5 empty] | 80 | 2020-08-27 18:50 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-27 17:40 | 2020-05-22 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 259 |  |  |  | 101270
2025 | Task(Task)-->E (Engineering) | LIGHTING LAYOUT PLAN WITH POWER DISTRIBUTION ARRANGEMENT, SECTIONAL VIEW, BOM OF SS-3 |  | 1.15.1.2 | Unscheduled | No | No | 2020-02-24 18:00 | 2020-04-14 17:40 | 2020-05-30 09:00 | 2020-07-15 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5073 |  | 2020-02-13 11:44 | 7012-155-PVE-G-035 |  |  |  | A |  |  |  | 40.1198 | 0.013238 | 0.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 248.42 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4404 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-24 18:00 | 2020-06-03 18:00 |  | 10 | 2020-05-25 23:31 |  |  | 2020-03-03 17:40 | 2020-06-10 18:00 |  | 30 | 2020-05-25 23:31 |  |  | 2020-03-09 17:40 | 2020-06-17 18:00 |  | 35 | 2020-05-25 23:31 |  |  | 2020-03-16 23:59 | 2020-06-24 18:00 |  | 65 | 2020-05-30 23:31 |  |  | 2020-03-21 17:40 | 2020-07-15 18:00 |  | 80 | 2020-06-17 13:15 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-14 17:40 | 2020-07-15 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 270 |  |  |  | 101281
2026 | Task(Task)-->E (Engineering) | GA, SLD & BOM FOR 415V LT CHP PMCC-3 |  | 1.15.1.2 | Unscheduled | No | No | 2020-03-12 17:40 | 2020-04-23 17:40 | 2020-05-21 18:00 | 2020-09-22 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-157 |  | 2020-02-13 11:46 | 7012-155-PVE-W-102 |  |  |  | A |  |  |  | 19.7605 | 0.00652 | 0.33 | Plan & Actual | Date |  | 0 | 0 | 0 | 124.21 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4434 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-12 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-12 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-03-19 17:40 | 2020-06-03 18:00 |  | 35 |  |  |  | 2020-03-25 23:59 | 2020-06-03 18:00 |  | 65 |  |  |  | 2020-04-01 17:40 | 2020-06-24 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-23 17:40 | 2020-06-24 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 337 |  |  |  | 101348
2027 | Task(Task)-->P (Procurement) | PROCUREMENT | 1.15.2 | 1.15 | Work In Progress | No | No | 2019-11-12 09:00 | 2021-03-31 18:00 | 2019-11-02 09:00 | 2021-10-24 23:59 |  |  | 2019-11-02 10:57 |  |  |  | 78.6968 | 18.9727 | [15 empty] | 53.0846 | 1.4744 | 144.99 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4438 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019488
2028 | Task(Task)-->P (Procurement) | PURCHASE REQUISITION | 1.15.2.1 | 1.15.2 | Work In Progress | No | No | 2019-11-12 09:00 | 2020-06-25 18:00 | 2019-11-02 09:00 | 2020-04-18 18:00 |  |  | 2019-11-02 10:57 |  |  |  | 100 | 78.022 | [15 empty] | 5 | 0.073719 | 7.25 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4439 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019489
2029 | Task(Task)-->P (Procurement) | 33/6.9KV HT TRANSFORMER (ONAN TYPE) |  | 1.15.2.1 | Completed | No | No | 2019-11-28 09:00 | 2019-11-28 18:00 | 2020-01-17 09:00 | 2020-01-17 18:00 |  |  | 2020-01-22 10:57 | 2020-01-22 10:57 |  |  | 100 | 100 | [15 empty] | 14.011 | 0.010329 | 1.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4440 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019490
2030 | Task(Task)-->P (Procurement) | HT SWITCHGEAR (33KV & 6.6KV) |  | 1.15.2.1 | Completed | No | No | 2019-11-13 09:00 | 2019-11-13 18:00 | 2019-11-02 09:00 | 2019-11-02 18:00 |  |  | 2019-11-02 10:57 | 2019-11-02 10:57 |  |  | 100 | 100 | [15 empty] | 18.544 | 0.01367 | 1.35 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4441 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019491
2031 | Task(Task)-->P (Procurement) | 6.6KV HT VFD with Motors |  | 1.15.2.1 | Completed | No | No | 2019-12-30 09:00 | 2019-12-30 18:00 | 2020-01-24 09:00 | 2020-01-24 18:00 |  |  | 2019-11-21 10:57 | 2019-11-21 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4442 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019492
2032 | Task(Task)-->P (Procurement) | 6.6KV HT APFC PANEL |  | 1.15.2.1 | Completed | No | No | 2020-01-24 09:00 | 2020-01-24 18:00 | 2020-02-13 09:00 | 2020-02-13 18:00 |  |  | 2020-02-13 10:57 | 2020-02-13 10:57 |  |  | 100 | 100 | [15 empty] | 1.6484 | 0.001215 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4443 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019493
2033 | Task(Task)-->P (Procurement) | 6.6KV/0.433V LT TRANSFORMER |  | 1.15.2.1 | Completed | No | No | 2019-11-25 09:00 | 2019-11-25 18:00 | 2020-01-22 09:00 | 2020-01-22 18:00 |  |  | 2020-01-22 15:37 | 2020-01-22 15:37 |  |  | 100 | 100 | [15 empty] | 7.0055 | 0.005164 | 0.51 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4444 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019494
2034 | Task(Task)-->P (Procurement) | LT BUSDUCT |  | 1.15.2.1 | Completed | No | No | 2019-12-02 09:00 | 2019-12-02 18:00 | 2019-12-11 09:00 | 2019-12-11 18:00 |  |  | 2019-12-11 15:44 | 2019-12-11 15:44 |  |  | 100 | 100 | [15 empty] | 2.1978 | 0.00162 | 0.16 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4445 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019495
2035 | Task(Task)-->P (Procurement) | 415V MCC |  | 1.15.2.1 | Unscheduled | No | No | 2019-11-28 09:00 | 2019-11-28 18:00 | 2019-11-14 09:00 | 2019-11-14 18:00 | [6 empty] | 100 | 0 | [15 empty] | 14.1484 | 0.01043 | 1.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4446 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019496
2036 | Task(Task)-->P (Procurement) | 110V DC BATTERY & BATTERY CHARGER SYSTEM |  | 1.15.2.1 | Completed | No | No | 2020-01-13 09:00 | 2020-01-13 18:00 | 2020-01-13 09:00 | 2020-01-13 18:00 |  |  | 2020-01-13 10:57 | 2020-01-13 10:57 |  |  | 100 | 100 | [15 empty] | 4.6703 | 0.003443 | 0.34 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4447 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019497
2037 | Task(Task)-->P (Procurement) | 6.6KV NEUTRAL GROUNDING RESISTOR |  | 1.15.2.1 | Completed | No | No | 2019-12-12 09:00 | 2019-12-12 18:00 | 2019-12-12 09:00 | 2019-12-12 18:00 |  |  | 2019-12-12 15:21 | 2019-12-12 15:22 |  |  | 100 | 100 | [15 empty] | 0.41209 | 0.000304 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4448 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019498
2038 | Task(Task)-->P (Procurement) | PLC SYSTEM |  | 1.15.2.1 | Completed | No | No | 2019-11-12 09:00 | 2019-11-12 18:00 | 2019-11-12 09:00 | 2019-11-12 18:00 |  |  | 2019-11-12 10:57 | 2019-11-12 10:57 |  |  | 100 | 100 | [15 empty] | 10.0275 | 0.007392 | 0.73 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4449 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019499
2039 | Task(Task)-->P (Procurement) | UPS SYSTEM |  | 1.15.2.1 | Completed | No | No | 2020-01-08 09:00 | 2020-01-08 18:00 | 2020-02-19 09:00 | 2020-02-19 18:00 |  |  | 2020-02-19 10:57 | 2020-02-19 10:57 |  |  | 100 | 100 | [15 empty] | 2.0604 | 0.001519 | 0.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4450 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019500
2040 | Task(Task)-->P (Procurement) | 24V DC BATTERY AND BATTERY CHARGER SYSTEM |  | 1.15.2.1 | Completed | No | No | 2020-01-27 09:00 | 2020-01-27 18:00 | 2020-02-26 09:00 | 2020-02-26 18:00 |  |  | 2020-02-26 10:57 | 2020-02-26 10:57 |  |  | 100 | 100 | [15 empty] | 0.96154 | 0.000709 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4451 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019501
2041 | Task(Task)-->P (Procurement) | FDA SYSTEM |  | 1.15.2.1 | Completed | No | No | 2020-02-14 09:00 | 2020-02-14 18:00 | 2020-02-17 09:00 | 2020-02-17 18:00 |  |  | 2020-02-17 10:57 | 2020-02-17 10:57 |  |  | 100 | 100 | [15 empty] | 6.7308 | 0.004962 | 0.49 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4452 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019502
2042 | Task(Task)-->P (Procurement) | SCADA |  | 1.15.2.1 | Completed | No | No | 2019-12-10 09:00 | 2019-12-10 18:00 | 2019-12-21 09:00 | 2019-12-21 18:00 |  |  | 2019-12-21 10:57 | 2019-12-21 10:57 |  |  | 100 | 100 | [15 empty] | 3.1593 | 0.002329 | 0.23 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4453 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019503
2043 | Task(Task)-->P (Procurement) | RUBBER MATS |  | 1.15.2.1 | Completed | No | No | 2020-06-25 09:00 | 2020-06-25 18:00 | 2020-04-18 09:00 | 2020-04-18 18:00 |  |  | 2020-04-18 10:57 | 2020-04-18 10:57 |  |  | 100 | 100 | [15 empty] | 0.13736 | 0.000101 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4456 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019504
2044 | Task(Task)-->P (Procurement) | MAIN LIGHTING DISTRIBUTION BOARD |  | 1.15.2.1 | Completed | No | No | 2020-02-04 09:00 | 2020-02-04 18:00 | 2020-04-02 09:00 | 2020-04-02 18:00 |  |  | 2020-04-02 17:08 | 2020-04-02 17:08 |  |  | 100 | 100 | [15 empty] | 0.68681 | 0.000506 | 0.05 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4457 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019505
2045 | Task(Task)-->P (Procurement) | LIGHTING PANELS |  | 1.15.2.1 | Unscheduled | No | No | 2020-02-28 09:00 | 2020-02-28 18:00 | 2020-04-02 09:00 | 2020-04-02 18:00 | [6 empty] | 100 | 0 | [15 empty] | 7.8297 | 0.005772 | 0.57 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4458 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019506
2046 | Task(Task)-->P (Procurement) | DCDB & DC FUSE BOARD |  | 1.15.2.1 | Completed | No | No | 2020-01-28 09:00 | 2020-01-28 18:00 | 2020-04-02 09:00 | 2020-04-02 18:00 |  |  | 2020-04-02 16:54 | 2020-04-02 16:54 |  |  | 100 | 100 | [15 empty] | 2.8846 | 0.002127 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4459 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019507
2047 | Task(Task)-->P (Procurement) | UPS DB,ACDB,MCBDB & AFB |  | 1.15.2.1 | Completed | No | No | 2020-03-18 09:00 | 2020-03-18 18:00 | 2020-04-02 09:00 | 2020-04-02 18:00 |  |  | 2020-04-02 17:02 | 2020-04-02 17:02 |  |  | 100 | 100 | [15 empty] | 2.8846 | 0.002127 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4460 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019508
2048 | Task(Task)-->P (Procurement) | TECHNICAL CLEARANCE | 1.15.2.2 | 1.15.2 | Work In Progress | No | No | 2019-11-13 09:00 | 2020-07-20 18:00 | 2019-11-02 09:00 | 2020-07-10 18:00 |  |  | 2019-11-04 14:47 |  |  |  | 100 | 77.0602 | [15 empty] | 5 | 0.073719 | 7.25 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4461 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019509
2049 | Task(Task)-->P (Procurement) | 33/6.9KV HT TRANSFORMER (ONAN TYPE) |  | 1.15.2.2 | Completed | No | No | 2019-11-29 09:00 | 2019-12-22 23:59 | 2020-01-17 09:00 | 2020-02-17 18:00 |  |  | 2020-03-16 10:57 | 2020-03-16 10:57 |  |  | 100 | 100 | [15 empty] | 14.011 | 0.010329 | 1.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4462 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019510
2050 | Task(Task)-->P (Procurement) | HT SWITCHGEAR (33KV & 6.6KV) |  | 1.15.2.2 | Completed | No | No | 2019-11-14 09:00 | 2019-12-13 18:00 | 2019-11-02 09:00 | 2020-03-10 18:00 |  |  | 2019-11-04 14:47 | 2020-03-10 14:47 |  |  | 100 | 100 | [15 empty] | 18.544 | 0.01367 | 1.35 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4463 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019511
2051 | Task(Task)-->P (Procurement) | 6.6KV HT VFD with Motors |  | 1.15.2.2 | Completed | No | No | 2019-12-31 09:00 | 2020-01-29 18:00 | 2020-01-24 09:00 | 2020-04-16 18:00 |  |  | 2020-02-26 10:57 | 2020-02-26 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4464 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019512
2052 | Task(Task)-->P (Procurement) | 6.6KV HT APFC PANEL |  | 1.15.2.2 | Completed | No | No | 2020-01-25 09:00 | 2020-02-16 23:59 | 2020-02-13 09:00 | 2020-04-28 18:00 |  |  | 2020-04-28 10:57 | 2020-04-28 10:57 |  |  | 100 | 100 | [15 empty] | 1.6484 | 0.001215 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4465 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019513
2053 | Task(Task)-->P (Procurement) | 6.6KV/0.433V LT TRANSFORMER |  | 1.15.2.2 | Completed | No | No | 2019-11-26 09:00 | 2019-12-20 18:00 | 2020-01-22 09:00 | 2020-03-16 18:00 |  |  | 2020-01-23 15:39 | 2020-03-16 15:39 |  |  | 100 | 100 | [15 empty] | 7.0055 | 0.005164 | 0.51 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4466 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019514
2054 | Task(Task)-->P (Procurement) | LT BUSDUCT |  | 1.15.2.2 | Completed | No | No | 2019-12-03 09:00 | 2020-01-03 18:00 | 2019-12-11 09:00 | 2020-03-10 18:00 |  |  | 2019-12-12 15:46 | 2020-03-10 15:46 |  |  | 100 | 100 | [15 empty] | 2.1978 | 0.00162 | 0.16 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4467 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019515
2055 | Task(Task)-->P (Procurement) | 415V MCC |  | 1.15.2.2 | Unscheduled | No | No | 2019-11-29 09:00 | 2020-01-11 18:00 | 2019-11-14 09:00 | 2020-03-11 18:00 | [6 empty] | 100 | 0 | [15 empty] | 14.1484 | 0.01043 | 1.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4468 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019516
2056 | Task(Task)-->P (Procurement) | 110V DC BATTERY & BATTERY CHARGER SYSTEM |  | 1.15.2.2 | Completed | No | No | 2020-01-14 09:00 | 2020-02-03 18:00 | 2020-01-13 09:00 | 2020-06-04 18:00 |  |  | 2020-01-14 17:10 | 2020-06-04 17:10 |  |  | 100 | 100 | [15 empty] | 4.6703 | 0.003443 | 0.34 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4469 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019517
2057 | Task(Task)-->P (Procurement) | 6.6KV NEUTRAL GROUNDING RESISTOR |  | 1.15.2.2 | Completed | No | No | 2019-12-13 09:00 | 2019-12-31 18:00 | 2019-12-12 09:00 | 2020-01-21 18:00 |  |  | 2019-12-13 15:23 | 2020-01-21 15:24 |  |  | 100 | 100 | [15 empty] | 0.41209 | 0.000304 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4470 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019518
2058 | Task(Task)-->P (Procurement) | PLC SYSTEM |  | 1.15.2.2 | Completed | No | No | 2019-11-13 09:00 | 2019-12-04 18:00 | 2019-11-12 09:00 | 2020-03-16 18:00 |  |  | 2020-03-16 10:57 | 2020-03-16 10:57 |  |  | 100 | 100 | [15 empty] | 10.0275 | 0.007392 | 0.73 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4471 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019519
2059 | Task(Task)-->P (Procurement) | UPS SYSTEM |  | 1.15.2.2 | Completed | No | No | 2020-01-09 09:00 | 2020-01-28 18:00 | 2020-02-19 09:00 | 2020-06-06 18:00 |  |  | 2020-06-06 10:57 | 2020-06-06 10:57 |  |  | 100 | 100 | [15 empty] | 2.0604 | 0.001519 | 0.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4472 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019520
2060 | Task(Task)-->P (Procurement) | 24V DC BATTERY AND BATTERY CHARGER SYSTEM |  | 1.15.2.2 | Unscheduled | No | No | 2020-01-28 09:00 | 2020-02-07 18:00 | 2020-02-26 09:00 | 2020-07-10 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.96154 | 0.000709 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4473 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019521
2061 | Task(Task)-->P (Procurement) | FDA SYSTEM |  | 1.15.2.2 | Completed | No | No | 2020-02-15 09:00 | 2020-03-12 18:00 | 2020-02-17 09:00 | 2020-06-10 18:00 |  |  | 2020-06-10 10:57 | 2020-06-10 10:57 |  |  | 100 | 100 | [15 empty] | 6.7308 | 0.004962 | 0.49 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4474 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019522
2062 | Task(Task)-->P (Procurement) | SCADA |  | 1.15.2.2 | Completed | No | No | 2019-12-11 09:00 | 2020-01-15 18:00 | 2019-12-21 09:00 | 2020-03-16 18:00 |  |  | 2020-03-16 10:57 | 2020-03-16 10:57 |  |  | 100 | 100 | [15 empty] | 3.1593 | 0.002329 | 0.23 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4475 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019523
2063 | Task(Task)-->P (Procurement) | RUBBER MATS |  | 1.15.2.2 | Completed | No | No | 2020-06-26 09:00 | 2020-07-20 18:00 | 2020-04-18 09:00 | 2020-04-20 18:00 |  |  | 2020-04-20 10:57 | 2020-04-20 10:57 |  |  | 100 | 100 | [15 empty] | 0.13736 | 0.000101 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4478 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019524
2064 | Task(Task)-->P (Procurement) | MAIN LIGHTING DISTRIBUTION BOARD |  | 1.15.2.2 | Completed | No | No | 2020-02-05 09:00 | 2020-04-02 18:00 | 2020-04-02 09:00 | 2020-07-01 18:00 |  |  | 2020-04-03 17:08 | 2020-07-01 17:08 |  |  | 100 | 100 | [15 empty] | 0.68681 | 0.000506 | 0.05 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4479 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019525
2065 | Task(Task)-->P (Procurement) | LIGHTING PANELS |  | 1.15.2.2 | Unscheduled | No | No | 2020-02-29 09:00 | 2020-05-11 18:00 | 2020-04-02 09:00 | 2020-07-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 7.8297 | 0.005772 | 0.57 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4480 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019526
2066 | Task(Task)-->P (Procurement) | DCDB & DC FUSE BOARD |  | 1.15.2.2 | Completed | No | No | 2020-01-29 09:00 | 2020-04-02 18:00 | 2020-04-02 09:00 | 2020-07-01 18:00 |  |  | 2020-04-03 16:59 | 2020-07-01 16:59 |  |  | 100 | 100 | [15 empty] | 2.8846 | 0.002127 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4481 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019527
2067 | Task(Task)-->P (Procurement) | UPS DB,ACDB,MCBDB & AFB |  | 1.15.2.2 | Completed | No | No | 2020-03-19 09:00 | 2020-04-02 18:00 | 2020-04-02 09:00 | 2020-07-01 18:00 |  |  | 2020-04-03 17:03 | 2020-07-01 17:03 |  |  | 100 | 100 | [15 empty] | 2.8846 | 0.002127 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4482 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019528
2068 | Task(Task)-->P (Procurement) | ORDERING | 1.15.2.3 | 1.15.2 | Work In Progress | No | No | 2019-12-05 09:00 | 2020-07-25 18:00 | 2020-01-21 09:00 | 2020-08-13 18:00 |  |  | 2020-01-04 08:00 |  |  |  | 100 | 68.2318 | [15 empty] | 10 | 0.14744 | 14.5 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4483 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019529
2069 | Task(Task)-->P (Procurement) | 33/6.9KV HT TRANSFORMER (ONAN TYPE) |  | 1.15.2.3 | Completed | No | No | 2019-12-23 09:00 | 2020-01-15 18:00 | 2020-02-17 09:00 | 2020-06-24 18:00 |  |  | 2020-07-16 22:28 | 2020-07-16 22:28 |  |  | 100 | 100 | [15 empty] | 14.0193 | 0.02067 | 2.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4484 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019530
2070 | Task(Task)-->P (Procurement) | HT SWITCHGEAR (33KV & 6.6KV) |  | 1.15.2.3 | Completed | No | No | 2019-12-14 09:00 | 2020-01-13 18:00 | 2020-03-10 09:00 | 2020-07-18 18:00 |  |  | 2020-03-11 14:49 | 2020-07-04 14:49 |  |  | 100 | 100 | [15 empty] | 18.6464 | 0.027492 | 2.7 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4485 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019531
2071 | Task(Task)-->P (Procurement) | 6.6KV HT VFD with Motors |  | 1.15.2.3 | Completed | No | No | 2020-01-30 09:00 | 2020-02-28 18:00 | 2020-04-16 09:00 | 2020-07-18 18:00 |  |  | 2020-04-29 10:57 | 2020-04-29 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4486 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019532
2072 | Task(Task)-->P (Procurement) | 6.6KV HT APFC PANEL |  | 1.15.2.3 | Completed | No | No | 2020-02-17 09:00 | 2020-03-10 18:00 | 2020-04-28 09:00 | 2020-07-28 18:00 |  |  | 2020-05-04 15:17 | 2020-07-10 15:17 |  |  | 100 | 100 | [15 empty] | 1.6575 | 0.002444 | 0.24 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4487 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019533
2073 | Task(Task)-->P (Procurement) | 6.6KV/0.433V LT TRANSFORMER |  | 1.15.2.3 | Completed | No | No | 2019-12-21 09:00 | 2020-01-15 18:00 | 2020-03-16 09:00 | 2020-06-23 18:00 |  |  | 2020-06-23 10:14 | 2020-06-23 10:14 |  |  | 100 | 100 | [15 empty] | 7.0442 | 0.010386 | 1.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4488 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019534
2074 | Task(Task)-->P (Procurement) | LT BUSDUCT |  | 1.15.2.3 | Completed | No | No | 2020-01-04 09:00 | 2020-02-04 18:00 | 2020-03-10 09:00 | 2020-06-11 18:00 |  |  | 2020-01-04 08:00 | 2020-04-27 15:47 |  |  | 100 | 100 | [15 empty] | 2.1409 | 0.003156 | 0.31 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4489 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019535
2075 | Task(Task)-->P (Procurement) | 415V MCC |  | 1.15.2.3 | Unscheduled | No | No | 2020-01-12 | 2020-02-25 18:00 | 2020-03-11 09:00 | 2020-07-04 18:00 | [6 empty] | 100 | 0 | [15 empty] | 14.2956 | 0.021077 | 2.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4490 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019536
2076 | Task(Task)-->P (Procurement) | 110V DC BATTERY & BATTERY CHARGER SYSTEM |  | 1.15.2.3 | Completed | No | No | 2020-02-04 09:00 | 2020-02-24 18:00 | 2020-06-04 09:00 | 2020-07-18 18:00 |  |  | 2020-06-05 17:10 | 2020-07-06 17:10 |  |  | 100 | 100 | [15 empty] | 4.6271 | 0.006822 | 0.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4491 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019537
2077 | Task(Task)-->P (Procurement) | 6.6KV NEUTRAL GROUNDING RESISTOR |  | 1.15.2.3 | Completed | No | No | 2020-01-01 09:00 | 2020-01-20 18:00 | 2020-01-21 09:00 | 2020-03-19 18:00 |  |  | 2020-03-19 10:20 | 2020-03-19 10:21 |  |  | 100 | 100 | [15 empty] | 0.41436 | 0.000611 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4492 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019538
2078 | Task(Task)-->P (Procurement) | PLC SYSTEM |  | 1.15.2.3 | Completed | No | No | 2019-12-05 09:00 | 2019-12-27 18:00 | 2020-03-16 09:00 | 2020-07-07 18:00 |  |  | 2020-03-16 17:20 | 2020-06-04 17:21 |  |  | 100 | 100 | [15 empty] | 10.0829 | 0.014866 | 1.46 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4493 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019539
2079 | Task(Task)-->P (Procurement) | UPS SYSTEM |  | 1.15.2.3 | Unscheduled | No | No | 2020-01-29 09:00 | 2020-02-18 18:00 | 2020-06-06 09:00 | 2020-07-31 18:00 | [6 empty] | 100 | 0 | [15 empty] | 2.0028 | 0.002953 | 0.29 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4494 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019540
2080 | Task(Task)-->P (Procurement) | 24V DC BAT TERY AND BATTERY CHARGER SYSTEM |  | 1.15.2.3 | Unscheduled | No | No | 2020-02-08 09:00 | 2020-02-19 18:00 | 2020-07-10 09:00 | 2020-08-07 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.96685 | 0.001426 | 0.14 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4495 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019541
2081 | Task(Task)-->P (Procurement) | FDA SYSTEM |  | 1.15.2.3 | Unscheduled | No | No | 2020-03-13 09:00 | 2020-04-08 18:00 | 2020-06-10 09:00 | 2020-08-06 18:00 | [6 empty] | 100 | 0 | [15 empty] | 6.6989 | 0.009877 | 0.97 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4496 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019542
2082 | Task(Task)-->P (Procurement) | SCADA |  | 1.15.2.3 | Completed | No | No | 2020-01-16 09:00 | 2020-02-20 18:00 | 2020-03-16 09:00 | 2020-06-24 18:00 |  |  | 2020-06-24 10:20 | 2020-06-24 10:20 |  |  | 100 | 100 | [15 empty] | 3.1077 | 0.004582 | 0.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4497 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019543
2083 | Task(Task)-->P (Procurement) | RUBBER MATS |  | 1.15.2.3 | Completed | No | No | 2020-07-21 09:00 | 2020-07-25 18:00 | 2020-04-20 09:00 | 2020-06-06 18:00 |  |  | 2020-04-25 10:57 | 2020-04-25 10:57 |  |  | 100 | 100 | [15 empty] | 0.13812 | 0.000204 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4500 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019544
2084 | Task(Task)-->P (Procurement) | MAIN LIGHTING DISTRIBUTION BOARD |  | 1.15.2.3 | Completed | No | No | 2020-04-03 09:00 | 2020-04-18 18:00 | 2020-07-01 09:00 | 2020-08-13 18:00 |  |  | 2020-07-02 17:08 | 2020-07-07 17:08 |  |  | 100 | 100 | [15 empty] | 0.69061 | 0.001018 | 0.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4501 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019545
2085 | Task(Task)-->P (Procurement) | LIGHTING PANELS |  | 1.15.2.3 | Unscheduled | No | No | 2020-05-12 09:00 | 2020-06-25 18:00 | 2020-07-01 09:00 | 2020-08-13 18:00 | [6 empty] | 100 | 0 | [15 empty] | 7.8039 | 0.011506 | 1.13 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4502 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019546
2086 | Task(Task)-->P (Procurement) | DCDB & DC FUSE BOARD |  | 1.15.2.3 | Completed | No | No | 2020-04-03 09:00 | 2020-04-18 18:00 | 2020-07-01 09:00 | 2020-08-13 18:00 |  |  | 2020-07-02 17:00 | 2020-07-07 17:00 |  |  | 100 | 100 | [15 empty] | 2.8315 | 0.004175 | 0.41 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4503 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019547
2087 | Task(Task)-->P (Procurement) | UPS DB,ACDB,MCBDB & AFB |  | 1.15.2.3 | Completed | No | No | 2020-04-03 09:00 | 2020-04-18 18:00 | 2020-07-01 09:00 | 2020-08-13 18:00 |  |  | 2020-07-02 17:05 | 2020-07-07 17:05 |  |  | 100 | 100 | [15 empty] | 2.8315 | 0.004175 | 0.41 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4504 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019548
2088 | Task(Task)-->P (Procurement) | ITP APPROVAL | 1.15.2.4 | 1.15.2 | Work In Progress | No | No | 2019-12-28 09:00 | 2020-09-03 18:00 | 2020-06-05 09:00 | 2020-10-30 18:00 |  |  | 2020-06-05 08:54 |  |  |  | 100 | 14.4237 | [15 empty] | 5 | 0.073719 | 7.25 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4505 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019549
2089 | Task(Task)-->P (Procurement) | 33/6.9KV HT TRANSFORMER (ONAN TYPE) |  | 1.15.2.4 | Completed | No | No | 2020-01-16 09:00 | 2020-02-24 18:00 | 2020-07-03 09:00 | 2020-07-15 18:00 |  |  | 2020-07-03 08:47 | 2020-07-15 08:47 |  |  | 100 | 100 | [15 empty] | 14.011 | 0.010329 | 1.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4506 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019550
2090 | Task(Task)-->P (Procurement) | HT SWITCHGEAR (33KV & 6.6KV) |  | 1.15.2.4 | Unscheduled | No | No | 2020-01-14 09:00 | 2020-02-22 18:00 | 2020-08-06 09:00 | 2020-10-20 18:00 |  |  | 2020-07-13 10:49 |  |  |  | 100 | 0 | [15 empty] | 18.544 | 0.01367 | 1.35 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4507 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019551
2091 | Task(Task)-->P (Procurement) | 6.6KV HT VFD with Motors |  | 1.15.2.4 | Unscheduled | No | No | 2020-02-29 09:00 | 2020-04-08 18:00 | 2020-08-01 09:00 | 2020-09-09 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4508 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019552
2092 | Task(Task)-->P (Procurement) | 6.6KV HT APFC PANEL |  | 1.15.2.4 | Unscheduled | No | No | 2020-03-11 09:00 | 2020-04-19 23:59 | 2020-08-01 09:00 | 2020-09-09 18:00 | [6 empty] | 100 | 0 | [15 empty] | 1.6484 | 0.001215 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4509 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019553
2093 | Task(Task)-->P (Procurement) | 6.6KV/0.433V LT TRANSFORMER |  | 1.15.2.4 | Unscheduled | No | No | 2020-01-16 09:00 | 2020-02-24 18:00 | 2020-08-05 09:00 | 2020-10-10 18:00 | [6 empty] | 100 | 0 | [15 empty] | 7.0055 | 0.005164 | 0.51 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4510 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019554
2094 | Task(Task)-->P (Procurement) | LT BUSDUCT |  | 1.15.2.4 | Unscheduled | No | No | 2020-02-05 09:00 | 2020-03-15 23:59 | 2020-09-21 09:00 | 2020-10-20 18:00 |  |  | 2020-09-21 17:35 |  |  |  | 100 | 0 | [15 empty] | 2.1978 | 0.00162 | 0.16 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4511 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019555
2095 | Task(Task)-->P (Procurement) | 415V MCC |  | 1.15.2.4 | Unscheduled | No | No | 2020-02-26 09:00 | 2020-04-05 23:59 | 2020-08-01 09:00 | 2020-09-09 18:00 | [6 empty] | 100 | 0 | [15 empty] | 14.1484 | 0.01043 | 1.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4512 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019556
2096 | Task(Task)-->P (Procurement) | 110V DC BATTERY & BATTERY CHARGER SYSTEM |  | 1.15.2.4 | Unscheduled | No | No | 2020-02-25 09:00 | 2020-04-04 18:00 | 2020-07-07 09:00 | 2020-10-10 18:00 |  |  | 2020-07-07 10:31 |  |  |  | 100 | 0 | [15 empty] | 4.6703 | 0.003443 | 0.34 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4513 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019557
2097 | Task(Task)-->P (Procurement) | 6.6KV NEUTRAL GROUNDING RESISTOR |  | 1.15.2.4 | Completed | No | No | 2020-01-21 09:00 | 2020-02-29 18:00 | 2020-06-05 09:00 | 2020-07-15 18:00 |  |  | 2020-06-05 08:54 | 2020-07-15 08:54 |  |  | 100 | 100 | [15 empty] | 0.41209 | 0.000304 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4514 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019558
2098 | Task(Task)-->P (Procurement) | PLC SYSTEM |  | 1.15.2.4 | Unscheduled | No | No | 2019-12-28 09:00 | 2020-02-05 18:00 | 2020-08-27 09:00 | 2020-10-30 18:00 |  |  | 2020-08-27 17:08 |  |  |  | 100 | 0 | [15 empty] | 10.0275 | 0.007392 | 0.73 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4515 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019559
2099 | Task(Task)-->P (Procurement) | UPS SYSTEM |  | 1.15.2.4 | Unscheduled | No | No | 2020-02-19 09:00 | 2020-03-29 23:59 | 2020-09-01 09:00 | 2020-10-30 18:00 | [6 empty] | 100 | 0 | [15 empty] | 2.0604 | 0.001519 | 0.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4516 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019560
2100 | Task(Task)-->P (Procurement) | 24V DC BATTERY AND BATTERY CHARGER SYSTEM |  | 1.15.2.4 | Unscheduled | No | No | 2020-02-20 09:00 | 2020-03-30 18:00 | 2020-08-08 09:00 | 2020-10-30 18:00 |  |  | 2020-08-06 16:18 |  |  |  | 100 | 0 | [15 empty] | 0.96154 | 0.000709 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4517 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019561
2101 | Task(Task)-->P (Procurement) | FDA SYSTEM |  | 1.15.2.4 | Unscheduled | No | No | 2020-04-09 09:00 | 2020-05-18 18:00 | 2020-08-21 09:00 | 2020-10-30 18:00 | [6 empty] | 100 | 0 | [15 empty] | 6.7308 | 0.004962 | 0.49 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4518 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019562
2102 | Task(Task)-->P (Procurement) | SCADA |  | 1.15.2.4 | Unscheduled | No | No | 2020-02-21 09:00 | 2020-03-31 18:00 | 2020-09-17 09:00 | 2020-10-25 23:59 | [6 empty] | 100 | 0 | [15 empty] | 3.1593 | 0.002329 | 0.23 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4519 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019563
2103 | Task(Task)-->P (Procurement) | RUBBER MATS |  | 1.15.2.4 | Unscheduled | No | No | 2020-07-26 | 2020-09-03 18:00 | 2020-08-10 09:00 | 2020-08-10 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.13736 | 0.000101 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4522 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019564
2104 | Task(Task)-->P (Procurement) | MAIN LIGHTING DISTRIBUTION BOARD |  | 1.15.2.4 | Unscheduled | No | No | 2020-04-19 | 2020-05-28 18:00 | 2020-07-28 09:00 | 2020-10-10 18:00 |  |  | 2020-07-28 17:50 |  |  |  | 100 | 0 | [15 empty] | 0.68681 | 0.000506 | 0.05 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4523 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019565
2105 | Task(Task)-->P (Procurement) | LIGHTING PANELS |  | 1.15.2.4 | Unscheduled | No | No | 2020-06-26 09:00 | 2020-08-04 18:00 | 2020-07-28 09:00 | 2020-10-10 18:00 |  |  | 2020-07-28 17:39 |  |  |  | 100 | 0 | [15 empty] | 7.8297 | 0.005772 | 0.57 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4524 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019566
2106 | Task(Task)-->P (Procurement) | DCDB & DC FUSE BOARD |  | 1.15.2.4 | Unscheduled | No | No | 2020-04-19 | 2020-05-28 18:00 | 2020-07-28 09:00 | 2020-10-10 18:00 |  |  | 2020-07-28 14:24 |  |  |  | 100 | 0 | [15 empty] | 2.8846 | 0.002127 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4525 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019567
2107 | Task(Task)-->P (Procurement) | UPS DB,ACDB,MCBDB & AFB |  | 1.15.2.4 | Unscheduled | No | No | 2020-04-19 | 2020-05-28 18:00 | 2020-07-28 09:00 | 2020-10-10 18:00 |  |  | 2020-07-28 17:49 |  |  |  | 100 | 0 | [15 empty] | 2.8846 | 0.002127 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4526 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019568
2108 | Task(Task)-->P (Procurement) | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE | 1.15.2.5 | 1.15.2 | Work In Progress | No | No | 2019-12-28 09:00 | 2020-08-15 18:00 | 2020-03-19 09:00 | 2020-10-31 18:00 |  |  | 2020-03-20 15:25 |  |  |  | 100 | 24.4948 | [15 empty] | 15 | 0.22116 | 21.75 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4527 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019569
2109 | Task(Task)-->P (Procurement) | 33/6.9KV HT TRANSFORMER (ONAN TYPE) |  | 1.15.2.5 | Completed | No | No | 2020-01-16 09:00 | 2020-03-15 23:59 | 2020-06-30 09:00 | 2020-09-22 18:00 |  |  | 2020-06-30 08:49 | 2020-09-22 12:23 |  |  | 100 | 100 | [15 empty] | 14.0165 | 0.030999 | 3.05 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4528 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019570
2110 | Task(Task)-->P (Procurement) | HT SWITCHGEAR (33KV & 6.6KV) |  | 1.15.2.5 | Unscheduled | No | No | 2020-01-14 09:00 | 2020-03-28 18:00 | 2020-07-30 09:00 | 2020-10-20 18:00 |  |  | 2020-07-30 10:51 |  |  |  | 100 | 0 | [15 empty] | 18.5662 | 0.04106 | 4.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4529 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019571
2111 | Task(Task)-->P (Procurement) | 6.6KV HT VFD with Motors |  | 1.15.2.5 | Completed | No | No | 2020-02-29 09:00 | 2020-05-13 18:00 | 2020-08-08 09:00 | 2020-10-10 18:00 |  |  | 2020-07-28 11:51 | 2020-09-23 15:24 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4530 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019572
2112 | Task(Task)-->P (Procurement) | 6.6KV HT APFC PANEL |  | 1.15.2.5 | Unscheduled | No | No | 2020-03-11 09:00 | 2020-04-24 18:00 | 2020-07-22 09:00 | 2020-10-20 18:00 |  |  | 2020-07-22 08:57 |  |  |  | 100 | 0 | [15 empty] | 1.6544 | 0.003659 | 0.36 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4531 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019573
2113 | Task(Task)-->P (Procurement) | 6.6KV/0.433V LT TRANSFORMER |  | 1.15.2.5 | Completed | No | No | 2020-01-16 09:00 | 2020-03-15 23:59 | 2020-07-20 09:00 | 2020-09-17 18:00 |  |  | 2020-07-20 09:00 | 2020-09-17 12:32 |  |  | 100 | 100 | [15 empty] | 7.0772 | 0.015652 | 1.54 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4532 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019574
2114 | Task(Task)-->P (Procurement) | LT BUSDUCT |  | 1.15.2.5 | Unscheduled | No | No | 2020-02-05 09:00 | 2020-03-20 18:00 | 2020-06-12 09:00 | 2020-07-21 18:00 |  |  | 2020-09-16 17:36 |  |  |  | 100 | 0 | [15 empty] | 2.1599 | 0.004777 | 0.47 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4533 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019575
2115 | Task(Task)-->P (Procurement) | 415V MCC |  | 1.15.2.5 | Unscheduled | No | No | 2020-02-26 09:00 | 2020-05-10 23:59 | 2020-08-17 09:00 | 2020-10-31 18:00 |  |  | 2020-08-17 14:15 |  |  |  | 100 | 0 | [15 empty] | 14.2463 | 0.031507 | 3.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4534 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019576
2116 | Task(Task)-->P (Procurement) | 110V DC BATTERY & BATTERY CHARGER SYSTEM |  | 1.15.2.5 | Unscheduled | No | No | 2020-02-25 09:00 | 2020-04-19 23:59 | 2020-07-07 09:00 | 2020-10-31 18:00 |  |  | 2020-07-07 10:31 |  |  |  | 100 | 0 | [15 empty] | 4.6415 | 0.010265 | 1.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4535 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019577
2117 | Task(Task)-->P (Procurement) | 6.6KV NEUTRAL GROUNDING RESISTOR |  | 1.15.2.5 | Completed | No | No | 2020-01-21 09:00 | 2020-03-05 18:00 | 2020-03-19 09:00 | 2020-06-04 18:00 |  |  | 2020-03-20 15:25 | 2020-06-04 15:25 |  |  | 100 | 100 | [15 empty] | 0.4136 | 0.000915 | 0.09 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4536 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019578
2118 | Task(Task)-->P (Procurement) | PLC SYSTEM |  | 1.15.2.5 | Unscheduled | No | No | 2019-12-28 09:00 | 2020-03-11 18:00 | 2020-07-29 09:00 | 2020-10-15 18:00 |  |  | 2020-07-29 17:09 |  |  |  | 100 | 0 | [15 empty] | 10.0184 | 0.022156 | 2.18 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4537 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019579
2119 | Task(Task)-->P (Procurement) | UPS SYSTEM |  | 1.15.2.5 | Unscheduled | No | No | 2020-02-19 09:00 | 2020-04-03 18:00 | 2020-08-01 09:00 | 2020-09-14 18:00 |  |  | 2020-08-31 12:21 |  |  |  | 100 | 0 | [15 empty] | 2.0221 | 0.004472 | 0.44 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4538 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019580
2120 | Task(Task)-->P (Procurement) | 24V DC BATTERY AND BATTERY CHARGER SYSTEM |  | 1.15.2.5 | Unscheduled | No | No | 2020-02-20 09:00 | 2020-04-14 18:00 | 2020-08-06 09:00 | 2020-10-20 18:00 |  |  | 2020-08-06 16:16 |  |  |  | 100 | 0 | [15 empty] | 0.96507 | 0.002134 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4539 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019581
2121 | Task(Task)-->P (Procurement) | FDA SYSTEM |  | 1.15.2.5 | Unscheduled | No | No | 2020-04-09 09:00 | 2020-06-22 18:00 | 2020-08-13 09:00 | 2020-10-15 18:00 | [6 empty] | 100 | 0 | [15 empty] | 6.7096 | 0.014839 | 1.46 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4540 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019582
2122 | Task(Task)-->P (Procurement) | SCADA |  | 1.15.2.5 | Unscheduled | No | No | 2020-02-21 09:00 | 2020-05-05 18:00 | 2020-08-15 09:00 | 2020-10-31 18:00 |  |  | 2020-07-06 17:05 |  |  |  | 100 | 0 | [15 empty] | 3.125 | 0.006911 | 0.68 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4541 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019583
2123 | Task(Task)-->P (Procurement) | RUBBER MATS |  | 1.15.2.5 | Completed | No | No | 2020-07-26 | 2020-08-15 18:00 | 2020-06-30 09:00 | 2020-07-23 18:00 |  |  | 2020-06-11 21:17 | 2020-07-03 21:17 |  |  | 100 | 100 | [15 empty] | 0.13787 | 0.000305 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4544 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019584
2124 | Task(Task)-->P (Procurement) | MAIN LIGHTING DISTRIBUTION BOARD |  | 1.15.2.5 | Unscheduled | No | No | 2020-04-19 | 2020-06-02 18:00 | 2020-07-28 09:00 | 2020-10-31 18:00 |  |  | 2020-07-28 17:31 |  |  |  | 100 | 0 | [15 empty] | 0.73529 | 0.001626 | 0.16 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4545 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019585
2125 | Task(Task)-->P (Procurement) | LIGHTING PANELS |  | 1.15.2.5 | Unscheduled | No | No | 2020-06-26 09:00 | 2020-08-09 23:59 | 2020-07-28 09:00 | 2020-10-31 18:00 |  |  | 2020-07-28 17:40 |  |  |  | 100 | 0 | [15 empty] | 7.8125 | 0.017278 | 1.7 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4546 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019586
2126 | Task(Task)-->P (Procurement) | DCDB & DC FUSE BOARD |  | 1.15.2.5 | Unscheduled | No | No | 2020-04-19 | 2020-06-02 18:00 | 2020-07-28 09:00 | 2020-10-31 18:00 |  |  | 2020-07-28 14:23 |  |  |  | 100 | 0 | [15 empty] | 2.8493 | 0.006301 | 0.62 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4547 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019587
2127 | Task(Task)-->P (Procurement) | UPS DB,ACDB,MCBDB & AFB |  | 1.15.2.5 | Completed | No | No | 2020-04-19 | 2020-06-02 18:00 | 2020-07-28 09:00 | 2020-10-31 18:00 |  |  | 2020-07-28 17:47 | 2020-09-28 17:47 |  |  | 100 | 100 | [15 empty] | 2.8493 | 0.006301 | 0.62 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4548 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019588
2128 | Task(Task)-->P (Procurement) | MANUFACTURING & RECEIPT AT SITE (MRN) | 1.15.2.6 | 1.15.2 | Unscheduled | No | No | 2020-03-06 09:00 | 2021-03-31 18:00 | 2020-07-16 09:00 | 2021-10-24 23:59 |  |  | 2020-06-04 11:32 |  |  |  | 64.4947 | 0 | [15 empty] | 60 | 0.88463 | 87 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4549 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019589
2129 | Task(Task)-->P (Procurement) | 33/6.9KV HT TRANSFORMER (ONAN TYPE) |  | 1.15.2.6 | Unscheduled | No | No | 2020-03-16 09:00 | 2021-03-22 18:00 | 2020-09-23 09:00 | 2021-09-29 18:00 |  |  | 2020-09-23 09:25 |  |  |  | 55.3763 | 0 | [15 empty] | 14.0048 | 0.12389 | 12.18 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4550 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019590
2130 | Task(Task)-->P (Procurement) | HT SWITCHGEAR (33KV & 6.6KV) |  | 1.15.2.6 | Unscheduled | No | No | 2020-03-29 | 2021-03-22 18:00 | 2020-10-21 09:00 | 2021-10-14 18:00 | [6 empty] | 53.7604 | 0 | [15 empty] | 18.6041 | 0.16458 | 16.18 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4551 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019591
2131 | Task(Task)-->P (Procurement) | 6.6KV HT VFD with Motors |  | 1.15.2.6 | Unscheduled | No | No | 2020-05-14 09:00 | 2021-03-09 18:00 | 2020-10-11 | 2021-08-06 18:00 | [6 empty] | 49 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4552 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019592
2132 | Task(Task)-->P (Procurement) | 6.6KV HT APFC PANEL |  | 1.15.2.6 | Unscheduled | No | No | 2020-04-25 09:00 | 2020-11-04 18:00 | 2020-10-21 09:00 | 2021-05-02 23:59 | [6 empty] | 85.567 | 0 | [15 empty] | 1.6672 | 0.014749 | 1.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4553 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019593
2133 | Task(Task)-->P (Procurement) | 6.6KV/0.433V LT TRANSFORMER |  | 1.15.2.6 | Unscheduled | No | No | 2020-03-16 09:00 | 2021-03-29 18:00 | 2020-10-11 | 2021-10-24 23:59 |  |  | 2020-09-18 12:33 |  |  |  | 54.3536 | 0 | [15 empty] | 7.0714 | 0.062556 | 6.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4554 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019594
2134 | Task(Task)-->P (Procurement) | LT BUSDUCT |  | 1.15.2.6 | Unscheduled | No | No | 2020-03-21 09:00 | 2020-08-13 18:00 | 2020-10-21 09:00 | 2021-03-15 18:00 | [6 empty] | 100 | 0 | [15 empty] | 2.1502 | 0.019021 | 1.87 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4555 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019595
2135 | Task(Task)-->P (Procurement) | 415V MCC |  | 1.15.2.6 | Unscheduled | No | No | 2020-05-11 09:00 | 2021-03-31 18:00 | 2020-11-01 | 2021-09-21 18:00 | [6 empty] | 46.1538 | 0 | [15 empty] | 14.2693 | 0.12623 | 12.41 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4556 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019596
2136 | Task(Task)-->P (Procurement) | 110V DC BATTERY & BATTERY CHARGER SYSTEM |  | 1.15.2.6 | Unscheduled | No | No | 2020-04-20 09:00 | 2020-11-03 18:00 | 2020-11-01 | 2021-05-17 18:00 | [6 empty] | 86.3636 | 0 | [15 empty] | 4.6453 | 0.041093 | 4.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4557 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019597
2137 | Task(Task)-->P (Procurement) | 6.6KV NEUTRAL GROUNDING RESISTOR |  | 1.15.2.6 | Unscheduled | No | No | 2020-03-06 09:00 | 2020-09-02 18:00 | 2020-07-16 09:00 | 2021-02-28 23:59 |  |  | 2020-06-04 11:32 |  |  |  | 100 | 0 | [15 empty] | 0.42543 | 0.003764 | 0.37 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4558 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019598
2138 | Task(Task)-->P (Procurement) | PLC SYSTEM |  | 1.15.2.6 | Unscheduled | No | No | 2020-03-12 09:00 | 2021-01-20 18:00 | 2020-10-31 09:00 | 2021-09-10 18:00 | [6 empty] | 66.6667 | 0 | [15 empty] | 10.0379 | 0.088798 | 8.73 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4559 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019599
2139 | Task(Task)-->P (Procurement) | UPS SYSTEM |  | 1.15.2.6 | Unscheduled | No | No | 2020-04-04 09:00 | 2020-11-03 18:00 | 2020-10-31 09:00 | 2021-06-01 18:00 | [6 empty] | 87.3832 | 0 | [15 empty] | 2.0122 | 0.0178 | 1.75 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4560 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019600
2140 | Task(Task)-->P (Procurement) | 24V DC BATTERY AND BATTERY CHARGER SYSTEM |  | 1.15.2.6 | Unscheduled | No | No | 2020-04-15 09:00 | 2020-10-18 23:59 | 2020-10-31 09:00 | 2021-05-05 18:00 | [6 empty] | 94.1176 | 0 | [15 empty] | 0.97735 | 0.008646 | 0.85 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4561 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019601
2141 | Task(Task)-->P (Procurement) | FDA SYSTEM |  | 1.15.2.6 | Unscheduled | No | No | 2020-06-23 09:00 | 2020-12-25 18:00 | 2020-10-31 09:00 | 2021-05-04 18:00 | [6 empty] | 57.5269 | 0 | [15 empty] | 6.692 | 0.059199 | 5.82 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4562 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019602
2142 | Task(Task)-->P (Procurement) | SCADA |  | 1.15.2.6 | Unscheduled | No | No | 2020-05-06 09:00 | 2021-02-17 18:00 | 2020-11-01 | 2021-08-15 23:59 | [6 empty] | 53.8194 | 0 | [15 empty] | 3.1045 | 0.027463 | 2.7 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4563 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019603
2143 | Task(Task)-->P (Procurement) | RUBBER MATS |  | 1.15.2.6 | Unscheduled | No | No | 2020-09-04 09:00 | 2021-02-15 18:00 | 2020-08-11 09:00 | 2021-01-22 18:00 | [6 empty] | 20.6061 | 0 | [15 empty] | 0.13798 | 0.001221 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4566 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019604
2144 | Task(Task)-->P (Procurement) | MAIN LIGHTING DISTRIBUTION BOARD |  | 1.15.2.6 | Unscheduled | No | No | 2020-06-03 09:00 | 2020-09-16 18:00 | 2020-11-01 | 2021-02-14 23:59 | [6 empty] | 100 | 0 | [15 empty] | 0.71289 | 0.006306 | 0.62 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4567 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019605
2145 | Task(Task)-->P (Procurement) | LIGHTING PANELS |  | 1.15.2.6 | Unscheduled | No | No | 2020-08-10 09:00 | 2020-09-10 18:00 | 2020-11-01 | 2020-12-02 18:00 | [6 empty] | 100 | 0 | [15 empty] | 7.8073 | 0.069065 | 6.79 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4568 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019606
2146 | Task(Task)-->P (Procurement) | DCDB & DC FUSE BOARD |  | 1.15.2.6 | Unscheduled | No | No | 2020-06-03 09:00 | 2020-08-10 18:00 | 2020-11-01 | 2021-01-08 18:00 | [6 empty] | 100 | 0 | [15 empty] | 2.8401 | 0.025124 | 2.47 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4569 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019607
2147 | Task(Task)-->P (Procurement) | UPS DB,ACDB,MCBDB & AFB |  | 1.15.2.6 | Unscheduled | No | No | 2020-06-03 09:00 | 2020-11-28 18:00 | 2020-11-01 | 2021-04-28 18:00 |  |  | 2020-09-29 09:00 |  |  |  | 70.9497 | 0 | [15 empty] | 2.8401 | 0.025124 | 2.47 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4570 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019608
2148 | Task(Task)-->C (Construction) | CONSTRUCTION | 1.15.3 | 1.15 | Unscheduled | No | No | 2020-06-01 09:00 | 2021-08-29 23:59 | 2020-08-01 09:00 | 2022-02-16 18:00 | [6 empty] | 37.9135 | 0 | [15 empty] | 42.7855 | 1.1883 | 116.86 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4571 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019609
2149 | Task(Task)-->C (Construction) | CIVIL | 1.15.3.1 | 1.15.3 | Unscheduled | No | No | 2020-06-01 09:00 | 2021-08-29 23:59 | 2020-08-01 09:00 | 2022-01-26 18:00 | [6 empty] | 41.4034 | 0 | [15 empty] | 91.5711 | 1.0882 | 107.01 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4572 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019610
2150 | Task(Task)-->C (Construction) | AVAILABILITY OF FRONT BY NTPC |  | 1.15.3.1 | Unscheduled | No | No | 2020-06-01 09:00 | 2020-06-01 18:00 | 2020-08-01 09:00 | 2020-08-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4573 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019611
2151 | Task(Task)-->C (Construction) | EXCAVATION |  | 1.15.3.1 | Unscheduled | No | No | 2020-06-08 09:00 | 2020-06-27 18:00 | 2020-11-05 09:00 | 2021-01-28 18:00 | [6 empty] | 100 | 0 | [15 empty] | 1.6165 | 0.01759 | 1.73 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 6500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5531 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | Excavation | [21 empty] | 1019612
2152 | Task(Task)-->C (Construction) | PCC |  | 1.15.3.1 | Unscheduled | No | No | 2020-06-15 09:00 | 2020-07-04 18:00 | 2020-11-12 09:00 | 2020-12-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.75687 | 0.008236 | 0.81 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5532 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | PCC | [21 empty] | 1019613
2153 | Task(Task)-->C (Construction) | RAFT |  | 1.15.3.1 | Unscheduled | No | No | 2020-06-22 09:00 | 2020-07-26 23:59 | 2020-11-19 09:00 | 2020-12-23 18:00 | [6 empty] | 100 | 0 | [15 empty] | 15.1467 | 0.16482 | 16.21 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 611 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5533 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019614
2154 | Task(Task)-->C (Construction) | PLINTH BEAM |  | 1.15.3.1 | Unscheduled | No | No | 2020-07-17 09:00 | 2020-09-04 18:00 | 2020-12-14 09:00 | 2021-02-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 2.4762 | 0.026945 | 2.65 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5534 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019615
2155 | Task(Task)-->C (Construction) | PULL PIT & GRADE SLAB FOR GROUND FLOOR |  | 1.15.3.1 | Unscheduled | No | No | 2020-08-16 | 2020-09-24 18:00 | 2021-01-13 09:00 | 2021-02-21 23:59 | [6 empty] | 100 | 0 | [15 empty] | 16.0624 | 0.17479 | 17.19 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 918 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5535 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019616
2156 | Task(Task)-->C (Construction) | COLUMN AND SLAB OF 1ST FLOOR |  | 1.15.3.1 | Unscheduled | No | No | 2020-09-15 09:00 | 2020-10-29 18:00 | 2021-02-12 09:00 | 2021-03-28 23:59 | [6 empty] | 51.1111 | 0 | [15 empty] | 8.6806 | 0.09446 | 9.29 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5536 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019617
2157 | Task(Task)-->C (Construction) | COLUMN AND ROOF SLAB (2ND FLOOR) |  | 1.15.3.1 | Unscheduled | No | No | 2020-11-06 09:00 | 2021-01-04 18:00 | 2021-04-05 09:00 | 2021-06-03 18:00 | [6 empty] | 0 | 0 | [15 empty] | 8.6806 | 0.09446 | 9.29 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5537 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019618
2158 | Task(Task)-->C (Construction) | RCC COLUMN & SLAB OF MUMTY & FOUNDATION OF FAN/ AC ETC |  | 1.15.3.1 | Unscheduled | No | No | 2021-01-05 09:00 | 2021-02-03 18:00 | 2021-06-04 09:00 | 2021-07-03 18:00 | [6 empty] | 0 | 0 | [15 empty] | 1.2428 | 0.013523 | 1.33 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5538 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019619
2159 | Task(Task)-->C (Construction) | BRICK WORK OF GROUND FLOOR |  | 1.15.3.1 | Unscheduled | No | No | 2020-11-27 09:00 | 2021-01-15 18:00 | 2021-04-26 09:00 | 2021-06-14 18:00 | [6 empty] | 0 | 0 | [15 empty] | 4.4197 | 0.048094 | 4.73 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5539 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019620
2160 | Task(Task)-->C (Construction) | PLASTERING OF GROUND FLOOR (IN SIDE) & HANDING OVER FOR ELECTRICAL WORKS |  | 1.15.3.1 | Unscheduled | No | No | 2020-12-07 09:00 | 2021-01-25 18:00 | 2021-05-06 09:00 | 2021-06-24 18:00 | [6 empty] | 0 | 0 | [15 empty] | 1.9155 | 0.020844 | 2.05 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 3698 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5540 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019621
2161 | Task(Task)-->C (Construction) | BRICK WORK OF 1ST FLOOR |  | 1.15.3.1 | Unscheduled | No | No | 2021-02-02 09:00 | 2021-04-02 18:00 | 2021-07-02 09:00 | 2021-08-30 18:00 | [6 empty] | 0 | 0 | [15 empty] | 4.4197 | 0.048094 | 4.73 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5541 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019622
2162 | Task(Task)-->C (Construction) | PLASTERING OF 1ST FLOOR (IN SIDE) |  | 1.15.3.1 | Unscheduled | No | No | 2021-02-26 09:00 | 2021-04-16 18:00 | 2021-07-26 09:00 | 2021-09-13 18:00 | [6 empty] | 0 | 0 | [15 empty] | 1.9155 | 0.020844 | 2.05 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 3698 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5542 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019623
2163 | Task(Task)-->C (Construction) | PAINTING OF CEILING OF ROOF SLAB (NON-AC) & HANDING OVER FOR ELECTRICAL WORKS |  | 1.15.3.1 | Unscheduled | No | No | 2021-04-07 09:00 | 2021-04-26 18:00 | 2021-09-04 09:00 | 2021-09-23 18:00 | [6 empty] | 0 | 0 | [15 empty] | 1.7473 | 0.019014 | 1.87 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 3698 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5543 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019624
2164 | Task(Task)-->C (Construction) | INSIDE PAINTING & FALSE CEILING (AC) & HANDING OVER FOR ELECTRICAL WORKS |  | 1.15.3.1 | Unscheduled | No | No | 2021-04-17 09:00 | 2021-05-16 23:59 | 2021-09-14 09:00 | 2021-10-13 18:00 | [6 empty] | 0 | 0 | [15 empty] | 6.4848 | 0.070565 | 6.94 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 3698 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5544 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019625
2165 | Task(Task)-->C (Construction) | TRANSFORMER FOUNDATION, TRENCH, BRICK WORK & PLASTERING ETC & HANDING OVER TO ELECTRICAL |  | 1.15.3.1 | Unscheduled | No | No | 2020-09-05 09:00 | 2020-12-03 18:00 | 2021-02-02 09:00 | 2021-05-02 23:59 | [6 empty] | 36.6667 | 0 | [15 empty] | 2.4762 | 0.026945 | 2.65 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5545 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019626
2166 | Task(Task)-->C (Construction) | BALANCE BRICK WORK |  | 1.15.3.1 | Unscheduled | No | No | 2021-04-17 09:00 | 2021-05-16 23:59 | 2021-09-14 09:00 | 2021-10-13 18:00 | [6 empty] | 0 | 0 | [15 empty] | 3.4666 | 0.037723 | 3.71 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 235 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5546 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019627
2167 | Task(Task)-->C (Construction) | OUTSIDE PLASTERING |  | 1.15.3.1 | Unscheduled | No | No | 2021-05-17 09:00 | 2021-07-15 18:00 | 2021-10-14 09:00 | 2021-12-12 23:59 | [6 empty] | 0 | 0 | [15 empty] | 3.8311 | 0.041688 | 4.1 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 7395 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5547 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019628
2168 | Task(Task)-->C (Construction) | DOOR , WINDOW, MONORAIL DOOR & ROLLING SHUTTER |  | 1.15.3.1 | Unscheduled | No | No | 2021-06-16 09:00 | 2021-07-23 18:00 | 2021-11-13 09:00 | 2021-12-20 18:00 | [6 empty] | 0 | 0 | [15 empty] | 3.205 | 0.034876 | 3.43 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5548 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019629
2169 | Task(Task)-->C (Construction) | BALANCE PAINTING |  | 1.15.3.1 | Unscheduled | No | No | 2021-07-16 09:00 | 2021-08-29 23:59 | 2021-12-13 09:00 | 2022-01-26 18:00 | [6 empty] | 0 | 0 | [15 empty] | 3.4853 | 0.037926 | 3.73 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 7395 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5549 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019630
2170 | Task(Task)-->C (Construction) | ROOF WATER PROFING & RWDC PIPE |  | 1.15.3.1 | Unscheduled | No | No | 2021-03-04 09:00 | 2021-04-03 18:00 | 2021-08-01 | 2021-08-31 18:00 | [6 empty] | 0 | 0 | [15 empty] | 5.812 | 0.063244 | 6.22 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 1296 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5550 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019631
2171 | Task(Task)-->C (Construction) | GARLAND DRAIN & PLINTH PROTECTION |  | 1.15.3.1 | Unscheduled | No | No | 2021-07-16 09:00 | 2021-08-29 23:59 | 2021-12-13 09:00 | 2022-01-26 18:00 | [6 empty] | 0 | 0 | [15 empty] | 2.1585 | 0.023488 | 2.31 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5551 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019632
2172 | Task(Task)-->C (Construction) | ELECTRICAL & INSTRUMENTATION | 1.15.3.2 | 1.15.3 | Unscheduled | No | No | 2020-12-04 09:00 | 2021-08-29 23:59 | 2021-05-03 09:00 | 2022-01-26 18:00 | [6 empty] | 0 | 0 | [15 empty] | 6.2639 | 0.074436 | 7.32 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5256 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019633
2173 | Task(Task)-->C (Construction) | TRANSFORMERS |  | 1.15.3.2 | Unscheduled | No | No | 2020-12-04 09:00 | 2020-12-24 18:00 | 2021-05-03 09:00 | 2021-05-23 23:59 | [6 empty] | 0 | 0 | [15 empty] | 21.0095 | 0.015639 | 1.54 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4592 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019634
2174 | Task(Task)-->C (Construction) | HT PANEL |  | 1.15.3.2 | Unscheduled | No | No | 2021-04-27 09:00 | 2021-05-11 18:00 | 2021-10-15 09:00 | 2021-10-29 18:00 | [6 empty] | 0 | 0 | [15 empty] | 8.5948 | 0.006398 | 0.63 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5257 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019635
2175 | Task(Task)-->C (Construction) | HT VFD |  | 1.15.3.2 | Unscheduled | No | No | 2021-05-17 09:00 | 2021-05-18 18:00 | 2021-10-14 09:00 | 2021-10-15 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4593 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019636
2176 | Task(Task)-->C (Construction) | HT APFC |  | 1.15.3.2 | Unscheduled | No | No | 2021-05-17 09:00 | 2021-05-17 18:00 | 2021-10-14 09:00 | 2021-10-14 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5367 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019637
2177 | Task(Task)-->C (Construction) | LT PANEL |  | 1.15.3.2 | Unscheduled | No | No | 2021-04-27 09:00 | 2021-05-16 23:59 | 2021-10-25 09:00 | 2021-11-13 18:00 | [6 empty] | 0 | 0 | [15 empty] | 2.3192 | 0.001726 | 0.17 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5368 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019638
2178 | Task(Task)-->C (Construction) | BATTERY, BATTERY CHARGER & UPS |  | 1.15.3.2 | Unscheduled | No | No | 2021-01-26 09:00 | 2021-02-01 18:00 | 2021-06-25 09:00 | 2021-07-01 18:00 | [6 empty] | 0 | 0 | [15 empty] | 2.1828 | 0.001625 | 0.16 | Plan & Actual | Quantity | Set | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5559 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019639
2179 | Task(Task)-->C (Construction) | CABLE TRAY |  | 1.15.3.2 | Unscheduled | No | No | 2021-01-26 09:00 | 2021-02-04 18:00 | 2021-06-25 09:00 | 2021-07-04 23:59 | [6 empty] | 0 | 0 | [15 empty] | 8.7312 | 0.006499 | 0.64 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5369 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019640
2180 | Task(Task)-->C (Construction) | POWER CABLE |  | 1.15.3.2 | Unscheduled | No | No | 2021-05-19 09:00 | 2021-06-02 18:00 | 2021-11-14 | 2021-11-28 23:59 | [6 empty] | 0 | 0 | [15 empty] | 15.9618 | 0.011881 | 1.17 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 8300 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5370 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019641
2181 | Task(Task)-->C (Construction) | CONTROL CABLE |  | 1.15.3.2 | Unscheduled | No | No | 2021-05-29 09:00 | 2021-06-02 18:00 | 2021-11-24 09:00 | 2021-11-28 23:59 | [6 empty] | 0 | 0 | [15 empty] | 12.9604 | 0.009647 | 0.95 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 6700 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5371 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019642
2182 | Task(Task)-->C (Construction) | EARTHING |  | 1.15.3.2 | Unscheduled | No | No | 2021-05-27 09:00 | 2021-06-02 18:00 | 2021-11-22 09:00 | 2021-11-28 23:59 | [6 empty] | 0 | 0 | [15 empty] | 4.2292 | 0.003148 | 0.31 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 1377 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5372 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019643
2183 | Task(Task)-->C (Construction) | EARTH PIT |  | 1.15.3.2 | Unscheduled | No | No | 2021-08-16 09:00 | 2021-08-29 23:59 | 2022-01-13 09:00 | 2022-01-26 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5373 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019644
2184 | Task(Task)-->C (Construction) | LIGHTING |  | 1.15.3.2 | Unscheduled | No | No | 2021-05-01 09:00 | 2021-05-07 18:00 | 2021-09-28 09:00 | 2021-10-04 18:00 | [6 empty] | 0 | 0 | [15 empty] | 24.0109 | 0.017873 | 1.76 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5374 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019645
2185 | Task(Task)-->C (Construction) | NON-MOTOR TERMINATION |  | 1.15.3.2 | Unscheduled | No | No | 2021-06-03 09:00 | 2021-06-04 18:00 | 2021-11-29 09:00 | 2021-11-30 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 148 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5377 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019646
2186 | Task(Task)-->C (Construction) | TESTING & CHARGING FOR LOAD & TRIAL OPERATION | 1.15.3.3 | 1.15.3 | Unscheduled | No | No | 2021-06-03 09:00 | 2021-08-21 18:00 | 2021-11-29 09:00 | 2022-02-16 18:00 | [6 empty] | 0 | 0 | [15 empty] | 2.165 | 0.025727 | 2.53 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5378 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019647
2187 | Task(Task)-->C (Construction) | TRANSFORMERS (33KV/6.6KV) |  | 1.15.3.3 | Unscheduled | No | No | 2021-06-23 09:00 | 2021-07-02 18:00 | 2021-12-19 | 2021-12-28 18:00 | [6 empty] | 0 | 0 | [15 empty] | 19.685 | 0.005064 | 0.5 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5593 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019648
2188 | Task(Task)-->C (Construction) | TRANSFORMERS (6.6KV/415V) |  | 1.15.3.3 | Unscheduled | No | No | 2021-07-23 09:00 | 2021-08-01 23:59 | 2022-01-18 09:00 | 2022-01-27 18:00 | [6 empty] | 0 | 0 | [15 empty] | 19.685 | 0.005064 | 0.5 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5594 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019649
2189 | Task(Task)-->C (Construction) | 33 KV SWBD |  | 1.15.3.3 | Unscheduled | No | No | 2021-06-03 09:00 | 2021-06-22 18:00 | 2021-11-29 09:00 | 2021-12-18 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5379 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019650
2190 | Task(Task)-->C (Construction) | 6.6. KV SWBD |  | 1.15.3.3 | Unscheduled | No | No | 2021-07-03 09:00 | 2021-07-22 18:00 | 2021-12-29 09:00 | 2022-01-17 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5595 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019651
2191 | Task(Task)-->C (Construction) | PMCC-3 |  | 1.15.3.3 | Unscheduled | No | No | 2021-08-02 09:00 | 2021-08-21 18:00 | 2022-01-28 09:00 | 2022-02-16 18:00 | [6 empty] | 0 | 0 | [15 empty] | 60.6299 | 0.015598 | 1.54 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5380 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019652
2192 | Task(Task)-->C (Construction) | BATTERY, BATTERY CHARGER & UPS |  | 1.15.3.3 | Unscheduled | No | No | 2021-06-03 09:00 | 2021-06-09 18:00 | 2021-11-29 09:00 | 2021-12-05 23:59 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Set | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5560 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019653
2193 | Task(Task)-->E (Engineering) | PUMP HOUSE -A NEAR DUMP HOPPER | 1.16 | 1 | Work In Progress | No | No | 2019-12-17 09:00 | 2021-09-07 18:00 | 2020-01-13 09:00 | 2022-03-30 18:00 |  |  | 2020-01-13 10:57 |  |  |  | 64.4296 | 16.5514 | [15 empty] | 0.6035 | 0.6035 | 59.35 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4594 | 0 | 1 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019654
2194 | Task(Task)-->E (Engineering) | ENGINEERING | 1.16.1 | 1.16 | Work In Progress | No | No | 2020-01-22 18:00 | 2020-08-21 17:40 | 2020-05-04 18:00 | 2020-10-05 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 76.5482 | [15 empty] | 18.6889 | 0.11279 | 11.09 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4595 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019655
2195 | Task(Task)-->E (Engineering) | MECHANICAL | 1.16.1.1 | 1.16.1 | Unscheduled | No | No | 2020-01-22 18:00 | 2020-06-11 17:40 | 2020-05-16 18:00 | 2020-09-01 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 76.0489 | [15 empty] | 50.3686 | 0.056809 | 2.05 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4596 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036119
2196 | Task(Task)-->E (Engineering) | G.A AND SCHEDULE OF ELECTRIC HOIST |  | 1.16.1.1 | Unscheduled | No | No | 2020-04-19 23:59 | 2020-06-11 17:40 | 2020-06-30 18:00 | 2020-09-01 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1034 |  | 2020-02-13 10:27 | 7012-155-PVM-B-134 |  |  |  | A |  |  |  | 31.7073 | 0.018013 | 0.65 | Plan & Actual | Date |  | 0 | 0 | 0 | 240 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4598 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-19 23:59 | 2020-06-30 18:00 |  | 10 |  |  |  | 2020-05-01 17:40 | 2020-07-15 18:00 |  | 30 |  |  |  | 2020-05-07 17:40 | 2020-07-18 18:00 |  | 35 |  |  |  | 2020-05-14 23:59 | 2020-07-25 18:00 |  | 65 | 2020-08-19 11:04 |  |  | 2020-05-20 17:40 | 2020-08-15 18:00 |  | 80 | 2020-09-02 16:06 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-11 17:40 | 2020-08-15 18:00 |  | 100 | [122 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 64 |  |  |  | 101078
2197 | Task(Task)-->E (Engineering) | G.A AND SCHEDULE OF MANUAL HOIST |  | 1.16.1.1 | Unscheduled | No | No | 2020-04-19 23:59 | 2020-06-11 17:40 | 2020-06-30 18:00 | 2020-09-01 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1035 |  | 2020-02-13 10:27 | 7012-155-PVM-B-135 |  |  |  | A |  |  |  | 41.9512 | 0.023832 | 0.86 | Plan & Actual | Date |  | 0 | 0 | 0 | 320 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4599 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-19 23:59 | 2020-06-30 18:00 |  | 10 |  |  |  | 2020-05-01 17:40 | 2020-07-15 18:00 |  | 30 |  |  |  | 2020-05-07 17:40 | 2020-07-18 18:00 |  | 35 |  |  |  | 2020-05-14 23:59 | 2020-07-25 18:00 |  | 65 | 2020-08-14 23:27 |  |  | 2020-05-20 17:40 | 2020-08-15 18:00 |  | 80 | 2020-09-02 16:08 | [5 empty] | 80 | 2020-09-02 16:56 | [5 empty] | 80 | 2020-09-02 16:56 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-11 17:40 | 2020-08-15 18:00 |  | 100 | [122 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 65 |  |  |  | 101079
2198 | Task(Task)-->E (Engineering) | PUMP HOUSE -A ARRANGEMENT ( PUMP HOUSE A) ALONG WITH PIPING LAYOUT & MS WATER TANK |  | 1.16.1.1 | Unscheduled | No | No | 2020-01-22 18:00 | 2020-03-25 17:40 | 2020-05-16 18:00 | 2020-07-15 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-DS-GA-6008 |  | 2020-02-13 11:40 | 7012-155-PVM-B-038 |  |  |  | A |  |  |  | 26.3415 | 0.014964 | 0.54 | Plan & Actual | Date |  | 0 | 0 | 0 | 200 | 0 | 11.45 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4597 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-22 18:00 | 2020-05-16 18:00 |  | 10 |  |  |  | 2020-02-13 17:40 | 2020-06-06 18:00 |  | 30 |  |  |  | 2020-02-19 17:40 | 2020-06-13 18:00 |  | 35 | 2020-06-30 13:09 |  |  | 2020-02-26 23:59 | 2020-06-20 18:00 |  | 65 | 2020-08-22 12:47 |  |  | 2020-03-03 17:40 | 2020-07-11 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-25 17:40 | 2020-07-11 18:00 |  | 100 | [122 empty] | Ram Prasad Roy |  |  |  |  | U - Water Media & Utility System | [16 empty] | 83 |  |  |  | 101097
2199 | Task(Task)-->E (Engineering) | CIVIL | 1.16.1.2 | 1.16.1 | Work In Progress | No | No | 2020-04-15 18:00 | 2020-08-13 17:40 | 2020-06-20 18:00 | 2020-10-05 18:00 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 75.2754 | [15 empty] | 22.3587 | 0.025218 | 0.91 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4600 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036120
2200 | Task(Task)-->E (Engineering) | Pump House-A : DESIGN CALCULATION |  | 1.16.1.2 | Completed | No | No | 2020-04-15 18:00 | 2020-06-15 17:40 | 2020-07-24 09:00 | 2020-08-07 18:00 |  |  | 2020-02-21 15:37 | 2020-08-07 23:19 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0022 |  | 2020-02-13 11:42 | 7012-155-PVC-U-074 |  |  |  | A |  |  |  | 40.6593 | 0.010253 | 0.37 | Plan & Actual | Date |  | 0 | 0 | 0 | 136.02 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4605 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-15 18:00 | 2020-06-20 18:00 |  | 10 |  |  |  | 2020-05-04 17:40 | 2020-07-15 18:00 |  | 30 |  |  |  | 2020-05-11 17:40 | 2020-07-18 18:00 |  | 35 |  |  |  | 2020-05-16 23:59 | 2020-07-25 18:00 |  | 65 | 2020-08-07 23:08 |  |  | 2020-05-22 17:40 | 2020-08-15 18:00 |  | 80 | 2020-08-07 23:16 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-15 17:40 | 2020-08-29 18:00 |  | 100 | 2020-08-07 23:19 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 175 |  |  |  | 101185
2201 | Task(Task)-->E (Engineering) | Pump House-A : NUM & RC DETAILS (SHT 1) |  | 1.16.1.2 | Unscheduled | No | No | 2020-04-15 18:00 | 2020-06-15 17:40 | 2020-06-20 18:00 | 2020-08-29 18:00 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-NR-0025 |  | 2020-02-13 11:42 | 7012-155-PVC-C-075 |  |  |  | A |  |  |  | 13.1868 | 0.003325 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 45.03 | 0 | 5.15 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4601 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-15 18:00 | 2020-06-20 18:00 |  | 10 |  |  |  | 2020-05-04 17:40 | 2020-07-15 18:00 |  | 30 |  |  |  | 2020-05-11 17:40 | 2020-07-18 18:00 |  | 35 | 2020-07-20 18:56 |  |  | 2020-05-16 23:59 | 2020-07-25 18:00 |  | 65 | 2020-08-07 23:10 |  |  | 2020-05-22 17:40 | 2020-08-15 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-15 17:40 | 2020-08-29 18:00 |  | 100 | [122 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 176 |  |  |  | 101186
2202 | Task(Task)-->E (Engineering) | Pump House-A : NUM & RC DETAILS (SHT 2) |  | 1.16.1.2 | Completed | No | No | 2020-04-15 18:00 | 2020-06-15 17:40 | 2020-07-24 09:00 | 2020-08-07 18:00 |  |  | 2020-02-21 15:37 | 2020-08-07 23:19 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-NR-0026 |  | 2020-02-13 11:42 | 7012-155-PVC-C-076 |  |  |  | A |  |  |  | 13.1868 | 0.003325 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 45.03 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4602 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-15 18:00 | 2020-06-20 18:00 |  | 10 |  |  |  | 2020-05-04 17:40 | 2020-07-15 18:00 |  | 30 |  |  |  | 2020-05-11 17:40 | 2020-07-18 18:00 |  | 35 |  |  |  | 2020-05-16 23:59 | 2020-07-25 18:00 |  | 65 | 2020-08-07 23:11 |  |  | 2020-05-22 17:40 | 2020-08-15 18:00 |  | 80 | 2020-08-07 23:17 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-15 17:40 | 2020-08-29 18:00 |  | 100 | 2020-08-07 23:20 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 177 |  |  |  | 101187
2203 | Task(Task)-->E (Engineering) | Pump House-A : NUM & RC DETAILS (SHT 3) |  | 1.16.1.2 | Unscheduled | No | No | 2020-04-15 18:00 | 2020-06-15 17:40 | 2020-06-20 18:00 | 2020-08-29 18:00 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-NR-0027 |  | 2020-02-13 11:42 | 7012-155-PVC-C-077 |  |  |  | A |  |  |  | 13.1868 | 0.003325 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 45.03 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4603 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-15 18:00 | 2020-06-20 18:00 |  | 10 |  |  |  | 2020-05-04 17:40 | 2020-07-15 18:00 |  | 30 |  |  |  | 2020-05-11 17:40 | 2020-07-18 18:00 |  | 35 |  |  |  | 2020-05-16 23:59 | 2020-07-25 18:00 |  | 65 |  |  |  | 2020-05-22 17:40 | 2020-08-15 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-15 17:40 | 2020-08-29 18:00 |  | 100 | [122 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 178 |  |  |  | 101188
2204 | Task(Task)-->E (Engineering) | ARCHITECTURAL GA OF PUMP HOUSE A |  | 1.16.1.2 | Unscheduled | No | No | 2020-06-14 23:59 | 2020-08-13 17:40 | 2020-07-27 18:00 | 2020-10-05 18:00 |  |  | 2020-02-21 15:39 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-AR-0008 |  | 2020-02-13 11:43 | 7012-155-PVC-C-114 |  |  |  | A |  |  |  | 19.7802 | 0.004988 | 0.18 | Plan & Actual | Date |  | 0 | 0 | 0 | 68.01 | 0 | 54 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4604 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-06-14 23:59 | 2020-07-27 18:00 |  | 10 |  |  |  | 2020-07-02 17:40 | 2020-08-21 18:00 |  | 30 |  |  |  | 2020-07-08 17:40 | 2020-08-24 18:00 |  | 35 | 2020-09-03 17:09 |  |  | 2020-07-15 23:59 | 2020-08-31 18:00 |  | 65 | 2020-09-06 16:08 |  |  | 2020-07-21 17:40 | 2020-09-21 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-08-13 17:40 | 2020-10-05 18:00 |  | 100 | [122 empty] | Chetan Khodke |  |  |  |  | A - Architecture | [16 empty] | 215 |  |  |  | 101225
2205 | Task(Task)-->E (Engineering) | ELECTRICAL | 1.16.1.3 | 1.16.1 | Unscheduled | No | No | 2020-04-06 18:00 | 2020-08-21 17:40 | 2020-05-04 18:00 | 2020-08-21 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 78.5136 | [15 empty] | 27.2727 | 0.03076 | 1.11 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4606 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036121
2206 | Task(Task)-->E (Engineering) | GA, DATA SHEET, WIRING DIAGRAM & BOM OF ELECTRIC HOIST FOR CHP. |  | 1.16.1.3 | Unscheduled | No | No | 2020-07-10 17:40 | 2020-08-21 17:40 | 2020-07-11 18:00 | 2020-08-21 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-407 |  | 2020-02-13 11:47 | 7012-155-PVE-W-143 |  |  |  | A |  |  |  | 9.9099 | 0.003048 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4609 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-07-11 18:00 | 2020-07-11 18:00 |  | 10 |  |  |  | 2020-07-10 17:40 | 2020-07-18 18:00 |  | 30 |  |  |  | 2020-07-17 17:40 | 2020-07-23 18:00 |  | 35 |  |  |  | 2020-07-23 23:59 | 2020-07-23 18:00 |  | 65 | 2020-10-07 15:52 |  |  | 2020-07-30 17:40 | 2020-08-13 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-08-21 17:40 | 2020-08-13 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 378 |  |  |  | 101389
2207 | Task(Task)-->E (Engineering) | EQUIPMENT, CABLE ROUTING, EARTHING & LIGHTNING LAYOUT WITH PLAN, SECTIONAL VIEWS & BOM OF PUMP HOUSE-A NEAR KDTP-1 |  | 1.16.1.3 | Unscheduled | No | No | 2020-04-06 18:00 | 2020-05-26 17:40 | 2020-05-04 18:00 | 2020-07-02 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5057 |  | 2020-02-13 11:44 | 7012-155-PVE-F-019 |  |  |  | A |  |  |  | 60.3604 | 0.018567 | 0.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 248.42 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4607 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-06 18:00 | 2020-05-04 18:00 |  | 10 |  |  |  | 2020-04-14 17:40 | 2020-05-18 18:00 |  | 30 | 2020-06-09 11:11 |  |  | 2020-04-20 17:40 | 2020-05-25 18:00 |  | 35 | 2020-07-01 19:14 |  |  | 2020-04-27 23:59 | 2020-06-01 18:00 |  | 65 | 2020-07-28 15:41 |  |  | 2020-05-02 17:40 | 2020-06-22 18:00 |  | 80 | 2020-07-28 17:47 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-26 17:40 | 2020-06-22 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 254 |  |  |  | 101265
2208 | Task(Task)-->E (Engineering) | LIGHTING LAYOUT PLAN WITH POWER DISTRIBUTION ARRANGEMENT, SECTIONAL VIEW, BOM OF PUMP HOUSE-A |  | 1.16.1.3 | Unscheduled | No | No | 2020-04-17 18:00 | 2020-06-06 17:40 | 2020-05-12 18:00 | 2020-07-06 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5068 |  | 2020-02-13 11:44 | 7012-155-PVE-G-030 |  |  |  | A |  |  |  | 29.7297 | 0.009145 | 0.33 | Plan & Actual | Date |  | 0 | 0 | 0 | 124.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4608 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-17 18:00 | 2020-05-12 18:00 |  | 10 |  |  |  | 2020-04-27 17:40 | 2020-05-19 18:00 |  | 30 |  |  |  | 2020-05-02 17:40 | 2020-05-26 18:00 |  | 35 |  |  |  | 2020-05-08 23:59 | 2020-06-02 18:00 |  | 65 | 2020-08-03 12:06 |  |  | 2020-05-15 17:40 | 2020-06-23 18:00 |  | 80 | 2020-08-03 13:29 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-06 17:40 | 2020-06-23 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 265 |  |  |  | 101276
2209 | Task(Task)-->P (Procurement) | PROCUREMENT | 1.16.2 | 1.16 | Work In Progress | No | No | 2019-12-17 09:00 | 2020-10-27 18:00 | 2020-01-13 09:00 | 2021-06-07 18:00 |  |  | 2020-01-13 10:57 |  |  |  | 98.7225 | 23.7083 | [15 empty] | 9.4708 | 0.057156 | 5.62 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4610 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019659
2210 | Task(Task)-->P (Procurement) | PURCHASE REQUISITION | 1.16.2.1 | 1.16.2 | Work In Progress | No | No | 2019-12-17 09:00 | 2020-03-20 18:00 | 2020-01-13 09:00 | 2020-05-29 18:00 |  |  | 2020-01-13 10:57 |  |  |  | 100 | 96.4248 | [15 empty] | 4.9911 | 0.002853 | 0.28 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4611 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019660
2211 | Task(Task)-->P (Procurement) | Building Structure |  | 1.16.2.1 | Completed | No | No | 2020-03-18 09:00 | 2020-03-18 18:00 | 2020-05-29 09:00 | 2020-05-29 18:00 |  |  | 2020-05-31 17:35 | 2020-05-31 17:35 |  |  | 100 | 100 | [15 empty] | 71.4286 | 0.002038 | 0.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4612 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019661
2212 | Task(Task)-->P (Procurement) | LPBS |  | 1.16.2.1 | Unscheduled | No | No | 2020-03-20 09:00 | 2020-03-20 18:00 | 2020-04-14 09:00 | 2020-04-14 18:00 | [6 empty] | 100 | 0 | [15 empty] | 3.5714 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4613 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019662
2213 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR UTILITY SYSTEM |  | 1.16.2.1 | Completed | No | No | 2019-12-17 09:00 | 2019-12-17 18:00 | 2020-01-13 09:00 | 2020-01-13 18:00 |  |  | 2020-01-13 10:57 | 2020-01-13 10:57 |  |  | 100 | 100 | [15 empty] | 25 | 0.000713 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4614 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019663
2214 | Task(Task)-->P (Procurement) | TECHNICAL CLEARANCE | 1.16.2.2 | 1.16.2 | Work In Progress | No | No | 2019-12-18 09:00 | 2020-04-04 18:00 | 2020-01-13 09:00 | 2020-06-12 18:00 |  |  | 2020-04-11 10:57 |  |  |  | 100 | 96.4248 | [15 empty] | 4.9911 | 0.002853 | 0.28 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4615 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019664
2215 | Task(Task)-->P (Procurement) | Building Structure |  | 1.16.2.2 | Completed | No | No | 2020-03-19 09:00 | 2020-03-25 18:00 | 2020-05-29 09:00 | 2020-05-29 18:00 |  |  | 2020-05-29 17:31 | 2020-05-29 17:31 |  |  | 100 | 100 | [15 empty] | 71.4286 | 0.002038 | 0.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4616 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019665
2216 | Task(Task)-->P (Procurement) | LPBS |  | 1.16.2.2 | Unscheduled | No | No | 2020-03-21 09:00 | 2020-04-04 18:00 | 2020-04-14 09:00 | 2020-06-12 18:00 | [6 empty] | 100 | 0 | [15 empty] | 3.5714 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4617 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019666
2217 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR UTILITY SYSTEM |  | 1.16.2.2 | Completed | No | No | 2019-12-18 09:00 | 2020-01-01 18:00 | 2020-01-13 09:00 | 2020-04-11 18:00 |  |  | 2020-04-11 10:57 | 2020-04-11 10:57 |  |  | 100 | 100 | [15 empty] | 25 | 0.000713 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4618 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019667
2218 | Task(Task)-->P (Procurement) | ORDERING | 1.16.2.3 | 1.16.2 | Work In Progress | No | No | 2020-01-02 09:00 | 2020-04-24 18:00 | 2020-04-11 09:00 | 2020-08-19 18:00 |  |  | 2020-04-12 15:47 |  |  |  | 100 | 96.4242 | [15 empty] | 9.9822 | 0.005705 | 0.56 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4619 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019668
2219 | Task(Task)-->P (Procurement) | Building Structure |  | 1.16.2.3 | Completed | No | No | 2020-03-26 09:00 | 2020-04-24 18:00 | 2020-05-29 09:00 | 2020-05-31 23:59 |  |  | 2020-05-31 17:38 | 2020-05-31 17:39 |  |  | 100 | 100 | [15 empty] | 71.4286 | 0.004075 | 0.4 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4620 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019669
2220 | Task(Task)-->P (Procurement) | LPBS |  | 1.16.2.3 | Unscheduled | No | No | 2020-04-05 | 2020-04-20 18:00 | 2020-06-12 09:00 | 2020-08-19 18:00 | [6 empty] | 100 | 0 | [15 empty] | 3.5714 | 0.000204 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4621 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019670
2221 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR UTILITY SYSTEM |  | 1.16.2.3 | Completed | No | No | 2020-01-02 09:00 | 2020-01-16 18:00 | 2020-04-11 09:00 | 2020-07-20 18:00 |  |  | 2020-04-12 15:47 | 2020-06-20 15:47 |  |  | 100 | 100 | [15 empty] | 25 | 0.001426 | 0.14 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4622 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019671
2222 | Task(Task)-->P (Procurement) | ITP APPROVAL | 1.16.2.4 | 1.16.2 | Work In Progress | No | No | 2020-01-17 09:00 | 2020-05-30 18:00 | 2020-05-31 | 2020-10-10 18:00 |  |  | 2020-07-29 15:02 |  |  |  | 100 | 3.5752 | [15 empty] | 4.9911 | 0.002853 | 0.28 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4623 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019672
2223 | Task(Task)-->P (Procurement) | Building Structure |  | 1.16.2.4 | Unscheduled | No | No | 2020-04-25 09:00 | 2020-05-01 18:00 | 2020-05-31 | 2020-08-04 18:00 | [6 empty] | 100 | 0 | [15 empty] | 71.4286 | 0.002038 | 0.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4624 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019673
2224 | Task(Task)-->P (Procurement) | LPBS |  | 1.16.2.4 | Completed | No | No | 2020-04-21 09:00 | 2020-05-30 18:00 | 2020-07-29 09:00 | 2020-08-21 18:00 |  |  | 2020-07-29 15:02 | 2020-08-22 12:54 |  |  | 100 | 100 | [15 empty] | 3.5714 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4625 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019674
2225 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR UTILITY SYSTEM |  | 1.16.2.4 | Unscheduled | No | No | 2020-01-17 09:00 | 2020-02-25 18:00 | 2020-09-08 09:00 | 2020-10-10 18:00 | [6 empty] | 100 | 0 | [15 empty] | 25 | 0.000713 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4626 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019675
2226 | Task(Task)-->P (Procurement) | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE | 1.16.2.5 | 1.16.2 | Work In Progress | No | No | 2020-01-17 09:00 | 2020-06-04 18:00 | 2020-05-31 | 2020-10-30 18:00 |  |  | 2020-07-07 10:15 |  |  |  | 100 | 28.5781 | [15 empty] | 14.9733 | 0.008558 | 0.84 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4627 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019676
2227 | Task(Task)-->P (Procurement) | Building Structure |  | 1.16.2.5 | Unscheduled | No | No | 2020-04-17 09:00 | 2020-04-23 18:00 | 2020-05-31 | 2020-10-30 18:00 | [6 empty] | 100 | 0 | [15 empty] | 71.4286 | 0.006113 | 0.6 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4628 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019677
2228 | Task(Task)-->P (Procurement) | LPBS |  | 1.16.2.5 | Completed | No | No | 2020-04-21 09:00 | 2020-06-04 18:00 | 2020-07-25 09:00 | 2020-08-22 18:00 |  |  | 2020-07-24 18:45 | 2020-08-22 12:58 |  |  | 100 | 100 | [15 empty] | 3.5714 | 0.000306 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4629 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019678
2229 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR UTILITY SYSTEM |  | 1.16.2.5 | Completed | No | No | 2020-01-17 09:00 | 2020-03-01 23:59 | 2020-07-07 09:00 | 2020-09-29 18:00 |  |  | 2020-07-07 10:15 | 2020-09-29 14:40 |  |  | 100 | 100 | [15 empty] | 25 | 0.00214 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4630 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019679
2230 | Task(Task)-->P (Procurement) | MANUFACTURING & RECEIPT AT SITE (MRN) | 1.16.2.6 | 1.16.2 | Unscheduled | No | No | 2020-03-02 09:00 | 2020-10-27 18:00 | 2020-08-23 | 2021-06-07 18:00 |  |  | 2020-08-22 13:01 |  |  |  | 97.8733 | 0 | [15 empty] | 60.0713 | 0.034334 | 3.37 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4631 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019680
2231 | Task(Task)-->P (Procurement) | Water tanks |  | 1.16.2.6 | Unscheduled | No | No | 2020-05-02 09:00 | 2020-07-30 18:00 | 2020-10-31 09:00 | 2021-01-28 18:00 | [6 empty] | 100 | 0 | [15 empty] | 70.6231 | 0.024248 | 2.38 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4632 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019681
2232 | Task(Task)-->P (Procurement) | LPBS |  | 1.16.2.6 | Unscheduled | No | No | 2020-06-05 09:00 | 2020-09-16 18:00 | 2020-08-23 | 2020-12-04 18:00 |  |  | 2020-08-22 13:01 |  |  |  | 100 | 0 | [15 empty] | 3.8576 | 0.001324 | 0.13 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4633 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019682
2233 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR UTILITY SYSTEM |  | 1.16.2.6 | Unscheduled | No | No | 2020-03-02 09:00 | 2020-10-27 18:00 | 2020-10-11 | 2021-06-07 18:00 |  |  | 2020-09-29 16:44 |  |  |  | 91.6667 | 0 | [15 empty] | 25.5193 | 0.008762 | 0.86 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4634 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019683
2234 | Task(Task)-->C (Construction) | CONSTRUCTION | 1.16.3 | 1.16 | Unscheduled | No | No | 2020-05-30 09:00 | 2021-09-07 18:00 | 2020-08-01 09:00 | 2022-03-30 18:00 | [6 empty] | 50.6553 | 0 | [15 empty] | 71.8402 | 0.43355 | 42.63 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4635 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019684
2235 | Task(Task)-->C (Construction) | CIVIL | 1.16.3.1 | 1.16.3 | Unscheduled | No | No | 2020-05-30 09:00 | 2021-02-19 18:00 | 2020-08-01 09:00 | 2021-05-26 18:00 | [6 empty] | 66.8143 | 0 | [15 empty] | 75.8152 | 0.3287 | 32.32 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4636 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019685
2236 | Task(Task)-->C (Construction) | AVAILABILITY OF FRONT BY NTPC |  | 1.16.3.1 | Unscheduled | No | No | 2020-05-30 09:00 | 2020-05-30 18:00 | 2020-08-01 09:00 | 2020-08-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4637 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019686
2237 | Task(Task)-->C (Construction) | EXCAVATION |  | 1.16.3.1 | Unscheduled | No | No | 2020-06-06 09:00 | 2020-06-19 18:00 | 2020-08-22 09:00 | 2020-09-04 18:00 | [6 empty] | 100 | 0 | [15 empty] | 2.63 | 0.008645 | 0.85 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 3203 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4638 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | Excavation | [21 empty] | 1019687
2238 | Task(Task)-->C (Construction) | PCC |  | 1.16.3.1 | Unscheduled | No | No | 2020-06-20 09:00 | 2020-06-29 18:00 | 2020-09-24 09:00 | 2020-10-03 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.95916 | 0.003153 | 0.31 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4639 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | PCC | [21 empty] | 1019688
2239 | Task(Task)-->C (Construction) | RAFT |  | 1.16.3.1 | Unscheduled | No | No | 2020-06-30 09:00 | 2020-07-24 18:00 | 2020-10-04 | 2020-10-28 18:00 | [6 empty] | 100 | 0 | [15 empty] | 6.9926 | 0.022985 | 2.26 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4640 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019689
2240 | Task(Task)-->C (Construction) | PLINTH BEAM |  | 1.16.3.1 | Unscheduled | No | No | 2020-07-27 09:00 | 2020-08-06 18:00 | 2020-10-31 09:00 | 2020-11-10 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.8354 | 0.002746 | 0.27 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4641 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019690
2241 | Task(Task)-->C (Construction) | PUMP FOUNDATION & TRENCH |  | 1.16.3.1 | Unscheduled | No | No | 2020-08-01 09:00 | 2020-08-16 23:59 | 2020-11-05 09:00 | 2020-11-20 18:00 | [6 empty] | 100 | 0 | [15 empty] | 1.2376 | 0.004068 | 0.4 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4642 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019691
2242 | Task(Task)-->C (Construction) | GRADE SLAB |  | 1.16.3.1 | Unscheduled | No | No | 2020-08-14 09:00 | 2020-09-13 23:59 | 2020-11-18 09:00 | 2020-12-18 18:00 | [6 empty] | 100 | 0 | [15 empty] | 40.3775 | 0.13272 | 13.05 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 697 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4643 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019692
2243 | Task(Task)-->C (Construction) | COLUMN AND ROOF SLAB |  | 1.16.3.1 | Unscheduled | No | No | 2020-09-01 09:00 | 2020-10-13 18:00 | 2020-12-06 | 2021-01-17 23:59 | [6 empty] | 86.0465 | 0 | [15 empty] | 2.2896 | 0.007526 | 0.74 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4644 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019693
2244 | Task(Task)-->C (Construction) | WATER TANK FOUNDATION |  | 1.16.3.1 | Unscheduled | No | No | 2020-06-20 09:00 | 2020-11-02 18:00 | 2020-09-05 09:00 | 2021-01-18 18:00 | [6 empty] | 80.8824 | 0 | [15 empty] | 14.604 | 0.048003 | 4.72 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 178 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4645 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019694
2245 | Task(Task)-->C (Construction) | BRICK WORK |  | 1.16.3.1 | Unscheduled | No | No | 2020-10-14 09:00 | 2020-11-13 18:00 | 2021-01-18 09:00 | 2021-02-17 18:00 | [6 empty] | 0 | 0 | [15 empty] | 2.4752 | 0.008136 | 0.8 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4646 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019695
2246 | Task(Task)-->C (Construction) | PLASTER |  | 1.16.3.1 | Unscheduled | No | No | 2020-11-04 09:00 | 2020-12-04 18:00 | 2021-02-08 09:00 | 2021-03-10 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0.71163 | 0.002339 | 0.23 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 410 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4647 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019696
2247 | Task(Task)-->C (Construction) | DOOR , WINDOW, MONORAIL DOOR & ROLLING SHUTTER |  | 1.16.3.1 | Unscheduled | No | No | 2020-11-28 09:00 | 2020-12-20 23:59 | 2021-03-04 09:00 | 2021-03-26 18:00 | [6 empty] | 0 | 0 | [15 empty] | 10.6126 | 0.034884 | 3.43 | Plan & Actual | Quantity | Lot | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4648 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019697
2248 | Task(Task)-->C (Construction) | FLOORING |  | 1.16.3.1 | Unscheduled | No | No | 2020-11-28 09:00 | 2020-12-25 18:00 | 2021-03-04 09:00 | 2021-03-31 18:00 | [6 empty] | 0 | 0 | [15 empty] | 6.0644 | 0.019934 | 1.96 | Plan & Actual | Quantity | Lot | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4649 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019698
2249 | Task(Task)-->C (Construction) | ROOF WATER PROFING & RWDC PIPE |  | 1.16.3.1 | Unscheduled | No | No | 2020-11-11 09:00 | 2020-12-11 18:00 | 2021-02-15 09:00 | 2021-03-17 18:00 | [6 empty] | 0 | 0 | [15 empty] | 2.5371 | 0.00834 | 0.82 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 171 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4650 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019699
2250 | Task(Task)-->C (Construction) | GARLAND DRAIN & PLINTH PROTECTION |  | 1.16.3.1 | Unscheduled | No | No | 2020-11-28 09:00 | 2021-01-09 18:00 | 2021-03-04 09:00 | 2021-04-15 18:00 | [6 empty] | 0 | 0 | [15 empty] | 7.1473 | 0.023493 | 2.31 | Plan & Actual | Quantity | Lot | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4651 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019700
2251 | Task(Task)-->C (Construction) | PAINTING |  | 1.16.3.1 | Unscheduled | No | No | 2020-12-21 09:00 | 2021-02-19 18:00 | 2021-03-27 09:00 | 2021-05-26 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0.52599 | 0.001729 | 0.17 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 342 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4652 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019701
2252 | Task(Task)-->C (Construction) | MECHANICAL | 1.16.3.2 | 1.16.3 | Unscheduled | No | No | 2020-12-01 09:00 | 2021-06-08 18:00 | 2021-02-16 09:00 | 2021-06-06 23:59 | [6 empty] | 0 | 0 | [15 empty] | 13.6289 | 0.059089 | 5.81 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4653 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019702
2253 | Task(Task)-->C (Construction) | WATER TANKS |  | 1.16.3.2 | Unscheduled | No | No | 2020-12-01 09:00 | 2021-01-29 18:00 | 2021-02-16 09:00 | 2021-04-16 18:00 | [6 empty] | 0 | 0 | [15 empty] | 90.8778 | 0.053699 | 5.28 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4654 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019703
2254 | Task(Task)-->C (Construction) | ERECTION OF MONORAIL & HOISTS |  | 1.16.3.2 | Unscheduled | No | No | 2021-03-20 09:00 | 2021-04-09 18:00 | 2021-03-18 09:00 | 2021-04-07 18:00 | [6 empty] | 0 | 0 | [15 empty] | 4.475 | 0.002644 | 0.26 | Plan & Actual | Quantity | Set | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5480 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019704
2255 | Task(Task)-->C (Construction) | ERECTION OF PUMPS |  | 1.16.3.2 | Unscheduled | No | No | 2021-04-10 09:00 | 2021-06-08 18:00 | 2021-04-08 09:00 | 2021-06-06 23:59 | [6 empty] | 0 | 0 | [15 empty] | 4.6472 | 0.002746 | 0.27 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4655 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019705
2256 | Task(Task)-->C (Construction) | ELECTRICAL & INSTRUMENTATION | 1.16.3.3 | 1.16.3 | Unscheduled | No | No | 2020-12-05 09:00 | 2021-08-28 18:00 | 2021-03-11 09:00 | 2022-03-20 23:59 | [6 empty] | 0 | 0 | [15 empty] | 6.9435 | 0.030104 | 2.96 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5259 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019706
2257 | Task(Task)-->C (Construction) | CABLE TRAY |  | 1.16.3.3 | Unscheduled | No | No | 2020-12-05 09:00 | 2020-12-06 23:59 | 2021-03-11 09:00 | 2021-03-12 18:00 | [6 empty] | 0 | 0 | [15 empty] | 7.1186 | 0.002143 | 0.21 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4656 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019707
2258 | Task(Task)-->C (Construction) | POWER CABLE |  | 1.16.3.3 | Unscheduled | No | No | 2021-06-09 09:00 | 2021-06-15 18:00 | 2021-07-25 | 2021-07-31 18:00 | [6 empty] | 0 | 0 | [15 empty] | 10.5085 | 0.003163 | 0.31 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 2220 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5258 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019708
2259 | Task(Task)-->C (Construction) | CONTROL CABLE |  | 1.16.3.3 | Unscheduled | No | No | 2021-06-13 | 2021-06-15 18:00 | 2021-09-25 09:00 | 2021-09-27 18:00 | [6 empty] | 0 | 0 | [15 empty] | 16.9492 | 0.005102 | 0.5 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4657 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019709
2260 | Task(Task)-->C (Construction) | EARTHING |  | 1.16.3.3 | Unscheduled | No | No | 2021-06-13 | 2021-06-15 18:00 | 2021-07-29 09:00 | 2021-07-31 18:00 | [6 empty] | 0 | 0 | [15 empty] | 2.7119 | 0.000816 | 0.08 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 377 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5381 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019710
2261 | Task(Task)-->C (Construction) | EARTH PIT |  | 1.16.3.3 | Unscheduled | No | No | 2021-01-07 09:00 | 2021-01-09 18:00 | 2021-04-13 09:00 | 2021-04-15 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5382 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019711
2262 | Task(Task)-->C (Construction) | LIGHTING |  | 1.16.3.3 | Unscheduled | No | No | 2020-12-05 09:00 | 2020-12-11 18:00 | 2021-03-11 09:00 | 2021-03-17 18:00 | [6 empty] | 0 | 0 | [15 empty] | 10.5085 | 0.003163 | 0.31 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5383 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019712
2263 | Task(Task)-->C (Construction) | FIELD INTRUMENTS |  | 1.16.3.3 | Unscheduled | No | No | 2021-06-12 09:00 | 2021-06-16 18:00 | 2021-09-24 09:00 | 2021-09-28 18:00 | [6 empty] | 0 | 0 | [15 empty] | 52.2034 | 0.015715 | 1.54 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5384 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019713
2264 | Task(Task)-->C (Construction) | MOTOR TERMINATION |  | 1.16.3.3 | Unscheduled | No | No | 2021-06-16 09:00 | 2021-06-19 18:00 | 2021-09-25 09:00 | 2021-09-28 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5385 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019714
2265 | Task(Task)-->C (Construction) | NO LOAD RUN OF MOTOR |  | 1.16.3.3 | Unscheduled | No | No | 2021-08-22 | 2021-08-28 18:00 | 2022-03-14 09:00 | 2022-03-20 23:59 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5481 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019715
2266 | Task(Task)-->C (Construction) | NO LOAD COMMISSIONING & SYSTEM READYNESS FOR LOAD & TRIAL OPERATION |  | 1.16.3 | Unscheduled | No | No | 2021-08-29 | 2021-09-07 18:00 | 2022-03-21 09:00 | 2022-03-30 18:00 | [6 empty] | 0 | 0 | [15 empty] | 3.6125 | 0.015662 | 1.54 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5386 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019716
2267 | Task(Task)-->E (Engineering) | PUMP HOUSE -B NEAR KDTP-2 | 1.17 | 1 | Work In Progress | No | No | 2019-12-17 09:00 | 2021-09-13 18:00 | 2020-01-13 09:00 | 2022-04-05 18:00 |  |  | 2020-01-13 10:57 |  |  |  | 44.5776 | 10.3909 | [15 empty] | 0.36789 | 0.3679 | 36.18 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4658 | 0 | 1 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019717
2268 | Task(Task)-->E (Engineering) | ENGINEERING | 1.17.1 | 1.17 | Work In Progress | No | No | 2020-01-22 18:00 | 2020-08-14 17:40 | 2020-05-06 18:00 | 2020-11-02 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 76.3229 | [15 empty] | 8.7894 | 0.032336 | 3.18 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4659 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019718
2269 | Task(Task)-->E (Engineering) | MECHANICAL | 1.17.1.1 | 1.17.1 | Unscheduled | No | No | 2020-01-22 18:00 | 2020-03-25 17:40 | 2020-05-22 18:00 | 2020-07-17 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 65 | [15 empty] | 24.2152 | 0.00783 | 0.54 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4660 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036122
2270 | Task(Task)-->E (Engineering) | PUMP HOUSE -2 ARRANGEMENT ( PUMP HOUSE B) ALONG WITH PIPING LAYOUT & MS WATER TANK |  | 1.17.1.1 | Unscheduled | No | No | 2020-01-22 18:00 | 2020-03-25 17:40 | 2020-05-22 18:00 | 2020-07-17 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-DS-GA-6009 |  | 2020-02-13 11:40 | 7012-155-PVM-B-039 |  |  |  | A |  |  |  | 100 | 0.00783 | 0.54 | Plan & Actual | Date |  | 0 | 0 | 0 | 200 | 0 | 11.1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4661 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-22 18:00 | 2020-05-22 18:00 |  | 10 |  |  |  | 2020-02-13 17:40 | 2020-06-12 18:00 |  | 30 |  |  |  | 2020-02-19 17:40 | 2020-06-19 18:00 |  | 35 | 2020-06-19 09:46 |  |  | 2020-02-26 23:59 | 2020-06-26 18:00 |  | 65 | 2020-06-19 17:16 |  |  | 2020-03-03 17:40 | 2020-07-17 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-25 17:40 | 2020-07-17 18:00 |  | 100 | [122 empty] | Ram Prasad Roy |  |  |  |  | U - Water Media & Utility System | [16 empty] | 84 |  |  |  | 101098
2271 | Task(Task)-->E (Engineering) | CIVIL | 1.17.1.2 | 1.17.1 | Work In Progress | No | No | 2020-04-16 18:00 | 2020-08-14 17:40 | 2020-06-26 18:00 | 2020-11-02 18:00 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 79.8901 | [15 empty] | 40.8072 | 0.013195 | 0.91 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4664 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036123
2272 | Task(Task)-->E (Engineering) | Pump House-B : DESIGN CALCULATION |  | 1.17.1.2 | Completed | No | No | 2020-04-16 18:00 | 2020-06-15 17:40 | 2020-07-28 09:00 | 2020-08-17 18:00 |  |  | 2020-02-21 15:37 | 2020-08-17 22:44 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0023 |  | 2020-02-13 11:42 | 7012-155-PVC-U-078 |  |  |  | A |  |  |  | 40.6593 | 0.005365 | 0.37 | Plan & Actual | Date |  | 0 | 0 | 0 | 136.02 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4669 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-16 18:00 | 2020-06-26 18:00 |  | 10 |  |  |  | 2020-05-05 17:40 | 2020-07-21 18:00 |  | 30 |  |  |  | 2020-05-12 17:40 | 2020-07-24 18:00 |  | 35 |  |  |  | 2020-05-17 23:59 | 2020-07-31 18:00 |  | 65 | 2020-08-13 19:56 |  |  | 2020-05-22 17:40 | 2020-08-21 18:00 |  | 80 | 2020-08-17 22:40 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-15 17:40 | 2020-09-04 18:00 |  | 100 | 2020-08-17 22:45 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 179 |  |  |  | 101189
2273 | Task(Task)-->E (Engineering) | Pump House-B : NUM & RC DETAILS (SHT 1) |  | 1.17.1.2 | Completed | No | No | 2020-04-16 18:00 | 2020-06-15 17:40 | 2020-07-28 09:00 | 2020-08-17 18:00 |  |  | 2020-02-21 15:37 | 2020-08-17 22:44 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-NR-0028 |  | 2020-02-13 11:42 | 7012-155-PVC-C-079 |  |  |  | A |  |  |  | 13.1868 | 0.00174 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 45.03 | 0 | 5.1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4665 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-16 18:00 | 2020-06-26 18:00 |  | 10 |  |  |  | 2020-05-05 17:40 | 2020-07-21 18:00 |  | 30 |  |  |  | 2020-05-12 17:40 | 2020-07-24 18:00 |  | 35 | 2020-07-26 10:51 |  |  | 2020-05-17 23:59 | 2020-07-31 18:00 |  | 65 | 2020-08-13 19:56 |  |  | 2020-05-22 17:40 | 2020-08-21 18:00 |  | 80 | 2020-08-17 22:39 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-15 17:40 | 2020-09-04 18:00 |  | 100 | 2020-08-17 22:45 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 180 |  |  |  | 101190
2274 | Task(Task)-->E (Engineering) | Pump House-B : NUM & RC DETAILS (SHT 2) |  | 1.17.1.2 | Completed | No | No | 2020-04-16 18:00 | 2020-06-15 17:40 | 2020-07-28 09:00 | 2020-08-17 18:00 |  |  | 2020-02-21 15:37 | 2020-08-17 22:44 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-NR-0029 |  | 2020-02-13 11:42 | 7012-155-PVC-C-080 |  |  |  | A |  |  |  | 13.1868 | 0.00174 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 45.03 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4666 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-16 18:00 | 2020-06-26 18:00 |  | 10 |  |  |  | 2020-05-05 17:40 | 2020-07-21 18:00 |  | 30 |  |  |  | 2020-05-12 17:40 | 2020-07-24 18:00 |  | 35 |  |  |  | 2020-05-17 23:59 | 2020-07-31 18:00 |  | 65 | 2020-08-13 19:56 |  |  | 2020-05-22 17:40 | 2020-08-21 18:00 |  | 80 | 2020-08-17 22:36 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-15 17:40 | 2020-09-04 18:00 |  | 100 | 2020-08-17 22:45 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 181 |  |  |  | 101191
2275 | Task(Task)-->E (Engineering) | Pump House-B : NUM & RC DETAILS (SHT 3) |  | 1.17.1.2 | Unscheduled | No | No | 2020-04-16 18:00 | 2020-06-15 17:40 | 2020-06-26 18:00 | 2020-09-04 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-NR-0030 |  | 2020-02-13 11:42 | 7012-155-PVC-C-081 |  |  |  | A |  |  |  | 13.1868 | 0.00174 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 45.03 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4667 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-16 18:00 | 2020-06-26 18:00 |  | 10 |  |  |  | 2020-05-05 17:40 | 2020-07-21 18:00 |  | 30 |  |  |  | 2020-05-12 17:40 | 2020-07-24 18:00 |  | 35 |  |  |  | 2020-05-17 23:59 | 2020-07-31 18:00 |  | 65 |  |  |  | 2020-05-22 17:40 | 2020-08-21 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-15 17:40 | 2020-09-04 18:00 |  | 100 | [122 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 182 |  |  |  | 101192
2276 | Task(Task)-->E (Engineering) | ARCHITECTURAL GA OF PUMP HOUSE B |  | 1.17.1.2 | Unscheduled | No | No | 2020-06-15 18:00 | 2020-08-14 17:40 | 2020-07-27 18:00 | 2020-11-02 18:00 |  |  | 2020-02-21 15:39 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-AR-0009 |  | 2020-02-13 11:43 | 7012-155-PVC-C-115 |  |  |  | A |  |  |  | 19.7802 | 0.00261 | 0.18 | Plan & Actual | Date |  | 0 | 0 | 0 | 68.01 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4668 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-06-15 18:00 | 2020-07-27 18:00 |  | 10 |  |  |  | 2020-07-03 17:40 | 2020-08-21 18:00 |  | 30 |  |  |  | 2020-07-09 17:40 | 2020-08-24 18:00 |  | 35 | 2020-09-14 12:35 |  |  | 2020-07-16 23:59 | 2020-08-31 18:00 |  | 65 | 2020-09-14 20:16 |  |  | 2020-07-22 17:40 | 2020-09-21 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-08-14 17:40 | 2020-10-05 18:00 |  | 100 | [122 empty] | Chetan Khodke |  |  |  |  | A - Architecture | [16 empty] | 216 |  |  |  | 101226
2277 | Task(Task)-->E (Engineering) | ELECTRICAL | 1.17.1.3 | 1.17.1 | Unscheduled | No | No | 2020-04-23 18:00 | 2020-06-19 17:40 | 2020-05-06 18:00 | 2020-07-06 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 | [15 empty] | 34.9776 | 0.01131 | 0.78 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4670 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036124
2278 | Task(Task)-->E (Engineering) | EQUIPMENT, CABLE ROUTING, EARTHING & LIGHTNING LAYOUT WITH PLAN, SECTIONAL VIEWS & BOM OF PUMP HOUSE-B NEAR KDTP-2 |  | 1.17.1.3 | Unscheduled | No | No | 2020-04-23 18:00 | 2020-06-11 17:40 | 2020-05-06 18:00 | 2020-07-01 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5058 |  | 2020-02-13 11:44 | 7012-155-PVE-F-020 |  |  |  | A |  |  |  | 57.6923 | 0.006525 | 0.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 165.48 | 0 | 33.47 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4671 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-23 18:00 | 2020-05-06 18:00 |  | 10 |  |  |  | 2020-05-01 17:40 | 2020-05-20 18:00 |  | 30 | 2020-06-19 10:07 |  |  | 2020-05-07 17:40 | 2020-05-27 18:00 |  | 35 | 2020-06-23 14:41 |  |  | 2020-05-14 23:59 | 2020-06-03 18:00 |  | 65 | 2020-08-03 11:20 |  |  | 2020-05-20 17:40 | 2020-06-24 18:00 |  | 80 | 2020-08-03 11:27 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-11 17:40 | 2020-06-24 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 255 |  |  |  | 101266
2279 | Task(Task)-->E (Engineering) | LIGHTING LAYOUT PLAN WITH POWER DISTRIBUTION ARRANGEMENT, SECTIONAL VIEW, BOM OF PUMP HOUSE-B |  | 1.17.1.3 | Unscheduled | No | No | 2020-04-30 18:00 | 2020-06-19 17:40 | 2020-05-20 18:00 | 2020-07-06 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5069 |  | 2020-02-13 11:44 | 7012-155-PVE-G-031 |  |  |  | A |  |  |  | 42.3077 | 0.004785 | 0.33 | Plan & Actual | Date |  | 0 | 0 | 0 | 124.21 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4672 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-30 18:00 | 2020-05-20 18:00 |  | 10 |  |  |  | 2020-05-08 17:40 | 2020-05-27 18:00 |  | 30 | 2020-07-20 12:23 |  |  | 2020-05-15 17:40 | 2020-06-03 18:00 |  | 35 |  |  |  | 2020-05-21 23:59 | 2020-06-10 18:00 |  | 65 | 2020-07-20 12:36 |  |  | 2020-05-28 17:40 | 2020-07-01 18:00 |  | 80 | 2020-07-28 17:53 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-19 17:40 | 2020-07-01 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 266 |  |  |  | 101277
2280 | Task(Task)-->P (Procurement) | PROCUREMENT | 1.17.2 | 1.17 | Work In Progress | No | No | 2019-12-17 09:00 | 2020-10-27 18:00 | 2020-01-13 09:00 | 2021-06-08 18:00 |  |  | 2020-01-13 10:57 |  |  |  | 98.7224 | 23.7073 | [15 empty] | 15.5334 | 0.057147 | 5.62 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4674 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019722
2281 | Task(Task)-->P (Procurement) | PURCHASE REQUISITION | 1.17.2.1 | 1.17.2 | Work In Progress | No | No | 2019-12-17 09:00 | 2020-03-20 18:00 | 2020-01-13 09:00 | 2020-05-29 18:00 |  |  | 2020-01-13 10:57 |  |  |  | 100 | 96.4236 | [15 empty] | 4.9911 | 0.002852 | 0.28 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4675 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019723
2282 | Task(Task)-->P (Procurement) | Building Structure |  | 1.17.2.1 | Completed | No | No | 2020-03-18 09:00 | 2020-03-18 18:00 | 2020-05-29 09:00 | 2020-05-29 18:00 |  |  | 2020-05-31 17:35 | 2020-05-31 17:35 |  |  | 100 | 100 | [15 empty] | 71.4286 | 0.002037 | 0.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4676 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019724
2283 | Task(Task)-->P (Procurement) | LPBS |  | 1.17.2.1 | Unscheduled | No | No | 2020-03-20 09:00 | 2020-03-20 18:00 | 2020-04-14 09:00 | 2020-04-14 18:00 | [6 empty] | 100 | 0 | [15 empty] | 3.5714 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4677 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019725
2284 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR UTILITY SYSTEM |  | 1.17.2.1 | Completed | No | No | 2019-12-17 09:00 | 2019-12-17 18:00 | 2020-01-13 09:00 | 2020-01-13 18:00 |  |  | 2020-01-13 10:57 | 2020-01-13 10:57 |  |  | 100 | 100 | [15 empty] | 25 | 0.000713 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4678 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019726
2285 | Task(Task)-->P (Procurement) | TECHNICAL CLEARANCE | 1.17.2.2 | 1.17.2 | Work In Progress | No | No | 2019-12-18 09:00 | 2020-04-04 18:00 | 2020-01-13 09:00 | 2020-06-12 18:00 |  |  | 2020-04-11 10:57 |  |  |  | 100 | 96.4236 | [15 empty] | 4.9911 | 0.002852 | 0.28 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4679 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019727
2286 | Task(Task)-->P (Procurement) | Building Structure |  | 1.17.2.2 | Completed | No | No | 2020-03-19 09:00 | 2020-03-25 18:00 | 2020-05-29 09:00 | 2020-05-29 18:00 |  |  | 2020-05-29 17:31 | 2020-05-29 17:31 |  |  | 100 | 100 | [15 empty] | 71.4286 | 0.002037 | 0.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4680 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019728
2287 | Task(Task)-->P (Procurement) | LPBS |  | 1.17.2.2 | Unscheduled | No | No | 2020-03-21 09:00 | 2020-04-04 18:00 | 2020-04-14 09:00 | 2020-06-12 18:00 | [6 empty] | 100 | 0 | [15 empty] | 3.5714 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4681 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019729
2288 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR UTILITY SYSTEM |  | 1.17.2.2 | Completed | No | No | 2019-12-18 09:00 | 2020-01-01 18:00 | 2020-01-13 09:00 | 2020-04-11 18:00 |  |  | 2020-04-11 10:57 | 2020-04-11 10:57 |  |  | 100 | 100 | [15 empty] | 25 | 0.000713 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4682 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019730
2289 | Task(Task)-->P (Procurement) | ORDERING | 1.17.2.3 | 1.17.2 | Work In Progress | No | No | 2020-01-02 09:00 | 2020-04-24 18:00 | 2020-04-11 09:00 | 2020-08-20 18:00 |  |  | 2020-04-12 15:47 |  |  |  | 100 | 96.4242 | [15 empty] | 9.9822 | 0.005705 | 0.56 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4683 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019731
2290 | Task(Task)-->P (Procurement) | Building Structure |  | 1.17.2.3 | Completed | No | No | 2020-03-26 09:00 | 2020-04-24 18:00 | 2020-05-29 09:00 | 2020-05-31 23:59 |  |  | 2020-05-31 17:39 | 2020-05-31 17:39 |  |  | 100 | 100 | [15 empty] | 71.4286 | 0.004075 | 0.4 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4684 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019732
2291 | Task(Task)-->P (Procurement) | LPBS |  | 1.17.2.3 | Unscheduled | No | No | 2020-04-05 | 2020-04-20 18:00 | 2020-06-12 09:00 | 2020-08-19 18:00 | [6 empty] | 100 | 0 | [15 empty] | 3.5714 | 0.000204 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4685 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019733
2292 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR UTILITY SYSTEM |  | 1.17.2.3 | Completed | No | No | 2020-01-02 09:00 | 2020-01-16 18:00 | 2020-04-11 09:00 | 2020-08-20 18:00 |  |  | 2020-04-12 15:47 | 2020-06-20 15:47 |  |  | 100 | 100 | [15 empty] | 25 | 0.001426 | 0.14 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4686 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019734
2293 | Task(Task)-->P (Procurement) | ITP APPROVAL | 1.17.2.4 | 1.17.2 | Work In Progress | No | No | 2020-01-17 09:00 | 2020-05-30 18:00 | 2020-05-31 | 2020-10-11 23:59 |  |  | 2020-07-29 15:03 |  |  |  | 100 | 3.5764 | [15 empty] | 4.9911 | 0.002852 | 0.28 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4687 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019735
2294 | Task(Task)-->P (Procurement) | Building Structure |  | 1.17.2.4 | Unscheduled | No | No | 2020-04-25 09:00 | 2020-05-01 18:00 | 2020-05-31 | 2020-08-04 18:00 | [6 empty] | 100 | 0 | [15 empty] | 71.4286 | 0.002037 | 0.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4688 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019736
2295 | Task(Task)-->P (Procurement) | LPBS |  | 1.17.2.4 | Completed | No | No | 2020-04-21 09:00 | 2020-05-30 18:00 | 2020-07-29 09:00 | 2020-08-21 18:00 |  |  | 2020-07-29 15:03 | 2020-08-22 12:55 |  |  | 100 | 100 | [15 empty] | 3.5714 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4689 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019737
2296 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR UTILITY SYSTEM |  | 1.17.2.4 | Unscheduled | No | No | 2020-01-17 09:00 | 2020-02-25 18:00 | 2020-09-08 09:00 | 2020-10-11 23:59 | [6 empty] | 100 | 0 | [15 empty] | 25 | 0.000713 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4690 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019738
2297 | Task(Task)-->P (Procurement) | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE | 1.17.2.5 | 1.17.2 | Work In Progress | No | No | 2020-01-17 09:00 | 2020-06-04 18:00 | 2020-05-31 | 2020-10-30 18:00 |  |  | 2020-07-07 10:15 |  |  |  | 100 | 28.5731 | [15 empty] | 14.9733 | 0.008557 | 0.84 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4691 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019739
2298 | Task(Task)-->P (Procurement) | Building Structure |  | 1.17.2.5 | Unscheduled | No | No | 2020-04-17 09:00 | 2020-04-23 18:00 | 2020-05-31 | 2020-10-30 18:00 | [6 empty] | 100 | 0 | [15 empty] | 71.4286 | 0.006112 | 0.6 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4692 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019740
2299 | Task(Task)-->P (Procurement) | LPBS |  | 1.17.2.5 | Completed | No | No | 2020-04-21 09:00 | 2020-06-04 18:00 | 2020-07-25 09:00 | 2020-08-22 18:00 |  |  | 2020-07-24 18:41 | 2020-08-22 12:58 |  |  | 100 | 100 | [15 empty] | 3.5714 | 0.000306 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4693 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019741
2300 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR UTILITY SYSTEM |  | 1.17.2.5 | Completed | No | No | 2020-01-17 09:00 | 2020-03-01 23:59 | 2020-07-07 09:00 | 2020-09-29 18:00 |  |  | 2020-07-07 10:15 | 2020-09-29 14:41 |  |  | 100 | 100 | [15 empty] | 25 | 0.002139 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4694 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019742
2301 | Task(Task)-->P (Procurement) | MANUFACTURING & RECEIPT AT SITE (MRN) | 1.17.2.6 | 1.17.2 | Unscheduled | No | No | 2020-03-02 09:00 | 2020-10-27 18:00 | 2020-08-23 | 2021-06-08 18:00 |  |  | 2020-08-22 13:01 |  |  |  | 97.8733 | 0 | [15 empty] | 60.0713 | 0.034329 | 3.37 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4695 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019743
2302 | Task(Task)-->P (Procurement) | WATER TANK |  | 1.17.2.6 | Unscheduled | No | No | 2020-05-02 09:00 | 2020-07-30 18:00 | 2020-10-31 09:00 | 2021-01-28 18:00 | [6 empty] | 100 | 0 | [15 empty] | 70.6231 | 0.024244 | 2.38 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4696 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019744
2303 | Task(Task)-->P (Procurement) | LPBS |  | 1.17.2.6 | Unscheduled | No | No | 2020-06-05 09:00 | 2020-09-16 18:00 | 2020-08-23 | 2020-12-04 18:00 |  |  | 2020-08-22 13:01 |  |  |  | 100 | 0 | [15 empty] | 3.8576 | 0.001324 | 0.13 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4697 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019745
2304 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR UTILITY SYSTEM |  | 1.17.2.6 | Unscheduled | No | No | 2020-03-02 09:00 | 2020-10-27 18:00 | 2020-10-12 09:00 | 2021-06-08 18:00 |  |  | 2020-09-29 16:44 |  |  |  | 91.6667 | 0 | [15 empty] | 25.5193 | 0.008761 | 0.86 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4698 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019746
2305 | Task(Task)-->C (Construction) | CONSTRUCTION | 1.17.3 | 1.17 | Unscheduled | No | No | 2020-05-31 | 2021-09-13 18:00 | 2020-08-11 09:00 | 2022-04-05 18:00 | [6 empty] | 27.0269 | 0 | [15 empty] | 75.6772 | 0.27841 | 27.38 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4699 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019747
2306 | Task(Task)-->C (Construction) | CIVIL | 1.17.3.1 | 1.17.3 | Unscheduled | No | No | 2020-05-31 | 2021-01-23 18:00 | 2020-08-11 09:00 | 2021-04-30 18:00 | [6 empty] | 44.8753 | 0 | [15 empty] | 60.2264 | 0.16768 | 16.49 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4700 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019748
2307 | Task(Task)-->C (Construction) | AVAILABILITY OF FRONT BY NTPC |  | 1.17.3.1 | Unscheduled | No | No | 2020-05-31 | 2020-05-31 23:59 | 2020-08-11 09:00 | 2020-08-11 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4701 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019749
2308 | Task(Task)-->C (Construction) | EXCAVATION |  | 1.17.3.1 | Unscheduled | No | No | 2020-06-07 | 2020-06-18 18:00 | 2020-08-22 09:00 | 2020-09-02 18:00 | [6 empty] | 100 | 0 | [15 empty] | 2.7273 | 0.004573 | 0.45 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 1670 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4702 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | Excavation | [21 empty] | 1019750
2309 | Task(Task)-->C (Construction) | PCC |  | 1.17.3.1 | Unscheduled | No | No | 2020-06-19 09:00 | 2020-06-27 18:00 | 2020-09-24 09:00 | 2020-10-02 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.54545 | 0.000915 | 0.09 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4703 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | PCC | [21 empty] | 1019751
2310 | Task(Task)-->C (Construction) | RAFT |  | 1.17.3.1 | Unscheduled | No | No | 2020-06-28 | 2020-07-21 18:00 | 2020-10-03 09:00 | 2020-10-26 18:00 | [6 empty] | 100 | 0 | [15 empty] | 8.0606 | 0.013516 | 1.33 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4704 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019752
2311 | Task(Task)-->C (Construction) | PLINTH BEAM |  | 1.17.3.1 | Unscheduled | No | No | 2020-06-30 09:00 | 2020-07-10 18:00 | 2020-10-05 09:00 | 2020-10-15 18:00 | [6 empty] | 100 | 0 | [15 empty] | 1.6364 | 0.002744 | 0.27 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4705 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019753
2312 | Task(Task)-->C (Construction) | PUMP FOUNDATION & TRENCH |  | 1.17.3.1 | Unscheduled | No | No | 2020-07-05 | 2020-07-20 18:00 | 2020-10-10 09:00 | 2020-10-25 23:59 | [6 empty] | 100 | 0 | [15 empty] | 2.4242 | 0.004065 | 0.4 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4706 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019754
2313 | Task(Task)-->C (Construction) | GRADE SLAB |  | 1.17.3.1 | Unscheduled | No | No | 2020-07-18 09:00 | 2020-08-17 18:00 | 2020-10-23 09:00 | 2020-11-22 23:59 | [6 empty] | 100 | 0 | [15 empty] | 16.2424 | 0.027235 | 2.68 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 143 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4707 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019755
2314 | Task(Task)-->C (Construction) | COLUMN AND ROOF SLAB |  | 1.17.3.1 | Unscheduled | No | No | 2020-08-05 09:00 | 2020-09-16 18:00 | 2020-11-10 09:00 | 2020-12-22 18:00 | [6 empty] | 100 | 0 | [15 empty] | 4 | 0.006707 | 0.66 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4708 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019756
2315 | Task(Task)-->C (Construction) | WATER TANK FOUNDATION |  | 1.17.3.1 | Unscheduled | No | No | 2020-06-19 09:00 | 2020-10-11 23:59 | 2020-09-03 09:00 | 2020-12-26 18:00 | [6 empty] | 96.5217 | 0 | [15 empty] | 6.4242 | 0.010772 | 1.06 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4709 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019757
2316 | Task(Task)-->C (Construction) | BRICK WORK |  | 1.17.3.1 | Unscheduled | No | No | 2020-09-17 09:00 | 2020-10-17 18:00 | 2020-12-23 09:00 | 2021-01-22 18:00 | [6 empty] | 67.7419 | 0 | [15 empty] | 4.4848 | 0.00752 | 0.74 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4710 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019758
2317 | Task(Task)-->C (Construction) | PLASTER |  | 1.17.3.1 | Unscheduled | No | No | 2020-10-08 09:00 | 2020-11-07 18:00 | 2021-01-13 09:00 | 2021-02-12 18:00 | [6 empty] | 0 | 0 | [15 empty] | 1.2727 | 0.002134 | 0.21 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 378 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4711 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019759
2318 | Task(Task)-->C (Construction) | DOOR , WINDOW, MONORAIL DOOR & ROLLING SHUTTER |  | 1.17.3.1 | Unscheduled | No | No | 2020-11-01 | 2020-11-23 18:00 | 2021-02-06 09:00 | 2021-02-28 23:59 | [6 empty] | 0 | 0 | [15 empty] | 20.7879 | 0.034857 | 3.43 | Plan & Actual | Quantity | Lot | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4712 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019760
2319 | Task(Task)-->C (Construction) | FLOORING |  | 1.17.3.1 | Unscheduled | No | No | 2020-11-01 | 2020-11-28 18:00 | 2021-02-06 09:00 | 2021-03-05 18:00 | [6 empty] | 0 | 0 | [15 empty] | 11.8788 | 0.019918 | 1.96 | Plan & Actual | Quantity | Lot | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4713 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019761
2320 | Task(Task)-->C (Construction) | ROOF WATER PROFING & RWDC PIPE |  | 1.17.3.1 | Unscheduled | No | No | 2020-10-15 09:00 | 2020-11-14 18:00 | 2021-01-20 09:00 | 2021-02-19 18:00 | [6 empty] | 0 | 0 | [15 empty] | 4.5455 | 0.007622 | 0.75 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 156 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4714 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019762
2321 | Task(Task)-->C (Construction) | GARLAND DRAIN & PLINTH PROTECTION |  | 1.17.3.1 | Unscheduled | No | No | 2020-11-01 | 2020-12-13 23:59 | 2021-02-06 09:00 | 2021-03-20 18:00 | [6 empty] | 0 | 0 | [15 empty] | 14 | 0.023475 | 2.31 | Plan & Actual | Quantity | Lot | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4715 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019763
2322 | Task(Task)-->C (Construction) | PAINTING |  | 1.17.3.1 | Unscheduled | No | No | 2020-11-24 09:00 | 2021-01-23 18:00 | 2021-03-01 09:00 | 2021-04-30 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0.9697 | 0.001626 | 0.16 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 313 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4716 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019764
2323 | Task(Task)-->C (Construction) | MECHANICAL | 1.17.3.2 | 1.17.3 | Unscheduled | No | No | 2020-11-09 09:00 | 2021-06-08 18:00 | 2021-01-29 09:00 | 2021-05-11 18:00 | [6 empty] | 0 | 0 | [15 empty] | 21.2199 | 0.059079 | 5.81 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4717 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019765
2324 | Task(Task)-->C (Construction) | WATER TANKS |  | 1.17.3.2 | Unscheduled | No | No | 2020-11-09 09:00 | 2020-12-08 18:00 | 2021-01-29 09:00 | 2021-02-27 18:00 | [6 empty] | 0 | 0 | [15 empty] | 90.8778 | 0.05369 | 5.28 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4718 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019766
2325 | Task(Task)-->C (Construction) | ERECTION OF MONORAIL & HOISTS |  | 1.17.3.2 | Unscheduled | No | No | 2021-03-20 09:00 | 2021-04-09 18:00 | 2021-02-20 09:00 | 2021-03-12 18:00 | [6 empty] | 0 | 0 | [15 empty] | 4.475 | 0.002644 | 0.26 | Plan & Actual | Quantity | Set | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5482 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019767
2326 | Task(Task)-->C (Construction) | ERECTION OF PUMPS |  | 1.17.3.2 | Unscheduled | No | No | 2021-04-10 09:00 | 2021-06-08 18:00 | 2021-03-13 09:00 | 2021-05-11 18:00 | [6 empty] | 0 | 0 | [15 empty] | 4.6472 | 0.002745 | 0.27 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4719 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019768
2327 | Task(Task)-->C (Construction) | ELECTRICAL & INSTRUMENTATION | 1.17.3.3 | 1.17.3 | Unscheduled | No | No | 2020-11-08 | 2021-09-03 18:00 | 2021-02-13 09:00 | 2022-03-26 18:00 | [6 empty] | 0 | 0 | [15 empty] | 12.9291 | 0.035996 | 3.54 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5260 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019769
2328 | Task(Task)-->C (Construction) | CABLE TRAY |  | 1.17.3.3 | Unscheduled | No | No | 2020-11-08 | 2020-11-09 18:00 | 2021-02-13 09:00 | 2021-02-14 23:59 | [6 empty] | 0 | 0 | [15 empty] | 5.9322 | 0.002135 | 0.21 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4720 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019770
2329 | Task(Task)-->C (Construction) | POWER CABLE |  | 1.17.3.3 | Unscheduled | No | No | 2021-06-05 09:00 | 2021-06-11 18:00 | 2021-07-25 | 2021-07-31 18:00 | [6 empty] | 0 | 0 | [15 empty] | 16.1017 | 0.005796 | 0.57 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5261 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019771
2330 | Task(Task)-->C (Construction) | CONTROL CABLE |  | 1.17.3.3 | Unscheduled | No | No | 2021-06-09 09:00 | 2021-06-11 18:00 | 2021-09-25 09:00 | 2021-09-27 18:00 | [6 empty] | 0 | 0 | [15 empty] | 22.0339 | 0.007931 | 0.78 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 5505 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4721 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019772
2331 | Task(Task)-->C (Construction) | EARTHING |  | 1.17.3.3 | Unscheduled | No | No | 2021-06-09 09:00 | 2021-06-11 18:00 | 2021-07-29 09:00 | 2021-07-31 18:00 | [6 empty] | 0 | 0 | [15 empty] | 2.2599 | 0.000813 | 0.08 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 377 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5387 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019773
2332 | Task(Task)-->C (Construction) | EARTH PIT |  | 1.17.3.3 | Unscheduled | No | No | 2020-12-11 09:00 | 2020-12-13 23:59 | 2021-03-18 09:00 | 2021-03-20 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5388 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019774
2333 | Task(Task)-->C (Construction) | LIGHTING |  | 1.17.3.3 | Unscheduled | No | No | 2020-11-08 | 2020-11-14 18:00 | 2021-02-13 09:00 | 2021-02-19 18:00 | [6 empty] | 0 | 0 | [15 empty] | 8.1921 | 0.002949 | 0.29 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5389 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019775
2334 | Task(Task)-->C (Construction) | FIELD INTRUMENTS |  | 1.17.3.3 | Unscheduled | No | No | 2021-06-08 09:00 | 2021-06-12 18:00 | 2021-09-24 09:00 | 2021-09-28 18:00 | [6 empty] | 0 | 0 | [15 empty] | 45.4802 | 0.016371 | 1.61 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5390 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019776
2335 | Task(Task)-->C (Construction) | MOTOR TERMINATION |  | 1.17.3.3 | Unscheduled | No | No | 2021-06-09 09:00 | 2021-06-12 18:00 | 2021-12-03 09:00 | 2021-12-06 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5391 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019777
2336 | Task(Task)-->C (Construction) | NO LOAD RUN OF MOTOR |  | 1.17.3.3 | Unscheduled | No | No | 2021-08-27 09:00 | 2021-09-03 18:00 | 2022-03-19 09:00 | 2022-03-26 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5483 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019778
2337 | Task(Task)-->C (Construction) | NO LOAD COMMISSIONING & SYSTEM READYNESS FOR LOAD & TRIAL OPERATION |  | 1.17.3 | Unscheduled | No | No | 2021-09-04 09:00 | 2021-09-13 18:00 | 2022-03-27 | 2022-04-05 18:00 | [6 empty] | 0 | 0 | [15 empty] | 5.6245 | 0.015659 | 1.54 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5392 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019779
2338 | Task(Task)-->E (Engineering) | PUMP HOUSE -C NEAR KDTP-3 | 1.18 | 1 | Work In Progress | No | No | 2019-12-17 09:00 | 2021-09-04 18:00 | 2020-01-13 09:00 | 2022-03-02 18:00 |  |  | 2020-01-13 10:57 |  |  |  | 41.5463 | 8.8588 | [15 empty] | 0.35803 | 0.35803 | 35.21 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4722 | 0 | 1 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019780
2339 | Task(Task)-->E (Engineering) | ENGINEERING | 1.18.1 | 1.18 | Work In Progress | No | No | 2020-01-22 18:00 | 2020-08-13 17:40 | 2020-05-09 18:00 | 2020-11-04 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 76.3228 | [15 empty] | 6.6477 | 0.023801 | 2.34 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4723 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019781
2340 | Task(Task)-->E (Engineering) | MECHANICAL | 1.18.1.1 | 1.18.1 | Unscheduled | No | No | 2020-01-22 18:00 | 2020-03-25 17:40 | 2020-05-26 18:00 | 2020-07-21 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 65 | [15 empty] | 24.2152 | 0.005763 | 0.54 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4724 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036125
2341 | Task(Task)-->E (Engineering) | PUMP HOUSE -C ARRANGEMENT ( PUMP HOUSE C) ALONG WITH PIPING LAYOUT & MS WATER TANK |  | 1.18.1.1 | Unscheduled | No | No | 2020-01-22 18:00 | 2020-03-25 17:40 | 2020-05-26 18:00 | 2020-07-21 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-DS-GA-6010 |  | 2020-02-13 11:40 | 7012-155-PVM-B-040 |  |  |  | A |  |  |  | 100 | 0.005763 | 0.54 | Plan & Actual | Date |  | 0 | 0 | 0 | 200 | 0 | 10.4 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4725 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-22 18:00 | 2020-05-26 18:00 |  | 10 |  |  |  | 2020-02-13 17:40 | 2020-06-16 18:00 |  | 30 |  |  |  | 2020-02-19 17:40 | 2020-06-23 18:00 |  | 35 | 2020-06-19 09:47 |  |  | 2020-02-26 23:59 | 2020-06-30 18:00 |  | 65 | 2020-06-19 17:16 |  |  | 2020-03-03 17:40 | 2020-07-21 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-25 17:40 | 2020-07-21 18:00 |  | 100 | [122 empty] | Ram Prasad Roy |  |  |  |  | U - Water Media & Utility System | [16 empty] | 85 |  |  |  | 101099
2342 | Task(Task)-->E (Engineering) | CIVIL | 1.18.1.2 | 1.18.1 | Work In Progress | No | No | 2020-04-15 18:00 | 2020-08-13 17:40 | 2020-06-30 18:00 | 2020-11-04 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 79.8893 | [15 empty] | 40.8072 | 0.009713 | 0.91 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4728 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036126
2343 | Task(Task)-->E (Engineering) | Pump House-C : DESIGN CALCULATION |  | 1.18.1.2 | Completed | No | No | 2020-04-15 18:00 | 2020-06-15 17:40 | 2020-07-31 09:00 | 2020-08-17 18:00 |  |  | 2020-02-21 15:38 | 2020-08-17 22:45 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0024 |  | 2020-02-13 11:42 | 7012-155-PVC-U-082 |  |  |  | A |  |  |  | 40.6593 | 0.003949 | 0.37 | Plan & Actual | Date |  | 0 | 0 | 0 | 136.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4733 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-15 18:00 | 2020-06-30 18:00 |  | 10 |  |  |  | 2020-05-04 17:40 | 2020-07-25 18:00 |  | 30 |  |  |  | 2020-05-11 17:40 | 2020-07-28 18:00 |  | 35 |  |  |  | 2020-05-16 23:59 | 2020-08-04 18:00 |  | 65 | 2020-08-13 19:58 |  |  | 2020-05-22 17:40 | 2020-08-25 18:00 |  | 80 | 2020-08-17 22:40 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-15 17:40 | 2020-09-08 18:00 |  | 100 | 2020-08-17 22:46 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 183 |  |  |  | 101193
2344 | Task(Task)-->E (Engineering) | Pump House-C : NUM & RC DETAILS (SHT 1) |  | 1.18.1.2 | Completed | No | No | 2020-04-15 18:00 | 2020-06-15 17:40 | 2020-07-31 09:00 | 2020-08-17 18:00 |  |  | 2020-02-21 15:38 | 2020-08-17 22:45 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-NR-0031 |  | 2020-02-13 11:42 | 7012-155-PVC-C-083 |  |  |  | A |  |  |  | 13.1868 | 0.001281 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 45.03 | 0 | 12.15 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4729 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-15 18:00 | 2020-06-30 18:00 |  | 10 |  |  |  | 2020-05-04 17:40 | 2020-07-25 18:00 |  | 30 |  |  |  | 2020-05-11 17:40 | 2020-07-28 18:00 |  | 35 | 2020-07-29 11:24 |  |  | 2020-05-16 23:59 | 2020-08-04 18:00 |  | 65 | 2020-08-13 19:58 |  |  | 2020-05-22 17:40 | 2020-08-25 18:00 |  | 80 | 2020-08-17 22:35 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-15 17:40 | 2020-09-08 18:00 |  | 100 | 2020-08-17 22:46 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 184 |  |  |  | 101194
2345 | Task(Task)-->E (Engineering) | Pump House-C : NUM & RC DETAILS (SHT 2) |  | 1.18.1.2 | Completed | No | No | 2020-04-15 18:00 | 2020-06-15 17:40 | 2020-07-31 09:00 | 2020-08-17 18:00 |  |  | 2020-02-21 15:38 | 2020-08-17 22:45 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-NR-0032 |  | 2020-02-13 11:42 | 7012-155-PVC-C-084 |  |  |  | A |  |  |  | 13.1868 | 0.001281 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 45.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4730 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-15 18:00 | 2020-06-30 18:00 |  | 10 |  |  |  | 2020-05-04 17:40 | 2020-07-25 18:00 |  | 30 |  |  |  | 2020-05-11 17:40 | 2020-07-28 18:00 |  | 35 |  |  |  | 2020-05-16 23:59 | 2020-08-04 18:00 |  | 65 | 2020-08-13 19:58 |  |  | 2020-05-22 17:40 | 2020-08-25 18:00 |  | 80 | 2020-08-17 22:41 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-15 17:40 | 2020-09-08 18:00 |  | 100 | 2020-08-17 22:46 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 185 |  |  |  | 101195
2346 | Task(Task)-->E (Engineering) | Pump House-C : NUM & RC DETAILS (SHT 3) |  | 1.18.1.2 | Unscheduled | No | No | 2020-04-15 18:00 | 2020-06-15 17:40 | 2020-06-30 18:00 | 2020-09-08 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-NR-0033 |  | 2020-02-13 11:42 | 7012-155-PVC-C-085 |  |  |  | A |  |  |  | 13.1868 | 0.001281 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 45.03 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4731 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-15 18:00 | 2020-06-30 18:00 |  | 10 |  |  |  | 2020-05-04 17:40 | 2020-07-25 18:00 |  | 30 |  |  |  | 2020-05-11 17:40 | 2020-07-28 18:00 |  | 35 |  |  |  | 2020-05-16 23:59 | 2020-08-04 18:00 |  | 65 |  |  |  | 2020-05-22 17:40 | 2020-08-25 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-15 17:40 | 2020-09-08 18:00 |  | 100 | [122 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 186 |  |  |  | 101196
2347 | Task(Task)-->E (Engineering) | ARCHITECTURAL GA OF PUMP HOUSE C |  | 1.18.1.2 | Unscheduled | No | No | 2020-06-14 23:59 | 2020-08-13 17:40 | 2020-07-27 18:00 | 2020-11-04 18:00 |  |  | 2020-02-21 15:39 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-AR-0010 |  | 2020-02-13 11:43 | 7012-155-PVC-C-116 |  |  |  | A |  |  |  | 19.7802 | 0.001921 | 0.18 | Plan & Actual | Date |  | 0 | 0 | 0 | 68.01 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4732 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-06-14 23:59 | 2020-07-27 18:00 |  | 10 |  |  |  | 2020-07-02 17:40 | 2020-08-21 18:00 |  | 30 |  |  |  | 2020-07-08 17:40 | 2020-08-24 18:00 |  | 35 | 2020-09-15 12:24 |  |  | 2020-07-15 23:59 | 2020-08-31 18:00 |  | 65 | 2020-09-15 15:54 |  |  | 2020-07-21 17:40 | 2020-09-21 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-08-13 17:40 | 2020-10-05 18:00 |  | 100 | [122 empty] | Chetan Khodke |  |  |  |  | A - Architecture | [16 empty] | 217 |  |  |  | 101227
2348 | Task(Task)-->E (Engineering) | ELECTRICAL | 1.18.1.3 | 1.18.1 | Unscheduled | No | No | 2020-04-30 18:00 | 2020-06-29 17:40 | 2020-05-09 18:00 | 2020-07-07 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 | [15 empty] | 34.9776 | 0.008325 | 0.78 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4734 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036127
2349 | Task(Task)-->E (Engineering) | EQUIPMENT, CABLE ROUTING, EARTHING & LIGHTNING LAYOUT WITH PLAN, SECTIONAL VIEWS & BOM OF PUMP HOUSE-C NEAR KDTP-3 |  | 1.18.1.3 | Unscheduled | No | No | 2020-04-30 18:00 | 2020-06-19 17:40 | 2020-05-09 18:00 | 2020-07-02 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5059 |  | 2020-02-13 11:44 | 7012-155-PVE-F-021 |  |  |  | A |  |  |  | 57.6923 | 0.004803 | 0.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 165.48 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4735 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-30 18:00 | 2020-05-09 18:00 |  | 10 |  |  |  | 2020-05-08 17:40 | 2020-05-23 18:00 |  | 30 | 2020-06-20 14:06 |  |  | 2020-05-15 17:40 | 2020-05-30 18:00 |  | 35 | 2020-06-24 13:47 |  |  | 2020-05-21 23:59 | 2020-06-06 18:00 |  | 65 | 2020-08-03 11:20 |  |  | 2020-05-28 17:40 | 2020-06-27 18:00 |  | 80 | 2020-08-03 11:26 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-19 17:40 | 2020-06-27 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 256 |  |  |  | 101267
2350 | Task(Task)-->E (Engineering) | LIGHTING LAYOUT PLAN WITH POWER DISTRIBUTION ARRANGEMENT, SECTIONAL VIEW, BOM OF PUMP HOUSE-C |  | 1.18.1.3 | Unscheduled | No | No | 2020-05-09 18:00 | 2020-06-29 17:40 | 2020-05-26 18:00 | 2020-07-07 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5070 |  | 2020-02-13 11:44 | 7012-155-PVE-G-032 |  |  |  | A |  |  |  | 42.3077 | 0.003522 | 0.33 | Plan & Actual | Date |  | 0 | 0 | 0 | 124.21 | 0 | 8.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4736 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-05-09 18:00 | 2020-05-26 18:00 |  | 10 |  |  |  | 2020-05-18 17:40 | 2020-06-02 18:00 |  | 30 | 2020-07-20 12:26 |  |  | 2020-05-25 17:40 | 2020-06-09 18:00 |  | 35 |  |  |  | 2020-05-30 23:59 | 2020-06-16 18:00 |  | 65 | 2020-07-20 12:38 |  |  | 2020-06-05 17:40 | 2020-07-07 18:00 |  | 80 | 2020-07-28 17:53 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-29 17:40 | 2020-07-07 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 267 |  |  |  | 101278
2351 | Task(Task)-->P (Procurement) | PROCUREMENT | 1.18.2 | 1.18 | Work In Progress | No | No | 2019-12-17 09:00 | 2020-10-27 18:00 | 2020-01-13 09:00 | 2021-06-07 18:00 |  |  | 2020-01-13 10:57 |  |  |  | 93.5373 | 23.7072 | [15 empty] | 15.9659 | 0.057163 | 5.62 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4738 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019785
2352 | Task(Task)-->P (Procurement) | PURCHASE REQUISITION | 1.18.2.1 | 1.18.2 | Work In Progress | No | No | 2019-12-17 09:00 | 2020-06-06 18:00 | 2020-01-13 09:00 | 2020-05-29 18:00 |  |  | 2020-01-13 10:57 |  |  |  | 100 | 96.4248 | [15 empty] | 4.9911 | 0.002853 | 0.28 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4739 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019786
2353 | Task(Task)-->P (Procurement) | Building Structure |  | 1.18.2.1 | Completed | No | No | 2020-06-06 09:00 | 2020-06-06 18:00 | 2020-05-29 09:00 | 2020-05-29 18:00 |  |  | 2020-05-31 17:36 | 2020-05-31 17:36 |  |  | 100 | 100 | [15 empty] | 71.4286 | 0.002038 | 0.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4740 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019787
2354 | Task(Task)-->P (Procurement) | LPBS |  | 1.18.2.1 | Unscheduled | No | No | 2020-03-20 09:00 | 2020-03-20 18:00 | 2020-04-14 09:00 | 2020-04-14 18:00 | [6 empty] | 100 | 0 | [15 empty] | 3.5714 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4741 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019788
2355 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR UTILITY SYSTEM |  | 1.18.2.1 | Completed | No | No | 2019-12-17 09:00 | 2019-12-17 18:00 | 2020-01-13 09:00 | 2020-01-13 18:00 |  |  | 2020-01-13 10:57 | 2020-01-13 10:57 |  |  | 100 | 100 | [15 empty] | 25 | 0.000713 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4742 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019789
2356 | Task(Task)-->P (Procurement) | TECHNICAL CLEARANCE | 1.18.2.2 | 1.18.2 | Work In Progress | No | No | 2019-12-18 09:00 | 2020-06-13 18:00 | 2020-01-13 09:00 | 2020-06-12 18:00 |  |  | 2020-04-11 10:57 |  |  |  | 100 | 96.4248 | [15 empty] | 4.9911 | 0.002853 | 0.28 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4743 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019790
2357 | Task(Task)-->P (Procurement) | Building Structure |  | 1.18.2.2 | Completed | No | No | 2020-06-07 | 2020-06-13 18:00 | 2020-05-29 09:00 | 2020-05-29 18:00 |  |  | 2020-05-29 17:31 | 2020-05-29 17:31 |  |  | 100 | 100 | [15 empty] | 71.4286 | 0.002038 | 0.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4744 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019791
2358 | Task(Task)-->P (Procurement) | LPBS |  | 1.18.2.2 | Unscheduled | No | No | 2020-03-21 09:00 | 2020-04-04 18:00 | 2020-04-14 09:00 | 2020-06-12 18:00 | [6 empty] | 100 | 0 | [15 empty] | 3.5714 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4745 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019792
2359 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR UTILITY SYSTEM |  | 1.18.2.2 | Completed | No | No | 2019-12-18 09:00 | 2020-01-01 18:00 | 2020-01-13 09:00 | 2020-04-11 18:00 |  |  | 2020-04-11 10:57 | 2020-04-11 10:57 |  |  | 100 | 100 | [15 empty] | 25 | 0.000713 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4746 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019793
2360 | Task(Task)-->P (Procurement) | ORDERING | 1.18.2.3 | 1.18.2 | Work In Progress | No | No | 2020-01-02 09:00 | 2020-07-13 18:00 | 2020-04-11 09:00 | 2020-08-19 18:00 |  |  | 2020-04-12 15:47 |  |  |  | 100 | 96.4254 | [15 empty] | 9.9822 | 0.005706 | 0.56 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4747 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019794
2361 | Task(Task)-->P (Procurement) | Building Structure |  | 1.18.2.3 | Completed | No | No | 2020-06-14 | 2020-07-13 18:00 | 2020-05-29 09:00 | 2020-05-31 23:59 |  |  | 2020-05-31 17:39 | 2020-05-31 17:39 |  |  | 100 | 100 | [15 empty] | 71.4286 | 0.004076 | 0.4 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4748 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019795
2362 | Task(Task)-->P (Procurement) | LPBS |  | 1.18.2.3 | Unscheduled | No | No | 2020-04-05 | 2020-04-20 18:00 | 2020-06-12 09:00 | 2020-08-19 18:00 | [6 empty] | 100 | 0 | [15 empty] | 3.5714 | 0.000204 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4749 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019796
2363 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR UTILITY SYSTEM |  | 1.18.2.3 | Completed | No | No | 2020-01-02 09:00 | 2020-01-16 18:00 | 2020-04-11 09:00 | 2020-07-20 18:00 |  |  | 2020-04-12 15:47 | 2020-06-20 15:47 |  |  | 100 | 100 | [15 empty] | 25 | 0.001427 | 0.14 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4750 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019797
2364 | Task(Task)-->P (Procurement) | ITP APPROVAL | 1.18.2.4 | 1.18.2 | Work In Progress | No | No | 2020-01-17 09:00 | 2020-07-20 18:00 | 2020-05-31 | 2020-10-10 18:00 |  |  | 2020-07-29 15:04 |  |  |  | 100 | 3.5752 | [15 empty] | 4.9911 | 0.002853 | 0.28 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4751 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019798
2365 | Task(Task)-->P (Procurement) | Building Structure |  | 1.18.2.4 | Unscheduled | No | No | 2020-07-14 09:00 | 2020-07-20 18:00 | 2020-05-31 | 2020-08-04 18:00 | [6 empty] | 100 | 0 | [15 empty] | 71.4286 | 0.002038 | 0.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4752 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019799
2366 | Task(Task)-->P (Procurement) | LPBS |  | 1.18.2.4 | Completed | No | No | 2020-04-21 09:00 | 2020-05-30 18:00 | 2020-07-29 09:00 | 2020-08-21 18:00 |  |  | 2020-07-29 15:04 | 2020-08-22 12:55 |  |  | 100 | 100 | [15 empty] | 3.5714 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4753 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019800
2367 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR UTILITY SYSTEM |  | 1.18.2.4 | Unscheduled | No | No | 2020-01-17 09:00 | 2020-02-25 18:00 | 2020-09-08 09:00 | 2020-10-10 18:00 | [6 empty] | 100 | 0 | [15 empty] | 25 | 0.000713 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4754 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019801
2368 | Task(Task)-->P (Procurement) | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE | 1.18.2.5 | 1.18.2 | Work In Progress | No | No | 2020-01-17 09:00 | 2020-07-12 23:59 | 2020-05-31 | 2020-10-30 18:00 |  |  | 2020-07-07 10:15 |  |  |  | 100 | 28.5748 | [15 empty] | 14.9733 | 0.008559 | 0.84 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4755 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019802
2369 | Task(Task)-->P (Procurement) | Building Structure |  | 1.18.2.5 | Unscheduled | No | No | 2020-07-06 09:00 | 2020-07-12 23:59 | 2020-05-31 | 2020-10-30 18:00 | [6 empty] | 100 | 0 | [15 empty] | 71.4286 | 0.006114 | 0.6 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4756 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019803
2370 | Task(Task)-->P (Procurement) | LPBS |  | 1.18.2.5 | Completed | No | No | 2020-04-21 09:00 | 2020-06-04 18:00 | 2020-07-25 09:00 | 2020-08-22 18:00 |  |  | 2020-07-24 18:40 | 2020-08-22 12:59 |  |  | 100 | 100 | [15 empty] | 3.5714 | 0.000306 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4757 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019804
2371 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR UTILITY SYSTEM |  | 1.18.2.5 | Completed | No | No | 2020-01-17 09:00 | 2020-03-01 23:59 | 2020-07-07 09:00 | 2020-09-29 18:00 |  |  | 2020-07-07 10:15 | 2020-09-29 14:41 |  |  | 100 | 100 | [15 empty] | 25 | 0.00214 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4758 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019805
2372 | Task(Task)-->P (Procurement) | MANUFACTURING & RECEIPT AT SITE (MRN) | 1.18.2.6 | 1.18.2 | Unscheduled | No | No | 2020-03-02 09:00 | 2020-10-27 18:00 | 2020-08-23 | 2021-06-07 18:00 |  |  | 2020-08-22 13:01 |  |  |  | 89.2418 | 0 | [15 empty] | 60.0713 | 0.034339 | 3.37 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4759 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019806
2373 | Task(Task)-->P (Procurement) | WATER TANK |  | 1.18.2.6 | Unscheduled | No | No | 2020-07-21 09:00 | 2020-10-18 23:59 | 2020-10-31 09:00 | 2021-01-28 18:00 | [6 empty] | 87.7778 | 0 | [15 empty] | 70.6231 | 0.024251 | 2.38 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4760 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019807
2374 | Task(Task)-->P (Procurement) | LPBS |  | 1.18.2.6 | Unscheduled | No | No | 2020-06-05 09:00 | 2020-09-16 18:00 | 2020-08-23 | 2020-12-04 18:00 |  |  | 2020-08-22 13:01 |  |  |  | 100 | 0 | [15 empty] | 3.8576 | 0.001325 | 0.13 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4761 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019808
2375 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR UTILITY SYSTEM |  | 1.18.2.6 | Unscheduled | No | No | 2020-03-02 09:00 | 2020-10-27 18:00 | 2020-10-11 | 2021-06-07 18:00 |  |  | 2020-09-29 16:43 |  |  |  | 91.6667 | 0 | [15 empty] | 25.5193 | 0.008763 | 0.86 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4762 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019809
2376 | Task(Task)-->C (Construction) | CONSTRUCTION | 1.18.3 | 1.18 | Unscheduled | No | No | 2020-05-30 09:00 | 2021-09-04 18:00 | 2020-08-11 09:00 | 2022-03-02 18:00 | [6 empty] | 25.7984 | 0 | [15 empty] | 77.3864 | 0.27707 | 27.24 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4763 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019810
2377 | Task(Task)-->C (Construction) | CIVIL | 1.18.3.1 | 1.18.3 | Unscheduled | No | No | 2020-05-30 09:00 | 2021-02-09 18:00 | 2020-08-11 09:00 | 2021-05-18 18:00 | [6 empty] | 42.0303 | 0 | [15 empty] | 61.3803 | 0.17006 | 16.72 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4764 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019811
2378 | Task(Task)-->C (Construction) | AVAILABILITY OF FRONT BY NTPC |  | 1.18.3.1 | Unscheduled | No | No | 2020-05-30 09:00 | 2020-05-30 18:00 | 2020-08-11 09:00 | 2020-08-11 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4765 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019812
2379 | Task(Task)-->C (Construction) | EXCAVATION |  | 1.18.3.1 | Unscheduled | No | No | 2020-06-06 09:00 | 2020-06-17 18:00 | 2020-08-26 09:00 | 2020-09-06 23:59 | [6 empty] | 100 | 0 | [15 empty] | 2.7496 | 0.004676 | 0.46 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 1713 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4766 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | Excavation | [21 empty] | 1019813
2380 | Task(Task)-->C (Construction) | PCC |  | 1.18.3.1 | Unscheduled | No | No | 2020-06-18 09:00 | 2020-06-26 18:00 | 2020-09-24 09:00 | 2020-10-02 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.53796 | 0.000915 | 0.09 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4767 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | PCC | [21 empty] | 1019814
2381 | Task(Task)-->C (Construction) | RAFT |  | 1.18.3.1 | Unscheduled | No | No | 2020-06-27 09:00 | 2020-07-20 18:00 | 2020-10-03 09:00 | 2020-10-26 18:00 | [6 empty] | 100 | 0 | [15 empty] | 8.2487 | 0.014028 | 1.38 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4768 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019815
2382 | Task(Task)-->C (Construction) | PLINTH BEAM |  | 1.18.3.1 | Unscheduled | No | No | 2020-07-23 09:00 | 2020-08-02 23:59 | 2020-10-29 09:00 | 2020-11-08 23:59 | [6 empty] | 100 | 0 | [15 empty] | 1.6139 | 0.002745 | 0.27 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4769 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019816
2383 | Task(Task)-->C (Construction) | PUMP FOUNDATION & TRENCH |  | 1.18.3.1 | Unscheduled | No | No | 2020-07-28 09:00 | 2020-08-12 18:00 | 2020-11-03 09:00 | 2020-11-18 18:00 | [6 empty] | 100 | 0 | [15 empty] | 2.3909 | 0.004066 | 0.4 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4770 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019817
2384 | Task(Task)-->C (Construction) | GRADE SLAB |  | 1.18.3.1 | Unscheduled | No | No | 2020-08-10 09:00 | 2020-09-09 18:00 | 2020-11-16 09:00 | 2020-12-16 18:00 | [6 empty] | 100 | 0 | [15 empty] | 16.5571 | 0.028158 | 2.77 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 148 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4771 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019818
2385 | Task(Task)-->C (Construction) | COLUMN AND ROOF SLAB |  | 1.18.3.1 | Unscheduled | No | No | 2020-08-28 09:00 | 2020-10-09 18:00 | 2020-12-04 09:00 | 2021-01-15 18:00 | [6 empty] | 95.3488 | 0 | [15 empty] | 3.945 | 0.006709 | 0.66 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4772 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019819
2386 | Task(Task)-->C (Construction) | WATER TANK FOUNDATION |  | 1.18.3.1 | Unscheduled | No | No | 2020-06-18 09:00 | 2020-10-10 18:00 | 2020-09-07 09:00 | 2020-12-30 18:00 | [6 empty] | 97.3913 | 0 | [15 empty] | 6.3359 | 0.010775 | 1.06 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4773 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019820
2387 | Task(Task)-->C (Construction) | BRICK WORK |  | 1.18.3.1 | Unscheduled | No | No | 2020-10-10 09:00 | 2020-11-09 18:00 | 2021-01-16 09:00 | 2021-02-15 18:00 | [6 empty] | 0 | 0 | [15 empty] | 4.6025 | 0.007827 | 0.77 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4774 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019821
2388 | Task(Task)-->C (Construction) | PLASTER |  | 1.18.3.1 | Unscheduled | No | No | 2020-10-25 | 2020-11-24 18:00 | 2021-01-31 | 2021-03-02 18:00 | [6 empty] | 0 | 0 | [15 empty] | 1.315 | 0.002236 | 0.22 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 394 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4775 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019822
2389 | Task(Task)-->C (Construction) | DOOR , WINDOW, MONORAIL DOOR & ROLLING SHUTTER |  | 1.18.3.1 | Unscheduled | No | No | 2020-11-18 09:00 | 2020-12-10 18:00 | 2021-02-24 09:00 | 2021-03-18 18:00 | [6 empty] | 0 | 0 | [15 empty] | 20.5021 | 0.034867 | 3.43 | Plan & Actual | Quantity | Lot | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4776 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019823
2390 | Task(Task)-->C (Construction) | FLOORING |  | 1.18.3.1 | Unscheduled | No | No | 2020-11-18 09:00 | 2020-12-15 18:00 | 2021-02-24 09:00 | 2021-03-23 18:00 | [6 empty] | 0 | 0 | [15 empty] | 11.7155 | 0.019924 | 1.96 | Plan & Actual | Quantity | Lot | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4777 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019824
2391 | Task(Task)-->C (Construction) | ROOF WATER PROFING & RWDC PIPE |  | 1.18.3.1 | Unscheduled | No | No | 2020-11-07 09:00 | 2020-12-07 18:00 | 2021-02-13 09:00 | 2021-03-15 18:00 | [6 empty] | 0 | 0 | [15 empty] | 4.6623 | 0.007929 | 0.78 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 163 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4778 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019825
2392 | Task(Task)-->C (Construction) | GARLAND DRAIN & PLINTH PROTECTION |  | 1.18.3.1 | Unscheduled | No | No | 2020-11-18 09:00 | 2020-12-30 18:00 | 2021-02-24 09:00 | 2021-04-07 18:00 | [6 empty] | 0 | 0 | [15 empty] | 13.8075 | 0.023482 | 2.31 | Plan & Actual | Quantity | Lot | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4779 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019826
2393 | Task(Task)-->C (Construction) | PAINTING |  | 1.18.3.1 | Unscheduled | No | No | 2020-12-11 09:00 | 2021-02-09 18:00 | 2021-03-19 09:00 | 2021-05-18 18:00 | [6 empty] | 0 | 0 | [15 empty] | 1.0161 | 0.001728 | 0.17 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 327 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4780 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019827
2394 | Task(Task)-->C (Construction) | MECHANICAL | 1.18.3.2 | 1.18.3 | Unscheduled | No | No | 2020-11-08 | 2021-05-09 23:59 | 2021-01-29 09:00 | 2021-04-29 18:00 | [6 empty] | 0 | 0 | [15 empty] | 21.3289 | 0.059095 | 5.81 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4781 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019828
2395 | Task(Task)-->C (Construction) | WATER TANKS |  | 1.18.3.2 | Unscheduled | No | No | 2020-11-08 | 2020-12-07 18:00 | 2021-01-29 09:00 | 2021-02-27 18:00 | [6 empty] | 0 | 0 | [15 empty] | 90.8778 | 0.053704 | 5.28 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4782 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019829
2396 | Task(Task)-->C (Construction) | ERECTION OF MONORAIL & HOISTS |  | 1.18.3.2 | Unscheduled | No | No | 2021-03-20 09:00 | 2021-04-09 18:00 | 2021-03-10 09:00 | 2021-03-30 18:00 | [6 empty] | 0 | 0 | [15 empty] | 4.475 | 0.002645 | 0.26 | Plan & Actual | Quantity | Set | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5484 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019830
2397 | Task(Task)-->C (Construction) | ERECTION OF PUMPS |  | 1.18.3.2 | Unscheduled | No | No | 2021-04-10 09:00 | 2021-05-09 23:59 | 2021-03-31 09:00 | 2021-04-29 18:00 | [6 empty] | 0 | 0 | [15 empty] | 4.6472 | 0.002746 | 0.27 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4783 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019831
2398 | Task(Task)-->C (Construction) | ELECTRICAL & INSTRUMENTATION | 1.18.3.3 | 1.18.3 | Unscheduled | No | No | 2020-11-25 09:00 | 2021-08-25 18:00 | 2021-03-03 09:00 | 2022-02-20 23:59 | [6 empty] | 0 | 0 | [15 empty] | 11.6373 | 0.032243 | 3.17 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5262 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019832
2399 | Task(Task)-->C (Construction) | CABLE TRAY |  | 1.18.3.3 | Unscheduled | No | No | 2020-11-25 09:00 | 2020-11-26 18:00 | 2021-03-03 09:00 | 2021-03-04 18:00 | [6 empty] | 0 | 0 | [15 empty] | 6.6456 | 0.002143 | 0.21 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4784 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019833
2400 | Task(Task)-->C (Construction) | POWER CABLE |  | 1.18.3.3 | Unscheduled | No | No | 2021-05-04 09:00 | 2021-05-10 18:00 | 2021-07-25 | 2021-07-31 18:00 | [6 empty] | 0 | 0 | [15 empty] | 18.3544 | 0.005918 | 0.58 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 4080 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5263 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019834
2401 | Task(Task)-->C (Construction) | CONTROL CABLE |  | 1.18.3.3 | Unscheduled | No | No | 2021-05-08 09:00 | 2021-05-10 18:00 | 2021-09-25 09:00 | 2021-09-27 18:00 | [6 empty] | 0 | 0 | [15 empty] | 13.2911 | 0.004285 | 0.42 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4785 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019835
2402 | Task(Task)-->C (Construction) | EARTHING |  | 1.18.3.3 | Unscheduled | No | No | 2021-05-08 09:00 | 2021-05-10 18:00 | 2021-07-29 09:00 | 2021-07-31 18:00 | [6 empty] | 0 | 0 | [15 empty] | 2.5316 | 0.000816 | 0.08 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 377 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5393 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019836
2403 | Task(Task)-->C (Construction) | EARTH PIT |  | 1.18.3.3 | Unscheduled | No | No | 2020-12-28 09:00 | 2020-12-30 18:00 | 2021-04-05 09:00 | 2021-04-07 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5394 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019837
2404 | Task(Task)-->C (Construction) | LIGHTING |  | 1.18.3.3 | Unscheduled | No | No | 2020-12-02 09:00 | 2020-12-08 18:00 | 2021-03-10 09:00 | 2021-03-16 18:00 | [6 empty] | 0 | 0 | [15 empty] | 9.1772 | 0.002959 | 0.29 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5395 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019838
2405 | Task(Task)-->C (Construction) | FIELD INTRUMENTS |  | 1.18.3.3 | Unscheduled | No | No | 2021-05-07 09:00 | 2021-05-11 18:00 | 2021-09-24 09:00 | 2021-09-28 18:00 | [6 empty] | 0 | 0 | [15 empty] | 50 | 0.016122 | 1.58 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5396 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019839
2406 | Task(Task)-->C (Construction) | MOTOR TERMINATION |  | 1.18.3.3 | Unscheduled | No | No | 2021-05-19 09:00 | 2021-05-22 18:00 | 2021-12-03 09:00 | 2021-12-06 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5397 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019840
2407 | Task(Task)-->C (Construction) | NO LOAD RUN OF MOTOR |  | 1.18.3.3 | Unscheduled | No | No | 2021-08-22 | 2021-08-25 18:00 | 2022-02-17 09:00 | 2022-02-20 23:59 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5485 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019841
2408 | Task(Task)-->C (Construction) | NO LOAD COMMISSIONING & SYSTEM READYNESS FOR LOAD & TRIAL OPERATION |  | 1.18.3 | Unscheduled | No | No | 2021-08-26 09:00 | 2021-09-04 18:00 | 2022-02-21 09:00 | 2022-03-02 18:00 | [6 empty] | 0 | 0 | [15 empty] | 5.6535 | 0.015664 | 1.54 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5398 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019842
2409 | Task(Task)-->E (Engineering) | CABLE GALLERY & CABLE TRENCH | 1.19 | 1 | Work In Progress | No | No | 2020-01-28 09:00 | 2021-05-28 18:00 | 2020-03-16 09:00 | 2021-10-26 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 64.8141 | 12.7537 | [15 empty] | 1.3856 | 1.3856 | 136.26 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4786 | 0 | 1 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019843
2410 | Task(Task)-->E (Engineering) | ENGINEERING | 1.19.1 | 1.19 | Work In Progress | No | No | 2020-03-18 18:00 | 2020-06-10 17:40 | 2020-05-14 18:00 | 2020-09-10 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 81.8726 | [15 empty] | 0.79254 | 0.010981 | 1.08 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4787 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019844
2411 | Task(Task)-->E (Engineering) | CIVIL | 1.19.1.1 | 1.19.1 | Completed | No | No | 2020-03-18 18:00 | 2020-06-10 17:40 | 2020-08-26 09:00 | 2020-09-08 18:00 |  |  | 2020-02-21 15:38 | 2020-09-10 23:14 |  |  | 100 | 100 | [15 empty] | 73.1481 | 0.008032 | 0.79 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4788 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036128
2412 | Task(Task)-->E (Engineering) | CABLE GALLERY & SUPPORTING TRESTLES : DESIGN CALCULATION OF SUB STRUCTURE |  | 1.19.1.1 | Completed | No | No | 2020-04-12 23:59 | 2020-06-10 17:40 | 2020-08-31 09:00 | 2020-09-08 18:00 |  |  | 2020-02-21 15:38 | 2020-09-10 23:14 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0028 |  | 2020-02-13 11:43 | 7012-155-PVC-U-098 |  |  |  | A |  |  |  | 31.6456 | 0.002542 | 0.25 | Plan & Actual | Date |  | 0 | 0 | 0 | 92.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4790 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-12 23:59 | 2020-06-13 18:00 |  | 10 |  |  |  | 2020-04-30 17:40 | 2020-07-23 18:00 |  | 30 |  |  |  | 2020-05-06 17:40 | 2020-07-26 23:59 |  | 35 |  |  |  | 2020-05-13 23:59 | 2020-08-02 23:59 |  | 65 | 2020-08-31 23:46 |  |  | 2020-05-19 17:40 | 2020-08-23 23:59 |  | 80 | 2020-09-10 22:56 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-10 17:40 | 2020-09-06 23:59 |  | 100 | 2020-09-10 23:15 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 199 |  |  |  | 101209
2413 | Task(Task)-->E (Engineering) | CABLE GALLERY & SUPPORTING TRESTLES: NUM & RC DETAILS |  | 1.19.1.1 | Completed | No | No | 2020-04-12 23:59 | 2020-06-10 17:40 | 2020-08-31 09:00 | 2020-09-08 18:00 |  |  | 2020-02-21 15:38 | 2020-09-10 23:14 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-NR-0043 |  | 2020-02-13 11:43 | 7012-155-PVC-C-099 |  |  |  | A |  |  |  | 31.6456 | 0.002542 | 0.25 | Plan & Actual | Date |  | 0 | 0 | 0 | 92.1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4789 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-12 23:59 | 2020-06-13 18:00 |  | 10 |  |  |  | 2020-04-30 17:40 | 2020-07-23 18:00 |  | 30 |  |  |  | 2020-05-06 17:40 | 2020-07-26 23:59 |  | 35 | 2020-09-02 17:18 |  |  | 2020-05-13 23:59 | 2020-08-02 23:59 |  | 65 | 2020-09-02 20:31 |  |  | 2020-05-19 17:40 | 2020-08-23 23:59 |  | 80 | 2020-09-10 22:55 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-10 17:40 | 2020-09-06 23:59 |  | 100 | 2020-09-10 23:15 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 200 |  |  |  | 101210
2414 | Task(Task)-->E (Engineering) | CABLE GALLERY & SUPPORTING TRESTLES : DESIGN CALCULATION OF SUPER STRUCTURE |  | 1.19.1.1 | Completed | No | No | 2020-03-18 18:00 | 2020-05-18 17:40 | 2020-08-26 09:00 | 2020-09-08 18:00 |  |  | 2020-02-21 15:38 | 2020-09-10 23:14 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0029 |  | 2020-02-13 11:43 | 7012-155-PVC-U-100 |  |  |  | A |  |  |  | 36.7089 | 0.002948 | 0.29 | Plan & Actual | Date |  | 0 | 0 | 0 | 108.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4791 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-18 18:00 | 2020-05-14 18:00 |  | 10 |  |  |  | 2020-04-06 17:40 | 2020-06-23 18:00 |  | 30 |  |  |  | 2020-04-13 17:40 | 2020-06-26 18:00 |  | 35 |  |  |  | 2020-04-18 23:59 | 2020-07-03 18:00 |  | 65 | 2020-08-26 21:13 |  |  | 2020-04-24 17:40 | 2020-07-24 18:00 |  | 80 | 2020-09-10 22:58 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-18 17:40 | 2020-08-07 18:00 |  | 100 | 2020-09-10 23:15 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 201 |  |  |  | 101211
2415 | Task(Task)-->E (Engineering) | STRUCTURAL | 1.19.1.2 | 1.19.1 | Unscheduled | No | No | 2020-03-18 18:00 | 2020-05-18 17:40 | 2020-05-14 18:00 | 2020-09-10 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 32.5 | [15 empty] | 26.8519 | 0.002949 | 0.29 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4792 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036129
2416 | Task(Task)-->E (Engineering) | CABLE GALLERY & SUPPORTING TRESTLES : STRUCTURAL GA (SHT 1) |  | 1.19.1.2 | Unscheduled | No | No | 2020-03-18 18:00 | 2020-05-18 17:40 | 2020-05-14 18:00 | 2020-09-10 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-GA-0023 |  | 2020-02-13 11:43 | 7012-155-PVC-B-101 |  |  |  | A |  |  |  | 50 | 0.001475 | 0.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 54.29 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4793 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-18 18:00 | 2020-05-14 18:00 |  | 10 |  |  |  | 2020-04-06 17:40 | 2020-06-23 18:00 |  | 30 | 2020-08-20 17:46 |  |  | 2020-04-13 17:40 | 2020-06-26 18:00 |  | 35 |  |  |  | 2020-04-18 23:59 | 2020-07-03 18:00 |  | 65 | 2020-08-26 21:12 |  |  | 2020-04-24 17:40 | 2020-07-24 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-18 17:40 | 2020-08-07 18:00 |  | 100 | [122 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 202 |  |  |  | 101212
2417 | Task(Task)-->E (Engineering) | CABLE GALLERY & SUPPORTING TRESTLES : STRUCTURAL GA (SHT 2) |  | 1.19.1.2 | Unscheduled | No | No | 2020-03-18 18:00 | 2020-05-18 17:40 | 2020-05-14 18:00 | 2020-08-21 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-GA-0024 |  | 2020-02-13 11:43 | 7012-155-PVC-B-102 |  |  |  | A |  |  |  | 50 | 0.001475 | 0.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 54.29 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4794 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-18 18:00 | 2020-05-14 18:00 |  | 10 |  |  |  | 2020-04-06 17:40 | 2020-06-23 18:00 |  | 30 |  |  |  | 2020-04-13 17:40 | 2020-06-26 18:00 |  | 35 |  |  |  | 2020-04-18 23:59 | 2020-07-03 18:00 |  | 65 |  |  |  | 2020-04-24 17:40 | 2020-07-24 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-18 17:40 | 2020-08-07 18:00 |  | 100 | [122 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 203 |  |  |  | 101213
2418 | Task(Task)-->P (Procurement) | PROCUREMENT | 1.19.2 | 1.19 | Work In Progress | No | No | 2020-01-28 09:00 | 2020-11-30 18:00 | 2020-03-16 09:00 | 2021-04-30 18:00 |  |  | 2020-03-16 16:04 |  |  |  | 89.6933 | 26.3124 | [15 empty] | 46.0043 | 0.63741 | 62.69 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4796 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019847
2419 | Task(Task)-->P (Procurement) | PURCHASE REQUISITION | 1.19.2.1 | 1.19.2 | Completed | No | No | 2020-01-28 09:00 | 2020-04-18 18:00 | 2020-03-16 09:00 | 2020-05-29 18:00 |  |  | 2020-03-16 16:04 | 2020-05-31 18:44 |  |  | 100 | 100 | [15 empty] | 4.9944 | 0.031835 | 3.13 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4797 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019848
2420 | Task(Task)-->P (Procurement) | Building Structure |  | 1.19.2.1 | Completed | No | No | 2020-04-18 09:00 | 2020-04-18 18:00 | 2020-05-29 09:00 | 2020-05-29 18:00 |  |  | 2020-05-31 18:44 | 2020-05-31 18:44 |  |  | 100 | 100 | [15 empty] | 57.8275 | 0.018409 | 1.81 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4798 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019849
2421 | Task(Task)-->P (Procurement) | CABLE TRAY & ACCESSORIES |  | 1.19.2.1 | Completed | No | No | 2020-01-28 09:00 | 2020-01-28 18:00 | 2020-03-16 09:00 | 2020-03-16 18:00 |  |  | 2020-03-16 16:04 | 2020-03-16 16:04 |  |  | 100 | 100 | [15 empty] | 42.1725 | 0.013426 | 1.32 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4799 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019850
2422 | Task(Task)-->P (Procurement) | TECHNICAL CLEARANCE | 1.19.2.2 | 1.19.2 | Completed | No | No | 2020-01-29 09:00 | 2020-04-25 18:00 | 2020-03-16 09:00 | 2020-05-29 18:00 |  |  | 2020-03-17 16:05 | 2020-05-29 17:31 |  |  | 100 | 100 | [15 empty] | 4.9944 | 0.031835 | 3.13 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4800 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019851
2423 | Task(Task)-->P (Procurement) | Building Structure |  | 1.19.2.2 | Completed | No | No | 2020-04-19 | 2020-04-25 18:00 | 2020-05-29 09:00 | 2020-05-29 18:00 |  |  | 2020-05-29 17:31 | 2020-05-29 17:31 |  |  | 100 | 100 | [15 empty] | 57.8275 | 0.018409 | 1.81 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4801 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019852
2424 | Task(Task)-->P (Procurement) | CABLE TRAY & ACCESSORIES |  | 1.19.2.2 | Completed | No | No | 2020-01-29 09:00 | 2020-02-06 18:00 | 2020-03-16 09:00 | 2020-05-04 18:00 |  |  | 2020-03-17 16:05 | 2020-05-04 16:05 |  |  | 100 | 100 | [15 empty] | 42.1725 | 0.013426 | 1.32 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4802 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019853
2425 | Task(Task)-->P (Procurement) | ORDERING | 1.19.2.3 | 1.19.2 | Completed | No | No | 2020-02-07 09:00 | 2020-05-25 18:00 | 2020-05-04 09:00 | 2020-08-07 18:00 |  |  | 2020-05-05 16:06 | 2020-07-06 16:06 |  |  | 100 | 100 | [15 empty] | 10.0048 | 0.063772 | 6.27 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4803 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019854
2426 | Task(Task)-->P (Procurement) | Building Structure |  | 1.19.2.3 | Completed | No | No | 2020-04-26 | 2020-05-25 18:00 | 2020-05-29 09:00 | 2020-05-31 23:59 |  |  | 2020-05-31 18:49 | 2020-05-31 18:49 |  |  | 100 | 100 | [15 empty] | 57.8947 | 0.036921 | 3.63 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4804 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019855
2427 | Task(Task)-->P (Procurement) | CABLE TRAY & ACCESSORIES |  | 1.19.2.3 | Completed | No | No | 2020-02-07 09:00 | 2020-02-15 18:00 | 2020-05-04 09:00 | 2020-08-07 18:00 |  |  | 2020-05-05 16:06 | 2020-07-06 16:06 |  |  | 100 | 100 | [15 empty] | 42.1053 | 0.026851 | 2.64 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4805 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019856
2428 | Task(Task)-->P (Procurement) | ITP APPROVAL | 1.19.2.4 | 1.19.2 | Unscheduled | No | No | 2020-02-16 | 2020-06-01 18:00 | 2020-05-30 09:00 | 2020-08-04 18:00 |  |  | 2020-06-25 19:04 |  |  |  | 100 | 0 | [15 empty] | 4.9944 | 0.031835 | 3.13 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4806 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019857
2429 | Task(Task)-->P (Procurement) | Building Structure |  | 1.19.2.4 | Unscheduled | No | No | 2020-05-26 09:00 | 2020-06-01 18:00 | 2020-05-31 | 2020-08-04 18:00 |  |  | 2020-06-25 19:04 |  |  |  | 100 | 0 | [15 empty] | 57.8275 | 0.018409 | 1.81 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4807 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019858
2430 | Task(Task)-->P (Procurement) | CABLE TRAY & ACCESSORIES |  | 1.19.2.4 | Unscheduled | No | No | 2020-02-16 | 2020-03-26 18:00 | 2020-05-30 09:00 | 2020-07-28 18:00 | [6 empty] | 100 | 0 | [15 empty] | 42.1725 | 0.013426 | 1.32 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4808 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019859
2431 | Task(Task)-->P (Procurement) | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE | 1.19.2.5 | 1.19.2 | Work In Progress | No | No | 2020-02-16 | 2020-05-30 18:00 | 2020-05-30 09:00 | 2020-10-30 18:00 |  |  | 2020-07-06 10:19 |  |  |  | 100 | 42.1277 | [15 empty] | 14.9992 | 0.095607 | 9.4 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4809 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019860
2432 | Task(Task)-->P (Procurement) | Building Structure |  | 1.19.2.5 | Unscheduled | No | No | 2020-05-24 | 2020-05-30 18:00 | 2020-05-31 | 2020-10-30 18:00 | [6 empty] | 100 | 0 | [15 empty] | 57.8723 | 0.05533 | 5.44 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4810 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019861
2433 | Task(Task)-->P (Procurement) | CABLE TRAY & ACCESSORIES |  | 1.19.2.5 | Completed | No | No | 2020-02-16 | 2020-03-31 18:00 | 2020-05-30 09:00 | 2020-08-08 18:00 |  |  | 2020-07-06 10:19 | 2020-08-08 13:46 |  |  | 100 | 100 | [15 empty] | 42.1277 | 0.040277 | 3.96 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4811 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019862
2434 | Task(Task)-->P (Procurement) | MANUFACTURING & RECEIPT AT SITE (MRN) | 1.19.2.6 | 1.19.2 | Unscheduled | No | No | 2020-04-01 09:00 | 2020-11-30 18:00 | 2020-08-09 | 2021-04-30 18:00 |  |  | 2020-08-09 13:53 |  |  |  | 82.8258 | 0 | [15 empty] | 60.0128 | 0.38253 | 37.61 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4812 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019863
2435 | Task(Task)-->P (Procurement) | Building Structure |  | 1.19.2.6 | Unscheduled | No | No | 2020-06-02 09:00 | 2020-11-30 18:00 | 2020-10-31 09:00 | 2021-04-30 18:00 | [6 empty] | 70.3297 | 0 | [15 empty] | 57.8835 | 0.22142 | 21.77 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4813 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019864
2436 | Task(Task)-->P (Procurement) | CABLE TRAY & ACCESSORIES |  | 1.19.2.6 | Unscheduled | No | No | 2020-04-01 09:00 | 2020-08-10 18:00 | 2020-08-09 | 2020-12-19 18:00 |  |  | 2020-08-09 13:53 |  |  |  | 100 | 0 | [15 empty] | 42.1165 | 0.16111 | 15.84 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4814 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019865
2437 | Task(Task)-->C (Construction) | CONSTRUCTION | 1.19.3 | 1.19 | Unscheduled | No | No | 2020-05-27 09:00 | 2021-05-28 18:00 | 2020-09-02 09:00 | 2021-10-26 18:00 | [6 empty] | 42.7772 | 0 | [15 empty] | 53.2032 | 0.73716 | 72.5 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4815 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019866
2438 | Task(Task)-->C (Construction) | CIVIL | 1.19.3.1 | 1.19.3 | Unscheduled | No | No | 2020-05-27 09:00 | 2020-11-02 18:00 | 2020-09-02 09:00 | 2021-02-08 18:00 | [6 empty] | 78.5151 | 0 | [15 empty] | 54.4828 | 0.40163 | 39.5 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4816 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019867
2439 | Task(Task)-->C (Construction) | AVAILABILITY OF FRONT BY NTPC |  | 1.19.3.1 | Unscheduled | No | No | 2020-05-27 09:00 | 2020-05-27 18:00 | 2020-09-02 09:00 | 2020-09-02 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4817 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019868
2440 | Task(Task)-->C (Construction) | EXCAVATION |  | 1.19.3.1 | Unscheduled | No | No | 2020-06-03 09:00 | 2020-07-28 18:00 | 2020-09-09 09:00 | 2020-11-03 18:00 | [6 empty] | 100 | 0 | [15 empty] | 6.7612 | 0.027155 | 2.67 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 9990 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4818 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | Excavation | [21 empty] | 1019869
2441 | Task(Task)-->C (Construction) | PCC |  | 1.19.3.1 | Unscheduled | No | No | 2020-06-18 09:00 | 2020-08-04 18:00 | 2020-09-24 09:00 | 2020-11-10 18:00 | [6 empty] | 100 | 0 | [15 empty] | 2.0765 | 0.00834 | 0.82 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 91 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4819 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | PCC | [21 empty] | 1019870
2442 | Task(Task)-->C (Construction) | CABLE GALLARY TRESTLE FOUNDATION |  | 1.19.3.1 | Unscheduled | No | No | 2020-07-03 09:00 | 2020-08-19 18:00 | 2020-10-09 09:00 | 2020-11-25 18:00 | [6 empty] | 100 | 0 | [15 empty] | 8.0527 | 0.032342 | 3.18 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4820 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019871
2443 | Task(Task)-->C (Construction) | CABLE GALLARY TRESTLE PEDESTAL |  | 1.19.3.1 | Unscheduled | No | No | 2020-07-28 09:00 | 2020-09-18 18:00 | 2020-11-03 09:00 | 2020-12-25 18:00 | [6 empty] | 100 | 0 | [15 empty] | 4.7607 | 0.01912 | 1.88 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 71 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4821 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019872
2444 | Task(Task)-->C (Construction) | CABLE TRENCH FOUNDATION, WALL & RCC COVER |  | 1.19.3.1 | Unscheduled | No | No | 2020-07-28 09:00 | 2020-10-03 18:00 | 2020-11-03 09:00 | 2021-01-09 18:00 | [6 empty] | 100 | 0 | [15 empty] | 16.7891 | 0.067429 | 6.63 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4822 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019873
2445 | Task(Task)-->C (Construction) | PIPE CULVERT & PULPIT |  | 1.19.3.1 | Unscheduled | No | No | 2020-07-28 09:00 | 2020-10-03 18:00 | 2020-11-03 09:00 | 2021-01-09 18:00 | [6 empty] | 100 | 0 | [15 empty] | 5.3684 | 0.021561 | 2.12 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4823 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019874
2446 | Task(Task)-->C (Construction) | BACK FILLING |  | 1.19.3.1 | Unscheduled | No | No | 2020-08-27 09:00 | 2020-11-02 18:00 | 2020-12-03 09:00 | 2021-02-08 18:00 | [6 empty] | 61.7647 | 0 | [15 empty] | 56.1914 | 0.22568 | 22.19 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 8319 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4824 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019875
2447 | Task(Task)-->C (Construction) | STRUCTURAL | 1.19.3.2 | 1.19.3 | Unscheduled | No | No | 2020-12-01 09:00 | 2021-04-29 18:00 | 2021-05-01 09:00 | 2021-09-27 18:00 | [6 empty] | 0 | 0 | [15 empty] | 31.131 | 0.22948 | 22.57 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5264 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019876
2448 | Task(Task)-->C (Construction) | STRUCTURAL WORK |  | 1.19.3.2 | Unscheduled | No | No | 2020-12-01 09:00 | 2021-04-29 18:00 | 2021-05-01 09:00 | 2021-09-27 18:00 | [6 empty] | 0 | 0 | [15 empty] | 100 | 0.22948 | 22.57 | Plan & Actual | Quantity | Metric Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 349 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4825 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019877
2449 | Task(Task)-->C (Construction) | ELECTRICAL | 1.19.3.3 | 1.19.3 | Unscheduled | No | No | 2021-04-15 09:00 | 2021-05-28 18:00 | 2021-09-13 09:00 | 2021-10-26 18:00 | [6 empty] | 0 | 0 | [15 empty] | 14.3862 | 0.10605 | 10.43 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5265 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019878
2450 | Task(Task)-->C (Construction) | CABLE TRAY |  | 1.19.3.3 | Unscheduled | No | No | 2021-04-15 09:00 | 2021-04-27 18:00 | 2021-09-13 09:00 | 2021-09-25 18:00 | [6 empty] | 0 | 0 | [15 empty] | 13.3269 | 0.014133 | 1.39 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 3250 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4826 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019879
2451 | Task(Task)-->C (Construction) | CABLE LAYING |  | 1.19.3.3 | Unscheduled | No | No | 2021-04-28 09:00 | 2021-05-18 18:00 | 2021-09-26 | 2021-10-16 18:00 | [6 empty] | 0 | 0 | [15 empty] | 28.9549 | 0.030706 | 3.02 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 21355 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5399 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019880
2452 | Task(Task)-->C (Construction) | EARTHING |  | 1.19.3.3 | Unscheduled | No | No | 2021-04-20 09:00 | 2021-05-12 18:00 | 2021-09-18 09:00 | 2021-10-10 23:59 | [6 empty] | 0 | 0 | [15 empty] | 50.5273 | 0.053584 | 5.27 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 23600 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5400 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019881
2453 | Task(Task)-->C (Construction) | LIGHTING |  | 1.19.3.3 | Unscheduled | No | No | 2021-05-19 09:00 | 2021-05-28 18:00 | 2021-10-17 | 2021-10-26 18:00 | [6 empty] | 0 | 0 | [15 empty] | 7.1908 | 0.007626 | 0.75 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 77 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5401 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019882
2454 | Task(Task)-->E (Engineering) | TRANSMISSION LINE | 1.20 | 1 | Work In Progress | No | No | 2019-09-27 09:00 | 2021-05-18 18:00 | 2019-09-27 09:00 | 2021-12-02 18:00 |  |  | 2019-09-27 10:57 |  |  |  | 78.9461 | 11.6967 | [15 empty] | 2.8466 | 2.8466 | 279.94 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4827 | 0 | 1 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019883
2455 | Task(Task)-->E (Engineering) | ENGINEERING | 1.20.1 | 1.20 | Unscheduled | No | No | 2019-11-18 18:00 | 2020-06-12 17:40 | 2019-10-18 18:00 | 2020-10-23 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 17.1725 | [15 empty] | 0.63585 | 0.0181 | 1.78 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4828 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019884
2456 | Task(Task)-->E (Engineering) | CIVIL | 1.20.1.1 | 1.20.1 | Unscheduled | No | No | 2019-12-31 18:00 | 2020-06-12 17:40 | 2019-10-18 18:00 | 2020-08-21 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 7.2727 | [15 empty] | 38.764 | 0.007016 | 0.69 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4829 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036130
2457 | Task(Task)-->E (Engineering) | Gantry Tower : Design calculation for Sub Structure |  | 1.20.1.1 | Unscheduled | No | No | 2020-04-14 18:00 | 2020-06-12 17:40 | 2020-06-15 18:00 | 2020-08-21 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0041 |  | 2020-02-13 11:44 | 7012-155-PVC-U-134 |  |  |  | A |  |  |  | 9.0909 | 0.000638 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 22.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4833 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-14 18:00 | 2020-06-15 18:00 |  | 10 |  |  |  | 2020-05-02 17:40 | 2020-07-06 18:00 |  | 30 |  |  |  | 2020-05-08 17:40 | 2020-07-09 18:00 |  | 35 |  |  |  | 2020-05-15 23:59 | 2020-07-16 18:00 |  | 65 |  |  |  | 2020-05-21 17:40 | 2020-08-06 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-12 17:40 | 2020-08-06 18:00 |  | 100 | [122 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 234 |  |  |  | 101244
2458 | Task(Task)-->E (Engineering) | Gantry Tower : NUM & RC DETAILS (SHT 1) |  | 1.20.1.1 | Unscheduled | No | No | 2020-04-14 18:00 | 2020-06-12 17:40 | 2020-06-15 18:00 | 2020-08-21 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-NR-0049 |  | 2020-02-13 11:44 | 7012-155-PVC-C-135 |  |  |  | A |  |  |  | 9.0909 | 0.000638 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 22.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4832 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-14 18:00 | 2020-06-15 18:00 |  | 10 |  |  |  | 2020-05-02 17:40 | 2020-07-06 18:00 |  | 30 |  |  |  | 2020-05-08 17:40 | 2020-07-09 18:00 |  | 35 |  |  |  | 2020-05-15 23:59 | 2020-07-16 18:00 |  | 65 |  |  |  | 2020-05-21 17:40 | 2020-08-06 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-12 17:40 | 2020-08-06 18:00 |  | 100 | [122 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 235 |  |  |  | 101245
2459 | Task(Task)-->E (Engineering) | Route Survey Report (for 33kV D/C transmission line route). |  | 1.20.1.1 | Unscheduled | No | No | 2019-12-31 18:00 | 2020-02-29 17:40 | 2019-10-18 18:00 | 2019-12-27 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0036 |  | 2020-02-13 11:43 | 7012-155-PVC-U-126 |  |  |  | A |  |  |  | 9.0909 | 0.000638 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 22.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4830 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-12-31 18:00 | 2019-10-18 18:00 |  | 10 | 2019-10-18 23:31 |  |  | 2020-01-20 17:40 | 2019-11-12 18:00 |  | 30 | 2019-11-12 23:31 |  |  | 2020-01-25 17:40 | 2019-11-15 18:00 |  | 35 | 2019-11-15 23:31 |  |  | 2020-01-31 23:59 | 2019-11-22 18:00 |  | 65 | 2019-11-22 23:31 |  |  | 2020-02-06 17:40 | 2019-12-27 18:00 |  | 80 | 2019-12-27 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-02-29 17:40 | 2019-12-27 18:00 |  | 100 | [122 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 226 |  |  |  | 101236
2460 | Task(Task)-->E (Engineering) | Geotechnical Investigation Report (for 33kV D/C transmission line route). |  | 1.20.1.1 | Unscheduled | No | No | 2020-01-28 18:00 | 2020-03-27 17:40 | 2020-06-15 18:00 | 2020-08-21 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0037 |  | 2020-02-13 11:43 | 7012-155-PVC-U-127 |  |  |  | A |  |  |  | 18.1818 | 0.001276 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 45.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4831 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-28 18:00 | 2020-06-15 18:00 |  | 10 |  |  |  | 2020-02-15 17:40 | 2020-07-06 18:00 |  | 30 |  |  |  | 2020-02-21 17:40 | 2020-07-09 18:00 |  | 35 |  |  |  | 2020-02-28 23:59 | 2020-07-16 18:00 |  | 65 |  |  |  | 2020-03-05 17:40 | 2020-08-06 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-27 17:40 | 2020-08-06 18:00 |  | 100 | [122 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 227 |  |  |  | 101237
2461 | Task(Task)-->E (Engineering) | 220kV Monopole Tower : Design calculation for Sub Structure |  | 1.20.1.1 | Unscheduled | No | No | 2020-03-26 18:00 | 2020-05-25 17:40 | 2020-06-15 18:00 | 2020-08-21 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0038 |  | 2020-02-13 11:43 | 7012-155-PVC-U-128 |  |  |  | A |  |  |  | 9.0909 | 0.000638 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 22.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4837 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-26 18:00 | 2020-06-15 18:00 |  | 10 |  |  |  | 2020-04-14 17:40 | 2020-07-06 18:00 |  | 30 |  |  |  | 2020-04-20 17:40 | 2020-07-09 18:00 |  | 35 |  |  |  | 2020-04-26 23:59 | 2020-07-16 18:00 |  | 65 |  |  |  | 2020-05-01 17:40 | 2020-08-06 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-25 17:40 | 2020-08-06 18:00 |  | 100 | [122 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 228 |  |  |  | 101238
2462 | Task(Task)-->E (Engineering) | 220kV Monopole Tower : NUM & RC DETAILS (SHT 1) |  | 1.20.1.1 | Unscheduled | No | No | 2020-03-26 18:00 | 2020-05-25 17:40 | 2020-06-15 18:00 | 2020-08-21 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-NR-0046 |  | 2020-02-13 11:43 | 7012-155-PVC-C-129 |  |  |  | A |  |  |  | 9.0909 | 0.000638 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 22.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4834 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-26 18:00 | 2020-06-15 18:00 |  | 10 |  |  |  | 2020-04-14 17:40 | 2020-07-06 18:00 |  | 30 |  |  |  | 2020-04-20 17:40 | 2020-07-09 18:00 |  | 35 |  |  |  | 2020-04-26 23:59 | 2020-07-16 18:00 |  | 65 |  |  |  | 2020-05-01 17:40 | 2020-08-06 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-25 17:40 | 2020-08-06 18:00 |  | 100 | [122 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 229 |  |  |  | 101239
2463 | Task(Task)-->E (Engineering) | 33 kV Isolator : Design calculation for Sub Structure |  | 1.20.1.1 | Unscheduled | No | No | 2020-04-02 18:00 | 2020-06-01 17:40 | 2020-06-15 18:00 | 2020-08-21 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0039 |  | 2020-02-13 11:43 | 7012-155-PVC-U-130 |  |  |  | A |  |  |  | 9.0909 | 0.000638 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 22.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4838 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-02 18:00 | 2020-06-15 18:00 |  | 10 |  |  |  | 2020-04-21 17:40 | 2020-07-06 18:00 |  | 30 |  |  |  | 2020-04-28 17:40 | 2020-07-09 18:00 |  | 35 |  |  |  | 2020-05-03 23:59 | 2020-07-16 18:00 |  | 65 |  |  |  | 2020-05-08 17:40 | 2020-08-06 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-01 17:40 | 2020-08-06 18:00 |  | 100 | [122 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 230 |  |  |  | 101240
2464 | Task(Task)-->E (Engineering) | 33 kV Isolator : NUM & RC DETAILS (SHT 1) |  | 1.20.1.1 | Unscheduled | No | No | 2020-04-02 18:00 | 2020-06-01 17:40 | 2020-06-15 18:00 | 2020-08-21 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-NR-0047 |  | 2020-02-13 11:44 | 7012-155-PVC-C-131 |  |  |  | A |  |  |  | 9.0909 | 0.000638 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 22.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4835 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-02 18:00 | 2020-06-15 18:00 |  | 10 |  |  |  | 2020-04-21 17:40 | 2020-07-06 18:00 |  | 30 |  |  |  | 2020-04-28 17:40 | 2020-07-09 18:00 |  | 35 |  |  |  | 2020-05-03 23:59 | 2020-07-16 18:00 |  | 65 |  |  |  | 2020-05-08 17:40 | 2020-08-06 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-01 17:40 | 2020-08-06 18:00 |  | 100 | [122 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 231 |  |  |  | 101241
2465 | Task(Task)-->E (Engineering) | 33 kV LA : Design calculation for Sub Structure |  | 1.20.1.1 | Unscheduled | No | No | 2020-04-02 18:00 | 2020-06-01 17:40 | 2020-06-15 18:00 | 2020-08-21 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0040 |  | 2020-02-13 11:44 | 7012-155-PVC-U-132 |  |  |  | A |  |  |  | 9.0909 | 0.000638 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 22.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4839 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-02 18:00 | 2020-06-15 18:00 |  | 10 |  |  |  | 2020-04-21 17:40 | 2020-07-06 18:00 |  | 30 |  |  |  | 2020-04-28 17:40 | 2020-07-09 18:00 |  | 35 |  |  |  | 2020-05-03 23:59 | 2020-07-16 18:00 |  | 65 |  |  |  | 2020-05-08 17:40 | 2020-08-06 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-01 17:40 | 2020-08-06 18:00 |  | 100 | [122 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 232 |  |  |  | 101242
2466 | Task(Task)-->E (Engineering) | 33 kV LA : NUM & RC DETAILS (SHT 1) |  | 1.20.1.1 | Unscheduled | No | No | 2020-04-02 18:00 | 2020-06-01 17:40 | 2020-06-15 18:00 | 2020-08-21 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-NR-0048 |  | 2020-02-13 11:44 | 7012-155-PVC-C-133 |  |  |  | A |  |  |  | 9.0909 | 0.000638 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 22.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4836 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-02 18:00 | 2020-06-15 18:00 |  | 10 |  |  |  | 2020-04-21 17:40 | 2020-07-06 18:00 |  | 30 |  |  |  | 2020-04-28 17:40 | 2020-07-09 18:00 |  | 35 |  |  |  | 2020-05-03 23:59 | 2020-07-16 18:00 |  | 65 |  |  |  | 2020-05-08 17:40 | 2020-08-06 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-01 17:40 | 2020-08-06 18:00 |  | 100 | [122 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 233 |  |  |  | 101243
2467 | Task(Task)-->E (Engineering) | ELECTRICAL | 1.20.1.2 | 1.20.1 | Unscheduled | No | No | 2019-11-18 18:00 | 2020-05-15 17:40 | 2019-11-13 18:00 | 2020-10-23 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 23.4389 | [15 empty] | 61.236 | 0.011084 | 1.09 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4841 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036131
2468 | Task(Task)-->E (Engineering) | 6.6kV HT APFC CAPACITOR SIZING CALCULATION FOR CHP |  | 1.20.1.2 | Unscheduled | No | No | 2019-11-18 18:00 | 2020-01-06 17:40 | 2019-11-25 18:00 | 2020-04-30 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DC-5011 |  | 2020-02-13 11:44 | 7012-155-PVE-U-011 |  |  |  | A |  |  |  | 18.0328 | 0.001999 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 82.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4843 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-11-18 18:00 | 2019-11-25 18:00 |  | 10 | 2019-11-25 23:31 |  |  | 2019-11-28 17:40 | 2019-12-10 18:00 |  | 30 | 2019-12-10 23:31 |  |  | 2019-12-04 17:40 | 2019-12-10 18:00 |  | 35 | 2019-12-10 23:31 |  |  | 2019-12-10 23:59 | 2019-12-13 18:00 |  | 65 | 2019-12-13 23:31 |  |  | 2019-12-16 17:40 | 2019-12-27 18:00 |  | 80 | 2019-12-27 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-01-06 17:40 | 2020-04-30 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 246 |  |  |  | 101257
2469 | Task(Task)-->E (Engineering) | TRANSMISSION LINE ROUTE & 220kV MONOPOLE TOWER SPOTTING PROFILE FOR 33KV D/C TRANSMISSION LINE |  | 1.20.1.2 | Unscheduled | No | No | 2020-03-26 18:00 | 2020-05-15 17:40 | 2019-11-13 18:00 | 2020-04-05 23:59 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-100 |  | 2020-02-13 11:45 | 7012-155-PVE-V-045 |  |  |  | A |  |  |  | 9.0164 | 0.000999 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 22.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4845 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-26 18:00 | 2019-11-13 18:00 |  | 10 | 2019-11-13 23:31 |  |  | 2020-04-03 17:40 | 2019-11-20 18:00 |  | 30 | 2019-11-20 23:31 |  |  | 2020-04-09 17:40 | 2019-11-27 18:00 |  | 35 | 2019-11-27 23:31 |  |  | 2020-04-16 23:59 | 2019-12-04 18:00 |  | 65 | 2019-12-04 23:31 |  |  | 2020-04-22 17:40 | 2019-12-10 18:00 |  | 80 | 2019-12-10 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-15 17:40 | 2020-04-05 23:59 |  | 100 | 2020-05-11 23:31 | [121 empty] | Varun Parihari | [21 empty] | 280 |  |  |  | 101291
2470 | Task(Task)-->E (Engineering) | 33KV EQUIPMENT SUPPORT STRUCTURE-ISOLATOR |  | 1.20.1.2 | Unscheduled | No | No | 2020-02-24 18:00 | 2020-05-15 17:40 | 2020-06-05 18:00 | 2020-08-21 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-101 |  | 2020-02-13 11:45 | 7012-155-PVE-V-046 |  |  |  | A |  |  |  | 4.918 | 0.000545 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4846 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-24 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-04-03 17:40 | 2020-07-20 18:00 |  | 30 |  |  |  | 2020-04-09 17:40 | 2020-07-27 18:00 |  | 35 |  |  |  | 2020-04-16 23:59 | 2020-07-27 18:00 |  | 65 |  |  |  | 2020-04-22 17:40 | 2020-08-17 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-15 17:40 | 2020-08-17 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 281 |  |  |  | 101292
2471 | Task(Task)-->E (Engineering) | 33KV EQUIPMENT SUPPORT STRUCTURE-LA |  | 1.20.1.2 | Unscheduled | No | No | 2020-02-24 18:00 | 2020-05-15 17:40 | 2020-06-05 18:00 | 2020-08-21 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-102 |  | 2020-02-13 11:45 | 7012-155-PVE-V-047 |  |  |  | A |  |  |  | 4.918 | 0.000545 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4847 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-24 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-04-03 17:40 | 2020-07-20 18:00 |  | 30 |  |  |  | 2020-04-09 17:40 | 2020-07-27 18:00 |  | 35 |  |  |  | 2020-04-16 23:59 | 2020-07-27 18:00 |  | 65 |  |  |  | 2020-04-22 17:40 | 2020-08-17 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-15 17:40 | 2020-08-17 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 282 |  |  |  | 101293
2472 | Task(Task)-->E (Engineering) | 33KV EQUIPMENT SUPPORT STRUCTURE-BPI |  | 1.20.1.2 | Unscheduled | No | No | 2020-02-24 18:00 | 2020-05-15 17:40 | 2020-06-05 18:00 | 2020-08-21 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-103 |  | 2020-02-13 11:45 | 7012-155-PVE-V-048 |  |  |  | A |  |  |  | 4.918 | 0.000545 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4848 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-24 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-04-03 17:40 | 2020-07-20 18:00 |  | 30 |  |  |  | 2020-04-09 17:40 | 2020-07-27 18:00 |  | 35 |  |  |  | 2020-04-16 23:59 | 2020-07-27 18:00 |  | 65 |  |  |  | 2020-04-22 17:40 | 2020-08-17 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-15 17:40 | 2020-08-17 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 283 |  |  |  | 101294
2473 | Task(Task)-->E (Engineering) | 33KV EQPT. PROTO CORRECTED SUPPORT STRUCTURE-ISOLATOR |  | 1.20.1.2 | Unscheduled | No | No | 2020-02-24 18:00 | 2020-05-15 17:40 | 2020-06-05 18:00 | 2020-08-21 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-104 |  | 2020-02-13 11:45 | 7012-155-PVE-V-049 |  |  |  | A |  |  |  | 4.918 | 0.000545 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4849 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-24 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-04-03 17:40 | 2020-07-20 18:00 |  | 30 |  |  |  | 2020-04-09 17:40 | 2020-07-27 18:00 |  | 35 |  |  |  | 2020-04-16 23:59 | 2020-07-27 18:00 |  | 65 |  |  |  | 2020-04-22 17:40 | 2020-08-17 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-15 17:40 | 2020-08-17 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 284 |  |  |  | 101295
2474 | Task(Task)-->E (Engineering) | 33KV EQPT. PROTO CORRECTED SUPPORT STRUCTURE-LA |  | 1.20.1.2 | Unscheduled | No | No | 2020-02-24 18:00 | 2020-05-15 17:40 | 2020-06-05 18:00 | 2020-08-21 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-105 |  | 2020-02-13 11:45 | 7012-155-PVE-V-050 |  |  |  | A |  |  |  | 4.918 | 0.000545 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4850 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-24 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-04-03 17:40 | 2020-07-20 18:00 |  | 30 |  |  |  | 2020-04-09 17:40 | 2020-07-27 18:00 |  | 35 |  |  |  | 2020-04-16 23:59 | 2020-07-27 18:00 |  | 65 |  |  |  | 2020-04-22 17:40 | 2020-08-17 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-15 17:40 | 2020-08-17 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 285 |  |  |  | 101296
2475 | Task(Task)-->E (Engineering) | 33KV EQPT. PROTO CORRECTED SUPPORT STRUCTURE-BPI |  | 1.20.1.2 | Unscheduled | No | No | 2020-02-24 18:00 | 2020-05-15 17:40 | 2020-06-05 18:00 | 2020-08-21 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-106 |  | 2020-02-13 11:45 | 7012-155-PVE-V-051 |  |  |  | A |  |  |  | 4.918 | 0.000545 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4851 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-24 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-04-03 17:40 | 2020-07-20 18:00 |  | 30 |  |  |  | 2020-04-09 17:40 | 2020-07-27 18:00 |  | 35 |  |  |  | 2020-04-16 23:59 | 2020-07-27 18:00 |  | 65 |  |  |  | 2020-04-22 17:40 | 2020-08-17 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-15 17:40 | 2020-08-17 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 286 |  |  |  | 101297
2476 | Task(Task)-->E (Engineering) | 33KV ISOLATOR -DRAWINGS |  | 1.20.1.2 | Unscheduled | No | No | 2020-02-24 18:00 | 2020-05-15 17:40 | 2020-06-05 18:00 | 2020-08-21 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-107 |  | 2020-02-13 11:45 | 7012-155-PVE-W-052 |  |  |  | A |  |  |  | 4.918 | 0.000545 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4852 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-24 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-04-03 17:40 | 2020-07-20 18:00 |  | 30 |  |  |  | 2020-04-09 17:40 | 2020-07-27 18:00 |  | 35 |  |  |  | 2020-04-16 23:59 | 2020-07-27 18:00 |  | 65 |  |  |  | 2020-04-22 17:40 | 2020-08-17 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-15 17:40 | 2020-08-17 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 287 |  |  |  | 101298
2477 | Task(Task)-->E (Engineering) | 33KV LA -DRAWINGS |  | 1.20.1.2 | Unscheduled | No | No | 2020-02-24 18:00 | 2020-05-15 17:40 | 2020-06-05 18:00 | 2020-08-21 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-108 |  | 2020-02-13 11:45 | 7012-155-PVE-W-053 |  |  |  | A |  |  |  | 4.918 | 0.000545 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4853 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-24 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-04-03 17:40 | 2020-07-20 18:00 |  | 30 |  |  |  | 2020-04-09 17:40 | 2020-07-27 18:00 |  | 35 |  |  |  | 2020-04-16 23:59 | 2020-07-27 18:00 |  | 65 |  |  |  | 2020-04-22 17:40 | 2020-08-17 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-15 17:40 | 2020-08-17 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 288 |  |  |  | 101299
2478 | Task(Task)-->E (Engineering) | 33KV STRING HARDWARE -GA, PART DRAWINGS |  | 1.20.1.2 | Unscheduled | No | No | 2020-02-24 18:00 | 2020-05-15 17:40 | 2020-06-05 18:00 | 2020-08-21 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-109 |  | 2020-02-13 11:45 | 7012-155-PVE-W-054 |  |  |  | A |  |  |  | 4.918 | 0.000545 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4854 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-24 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-04-03 17:40 | 2020-07-20 18:00 |  | 30 |  |  |  | 2020-04-09 17:40 | 2020-07-27 18:00 |  | 35 |  |  |  | 2020-04-16 23:59 | 2020-07-27 18:00 |  | 65 |  |  |  | 2020-04-22 17:40 | 2020-08-17 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-15 17:40 | 2020-08-17 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 289 |  |  |  | 101300
2479 | Task(Task)-->E (Engineering) | 33KV CLAMPS & CONNECTORS- DRAWINGS & DATA SHEET |  | 1.20.1.2 | Unscheduled | No | No | 2020-02-24 18:00 | 2020-05-15 17:40 | 2020-06-05 18:00 | 2020-08-21 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-110 |  | 2020-02-13 11:45 | 7012-155-PVE-W-055 |  |  |  | A |  |  |  | 1.6393 | 0.000182 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 8.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4855 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-24 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-04-03 17:40 | 2020-07-20 18:00 |  | 30 |  |  |  | 2020-04-09 17:40 | 2020-07-27 18:00 |  | 35 |  |  |  | 2020-04-16 23:59 | 2020-07-27 18:00 |  | 65 |  |  |  | 2020-04-22 17:40 | 2020-08-17 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-15 17:40 | 2020-08-17 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 290 |  |  |  | 101301
2480 | Task(Task)-->E (Engineering) | 33kV D/C TRANSMISSION LINE ERECTION KEY DIAGRAM |  | 1.20.1.2 | Unscheduled | No | No | 2020-02-24 18:00 | 2020-05-15 17:40 | 2020-06-05 18:00 | 2020-08-21 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-111 |  | 2020-02-13 11:45 | 7012-155-PVE-E-056 |  |  |  | A |  |  |  | 4.918 | 0.000545 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4842 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-24 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-04-03 17:40 | 2020-07-20 18:00 |  | 30 |  |  |  | 2020-04-09 17:40 | 2020-07-27 18:00 |  | 35 |  |  |  | 2020-04-16 23:59 | 2020-07-27 18:00 |  | 65 |  |  |  | 2020-04-22 17:40 | 2020-08-17 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-15 17:40 | 2020-08-17 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 291 |  |  |  | 101302
2481 | Task(Task)-->E (Engineering) | 33KV D/C TRANSMISSION LINE- ACSR ZEBRA CONDUCTOR- DRAWINGS & DATA SHEET |  | 1.20.1.2 | Unscheduled | No | No | 2020-02-24 18:00 | 2020-05-15 17:40 | 2020-06-05 18:00 | 2020-08-21 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-112 |  | 2020-02-13 11:45 | 7012-155-PVE-Y-057 |  |  |  | A |  |  |  | 1.6393 | 0.000182 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 8.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4860 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-24 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-04-03 17:40 | 2020-07-20 18:00 |  | 30 |  |  |  | 2020-04-09 17:40 | 2020-07-27 18:00 |  | 35 |  |  |  | 2020-04-16 23:59 | 2020-07-27 18:00 |  | 65 |  |  |  | 2020-04-22 17:40 | 2020-08-17 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-15 17:40 | 2020-08-17 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 292 |  |  |  | 101303
2482 | Task(Task)-->E (Engineering) | TRANSMISSION LINE- 33KV INSULATOR- DRAWINGS & DATA SHEET |  | 1.20.1.2 | Unscheduled | No | No | 2020-02-24 18:00 | 2020-05-15 17:40 | 2020-06-05 18:00 | 2020-08-21 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-113 |  | 2020-02-13 11:45 | 7012-155-PVE-Y-058 |  |  |  | A |  |  |  | 1.6393 | 0.000182 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 8.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4861 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-24 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-04-03 17:40 | 2020-07-20 18:00 |  | 30 |  |  |  | 2020-04-09 17:40 | 2020-07-27 18:00 |  | 35 |  |  |  | 2020-04-16 23:59 | 2020-07-27 18:00 |  | 65 |  |  |  | 2020-04-22 17:40 | 2020-08-17 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-15 17:40 | 2020-08-17 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 293 |  |  |  | 101304
2483 | Task(Task)-->E (Engineering) | TRANSMISSION LINE- PLACEMENT CHART OF VIBRATION DAMPERS |  | 1.20.1.2 | Unscheduled | No | No | 2020-02-24 18:00 | 2020-05-15 17:40 | 2020-06-05 18:00 | 2020-08-21 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-114 |  | 2020-02-13 11:45 | 7012-155-PVE-W-059 |  |  |  | A |  |  |  | 1.6393 | 0.000182 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 8.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4862 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-24 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-04-03 17:40 | 2020-07-20 18:00 |  | 30 |  |  |  | 2020-04-09 17:40 | 2020-07-27 18:00 |  | 35 |  |  |  | 2020-04-16 23:59 | 2020-07-27 18:00 |  | 65 |  |  |  | 2020-04-22 17:40 | 2020-08-17 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-15 17:40 | 2020-08-17 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 294 |  |  |  | 101305
2484 | Task(Task)-->E (Engineering) | TRANSMISSION LINE- EARTHING DETAILS |  | 1.20.1.2 | Unscheduled | No | No | 2020-02-24 18:00 | 2020-05-15 17:40 | 2020-06-05 18:00 | 2020-08-21 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-115 |  | 2020-02-13 11:45 | 7012-155-PVE-W-060 |  |  |  | A |  |  |  | 1.6393 | 0.000182 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 8.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4863 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-24 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-04-03 17:40 | 2020-07-20 18:00 |  | 30 |  |  |  | 2020-04-09 17:40 | 2020-07-27 18:00 |  | 35 |  |  |  | 2020-04-16 23:59 | 2020-07-27 18:00 |  | 65 |  |  |  | 2020-04-22 17:40 | 2020-08-17 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-15 17:40 | 2020-08-17 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 295 |  |  |  | 101306
2485 | Task(Task)-->E (Engineering) | D/C TRANSMISSION LINE- BILL OF MATERIALS |  | 1.20.1.2 | Unscheduled | No | No | 2020-02-24 18:00 | 2020-05-15 17:40 | 2020-06-05 18:00 | 2020-10-23 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-116 |  | 2020-02-13 11:45 | 7012-155-PVE-W-061 |  |  |  | A |  |  |  | 1.6393 | 0.000182 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 8.17 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4864 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-24 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-04-03 17:40 | 2020-07-20 18:00 |  | 30 |  |  |  | 2020-04-09 17:40 | 2020-07-27 18:00 |  | 35 |  |  |  | 2020-04-16 23:59 | 2020-07-27 18:00 |  | 65 |  |  |  | 2020-04-22 17:40 | 2020-08-17 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-15 17:40 | 2020-08-17 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 296 |  |  |  | 101307
2486 | Task(Task)-->E (Engineering) | 33 KV D/C TRANSMISSION LINE- 220kV MONO POLE TOWER TYPE- DB- TYPE TESTED/ PROTO CORRECTED STRUCTAL DRAWING |  | 1.20.1.2 | Unscheduled | No | No | 2020-02-24 18:00 | 2020-05-15 17:40 | 2020-06-05 18:00 | 2020-08-21 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-118 |  | 2020-02-13 11:45 | 7012-155-PVE-W-063 |  |  |  | A |  |  |  | 1.6393 | 0.000182 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 8.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4856 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-24 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-04-03 17:40 | 2020-07-20 18:00 |  | 30 |  |  |  | 2020-04-09 17:40 | 2020-07-27 18:00 |  | 35 |  |  |  | 2020-04-16 23:59 | 2020-07-27 18:00 |  | 65 |  |  |  | 2020-04-22 17:40 | 2020-08-17 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-15 17:40 | 2020-08-17 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 298 |  |  |  | 101309
2487 | Task(Task)-->E (Engineering) | 33 KV D/C TRANSMISSION LINE- 220kV MONO POLE TOWER TYPE- DD- TYPE TESTED/ PROTO CORRECTED STRUCTAL DRAWING |  | 1.20.1.2 | Unscheduled | No | No | 2020-02-24 18:00 | 2020-05-15 17:40 | 2020-06-05 18:00 | 2020-08-21 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-119 |  | 2020-02-13 11:45 | 7012-155-PVE-W-064 |  |  |  | A |  |  |  | 1.6393 | 0.000182 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 8.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4857 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-24 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-04-03 17:40 | 2020-07-20 18:00 |  | 30 |  |  |  | 2020-04-09 17:40 | 2020-07-27 18:00 |  | 35 |  |  |  | 2020-04-16 23:59 | 2020-07-27 18:00 |  | 65 |  |  |  | 2020-04-22 17:40 | 2020-08-17 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-15 17:40 | 2020-08-17 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 299 |  |  |  | 101310
2488 | Task(Task)-->E (Engineering) | 33 KV D/C TRANSMISSION LINE- 220kV MONO POLE TOWER TYPE- DE- TYPE TESTED/ PROTO CORRECTED STRUCTAL DRAWING |  | 1.20.1.2 | Unscheduled | No | No | 2020-02-24 18:00 | 2020-05-15 17:40 | 2020-06-05 18:00 | 2020-08-21 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-120 |  | 2020-02-13 11:45 | 7012-155-PVE-W-065 |  |  |  | A |  |  |  | 1.6393 | 0.000182 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 8.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4858 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-24 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-04-03 17:40 | 2020-07-20 18:00 |  | 30 |  |  |  | 2020-04-09 17:40 | 2020-07-27 18:00 |  | 35 |  |  |  | 2020-04-16 23:59 | 2020-07-27 18:00 |  | 65 |  |  |  | 2020-04-22 17:40 | 2020-08-17 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-15 17:40 | 2020-08-17 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 300 |  |  |  | 101311
2489 | Task(Task)-->E (Engineering) | 33 KV D/C TRANSMISSION LINE- SAG TENSION CALCULATION & CLEARANCE CHECK DIAGRAM |  | 1.20.1.2 | Unscheduled | No | No | 2020-02-24 18:00 | 2020-05-15 17:40 | 2020-06-05 18:00 | 2020-09-18 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-117 |  | 2020-02-13 11:45 | 7012-155-PVE-U-062 |  |  |  | A |  |  |  | 9.0164 | 0.000999 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4844 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-24 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-04-03 17:40 | 2020-07-20 18:00 |  | 30 |  |  |  | 2020-04-09 17:40 | 2020-07-27 18:00 |  | 35 |  |  |  | 2020-04-16 23:59 | 2020-07-27 18:00 |  | 65 |  |  |  | 2020-04-22 17:40 | 2020-08-17 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-15 17:40 | 2020-08-17 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 297 |  |  |  | 101308
2490 | Task(Task)-->P (Procurement) | PROCUREMENT | 1.20.2 | 1.20 | Work In Progress | No | No | 2019-09-27 09:00 | 2020-11-13 18:00 | 2019-09-27 09:00 | 2021-07-21 18:00 |  |  | 2019-09-27 10:57 |  |  |  | 91.5271 | 20.0012 | [15 empty] | 57.9338 | 1.6491 | 162.18 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4865 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019887
2491 | Task(Task)-->P (Procurement) | PURCHASE REQUISITION | 1.20.2.1 | 1.20.2 | Completed | No | No | 2019-09-27 09:00 | 2019-09-27 18:00 | 2019-09-27 09:00 | 2019-09-27 18:00 |  |  | 2019-09-27 10:57 | 2019-09-27 10:57 |  |  | 100 | 100 | [15 empty] | 5.0003 | 0.082461 | 8.11 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4866 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019888
2492 | Task(Task)-->P (Procurement) | 33KV OVERHEAD TRANSMISSION LINE |  | 1.20.2.1 | Completed | No | No | 2019-09-27 09:00 | 2019-09-27 18:00 | 2019-09-27 09:00 | 2019-09-27 18:00 |  |  | 2019-09-27 10:57 | 2019-09-27 10:57 |  |  | 100 | 100 | [15 empty] | 100 | 0.082461 | 8.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4867 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019889
2493 | Task(Task)-->P (Procurement) | TECHNICAL CLEARANCE | 1.20.2.2 | 1.20.2 | Completed | No | No | 2019-09-28 09:00 | 2019-11-15 18:00 | 2019-09-27 09:00 | 2020-03-10 18:00 |  |  | 2020-03-10 10:57 | 2020-03-10 10:57 |  |  | 100 | 100 | [15 empty] | 5.0003 | 0.082461 | 8.11 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4868 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019890
2494 | Task(Task)-->P (Procurement) | 33KV OVERHEAD TRANSMISSION LINE |  | 1.20.2.2 | Completed | No | No | 2019-09-28 09:00 | 2019-11-15 18:00 | 2019-09-27 09:00 | 2020-03-10 18:00 |  |  | 2020-03-10 10:57 | 2020-03-10 10:57 |  |  | 100 | 100 | [15 empty] | 100 | 0.082461 | 8.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4869 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019891
2495 | Task(Task)-->P (Procurement) | ORDERING | 1.20.2.3 | 1.20.2 | Completed | No | No | 2019-11-16 09:00 | 2019-12-27 18:00 | 2020-03-10 09:00 | 2020-08-01 18:00 |  |  | 2020-03-11 17:28 | 2020-07-07 17:28 |  |  | 100 | 100 | [15 empty] | 10.0006 | 0.16492 | 16.22 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4870 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019892
2496 | Task(Task)-->P (Procurement) | 33KV OVERHEAD TRANSMISSION LINE |  | 1.20.2.3 | Completed | No | No | 2019-11-16 09:00 | 2019-12-27 18:00 | 2020-03-10 09:00 | 2020-08-01 18:00 |  |  | 2020-03-11 17:28 | 2020-07-07 17:28 |  |  | 100 | 100 | [15 empty] | 100 | 0.16492 | 16.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4871 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019893
2497 | Task(Task)-->P (Procurement) | ITP APPROVAL | 1.20.2.4 | 1.20.2 | Unscheduled | No | No | 2019-12-28 09:00 | 2020-02-05 18:00 | 2020-07-16 09:00 | 2020-10-31 18:00 |  |  | 2020-07-16 10:54 |  |  |  | 100 | 0 | [15 empty] | 5.0003 | 0.082461 | 8.11 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4872 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019894
2498 | Task(Task)-->P (Procurement) | 33KV OVERHEAD TRANSMISSION LINE |  | 1.20.2.4 | Unscheduled | No | No | 2019-12-28 09:00 | 2020-02-05 18:00 | 2020-07-16 09:00 | 2020-10-31 18:00 |  |  | 2020-07-16 10:54 |  |  |  | 100 | 0 | [15 empty] | 100 | 0.082461 | 8.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4873 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019895
2499 | Task(Task)-->P (Procurement) | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE | 1.20.2.5 | 1.20.2 | Unscheduled | No | No | 2019-12-28 09:00 | 2020-02-25 18:00 | 2020-07-20 09:00 | 2020-11-01 23:59 |  |  | 2020-07-20 10:53 |  |  |  | 100 | 0 | [15 empty] | 15.0009 | 0.24738 | 24.33 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4874 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019896
2500 | Task(Task)-->P (Procurement) | 33KV OVERHEAD TRANSMISSION LINE |  | 1.20.2.5 | Unscheduled | No | No | 2019-12-28 09:00 | 2020-02-25 18:00 | 2020-07-20 09:00 | 2020-11-01 23:59 |  |  | 2020-07-20 10:53 |  |  |  | 100 | 0 | [15 empty] | 100 | 0.24738 | 24.33 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4875 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019897
2501 | Task(Task)-->P (Procurement) | MANUFACTURING & RECEIPT AT SITE (MRN) | 1.20.2.6 | 1.20.2 | Unscheduled | No | No | 2020-02-26 09:00 | 2020-11-13 18:00 | 2020-11-02 09:00 | 2021-07-21 18:00 | [6 empty] | 85.8779 | 0 | [15 empty] | 59.9975 | 0.98943 | 97.31 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4876 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019898
2502 | Task(Task)-->P (Procurement) | 33KV OVERHEAD TRANSMISSION LINE |  | 1.20.2.6 | Unscheduled | No | No | 2020-02-26 09:00 | 2020-11-13 18:00 | 2020-11-02 09:00 | 2021-07-21 18:00 | [6 empty] | 85.8779 | 0 | [15 empty] | 100 | 0.98943 | 97.31 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4877 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019899
2503 | Task(Task)-->C (Construction) | CONSTRUCTION | 1.20.3 | 1.20 | Unscheduled | No | No | 2020-05-10 | 2021-05-18 18:00 | 2020-08-15 09:00 | 2021-12-02 18:00 | [6 empty] | 61.0304 | 0 | [15 empty] | 41.4303 | 1.1793 | 115.98 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4878 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019900
2504 | Task(Task)-->C (Construction) | CIVIL | 1.20.3.1 | 1.20.3 | Unscheduled | No | No | 2020-05-10 | 2021-01-04 18:00 | 2020-08-15 09:00 | 2021-04-15 18:00 | [6 empty] | 76.1763 | 0 | [15 empty] | 80.1173 | 0.94485 | 92.92 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4879 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019901
2505 | Task(Task)-->C (Construction) | AVAILABILITY OF FRONT BY NTPC |  | 1.20.3.1 | Unscheduled | No | No | 2020-05-10 | 2020-05-10 23:59 | 2020-08-15 09:00 | 2020-08-15 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4880 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019902
2506 | Task(Task)-->C (Construction) | GEO TECHNICAL INVESTIGATION WORK |  | 1.20.3.1 | Unscheduled | No | No | 2020-05-11 09:00 | 2020-07-09 18:00 | 2020-08-16 | 2020-10-14 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5275 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019903
2507 | Task(Task)-->C (Construction) | EXCAVATION |  | 1.20.3.1 | Unscheduled | No | No | 2020-06-05 09:00 | 2020-10-09 18:00 | 2020-08-22 09:00 | 2020-12-26 18:00 | [6 empty] | 98.4252 | 0 | [15 empty] | 7.232 | 0.068332 | 6.72 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 25202 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4881 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | Excavation | [21 empty] | 1019904
2508 | Task(Task)-->C (Construction) | PCC |  | 1.20.3.1 | Unscheduled | No | No | 2020-06-15 09:00 | 2020-10-16 18:00 | 2020-09-24 09:00 | 2021-01-25 18:00 | [6 empty] | 92.7419 | 0 | [15 empty] | 2.6797 | 0.025319 | 2.49 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 275 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4882 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | PCC | [21 empty] | 1019905
2509 | Task(Task)-->C (Construction) | MONOPOLE FOUNDATION - RCC (21 FOUNDATIONS) |  | 1.20.3.1 | Unscheduled | No | No | 2020-06-22 09:00 | 2020-11-10 18:00 | 2020-10-01 09:00 | 2021-02-19 18:00 | [6 empty] | 76.0563 | 0 | [15 empty] | 79.2617 | 0.74891 | 73.65 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4883 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019906
2510 | Task(Task)-->C (Construction) | MONOPOLE PEDESTAL |  | 1.20.3.1 | Unscheduled | No | No | 2020-06-29 09:00 | 2020-12-05 18:00 | 2020-10-08 09:00 | 2021-03-16 18:00 | [6 empty] | 63.125 | 0 | [15 empty] | 7.9208 | 0.07484 | 7.36 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4884 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019907
2511 | Task(Task)-->C (Construction) | BACK FILLING |  | 1.20.3.1 | Unscheduled | No | No | 2020-07-29 09:00 | 2021-01-04 18:00 | 2020-11-07 09:00 | 2021-04-15 18:00 | [6 empty] | 44.375 | 0 | [15 empty] | 2.9057 | 0.027455 | 2.7 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 22452 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4885 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019908
2512 | Task(Task)-->C (Construction) | ELECTRICAL & INSTRUMENTATION | 1.20.3.2 | 1.20.3 | Unscheduled | No | No | 2021-01-05 09:00 | 2021-04-18 23:59 | 2021-04-16 09:00 | 2021-11-02 18:00 | [6 empty] | 0 | 0 | [15 empty] | 18.5549 | 0.21882 | 21.52 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4886 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019909
2513 | Task(Task)-->C (Construction) | CABLE TRAY |  | 1.20.3.2 | Unscheduled | No | No | 2021-01-05 09:00 | 2021-01-18 18:00 | 2021-04-16 09:00 | 2021-04-29 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0.41783 | 0.000914 | 0.09 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4887 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019910
2514 | Task(Task)-->C (Construction) | CABLE LAYING |  | 1.20.3.2 | Unscheduled | No | No | 2021-02-04 09:00 | 2021-02-17 18:00 | 2021-09-25 09:00 | 2021-10-08 18:00 | [6 empty] | 0 | 0 | [15 empty] | 4.5961 | 0.010057 | 0.99 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 7000 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4888 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019911
2515 | Task(Task)-->C (Construction) | EARTHING |  | 1.20.3.2 | Unscheduled | No | No | 2021-02-09 09:00 | 2021-02-22 18:00 | 2021-09-25 09:00 | 2021-10-08 18:00 | [6 empty] | 0 | 0 | [15 empty] | 8.3101 | 0.018185 | 1.79 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5251 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019912
2516 | Task(Task)-->C (Construction) | EARTH PIT |  | 1.20.3.2 | Unscheduled | No | No | 2021-02-09 09:00 | 2021-02-22 18:00 | 2021-09-25 09:00 | 2021-10-08 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4889 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019913
2517 | Task(Task)-->C (Construction) | LIGHTING |  | 1.20.3.2 | Unscheduled | No | No | 2021-02-23 09:00 | 2021-03-08 18:00 | 2021-10-09 09:00 | 2021-10-22 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0.7428 | 0.001625 | 0.16 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5402 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019914
2518 | Task(Task)-->C (Construction) | ERECTION OF MONOPOLES |  | 1.20.3.2 | Unscheduled | No | No | 2021-01-05 09:00 | 2021-03-05 18:00 | 2021-07-22 09:00 | 2021-09-19 23:59 | [6 empty] | 0 | 0 | [15 empty] | 59.2386 | 0.12963 | 12.76 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5403 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019915
2519 | Task(Task)-->C (Construction) | STRINGING OF CONDUCTOR |  | 1.20.3.2 | Unscheduled | No | No | 2021-02-04 09:00 | 2021-04-04 23:59 | 2021-08-21 09:00 | 2021-10-19 18:00 | [6 empty] | 0 | 0 | [15 empty] | 26.6945 | 0.058414 | 5.75 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 28000 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5404 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019916
2520 | Task(Task)-->C (Construction) | GANTRY WORK AT SUB-STATION |  | 1.20.3.2 | Unscheduled | No | No | 2021-02-18 09:00 | 2021-04-18 23:59 | 2021-09-04 09:00 | 2021-11-02 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5561 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019917
2521 | Task(Task)-->C (Construction) | TESTING & CHARGING FOR LOAD & TRIAL OPERATION |  | 1.20.3 | Unscheduled | No | No | 2021-04-19 09:00 | 2021-05-18 18:00 | 2021-11-03 09:00 | 2021-12-02 18:00 | [6 empty] | 0 | 0 | [15 empty] | 1.3278 | 0.015659 | 1.54 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5405 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019918
2522 | Task(Task)-->E (Engineering) | UTILITY- VENTILATION & AIR CONDITIONING | 1.21 | 1 | Work In Progress | No | No | 2019-09-27 09:00 | 2021-09-09 18:00 | 2019-09-27 09:00 | 2022-04-01 18:00 |  |  | 2019-09-27 10:57 |  |  |  | 48.9074 | 18.8223 | [15 empty] | 0.92136 | 0.92136 | 90.61 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4890 | 0 | 1 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019919
2523 | Task(Task)-->E (Engineering) | ENGINEERING | 1.21.1 | 1.21 | Unscheduled | No | No | 2020-02-07 18:00 | 2020-06-11 17:40 | 2020-05-16 18:00 | 2020-10-05 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 70.6512 | [15 empty] | 2.3731 | 0.021865 | 2.15 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4891 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019920
2524 | Task(Task)-->E (Engineering) | MECHANICAL | 1.21.1.1 | 1.21.1 | Unscheduled | No | No | 2020-02-07 18:00 | 2020-06-11 17:40 | 2020-05-16 18:00 | 2020-10-05 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 70.6512 | [15 empty] | 100 | 0.021865 | 2.15 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4892 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036132
2525 | Task(Task)-->E (Engineering) | DESIGN BASIS REPORT FOR DRY TYPE PRESSURISATION VENTILATION SYSTEM |  | 1.21.1.1 | Unscheduled | No | No | 2020-02-07 18:00 | 2020-04-13 17:40 | 2020-05-16 18:00 | 2020-07-25 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-VS-DB-6002 |  | 2020-02-13 11:40 | 7012-155-PVM-L-032 |  |  |  | A |  |  |  | 31.1628 | 0.006814 | 0.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 250 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4894 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-07 18:00 | 2020-05-16 18:00 |  | 10 |  |  |  | 2020-03-02 17:40 | 2020-06-06 18:00 |  | 30 |  |  |  | 2020-03-07 17:40 | 2020-06-13 18:00 |  | 35 | 2020-06-25 10:27 |  |  | 2020-03-13 23:59 | 2020-06-20 18:00 |  | 65 | 2020-08-22 12:47 |  |  | 2020-03-20 17:40 | 2020-07-11 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-13 17:40 | 2020-07-25 18:00 |  | 100 | [122 empty] | Ram Prasad Roy |  |  |  |  | U - Water Media & Utility System | [16 empty] | 77 |  |  |  | 101091
2526 | Task(Task)-->E (Engineering) | DESIGN BASIS FOR AIR CONDITIONING SYSTEM |  | 1.21.1.1 | Unscheduled | No | No | 2020-02-21 18:00 | 2020-04-27 17:40 | 2020-05-18 18:00 | 2020-07-27 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-AC-DB-6003 |  | 2020-02-13 11:40 | 7012-155-PVM-L-033 |  |  |  | A |  |  |  | 31.1628 | 0.006814 | 0.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 250 | 0 | 2.15 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4896 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-21 18:00 | 2020-05-18 18:00 |  | 10 |  |  |  | 2020-03-16 17:40 | 2020-06-08 18:00 |  | 30 |  |  |  | 2020-03-21 17:40 | 2020-06-15 18:00 |  | 35 | 2020-07-04 14:25 |  |  | 2020-03-27 23:59 | 2020-06-22 18:00 |  | 65 | 2020-08-22 12:50 |  |  | 2020-04-03 17:40 | 2020-07-13 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-27 17:40 | 2020-07-27 18:00 |  | 100 | [122 empty] | Ram Prasad Roy |  |  |  |  | U - Water Media & Utility System | [16 empty] | 78 |  |  |  | 101092
2527 | Task(Task)-->E (Engineering) | GA, CS, DATA SHEET & CURVE OF SUPPLY & EXHAUST FANS FOR VENTILATION SYSTEM |  | 1.21.1.1 | Unscheduled | No | No | 2020-03-19 18:00 | 2020-05-11 17:40 | 2020-08-20 18:00 | 2020-10-03 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-VS-GA-6201 |  | 2020-02-13 11:40 | 7012-155-PVM-B-152 |  |  |  | A |  |  |  | 25.1163 | 0.005492 | 0.54 | Plan & Actual | Date |  | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4893 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-19 18:00 | 2020-08-20 18:00 |  | 10 |  |  |  | 2020-03-31 17:40 | 2020-09-04 18:00 |  | 30 |  |  |  | 2020-04-06 17:40 | 2020-09-08 18:00 |  | 35 |  |  |  | 2020-04-11 23:59 | 2020-09-12 18:00 |  | 65 | 2020-08-22 12:42 |  |  | 2020-04-17 17:40 | 2020-10-03 18:00 |  | 80 | 2020-09-09 10:31 | [5 empty] | 80 | 2020-09-17 12:06 | [5 empty] | 80 | 2020-09-17 12:06 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-11 17:40 | 2020-10-03 18:00 |  | 100 | [122 empty] | Ram Prasad Roy |  |  |  |  | U - Water Media & Utility System | [16 empty] | 92 |  |  |  | 101106
2528 | Task(Task)-->E (Engineering) | DATA SHEET & GA DRG OF AIR CONDITIONERS |  | 1.21.1.1 | Unscheduled | No | No | 2020-04-15 18:00 | 2020-06-11 17:40 | 2020-08-10 18:00 | 2020-10-05 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-AC-GA-6401 |  | 2020-02-13 11:40 | 7012-155-PVM-B-160 |  |  |  | A |  |  |  | 12.5581 | 0.002746 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4895 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-15 18:00 | 2020-08-10 18:00 |  | 10 |  |  |  | 2020-05-01 17:40 | 2020-08-25 18:00 |  | 30 |  |  |  | 2020-05-07 17:40 | 2020-09-01 18:00 |  | 35 |  |  |  | 2020-05-14 23:59 | 2020-09-08 18:00 |  | 65 | 2020-08-22 12:45 |  |  | 2020-05-20 17:40 | 2020-09-29 18:00 |  | 80 | 2020-09-10 17:23 | [5 empty] | 80 | 2020-09-28 10:18 | [5 empty] | 80 | 2020-09-28 10:18 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-11 17:40 | 2020-09-29 18:00 |  | 100 | [122 empty] | Ram Prasad Roy |  |  |  |  | U - Water Media & Utility System | [16 empty] | 100 |  |  |  | 101114
2529 | Task(Task)-->E (Engineering) | ELECTRICAL | 1.21.1.2 | 1.21.1 | Unscheduled | No | No | [10 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4898 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036133
2530 | Task(Task)-->P (Procurement) | PROCUREMENT | 1.21.2 | 1.21 | Work In Progress | No | No | 2019-09-27 09:00 | 2021-03-15 18:00 | 2019-09-27 09:00 | 2021-05-29 18:00 |  |  | 2019-09-27 10:57 |  |  |  | 54.2671 | 19.9948 | [15 empty] | 85.7506 | 0.79007 | 77.69 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4899 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019923
2531 | Task(Task)-->P (Procurement) | PURCHASE REQUISITION | 1.21.2.1 | 1.21.2 | Completed | No | No | 2019-09-27 09:00 | 2019-09-27 18:00 | 2019-09-27 09:00 | 2019-09-27 18:00 |  |  | 2019-09-27 10:57 | 2019-09-27 10:57 |  |  | 100 | 100 | [15 empty] | 4.9955 | 0.039468 | 3.88 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4900 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019924
2532 | Task(Task)-->P (Procurement) | Ventilation System |  | 1.21.2.1 | Completed | No | No | 2019-09-27 09:00 | 2019-09-27 18:00 | 2019-09-27 09:00 | 2019-09-27 18:00 |  |  | 2019-09-27 10:57 | 2019-09-27 10:57 |  |  | 100 | 100 | [15 empty] | 19.0231 | 0.007508 | 0.74 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4901 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019925
2533 | Task(Task)-->P (Procurement) | AC System |  | 1.21.2.1 | Completed | No | No | 2019-09-27 09:00 | 2019-09-27 18:00 | 2019-09-27 09:00 | 2019-09-27 18:00 |  |  | 2019-09-27 10:57 | 2019-09-27 10:57 |  |  | 100 | 100 | [15 empty] | 80.9769 | 0.03196 | 3.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4902 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019926
2534 | Task(Task)-->P (Procurement) | TECHNICAL CLEARANCE | 1.21.2.2 | 1.21.2 | Completed | No | No | 2019-09-28 09:00 | 2020-04-04 18:00 | 2019-09-27 09:00 | 2020-04-10 18:00 |  |  | 2020-04-09 10:57 | 2020-04-10 10:57 |  |  | 100 | 100 | [15 empty] | 4.9955 | 0.039468 | 3.88 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4903 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019927
2535 | Task(Task)-->P (Procurement) | Ventilation System |  | 1.21.2.2 | Completed | No | No | 2019-09-28 09:00 | 2020-02-26 18:00 | 2019-09-27 09:00 | 2020-04-10 18:00 |  |  | 2020-04-10 10:57 | 2020-04-10 10:57 |  |  | 100 | 100 | [15 empty] | 19.0231 | 0.007508 | 0.74 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4904 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019928
2536 | Task(Task)-->P (Procurement) | AC System |  | 1.21.2.2 | Completed | No | No | 2019-09-28 09:00 | 2020-04-04 18:00 | 2019-09-27 09:00 | 2020-04-09 18:00 |  |  | 2020-04-09 10:57 | 2020-04-09 10:57 |  |  | 100 | 100 | [15 empty] | 80.9769 | 0.03196 | 3.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4905 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019929
2537 | Task(Task)-->P (Procurement) | ORDERING | 1.21.2.3 | 1.21.2 | Completed | No | No | 2020-02-27 09:00 | 2020-04-29 18:00 | 2020-04-09 09:00 | 2020-06-11 18:00 |  |  | 2020-06-11 10:57 | 2020-06-11 10:57 |  |  | 100 | 100 | [15 empty] | 10.0039 | 0.079038 | 7.77 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4906 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019930
2538 | Task(Task)-->P (Procurement) | Ventilation System |  | 1.21.2.3 | Completed | No | No | 2020-02-27 09:00 | 2020-03-27 18:00 | 2020-04-10 09:00 | 2020-06-11 18:00 |  |  | 2020-06-11 10:57 | 2020-06-11 10:57 |  |  | 100 | 100 | [15 empty] | 18.9189 | 0.014953 | 1.47 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4907 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019931
2539 | Task(Task)-->P (Procurement) | AC System |  | 1.21.2.3 | Completed | No | No | 2020-04-05 | 2020-04-29 18:00 | 2020-04-09 09:00 | 2020-06-11 18:00 |  |  | 2020-06-11 10:57 | 2020-06-11 10:57 |  |  | 100 | 100 | [15 empty] | 81.0811 | 0.064085 | 6.3 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4908 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019932
2540 | Task(Task)-->P (Procurement) | ITP APPROVAL | 1.21.2.4 | 1.21.2 | Unscheduled | No | No | 2020-03-28 09:00 | 2020-06-28 23:59 | 2020-06-11 09:00 | 2020-10-31 18:00 | [6 empty] | 100 | 0 | [15 empty] | 4.9955 | 0.039468 | 3.88 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4909 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019933
2541 | Task(Task)-->P (Procurement) | Ventilation System |  | 1.21.2.4 | Unscheduled | No | No | 2020-03-28 09:00 | 2020-05-26 18:00 | 2020-06-11 09:00 | 2020-10-31 18:00 | [6 empty] | 100 | 0 | [15 empty] | 19.0231 | 0.007508 | 0.74 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4910 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019934
2542 | Task(Task)-->P (Procurement) | AC System |  | 1.21.2.4 | Unscheduled | No | No | 2020-04-30 09:00 | 2020-06-28 23:59 | 2020-06-11 09:00 | 2020-10-31 18:00 | [6 empty] | 100 | 0 | [15 empty] | 80.9769 | 0.03196 | 3.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4911 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019935
2543 | Task(Task)-->P (Procurement) | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE | 1.21.2.5 | 1.21.2 | Unscheduled | No | No | 2020-03-28 09:00 | 2020-09-26 18:00 | 2020-06-11 09:00 | 2020-10-16 18:00 | [6 empty] | 100 | 0 | [15 empty] | 14.9994 | 0.11851 | 11.65 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4912 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019936
2544 | Task(Task)-->P (Procurement) | Ventilation System |  | 1.21.2.5 | Unscheduled | No | No | 2020-03-28 09:00 | 2020-08-24 18:00 | 2020-06-11 09:00 | 2020-10-16 18:00 | [6 empty] | 100 | 0 | [15 empty] | 18.9537 | 0.022461 | 2.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4913 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019937
2545 | Task(Task)-->P (Procurement) | AC System |  | 1.21.2.5 | Unscheduled | No | No | 2020-04-30 09:00 | 2020-09-26 18:00 | 2020-06-11 09:00 | 2020-10-16 18:00 | [6 empty] | 100 | 0 | [15 empty] | 81.0463 | 0.096045 | 9.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4914 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019938
2546 | Task(Task)-->P (Procurement) | MANUFACTURING & RECEIPT AT SITE (MRN) | 1.21.2.6 | 1.21.2 | Unscheduled | No | No | 2020-08-18 09:00 | 2021-03-15 18:00 | 2020-11-01 | 2021-05-29 18:00 | [6 empty] | 23.7917 | 0 | [15 empty] | 60.0103 | 0.47413 | 46.61 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4915 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019939
2547 | Task(Task)-->P (Procurement) | Ventilation System |  | 1.21.2.6 | Unscheduled | No | No | 2020-08-25 09:00 | 2021-03-15 18:00 | 2020-11-01 | 2021-05-22 18:00 | [6 empty] | 21.6749 | 0 | [15 empty] | 18.923 | 0.089719 | 8.82 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4916 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019940
2548 | Task(Task)-->P (Procurement) | AC System |  | 1.21.2.6 | Unscheduled | No | No | 2020-08-18 09:00 | 2021-03-15 18:00 | 2020-11-01 | 2021-05-29 18:00 | [6 empty] | 24.2857 | 0 | [15 empty] | 81.077 | 0.38441 | 37.79 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4917 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019941
2549 | Task(Task)-->C (Construction) | CONSTRUCTION | 1.21.3 | 1.21 | Unscheduled | No | No | 2021-03-16 09:00 | 2021-09-09 18:00 | 2021-05-23 | 2022-04-01 18:00 | [6 empty] | 0 | 0 | [15 empty] | 11.8764 | 0.10942 | 10.76 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4918 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019942
2550 | Task(Task)-->C (Construction) | MECHANICAL | 1.21.3.1 | 1.21.3 | Unscheduled | No | No | 2021-03-16 09:00 | 2021-06-30 18:00 | 2021-05-23 | 2021-11-27 18:00 | [6 empty] | 0 | 0 | [15 empty] | 57.1031 | 0.062485 | 6.15 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4924 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019943
2551 | Task(Task)-->C (Construction) | ERECTION OF VENTILATION DUCT FOR SS-1 |  | 1.21.3.1 | Unscheduled | No | No | 2021-04-17 09:00 | 2021-06-15 18:00 | 2021-06-26 09:00 | 2021-08-24 18:00 | [6 empty] | 0 | 0 | [15 empty] | 18.9233 | 0.011824 | 1.16 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5270 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019944
2552 | Task(Task)-->C (Construction) | ERECTION OF FANS (SUPPLY) FOR SS-1 |  | 1.21.3.1 | Unscheduled | No | No | 2021-03-16 09:00 | 2021-03-29 18:00 | 2021-05-23 | 2021-06-05 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0.97879 | 0.000612 | 0.06 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5440 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019945
2553 | Task(Task)-->C (Construction) | ERECTION OF FANS (EXHAUST) FOR SS-1 |  | 1.21.3.1 | Unscheduled | No | No | 2021-04-17 09:00 | 2021-04-30 18:00 | 2021-06-26 09:00 | 2021-07-09 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0.16313 | 0.000102 | 0.01 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5441 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019946
2554 | Task(Task)-->C (Construction) | ERECTION OF VENTILATION DUCT FOR SS-2 |  | 1.21.3.1 | Unscheduled | No | No | 2021-04-22 09:00 | 2021-06-05 18:00 | 2021-10-14 09:00 | 2021-11-27 18:00 | [6 empty] | 0 | 0 | [15 empty] | 18.9233 | 0.011824 | 1.16 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5562 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019947
2555 | Task(Task)-->C (Construction) | ERECTION OF FANS (SUPPLY) FOR SS-2 |  | 1.21.3.1 | Unscheduled | No | No | 2021-03-16 09:00 | 2021-03-29 18:00 | 2021-07-04 | 2021-07-17 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0.97879 | 0.000612 | 0.06 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5563 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019948
2556 | Task(Task)-->C (Construction) | ERECTION OF FANS (EXHAUST) FOR SS-2 |  | 1.21.3.1 | Unscheduled | No | No | 2021-04-22 09:00 | 2021-05-01 18:00 | 2021-10-14 09:00 | 2021-10-23 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0.16313 | 0.000102 | 0.01 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5564 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019949
2557 | Task(Task)-->C (Construction) | ERECTION OF VENTILATION DUCT FOR SS-3 |  | 1.21.3.1 | Unscheduled | No | No | 2021-05-17 09:00 | 2021-06-30 18:00 | 2021-10-14 09:00 | 2021-11-27 18:00 | [6 empty] | 0 | 0 | [15 empty] | 18.9233 | 0.011824 | 1.16 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5565 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019950
2558 | Task(Task)-->C (Construction) | ERECTION OF FANS (SUPPLY) FOR SS-3 |  | 1.21.3.1 | Unscheduled | No | No | 2021-03-16 09:00 | 2021-03-29 18:00 | 2021-07-04 | 2021-07-17 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0.97879 | 0.000612 | 0.06 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5566 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019951
2559 | Task(Task)-->C (Construction) | ERECTION OF FANS (EXHAUST) FOR SS-3 |  | 1.21.3.1 | Unscheduled | No | No | 2021-05-17 09:00 | 2021-05-26 18:00 | 2021-10-14 09:00 | 2021-10-23 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0.16313 | 0.000102 | 0.01 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5567 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019952
2560 | Task(Task)-->C (Construction) | INSTALLATION OF AC FOR SS-1 |  | 1.21.3.1 | Unscheduled | No | No | 2021-03-16 09:00 | 2021-03-30 18:00 | 2021-05-30 | 2021-06-13 23:59 | [6 empty] | 0 | 0 | [15 empty] | 9.1354 | 0.005708 | 0.56 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5442 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | Installation | [21 empty] | 1019953
2561 | Task(Task)-->C (Construction) | INSTALLATION OF AC FOR SS-2 |  | 1.21.3.1 | Unscheduled | No | No | 2021-03-16 09:00 | 2021-04-01 18:00 | 2021-07-04 | 2021-07-20 18:00 | [6 empty] | 0 | 0 | [15 empty] | 18.4339 | 0.011518 | 1.13 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5443 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | Installation | [21 empty] | 1019954
2562 | Task(Task)-->C (Construction) | INSTALATION OF AC FOR SS-3 |  | 1.21.3.1 | Unscheduled | No | No | 2021-03-16 09:00 | 2021-03-30 18:00 | 2021-07-04 | 2021-07-18 23:59 | [6 empty] | 0 | 0 | [15 empty] | 12.2349 | 0.007645 | 0.75 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5444 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019955
2563 | Task(Task)-->C (Construction) | ELECTRICAL WORKS | 1.21.3.2 | 1.21.3 | Unscheduled | No | No | 2021-05-01 09:00 | 2021-06-25 18:00 | 2021-07-10 09:00 | 2021-11-22 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5570 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019956
2564 | Task(Task)-->C (Construction) | ELECTRICAL & INSTRUMENTATION FOR SS-1 |  | 1.21.3.2 | Unscheduled | No | No | 2021-05-01 09:00 | 2021-05-30 23:59 | 2021-07-10 09:00 | 2021-08-08 23:59 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5271 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019957
2565 | Task(Task)-->C (Construction) | ELECTRICAL & INSTRUMENTATION FOR SS-2 |  | 1.21.3.2 | Unscheduled | No | No | 2021-05-02 | 2021-05-31 18:00 | 2021-10-24 | 2021-11-22 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5568 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019958
2566 | Task(Task)-->C (Construction) | ELECTRICAL & INSTRUMENTATION FOR SS-2 |  | 1.21.3.2 | Unscheduled | No | No | 2021-05-27 09:00 | 2021-06-25 18:00 | 2021-10-24 | 2021-11-22 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5569 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019959
2567 | Task(Task)-->C (Construction) | NO LOAD COMMISSIONING & SYSTEM READYNESS FOR TRIAL OPERATION | 1.21.3.3 | 1.21.3 | Unscheduled | No | No | 2021-08-22 | 2021-09-09 18:00 | 2022-02-17 09:00 | 2022-04-01 18:00 | [6 empty] | 0 | 0 | [15 empty] | 42.8969 | 0.04694 | 4.62 |  | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5272 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019960
2568 | Task(Task)-->C (Construction) | SS-1 & CONTROL ROOM |  | 1.21.3.3 | Unscheduled | No | No | 2021-08-22 | 2021-09-04 18:00 | 2022-03-14 09:00 | 2022-03-27 23:59 | [6 empty] | 0 | 0 | [15 empty] | 33.3333 | 0.015647 | 1.54 | Plan & Actual | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5572 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019961
2569 | Task(Task)-->C (Construction) | SS-2 |  | 1.21.3.3 | Unscheduled | No | No | 2021-08-27 09:00 | 2021-09-09 18:00 | 2022-03-19 09:00 | 2022-04-01 18:00 | [6 empty] | 0 | 0 | [15 empty] | 33.3333 | 0.015647 | 1.54 | Plan & Actual | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5573 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019962
2570 | Task(Task)-->C (Construction) | SS-3 |  | 1.21.3.3 | Unscheduled | No | No | 2021-08-22 | 2021-09-04 18:00 | 2022-02-17 09:00 | 2022-03-02 18:00 | [6 empty] | 0 | 0 | [15 empty] | 33.3333 | 0.015647 | 1.54 | Plan & Actual | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5571 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019963
2571 | Task(Task)-->E (Engineering) | UTILITY- PWDS, SW, DW, MVWS & DS | 1.22 | 1 | Work In Progress | No | No | 2019-09-27 09:00 | 2021-07-14 18:00 | 2019-09-27 09:00 | 2021-11-12 18:00 |  |  | 2019-09-27 14:27 |  |  |  | 53.575 | 29.97 | [15 empty] | 0.35915 | 0.35915 | 35.32 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4927 | 0 | 1 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019964
2572 | Task(Task)-->E (Engineering) | ENGINEERING | 1.22.1 | 1.22 | Unscheduled | No | No | 2019-12-16 18:00 | 2020-05-12 17:40 | 2020-05-10 23:59 | 2020-10-15 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 62.1131 | [15 empty] | 7.5573 | 0.027142 | 2.67 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4928 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019965
2573 | Task(Task)-->E (Engineering) | MECHANICAL | 1.22.1.1 | 1.22.1 | Unscheduled | No | No | 2019-12-16 18:00 | 2020-05-12 17:40 | 2020-05-10 23:59 | 2020-10-15 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 62.1131 | [15 empty] | 100 | 0.027142 | 2.67 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4929 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036134
2574 | Task(Task)-->E (Engineering) | DBR & SCHEMATIC DIAGRAM FOR DS,SW & PW SYSTEM |  | 1.22.1.1 | Unscheduled | No | No | 2019-12-21 18:00 | 2020-02-24 17:40 | 2020-05-10 23:59 | 2020-07-19 23:59 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-DS-DB-6001 |  | 2020-02-13 11:40 | 7012-155-PVM-L-031 |  |  |  | A |  |  |  | 25.283 | 0.006862 | 0.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 250 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4935 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-12-21 18:00 | 2020-05-10 23:59 |  | 10 |  |  |  | 2020-01-14 17:40 | 2020-05-31 23:59 |  | 30 |  |  |  | 2020-01-20 17:40 | 2020-06-07 23:59 |  | 35 |  |  |  | 2020-01-25 23:59 | 2020-06-14 23:59 |  | 65 | 2020-05-30 23:31 |  |  | 2020-01-31 17:40 | 2020-07-05 23:59 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-02-24 17:40 | 2020-07-19 23:59 |  | 100 | [122 empty] | Ram Prasad Roy |  |  |  |  | U - Water Media & Utility System | [16 empty] | 76 |  |  |  | 101090
2575 | Task(Task)-->E (Engineering) | GENERAL LAYOUT PLAN SHOWING DS,SW & PW SYSTEM |  | 1.22.1.1 | Unscheduled | No | No | 2019-12-16 18:00 | 2020-02-17 17:40 | 2020-05-25 18:00 | 2020-10-15 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-DS-GA-6006 |  | 2020-02-13 11:40 | 7012-155-PVM-P-036 |  |  |  | A |  |  |  | 15.0943 | 0.004097 | 0.4 | Plan & Actual | Date |  | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4936 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-12-16 18:00 | 2020-05-25 18:00 |  | 10 |  |  |  | 2020-01-08 17:40 | 2020-06-15 18:00 |  | 30 |  |  |  | 2020-01-14 17:40 | 2020-06-22 18:00 |  | 35 |  |  |  | 2020-01-20 23:59 | 2020-06-29 18:00 |  | 65 | 2020-08-22 12:40 |  |  | 2020-01-25 17:40 | 2020-07-20 18:00 |  | 80 | 2020-09-10 17:18 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-02-17 17:40 | 2020-07-20 18:00 |  | 100 | [122 empty] | Ram Prasad Roy |  |  |  |  | U - Water Media & Utility System | [16 empty] | 81 |  |  |  | 101095
2576 | Task(Task)-->E (Engineering) | GA, CS, DATA SHEET & CURVE OF PUMPS FOR PLAIN WATER DS, SW & PW SYSTEM |  | 1.22.1.1 | Unscheduled | No | No | 2020-01-24 18:00 | 2020-03-16 17:40 | 2020-07-20 18:00 | 2020-10-15 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-DS-GA-6100 |  | 2020-02-13 11:40 | 7012-155-PVM-B-146 |  |  |  | A |  |  |  | 20.3774 | 0.005531 | 0.54 | Plan & Actual | Date |  | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4930 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-24 18:00 | 2020-07-20 18:00 |  | 10 |  |  |  | 2020-02-03 17:40 | 2020-08-04 18:00 |  | 30 |  |  |  | 2020-02-10 17:40 | 2020-08-08 18:00 |  | 35 |  |  |  | 2020-02-15 23:59 | 2020-08-11 18:00 |  | 65 | 2020-09-12 14:30 |  |  | 2020-02-21 17:40 | 2020-09-01 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-16 17:40 | 2020-09-01 18:00 |  | 100 | [122 empty] | Ram Prasad Roy |  |  |  |  | U - Water Media & Utility System | [16 empty] | 86 |  |  |  | 101100
2577 | Task(Task)-->E (Engineering) | DATA SHEET & GA DRG OF MANUAL VALVES FOR PLAIN WATER DS, SW & PW SYSTEM |  | 1.22.1.1 | Unscheduled | No | No | 2020-02-05 17:40 | 2020-03-18 17:40 | 2020-08-05 18:00 | 2020-10-15 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-DS-GA-6101 |  | 2020-02-13 11:40 | 7012-155-PVM-B-147 |  |  |  | A |  |  |  | 10.1887 | 0.002765 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4931 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-07 18:00 | 2020-08-05 18:00 |  | 10 |  |  |  | 2020-02-05 17:40 | 2020-08-12 18:00 |  | 30 |  |  |  | 2020-02-12 17:40 | 2020-08-16 23:59 |  | 35 |  |  |  | 2020-02-18 23:59 | 2020-08-16 23:59 |  | 65 | 2020-09-12 14:30 |  |  | 2020-02-25 17:40 | 2020-09-06 23:59 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-18 17:40 | 2020-09-06 23:59 |  | 100 | [122 empty] | Ram Prasad Roy |  |  |  |  | U - Water Media & Utility System | [16 empty] | 87 |  |  |  | 101101
2578 | Task(Task)-->E (Engineering) | DATA SHEET & GA DRG OF SPRAY NOZZLES & SPRAY HEADERS FOR PLAIN WATER DS SYSTEM |  | 1.22.1.1 | Unscheduled | No | No | 2020-02-07 17:40 | 2020-03-20 17:40 | 2020-07-15 18:00 | 2020-10-15 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-DS-GA-6102 |  | 2020-02-13 11:40 | 7012-155-PVM-B-148 |  |  |  | A |  |  |  | 4.9057 | 0.001331 | 0.13 | Plan & Actual | Date |  | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4932 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-09 23:59 | 2020-07-15 18:00 |  | 10 |  |  |  | 2020-02-07 17:40 | 2020-07-22 18:00 |  | 30 |  |  |  | 2020-02-14 17:40 | 2020-07-26 23:59 |  | 35 |  |  |  | 2020-02-20 23:59 | 2020-07-26 23:59 |  | 65 | 2020-09-16 10:02 |  |  | 2020-02-27 17:40 | 2020-08-16 23:59 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-20 17:40 | 2020-08-16 23:59 |  | 100 | [122 empty] | Ram Prasad Roy |  |  |  |  | U - Water Media & Utility System | [16 empty] | 88 |  |  |  | 101102
2579 | Task(Task)-->E (Engineering) | DATA SHEET OF PIPES & PIPE FITTINGS FOR PLAIN WATER DS, SW & PW SYSTEM |  | 1.22.1.1 | Unscheduled | No | No | 2020-02-11 17:40 | 2020-03-21 17:40 | 2020-08-20 18:00 | 2020-09-21 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-DS-GA-6103 |  | 2020-02-13 11:40 | 7012-155-PVM-Y-149 |  |  |  | A |  |  |  | 4.9057 | 0.001331 | 0.13 | Plan & Actual | Date |  | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4937 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-11 18:00 | 2020-08-20 18:00 |  | 10 |  |  |  | 2020-02-11 17:40 | 2020-08-27 18:00 |  | 30 |  |  |  | 2020-02-17 17:40 | 2020-08-31 18:00 |  | 35 |  |  |  | 2020-02-22 23:59 | 2020-08-31 18:00 |  | 65 | 2020-08-22 12:40 |  |  | 2020-02-28 17:40 | 2020-09-21 18:00 |  | 80 | 2020-09-10 17:21 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-21 17:40 | 2020-09-21 18:00 |  | 100 | [122 empty] | Ram Prasad Roy |  |  |  |  | U - Water Media & Utility System | [16 empty] | 89 |  |  |  | 101103
2580 | Task(Task)-->E (Engineering) | DATA SHEET & GA DRG OF DUPLEX STRAINERS FOR PLAIN WATER DS, SW & PW SYSTEM |  | 1.22.1.1 | Unscheduled | No | No | 2020-02-12 17:40 | 2020-03-24 17:40 | 2020-08-12 18:00 | 2020-10-15 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-DS-GA-6104 |  | 2020-02-13 11:40 | 7012-155-PVM-B-150 |  |  |  | A |  |  |  | 10.1887 | 0.002765 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4933 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-14 18:00 | 2020-08-12 18:00 |  | 10 |  |  |  | 2020-02-12 17:40 | 2020-08-19 18:00 |  | 30 |  |  |  | 2020-02-18 17:40 | 2020-08-23 23:59 |  | 35 |  |  |  | 2020-02-25 23:59 | 2020-08-23 23:59 |  | 65 | 2020-09-17 12:25 |  |  | 2020-03-02 17:40 | 2020-09-13 23:59 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-24 17:40 | 2020-09-13 23:59 |  | 100 | [122 empty] | Ram Prasad Roy |  |  |  |  | U - Water Media & Utility System | [16 empty] | 90 |  |  |  | 101104
2581 | Task(Task)-->E (Engineering) | DATA SHEET & GA DRG OF SOLENOID BOX ASSEMBLY FOR PLAIN WATER DS SYSTEM |  | 1.22.1.1 | Unscheduled | No | No | 2020-02-12 18:00 | 2020-03-26 17:40 | 2020-07-15 18:00 | 2020-08-21 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-DS-GA-6105 |  | 2020-02-13 11:40 | 7012-155-PVM-B-151 |  |  |  | A |  |  |  | 4.9057 | 0.001331 | 0.13 | Plan & Actual | Date |  | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4934 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-12 18:00 | 2020-07-15 18:00 |  | 10 |  |  |  | 2020-02-14 17:40 | 2020-07-22 18:00 |  | 30 |  |  |  | 2020-02-20 17:40 | 2020-07-26 23:59 |  | 35 |  |  |  | 2020-02-27 23:59 | 2020-07-30 18:00 |  | 65 |  |  |  | 2020-03-04 17:40 | 2020-08-20 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-26 17:40 | 2020-08-20 18:00 |  | 100 | [122 empty] | Ram Prasad Roy |  |  |  |  | U - Water Media & Utility System | [16 empty] | 91 |  |  |  | 101105
2582 | Task(Task)-->E (Engineering) | GA, DATA SHEET, TERMINAL BOX ARRANGEMET & CHARACTERISTICS CURVES OF LT MOTOR (UTILITY SYSTEM) |  | 1.22.1.1 | Unscheduled | No | No | 2020-03-31 17:40 | 2020-05-12 17:40 | 2020-05-31 23:59 | 2020-10-15 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-163 |  | 2020-02-13 11:46 | 7012-155-PVE-W-108 |  |  |  | A |  |  |  | 4.1509 | 0.001127 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4938 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-02 18:00 | 2020-05-31 23:59 |  | 10 |  |  |  | 2020-03-31 17:40 | 2020-06-07 23:59 |  | 30 |  |  |  | 2020-04-06 17:40 | 2020-06-11 18:00 |  | 35 |  |  |  | 2020-04-13 23:59 | 2020-06-11 18:00 |  | 65 |  |  |  | 2020-04-18 17:40 | 2020-07-02 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-12 17:40 | 2020-07-02 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 343 |  |  |  | 101354
2583 | Task(Task)-->E (Engineering) | CIVIL | 1.22.1.2 | 1.22.1 | Unscheduled | No | No | [10 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4939 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036135
2584 | Task(Task)-->E (Engineering) | ELECTRICAL | 1.22.1.3 | 1.22.1 | Unscheduled | No | No | [10 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4940 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036136
2585 | Task(Task)-->P (Procurement) | PROCUREMENT | 1.22.2 | 1.22 | Work In Progress | No | No | 2019-09-27 09:00 | 2021-03-15 18:00 | 2019-09-27 09:00 | 2021-06-08 18:00 |  |  | 2019-09-27 14:27 |  |  |  | 63.5576 | 34.91 | [15 empty] | 72.4031 | 0.26004 | 25.58 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4941 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019969
2586 | Task(Task)-->P (Procurement) | PURCHASE REQUISITION | 1.22.2.1 | 1.22.2 | Work In Progress | No | No | 2019-09-27 09:00 | 2020-03-20 18:00 | 2019-09-27 09:00 | 2020-04-14 18:00 |  |  | 2019-09-27 14:27 |  |  |  | 100 | 99.2162 | [15 empty] | 5.0039 | 0.013012 | 1.28 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4942 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019970
2587 | Task(Task)-->P (Procurement) | DS System |  | 1.22.2.1 | Completed | No | No | 2019-09-27 09:00 | 2019-09-27 18:00 | 2019-09-27 09:00 | 2019-09-27 18:00 |  |  | 2019-09-27 14:27 | 2019-09-27 14:27 |  |  | 100 | 100 | [15 empty] | 93.75 | 0.012199 | 1.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4943 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019971
2588 | Task(Task)-->P (Procurement) | LPBS |  | 1.22.2.1 | Unscheduled | No | No | 2020-03-20 09:00 | 2020-03-20 18:00 | 2020-04-14 09:00 | 2020-04-14 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.78125 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4944 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019972
2589 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR UTILITY SYSTEM |  | 1.22.2.1 | Completed | No | No | 2019-12-16 09:00 | 2019-12-16 18:00 | 2020-01-13 09:00 | 2020-01-13 18:00 |  |  | 2020-01-13 10:57 | 2020-01-13 10:57 |  |  | 100 | 100 | [15 empty] | 5.4688 | 0.000712 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4945 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019973
2590 | Task(Task)-->P (Procurement) | TECHNICAL CLEARANCE | 1.22.2.2 | 1.22.2 | Work In Progress | No | No | 2019-09-28 09:00 | 2020-04-04 18:00 | 2019-09-27 09:00 | 2020-06-12 18:00 |  |  | 2019-09-28 14:28 |  |  |  | 100 | 99.2162 | [15 empty] | 5.0039 | 0.013012 | 1.28 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4946 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019974
2591 | Task(Task)-->P (Procurement) | DS System |  | 1.22.2.2 | Completed | No | No | 2019-09-28 09:00 | 2020-01-13 18:00 | 2019-09-27 09:00 | 2020-02-19 18:00 |  |  | 2019-09-28 14:28 | 2020-02-19 14:28 |  |  | 100 | 100 | [15 empty] | 93.75 | 0.012199 | 1.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4947 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019975
2592 | Task(Task)-->P (Procurement) | LPBS |  | 1.22.2.2 | Unscheduled | No | No | 2020-03-21 09:00 | 2020-04-04 18:00 | 2020-04-14 09:00 | 2020-06-12 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.78125 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4948 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019976
2593 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR UTILITY SYSTEM |  | 1.22.2.2 | Completed | No | No | 2019-12-17 09:00 | 2019-12-31 18:00 | 2020-01-13 09:00 | 2020-04-11 18:00 |  |  | 2020-04-11 10:57 | 2020-04-11 10:57 |  |  | 100 | 100 | [15 empty] | 5.4688 | 0.000712 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4949 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019977
2594 | Task(Task)-->P (Procurement) | ORDERING | 1.22.2.3 | 1.22.2 | Work In Progress | No | No | 2020-01-01 09:00 | 2020-04-20 18:00 | 2020-02-19 09:00 | 2020-08-19 18:00 |  |  | 2020-02-20 14:29 |  |  |  | 100 | 100 | [15 empty] | 9.9296 | 0.025821 | 2.54 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4950 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019978
2595 | Task(Task)-->P (Procurement) | DS System |  | 1.22.2.3 | Completed | No | No | 2020-01-14 09:00 | 2020-02-12 18:00 | 2020-02-19 09:00 | 2020-04-28 18:00 |  |  | 2020-02-20 14:29 | 2020-04-28 14:29 |  |  | 100 | 100 | [15 empty] | 94.4664 | 0.024392 | 2.39 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4951 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019979
2596 | Task(Task)-->P (Procurement) | LPBS |  | 1.22.2.3 | Unscheduled | No | No | 2020-04-05 | 2020-04-20 18:00 | 2020-06-12 09:00 | 2020-08-19 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4952 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019980
2597 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR UTILITY SYSTEM |  | 1.22.2.3 | Completed | No | No | 2020-01-01 09:00 | 2020-01-16 18:00 | 2020-04-11 09:00 | 2020-07-20 18:00 |  |  | 2020-04-12 15:47 | 2020-06-20 15:47 |  |  | 100 | 100 | [15 empty] | 5.5336 | 0.001429 | 0.14 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4953 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019981
2598 | Task(Task)-->P (Procurement) | ITP APPROVAL | 1.22.2.4 | 1.22.2 | Work In Progress | No | No | 2020-01-17 09:00 | 2020-05-30 18:00 | 2020-04-28 09:00 | 2020-10-15 18:00 |  |  | 2020-07-29 15:06 |  |  |  | 100 | 0.78383 | [15 empty] | 5.0039 | 0.013012 | 1.28 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4954 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019982
2599 | Task(Task)-->P (Procurement) | DS System |  | 1.22.2.4 | Unscheduled | No | No | 2020-02-13 09:00 | 2020-03-23 18:00 | 2020-04-28 09:00 | 2020-10-15 18:00 | [6 empty] | 100 | 0 | [15 empty] | 93.75 | 0.012199 | 1.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4955 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019983
2600 | Task(Task)-->P (Procurement) | LPBS |  | 1.22.2.4 | Completed | No | No | 2020-04-21 09:00 | 2020-05-30 18:00 | 2020-07-29 09:00 | 2020-08-21 18:00 |  |  | 2020-07-29 15:06 | 2020-08-22 12:55 |  |  | 100 | 100 | [15 empty] | 0.78125 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4956 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019984
2601 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR UTILITY SYSTEM |  | 1.22.2.4 | Unscheduled | No | No | 2020-01-17 09:00 | 2020-02-25 18:00 | 2020-09-08 09:00 | 2020-10-11 23:59 | [6 empty] | 100 | 0 | [15 empty] | 5.4688 | 0.000712 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4957 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019985
2602 | Task(Task)-->P (Procurement) | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE | 1.22.2.5 | 1.22.2 | Completed | No | No | 2020-01-17 09:00 | 2020-07-11 18:00 | 2020-04-28 09:00 | 2020-09-29 18:00 |  |  | 2020-04-29 14:33 | 2020-09-29 14:41 |  |  | 100 | 100 | [15 empty] | 15.0117 | 0.039036 | 3.84 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4958 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019986
2603 | Task(Task)-->P (Procurement) | DS System |  | 1.22.2.5 | Completed | No | No | 2020-02-13 09:00 | 2020-07-11 18:00 | 2020-04-28 09:00 | 2020-06-25 18:00 |  |  | 2020-04-29 14:33 | 2020-06-25 14:33 |  |  | 100 | 100 | [15 empty] | 93.7337 | 0.03659 | 3.59 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4959 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019987
2604 | Task(Task)-->P (Procurement) | LPBS |  | 1.22.2.5 | Completed | No | No | 2020-04-21 09:00 | 2020-06-04 18:00 | 2020-07-25 09:00 | 2020-08-22 18:00 |  |  | 2020-07-24 18:39 | 2020-08-22 12:59 |  |  | 100 | 100 | [15 empty] | 0.78329 | 0.000306 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4960 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019988
2605 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR UTILITY SYSTEM |  | 1.22.2.5 | Completed | No | No | 2020-01-17 09:00 | 2020-03-01 23:59 | 2020-07-07 09:00 | 2020-09-29 18:00 |  |  | 2020-07-07 10:15 | 2020-09-29 14:41 |  |  | 100 | 100 | [15 empty] | 5.483 | 0.00214 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4961 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019989
2606 | Task(Task)-->P (Procurement) | MANUFACTURING & RECEIPT AT SITE (MRN) | 1.22.2.6 | 1.22.2 | Unscheduled | No | No | 2020-03-02 09:00 | 2021-03-15 18:00 | 2020-06-25 09:00 | 2021-06-08 18:00 |  |  | 2020-08-22 13:02 |  |  |  | 39.31 | 0 | [15 empty] | 60.0469 | 0.15614 | 15.36 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4962 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019990
2607 | Task(Task)-->P (Procurement) | DS System |  | 1.22.2.6 | Unscheduled | No | No | 2020-07-12 | 2021-03-15 18:00 | 2020-06-25 09:00 | 2021-01-31 23:59 | [6 empty] | 35.6275 | 0 | [15 empty] | 93.5547 | 0.14608 | 14.37 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4963 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019991
2608 | Task(Task)-->P (Procurement) | LPBS |  | 1.22.2.6 | Unscheduled | No | No | 2020-06-05 09:00 | 2020-09-16 18:00 | 2020-08-23 | 2020-12-04 18:00 |  |  | 2020-08-22 13:02 |  |  |  | 100 | 0 | [15 empty] | 0.84635 | 0.001322 | 0.13 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4964 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019992
2609 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR UTILITY SYSTEM |  | 1.22.2.6 | Unscheduled | No | No | 2020-03-02 09:00 | 2020-10-27 18:00 | 2020-10-12 09:00 | 2021-06-08 18:00 |  |  | 2020-09-29 16:43 |  |  |  | 91.6667 | 0 | [15 empty] | 5.599 | 0.008742 | 0.86 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4965 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019993
2610 | Task(Task)-->C (Construction) | CONSTRUCTION | 1.22.3 | 1.22 | Unscheduled | No | No | 2021-04-02 09:00 | 2021-07-14 18:00 | 2021-08-01 | 2021-11-12 18:00 | [6 empty] | 0 | 0 | [15 empty] | 20.0396 | 0.071972 | 7.08 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4966 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019994
2611 | Task(Task)-->C (Construction) | INSTALLATION OF PIPING & FITTINGS |  | 1.22.3 | Unscheduled | No | No | 2021-04-02 09:00 | 2021-06-30 18:00 | 2021-08-01 | 2021-10-29 18:00 | [6 empty] | 0 | 0 | [15 empty] | 75.8475 | 0.054589 | 5.37 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4968 | 0 | 3 | Low | [7 empty] | 0 | 0 | [222 empty] | Installation | [21 empty] | 1019995
2612 | Task(Task)-->C (Construction) | ELECTRICAL & INSTRUMENTATION |  | 1.22.3 | Unscheduled | No | No | 2021-04-02 09:00 | 2021-06-30 18:00 | 2021-08-01 | 2021-10-29 18:00 | [6 empty] | 0 | 0 | [15 empty] | 2.4011 | 0.001728 | 0.17 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4969 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019996
2613 | Task(Task)-->C (Construction) | NO LOAD COMMISSIONING & SYSTEM READYNESS FOR TRIAL OPERATION |  | 1.22.3 | Unscheduled | No | No | 2021-07-01 09:00 | 2021-07-14 18:00 | 2021-10-30 09:00 | 2021-11-12 18:00 | [6 empty] | 0 | 0 | [15 empty] | 21.7514 | 0.015655 | 1.54 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4970 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019997
2614 | Task(Task)-->E (Engineering) | UITLITY- FIRE FIGHTING SYSTEM (FDAS & FHS) | 1.23 | 1 | Work In Progress | No | No | 2019-09-27 09:00 | 2021-07-28 18:00 | 2019-10-07 18:00 | 2021-11-13 18:00 |  |  | 2019-09-27 10:57 |  |  |  | 50.2186 | 9.2419 | [15 empty] | 0.0078297 | 0.00783 | 0.77 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4971 | 0 | 1 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019998
2615 | Task(Task)-->E (Engineering) | ENGINEERING | 1.23.1 | 1.23 | Unscheduled | No | No | 2019-10-07 18:00 | 2020-07-09 17:40 | 2019-10-07 18:00 | 2020-10-15 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 67.4631 | [15 empty] | 4.3703 | 0.000342 | 4.31 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4972 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1019999
2616 | Task(Task)-->E (Engineering) | MECHANICAL | 1.23.1.1 | 1.23.1 | Unscheduled | No | No | 2020-03-06 18:00 | 2020-06-09 17:40 | 2020-04-16 18:00 | 2020-10-15 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 70.1613 | [15 empty] | 81.2065 | 0.000278 | 3.5 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4973 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036137
2617 | Task(Task)-->E (Engineering) | DBR & SCHEMATIC FOR FIRE FIGHTING SYSTEM |  | 1.23.1.1 | Unscheduled | No | No | 2020-03-06 18:00 | 2020-05-11 17:40 | 2020-04-16 18:00 | 2020-08-17 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-FF-DB-6004 |  | 2020-02-13 11:40 | 7012-155-PVM-L-034 |  |  |  | A |  |  |  | 19.1977 | 5.3e-05 | 0.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 250 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4980 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-06 18:00 | 2020-04-16 18:00 |  | 10 |  |  |  | 2020-03-30 17:40 | 2020-05-07 18:00 |  | 30 |  |  |  | 2020-04-04 17:40 | 2020-05-14 18:00 |  | 35 |  |  |  | 2020-04-10 23:59 | 2020-05-21 18:00 |  | 65 | 2020-05-05 23:31 |  |  | 2020-04-17 17:40 | 2020-06-11 18:00 |  | 80 | 2020-05-22 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | 2020-09-18 09:35 | [5 empty] | 80 | 2020-09-18 09:35 | [5 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-11 17:40 | 2020-06-25 18:00 |  | 100 | [122 empty] | Ram Prasad Roy |  |  |  |  | U - Water Media & Utility System | [16 empty] | 79 |  |  |  | 101093
2618 | Task(Task)-->E (Engineering) | GENERAL LAYOUT PLAN SHOWING FIRE FIGHTING SYSTEM PIPING |  | 1.23.1.1 | Unscheduled | No | No | 2020-03-20 18:00 | 2020-05-25 17:40 | 2020-05-05 09:00 | 2020-07-10 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-FF-GA-6007 |  | 2020-02-13 11:40 | 7012-155-PVM-P-037 |  |  |  | A |  |  |  | 15.4728 | 4.3e-05 | 0.54 | Plan & Actual | Date |  | 0 | 0 | 0 | 200 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4981 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-20 18:00 | 2020-05-12 18:00 |  | 10 |  |  |  | 2020-04-13 17:40 | 2020-06-02 18:00 |  | 30 |  |  |  | 2020-04-18 17:40 | 2020-06-09 18:00 |  | 35 |  |  |  | 2020-04-24 23:59 | 2020-06-16 18:00 |  | 65 | 2020-05-05 23:31 |  |  | 2020-05-01 17:40 | 2020-07-07 18:00 |  | 80 | 2020-05-16 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-25 17:40 | 2020-07-07 18:00 |  | 100 | [122 empty] | Ram Prasad Roy |  |  |  |  | U - Water Media & Utility System | [16 empty] | 82 |  |  |  | 101096
2619 | Task(Task)-->E (Engineering) | GA, CS, DATA SHEET & CURVE OF PUMPS FOR FIRE FIGHTING SYSTEM |  | 1.23.1.1 | Unscheduled | No | No | 2020-04-01 18:00 | 2020-05-25 17:40 | 2020-07-16 18:00 | 2020-09-28 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-FF-GA-6301 |  | 2020-02-13 11:40 | 7012-155-PVM-B-153 |  |  |  | A |  |  |  | 15.4728 | 4.3e-05 | 0.54 | Plan & Actual | Date |  | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4974 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-01 18:00 | 2020-07-16 18:00 |  | 10 |  |  |  | 2020-04-13 17:40 | 2020-07-31 18:00 |  | 30 |  |  |  | 2020-04-18 17:40 | 2020-08-04 18:00 |  | 35 |  |  |  | 2020-04-24 23:59 | 2020-08-08 18:00 |  | 65 | 2020-09-12 14:30 |  |  | 2020-05-01 17:40 | 2020-08-29 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-25 17:40 | 2020-08-29 18:00 |  | 100 | [122 empty] | Ram Prasad Roy |  |  |  |  | U - Water Media & Utility System | [16 empty] | 93 |  |  |  | 101107
2620 | Task(Task)-->E (Engineering) | DATA SHEET & GA DRG OF MANUAL VALVES & STRAINERS FOR FIRE FIGHTING SYSTEM |  | 1.23.1.1 | Unscheduled | No | No | 2020-04-14 17:40 | 2020-05-26 17:40 | 2020-08-30 23:59 | 2020-10-01 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-FF-GA-6302 |  | 2020-02-13 11:40 | 7012-155-PVM-B-154 |  |  |  | A |  |  |  | 11.4613 | 3.2e-05 | 0.4 | Plan & Actual | Date |  | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4975 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-16 18:00 | 2020-08-30 23:59 |  | 10 |  |  |  | 2020-04-14 17:40 | 2020-09-06 23:59 |  | 30 |  |  |  | 2020-04-20 17:40 | 2020-09-10 18:00 |  | 35 |  |  |  | 2020-04-27 23:59 | 2020-09-10 18:00 |  | 65 | 2020-09-16 10:02 |  |  | 2020-05-02 17:40 | 2020-10-01 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-26 17:40 | 2020-10-01 18:00 |  | 100 | [122 empty] | Ram Prasad Roy |  |  |  |  | U - Water Media & Utility System | [16 empty] | 94 |  |  |  | 101108
2621 | Task(Task)-->E (Engineering) | GA DRG & TECHNICAL DATA SHEET FOR HYDRANT VALVE FOR FIRE FIGHTING SYSTEM |  | 1.23.1.1 | Unscheduled | No | No | 2020-04-16 17:40 | 2020-05-28 17:40 | 2020-08-20 18:00 | 2020-10-15 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-FF-GA-6303 |  | 2020-02-13 11:40 | 7012-155-PVM-B-155 |  |  |  | A |  |  |  | 11.4613 | 3.2e-05 | 0.4 | Plan & Actual | Date |  | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4976 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-18 18:00 | 2020-08-20 18:00 |  | 10 |  |  |  | 2020-04-16 17:40 | 2020-08-27 18:00 |  | 30 |  |  |  | 2020-04-22 17:40 | 2020-08-31 18:00 |  | 35 |  |  |  | 2020-04-29 23:59 | 2020-08-31 18:00 |  | 65 | 2020-09-12 14:30 |  |  | 2020-05-05 17:40 | 2020-09-21 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-28 17:40 | 2020-09-21 18:00 |  | 100 | [122 empty] | Ram Prasad Roy |  |  |  |  | U - Water Media & Utility System | [16 empty] | 95 |  |  |  | 101109
2622 | Task(Task)-->E (Engineering) | GA DRG & TECHNICAL DATA SHEET FOR WATER MONITOR FOR FIRE FIGHTING SYSTEM |  | 1.23.1.1 | Unscheduled | No | No | 2020-04-21 17:40 | 2020-06-02 17:40 | 2020-08-16 23:59 | 2020-10-15 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-FF-GA-6304 |  | 2020-02-13 11:40 | 7012-155-PVM-B-156 |  |  |  | A |  |  |  | 7.7364 | 2.2e-05 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4977 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-23 18:00 | 2020-08-16 23:59 |  | 10 |  |  |  | 2020-04-21 17:40 | 2020-08-23 23:59 |  | 30 |  |  |  | 2020-04-28 17:40 | 2020-08-27 18:00 |  | 35 |  |  |  | 2020-05-04 23:59 | 2020-08-27 18:00 |  | 65 | 2020-09-12 14:30 |  |  | 2020-05-11 17:40 | 2020-09-17 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-02 17:40 | 2020-09-17 18:00 |  | 100 | [122 empty] | Ram Prasad Roy |  |  |  |  | U - Water Media & Utility System | [16 empty] | 96 |  |  |  | 101110
2623 | Task(Task)-->E (Engineering) | DATA SHEET OF PIPES & PIPE FITTINGS FOR FIRE FIGHTING SYSTEM |  | 1.23.1.1 | Unscheduled | No | No | 2020-04-23 17:40 | 2020-06-04 17:40 | 2020-07-25 18:00 | 2020-10-15 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-FF-GA-6305 |  | 2020-02-13 11:40 | 7012-155-PVM-Y-157 |  |  |  | A |  |  |  | 3.7249 | 1e-05 | 0.13 | Plan & Actual | Date |  | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4982 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-25 18:00 | 2020-07-25 18:00 |  | 10 |  |  |  | 2020-04-23 17:40 | 2020-08-01 18:00 |  | 30 |  |  |  | 2020-04-30 17:40 | 2020-08-05 18:00 |  | 35 |  |  |  | 2020-05-06 23:59 | 2020-08-05 18:00 |  | 65 | 2020-08-22 12:45 |  |  | 2020-05-13 17:40 | 2020-08-26 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-04 17:40 | 2020-08-26 18:00 |  | 100 | [122 empty] | Ram Prasad Roy |  |  |  |  | U - Water Media & Utility System | [16 empty] | 97 |  |  |  | 101111
2624 | Task(Task)-->E (Engineering) | GA DRG & TECHNICAL DATA SHEET FOR HOSE PIPE WITH COUPLING, BRANCH PIPE (NOZZLE) & HOSE BOX FOR FIRE FIGHTING SYSTEM. |  | 1.23.1.1 | Unscheduled | No | No | 2020-04-27 17:40 | 2020-06-06 17:40 | 2020-07-20 18:00 | 2020-10-15 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-FF-GA-6306 |  | 2020-02-13 11:40 | 7012-155-PVM-B-158 |  |  |  | A |  |  |  | 7.7364 | 2.2e-05 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4978 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-27 18:00 | 2020-07-20 18:00 |  | 10 |  |  |  | 2020-04-27 17:40 | 2020-07-27 18:00 |  | 30 |  |  |  | 2020-05-02 17:40 | 2020-07-31 18:00 |  | 35 |  |  |  | 2020-05-08 23:59 | 2020-07-31 18:00 |  | 65 | 2020-09-12 14:30 |  |  | 2020-05-15 17:40 | 2020-08-21 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-06 17:40 | 2020-08-21 18:00 |  | 100 | [122 empty] | Ram Prasad Roy |  |  |  |  | U - Water Media & Utility System | [16 empty] | 98 |  |  |  | 101112
2625 | Task(Task)-->E (Engineering) | DATA SHEET & GA DRG OF DELUGE VALVE FOR FIRE FIGHTING SYSTEM |  | 1.23.1.1 | Unscheduled | No | No | 2020-04-29 17:40 | 2020-06-09 17:40 | 2020-08-14 18:00 | 2020-10-15 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-FF-GA-6307 |  | 2020-02-13 11:40 | 7012-155-PVM-B-159 |  |  |  | A |  |  |  | 7.7364 | 2.2e-05 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4979 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-05-01 18:00 | 2020-08-14 18:00 |  | 10 |  |  |  | 2020-04-29 17:40 | 2020-08-21 18:00 |  | 30 |  |  |  | 2020-05-05 17:40 | 2020-08-25 18:00 |  | 35 |  |  |  | 2020-05-12 23:59 | 2020-08-25 18:00 |  | 65 | 2020-09-16 10:02 |  |  | 2020-05-18 17:40 | 2020-09-15 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-09 17:40 | 2020-09-15 18:00 |  | 100 | [122 empty] | Ram Prasad Roy |  |  |  |  | U - Water Media & Utility System | [16 empty] | 99 |  |  |  | 101113
2626 | Task(Task)-->E (Engineering) | CIVIL | 1.23.1.2 | 1.23.1 | Unscheduled | No | No | 2020-05-10 23:59 | 2020-07-09 17:40 | 2020-06-30 18:00 | 2020-09-08 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 0 | [15 empty] | 2.7842 | 1e-05 | 0.12 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4983 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036138
2627 | Task(Task)-->E (Engineering) | Design calculation of fire fighting system |  | 1.23.1.2 | Unscheduled | No | No | 2020-05-10 23:59 | 2020-07-09 17:40 | 2020-06-30 18:00 | 2020-09-08 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0035 |  | 2020-02-13 11:43 | 7012-155-PVC-U-123 |  |  |  | A |  |  |  | 50 | 5e-06 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 22.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4986 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-05-10 23:59 | 2020-06-30 18:00 |  | 10 |  |  |  | 2020-05-29 17:40 | 2020-07-25 18:00 |  | 30 |  |  |  | 2020-06-04 17:40 | 2020-07-28 18:00 |  | 35 |  |  |  | 2020-06-10 23:59 | 2020-08-04 18:00 |  | 65 |  |  |  | 2020-06-17 17:40 | 2020-08-25 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-07-09 17:40 | 2020-09-08 18:00 |  | 100 | [122 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 223 |  |  |  | 101233
2628 | Task(Task)-->E (Engineering) | Fire fighting system : NUM & RC DETAILS (SHT 1) |  | 1.23.1.2 | Unscheduled | No | No | 2020-05-10 23:59 | 2020-07-09 17:40 | 2020-06-30 18:00 | 2020-09-08 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-NR-0044 |  | 2020-02-13 11:43 | 7012-155-PVC-C-124 |  |  |  | A |  |  |  | 25 | 3e-06 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 11.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4984 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-05-10 23:59 | 2020-06-30 18:00 |  | 10 |  |  |  | 2020-05-29 17:40 | 2020-07-25 18:00 |  | 30 |  |  |  | 2020-06-04 17:40 | 2020-07-28 18:00 |  | 35 |  |  |  | 2020-06-10 23:59 | 2020-08-04 18:00 |  | 65 |  |  |  | 2020-06-17 17:40 | 2020-08-25 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-07-09 17:40 | 2020-09-08 18:00 |  | 100 | [122 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 224 |  |  |  | 101234
2629 | Task(Task)-->E (Engineering) | Fire fighting system : NUM & RC DETAILS (SHT 2) |  | 1.23.1.2 | Unscheduled | No | No | 2020-05-10 23:59 | 2020-07-09 17:40 | 2020-06-30 18:00 | 2020-09-08 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-NR-0045 |  | 2020-02-13 11:43 | 7012-155-PVC-C-125 |  |  |  | A |  |  |  | 25 | 3e-06 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 11.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4985 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-05-10 23:59 | 2020-06-30 18:00 |  | 10 |  |  |  | 2020-05-29 17:40 | 2020-07-25 18:00 |  | 30 |  |  |  | 2020-06-04 17:40 | 2020-07-28 18:00 |  | 35 |  |  |  | 2020-06-10 23:59 | 2020-08-04 18:00 |  | 65 |  |  |  | 2020-06-17 17:40 | 2020-08-25 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-07-09 17:40 | 2020-09-08 18:00 |  | 100 | [122 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 225 |  |  |  | 101235
2630 | Task(Task)-->E (Engineering) | ELECTRICAL | 1.23.1.3 | 1.23.1 | Unscheduled | No | No | 2019-10-07 18:00 | 2020-06-06 17:40 | 2019-10-07 18:00 | 2020-08-21 18:00 |  |  | 2020-02-21 14:08 |  |  |  | 100 | 66.0909 | [15 empty] | 16.0093 | 5.5e-05 | 0.69 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4987 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036139
2631 | Task(Task)-->E (Engineering) | FDA SYSTEM CONFIGURATION DIAGRAM |  | 1.23.1.3 | Unscheduled | No | No | 2019-10-07 18:00 | 2019-11-30 17:40 | 2019-10-07 18:00 | 2020-04-22 18:00 |  |  | 2020-02-21 14:08 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-BE-005 |  | 2020-02-13 11:48 | 7012-155-PVI-Q-005 |  |  |  | A |  |  |  | 7.6923 | 4e-06 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 15 | 0 | 5.04 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4988 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-10-07 18:00 | 2019-10-07 18:00 |  | 10 | 2019-10-07 23:31 |  |  | 2019-10-23 17:40 | 2019-10-15 18:00 |  | 30 | 2019-10-15 23:31 |  |  | 2019-10-29 17:40 | 2019-10-30 18:00 |  | 35 | 2019-10-30 23:31 |  |  | 2019-11-04 23:59 | 2020-01-16 18:00 |  | 65 | 2020-01-16 23:31 |  |  | 2019-11-09 17:40 | 2020-01-30 18:00 |  | 80 | 2020-01-30 23:31 | [5 empty] | 80 | 2020-05-26 15:35 | [5 empty] | 80 | 2020-05-26 15:35 | [5 empty] | 80 | 2020-07-24 15:55 | [5 empty] | 80 | 2020-07-24 15:55 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2019-11-30 17:40 | 2020-01-30 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [21 empty] | 410 |  |  |  | 101422
2632 | Task(Task)-->E (Engineering) | GA,DATA SHEET & SCHEME OF FDA SYSTEM |  | 1.23.1.3 | Unscheduled | No | No | 2020-04-27 17:40 | 2020-06-06 17:40 | 2020-06-21 23:59 | 2020-08-21 18:00 |  |  | 2020-02-21 14:09 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-VD-016 |  | 2020-02-13 11:49 | 7012-155-PVI-W-041 |  |  |  | A |  |  |  | 92.3077 | 5.1e-05 | 0.48 | Plan & Actual | Date |  | 0 | 0 | 0 | 180 | 0 | 9.02 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4990 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-28 18:00 | 2020-06-21 23:59 |  | 10 |  |  |  | 2020-04-27 17:40 | 2020-06-26 18:00 |  | 30 |  |  |  | 2020-05-02 17:40 | 2020-06-28 23:59 |  | 35 |  |  |  | 2020-05-08 23:59 | 2020-07-01 18:00 |  | 65 | 2020-10-07 10:15 |  |  | 2020-05-15 17:40 | 2020-07-22 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-06 17:40 | 2020-07-22 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [21 empty] | 446 |  |  |  | 101458
2633 | Task(Task)-->P (Procurement) | PROCUREMENT | 1.23.2 | 1.23 | Work In Progress | No | No | 2019-09-27 09:00 | 2021-03-15 18:00 | 2020-01-17 09:00 | 2021-05-05 18:00 |  |  | 2019-09-27 10:57 |  |  |  | 58.9362 | 8.5948 | [15 empty] | 73.2407 | 0.005735 | 72.23 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4991 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020003
2634 | Task(Task)-->P (Procurement) | PURCHASE REQUISITION | 1.23.2.1 | 1.23.2 | Work In Progress | No | No | 2019-09-27 09:00 | 2020-03-20 18:00 | 2020-01-17 09:00 | 2020-06-26 18:00 |  |  | 2019-09-27 10:57 |  |  |  | 100 | 100 | [15 empty] | 4.9979 | 0.000287 | 3.61 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4992 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020004
2635 | Task(Task)-->P (Procurement) | FFS System |  | 1.23.2.1 | Completed | No | No | 2019-09-27 09:00 | 2019-09-27 18:00 | 2020-06-26 09:00 | 2020-06-26 18:00 |  |  | 2019-09-27 10:57 | 2019-09-27 10:57 |  |  | 100 | 100 | [15 empty] | 88.0886 | 0.000253 | 3.18 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4993 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020005
2636 | Task(Task)-->P (Procurement) | LPBS |  | 1.23.2.1 | Unscheduled | No | No | 2020-03-20 09:00 | 2020-03-20 18:00 | 2020-04-14 09:00 | 2020-04-14 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4994 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020006
2637 | Task(Task)-->P (Procurement) | HT AC MOTORS |  | 1.23.2.1 | Completed | No | No | 2020-01-07 09:00 | 2020-01-07 18:00 | 2020-01-17 09:00 | 2020-01-17 18:00 |  |  | 2020-01-17 10:57 | 2020-01-17 10:57 |  |  | 100 | 100 | [15 empty] | 11.9114 | 3.4e-05 | 0.43 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4995 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020007
2638 | Task(Task)-->P (Procurement) | TECHNICAL CLEARANCE | 1.23.2.2 | 1.23.2 | Work In Progress | No | No | 2019-09-28 09:00 | 2020-04-07 18:00 | 2020-01-17 09:00 | 2020-07-17 18:00 |  |  | 2020-04-11 10:57 |  |  |  | 100 | 11.8467 | [15 empty] | 4.9979 | 0.000287 | 3.61 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4996 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020008
2639 | Task(Task)-->P (Procurement) | FFS System |  | 1.23.2.2 | Unscheduled | No | No | 2019-09-28 09:00 | 2020-04-07 18:00 | 2020-06-26 09:00 | 2020-07-17 18:00 | [6 empty] | 100 | 0 | [15 empty] | 88.0886 | 0.000253 | 3.18 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4997 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020009
2640 | Task(Task)-->P (Procurement) | LPBS |  | 1.23.2.2 | Unscheduled | No | No | 2020-03-21 09:00 | 2020-04-04 18:00 | 2020-04-14 09:00 | 2020-06-12 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4998 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020010
2641 | Task(Task)-->P (Procurement) | HT AC MOTORS |  | 1.23.2.2 | Completed | No | No | 2020-01-08 09:00 | 2020-01-29 18:00 | 2020-01-17 09:00 | 2020-04-11 18:00 |  |  | 2020-04-11 10:57 | 2020-04-11 10:57 |  |  | 100 | 100 | [15 empty] | 11.9114 | 3.4e-05 | 0.43 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4999 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020011
2642 | Task(Task)-->P (Procurement) | ORDERING | 1.23.2.3 | 1.23.2 | Work In Progress | No | No | 2020-01-30 09:00 | 2020-04-27 18:00 | 2020-04-11 09:00 | 2020-08-19 18:00 |  |  | 2020-04-12 09:40 |  |  |  | 100 | 12.0419 | [15 empty] | 9.9958 | 0.000573 | 7.22 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5000 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020012
2643 | Task(Task)-->P (Procurement) | FFS System |  | 1.23.2.3 | Unscheduled | No | No | 2020-04-08 09:00 | 2020-04-27 18:00 | 2020-07-17 09:00 | 2020-07-31 18:00 | [6 empty] | 100 | 0 | [15 empty] | 87.9501 | 0.000504 | 6.35 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5001 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020013
2644 | Task(Task)-->P (Procurement) | LPBS |  | 1.23.2.3 | Unscheduled | No | No | 2020-04-05 | 2020-04-20 18:00 | 2020-06-12 09:00 | 2020-08-19 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5002 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020014
2645 | Task(Task)-->P (Procurement) | HT AC MOTORS |  | 1.23.2.3 | Completed | No | No | 2020-01-30 09:00 | 2020-02-20 18:00 | 2020-04-11 09:00 | 2020-06-25 18:00 |  |  | 2020-04-12 09:40 | 2020-06-25 09:40 |  |  | 100 | 100 | [15 empty] | 12.0499 | 6.9e-05 | 0.87 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5003 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020015
2646 | Task(Task)-->P (Procurement) | ITP APPROVAL | 1.23.2.4 | 1.23.2 | Work In Progress | No | No | 2020-02-21 09:00 | 2020-06-06 18:00 | 2020-07-29 09:00 | 2020-10-21 18:00 |  |  | 2020-07-29 15:07 |  |  |  | 100 | 0 | [15 empty] | 4.9979 | 0.000287 | 3.61 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5004 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020016
2647 | Task(Task)-->P (Procurement) | FFS System |  | 1.23.2.4 | Unscheduled | No | No | 2020-04-28 09:00 | 2020-06-06 18:00 | 2020-07-31 09:00 | 2020-09-30 18:00 | [6 empty] | 100 | 0 | [15 empty] | 88.0886 | 0.000253 | 3.18 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5005 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020017
2648 | Task(Task)-->P (Procurement) | LPBS |  | 1.23.2.4 | Completed | No | No | 2020-04-21 09:00 | 2020-05-30 18:00 | 2020-07-29 09:00 | 2020-08-21 18:00 |  |  | 2020-07-29 15:07 | 2020-08-22 12:56 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5006 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020018
2649 | Task(Task)-->P (Procurement) | HT AC MOTORS |  | 1.23.2.4 | Unscheduled | No | No | 2020-02-21 09:00 | 2020-03-31 18:00 | 2020-09-11 09:00 | 2020-10-21 18:00 | [6 empty] | 100 | 0 | [15 empty] | 11.9114 | 3.4e-05 | 0.43 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5007 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020019
2650 | Task(Task)-->P (Procurement) | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE | 1.23.2.5 | 1.23.2 | Work In Progress | No | No | 2020-02-21 09:00 | 2020-09-24 18:00 | 2020-07-18 09:00 | 2020-09-28 18:00 |  |  | 2020-07-07 09:06 |  |  |  | 100 | 11.9628 | [15 empty] | 15.0076 | 0.000861 | 10.84 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5008 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020020
2651 | Task(Task)-->P (Procurement) | FFS System |  | 1.23.2.5 | Unscheduled | No | No | 2020-04-28 09:00 | 2020-09-24 18:00 | 2020-07-31 09:00 | 2020-09-28 18:00 | [6 empty] | 100 | 0 | [15 empty] | 87.9963 | 0.000758 | 9.53 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5009 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020021
2652 | Task(Task)-->P (Procurement) | LPBS |  | 1.23.2.5 | Completed | No | No | 2020-04-21 09:00 | 2020-06-04 18:00 | 2020-07-25 09:00 | 2020-08-22 18:00 |  |  | 2020-07-24 18:36 | 2020-08-22 12:59 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5010 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020022
2653 | Task(Task)-->P (Procurement) | HT AC MOTORS |  | 1.23.2.5 | Completed | No | No | 2020-02-21 09:00 | 2020-05-05 18:00 | 2020-07-18 09:00 | 2020-09-28 18:00 |  |  | 2020-07-07 09:06 | 2020-09-28 10:23 |  |  | 100 | 100 | [15 empty] | 12.0037 | 0.000103 | 1.3 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5011 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020023
2654 | Task(Task)-->P (Procurement) | MANUFACTURING & RECEIPT AT SITE (MRN) | 1.23.2.6 | 1.23.2 | Unscheduled | No | No | 2020-05-06 09:00 | 2021-03-15 18:00 | 2020-08-23 | 2021-05-05 18:00 |  |  | 2020-08-22 13:02 |  |  |  | 31.5485 | 0 | [15 empty] | 60.0028 | 0.003441 | 43.34 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5012 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020024
2655 | Task(Task)-->P (Procurement) | FFS System |  | 1.23.2.6 | Unscheduled | No | No | 2020-08-16 | 2021-03-15 18:00 | 2020-09-28 09:00 | 2021-01-31 23:59 | [6 empty] | 25 | 0 | [15 empty] | 87.9326 | 0.003026 | 38.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5013 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020025
2656 | Task(Task)-->P (Procurement) | LPBS |  | 1.23.2.6 | Unscheduled | No | No | 2020-06-05 09:00 | 2020-09-16 18:00 | 2020-08-23 | 2020-12-04 18:00 |  |  | 2020-08-22 13:02 |  |  |  | 100 | 0 | [15 empty] | 0.046147 | 2e-06 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5014 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020026
2657 | Task(Task)-->P (Procurement) | HT AC MOTORS |  | 1.23.2.6 | Unscheduled | No | No | 2020-05-06 09:00 | 2020-11-17 18:00 | 2020-10-22 09:00 | 2021-05-05 18:00 |  |  | 2020-09-28 10:24 |  |  |  | 79.0816 | 0 | [15 empty] | 12.0212 | 0.000414 | 5.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5015 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020027
2658 | Task(Task)-->C (Construction) | CONSTRUCTION | 1.23.3 | 1.23 | Unscheduled | No | No | 2020-06-24 09:00 | 2021-07-28 18:00 | 2020-08-19 09:00 | 2021-11-13 18:00 | [6 empty] | 11.9863 | 0 | [15 empty] | 22.389 | 0.001753 | 22.08 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5016 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020028
2659 | Task(Task)-->C (Construction) | AVAILABILITY OF FRONT BY NTPC |  | 1.23.3 | Unscheduled | No | No | 2020-06-24 09:00 | 2020-06-24 18:00 | 2020-08-19 09:00 | 2020-08-19 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5607 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020029
2660 | Task(Task)-->C (Construction) | CIVIL |  | 1.23.3 | Unscheduled | No | No | 2020-07-01 09:00 | 2020-09-28 18:00 | 2020-08-26 09:00 | 2020-11-23 18:00 | [6 empty] | 100 | 0 | [15 empty] | 12.0018 | 0.00021 | 2.65 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5017 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020030
2661 | Task(Task)-->C (Construction) | INSTALLATION OF PIPING |  | 1.23.3 | Unscheduled | No | No | 2021-03-16 09:00 | 2021-07-13 18:00 | 2021-07-02 09:00 | 2021-10-29 18:00 | [6 empty] | 0 | 0 | [15 empty] | 63.6775 | 0.001116 | 14.06 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5018 | 0 | 3 | Low | [7 empty] | 0 | 0 | [222 empty] | Installation | [21 empty] | 1020031
2662 | Task(Task)-->C (Construction) | ELECTRICAL & INSTRUMENTATION |  | 1.23.3 | Unscheduled | No | No | 2021-05-14 09:00 | 2021-07-13 18:00 | 2021-08-30 09:00 | 2021-10-29 18:00 | [6 empty] | 0 | 0 | [15 empty] | 17.346 | 0.000304 | 3.83 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5019 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020032
2663 | Task(Task)-->C (Construction) | NO LOAD COMMISSIONING & SYSTEM READYNESS FOR TRIAL OPERATION |  | 1.23.3 | Unscheduled | No | No | 2021-07-14 09:00 | 2021-07-28 18:00 | 2021-10-30 09:00 | 2021-11-13 18:00 | [6 empty] | 0 | 0 | [15 empty] | 6.9746 | 0.000122 | 1.54 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5020 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020033
2664 | Task(Task)-->E (Engineering) | COMMON FOR ALL AREA | 1.24 | 1 | Work In Progress | No | No | 2019-08-01 18:00 | 2021-09-26 23:59 | 2019-08-01 18:00 | 2021-11-23 18:00 |  |  | 2019-11-12 17:40 |  |  |  | 64.6833 | 24.9647 | [15 empty] | 8.8226 | 8.8226 | 867.64 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5021 | 0 | 1 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020034
2665 | Task(Task)-->E (Engineering) | ENGINEERING | 1.24.1 | 1.24 | Work In Progress | No | No | 2019-10-10 17:40 | 2020-12-15 17:40 | 2019-10-10 17:40 | 2020-12-07 18:00 |  |  | 2019-11-12 17:40 |  |  |  | 99.1279 | 68.6695 | [15 empty] | 2.5379 | 0.22391 | 22.02 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5022 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020035
2666 | Task(Task)-->E (Engineering) | MECHANICAL | 1.24.1.1 | 1.24.1 | Work In Progress | No | No | 2019-10-10 17:40 | 2020-12-15 17:40 | 2019-10-10 17:40 | 2020-12-07 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 84.1294 | 18.0348 | [15 empty] | 5.495 | 0.012304 | 1.21 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5023 | 1 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036140
2667 | Task(Task)-->E (Engineering) | GENERAL PLOT PLAN FOR COAL MINING PROJECT - KERANDARI 'A' |  | 1.24.1.1 | Completed | No | No | 2019-10-24 17:40 | 2019-12-02 17:40 | 2019-11-04 09:00 | 2020-02-07 18:00 |  |  | 2020-06-19 22:19 | 2020-06-19 22:39 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-PP-0001 |  | 2020-02-13 10:26 | 7012-155-PVM-F-001 |  |  |  | A |  |  |  | 18.0328 | 0.002219 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5026 | 3 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-10-01 18:00 | 2019-09-30 18:00 |  | 10 | 2019-09-30 23:31 |  |  | 2019-10-24 17:40 | 2019-10-25 18:00 |  | 30 | 2019-10-25 23:31 |  |  | 2019-10-30 17:40 | 2019-10-30 18:00 |  | 35 | 2019-10-30 23:31 |  |  | 2019-11-05 23:59 | 2019-11-04 18:00 |  | 65 | 2019-11-04 23:31 |  |  | 2019-11-11 17:40 | 2020-01-17 18:00 |  | 80 | 2020-01-17 23:31 | [5 empty] | 80 | 2020-06-13 11:25 | [5 empty] | 80 | 2020-06-13 11:25 | [5 empty] | 80 | 2020-06-13 11:29 | [5 empty] | 80 | 2020-06-13 11:29 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2019-12-02 17:40 | 2020-02-07 18:00 |  | 100 | 2020-02-07 23:31 | [121 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 1 |  |  |  | 101015
2668 | Task(Task)-->E (Engineering) | CONTROL WRITE UP / OPERATIONAL PHILOSOPHY OF COAL MINING PROJECT, PART-A |  | 1.24.1.1 | Unscheduled | No | No | 2020-10-04 23:59 | 2020-12-15 17:40 | 2020-10-04 23:59 | 2020-12-07 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 12 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-DC-0030 |  | 2020-02-13 10:26 | 7012-155-PVM-Y-030 |  |  |  | A |  |  |  | 18.0328 | 0.002219 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5029 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-10-04 23:59 | 2020-10-04 23:59 |  | 10 |  |  |  | 2020-11-03 17:40 | 2020-10-25 23:59 |  | 30 |  |  |  | 2020-11-09 17:40 | 2020-11-01 23:59 |  | 35 |  |  |  | 2020-11-16 23:59 | 2020-11-16 18:00 |  | 65 |  |  |  | 2020-11-21 17:40 | 2020-12-07 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-12-15 17:40 | 2020-12-07 18:00 |  | 100 | [122 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 30 |  |  |  | 101044
2669 | Task(Task)-->E (Engineering) | G.A OF BELT VULCANIZER |  | 1.24.1.1 | Unscheduled | No | No | 2020-06-04 18:00 | 2020-07-27 17:40 | 2020-07-10 18:00 | 2020-08-23 23:59 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1036 |  | 2020-02-13 10:27 | 7012-155-PVM-B-136 |  |  |  | A |  |  |  | 9.0164 | 0.001109 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5024 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-06-04 18:00 | 2020-07-10 18:00 |  | 10 |  |  |  | 2020-06-16 17:40 | 2020-07-25 18:00 |  | 30 |  |  |  | 2020-06-22 17:40 | 2020-07-28 18:00 |  | 35 |  |  |  | 2020-06-27 23:59 | 2020-08-02 23:59 |  | 65 |  |  |  | 2020-07-03 17:40 | 2020-08-23 23:59 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-07-27 17:40 | 2020-08-23 23:59 |  | 100 | [122 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 66 |  |  |  | 101080
2670 | Task(Task)-->E (Engineering) | DBR FOR BOREWELL SYSTEM |  | 1.24.1.1 | Unscheduled | No | No | 2020-03-20 18:00 | 2020-05-25 17:40 | 2020-06-21 23:59 | 2020-08-30 23:59 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-BB-DB-6005 |  | 2020-02-13 11:40 | 7012-155-PVM-L-035 |  |  |  | A |  |  |  | 32.7869 | 0.004034 | 0.4 | Plan & Actual | Date |  | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5028 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-20 18:00 | 2020-06-21 23:59 |  | 10 |  |  |  | 2020-04-13 17:40 | 2020-07-12 23:59 |  | 30 |  |  |  | 2020-04-18 17:40 | 2020-07-19 23:59 |  | 35 |  |  |  | 2020-04-24 23:59 | 2020-07-26 23:59 |  | 65 |  |  |  | 2020-05-01 17:40 | 2020-08-16 23:59 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-25 17:40 | 2020-08-30 23:59 |  | 100 | [122 empty] | Ram Prasad Roy |  |  |  |  | U - Water Media & Utility System | [16 empty] | 80 |  |  |  | 101094
2671 | Task(Task)-->E (Engineering) | GA, CS, DATA SHEET & CURVE OF PUMPS FOR BOREWELL |  | 1.24.1.1 | Unscheduled | No | No | 2020-04-20 18:00 | 2020-06-17 17:40 | 2020-08-22 18:00 | 2020-10-11 23:59 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-BB-GA-6501 |  | 2020-02-13 11:40 | 7012-155-PVM-B-161 |  |  |  | A |  |  |  | 22.1311 | 0.002723 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5025 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-20 18:00 | 2020-08-22 18:00 |  | 10 |  |  |  | 2020-05-06 17:40 | 2020-09-06 23:59 |  | 30 |  |  |  | 2020-05-13 17:40 | 2020-09-13 23:59 |  | 35 |  |  |  | 2020-05-19 23:59 | 2020-09-20 23:59 |  | 65 |  |  |  | 2020-05-26 17:40 | 2020-10-11 23:59 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-17 17:40 | 2020-10-11 23:59 |  | 100 | [122 empty] | Ram Prasad Roy |  |  |  |  | U - Water Media & Utility System | [16 empty] | 101 |  |  |  | 101115
2672 | Task(Task)-->E (Engineering) | FLOW DIAGRAM FOR COAL MINING PROJECT - KERANDARI 'A' |  | 1.24.1.1 | Completed | No | No | 2019-10-10 17:40 | 2019-11-18 17:40 | 2019-10-10 17:40 | 2019-11-18 17:40 |  |  | 2020-06-19 22:23 | 2020-06-19 22:40 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-CS-FD-0002 |  | 2020-02-13 10:26 | 7012-155-PVM-L-002 |  |  |  | A |  |  |  | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 2 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-10-07 18:00 | 2019-10-20 23:59 |  | 10 | 2019-10-20 23:31 |  |  | 2019-10-10 17:40 | 2019-10-29 18:00 |  | 30 | 2019-10-29 23:31 |  |  | 2019-10-16 17:40 | 2019-11-03 23:59 |  | 35 | 2019-11-03 23:31 |  |  | 2019-10-22 23:59 | 2019-11-05 18:00 |  | 65 | 2019-11-05 23:31 |  |  | 2019-10-28 17:40 | 2019-11-25 18:00 |  | 80 | 2019-11-25 23:31 | [5 empty] | 80 | 2020-03-21 16:43 | [5 empty] | 80 | 2020-03-21 16:43 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2019-11-18 17:40 | 2019-12-27 18:00 |  | 100 | 2019-12-27 23:31 | [121 empty] | Satyanarayana GV |  |  |  |  | M - Mechanical Process & Equipment | [16 empty] | 2 |  |  |  | 101016
2673 | Task(Task)-->E (Engineering) | CIVIL | 1.24.1.2 | 1.24.1 | Completed | No | No | 2019-11-12 17:40 | 2020-02-29 17:40 | 2019-11-13 09:00 | 2020-05-18 18:00 |  |  | 2019-11-12 17:40 | 2020-09-01 14:23 |  |  | 100 | 100 | [15 empty] | 13.6694 | 0.030607 | 3.01 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5030 | 6 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036141
2674 | Task(Task)-->E (Engineering) | BASIC DESIGN CRITERIA FOR CIVIL WORKS |  | 1.24.1.2 | Completed | No | No | 2019-11-14 17:40 | 2019-12-23 17:40 | 2019-11-13 09:00 | 2019-12-20 18:00 |  |  | 2019-11-14 17:40 | 2020-03-02 10:52 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DB-0001 |  | 2020-02-13 11:41 | 7012-155-PVC-W-001 |  |  |  | A |  |  |  | 12.2112 | 0.003737 | 0.37 | Plan & Actual | Date |  | 0 | 0 | 0 | 136.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5036 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-10-26 18:00 | 2019-10-13 23:59 |  | 10 | 2019-10-13 23:31 |  |  | 2019-11-14 17:40 | 2019-11-03 23:59 |  | 30 | 2019-11-03 23:31 |  |  | 2019-11-20 17:40 | 2019-11-06 18:00 |  | 35 | 2019-11-06 23:31 |  |  | 2019-11-26 23:59 | 2019-11-13 18:00 |  | 65 | 2019-11-13 23:31 |  |  | 2019-12-02 17:40 | 2019-12-19 18:00 |  | 80 | 2019-12-19 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2019-12-23 17:40 | 2019-12-27 18:00 |  | 100 | 2019-12-27 23:31 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 102 |  |  |  | 101116
2675 | Task(Task)-->E (Engineering) | BASIC DESIGN CRITERIA FOR STRUCTURAL WORKS |  | 1.24.1.2 | Completed | No | No | 2019-11-14 17:40 | 2019-12-23 17:40 | 2019-11-13 09:00 | 2019-12-23 18:00 |  |  | 2019-11-14 17:40 | 2020-03-02 10:52 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DB-0002 |  | 2020-02-13 11:41 | 7012-155-PVC-W-002 |  |  |  | A |  |  |  | 12.2112 | 0.003737 | 0.37 | Plan & Actual | Date |  | 0 | 0 | 0 | 136.02 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5037 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-10-26 18:00 | 2019-10-13 23:59 |  | 10 | 2019-10-13 23:31 |  |  | 2019-11-14 17:40 | 2019-11-03 23:59 |  | 30 | 2019-11-03 23:31 |  |  | 2019-11-20 17:40 | 2019-11-06 18:00 |  | 35 | 2019-11-06 23:31 |  |  | 2019-11-26 23:59 | 2019-11-13 18:00 |  | 65 | 2019-11-13 23:31 |  |  | 2019-12-02 17:40 | 2019-12-20 18:00 |  | 80 | 2019-12-20 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2019-12-23 17:40 | 2019-12-27 18:00 |  | 100 | 2019-12-27 23:31 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 103 |  |  |  | 101117
2676 | Task(Task)-->E (Engineering) | GENERAL NOTES CIVIL WORKS |  | 1.24.1.2 | Completed | No | No | 2019-11-19 17:40 | 2019-12-27 17:40 | 2019-11-28 09:00 | 2019-12-18 18:00 |  |  | 2019-11-19 17:40 | 2020-03-02 10:52 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-NR-0001 |  | 2020-02-13 11:41 | 7012-155-PVC-W-003 |  |  |  | A |  |  |  | 7.5908 | 0.002323 | 0.23 | Plan & Actual | Date |  | 0 | 0 | 0 | 86.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5038 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-10-30 18:00 | 2019-10-28 18:00 |  | 10 | 2019-10-28 23:31 |  |  | 2019-11-19 17:40 | 2019-11-18 18:00 |  | 30 | 2019-11-18 23:31 |  |  | 2019-11-25 17:40 | 2019-11-21 18:00 |  | 35 | 2019-11-21 23:31 |  |  | 2019-11-30 23:59 | 2019-11-28 18:00 |  | 65 | 2019-11-28 23:31 |  |  | 2019-12-06 17:40 | 2019-12-16 18:00 |  | 80 | 2019-12-16 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2019-12-27 17:40 | 2019-12-27 18:00 |  | 100 | 2019-12-27 23:31 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 104 |  |  |  | 101118
2677 | Task(Task)-->E (Engineering) | TECHNICAL SPECIFICATION FOR TOPOGRAPHICAL SURVEY |  | 1.24.1.2 | Completed | No | No | 2019-11-12 17:40 | 2019-12-20 17:40 | 2019-11-21 09:00 | 2019-12-11 18:00 |  |  | 2019-11-12 17:40 | 2020-03-02 10:52 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0030 |  | 2020-02-13 11:43 | 7012-155-PVC-W-103 |  |  |  | A |  |  |  | 5.9406 | 0.001818 | 0.18 | Plan & Actual | Date |  | 0 | 0 | 0 | 66.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5040 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-10-23 18:00 | 2019-10-17 18:00 |  | 10 | 2019-10-17 23:31 |  |  | 2019-11-12 17:40 | 2019-11-11 18:00 |  | 30 | 2019-11-11 23:31 |  |  | 2019-11-18 17:40 | 2019-11-14 18:00 |  | 35 | 2019-11-14 23:31 |  |  | 2019-11-23 23:59 | 2019-11-21 18:00 |  | 65 | 2019-11-21 23:31 |  |  | 2019-11-29 17:40 | 2019-12-11 18:00 |  | 80 | 2019-12-11 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2019-12-20 17:40 | 2019-12-25 18:00 |  | 100 | 2019-12-11 23:31 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 204 |  |  |  | 101214
2678 | Task(Task)-->E (Engineering) | TOPOGRAPHICAL SURVEY - G.A DRAWING |  | 1.24.1.2 | Completed | No | No | 2019-11-12 17:40 | 2019-12-20 17:40 | 2019-11-20 09:00 | 2019-12-30 18:00 |  |  | 2019-11-12 17:40 | 2020-02-29 17:19 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-GA-0025 |  | 2020-02-13 11:43 | 7012-155-PVC-B-104 |  |  |  | A |  |  |  | 10.231 | 0.003131 | 0.31 | Plan & Actual | Date |  | 0 | 0 | 0 | 113.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5031 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-10-23 18:00 | 2019-10-16 18:00 |  | 10 | 2019-10-16 23:31 |  |  | 2019-11-12 17:40 | 2019-11-10 23:59 |  | 30 | 2019-11-10 23:31 |  |  | 2019-11-18 17:40 | 2019-11-13 18:00 |  | 35 | 2019-11-13 23:31 |  |  | 2019-11-23 23:59 | 2019-11-20 18:00 |  | 65 | 2019-11-20 23:31 |  |  | 2019-11-29 17:40 | 2019-12-02 18:00 |  | 80 | 2019-12-02 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2019-12-20 17:40 | 2020-03-24 18:00 |  | 100 | 2020-03-24 23:31 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 205 |  |  |  | 101215
2679 | Task(Task)-->E (Engineering) | TECHNICAL SPECIFICATION FOR GEOTECHNICAL INVESTIGATION |  | 1.24.1.2 | Completed | No | No | 2020-01-20 17:40 | 2020-02-29 17:40 | 2020-01-07 09:00 | 2020-01-21 18:00 |  |  | 2020-01-20 17:40 | 2020-02-29 17:19 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0031 |  | 2020-02-13 11:43 | 7012-155-PVC-W-105 |  |  |  | A |  |  |  | 5.9406 | 0.001818 | 0.18 | Plan & Actual | Date |  | 0 | 0 | 0 | 66.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5041 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-12-31 18:00 | 2019-12-03 18:00 |  | 10 | 2019-12-03 23:31 |  |  | 2020-01-20 17:40 | 2019-12-28 18:00 |  | 30 | 2019-12-28 23:31 |  |  | 2020-01-25 17:40 | 2019-12-31 18:00 |  | 35 | 2019-12-31 23:31 |  |  | 2020-01-31 23:59 | 2020-01-07 18:00 |  | 65 | 2020-01-07 23:31 |  |  | 2020-02-06 17:40 | 2020-01-21 18:00 |  | 80 | 2020-01-21 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-02-29 17:40 | 2020-02-04 18:00 |  | 100 | 2020-01-21 23:31 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 206 |  |  |  | 101216
2680 | Task(Task)-->E (Engineering) | SOIL INVESTIGATION REPORT |  | 1.24.1.2 | Completed | No | No | 2019-12-31 18:00 | 2020-02-29 17:40 | 2020-04-25 09:00 | 2020-05-08 18:00 |  |  | 2020-02-21 15:38 | 2020-09-01 14:23 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0032 |  | 2020-02-13 11:43 | 7012-155-PVC-U-106 |  |  |  | A |  |  |  | 20.132 | 0.006162 | 0.61 | Plan & Actual | Date |  | 0 | 0 | 0 | 227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5033 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-12-31 18:00 | 2020-03-21 18:00 |  | 10 | 2020-03-21 23:31 |  |  | 2020-01-20 17:40 | 2020-03-21 18:00 |  | 30 | 2020-03-21 23:31 |  |  | 2020-01-25 17:40 | 2020-04-18 18:00 |  | 35 | 2020-04-18 23:31 |  |  | 2020-01-31 23:59 | 2020-04-25 18:00 |  | 65 | 2020-04-25 23:31 |  |  | 2020-02-06 17:40 | 2020-05-16 18:00 |  | 80 | 2020-05-08 23:31 | [5 empty] | 80 | 2020-09-01 00:15 | [5 empty] | 80 | 2020-09-01 00:15 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-02-29 17:40 | 2020-05-30 18:00 |  | 100 | 2020-09-01 14:24 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 207 |  |  |  | 101217
2681 | Task(Task)-->E (Engineering) | DESIGN CALCULATION OF ROOF & SIDE CLADDING |  | 1.24.1.2 | Completed | No | No | 2019-12-30 17:40 | 2020-02-06 17:40 | 2020-04-15 09:00 | 2020-05-18 18:00 |  |  | 2019-12-30 17:40 | 2020-05-18 15:58 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0033 |  | 2020-02-13 11:43 | 7012-155-PVC-U-121 |  |  |  | A |  |  |  | 4.9505 | 0.001515 | 0.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 54.29 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5034 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-12-10 18:00 | 2020-03-26 18:00 |  | 10 | 2020-03-16 23:31 |  |  | 2019-12-30 17:40 | 2020-04-20 18:00 |  | 30 | 2020-04-05 23:31 |  |  | 2020-01-04 17:40 | 2020-04-23 18:00 |  | 35 | 2020-04-12 23:31 |  |  | 2020-01-10 23:59 | 2020-04-30 18:00 |  | 65 | 2020-04-15 23:31 |  |  | 2020-01-16 17:40 | 2020-05-21 18:00 |  | 80 | 2020-05-18 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-02-06 17:40 | 2020-06-04 18:00 |  | 100 | 2020-05-18 23:31 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 221 |  |  |  | 101231
2682 | Task(Task)-->E (Engineering) | DESIGN CALCULATION OF METAL DECK SHEETING |  | 1.24.1.2 | Completed | No | No | 2019-12-30 17:40 | 2020-02-06 17:40 | 2020-04-15 09:00 | 2020-05-18 18:00 |  |  | 2019-12-30 17:40 | 2020-05-18 16:00 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0034 |  | 2020-02-13 11:43 | 7012-155-PVC-U-122 |  |  |  | A |  |  |  | 4.9505 | 0.001515 | 0.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 54.29 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5035 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-12-10 18:00 | 2020-03-26 18:00 |  | 10 | 2020-03-16 23:31 |  |  | 2019-12-30 17:40 | 2020-04-20 18:00 |  | 30 | 2020-04-05 23:31 |  |  | 2020-01-04 17:40 | 2020-04-23 18:00 |  | 35 | 2020-04-12 23:31 |  |  | 2020-01-10 23:59 | 2020-04-30 18:00 |  | 65 | 2020-04-15 23:31 |  |  | 2020-01-16 17:40 | 2020-05-21 18:00 |  | 80 | 2020-05-18 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-02-06 17:40 | 2020-06-04 18:00 |  | 100 | 2020-05-18 23:31 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 222 |  |  |  | 101232
2683 | Task(Task)-->E (Engineering) | LAYOUT DRAWING WITH SOIL TEST LOCATION |  | 1.24.1.2 | Completed | No | No | 2019-12-26 17:40 | 2020-02-03 17:40 | 2020-01-07 09:00 | 2020-02-17 18:00 |  |  | 2019-12-26 17:40 | 2020-02-29 17:19 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-GA-0026 |  | 2020-02-13 11:44 | 7012-155-PVC-B-136 |  |  |  | A |  |  |  | 8.2508 | 0.002525 | 0.25 | Plan & Actual | Date |  | 0 | 0 | 0 | 92.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5032 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-12-15 23:59 | 2019-12-15 23:59 |  | 10 | 2019-12-15 23:31 |  |  | 2019-12-26 17:40 | 2019-12-19 18:00 |  | 30 | 2019-12-19 23:31 |  |  | 2020-01-01 17:40 | 2019-12-25 18:00 |  | 35 | 2019-12-25 23:31 |  |  | 2020-01-07 23:59 | 2020-01-07 18:00 |  | 65 | 2020-01-07 23:31 |  |  | 2020-01-13 17:40 | 2020-02-11 18:00 |  | 80 | 2020-02-11 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-02-03 17:40 | 2020-02-11 18:00 |  | 100 | 2020-02-17 23:31 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 235A |  |  |  | 101246
2684 | Task(Task)-->E (Engineering) | GENERAL NOTES STRUCTURAL WORKS |  | 1.24.1.2 | Completed | No | No | 2019-11-19 17:40 | 2019-12-27 17:40 | 2019-11-30 09:00 | 2019-12-31 18:00 |  |  | 2019-11-19 17:40 | 2020-03-02 10:52 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-GA-0001 |  | 2020-02-13 11:41 | 7012-155-PVC-W-004 |  |  |  | A |  |  |  | 7.5908 | 0.002323 | 0.23 | Plan & Actual | Date |  | 0 | 0 | 0 | 86.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5039 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-10-30 18:00 | 2019-10-30 18:00 |  | 10 | 2019-10-30 23:31 |  |  | 2019-11-19 17:40 | 2019-11-20 18:00 |  | 30 | 2019-11-20 23:31 |  |  | 2019-11-25 17:40 | 2019-11-23 18:00 |  | 35 | 2019-11-23 23:31 |  |  | 2019-11-30 23:59 | 2019-11-30 18:00 |  | 65 | 2019-11-30 23:31 |  |  | 2019-12-06 17:40 | 2019-12-20 18:00 |  | 80 | 2019-12-20 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2019-12-27 17:40 | 2020-01-09 18:00 |  | 100 | 2020-01-09 23:31 | [121 empty] | Chetan Khodke |  |  |  |  | C - Civil | [16 empty] | 105 |  |  |  | 101119
2685 | Task(Task)-->E (Engineering) | ELECTRICAL | 1.24.1.3 | 1.24.1 | Unscheduled | No | No | 2019-11-01 18:00 | 2020-08-24 17:40 | 2019-11-06 18:00 | 2020-11-10 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 58.0572 | [15 empty] | 33.7875 | 0.075653 | 7.44 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5043 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036142
2686 | Task(Task)-->E (Engineering) | MASTER LOAD LIST FOR CHP |  | 1.24.1.3 | Unscheduled | No | No | 2019-11-07 18:00 | 2019-12-18 17:40 | 2019-11-06 18:00 | 2020-04-17 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-LL-5001 |  | 2020-02-13 11:44 | 7012-155-PVE-R-001 |  |  |  | I |  |  |  | 6.0647 | 0.004588 | 0.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 165.48 | 0 | 2.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5050 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-11-07 18:00 | 2019-11-06 18:00 |  | 10 | 2019-11-06 23:31 |  |  | 2019-11-09 17:40 | 2019-11-13 18:00 |  | 30 | 2019-11-13 23:31 |  |  | 2019-11-15 17:40 | 2019-11-19 18:00 |  | 35 | 2019-11-19 23:31 |  |  | 2019-11-21 23:59 | 2019-11-19 18:00 |  | 65 | 2019-11-19 23:31 |  |  | 2019-11-27 17:40 | 2019-12-10 18:00 |  | 80 | 2019-12-10 23:31 | [5 empty] | 80 | 2020-06-10 12:29 | [5 empty] | 80 | 2020-06-10 12:29 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2019-12-18 17:40 | 2020-04-17 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 236 |  |  |  | 101247
2687 | Task(Task)-->E (Engineering) | HT & LT TRANSFORMER SIZING CALCULATION FOR CHP |  | 1.24.1.3 | Unscheduled | No | No | 2019-11-01 18:00 | 2019-12-23 17:40 | 2019-11-06 18:00 | 2020-04-17 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DC-5002 |  | 2020-02-13 11:44 | 7012-155-PVE-U-002 |  |  |  | A |  |  |  | 4.4474 | 0.003365 | 0.33 | Plan & Actual | Date |  | 0 | 0 | 0 | 124.21 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5051 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-11-01 18:00 | 2019-11-06 18:00 |  | 10 | 2019-11-02 23:31 |  |  | 2019-11-14 17:40 | 2019-11-14 18:00 |  | 30 | 2019-11-14 23:31 |  |  | 2019-11-20 17:40 | 2019-11-19 18:00 |  | 35 | 2019-11-19 23:31 |  |  | 2019-11-26 23:59 | 2019-11-19 18:00 |  | 65 | 2019-11-19 23:31 |  |  | 2019-12-02 17:40 | 2019-11-28 18:00 |  | 80 | 2019-11-28 23:31 | [5 empty] | 80 | 2020-06-10 12:27 | [5 empty] | 80 | 2020-06-10 12:27 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2019-12-23 17:40 | 2020-04-17 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 237 |  |  |  | 101248
2688 | Task(Task)-->E (Engineering) | OVERALL SINGLE LINE DIAGRAM(SLD) FOR CHP |  | 1.24.1.3 | Unscheduled | No | No | 2019-11-08 18:00 | 2019-12-27 17:40 | 2019-11-15 18:00 | 2020-04-28 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-1L-5003 |  | 2020-02-13 11:44 | 7012-155-PVE-P-003 |  |  |  | A |  |  |  | 1.4825 | 0.001122 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5048 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-11-08 18:00 | 2019-11-15 18:00 |  | 10 | 2019-11-15 23:31 |  |  | 2019-11-19 17:40 | 2019-11-30 18:00 |  | 30 | 2019-11-30 23:31 |  |  | 2019-11-25 17:40 | 2019-11-30 18:00 |  | 35 | 2019-11-30 23:31 |  |  | 2019-11-30 23:59 | 2019-12-03 18:00 |  | 65 | 2019-12-03 23:31 |  |  | 2019-12-06 17:40 | 2019-12-11 18:00 |  | 80 | 2019-12-11 23:31 | [5 empty] | 80 | 2020-04-18 12:55 | [5 empty] | 80 | 2020-04-18 12:55 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2019-12-27 17:40 | 2020-04-28 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 238 |  |  |  | 101249
2689 | Task(Task)-->E (Engineering) | HT & LT CABLE SIZING CALCULATION FOR CHP |  | 1.24.1.3 | Unscheduled | No | No | 2019-11-15 18:00 | 2019-12-30 17:40 | 2019-11-20 18:00 | 2020-05-04 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DC-5004 |  | 2020-02-13 11:44 | 7012-155-PVE-U-004 |  |  |  | A |  |  |  | 4.4474 | 0.003365 | 0.33 | Plan & Actual | Date |  | 0 | 0 | 0 | 124.21 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5052 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-11-15 18:00 | 2019-11-20 18:00 |  | 10 | 2019-11-20 23:31 |  |  | 2019-11-21 17:40 | 2019-12-05 18:00 |  | 30 | 2019-12-05 23:31 |  |  | 2019-11-27 17:40 | 2019-12-05 18:00 |  | 35 | 2019-12-05 23:31 |  |  | 2019-12-03 23:59 | 2019-12-11 18:00 |  | 65 | 2019-12-11 23:31 |  |  | 2019-12-09 17:40 | 2019-12-27 18:00 |  | 80 | 2019-12-27 23:31 | [5 empty] | 80 | 2020-04-21 19:50 | [5 empty] | 80 | 2020-04-21 19:50 | [5 empty] | 80 | 2020-07-28 16:00 | [5 empty] | 80 | 2020-07-28 16:00 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2019-12-30 17:40 | 2020-05-04 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 239 |  |  |  | 101250
2690 | Task(Task)-->E (Engineering) | LIGHTING DESIGN MEMORANDUM FOR CHP |  | 1.24.1.3 | Unscheduled | No | No | 2019-11-11 18:00 | 2019-12-26 17:40 | 2019-11-13 18:00 | 2020-05-06 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-BE-5005 |  | 2020-02-13 11:44 | 7012-155-PVE-U-005 |  |  |  | A |  |  |  | 2.965 | 0.002243 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 82.54 | 0 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5053 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-11-11 18:00 | 2019-11-13 18:00 |  | 10 | 2019-11-13 23:31 |  |  | 2019-11-18 17:40 | 2019-11-28 18:00 |  | 30 | 2019-11-28 23:31 |  |  | 2019-11-23 17:40 | 2019-11-28 18:00 |  | 35 | 2019-11-28 23:31 |  |  | 2019-11-29 23:59 | 2019-11-30 18:00 |  | 65 | 2019-11-30 23:31 |  |  | 2019-12-05 17:40 | 2019-12-11 18:00 |  | 80 | 2019-12-11 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2019-12-26 17:40 | 2020-05-06 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 240 |  |  |  | 101251
2691 | Task(Task)-->E (Engineering) | 110V DC BATTERY & BATTERY CHARGER SIZING CALCULATION FOR CHP |  | 1.24.1.3 | Unscheduled | No | No | 2019-11-14 18:00 | 2020-01-02 17:40 | 2019-11-25 18:00 | 2020-05-01 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DC-5006 |  | 2020-02-13 11:44 | 7012-155-PVE-U-006 |  |  |  | A |  |  |  | 2.965 | 0.002243 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 82.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5054 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-11-14 18:00 | 2019-11-25 18:00 |  | 10 | 2019-11-25 23:31 |  |  | 2019-11-25 17:40 | 2019-12-10 18:00 |  | 30 | 2019-12-10 23:31 |  |  | 2019-11-30 17:40 | 2019-12-10 18:00 |  | 35 | 2019-12-10 23:31 |  |  | 2019-12-06 23:59 | 2019-12-13 18:00 |  | 65 | 2019-12-13 23:31 |  |  | 2019-12-12 17:40 | 2019-12-30 18:00 |  | 80 | 2019-12-30 23:31 | [5 empty] | 80 | 2020-04-18 14:35 | [5 empty] | 80 | 2020-04-18 14:35 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-01-02 17:40 | 2020-05-01 18:00 |  | 100 | 2020-04-28 23:31 | [121 empty] | Varun Parihari | [21 empty] | 241 |  |  |  | 101252
2692 | Task(Task)-->E (Engineering) | DC DISTRIBUTION DIAGRAM FOR CHP |  | 1.24.1.3 | Unscheduled | No | No | 2019-11-18 18:00 | 2020-01-06 17:40 | 2019-11-27 18:00 | 2020-05-08 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-1L-5007 |  | 2020-02-13 11:44 | 7012-155-PVE-P-007 |  |  |  | A |  |  |  | 1.4825 | 0.001122 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5049 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-11-18 18:00 | 2019-11-27 18:00 |  | 10 | 2019-11-27 23:31 |  |  | 2019-11-28 17:40 | 2019-12-12 18:00 |  | 30 | 2019-12-12 23:31 |  |  | 2019-12-04 17:40 | 2019-12-12 18:00 |  | 35 | 2019-12-12 23:31 |  |  | 2019-12-10 23:59 | 2019-12-17 18:00 |  | 65 | 2019-12-17 23:31 |  |  | 2019-12-16 17:40 | 2019-12-30 18:00 |  | 80 | 2019-12-30 23:31 | [5 empty] | 80 | 2020-04-22 19:50 | [5 empty] | 80 | 2020-04-22 19:50 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-01-06 17:40 | 2020-05-08 18:00 |  | 100 | 2020-05-01 23:31 | [121 empty] | Varun Parihari | [21 empty] | 242 |  |  |  | 101253
2693 | Task(Task)-->E (Engineering) | EARTHING & LIGHTNING PROTECTION CALCULATION FOR CHP |  | 1.24.1.3 | Unscheduled | No | No | 2019-11-24 23:59 | 2020-01-11 17:40 | 2019-12-04 18:00 | 2020-05-14 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-BE-5008 |  | 2020-02-13 11:44 | 7012-155-PVE-U-008 |  |  |  | A |  |  |  | 2.965 | 0.002243 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 82.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5055 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-11-24 23:59 | 2019-12-04 18:00 |  | 10 | 2019-12-04 23:31 |  |  | 2019-12-04 17:40 | 2019-12-19 18:00 |  | 30 | 2019-12-19 23:31 |  |  | 2019-12-10 17:40 | 2019-12-19 18:00 |  | 35 | 2019-12-19 23:31 |  |  | 2019-12-16 23:59 | 2019-12-27 18:00 |  | 65 | 2019-12-27 23:31 |  |  | 2019-12-21 17:40 | 2020-01-03 18:00 |  | 80 | 2020-01-03 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | 2020-08-03 13:34 | [5 empty] | 80 | 2020-08-03 13:34 | [5 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-01-11 17:40 | 2020-05-14 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 243 |  |  |  | 101254
2694 | Task(Task)-->E (Engineering) | TYPICAL EQUIPMENT EARTHING DETAILS AND LIGHTNING PROTECTION DETAILS FOR CHP |  | 1.24.1.3 | Unscheduled | No | No | 2019-11-21 18:00 | 2020-01-15 17:40 | 2019-12-20 18:00 | 2020-05-18 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-BE-5009 |  | 2020-02-13 11:44 | 7012-155-PVE-F-009 |  |  |  | A |  |  |  | 1.4825 | 0.001122 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5045 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-11-21 18:00 | 2019-12-20 18:00 |  | 10 | 2019-12-20 23:31 |  |  | 2019-12-07 17:40 | 2020-01-10 18:00 |  | 30 | 2020-01-10 23:31 |  |  | 2019-12-13 17:40 | 2020-01-10 18:00 |  | 35 | 2020-01-10 23:31 |  |  | 2019-12-19 23:59 | 2020-01-16 18:00 |  | 65 | 2020-01-16 23:31 |  |  | 2019-12-25 17:40 | 2020-01-24 18:00 |  | 80 | 2020-01-24 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-01-15 17:40 | 2020-05-18 18:00 |  | 100 | 2020-05-11 23:31 | [121 empty] | Varun Parihari | [21 empty] | 244 |  |  |  | 101255
2695 | Task(Task)-->E (Engineering) | NGR SIZING CALCULATION FOR CHP |  | 1.24.1.3 | Unscheduled | No | No | 2019-12-07 18:00 | 2020-01-20 17:40 | 2019-12-08 23:59 | 2019-12-27 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DC-5010 |  | 2020-02-13 11:44 | 7012-155-PVE-U-010 |  |  |  | A |  |  |  | 0.26954 | 0.000204 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 8.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5056 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-12-07 18:00 | 2019-12-08 23:59 |  | 10 | 2019-12-08 23:31 |  |  | 2019-12-12 17:40 | 2019-12-15 23:59 |  | 30 | 2019-12-15 23:31 |  |  | 2019-12-18 17:40 | 2019-12-15 23:59 |  | 35 | 2019-12-15 23:31 |  |  | 2019-12-24 23:59 | 2019-12-18 18:00 |  | 65 | 2019-12-18 23:31 |  |  | 2019-12-30 17:40 | 2019-12-27 18:00 |  | 80 | 2019-12-27 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-01-20 17:40 | 2019-12-27 18:00 |  | 100 | 2019-12-27 23:31 | [121 empty] | Varun Parihari | [21 empty] | 245 |  |  |  | 101256
2696 | Task(Task)-->E (Engineering) | OVERALL EARTHING & LIGHTNING PROTECTION LAYOUT FOR CHP |  | 1.24.1.3 | Unscheduled | No | No | 2019-11-29 18:00 | 2020-01-23 17:40 | 2020-02-25 18:00 | 2020-05-12 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-BE-5012 |  | 2020-02-13 11:44 | 7012-155-PVE-W-012 |  |  |  | A |  |  |  | 6.0647 | 0.004588 | 0.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 165.48 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5059 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-11-29 18:00 | 2020-02-25 18:00 |  | 10 | 2020-02-25 23:31 |  |  | 2019-12-16 17:40 | 2020-03-14 18:00 |  | 30 | 2020-03-14 23:31 |  |  | 2019-12-21 17:40 | 2020-03-19 18:00 |  | 35 | 2020-03-19 23:31 |  |  | 2019-12-27 23:59 | 2020-03-19 18:00 |  | 65 | 2020-03-19 23:31 |  |  | 2020-01-02 17:40 | 2020-04-09 18:00 |  | 80 | 2020-04-21 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-01-23 17:40 | 2020-05-12 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 247 |  |  |  | 101258
2697 | Task(Task)-->E (Engineering) | OVERALL CABLE ROUTING LAYOUT FOR CHP |  | 1.24.1.3 | Unscheduled | No | No | 2020-01-06 18:00 | 2020-03-03 17:40 | 2020-04-16 18:00 | 2020-06-04 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5051 |  | 2020-02-13 11:44 | 7012-155-PVE-F-013 |  |  |  | A |  |  |  | 6.0647 | 0.004588 | 0.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 165.48 | 0 | 43 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5046 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-06 18:00 | 2020-04-16 18:00 |  | 10 | 2020-04-16 23:31 |  |  | 2020-01-22 17:40 | 2020-04-30 18:00 |  | 30 | 2020-04-22 23:31 |  |  | 2020-01-28 17:40 | 2020-05-07 18:00 |  | 35 | 2020-04-30 23:31 |  |  | 2020-02-03 23:59 | 2020-05-14 18:00 |  | 65 | 2020-05-15 23:31 |  |  | 2020-02-10 17:40 | 2020-06-04 18:00 |  | 80 | 2020-05-29 23:31 | [5 empty] | 80 | 2020-08-19 16:45 | [5 empty] | 80 | 2020-08-19 16:45 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-03 17:40 | 2020-06-04 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 248 |  |  |  | 101259
2698 | Task(Task)-->E (Engineering) | POWER CABLE SCHEDULE |  | 1.24.1.3 | Unscheduled | No | No | 2020-03-24 18:00 | 2020-05-13 17:40 | 2020-04-11 18:00 | 2020-05-23 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5074 |  | 2020-02-13 11:44 | 7012-155-PVE-W-036 |  |  |  | A |  |  |  | 14.9596 | 0.011317 | 1.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 414.29 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5060 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-24 18:00 | 2020-04-11 18:00 |  | 10 | 2020-04-05 23:31 |  |  | 2020-04-01 17:40 | 2020-04-18 18:00 |  | 30 | 2020-04-18 23:31 |  |  | 2020-04-07 17:40 | 2020-04-25 18:00 |  | 35 | 2020-04-25 23:31 |  |  | 2020-04-14 23:59 | 2020-05-02 18:00 |  | 65 | 2020-05-12 23:31 |  |  | 2020-04-20 17:40 | 2020-05-23 18:00 |  | 80 | 2020-06-17 13:13 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-13 17:40 | 2020-05-23 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 271 |  |  |  | 101282
2699 | Task(Task)-->E (Engineering) | RELAY SETTING CALCULATION & CO-ORDINATION FOR CHP. |  | 1.24.1.3 | Unscheduled | No | No | 2020-05-09 18:00 | 2020-06-29 17:40 | 2020-09-29 18:00 | 2020-11-10 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5075 |  | 2020-02-13 11:44 | 7012-155-PVE-U-037 |  |  |  | A |  |  |  | 11.9946 | 0.009074 | 0.89 | Plan & Actual | Date |  | 0 | 0 | 0 | 331.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5057 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-05-09 18:00 | 2020-09-29 18:00 |  | 10 |  |  |  | 2020-05-18 17:40 | 2020-10-06 18:00 |  | 30 |  |  |  | 2020-05-25 17:40 | 2020-10-13 18:00 |  | 35 |  |  |  | 2020-05-30 23:59 | 2020-10-20 18:00 |  | 65 |  |  |  | 2020-06-05 17:40 | 2020-11-10 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-29 17:40 | 2020-11-10 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 272 |  |  |  | 101283
2700 | Task(Task)-->E (Engineering) | OVERALL LIGHTING LAYOUT FOR APPROACH ROAD & LIGHTING MAST AREA. |  | 1.24.1.3 | Unscheduled | No | No | 2020-04-24 18:00 | 2020-06-12 17:40 | 2020-04-14 09:00 | 2020-06-07 23:59 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5076 |  | 2020-02-13 11:44 | 7012-155-PVE-G-038 |  |  |  | A |  |  |  | 2.965 | 0.002243 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 82.54 | 0 | 24.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5047 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-24 18:00 | 2020-04-26 23:59 |  | 10 | 2020-04-04 23:31 |  |  | 2020-05-02 17:40 | 2020-05-03 23:59 |  | 30 | 2020-04-10 23:31 |  |  | 2020-05-08 17:40 | 2020-05-10 23:59 |  | 35 | 2020-04-14 23:31 |  |  | 2020-05-15 23:59 | 2020-05-17 23:59 |  | 65 | 2020-04-14 23:31 |  |  | 2020-05-21 17:40 | 2020-06-07 23:59 |  | 80 | 2020-04-23 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-12 17:40 | 2020-06-07 23:59 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 273 |  |  |  | 101284
2701 | Task(Task)-->E (Engineering) | HT CABLE DATA SHEET |  | 1.24.1.3 | Unscheduled | No | No | 2020-02-26 18:00 | 2020-04-08 17:40 | 2020-06-21 23:59 | 2020-08-17 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-164 |  | 2020-02-13 11:46 | 7012-155-PVE-Y-109 |  |  |  | A |  |  |  | 0.80863 | 0.000612 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5081 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-26 18:00 | 2020-06-21 23:59 |  | 10 |  |  |  | 2020-02-27 17:40 | 2020-06-28 23:59 |  | 30 |  |  |  | 2020-03-04 17:40 | 2020-07-04 18:00 |  | 35 |  |  |  | 2020-03-10 23:59 | 2020-07-04 18:00 |  | 65 |  |  |  | 2020-03-17 17:40 | 2020-07-25 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-08 17:40 | 2020-07-25 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 344 |  |  |  | 101355
2702 | Task(Task)-->E (Engineering) | LT POWER CABLE DATA SHEET |  | 1.24.1.3 | Unscheduled | No | No | 2020-03-17 17:40 | 2020-04-28 17:40 | 2020-06-21 23:59 | 2020-08-17 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-165 |  | 2020-02-13 11:46 | 7012-155-PVE-Y-110 |  |  |  | A |  |  |  | 0.80863 | 0.000612 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5082 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-18 18:00 | 2020-06-21 23:59 |  | 10 |  |  |  | 2020-03-17 17:40 | 2020-06-28 23:59 |  | 30 |  |  |  | 2020-03-23 17:40 | 2020-07-03 18:00 |  | 35 |  |  |  | 2020-03-30 23:59 | 2020-07-03 18:00 |  | 65 |  |  |  | 2020-04-04 17:40 | 2020-07-24 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-28 17:40 | 2020-07-24 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 345 |  |  |  | 101356
2703 | Task(Task)-->E (Engineering) | GAD, DATA SHEET & BOM OF 110V DC BATTERY FOR CHP |  | 1.24.1.3 | Unscheduled | No | No | 2020-04-01 17:40 | 2020-05-13 17:40 | 2020-06-21 23:59 | 2020-08-18 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-166 |  | 2020-02-13 11:46 | 7012-155-PVE-W-111 |  |  |  | A |  |  |  | 1.4825 | 0.001122 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5061 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-02 18:00 | 2020-06-21 23:59 |  | 10 |  |  |  | 2020-04-01 17:40 | 2020-06-28 23:59 |  | 30 |  |  |  | 2020-04-07 17:40 | 2020-07-03 18:00 |  | 35 |  |  |  | 2020-04-14 23:59 | 2020-07-03 18:00 |  | 65 |  |  |  | 2020-04-20 17:40 | 2020-07-24 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-13 17:40 | 2020-07-24 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 346 |  |  |  | 101357
2704 | Task(Task)-->E (Engineering) | GAD, DATA SHEET, WIRING DIAGRAM & BOM OF 110V DC BATTERY CHARGER FOR CHP |  | 1.24.1.3 | Unscheduled | No | No | 2020-04-01 17:40 | 2020-05-13 17:40 | 2020-06-21 23:59 | 2020-07-31 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-167 |  | 2020-02-13 11:46 | 7012-155-PVE-W-112 |  |  |  | A |  |  |  | 1.4825 | 0.001122 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5062 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-02 18:00 | 2020-06-21 23:59 |  | 10 |  |  |  | 2020-04-01 17:40 | 2020-06-28 23:59 |  | 30 |  |  |  | 2020-04-07 17:40 | 2020-07-03 18:00 |  | 35 |  |  |  | 2020-04-14 23:59 | 2020-07-03 18:00 |  | 65 | 2020-07-28 13:22 |  |  | 2020-04-20 17:40 | 2020-07-24 18:00 |  | 80 | 2020-08-03 10:02 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-13 17:40 | 2020-07-24 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 347 |  |  |  | 101358
2705 | Task(Task)-->E (Engineering) | GA, SLD,WIRING DIAGRAM & BOM OF MLDB |  | 1.24.1.3 | Unscheduled | No | No | 2020-03-24 17:40 | 2020-05-05 17:40 | 2020-06-30 18:00 | 2020-09-01 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-168 |  | 2020-02-13 11:46 | 7012-155-PVE-W-113 |  |  |  | A |  |  |  | 1.4825 | 0.001122 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5063 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-24 18:00 | 2020-06-30 18:00 |  | 10 |  |  |  | 2020-03-24 17:40 | 2020-07-07 18:00 |  | 30 |  |  |  | 2020-03-31 17:40 | 2020-07-13 18:00 |  | 35 |  |  |  | 2020-04-06 23:59 | 2020-07-13 18:00 |  | 65 |  |  |  | 2020-04-13 17:40 | 2020-08-03 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-05 17:40 | 2020-08-03 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 348 |  |  |  | 101359
2706 | Task(Task)-->E (Engineering) | GA,SLD,WIRING DIAGRAM & BOM OF AC & DC LIGHTING PANELS |  | 1.24.1.3 | Unscheduled | No | No | 2020-04-15 17:40 | 2020-05-27 17:40 | 2020-06-30 18:00 | 2020-10-15 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-169 |  | 2020-02-13 11:46 | 7012-155-PVE-W-114 |  |  |  | A |  |  |  | 1.4825 | 0.001122 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5064 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-15 18:00 | 2020-06-30 18:00 |  | 10 |  |  |  | 2020-04-15 17:40 | 2020-07-07 18:00 |  | 30 |  |  |  | 2020-04-21 17:40 | 2020-07-13 18:00 |  | 35 |  |  |  | 2020-04-28 23:59 | 2020-07-13 18:00 |  | 65 |  |  |  | 2020-05-04 17:40 | 2020-08-03 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-27 17:40 | 2020-08-03 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 349 |  |  |  | 101360
2707 | Task(Task)-->E (Engineering) | GAD,SLD, WIRING DIAGRAM & BOM OF DCDB AND DC LDB |  | 1.24.1.3 | Unscheduled | No | No | 2020-03-18 17:40 | 2020-04-29 17:40 | 2020-06-30 18:00 | 2020-09-03 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-170 |  | 2020-02-13 11:46 | 7012-155-PVE-W-115 |  |  |  | A |  |  |  | 1.4825 | 0.001122 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5065 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-18 18:00 | 2020-06-30 18:00 |  | 10 |  |  |  | 2020-03-18 17:40 | 2020-07-07 18:00 |  | 30 |  |  |  | 2020-03-24 17:40 | 2020-07-13 18:00 |  | 35 |  |  |  | 2020-03-31 23:59 | 2020-07-13 18:00 |  | 65 |  |  |  | 2020-04-06 17:40 | 2020-08-03 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-29 17:40 | 2020-08-03 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 350 |  |  |  | 101361
2708 | Task(Task)-->E (Engineering) | GAD,SLD, WIRING DIAGRAM & BOM OF AC MCCB BOX |  | 1.24.1.3 | Unscheduled | No | No | 2020-05-05 17:40 | 2020-06-16 17:40 | 2020-06-30 18:00 | 2020-08-21 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-171 |  | 2020-02-13 11:46 | 7012-155-PVE-W-116 |  |  |  | A |  |  |  | 1.4825 | 0.001122 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5066 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-05-05 18:00 | 2020-06-30 18:00 |  | 10 |  |  |  | 2020-05-05 17:40 | 2020-07-07 18:00 |  | 30 |  |  |  | 2020-05-12 17:40 | 2020-07-13 18:00 |  | 35 |  |  |  | 2020-05-18 23:59 | 2020-07-13 18:00 |  | 65 |  |  |  | 2020-05-25 17:40 | 2020-08-03 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-16 17:40 | 2020-08-03 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 351 |  |  |  | 101362
2709 | Task(Task)-->E (Engineering) | GAD & DATA SHEET OF CABLE TRAY & ACCESSORIES |  | 1.24.1.3 | Unscheduled | No | No | 2020-03-05 17:40 | 2020-04-16 17:40 | 2020-06-21 23:59 | 2020-07-27 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-172 |  | 2020-02-13 11:46 | 7012-155-PVE-W-117 |  |  |  | A |  |  |  | 1.4825 | 0.001122 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5067 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-06 18:00 | 2020-06-21 23:59 |  | 10 |  |  |  | 2020-03-05 17:40 | 2020-06-28 23:59 |  | 30 |  |  |  | 2020-03-11 17:40 | 2020-07-03 18:00 |  | 35 |  |  |  | 2020-03-18 23:59 | 2020-07-03 18:00 |  | 65 | 2020-07-28 13:21 |  |  | 2020-03-24 17:40 | 2020-07-24 18:00 |  | 80 | 2020-07-28 17:51 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-16 17:40 | 2020-07-24 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 352 |  |  |  | 101363
2710 | Task(Task)-->E (Engineering) | GAD AND DATA SHEET OF LPBS |  | 1.24.1.3 | Unscheduled | No | No | 2020-05-07 17:40 | 2020-06-18 17:40 | 2020-06-21 23:59 | 2020-08-12 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-173 |  | 2020-02-13 11:46 | 7012-155-PVE-W-118 |  |  |  | A |  |  |  | 1.4825 | 0.001122 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5068 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-05-07 18:00 | 2020-06-21 23:59 |  | 10 |  |  |  | 2020-05-07 17:40 | 2020-06-28 23:59 |  | 30 |  |  |  | 2020-05-14 17:40 | 2020-07-04 18:00 |  | 35 |  |  |  | 2020-05-20 23:59 | 2020-07-04 18:00 |  | 65 |  |  |  | 2020-05-27 17:40 | 2020-07-25 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-18 17:40 | 2020-07-25 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 353 |  |  |  | 101364
2711 | Task(Task)-->E (Engineering) | GA DRAWING & WIRING DIAGRAM FOR RECEPTACLES |  | 1.24.1.3 | Unscheduled | No | No | 2020-03-26 18:00 | 2020-05-11 17:40 | 2020-06-21 23:59 | 2020-07-28 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-174 |  | 2020-02-13 11:46 | 7012-155-PVE-W-119 |  |  |  | A |  |  |  | 1.4825 | 0.001122 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5069 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-26 18:00 | 2020-06-21 23:59 |  | 10 |  |  |  | 2020-03-30 17:40 | 2020-06-28 23:59 |  | 30 |  |  |  | 2020-04-04 17:40 | 2020-07-06 18:00 |  | 35 |  |  |  | 2020-04-10 23:59 | 2020-07-06 18:00 |  | 65 | 2020-07-28 13:21 |  |  | 2020-04-17 17:40 | 2020-07-27 18:00 |  | 80 | 2020-08-03 10:01 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-11 17:40 | 2020-07-27 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 354 |  |  |  | 101365
2712 | Task(Task)-->E (Engineering) | GA & DATA SHEET FOR LIGHTING FIXTURES |  | 1.24.1.3 | Unscheduled | No | No | 2020-04-28 17:40 | 2020-06-08 17:40 | 2020-06-21 23:59 | 2020-08-17 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-175 |  | 2020-02-13 11:46 | 7012-155-PVE-W-120 |  |  |  | A |  |  |  | 1.4825 | 0.001122 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5070 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-28 18:00 | 2020-06-21 23:59 |  | 10 |  |  |  | 2020-04-28 17:40 | 2020-06-28 23:59 |  | 30 |  |  |  | 2020-05-04 17:40 | 2020-07-04 18:00 |  | 35 |  |  |  | 2020-05-11 23:59 | 2020-07-04 18:00 |  | 65 |  |  |  | 2020-05-16 17:40 | 2020-07-25 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-08 17:40 | 2020-07-25 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 355 |  |  |  | 101366
2713 | Task(Task)-->E (Engineering) | GA, SLD, WIRING DIAGRAM & BOM OF WDB |  | 1.24.1.3 | Unscheduled | No | No | 2020-04-04 17:40 | 2020-05-16 17:40 | 2020-05-10 23:59 | 2020-06-15 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-176 |  | 2020-02-13 11:46 | 7012-155-PVE-W-121 |  |  |  | A |  |  |  | 1.4825 | 0.001122 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5071 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-04 18:00 | 2020-05-10 23:59 |  | 10 | 2020-05-10 23:31 |  |  | 2020-04-04 17:40 | 2020-05-17 23:59 |  | 30 | 2020-05-17 23:31 |  |  | 2020-04-10 17:40 | 2020-05-23 18:00 |  | 35 | 2020-05-23 23:31 |  |  | 2020-04-17 23:59 | 2020-05-23 18:00 |  | 65 | 2020-06-10 09:49 |  |  | 2020-04-23 17:40 | 2020-06-13 18:00 |  | 80 | 2020-07-28 18:04 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-16 17:40 | 2020-06-13 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 356 |  |  |  | 101367
2714 | Task(Task)-->E (Engineering) | GA, DATA SHEET OF NGR |  | 1.24.1.3 | Unscheduled | No | No | 2020-02-04 17:40 | 2020-03-17 17:40 | 2020-03-06 18:00 | 2020-05-22 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-177 |  | 2020-02-13 11:46 | 7012-155-PVE-W-122 |  |  |  | A |  |  |  | 1.4825 | 0.001122 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5072 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-05 18:00 | 2020-03-06 18:00 |  | 10 | 2020-03-06 23:31 |  |  | 2020-02-04 17:40 | 2020-03-21 18:00 |  | 30 | 2020-03-21 23:31 |  |  | 2020-02-11 17:40 | 2020-03-21 18:00 |  | 35 | 2020-04-21 23:31 |  |  | 2020-02-17 23:59 | 2020-04-25 18:00 |  | 65 | 2020-05-15 23:31 |  |  | 2020-02-24 17:40 | 2020-05-16 18:00 |  | 80 | 2020-05-22 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-17 17:40 | 2020-05-16 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 357 |  |  |  | 101368
2715 | Task(Task)-->E (Engineering) | GA DRAWINGS & DATA SHEET FOR HT CABLE TERMINATION KIT AND STRAIGHT THROUGH JOINT |  | 1.24.1.3 | Unscheduled | No | No | 2020-04-12 23:59 | 2020-05-25 17:40 | 2020-06-21 23:59 | 2020-10-15 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-178 |  | 2020-02-13 11:46 | 7012-155-PVE-W-123 |  |  |  | A |  |  |  | 0.80863 | 0.000612 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5073 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-12 23:59 | 2020-06-21 23:59 |  | 10 |  |  |  | 2020-04-13 17:40 | 2020-06-28 23:59 |  | 30 |  |  |  | 2020-04-18 17:40 | 2020-07-03 18:00 |  | 35 |  |  |  | 2020-04-24 23:59 | 2020-07-03 18:00 |  | 65 |  |  |  | 2020-05-01 17:40 | 2020-07-24 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-25 17:40 | 2020-07-24 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 358 |  |  |  | 101369
2716 | Task(Task)-->E (Engineering) | GA, BOM & WIRING DIAGRAM FOR BELT WATCH SYSTEM |  | 1.24.1.3 | Unscheduled | No | No | 2020-04-12 23:59 | 2020-05-25 17:40 | 2020-06-05 18:00 | 2020-08-21 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-179 |  | 2020-02-13 11:46 | 7012-155-PVE-W-124 |  |  |  | A |  |  |  | 1.4825 | 0.001122 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5074 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-12 23:59 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-04-13 17:40 | 2020-06-12 18:00 |  | 30 |  |  |  | 2020-04-18 17:40 | 2020-06-17 18:00 |  | 35 |  |  |  | 2020-04-24 23:59 | 2020-06-17 18:00 |  | 65 |  |  |  | 2020-05-01 17:40 | 2020-07-08 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-25 17:40 | 2020-07-08 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 359 |  |  |  | 101370
2717 | Task(Task)-->E (Engineering) | LIGHTING DESIGN CALCULATION FOR LIGHTING MAST |  | 1.24.1.3 | Unscheduled | No | No | 2020-03-09 17:40 | 2020-04-20 17:40 | 2020-06-05 18:00 | 2020-07-28 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-180 |  | 2020-02-13 11:46 | 7012-155-PVE-U-125 |  |  |  | A |  |  |  | 1.4825 | 0.001122 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 2.11 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5058 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-09 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-03-09 17:40 | 2020-06-12 18:00 |  | 30 |  |  |  | 2020-03-16 17:40 | 2020-06-17 18:00 |  | 35 |  |  |  | 2020-03-21 23:59 | 2020-06-17 18:00 |  | 65 | 2020-07-28 15:45 |  |  | 2020-03-27 17:40 | 2020-07-08 18:00 |  | 80 | 2020-07-28 17:45 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-20 17:40 | 2020-07-08 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 360 |  |  |  | 101371
2718 | Task(Task)-->E (Engineering) | GA, DATA SHEET, BOM & CIRCUIT DIAGRAM FOR LIGHTING MAST |  | 1.24.1.3 | Unscheduled | No | No | 2020-03-09 17:40 | 2020-04-20 17:40 | 2020-06-05 18:00 | 2020-07-12 23:59 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-181 |  | 2020-02-13 11:47 | 7012-155-PVE-W-126 |  |  |  | A |  |  |  | 1.4825 | 0.001122 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 4.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5075 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-09 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-03-09 17:40 | 2020-06-12 18:00 |  | 30 |  |  |  | 2020-03-16 17:40 | 2020-06-17 18:00 |  | 35 |  |  |  | 2020-03-21 23:59 | 2020-06-17 18:00 |  | 65 | 2020-08-03 12:01 |  |  | 2020-03-27 17:40 | 2020-07-08 18:00 |  | 80 | 2020-08-03 12:03 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-20 17:40 | 2020-07-08 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 361 |  |  |  | 101372
2719 | Task(Task)-->E (Engineering) | DATA SHEET OF FO CABLE FOR SCADA SYSTEM |  | 1.24.1.3 | Unscheduled | No | No | 2020-04-07 18:00 | 2020-05-20 17:40 | 2020-06-21 23:59 | 2020-08-21 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-182 |  | 2020-02-13 11:47 | 7012-155-PVE-Y-127 |  |  |  | A |  |  |  | 0.26954 | 0.000204 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 8.17 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5083 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-07 18:00 | 2020-06-21 23:59 |  | 10 |  |  |  | 2020-04-08 17:40 | 2020-06-28 23:59 |  | 30 |  |  |  | 2020-04-15 17:40 | 2020-07-05 23:59 |  | 35 |  |  |  | 2020-04-21 23:59 | 2020-07-05 23:59 |  | 65 |  |  |  | 2020-04-28 17:40 | 2020-07-26 23:59 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-20 17:40 | 2020-07-26 23:59 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 362 |  |  |  | 101373
2720 | Task(Task)-->E (Engineering) | GA & SCHEME ,BOM FOR DATA CONCENTRATOR PANEL |  | 1.24.1.3 | Unscheduled | No | No | 2020-03-13 17:40 | 2020-04-24 17:40 | 2020-06-21 23:59 | 2020-09-16 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-183 |  | 2020-02-13 11:47 | 7012-155-PVE-W-128 |  |  |  | A |  |  |  | 0.26954 | 0.000204 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 8.17 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5076 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-13 18:00 | 2020-06-21 23:59 |  | 10 |  |  |  | 2020-03-13 17:40 | 2020-06-28 23:59 |  | 30 |  |  |  | 2020-03-20 17:40 | 2020-07-04 18:00 |  | 35 |  |  |  | 2020-03-26 23:59 | 2020-07-04 18:00 |  | 65 |  |  |  | 2020-04-02 17:40 | 2020-07-25 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-24 17:40 | 2020-07-25 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 363 |  |  |  | 101374
2721 | Task(Task)-->E (Engineering) | NETWORK CONFIGURATION DWG FOR PROCESS LAN |  | 1.24.1.3 | Unscheduled | No | No | 2020-03-13 17:40 | 2020-04-24 17:40 | 2020-06-05 18:00 | 2020-09-16 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-184 |  | 2020-02-13 11:47 | 7012-155-PVE-W-129 |  |  |  | A |  |  |  | 0.80863 | 0.000612 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5077 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-14 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-03-13 17:40 | 2020-06-12 18:00 |  | 30 |  |  |  | 2020-03-20 17:40 | 2020-06-17 18:00 |  | 35 |  |  |  | 2020-03-26 23:59 | 2020-06-17 18:00 |  | 65 |  |  |  | 2020-04-02 17:40 | 2020-07-08 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-24 17:40 | 2020-07-08 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 364 |  |  |  | 101375
2722 | Task(Task)-->E (Engineering) | FAT PROCEDURE FOR MMI SYSTEM/DATA CONCENTRATOR |  | 1.24.1.3 | Unscheduled | No | No | 2020-03-12 18:00 | 2020-04-24 17:40 | 2020-06-05 18:00 | 2020-09-16 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-185 |  | 2020-02-13 11:47 | 7012-155-PVE-W-130 |  |  |  | A |  |  |  | 0.80863 | 0.000612 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5078 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-12 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-03-13 17:40 | 2020-06-12 18:00 |  | 30 |  |  |  | 2020-03-20 17:40 | 2020-06-19 18:00 |  | 35 |  |  |  | 2020-03-26 23:59 | 2020-06-19 18:00 |  | 65 |  |  |  | 2020-04-02 17:40 | 2020-07-10 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-24 17:40 | 2020-07-10 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 365 |  |  |  | 101376
2723 | Task(Task)-->E (Engineering) | GA & DATA SHEET OF RUBBER MATS |  | 1.24.1.3 | Unscheduled | No | No | 2020-07-12 23:59 | 2020-08-24 17:40 | 2020-06-29 09:00 | 2020-09-02 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-187 |  | 2020-02-13 11:47 | 7012-155-PVE-W-132 |  |  |  | I |  |  |  | 0.26954 | 0.000204 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 8.17 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5079 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-07-12 23:59 | 2020-07-31 18:00 |  | 10 |  |  |  | 2020-07-13 17:40 | 2020-08-07 18:00 |  | 30 |  |  |  | 2020-07-18 17:40 | 2020-08-12 18:00 |  | 35 |  |  |  | 2020-07-24 23:59 | 2020-08-12 18:00 |  | 65 | 2020-07-28 15:43 |  |  | 2020-07-31 17:40 | 2020-09-02 18:00 |  | 80 | 2020-08-03 10:01 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-08-24 17:40 | 2020-09-02 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 367 |  |  |  | 101378
2724 | Task(Task)-->E (Engineering) | GA DRAWING OF LIGHTING POLE |  | 1.24.1.3 | Unscheduled | No | No | 2020-07-12 23:59 | 2020-08-24 17:40 | 2020-06-21 23:59 | 2020-07-24 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-188 |  | 2020-02-13 11:47 | 7012-155-PVE-B-133 |  |  |  | I |  |  |  | 0.26954 | 0.000204 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 8.17 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5044 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-07-12 23:59 | 2020-06-21 23:59 |  | 10 |  |  |  | 2020-07-13 17:40 | 2020-06-28 23:59 |  | 30 |  |  |  | 2020-07-18 17:40 | 2020-07-03 18:00 |  | 35 |  |  |  | 2020-07-24 23:59 | 2020-07-03 18:00 |  | 65 | 2020-07-28 15:42 |  |  | 2020-07-31 17:40 | 2020-07-24 18:00 |  | 80 | 2020-07-28 17:46 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-08-24 17:40 | 2020-07-24 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 368 |  |  |  | 101379
2725 | Task(Task)-->E (Engineering) | DATA SHEET OF GLANDS & LUGS |  | 1.24.1.3 | Unscheduled | No | No | 2020-07-09 18:00 | 2020-08-24 17:40 | 2020-07-31 18:00 | 2020-09-05 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-189 |  | 2020-02-13 11:47 | 7012-155-PVE-Y-134 |  |  |  | I |  |  |  | 0.26954 | 0.000204 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 8.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5084 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-07-09 18:00 | 2020-07-31 18:00 |  | 10 |  |  |  | 2020-07-13 17:40 | 2020-08-07 18:00 |  | 30 |  |  |  | 2020-07-18 17:40 | 2020-08-15 18:00 |  | 35 |  |  |  | 2020-07-24 23:59 | 2020-08-15 18:00 |  | 65 |  |  |  | 2020-07-31 17:40 | 2020-09-05 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-08-24 17:40 | 2020-09-05 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 369 |  |  |  | 101380
2726 | Task(Task)-->E (Engineering) | DATA SHEET OF TRE-FOIL CLAMPS |  | 1.24.1.3 | Unscheduled | No | No | 2020-07-13 17:40 | 2020-08-24 17:40 | 2020-06-21 23:59 | 2020-08-21 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-190 |  | 2020-02-13 11:47 | 7012-155-PVE-Y-135 |  |  |  | I |  |  |  | 0.26954 | 0.000204 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 8.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5085 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-07-13 18:00 | 2020-06-21 23:59 |  | 10 |  |  |  | 2020-07-13 17:40 | 2020-06-28 23:59 |  | 30 |  |  |  | 2020-07-18 17:40 | 2020-07-02 18:00 |  | 35 |  |  |  | 2020-07-24 23:59 | 2020-07-02 18:00 |  | 65 |  |  |  | 2020-07-31 17:40 | 2020-07-23 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-08-24 17:40 | 2020-07-23 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 370 |  |  |  | 101381
2727 | Task(Task)-->E (Engineering) | DATA SHEET OF EARTHING & LIGHTNING MATERIALS |  | 1.24.1.3 | Unscheduled | No | No | 2020-07-11 18:00 | 2020-08-24 17:40 | 2020-07-11 18:00 | 2020-08-14 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-408 |  | 2020-02-13 11:47 | 7012-155-PVE-W-144 |  |  |  | A |  |  |  | 1.4825 | 0.001122 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 8.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5080 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-07-11 18:00 | 2020-07-11 18:00 |  | 10 |  |  |  | 2020-07-13 17:40 | 2020-07-18 18:00 |  | 30 |  |  |  | 2020-07-18 17:40 | 2020-07-24 18:00 |  | 35 |  |  |  | 2020-07-24 23:59 | 2020-07-24 18:00 |  | 65 | 2020-07-28 15:44 |  |  | 2020-07-31 17:40 | 2020-08-14 18:00 |  | 80 | 2020-08-03 10:00 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-08-24 17:40 | 2020-08-14 18:00 |  | 100 | [122 empty] | Varun Parihari | [21 empty] | 379 |  |  |  | 101390
2728 | Task(Task)-->E (Engineering) | C&I | 1.24.1.4 | 1.24.1 | Work In Progress | No | No | 2019-10-16 18:00 | 2020-06-15 17:40 | 2019-10-19 18:00 | 2020-12-02 18:00 |  |  | 2020-02-21 14:08 |  |  |  | 100 | 73.102 | [15 empty] | 47.0481 | 0.10534 | 10.36 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5086 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1036143
2729 | Task(Task)-->E (Engineering) | TYPICAL IO LIST |  | 1.24.1.4 | Completed | No | No | 2019-10-16 18:00 | 2019-11-27 17:40 | 2019-11-29 09:00 | 2020-02-07 18:00 |  |  | 2020-02-21 14:08 | 2020-06-19 12:13 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-BE-001 |  | 2020-02-13 11:48 | 7012-155-PVI-G-001 |  |  |  | A |  |  |  | 0.61224 | 0.000645 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 22.03 | 0 | 0.14 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5096 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-10-16 18:00 | 2019-10-19 18:00 |  | 10 | 2019-10-19 23:31 |  |  | 2019-10-19 17:40 | 2019-10-25 18:00 |  | 30 | 2019-10-25 23:31 |  |  | 2019-10-25 17:40 | 2019-10-30 18:00 |  | 35 | 2019-10-30 23:31 |  |  | 2019-10-31 23:59 | 2019-11-29 18:00 |  | 65 | 2019-11-29 23:31 |  |  | 2019-11-06 17:40 | 2019-12-27 18:00 |  | 80 | 2019-12-27 23:31 | [5 empty] | 80 | 2020-06-01 16:00 | [5 empty] | 80 | 2020-06-01 16:00 | [5 empty] | 80 | 2020-06-03 15:01 | [5 empty] | 80 | 2020-06-03 15:01 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2019-11-27 17:40 | 2020-02-21 18:00 |  | 100 | 2020-05-01 23:31 | [121 empty] | Subhrajyoti Ghosh | [21 empty] | 406 |  |  |  | 101418
2730 | Task(Task)-->E (Engineering) | CCTV SYSTEM CONFIGURATION DIAGRAM |  | 1.24.1.4 | Unscheduled | No | No | 2019-10-17 18:00 | 2019-11-27 17:40 | 2019-10-19 18:00 | 2020-03-12 18:00 |  |  | 2020-02-21 14:08 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-BE-003 |  | 2020-02-13 11:48 | 7012-155-PVI-Q-003 |  |  |  | A |  |  |  | 0.61224 | 0.000645 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 22.03 | 0 | 0.07 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5105 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-10-17 18:00 | 2019-10-19 18:00 |  | 10 | 2019-10-19 23:31 |  |  | 2019-10-19 17:40 | 2019-10-21 18:00 |  | 30 | 2019-10-21 23:31 |  |  | 2019-10-25 17:40 | 2019-10-31 18:00 |  | 35 | 2019-10-31 23:31 |  |  | 2019-10-31 23:59 | 2019-12-19 18:00 |  | 65 | 2019-12-19 23:31 |  |  | 2019-11-06 17:40 | 2020-01-30 18:00 |  | 80 | 2020-01-30 23:31 | [5 empty] | 80 | 2020-06-01 11:50 | [5 empty] | 80 | 2020-06-01 11:50 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2019-11-27 17:40 | 2020-03-12 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [21 empty] | 408 |  |  |  | 101420
2731 | Task(Task)-->E (Engineering) | PA SYSTEM CONFIGURATION DIAGRAM |  | 1.24.1.4 | Unscheduled | No | No | 2019-10-19 17:40 | 2019-11-27 17:40 | 2019-12-08 23:59 | 2020-03-17 18:00 |  |  | 2020-02-21 14:08 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-BE-004 |  | 2020-02-13 11:48 | 7012-155-PVI-Q-004 |  |  |  | A |  |  |  | 0.61224 | 0.000645 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 22.03 | 0 | 0.09 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5106 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-10-19 18:00 | 2019-12-08 23:59 |  | 10 | 2019-12-08 23:31 |  |  | 2019-10-19 17:40 | 2019-12-14 18:00 |  | 30 | 2019-12-14 23:31 |  |  | 2019-10-25 17:40 | 2019-12-17 18:00 |  | 35 | 2019-12-17 23:31 |  |  | 2019-10-31 23:59 | 2019-12-20 18:00 |  | 65 | 2019-12-20 23:31 |  |  | 2019-11-06 17:40 | 2020-01-30 18:00 |  | 80 | 2020-01-30 23:31 | [5 empty] | 80 | 2020-06-01 11:09 | [5 empty] | 80 | 2020-06-01 11:09 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2019-11-27 17:40 | 2020-03-17 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [21 empty] | 409 |  |  |  | 101421
2732 | Task(Task)-->E (Engineering) | UPS SIZING CALCULATION |  | 1.24.1.4 | Unscheduled | No | No | 2019-12-06 18:00 | 2020-01-16 17:40 | 2019-12-09 18:00 | 2020-05-02 18:00 |  |  | 2020-02-21 14:08 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-BE-009 |  | 2020-02-13 11:48 | 7012-155-PVI-U-009 |  |  |  | A |  |  |  | 1.2245 | 0.00129 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 45 | 0 | 0.16 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5108 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-12-06 18:00 | 2019-12-09 18:00 |  | 10 | 2019-12-09 23:31 |  |  | 2019-12-09 17:40 | 2019-12-13 18:00 |  | 30 | 2019-12-13 23:31 |  |  | 2019-12-14 17:40 | 2019-12-18 18:00 |  | 35 | 2019-12-18 23:31 |  |  | 2019-12-20 23:59 | 2020-02-18 18:00 |  | 65 | 2020-02-18 23:31 |  |  | 2019-12-26 17:40 | 2020-03-19 18:00 |  | 80 | 2020-03-07 23:31 | [5 empty] | 80 | 2020-06-03 15:56 | [5 empty] | 80 | 2020-06-03 15:56 | [5 empty] | 80 | 2020-06-12 11:42 | [5 empty] | 80 | 2020-06-12 11:42 | [5 empty] | 80 | 2020-08-17 11:40 | [5 empty] | 80 | 2020-08-17 11:40 | [5 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-01-16 17:40 | 2020-05-02 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [21 empty] | 414 |  |  |  | 101426
2733 | Task(Task)-->E (Engineering) | DRIVE LIST |  | 1.24.1.4 | Unscheduled | No | No | 2019-12-16 18:00 | 2020-01-24 17:40 | 2019-12-16 18:00 | 2020-05-02 18:00 |  |  | 2020-02-21 14:08 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-DD-001 |  | 2020-02-13 11:48 | 7012-155-PVI-H-010 |  |  |  | A |  |  |  | 1.4286 | 0.001505 | 0.14 | Plan & Actual | Date |  | 0 | 0 | 0 | 52.03 | 0 | 0.19 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5099 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-12-16 18:00 | 2019-12-16 18:00 |  | 10 | 2019-12-16 23:31 |  |  | 2019-12-17 17:40 | 2019-12-23 18:00 |  | 30 | 2019-12-23 23:31 |  |  | 2019-12-23 17:40 | 2019-12-23 18:00 |  | 35 | 2019-12-23 23:31 |  |  | 2019-12-28 23:59 | 2019-12-31 18:00 |  | 65 | 2019-12-31 23:31 |  |  | 2020-01-03 17:40 | 2020-01-31 18:00 |  | 80 | 2020-01-31 23:31 | [5 empty] | 80 | 2020-06-03 16:09 | [5 empty] | 80 | 2020-06-03 16:09 | [5 empty] | 80 | 2020-06-03 16:14 | [5 empty] | 80 | 2020-06-03 16:14 | [5 empty] | 80 | 2020-09-24 18:00 | [5 empty] | 80 | 2020-09-24 18:00 | [5 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-01-24 17:40 | 2020-05-02 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [21 empty] | 415 |  |  |  | 101427
2734 | Task(Task)-->E (Engineering) | PROCESS IO LIST |  | 1.24.1.4 | Unscheduled | No | No | 2019-12-04 17:40 | 2020-01-11 17:40 | 2019-12-04 18:00 | 2020-05-02 18:00 |  |  | 2020-02-21 14:08 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-DD-002 |  | 2020-02-13 11:48 | 7012-155-PVI-G-011 |  |  |  | A |  |  |  | 4.0816 | 0.0043 | 0.4 | Plan & Actual | Date |  | 0 | 0 | 0 | 150 | 0 | 6.1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5097 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-12-04 18:00 | 2019-12-04 18:00 |  | 10 | 2019-12-04 23:31 |  |  | 2019-12-04 17:40 | 2019-12-16 18:00 |  | 30 | 2019-12-16 23:31 |  |  | 2019-12-10 17:40 | 2019-12-16 18:00 |  | 35 |  |  |  | 2019-12-16 23:59 | 2019-12-20 18:00 |  | 65 | 2019-12-20 23:31 |  |  | 2019-12-21 17:40 | 2020-01-30 18:00 |  | 80 | 2020-01-30 23:31 | [5 empty] | 80 | 2020-06-01 16:43 | [5 empty] | 80 | 2020-06-01 16:43 | [5 empty] | 80 | 2020-06-03 10:56 | [5 empty] | 80 | 2020-06-03 10:56 | [5 empty] | 80 | 2020-09-24 17:50 | [5 empty] | 80 | 2020-09-24 17:50 | [5 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-01-11 17:40 | 2020-05-02 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [21 empty] | 416 |  |  |  | 101428
2735 | Task(Task)-->E (Engineering) | 24VDC SIZING CALCULATION, FEEDER LIST, BATTERY SIZING |  | 1.24.1.4 | Unscheduled | No | No | 2020-01-02 18:00 | 2020-02-12 17:40 | 2020-01-02 18:00 | 2020-04-01 18:00 |  |  | 2020-09-03 13:26 |  |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-DD-003 |  | 2020-02-13 11:48 | 7012-155-PVI-U-012 |  |  |  | A |  |  |  | 1.6327 | 0.00172 | 0.16 | Plan & Actual | Date |  | 0 | 0 | 0 | 60 | 0 | 2.05 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5109 | 1 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-02 18:00 | 2020-01-02 18:00 |  | 10 | 2020-01-02 23:31 |  |  | 2020-01-03 17:40 | 2020-01-10 18:00 |  | 30 | 2020-01-10 23:31 |  |  | 2020-01-09 17:40 | 2020-01-10 18:00 |  | 35 |  |  |  | 2020-01-15 23:59 | 2020-01-28 18:00 |  | 65 | 2020-01-28 23:31 |  |  | 2020-01-21 17:40 | 2020-03-07 18:00 |  | 80 | 2020-03-07 23:31 | [5 empty] | 80 | 2020-08-17 11:11 | [5 empty] | 80 | 2020-08-17 11:11 | [5 empty] | 80 | 2020-09-03 13:26 | [5 empty] | 80 | 2020-09-03 13:26 | [5 empty] | 80 | 2020-09-15 18:02 | [5 empty] | 80 | 2020-09-15 18:02 | [5 empty] | 80 | 2020-10-07 14:31 | [5 empty] | 80 | 2020-10-07 14:31 |  |  | 2020-02-12 17:40 | 2020-04-01 18:00 |  | 100 | 2020-08-17 11:38 | [121 empty] | Subhrajyoti Ghosh | [21 empty] | 417 |  |  |  | 101429
2736 | Task(Task)-->E (Engineering) | BLD LEGEND SHEET |  | 1.24.1.4 | Unscheduled | No | No | 2020-03-26 17:40 | 2020-05-07 17:40 | 2020-04-23 09:00 | 2020-07-08 18:00 |  |  | 2020-02-21 14:08 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-DD-004 |  | 2020-02-13 11:48 | 7012-155-PVI-T-013 |  |  |  | I |  |  |  | 1.2245 | 0.00129 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 45 | 0 | 12.16 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5087 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-29 23:59 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-03-26 17:40 | 2020-06-10 18:00 |  | 30 |  |  |  | 2020-04-02 17:40 | 2020-06-12 18:00 |  | 35 |  |  |  | 2020-04-08 23:59 | 2020-06-15 18:00 |  | 65 | 2020-04-23 23:31 |  |  | 2020-04-15 17:40 | 2020-07-06 18:00 |  | 80 | 2020-05-16 23:31 | [5 empty] | 80 | 2020-07-08 10:55 | [5 empty] | 80 | 2020-07-08 10:55 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-07 17:40 | 2020-07-06 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [21 empty] | 418 |  |  |  | 101430
2737 | Task(Task)-->E (Engineering) | BLD FOR FLAP GATE |  | 1.24.1.4 | Unscheduled | No | No | 2020-04-03 17:40 | 2020-05-15 17:40 | 2020-05-16 09:00 | 2020-12-02 18:00 |  |  | 2020-02-21 14:08 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-DD-006 |  | 2020-02-13 11:48 | 7012-155-PVI-T-015 |  |  |  | I |  |  |  | 2.8571 | 0.00301 | 0.28 | Plan & Actual | Date |  | 0 | 0 | 0 | 105 | 0 | 26.03 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5088 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-06 18:00 | 2020-10-04 23:59 |  | 10 |  |  |  | 2020-04-03 17:40 | 2020-10-09 18:00 |  | 30 |  |  |  | 2020-04-09 17:40 | 2020-10-11 23:59 |  | 35 |  |  |  | 2020-04-16 23:59 | 2020-10-14 18:00 |  | 65 | 2020-05-16 23:31 |  |  | 2020-04-22 17:40 | 2020-11-04 18:00 |  | 80 | 2020-05-22 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-15 17:40 | 2020-12-02 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [21 empty] | 420 |  |  |  | 101432
2738 | Task(Task)-->E (Engineering) | BLD FOR PIPE CONVEYOR |  | 1.24.1.4 | Unscheduled | No | No | 2020-05-04 17:40 | 2020-06-15 17:40 | 2020-10-04 23:59 | 2020-12-02 18:00 |  |  | 2020-02-21 14:08 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-DD-007 |  | 2020-02-13 11:48 | 7012-155-PVI-T-016 |  |  |  | I |  |  |  | 3.2653 | 0.00344 | 0.32 | Plan & Actual | Date |  | 0 | 0 | 0 | 120 | 0 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5095 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-05-06 18:00 | 2020-10-04 23:59 |  | 10 |  |  |  | 2020-05-04 17:40 | 2020-10-09 18:00 |  | 30 |  |  |  | 2020-05-11 17:40 | 2020-10-11 23:59 |  | 35 |  |  |  | 2020-05-16 23:59 | 2020-10-14 18:00 |  | 65 |  |  |  | 2020-05-22 17:40 | 2020-11-04 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-15 17:40 | 2020-12-02 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [21 empty] | 421 |  |  |  | 101433
2739 | Task(Task)-->E (Engineering) | BLD FOR ILMS/SM/MD |  | 1.24.1.4 | Unscheduled | No | No | 2020-04-07 17:40 | 2020-05-19 17:40 | 2020-05-02 09:00 | 2020-11-04 18:00 |  |  | 2020-02-21 14:08 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-DD-008 |  | 2020-02-13 11:48 | 7012-155-PVI-T-017 |  |  |  | I |  |  |  | 0.81633 | 0.00086 | 0.08 | Plan & Actual | Date |  | 0 | 0 | 0 | 30 | 0 | 17.03 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5089 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-10 18:00 | 2020-10-04 23:59 |  | 10 |  |  |  | 2020-04-07 17:40 | 2020-10-09 18:00 |  | 30 |  |  |  | 2020-04-14 17:40 | 2020-10-11 23:59 |  | 35 |  |  |  | 2020-04-20 23:59 | 2020-10-14 18:00 |  | 65 | 2020-05-02 23:31 |  |  | 2020-04-27 17:40 | 2020-11-04 18:00 |  | 80 | 2020-05-22 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-19 17:40 | 2020-11-04 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [21 empty] | 422 |  |  |  | 101434
2740 | Task(Task)-->E (Engineering) | BLD FOR APRON FEEDER |  | 1.24.1.4 | Unscheduled | No | No | 2020-04-09 17:40 | 2020-05-21 17:40 | 2020-06-23 09:00 | 2020-12-02 18:00 |  |  | 2020-02-21 14:08 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-DD-009 |  | 2020-02-13 11:48 | 7012-155-PVI-T-018 |  |  |  | I |  |  |  | 2.449 | 0.00258 | 0.24 | Plan & Actual | Date |  | 0 | 0 | 0 | 90 | 0 | 7.04 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5090 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-12 23:59 | 2020-10-04 23:59 |  | 10 |  |  |  | 2020-04-09 17:40 | 2020-10-09 18:00 |  | 30 |  |  |  | 2020-04-16 17:40 | 2020-10-11 23:59 |  | 35 |  |  |  | 2020-04-22 23:59 | 2020-10-14 18:00 |  | 65 | 2020-06-23 17:01 |  |  | 2020-04-29 17:40 | 2020-11-04 18:00 |  | 80 | 2020-07-18 10:29 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-21 17:40 | 2020-12-02 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [21 empty] | 423 |  |  |  | 101435
2741 | Task(Task)-->E (Engineering) | BLD FOR LT CONVEYOR AND BELT FEEDER |  | 1.24.1.4 | Unscheduled | No | No | 2020-04-16 17:40 | 2020-05-28 17:40 | 2020-10-04 23:59 | 2020-12-02 18:00 |  |  | 2020-02-21 14:08 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-DD-010 |  | 2020-02-13 11:48 | 7012-155-PVI-T-019 |  |  |  | I |  |  |  | 2.449 | 0.00258 | 0.24 | Plan & Actual | Date |  | 0 | 0 | 0 | 90 | 0 | 0.03 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5091 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-19 23:59 | 2020-10-04 23:59 |  | 10 |  |  |  | 2020-04-16 17:40 | 2020-10-09 18:00 |  | 30 |  |  |  | 2020-04-22 17:40 | 2020-10-11 23:59 |  | 35 |  |  |  | 2020-04-29 23:59 | 2020-10-14 18:00 |  | 65 |  |  |  | 2020-05-05 17:40 | 2020-11-04 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-28 17:40 | 2020-12-02 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [21 empty] | 424 |  |  |  | 101436
2742 | Task(Task)-->E (Engineering) | BLD FOR MISCELLANEOUS ITEMS (UTILITY ITEMS) |  | 1.24.1.4 | Unscheduled | No | No | 2020-04-17 17:40 | 2020-05-29 17:40 | 2020-06-22 09:00 | 2020-12-02 18:00 |  |  | 2020-02-21 14:08 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-DD-011 |  | 2020-02-13 11:48 | 7012-155-PVI-T-020 |  |  |  | I |  |  |  | 2.449 | 0.00258 | 0.24 | Plan & Actual | Date |  | 0 | 0 | 0 | 90 | 0 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5092 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-20 18:00 | 2020-10-04 23:59 |  | 10 |  |  |  | 2020-04-17 17:40 | 2020-10-09 18:00 |  | 30 |  |  |  | 2020-04-23 17:40 | 2020-10-11 23:59 |  | 35 |  |  |  | 2020-04-30 23:59 | 2020-10-14 18:00 |  | 65 | 2020-06-22 17:36 |  |  | 2020-05-06 17:40 | 2020-11-04 18:00 |  | 80 | 2020-07-18 11:11 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-29 17:40 | 2020-12-02 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [21 empty] | 425 |  |  |  | 101437
2743 | Task(Task)-->E (Engineering) | BLD FOR SEQUENCE |  | 1.24.1.4 | Unscheduled | No | No | 2020-04-23 17:40 | 2020-06-04 17:40 | 2020-05-10 | 2020-12-02 18:00 |  |  | 2020-02-21 14:08 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-DD-012 |  | 2020-02-13 11:48 | 7012-155-PVI-T-021 |  |  |  | I |  |  |  | 2.449 | 0.00258 | 0.24 | Plan & Actual | Date |  | 0 | 0 | 0 | 90 | 0 | 17.07 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5093 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-26 23:59 | 2020-10-04 23:59 |  | 10 |  |  |  | 2020-04-23 17:40 | 2020-10-09 18:00 |  | 30 |  |  |  | 2020-04-30 17:40 | 2020-10-11 23:59 |  | 35 |  |  |  | 2020-05-06 23:59 | 2020-10-14 18:00 |  | 65 | 2020-05-10 23:31 |  |  | 2020-05-13 17:40 | 2020-11-04 18:00 |  | 80 | 2020-06-04 16:19 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-04 17:40 | 2020-12-02 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [21 empty] | 426 |  |  |  | 101438
2744 | Task(Task)-->E (Engineering) | BLD HMI |  | 1.24.1.4 | Unscheduled | No | No | 2020-05-02 17:40 | 2020-06-12 17:40 | 2020-06-05 18:00 | 2020-10-15 18:00 |  |  | 2020-02-21 14:08 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-DD-013 |  | 2020-02-13 11:48 | 7012-155-PVI-T-022 |  |  |  | I |  |  |  | 4.0816 | 0.0043 | 0.4 | Plan & Actual | Date |  | 0 | 0 | 0 | 150 | 0 | 0.04 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5094 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-05-05 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-05-02 17:40 | 2020-06-10 18:00 |  | 30 |  |  |  | 2020-05-08 17:40 | 2020-06-12 18:00 |  | 35 |  |  |  | 2020-05-15 23:59 | 2020-06-15 18:00 |  | 65 | 2020-06-12 12:13 |  |  | 2020-05-21 17:40 | 2020-07-06 18:00 |  | 80 | 2020-07-06 16:41 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-12 17:40 | 2020-08-03 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [21 empty] | 427 |  |  |  | 101439
2745 | Task(Task)-->E (Engineering) | CONTROL CABLE BLOCK DIAGRAM |  | 1.24.1.4 | Unscheduled | No | No | 2019-11-08 17:40 | 2019-12-17 17:40 | 2019-11-19 18:00 | 2020-04-29 18:00 |  |  | 2020-02-21 14:08 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-DD-014 |  | 2020-02-13 11:48 | 7012-155-PVI-T-023 |  |  |  | A |  |  |  | 2.0408 | 0.00215 | 0.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 75 | 0 | 0.21 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5107 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-11-10 23:59 | 2019-11-19 18:00 |  | 10 | 2019-11-19 23:31 |  |  | 2019-11-08 17:40 | 2019-11-24 23:59 |  | 30 | 2019-11-24 23:31 |  |  | 2019-11-14 17:40 | 2019-11-26 18:00 |  | 35 | 2019-11-26 23:31 |  |  | 2019-11-20 23:59 | 2019-11-29 18:00 |  | 65 | 2019-11-29 23:31 |  |  | 2019-11-26 17:40 | 2020-01-08 18:00 |  | 80 | 2020-01-08 23:31 | [5 empty] | 80 | 2020-06-01 14:21 | [5 empty] | 80 | 2020-06-01 14:21 | [5 empty] | 80 | 2020-06-03 16:28 | [5 empty] | 80 | 2020-06-03 16:28 | [5 empty] | 80 | 2020-06-12 11:59 | [5 empty] | 80 | 2020-06-12 11:59 | [5 empty] | 80 | [6 empty] | 80 |  |  |  | 2019-12-17 17:40 | 2020-04-29 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [21 empty] | 428 |  |  |  | 101440
2746 | Task(Task)-->E (Engineering) | CABLE SCHEDULE WITH INTERCONNECTION |  | 1.24.1.4 | Unscheduled | No | No | 2020-04-23 17:40 | 2020-06-04 17:40 | 2020-05-30 18:00 | 2020-10-15 18:00 |  |  | 2020-02-21 14:08 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-DD-015 |  | 2020-02-13 11:48 | 7012-155-PVI-H-024 |  |  |  | I |  |  |  | 12.3469 | 0.013007 | 1.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 450 | 0 | 12.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5100 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-26 23:59 | 2020-05-30 18:00 |  | 10 |  |  |  | 2020-04-23 17:40 | 2020-05-30 18:00 |  | 30 |  |  |  | 2020-04-30 17:40 | 2020-06-02 18:00 |  | 35 |  |  |  | 2020-05-06 23:59 | 2020-06-02 18:00 |  | 65 | 2020-08-21 10:50 |  |  | 2020-05-13 17:40 | 2020-06-23 18:00 |  | 80 | 2020-09-03 12:58 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-04 17:40 | 2020-07-21 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [21 empty] | 429 |  |  |  | 101441
2747 | Task(Task)-->E (Engineering) | SLD FOR POWER DISTRIBUTION FOR C&I ITEMS |  | 1.24.1.4 | Unscheduled | No | No | 2019-12-06 17:40 | 2020-01-14 17:40 | 2020-01-14 18:00 | 2020-07-24 18:00 |  |  | 2020-02-21 14:08 |  |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-DD-016 |  | 2020-02-13 11:48 | 7012-155-PVI-L-025 |  |  |  | I |  |  |  | 0.81633 | 0.00086 | 0.08 | Plan & Actual | Date |  | 0 | 0 | 0 | 30 | 0 | 2.19 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5101 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-12-08 23:59 | 2020-01-14 18:00 |  | 10 | 2020-01-14 23:31 |  |  | 2019-12-06 17:40 | 2020-01-19 23:59 |  | 30 | 2020-01-19 23:31 |  |  | 2019-12-12 17:40 | 2020-01-21 18:00 |  | 35 | 2020-01-21 23:31 |  |  | 2019-12-18 23:59 | 2020-01-24 18:00 |  | 65 | 2020-01-24 23:31 |  |  | 2019-12-24 17:40 | 2020-02-17 18:00 |  | 80 | 2020-02-17 23:31 | [5 empty] | 80 | 2020-06-03 11:22 | [5 empty] | 80 | 2020-06-03 11:22 | [5 empty] | 80 | 2020-06-12 11:51 | [5 empty] | 80 | 2020-06-12 11:51 | [5 empty] | 80 | 2020-09-15 17:55 | [5 empty] | 80 | 2020-09-15 17:55 | [5 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-01-14 17:40 | 2020-04-29 18:00 |  | 100 | 2020-09-15 16:20 | [121 empty] | Subhrajyoti Ghosh | [21 empty] | 430 |  |  |  | 101442
2748 | Task(Task)-->E (Engineering) | TYPICAL PLC MODULE WIRING |  | 1.24.1.4 | Unscheduled | No | No | 2020-01-24 17:40 | 2020-03-05 17:40 | 2020-06-05 18:00 | 2020-10-15 18:00 |  |  | 2020-02-21 14:09 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-VD-002 |  | 2020-02-13 11:48 | 7012-155-PVI-L-027 |  |  |  | I |  |  |  | 0.61224 | 0.000645 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 22.03 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5102 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-26 23:59 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-01-24 17:40 | 2020-06-10 18:00 |  | 30 | 2020-09-25 12:31 |  |  | 2020-01-30 17:40 | 2020-06-12 18:00 |  | 35 |  |  |  | 2020-02-05 23:59 | 2020-06-15 18:00 |  | 65 | 2020-08-12 14:32 |  |  | 2020-02-12 17:40 | 2020-07-06 18:00 |  | 80 | 2020-08-25 11:23 | [5 empty] | 80 | 2020-09-25 12:14 | [5 empty] | 80 | 2020-09-25 12:14 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-05 17:40 | 2020-07-06 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [21 empty] | 432 |  |  |  | 101444
2749 | Task(Task)-->E (Engineering) | GA, POWER DISTRIBUTION SCHEME & BOM FOR CHP PLC |  | 1.24.1.4 | Unscheduled | No | No | 2020-01-24 17:40 | 2020-03-05 17:40 | 2020-07-05 23:59 | 2020-10-15 18:00 |  |  | 2020-02-21 14:09 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-VD-003 |  | 2020-02-13 11:48 | 7012-155-PVI-L-028 |  |  |  | A |  |  |  | 4.898 | 0.00516 | 0.48 | Plan & Actual | Date |  | 0 | 0 | 0 | 180 | 0 | 6.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5103 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-26 23:59 | 2020-07-05 23:59 |  | 10 |  |  |  | 2020-01-24 17:40 | 2020-07-10 18:00 |  | 30 | 2020-08-29 13:23 |  |  | 2020-01-30 17:40 | 2020-07-12 23:59 |  | 35 |  |  |  | 2020-02-05 23:59 | 2020-07-15 18:00 |  | 65 | 2020-08-29 13:23 |  |  | 2020-02-12 17:40 | 2020-08-05 18:00 |  | 80 | 2020-09-03 13:01 | [5 empty] | 80 | 2020-10-07 13:47 | [5 empty] | 80 | 2020-10-07 13:47 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-05 17:40 | 2020-08-05 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [21 empty] | 433 |  |  |  | 101445
2750 | Task(Task)-->E (Engineering) | PLC FAT PROCEDURE |  | 1.24.1.4 | Unscheduled | No | No | 2020-02-27 17:40 | 2020-04-08 17:40 | 2020-06-30 18:00 | 2020-10-15 18:00 |  |  | 2020-02-21 14:09 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-VD-004 |  | 2020-02-13 11:48 | 7012-155-PVI-W-029 |  |  |  | I |  |  |  | 1.6327 | 0.00172 | 0.16 | Plan & Actual | Date |  | 0 | 0 | 0 | 60 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5113 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-29 18:00 | 2020-06-30 18:00 |  | 10 |  |  |  | 2020-02-27 17:40 | 2020-07-05 23:59 |  | 30 |  |  |  | 2020-03-04 17:40 | 2020-07-07 18:00 |  | 35 |  |  |  | 2020-03-10 23:59 | 2020-07-10 18:00 |  | 65 | 2020-08-29 12:57 |  |  | 2020-03-17 17:40 | 2020-07-31 18:00 |  | 80 | 2020-09-03 13:02 | [5 empty] | 80 | 2020-09-25 12:34 | [5 empty] | 80 | 2020-09-25 12:34 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-08 17:40 | 2020-07-31 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [21 empty] | 434 |  |  |  | 101446
2751 | Task(Task)-->E (Engineering) | IO ASSIGNMENT FOR PLC |  | 1.24.1.4 | Unscheduled | No | No | 2020-01-24 17:40 | 2020-03-05 17:40 | 2020-06-05 18:00 | 2020-10-15 18:00 |  |  | 2020-02-21 14:09 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-VD-005 |  | 2020-02-13 11:48 | 7012-155-PVI-G-030 |  |  |  | I |  |  |  | 8.2653 | 0.008707 | 0.81 | Plan & Actual | Date |  | 0 | 0 | 0 | 300 | 0 | 6.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5098 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-26 23:59 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-01-24 17:40 | 2020-06-10 18:00 |  | 30 | 2020-09-24 18:00 |  |  | 2020-01-30 17:40 | 2020-06-12 18:00 |  | 35 |  |  |  | 2020-02-05 23:59 | 2020-06-15 18:00 |  | 65 | 2020-09-24 18:00 |  |  | 2020-02-12 17:40 | 2020-07-06 18:00 |  | 80 | 2020-10-10 16:00 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-05 17:40 | 2020-07-06 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [21 empty] | 435 |  |  |  | 101447
2752 | Task(Task)-->E (Engineering) | MMI SCREENS FOR CHP PLC SYSTEM |  | 1.24.1.4 | Unscheduled | No | No | 2020-02-27 17:40 | 2020-04-08 17:40 | 2020-06-05 18:00 | 2020-08-21 18:00 |  |  | 2020-02-21 14:09 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-VD-006 |  | 2020-02-13 11:48 | 7012-155-PVI-V-031 |  |  |  | I |  |  |  | 2.0408 | 0.00215 | 0.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 75 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5110 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-29 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-02-27 17:40 | 2020-06-10 18:00 |  | 30 |  |  |  | 2020-03-04 17:40 | 2020-06-12 18:00 |  | 35 |  |  |  | 2020-03-10 23:59 | 2020-06-15 18:00 |  | 65 |  |  |  | 2020-03-17 17:40 | 2020-07-06 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-08 17:40 | 2020-07-06 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [21 empty] | 436 |  |  |  | 101448
2753 | Task(Task)-->E (Engineering) | DATASHEETS OF PLC COMPONENTS |  | 1.24.1.4 | Unscheduled | No | No | 2020-01-24 17:40 | 2020-03-05 17:40 | 2020-06-05 18:00 | 2020-10-15 18:00 |  |  | 2020-02-21 14:09 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-VD-007 |  | 2020-02-13 11:48 | 7012-155-PVI-Y-032 |  |  |  | I |  |  |  | 3.0612 | 0.003225 | 0.3 | Plan & Actual | Date |  | 0 | 0 | 0 | 112.03 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5120 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-26 23:59 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-01-24 17:40 | 2020-06-10 18:00 |  | 30 | 2020-08-29 13:19 |  |  | 2020-01-30 17:40 | 2020-06-12 18:00 |  | 35 |  |  |  | 2020-02-05 23:59 | 2020-06-15 18:00 |  | 65 | 2020-08-29 13:19 |  |  | 2020-02-12 17:40 | 2020-07-06 18:00 |  | 80 | 2020-09-03 13:03 | [5 empty] | 80 | 2020-09-25 12:37 | [5 empty] | 80 | 2020-09-25 12:37 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-05 17:40 | 2020-07-06 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [21 empty] | 437 |  |  |  | 101449
2754 | Task(Task)-->E (Engineering) | DATA SHEETS FOR FIBRE OPTIC CABLE |  | 1.24.1.4 | Unscheduled | No | No | 2020-03-04 17:40 | 2020-04-15 17:40 | 2020-06-21 23:59 | 2020-09-26 18:00 |  |  | 2020-02-21 14:09 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-VD-008 |  | 2020-02-13 11:48 | 7012-155-PVI-Y-033 |  |  |  | A |  |  |  | 1.0204 | 0.001075 | 0.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 37.03 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5121 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-07 18:00 | 2020-06-21 23:59 |  | 10 |  |  |  | 2020-03-04 17:40 | 2020-06-26 18:00 |  | 30 |  |  |  | 2020-03-10 17:40 | 2020-06-28 23:59 |  | 35 |  |  |  | 2020-03-17 23:59 | 2020-07-01 18:00 |  | 65 | 2020-08-04 16:49 |  |  | 2020-03-23 17:40 | 2020-07-22 18:00 |  | 80 | 2020-08-25 11:25 | [5 empty] | 80 | 2020-08-29 10:28 | [5 empty] | 80 | 2020-08-29 10:28 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-15 17:40 | 2020-07-22 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [21 empty] | 438 |  |  |  | 101450
2755 | Task(Task)-->E (Engineering) | DATA SHEET FOR CONTROL & INSTRUMENTATION CABLES |  | 1.24.1.4 | Unscheduled | No | No | 2020-02-20 17:40 | 2020-04-02 17:40 | 2020-06-21 23:59 | 2020-08-21 18:00 |  |  | 2020-02-21 14:09 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-VD-009 |  | 2020-02-13 11:48 | 7012-155-PVI-Y-034 |  |  |  | A |  |  |  | 1.6327 | 0.00172 | 0.16 | Plan & Actual | Date |  | 0 | 0 | 0 | 60 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5122 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-23 23:59 | 2020-06-21 23:59 |  | 10 |  |  |  | 2020-02-20 17:40 | 2020-06-26 18:00 |  | 30 |  |  |  | 2020-02-27 17:40 | 2020-06-28 23:59 |  | 35 |  |  |  | 2020-03-04 23:59 | 2020-07-01 18:00 |  | 65 |  |  |  | 2020-03-10 17:40 | 2020-07-22 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-02 17:40 | 2020-07-22 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [21 empty] | 439 |  |  |  | 101451
2756 | Task(Task)-->E (Engineering) | GA, DATA SHEETS,BOM AND TYPICAL SCHEMES FOR UPS |  | 1.24.1.4 | Unscheduled | No | No | 2020-03-05 17:40 | 2020-04-16 17:40 | 2020-06-25 18:00 | 2020-10-15 18:00 |  |  | 2020-02-21 14:09 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-VD-010 |  | 2020-02-13 11:48 | 7012-155-PVI-W-035 |  |  |  | A |  |  |  | 3.0612 | 0.003225 | 0.3 | Plan & Actual | Date |  | 0 | 0 | 0 | 112.03 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5114 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-08 23:59 | 2020-06-25 18:00 |  | 10 |  |  |  | 2020-03-05 17:40 | 2020-06-30 18:00 |  | 30 | 2020-09-01 11:20 |  |  | 2020-03-11 17:40 | 2020-07-02 18:00 |  | 35 |  |  |  | 2020-03-18 23:59 | 2020-07-05 23:59 |  | 65 | 2020-09-01 11:20 |  |  | 2020-03-24 17:40 | 2020-07-26 23:59 |  | 80 | 2020-10-06 10:02 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-16 17:40 | 2020-07-26 23:59 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [21 empty] | 440 |  |  |  | 101452
2757 | Task(Task)-->E (Engineering) | GA, DISTRIBUTION SLD, DATA SHEETS,BOM AND TYPICAL SCHEMES FOR 24DC BATTERY AND BATTERY CHARGER |  | 1.24.1.4 | Unscheduled | No | No | 2020-02-28 17:40 | 2020-04-09 17:40 | 2020-07-05 23:59 | 2020-10-15 18:00 |  |  | 2020-02-21 14:09 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-VD-011 |  | 2020-02-13 11:48 | 7012-155-PVI-W-036 |  |  |  | A |  |  |  | 3.2653 | 0.00344 | 0.32 | Plan & Actual | Date |  | 0 | 0 | 0 | 120 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5115 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-01 23:59 | 2020-07-05 23:59 |  | 10 |  |  |  | 2020-02-28 17:40 | 2020-07-10 18:00 |  | 30 | 2020-09-01 11:16 |  |  | 2020-03-05 17:40 | 2020-07-12 23:59 |  | 35 |  |  |  | 2020-03-11 23:59 | 2020-07-15 18:00 |  | 65 | 2020-09-01 11:17 |  |  | 2020-03-18 17:40 | 2020-08-05 18:00 |  | 80 | 2020-10-06 10:15 | [5 empty] | 80 | 2020-10-07 14:14 | [5 empty] | 80 | 2020-10-07 14:14 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-09 17:40 | 2020-08-05 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [21 empty] | 441 |  |  |  | 101453
2758 | Task(Task)-->E (Engineering) | GA, AND WIRING OF PDB |  | 1.24.1.4 | Unscheduled | No | No | 2020-03-07 17:40 | 2020-04-18 17:40 | 2020-07-11 18:00 | 2020-09-03 18:00 |  |  | 2020-02-21 14:09 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-VD-012 |  | 2020-02-13 11:48 | 7012-155-PVI-W-037 |  |  |  | A |  |  |  | 3.2653 | 0.00344 | 0.32 | Plan & Actual | Date |  | 0 | 0 | 0 | 120 | 0 | 4.02 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5116 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-10 18:00 | 2020-07-11 18:00 |  | 10 |  |  |  | 2020-03-07 17:40 | 2020-07-16 18:00 |  | 30 |  |  |  | 2020-03-13 17:40 | 2020-07-18 18:00 |  | 35 |  |  |  | 2020-03-20 23:59 | 2020-07-21 18:00 |  | 65 | 2020-08-13 12:26 |  |  | 2020-03-26 17:40 | 2020-08-11 18:00 |  | 80 | 2020-09-03 12:53 | [5 empty] | 80 | 2020-09-06 13:47 | [5 empty] | 80 | 2020-09-06 13:47 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-18 17:40 | 2020-08-11 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [21 empty] | 442 |  |  |  | 101454
2759 | Task(Task)-->E (Engineering) | GA OF CONTROL JUNCTION BOXES |  | 1.24.1.4 | Unscheduled | No | No | 2020-03-26 17:40 | 2020-05-07 17:40 | 2020-07-21 18:00 | 2020-10-15 18:00 |  |  | 2020-02-21 14:09 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-VD-013 |  | 2020-02-13 11:48 | 7012-155-PVI-W-038 |  |  |  | A |  |  |  | 3.2653 | 0.00344 | 0.32 | Plan & Actual | Date |  | 0 | 0 | 0 | 120 | 0 | 4.03 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5117 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-29 23:59 | 2020-07-21 18:00 |  | 10 |  |  |  | 2020-03-26 17:40 | 2020-07-26 23:59 |  | 30 |  |  |  | 2020-04-02 17:40 | 2020-07-28 18:00 |  | 35 |  |  |  | 2020-04-08 23:59 | 2020-07-31 18:00 |  | 65 | 2020-08-04 16:53 |  |  | 2020-04-15 17:40 | 2020-08-21 18:00 |  | 80 | 2020-09-01 10:02 | [5 empty] | 80 | 2020-09-08 20:47 | [5 empty] | 80 | 2020-09-08 20:47 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-07 17:40 | 2020-08-21 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [21 empty] | 443 |  |  |  | 101455
2760 | Task(Task)-->E (Engineering) | GA,DATA SHEET & SCHEME OF CCTV SYSTEM |  | 1.24.1.4 | Unscheduled | No | No | 2020-04-01 17:40 | 2020-05-13 17:40 | 2020-06-21 23:59 | 2020-10-15 18:00 |  |  | 2020-02-21 14:09 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-VD-014 |  | 2020-02-13 11:49 | 7012-155-PVI-W-039 |  |  |  | A |  |  |  | 4.898 | 0.00516 | 0.48 | Plan & Actual | Date |  | 0 | 0 | 0 | 180 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5118 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-04 18:00 | 2020-06-21 23:59 |  | 10 |  |  |  | 2020-04-01 17:40 | 2020-06-26 18:00 |  | 30 |  |  |  | 2020-04-07 17:40 | 2020-06-28 23:59 |  | 35 |  |  |  | 2020-04-14 23:59 | 2020-07-01 18:00 |  | 65 | 2020-07-27 17:31 |  |  | 2020-04-20 17:40 | 2020-07-22 18:00 |  | 80 | 2020-09-01 09:57 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-13 17:40 | 2020-07-22 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [21 empty] | 444 |  |  |  | 101456
2761 | Task(Task)-->E (Engineering) | GA,DATA SHEET & SCHEME OF PA SYSTEM. |  | 1.24.1.4 | Unscheduled | No | No | 2020-03-20 17:40 | 2020-05-01 17:40 | 2020-06-21 23:59 | 2020-10-15 18:00 |  |  | 2020-02-21 14:09 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-VD-015 |  | 2020-02-13 11:49 | 7012-155-PVI-W-040 |  |  |  | A |  |  |  | 4.898 | 0.00516 | 0.48 | Plan & Actual | Date |  | 0 | 0 | 0 | 180 | 0 | 9.3 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5119 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-23 18:00 | 2020-06-21 23:59 |  | 10 |  |  |  | 2020-03-20 17:40 | 2020-06-26 18:00 |  | 30 |  |  |  | 2020-03-26 17:40 | 2020-06-28 23:59 |  | 35 |  |  |  | 2020-04-02 23:59 | 2020-07-01 18:00 |  | 65 | 2020-08-14 15:20 |  |  | 2020-04-08 17:40 | 2020-07-22 18:00 |  | 80 | 2020-09-03 13:00 | [5 empty] | 80 | 2020-10-12 11:39 | [5 empty] | 80 | 2020-10-12 11:39 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-01 17:40 | 2020-07-22 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [21 empty] | 445 |  |  |  | 101457
2762 | Task(Task)-->E (Engineering) | TECHNICAL DETAILS OF GROUP CONTROL PANEL, PCS AND BSS |  | 1.24.1.4 | Unscheduled | No | No | 2020-02-14 17:40 | 2020-03-26 17:40 | 2020-06-05 18:00 | 2020-09-03 18:00 |  |  | 2020-02-21 14:09 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-VD-017 |  | 2020-02-13 11:49 | 7012-155-PVI-Y-042 |  |  |  | A |  |  |  | 3.6735 | 0.00387 | 0.36 | Plan & Actual | Date |  | 0 | 0 | 0 | 135 | 0 | 2.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5123 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-17 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-02-14 17:40 | 2020-06-10 18:00 |  | 30 |  |  |  | 2020-02-20 17:40 | 2020-06-12 18:00 |  | 35 |  |  |  | 2020-02-27 23:59 | 2020-06-15 18:00 |  | 65 | 2020-08-22 17:38 |  |  | 2020-03-04 17:40 | 2020-07-06 18:00 |  | 80 | 2020-09-03 12:56 | [5 empty] | 80 | 2020-09-05 17:43 | [5 empty] | 80 | 2020-09-05 17:43 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-26 17:40 | 2020-07-06 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [21 empty] | 447 |  |  |  | 101459
2763 | Task(Task)-->E (Engineering) | TECHNICAL DETAILS OF ZERO SPEED SWITCH |  | 1.24.1.4 | Unscheduled | No | No | 2020-02-12 17:40 | 2020-03-24 17:40 | 2020-06-05 18:00 | 2020-08-25 18:00 |  |  | 2020-02-21 14:09 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-VD-018 |  | 2020-02-13 11:49 | 7012-155-PVI-Y-043 |  |  |  | A |  |  |  | 1.0204 | 0.001075 | 0.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 37.03 | 0 | 3.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5124 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-15 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-02-12 17:40 | 2020-06-10 18:00 |  | 30 |  |  |  | 2020-02-18 17:40 | 2020-06-12 18:00 |  | 35 |  |  |  | 2020-02-25 23:59 | 2020-06-15 18:00 |  | 65 | 2020-08-17 11:56 |  |  | 2020-03-02 17:40 | 2020-07-06 18:00 |  | 80 | 2020-08-25 11:27 | [5 empty] | 80 | 2020-10-08 11:50 | [5 empty] | 80 | 2020-10-08 11:50 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-24 17:40 | 2020-07-06 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [21 empty] | 448 |  |  |  | 101460
2764 | Task(Task)-->E (Engineering) | TECHNICAL DETAILS OF CHUTE BLOCK SWITCH |  | 1.24.1.4 | Unscheduled | No | No | 2020-02-13 17:40 | 2020-03-25 17:40 | 2020-02-08 18:00 | 2020-07-12 23:59 |  |  | 2020-02-21 14:09 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-VD-019 |  | 2020-02-13 11:49 | 7012-155-PVI-Y-044 |  |  |  | A |  |  |  | 1.0204 | 0.001075 | 0.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 37.03 | 0 | 5.03 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5125 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-16 23:59 | 2020-02-08 18:00 |  | 10 | 2020-02-08 23:31 |  |  | 2020-02-13 17:40 | 2020-02-13 18:00 |  | 30 | 2020-02-13 23:31 |  |  | 2020-02-19 17:40 | 2020-02-15 18:00 |  | 35 | 2020-02-15 23:31 |  |  | 2020-02-26 23:59 | 2020-02-18 18:00 |  | 65 | 2020-02-18 23:31 |  |  | 2020-03-03 17:40 | 2020-03-13 18:00 |  | 80 | 2020-03-13 23:31 | [5 empty] | 80 | 2020-06-01 17:05 | [5 empty] | 80 | 2020-06-01 17:05 | [5 empty] | 80 | 2020-06-01 17:11 | [5 empty] | 80 | 2020-06-01 17:11 | [5 empty] | 80 | 2020-07-08 11:02 | [5 empty] | 80 | 2020-07-08 11:02 | [5 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-25 17:40 | 2020-05-01 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [21 empty] | 449 |  |  |  | 101461
2765 | Task(Task)-->E (Engineering) | TECHNICAL DETAILS OF SINGLE CHANNEL TEMPERATURE TRANSMITTER |  | 1.24.1.4 | Unscheduled | No | No | 2020-03-30 17:40 | 2020-05-11 17:40 | 2020-05-21 18:00 | 2020-08-25 18:00 |  |  | 2020-02-21 14:09 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-VD-020 |  | 2020-02-13 11:49 | 7012-155-PVI-Y-045 |  |  |  | A |  |  |  | 1.0204 | 0.001075 | 0.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 37.03 | 0 | 3.06 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5126 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-31 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-30 17:40 | 2020-05-26 18:00 |  | 30 | 2020-07-24 16:30 |  |  | 2020-04-04 17:40 | 2020-05-28 18:00 |  | 35 |  |  |  | 2020-04-10 23:59 | 2020-05-31 23:59 |  | 65 | 2020-07-27 12:31 |  |  | 2020-04-17 17:40 | 2020-06-21 23:59 |  | 80 | 2020-08-25 11:30 | [5 empty] | 80 | 2020-09-07 12:20 | [5 empty] | 80 | 2020-09-07 12:20 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-11 17:40 | 2020-06-21 23:59 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [21 empty] | 450 |  |  |  | 101462
2766 | Task(Task)-->E (Engineering) | PLC CONFIGURATION DIAGRAM FOR CHP |  | 1.24.1.4 | Unscheduled | No | No | 2020-01-18 17:40 | 2020-02-28 17:40 | 2020-01-18 17:40 | 2020-07-06 18:00 |  |  | 2020-02-21 14:08 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-VD-001 |  | 2020-02-13 11:48 | 7012-155-PVI-Q-026 |  |  |  | A |  |  |  | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 15 | 0 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-20 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-01-18 17:40 | 2020-06-10 18:00 |  | 30 | 2020-09-25 12:34 |  |  | 2020-01-24 17:40 | 2020-06-12 18:00 |  | 35 |  |  |  | 2020-01-30 23:59 | 2020-06-15 18:00 |  | 65 | 2020-08-12 14:26 |  |  | 2020-02-05 17:40 | 2020-07-06 18:00 |  | 80 | 2020-08-25 11:21 | [5 empty] | 80 | 2020-09-25 12:32 | [5 empty] | 80 | 2020-09-25 12:32 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-02-28 17:40 | 2020-07-06 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [21 empty] | 431 |  |  |  | 101443
2767 | Task(Task)-->E (Engineering) | Fabrication Drawings | 1.24.1.5 | 1.24.1 | Unscheduled | No | No | 2020-06-12 18:00 | 2020-11-30 18:00 | 2020-06-12 18:00 | 2020-11-30 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No |  | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1098568
2768 | Task(Task)-->E (Engineering) | GENERAL NOTES ON FABRICATION |  | 1.24.1.5 | Unscheduled | No | No | 2020-06-12 18:00 | 2020-06-12 18:00 | 2020-06-12 18:00 | 2020-06-12 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2001 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-06-12 18:00 |  |  | 100 | [120 empty] | 1098580
2769 | Task(Task)-->E (Engineering) | GENERAL GUIDE LINES FOR CORNER DETAILS OF HOOD & CHUTE AND FIXING ARRG. OF SKIRTS, SADDLES, CHUTE BLOCK SWITCH AND LINERS. |  | 1.24.1.5 | Unscheduled | No | No | 2020-07-10 18:00 | 2020-07-10 18:00 | 2020-07-10 18:00 | 2020-07-10 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2002 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-07-10 18:00 |  |  | 100 | [120 empty] | 1098581
2770 | Task(Task)-->E (Engineering) | FAB. DETAIL OF STRINGER & SHORT POST FOR SC-1A/B & SC-2A/B (1400mm BELT WIDTH) |  | 1.24.1.5 | Unscheduled | No | No | 2020-06-17 18:00 | 2020-06-17 18:00 | 2020-06-17 18:00 | 2020-06-17 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2003 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-06-17 18:00 |  |  | 100 | [120 empty] | 1098582
2771 | Task(Task)-->E (Engineering) | FAB. DETAIL OF STRINGER & SHORT POST FOR SC-3A/B (1800mm BELT WIDTH) |  | 1.24.1.5 | Unscheduled | No | No | 2020-06-26 18:00 | 2020-06-26 18:00 | 2020-06-26 18:00 | 2020-06-26 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2004 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-06-26 18:00 |  |  | 100 | [120 empty] | 1098583
2772 | Task(Task)-->E (Engineering) | FAB. DETAIL OF STRINGER & SHORT POST FOR SY-1A/B (1800mm BELT WIDTH) |  | 1.24.1.5 | Unscheduled | No | No | 2020-06-12 18:00 | 2020-06-12 18:00 | 2020-06-12 18:00 | 2020-06-12 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2005 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-06-12 18:00 |  |  | 100 | [120 empty] | 1098584
2773 | Task(Task)-->E (Engineering) | FAB. DETAIL OF STRINGER & SHORT POST FOR PC-1A/B (2000mm BELT WIDTH) |  | 1.24.1.5 | Unscheduled | No | No | 2020-09-11 18:00 | 2020-09-11 18:00 | 2020-09-11 18:00 | 2020-09-11 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2006 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-09-11 18:00 |  |  | 100 | [120 empty] | 1098585
2774 | Task(Task)-->E (Engineering) | FAB. DETAIL OF STRINGER & SHORT POST FOR PC-2A/B (2000mm BELT WIDTH) |  | 1.24.1.5 | Unscheduled | No | No | 2020-09-18 18:00 | 2020-09-18 18:00 | 2020-09-18 18:00 | 2020-09-18 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2007 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-09-18 18:00 |  |  | 100 | [120 empty] | 1098586
2775 | Task(Task)-->E (Engineering) | FAB. DETAIL OF STRINGER & SHORT POST FOR DRIBBLE FEEDERS DF-1,DF-2,DF-3 & DF-4 (2200mm BELT WIDTH) |  | 1.24.1.5 | Unscheduled | No | No | 2020-06-26 18:00 | 2020-06-26 18:00 | 2020-06-26 18:00 | 2020-06-26 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2008 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-06-26 18:00 |  |  | 100 | [120 empty] | 1098587
2776 | Task(Task)-->E (Engineering) | FAB. DETAIL OF STRINGER & SHORT POST SECTION FOR BELT FEEDER BF-1/2 2000mm BELT WIDTH |  | 1.24.1.5 | Unscheduled | No | No | 2020-06-30 18:00 | 2020-06-30 18:00 | 2020-06-30 18:00 | 2020-06-30 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2009 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-06-30 18:00 |  |  | 100 | [120 empty] | 1098588
2777 | Task(Task)-->E (Engineering) | FAB. DETAIL OF DECK PLATE FOR SC-1A/B & SC-2A/B (1400mm BELT WIDTH) |  | 1.24.1.5 | Unscheduled | No | No | 2020-06-23 18:00 | 2020-06-23 18:00 | 2020-06-23 18:00 | 2020-06-23 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2010 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-06-23 18:00 |  |  | 100 | [120 empty] | 1098589
2778 | Task(Task)-->E (Engineering) | FAB. DETAIL OF DECK PLATE FOR SY-1A/B (1800mm BELT WIDTH) |  | 1.24.1.5 | Unscheduled | No | No | 2020-06-26 18:00 | 2020-06-26 18:00 | 2020-06-26 18:00 | 2020-06-26 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2011 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-06-26 18:00 |  |  | 100 | [120 empty] | 1098590
2779 | Task(Task)-->E (Engineering) | FAB. DETAIL OF DECK PLATE FOR PC-1A/B & PC-2A/B (2000mm BELT WIDTH) |  | 1.24.1.5 | Unscheduled | No | No | 2020-08-28 18:00 | 2020-08-28 18:00 | 2020-08-28 18:00 | 2020-08-28 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2012 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-08-28 18:00 |  |  | 100 | [120 empty] | 1098591
2780 | Task(Task)-->E (Engineering) | FAB. DETAIL OF DECK PLATE FOR BELT FEEDER FEEDER BF-1/2 (2000mm BELT WIDTH) |  | 1.24.1.5 | Unscheduled | No | No | 2020-06-30 18:00 | 2020-06-30 18:00 | 2020-06-30 18:00 | 2020-06-30 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2013 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-06-30 18:00 |  |  | 100 | [120 empty] | 1098592
2781 | Task(Task)-->E (Engineering) | FAB. DETAIL OF DECK PLATE FOR DRIBBLE FEEDERS DF-1,DF-2,DF-3 & DF-4 (2200mm BELT WIDTH) |  | 1.24.1.5 | Unscheduled | No | No | 2020-06-26 18:00 | 2020-06-26 18:00 | 2020-06-26 18:00 | 2020-06-26 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2014 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-06-26 18:00 |  |  | 100 | [120 empty] | 1098593
2782 | Task(Task)-->E (Engineering) | FAB. DETAIL OF DECK PLATE FOR SC-3A/B (1800mm BELT WIDTH) |  | 1.24.1.5 | Unscheduled | No | No | 2020-06-30 18:00 | 2020-06-30 18:00 | 2020-06-30 18:00 | 2020-06-30 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2015 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-06-30 18:00 |  |  | 100 | [120 empty] | 1098594
2783 | Task(Task)-->E (Engineering) | FAB. DETAIL OF TAIL PULLEY FRAME FOR SC-1A/1B & SC-2A/2B (1400mm BELT WIDTH) |  | 1.24.1.5 | Unscheduled | No | No | 2020-06-12 18:00 | 2020-06-12 18:00 | 2020-06-12 18:00 | 2020-06-12 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2016 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-06-12 18:00 |  |  | 100 | [120 empty] | 1098595
2784 | Task(Task)-->E (Engineering) | FAB. DETAIL OF TAIL PULLEY FRAME FOR SC-3A/3B (1800mm BELT WIDTH) |  | 1.24.1.5 | Unscheduled | No | No | 2020-06-12 18:00 | 2020-06-12 18:00 | 2020-06-12 18:00 | 2020-06-12 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2017 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-06-12 18:00 |  |  | 100 | [120 empty] | 1098596
2785 | Task(Task)-->E (Engineering) | FAB. DETAIL OF TAIL PULLEY FRAME FOR SY-1A/1B (1800mm BELT WIDTH) |  | 1.24.1.5 | Unscheduled | No | No | 2020-06-12 18:00 | 2020-06-12 18:00 | 2020-06-12 18:00 | 2020-06-12 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2018 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-06-12 18:00 |  |  | 100 | [120 empty] | 1098597
2786 | Task(Task)-->E (Engineering) | FAB. DETAIL OF TAIL CUM TAKE-UP PULLEY FRAME FOR BELT FEEDER BF-1/2 (2000mm BELT WIDTH) |  | 1.24.1.5 | Unscheduled | No | No | 2020-06-30 18:00 | 2020-06-30 18:00 | 2020-06-30 18:00 | 2020-06-30 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2019 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-06-30 18:00 |  |  | 100 | [120 empty] | 1098598
2787 | Task(Task)-->E (Engineering) | FAB. DETAIL OF TAIL CUM TAKE-UP PULLEY FRAME FOR DRIBBLE FEEDER DF-1/2/3/4 (2200mm BELT WIDTH) |  | 1.24.1.5 | Unscheduled | No | No | 2020-06-26 18:00 | 2020-06-26 18:00 | 2020-06-26 18:00 | 2020-06-26 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2020 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-06-26 18:00 |  |  | 100 | [120 empty] | 1098599
2788 | Task(Task)-->E (Engineering) | FAB.DETAIL OF DRIVE CUM DISCHARGE PULLEY FRAME FOR SC-1A/1B & SC-2A/2B (1400mm BELT WIDTH) |  | 1.24.1.5 | Unscheduled | No | No | 2020-06-17 18:00 | 2020-06-17 18:00 | 2020-06-17 18:00 | 2020-06-17 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2021 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-06-17 18:00 |  |  | 100 | [120 empty] | 1098600
2789 | Task(Task)-->E (Engineering) | FAB.DETAIL OF DRIVE CUM DISCHARGE PULLEY FRAME FOR SC-3A/3B (1800mm BELT WIDTH) |  | 1.24.1.5 | Unscheduled | No | No | 2020-06-17 18:00 | 2020-06-17 18:00 | 2020-06-17 18:00 | 2020-06-17 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2022 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-06-17 18:00 |  |  | 100 | [120 empty] | 1098601
2790 | Task(Task)-->E (Engineering) | FAB.DETAIL OF DISCHARGE PULLEY FRAME FOR SY-1A/1B (1800mm BELT WIDTH) |  | 1.24.1.5 | Unscheduled | No | No | 2020-06-30 18:00 | 2020-06-30 18:00 | 2020-06-30 18:00 | 2020-06-30 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2023 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-06-30 18:00 |  |  | 100 | [120 empty] | 1098602
2791 | Task(Task)-->E (Engineering) | FAB.DETAIL OF DRIVE PULLEY FRAME FOR SY-1A & 1B (1800mm BELT WIDTH) IN DRIVE HOUSE-3 |  | 1.24.1.5 | Unscheduled | No | No | 2020-06-30 18:00 | 2020-06-30 18:00 | 2020-06-30 18:00 | 2020-06-30 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2024 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-06-30 18:00 |  |  | 100 | [120 empty] | 1098603
2792 | Task(Task)-->E (Engineering) | FAB. DETAIL OF DRIVE CUM DISCHARGE PULLEY FRAME FOR DRIBBLE FEEDER, DF-1, DF-2, DF-3 & DF-4 (2200mm BELT WIDTH) |  | 1.24.1.5 | Unscheduled | No | No | 2020-06-26 18:00 | 2020-06-26 18:00 | 2020-06-26 18:00 | 2020-06-26 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2025 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-06-26 18:00 |  |  | 100 | [120 empty] | 1098604
2793 | Task(Task)-->E (Engineering) | FAB.DETAIL OF DRIVE CUM DISCHARGE PULLEY FRAME FOR BELT FEEDER BF-1/2 (2000mm BELT WIDTH) |  | 1.24.1.5 | Unscheduled | No | No | 2020-06-30 18:00 | 2020-06-30 18:00 | 2020-06-30 18:00 | 2020-06-30 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2026 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-06-30 18:00 |  |  | 100 | [120 empty] | 1098605
2794 | Task(Task)-->E (Engineering) | FAB.DETAIL OF LT BEND PULLEY FRAME FOR SC-1A/1B & SC-2A/2B (1400mm BELT WIDTH) |  | 1.24.1.5 | Unscheduled | No | No | 2020-06-12 18:00 | 2020-06-12 18:00 | 2020-06-12 18:00 | 2020-06-12 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2027 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-06-12 18:00 |  |  | 100 | [120 empty] | 1098606
2795 | Task(Task)-->E (Engineering) | FAB.DETAIL OF LT BEND PULLEY FRAME FOR SC-3A/3B (1800mm BELT WIDTH) |  | 1.24.1.5 | Unscheduled | No | No | 2020-06-12 18:00 | 2020-06-12 18:00 | 2020-06-12 18:00 | 2020-06-12 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2028 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-06-12 18:00 |  |  | 100 | [120 empty] | 1098607
2796 | Task(Task)-->E (Engineering) | FAB.DETAIL OF LT BEND PULLEY FRAME FOR SY-1A/1B (1800mm BELT WIDTH) |  | 1.24.1.5 | Unscheduled | No | No | 2020-06-12 18:00 | 2020-06-12 18:00 | 2020-06-12 18:00 | 2020-06-12 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2029 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-06-12 18:00 |  |  | 100 | [120 empty] | 1098608
2797 | Task(Task)-->E (Engineering) | FAB.DETAIL OF HT BEND PULLEY FRAME FOR SY-1A/1B (1800mm BELT WIDTH) |  | 1.24.1.5 | Unscheduled | No | No | 2020-06-12 18:00 | 2020-06-12 18:00 | 2020-06-12 18:00 | 2020-06-12 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2030 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-06-12 18:00 |  |  | 100 | [120 empty] | 1098609
2798 | Task(Task)-->E (Engineering) | FAB. DETAIL OF TAIL PULLEY FRAME FOR PC-1A/1B (2000mm BELT WIDTH) |  | 1.24.1.5 | Unscheduled | No | No | 2020-08-20 18:00 | 2020-08-20 18:00 | 2020-08-20 18:00 | 2020-08-20 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2031 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-08-20 18:00 |  |  | 100 | [120 empty] | 1098610
2799 | Task(Task)-->E (Engineering) | FAB. DETAIL OF TAIL PULLEY FRAME FOR PC-2A/1B (2000mm BELT WIDTH) |  | 1.24.1.5 | Unscheduled | No | No | 2020-08-20 18:00 | 2020-08-20 18:00 | 2020-08-20 18:00 | 2020-08-20 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2032 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-08-20 18:00 |  |  | 100 | [120 empty] | 1098611
2800 | Task(Task)-->E (Engineering) | FAB.DETAIL OF DISCHARGE PULLEY FRAME FOR PC-1A/1B & PC-2A/1B (2000mm BELT WIDTH) |  | 1.24.1.5 | Unscheduled | No | No | 2020-08-31 | 2020-08-31 | 2020-08-30 23:59 | 2020-08-30 23:59 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2033 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-08-31 |  |  | 100 | [120 empty] | 1098612
2801 | Task(Task)-->E (Engineering) | FAB. DETAIL OF TAIL SIDE DRIVE PULLEY FRAME FOR PC-1A/1B IN SHB & PC-2A/2B IN KDTP-2 |  | 1.24.1.5 | Unscheduled | No | No | 2020-09-04 18:00 | 2020-09-04 18:00 | 2020-09-04 18:00 | 2020-09-04 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2034 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-09-04 18:00 |  |  | 100 | [120 empty] | 1098613
2802 | Task(Task)-->E (Engineering) | FAB. DETAIL OF DRIVE PULLEY FRAME FOR PC-1A -1, PC-1A -2 & PC-1B -1 AT KDTPC-2 AND PC-2A -1, PC-2A -2 & PC-2B -1 AT KDTPC-3 |  | 1.24.1.5 | Unscheduled | No | No | 2020-09-11 18:00 | 2020-09-11 18:00 | 2020-09-11 18:00 | 2020-09-11 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2035 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-09-11 18:00 |  |  | 100 | [120 empty] | 1098614
2803 | Task(Task)-->E (Engineering) | FAB. DETAIL OF DRIVE PULLEY FRAME FOR PC-1B -2 AT KDTPC-2 AND PC-2B -2 AT KDTPC-3 |  | 1.24.1.5 | Unscheduled | No | No | 2020-09-11 18:00 | 2020-09-11 18:00 | 2020-09-11 18:00 | 2020-09-11 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2036 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-09-11 18:00 |  |  | 100 | [120 empty] | 1098615
2804 | Task(Task)-->E (Engineering) | FAB.DETAIL OF LT BEND PULLEY FRAME FOR PC-1A AT KDTPC-2 AND PC-2A AT KDTPC-3 ( ON GROUND) |  | 1.24.1.5 | Unscheduled | No | No | 2020-09-18 18:00 | 2020-09-18 18:00 | 2020-09-18 18:00 | 2020-09-18 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2037 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-09-18 18:00 |  |  | 100 | [120 empty] | 1098616
2805 | Task(Task)-->E (Engineering) | FAB.DETAIL OF LT BEND PULLEY FRAME FOR PC-1A , PC-1B, AT KDTPC-2 AND PC-2A & PC-2B AT KDTPC-3 (OVER GROUND) |  | 1.24.1.5 | Unscheduled | No | No | 2020-09-25 18:00 | 2020-09-25 18:00 | 2020-09-25 18:00 | 2020-09-25 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2038 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-09-25 18:00 |  |  | 100 | [120 empty] | 1098617
2806 | Task(Task)-->E (Engineering) | FAB.DETAIL OF HT BEND PULLEY FRAME FOR PC-1A , PC-1B, AT KDTPC-2 AND PC-2A & PC-2B AT KDTPC-3 (OVER GROUND) |  | 1.24.1.5 | Unscheduled | No | No | 2020-09-25 18:00 | 2020-09-25 18:00 | 2020-09-25 18:00 | 2020-09-25 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2039 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-09-25 18:00 |  |  | 100 | [120 empty] | 1098618
2807 | Task(Task)-->E (Engineering) | FAB. DETAIL OF DRIVE BASE FRAME FOR APRON FEEDER AF-1, AF-2, AF-3 & AF-4 |  | 1.24.1.5 | Unscheduled | No | No | 2020-09-04 18:00 | 2020-09-04 18:00 | 2020-09-04 18:00 | 2020-09-04 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2040 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-09-04 18:00 |  |  | 100 | [120 empty] | 1098619
2808 | Task(Task)-->E (Engineering) | FAB.DETAIL OF DRIVE BASE FRAME FOR SC-1A/1B, SC-2A/2B & SY 1AB |  | 1.24.1.5 | Unscheduled | No | No | 2020-09-11 18:00 | 2020-09-11 18:00 | 2020-09-11 18:00 | 2020-09-11 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2041 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-09-11 18:00 |  |  | 100 | [120 empty] | 1098620
2809 | Task(Task)-->E (Engineering) | FAB.DETAIL OF DRIVE BASE FRAME FOR SC-3A/3B (1800mm BELT WIDTH) |  | 1.24.1.5 | Unscheduled | No | No | 2020-09-15 18:00 | 2020-09-15 18:00 | 2020-09-15 18:00 | 2020-09-15 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2042 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-09-15 18:00 |  |  | 100 | [120 empty] | 1098621
2810 | Task(Task)-->E (Engineering) | FAB.DETAIL OF DRIVE BASE FRAME FOR BELT FEEDER BF-1/2 (2000mm BELT WIDTH) |  | 1.24.1.5 | Unscheduled | No | No | 2020-09-19 18:00 | 2020-09-19 18:00 | 2020-09-19 18:00 | 2020-09-19 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2043 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-09-19 18:00 |  |  | 100 | [120 empty] | 1098622
2811 | Task(Task)-->E (Engineering) | FAB.DETAIL OF DRIVE BASE FRAME FOR DRIBBLE FEEDER DF-1/2/3/4 (2200mm BELT WIDTH) |  | 1.24.1.5 | Unscheduled | No | No | 2020-09-19 18:00 | 2020-09-19 18:00 | 2020-09-19 18:00 | 2020-09-19 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2044 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-09-19 18:00 |  |  | 100 | [120 empty] | 1098623
2812 | Task(Task)-->E (Engineering) | FAB.DETAIL OF DRIVE BASE FRAME FOR PC-1A/1B & PC-2A/2B (ON GROUND) |  | 1.24.1.5 | Unscheduled | No | No | 2020-10-16 18:00 | 2020-10-16 18:00 | 2020-10-16 18:00 | 2020-10-16 18:00 | [6 empty] | 0 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2045 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-10-16 18:00 |  |  | 100 | [120 empty] | 1098624
2813 | Task(Task)-->E (Engineering) | FAB.DETAIL OF DRIVE BASE FRAME FOR PC-1B & PC-2B (ON SUB STRUCTURE) |  | 1.24.1.5 | Unscheduled | No | No | 2020-10-16 18:00 | 2020-10-16 18:00 | 2020-10-16 18:00 | 2020-10-16 18:00 | [6 empty] | 0 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2046 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-10-16 18:00 |  |  | 100 | [120 empty] | 1098625
2814 | Task(Task)-->E (Engineering) | G.A & FAB. DETAILS OF VGTU WITH ROPE FOR SC-1A/1B & SC-2A/2B (1400mm BELT WIDTH) |  | 1.24.1.5 | Unscheduled | No | No | 2020-06-30 18:00 | 2020-06-30 18:00 | 2020-06-30 18:00 | 2020-06-30 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2048 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-06-30 18:00 |  |  | 100 | [120 empty] | 1098626
2815 | Task(Task)-->E (Engineering) | G.A & FAB. DETAILS OF VGTU WITH ROPE FOR SC-3A/3B (1800mm BELT WIDTH) |  | 1.24.1.5 | Unscheduled | No | No | 2020-07-10 18:00 | 2020-07-10 18:00 | 2020-07-10 18:00 | 2020-07-10 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2049 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-07-10 18:00 |  |  | 100 | [120 empty] | 1098627
2816 | Task(Task)-->E (Engineering) | G.A & FAB. DETAILS OF VGTU WITH ROPE FOR SY-1A/1B (1800mm BELT WIDTH) |  | 1.24.1.5 | Unscheduled | No | No | 2020-07-04 18:00 | 2020-07-04 18:00 | 2020-07-04 18:00 | 2020-07-04 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2050 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-07-04 18:00 |  |  | 100 | [120 empty] | 1098628
2817 | Task(Task)-->E (Engineering) | G.A & FAB. DETAILS OF HGTU COUNTER WEIGHT FRAME FOR PC-1A /1B (2000 mm B/W) |  | 1.24.1.5 | Unscheduled | No | No | 2020-10-05 18:00 | 2020-10-05 18:00 | 2020-10-05 18:00 | 2020-10-05 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2051 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-10-05 18:00 |  |  | 100 | [120 empty] | 1098629
2818 | Task(Task)-->E (Engineering) | G.A & FAB. DETAILS OF HGTU COUNTER WEIGHT FRAME FOR PC-2A /2B (2000 mm B/W) |  | 1.24.1.5 | Unscheduled | No | No | 2020-10-05 18:00 | 2020-10-05 18:00 | 2020-10-05 18:00 | 2020-10-05 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2052 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-10-05 18:00 |  |  | 100 | [120 empty] | 1098630
2819 | Task(Task)-->E (Engineering) | G.A & FAB. DETAILS OF HGTU TROLLEY SUPPORT FRAME FOR PC-1A / B |  | 1.24.1.5 | Unscheduled | No | No | 2020-08-28 18:00 | 2020-08-28 18:00 | 2020-08-28 18:00 | 2020-08-28 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2053 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-08-28 18:00 |  |  | 100 | [120 empty] | 1098631
2820 | Task(Task)-->E (Engineering) | G.A & FAB. DETAILS OF HGTU TROLLEY SUPPORT FRAME FOR PC-2A / B |  | 1.24.1.5 | Unscheduled | No | No | 2020-08-28 18:00 | 2020-08-28 18:00 | 2020-08-28 18:00 | 2020-08-28 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2054 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-08-28 18:00 |  |  | 100 | [120 empty] | 1098632
2821 | Task(Task)-->E (Engineering) | MARKING G.A. & FAB. DETAIL OF DISCHARGE CHUTE FROM DUMP HOPPER TO AF-1, AF-2, AF-3 & AF-4 AND SKIRT BOARD ON AF-1, AF-2, AF-3 & AF-4 FEEDING TO PRIMARY SIZER-1,2,3&4 RESPECTIVELY INSIDE DUMP HOPPER BUILDING |  | 1.24.1.5 | Unscheduled | No | No | 2020-07-31 18:00 | 2020-07-31 18:00 | 2020-07-31 18:00 | 2020-07-31 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2056 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-07-31 18:00 |  |  | 100 | [120 empty] | 1098633
2822 | Task(Task)-->E (Engineering) | MARKING G.A. & FAB. DETAIL OF DISCHARGE CHUTE BELOW PRIMARY SIZER-1,2,3 & 4 AND TRAMP IRON CHUTE/SPILLAGE CHUTE OF PRIMARY SIZER-1,2,3 & 4 TO SC-1A/1B & SC-2A/2B AND SKIRT BOARD ON SC-1A/1B & SC-2A/2B IN DUMP HOPPER BUILDING |  | 1.24.1.5 | Unscheduled | No | No | 2020-07-24 18:00 | 2020-07-24 18:00 | 2020-07-24 18:00 | 2020-07-24 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2057 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-07-24 18:00 |  |  | 100 | [120 empty] | 1098634
2823 | Task(Task)-->E (Engineering) | MARKING G.A. & FAB. DETAIL OF DISCHARGE CHUTE FROM SC-1A/1B & SC-2A/2B TO SECONDARY SIZER-1,2,3 & 4 IN KDTP-1 BUILDING |  | 1.24.1.5 | Unscheduled | No | No | 2020-07-10 18:00 | 2020-07-10 18:00 | 2020-07-10 18:00 | 2020-07-10 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2058 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-07-10 18:00 |  |  | 100 | [120 empty] | 1098635
2824 | Task(Task)-->E (Engineering) | MARKING G.A. & FAB. DETAIL OF UNDER SIZE CHUTE FROM SECONDARY SIZER-1,2,3 & 4 TO SC-3A/3B AND SKIRT BOARD ON SC-3A/3B IN KDTP-1 BUILDING |  | 1.24.1.5 | Unscheduled | No | No | 2020-07-17 18:00 | 2020-07-17 18:00 | 2020-07-17 18:00 | 2020-07-17 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2059 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-07-17 18:00 |  |  | 100 | [120 empty] | 1098636
2825 | Task(Task)-->E (Engineering) | MARKING G.A. & FAB. DETAIL OF DISCHARGE CHUTE FROM SC-3A/3B TO SURGE HOPPER-1 & 2 IN SURGE HOPPER BUILDING |  | 1.24.1.5 | Unscheduled | No | No | 2020-08-07 18:00 | 2020-08-07 18:00 | 2020-08-07 18:00 | 2020-08-07 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2060 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-08-07 18:00 |  |  | 100 | [120 empty] | 1098637
2826 | Task(Task)-->E (Engineering) | MARKING G.A. & FAB. DETAIL OF DISCHARGE CHUTE RECEIVING MATERIAL FROM SURGE HOPPER 1 & 2 TO BELT FEEDER-1 & 2 AND SKIRT BOARD ON BELT FEEDER-1 & 2, DISCHARGE CHUTE FROM BELT FEEDER-1 & 2 TO PIPE CONVEYOR PC-1A/1B & SKIRT BOARD ON PIPE CONVEYOR PC-1... |  | 1.24.1.5 | Unscheduled | No | No | 2020-08-21 18:00 | 2020-08-21 18:00 | 2020-08-21 18:00 | 2020-08-21 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2061 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-08-21 18:00 |  |  | 100 | [120 empty] | 1098638
2827 | Task(Task)-->E (Engineering) | MARKING G.A. & FAB. DETAIL OF DISCHARGE CHUTE FROM PIPE CONVEYOR PC-1A/1B TO PIPE CONVEYOR PC-2A/2B AND SKIRT BOARD ON PIPE CONVEYOR PC-2A/2B IN KDTP-2 BUILDING |  | 1.24.1.5 | Unscheduled | No | No | 2020-08-28 18:00 | 2020-08-28 18:00 | 2020-08-28 18:00 | 2020-08-28 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2062 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-08-28 18:00 |  |  | 100 | [120 empty] | 1098639
2828 | Task(Task)-->E (Engineering) | MARKING G.A. & FAB. DETAIL OF DISCHARGE CHUTE FROM PIPE CONVEYOR PC-2A/2B TO STOCK YARD CONVEYOR SY-1A/1B AND SKIRT BOARD ON STOCK YARD CONVEYOR SY-1A/1B IN KDTP-3 BUILDING |  | 1.24.1.5 | Unscheduled | No | No | 2020-09-18 18:00 | 2020-09-18 18:00 | 2020-09-18 18:00 | 2020-09-18 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2063 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-09-18 18:00 |  |  | 100 | [120 empty] | 1098640
2829 | Task(Task)-->E (Engineering) | MARKING & FAB. DETAIL OF DEBRIS CHUTE AND ITS SUPPORTING BRACKETS IN DUMP HOPPER BUILDING |  | 1.24.1.5 | Unscheduled | No | No | 2020-08-28 18:00 | 2020-08-28 18:00 | 2020-08-28 18:00 | 2020-08-28 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2064 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-08-28 18:00 |  |  | 100 | [120 empty] | 1098641
2830 | Task(Task)-->E (Engineering) | MARKING & FAB. DETAIL OF DEBRIS CHUTE AND ITS SUPPORTING BRACKETS IN KDTP-1 BUILDING |  | 1.24.1.5 | Unscheduled | No | No | 2020-08-07 18:00 | 2020-08-07 18:00 | 2020-08-07 18:00 | 2020-08-07 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2065 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-08-07 18:00 |  |  | 100 | [120 empty] | 1098642
2831 | Task(Task)-->E (Engineering) | MARKING & FAB. DETAIL OF DEBRIS CHUTE AND ITS SUPPORTING BRACKETS IN SURGE HOPPER BUILDING |  | 1.24.1.5 | Unscheduled | No | No | 2020-08-07 18:00 | 2020-08-07 18:00 | 2020-08-07 18:00 | 2020-08-07 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2066 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-08-07 18:00 |  |  | 100 | [120 empty] | 1098643
2832 | Task(Task)-->E (Engineering) | MARKING & FAB. DETAIL OF DEBRIS CHUTE AND ITS SUPPORTING BRACKETS IN KDTP-2 BUILDING |  | 1.24.1.5 | Unscheduled | No | No | 2020-08-14 18:00 | 2020-08-14 18:00 | 2020-08-14 18:00 | 2020-08-14 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2067 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-08-14 18:00 |  |  | 100 | [120 empty] | 1098644
2833 | Task(Task)-->E (Engineering) | MARKING & FAB. DETAIL OF DEBRIS CHUTE AND ITS SUPPORTING BRACKETS IN KDTP-3 BUILDING |  | 1.24.1.5 | Unscheduled | No | No | 2020-08-21 18:00 | 2020-08-21 18:00 | 2020-08-21 18:00 | 2020-08-21 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2068 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-08-21 18:00 |  |  | 100 | [120 empty] | 1098645
2834 | Task(Task)-->E (Engineering) | MARKING & FAB. DETAIL OF TRAMP IRON CHUTE IN KDTP-1 BUILDING |  | 1.24.1.5 | Unscheduled | No | No | 2020-08-28 18:00 | 2020-08-28 18:00 | 2020-08-28 18:00 | 2020-08-28 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2069 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-08-28 18:00 |  |  | 100 | [120 empty] | 1098646
2835 | Task(Task)-->E (Engineering) | FAB. DETAIL OF INSPECTION DOOR |  | 1.24.1.5 | Unscheduled | No | No | 2020-09-30 18:00 | 2020-09-30 18:00 | 2020-09-30 18:00 | 2020-09-30 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2070 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-09-30 18:00 |  |  | 100 | [120 empty] | 1098647
2836 | Task(Task)-->E (Engineering) | MARKING & FAB. DETAIL OF LINER IN DUMP HOPPER BUILDING |  | 1.24.1.5 | Unscheduled | No | No | 2020-08-14 18:00 | 2020-08-14 18:00 | 2020-08-14 18:00 | 2020-08-14 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2071 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-08-14 18:00 |  |  | 100 | [120 empty] | 1098648
2837 | Task(Task)-->E (Engineering) | FAB. DETAIL OF TAIL PULLEY GUARD FOR TROUGH CONVEYOR |  | 1.24.1.5 | Unscheduled | No | No | 2020-10-07 18:00 | 2020-10-07 18:00 | 2020-10-07 18:00 | 2020-10-07 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2073 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-10-07 18:00 |  |  | 100 | [120 empty] | 1098649
2838 | Task(Task)-->E (Engineering) | FAB. DETAIL OF TAIL PULLEY GUARD FOR PIPE CONVEYOR |  | 1.24.1.5 | Unscheduled | No | No | 2020-10-23 18:00 | 2020-10-23 18:00 | 2020-10-23 18:00 | 2020-10-23 18:00 | [6 empty] | 0 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2074 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-10-23 18:00 |  |  | 100 | [120 empty] | 1098650
2839 | Task(Task)-->E (Engineering) | FAB. DETAIL OF TAIL CUM TAKE-UP PULLEY GUARD FOR DRIBBLE FEEDER DF-1,2,3 & 4 IN DUMP HOPPER BUILDING |  | 1.24.1.5 | Unscheduled | No | No | 2020-10-07 18:00 | 2020-10-07 18:00 | 2020-10-07 18:00 | 2020-10-07 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2075 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-10-07 18:00 |  |  | 100 | [120 empty] | 1098651
2840 | Task(Task)-->E (Engineering) | FAB. DETAIL OF TAIL CUM TAKE-UP PULLEY GUARD FOR BELT FEEDER BF-1/2 IN SURGE HOPPER BUILDING |  | 1.24.1.5 | Unscheduled | No | No | 2020-10-07 18:00 | 2020-10-07 18:00 | 2020-10-07 18:00 | 2020-10-07 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2076 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-10-07 18:00 |  |  | 100 | [120 empty] | 1098652
2841 | Task(Task)-->E (Engineering) | FAB. DETAIL OF BEND PULLEY GUARD FOR SY-1A/1B |  | 1.24.1.5 | Unscheduled | No | No | 2020-10-07 18:00 | 2020-10-07 18:00 | 2020-10-07 18:00 | 2020-10-07 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2077 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-10-07 18:00 |  |  | 100 | [120 empty] | 1098653
2842 | Task(Task)-->E (Engineering) | FAB. DETAIL OF BEND PULLEY GUARD FOR SC-3A/3B |  | 1.24.1.5 | Unscheduled | No | No | 2020-10-07 18:00 | 2020-10-07 18:00 | 2020-10-07 18:00 | 2020-10-07 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2078 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-10-07 18:00 |  |  | 100 | [120 empty] | 1098654
2843 | Task(Task)-->E (Engineering) | FAB. DETAIL OF BEND PULLEY GUARD FOR SC-1A/1B & SC-2A/2B |  | 1.24.1.5 | Unscheduled | No | No | 2020-10-07 18:00 | 2020-10-07 18:00 | 2020-10-07 18:00 | 2020-10-07 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2079 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-10-07 18:00 |  |  | 100 | [120 empty] | 1098655
2844 | Task(Task)-->E (Engineering) | FAB DETAIL OF HT BEND PULLEY GUARD FOR PIPE CONVEYOR PC-1A/1B & PC-2A/2B |  | 1.24.1.5 | Unscheduled | No | No | 2020-10-23 18:00 | 2020-10-23 18:00 | 2020-10-23 18:00 | 2020-10-23 18:00 | [6 empty] | 0 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2080 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-10-23 18:00 |  |  | 100 | [120 empty] | 1098656
2845 | Task(Task)-->E (Engineering) | FAB DETAIL OF LT BEND PULLEY GUARD FOR PIPE CONVEYOR PC-1A/1B & PC-2A/2B |  | 1.24.1.5 | Unscheduled | No | No | 2020-10-23 18:00 | 2020-10-23 18:00 | 2020-10-23 18:00 | 2020-10-23 18:00 | [6 empty] | 0 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2081 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-10-23 18:00 |  |  | 100 | [120 empty] | 1098657
2846 | Task(Task)-->E (Engineering) | FAB DETAIL OF LT BEND PULLEY GUARD FOR PIPE CONVEYOR PC-1A AT KDTP-2 & PC-2A AT KDTP-3. |  | 1.24.1.5 | Unscheduled | No | No | 2020-10-23 18:00 | 2020-10-23 18:00 | 2020-10-23 18:00 | 2020-10-23 18:00 | [6 empty] | 0 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2082 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-10-23 18:00 |  |  | 100 | [120 empty] | 1098658
2847 | Task(Task)-->E (Engineering) | FAB DETAIL OF TAIL DRIVE PULLEY GUARD FOR PIPE CONVEYOR PC-1A/1B AT SHB & C-2A/2B AT KDTP-2 |  | 1.24.1.5 | Unscheduled | No | No | 2020-10-23 18:00 | 2020-10-23 18:00 | 2020-10-23 18:00 | 2020-10-23 18:00 | [6 empty] | 0 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2083 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-10-23 18:00 |  |  | 100 | [120 empty] | 1098659
2848 | Task(Task)-->E (Engineering) | FAB. DETAIL OF DRIVE PULLEY FRAME GUARD FOR PC-1A -1, PC-1A -2 & PC-1B -1 AT KDTPC-2 AND PC-2A -1, PC-2A -2 & PC-2B -1 AT KDTPC-3 |  | 1.24.1.5 | Unscheduled | No | No | 2020-10-23 18:00 | 2020-10-23 18:00 | 2020-10-23 18:00 | 2020-10-23 18:00 | [6 empty] | 0 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2084 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-10-23 18:00 |  |  | 100 | [120 empty] | 1098660
2849 | Task(Task)-->E (Engineering) | FAB. DETAIL OF DRIVE PULLEY FRAME GUARD FOR PC-1B -2 AT KDTPC-2 AND PC-2B -2 AT KDTPC-3 |  | 1.24.1.5 | Unscheduled | No | No | 2020-10-23 18:00 | 2020-10-23 18:00 | 2020-10-23 18:00 | 2020-10-23 18:00 | [6 empty] | 0 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2085 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-10-23 18:00 |  |  | 100 | [120 empty] | 1098661
2850 | Task(Task)-->E (Engineering) | FAB. DETAIL OF GUARD AROUND VGTU TOWER FOR SC-1A/1B & SC-2A/2B |  | 1.24.1.5 | Unscheduled | No | No | 2020-10-23 18:00 | 2020-10-23 18:00 | 2020-10-23 18:00 | 2020-10-23 18:00 | [6 empty] | 0 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2086 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-10-23 18:00 |  |  | 100 | [120 empty] | 1098662
2851 | Task(Task)-->E (Engineering) | FAB. DETAIL OF GUARD AROUND VGTU TOWER FOR SC-3A/3B & SY-1A/1B |  | 1.24.1.5 | Unscheduled | No | No | 2020-10-23 18:00 | 2020-10-23 18:00 | 2020-10-23 18:00 | 2020-10-23 18:00 | [6 empty] | 0 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2087 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-10-23 18:00 |  |  | 100 | [120 empty] | 1098663
2852 | Task(Task)-->E (Engineering) | FAB. DETAIL OF GUARD AROUND HGTU TOWER FOR PIPE CONVEYOR PC-1A/1B & PC-2A/2B |  | 1.24.1.5 | Unscheduled | No | No | 2020-10-23 18:00 | 2020-10-23 18:00 | 2020-10-23 18:00 | 2020-10-23 18:00 | [6 empty] | 0 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2088 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-10-23 18:00 |  |  | 100 | [120 empty] | 1098664
2853 | Task(Task)-->E (Engineering) | GA AND MOUNTING ARRANGEMENT OF PULL CORD SWITCH, BELT SWAY SWITCH & ZERO SPEED SWITCH FOR TROUGH CONVEYOR |  | 1.24.1.5 | Unscheduled | No | No | 2020-10-30 18:00 | 2020-10-30 18:00 | 2020-10-30 18:00 | 2020-10-30 18:00 | [6 empty] | 0 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2090 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-10-30 18:00 |  |  | 100 | [120 empty] | 1098665
2854 | Task(Task)-->E (Engineering) | GA AND MOUNTING ARRANGEMENT OF PULL CORD SWITCH, BELT SWAY SWITCH & ZERO SPEED SWITCH FOR PIPE CONVEYOR |  | 1.24.1.5 | Unscheduled | No | No | 2020-10-30 18:00 | 2020-10-30 18:00 | 2020-10-30 18:00 | 2020-10-30 18:00 | [6 empty] | 0 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2091 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-10-30 18:00 |  |  | 100 | [120 empty] | 1098666
2855 | Task(Task)-->E (Engineering) | G A OF ZIG AND FIXER ARRANEGEMENT FOR PIPE CONVEYOR |  | 1.24.1.5 | Unscheduled | No | No | 2020-10-30 18:00 | 2020-10-30 18:00 | 2020-10-30 18:00 | 2020-10-30 18:00 | [6 empty] | 0 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2093 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-10-30 18:00 |  |  | 100 | [120 empty] | 1098667
2856 | Task(Task)-->E (Engineering) | BELT PULLING ARRANGEMENT FOR PIPE CONVEYOR |  | 1.24.1.5 | Unscheduled | No | No | 2020-10-30 18:00 | 2020-10-30 18:00 | 2020-10-30 18:00 | 2020-10-30 18:00 | [6 empty] | 0 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2094 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-10-30 18:00 |  |  | 100 | [120 empty] | 1098668
2857 | Task(Task)-->E (Engineering) | GA & ARRANGEMENT OF PADDLE SWITCH FOR PIPE CONVEYOR |  | 1.24.1.5 | Unscheduled | No | No | 2020-10-30 18:00 | 2020-10-30 18:00 | 2020-10-30 18:00 | 2020-10-30 18:00 | [6 empty] | 0 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2095 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-10-30 18:00 |  |  | 100 | [120 empty] | 1098669
2858 | Task(Task)-->E (Engineering) | MARKING DRAWING FOR CONV. SC 1AB,SC 2AB |  | 1.24.1.5 | Unscheduled | No | No | 2020-11-30 18:00 | 2020-11-30 18:00 | 2020-11-30 18:00 | 2020-11-30 18:00 | [6 empty] | 0 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2097 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-11-30 18:00 |  |  | 100 | [120 empty] | 1098670
2859 | Task(Task)-->E (Engineering) | MARKING DRAWING FOR CONV. SC 3AB |  | 1.24.1.5 | Unscheduled | No | No | 2020-11-30 18:00 | 2020-11-30 18:00 | 2020-11-30 18:00 | 2020-11-30 18:00 | [6 empty] | 0 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2098 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-11-30 18:00 |  |  | 100 | [120 empty] | 1098671
2860 | Task(Task)-->E (Engineering) | MARKING DRAWING FOR CONV. SY 1AB |  | 1.24.1.5 | Unscheduled | No | No | 2020-11-30 18:00 | 2020-11-30 18:00 | 2020-11-30 18:00 | 2020-11-30 18:00 | [6 empty] | 0 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2099 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-11-30 18:00 |  |  | 100 | [120 empty] | 1098672
2861 | Task(Task)-->E (Engineering) | MARKING DRAWING FOR BELT FEEDER BF-1/2 |  | 1.24.1.5 | Unscheduled | No | No | 2020-11-30 18:00 | 2020-11-30 18:00 | 2020-11-30 18:00 | 2020-11-30 18:00 | [6 empty] | 0 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2100 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-11-30 18:00 |  |  | 100 | [120 empty] | 1098673
2862 | Task(Task)-->E (Engineering) | MARKING DRAWING FOR DRIBBLE FEEDER DF-1/2/3/4 |  | 1.24.1.5 | Unscheduled | No | No | 2020-11-30 18:00 | 2020-11-30 18:00 | 2020-11-30 18:00 | 2020-11-30 18:00 | [6 empty] | 0 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2101 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-11-30 18:00 |  |  | 100 | [120 empty] | 1098674
2863 | Task(Task)-->E (Engineering) | MARKING DRAWING FOR PIPE CONV. PC 1AB |  | 1.24.1.5 | Unscheduled | No | No | 2020-11-30 18:00 | 2020-11-30 18:00 | 2020-11-30 18:00 | 2020-11-30 18:00 | [6 empty] | 0 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2102 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-11-30 18:00 |  |  | 100 | [120 empty] | 1098675
2864 | Task(Task)-->E (Engineering) | MARKING DRAWING FOR PIPE CONV. PC 2AB |  | 1.24.1.5 | Unscheduled | No | No | 2020-11-30 18:00 | 2020-11-30 18:00 | 2020-11-30 18:00 | 2020-11-30 18:00 | [6 empty] | 0 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2103 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-11-30 18:00 |  |  | 100 | [120 empty] | 1098676
2865 | Task(Task)-->E (Engineering) | FABRICATION DETAIL OF DEFLECTOR PLATE |  | 1.24.1.5 | Unscheduled | No | No | [10 empty] | 0 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2105 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1098677
2866 | Task(Task)-->E (Engineering) | FAB. DETAIL OF SUPPORTING ARRANGEMENT FOR METAL DETECTOR |  | 1.24.1.5 | Unscheduled | No | No | [10 empty] | 0 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2106 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1098678
2867 | Task(Task)-->P (Procurement) | PROCUREMENT | 1.24.2 | 1.24 | Work In Progress | No | No | 2019-08-01 18:00 | 2021-03-31 18:00 | 2019-08-01 18:00 | 2021-09-24 18:00 |  |  | 2020-01-13 16:08 |  |  |  | 80.373 | 30.2101 | [15 empty] | 76.8683 | 6.7817 | 666.94 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5128 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020040
2868 | Task(Task)-->P (Procurement) | PURCHASE REQUISITION | 1.24.2.1 | 1.24.2 | Work In Progress | No | No | 2019-08-01 18:00 | 2020-12-30 18:00 | 2019-08-01 18:00 | 2020-12-30 18:00 |  |  | 2020-01-13 16:08 |  |  |  | 100 | 97.602 | [15 empty] | 5.0004 | 0.33912 | 33.35 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5129 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020041
2869 | Task(Task)-->P (Procurement) | Manual Hoist |  | 1.24.2.1 | Completed | No | No | 2020-03-14 09:00 | 2020-03-14 18:00 | 2020-04-24 09:00 | 2020-04-24 18:00 |  |  | 2020-04-24 10:57 | 2020-04-24 10:57 |  |  | 100 | 100 | [15 empty] | 0.32974 | 0.001118 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5130 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020042
2870 | Task(Task)-->P (Procurement) | Electric Hoist |  | 1.24.2.1 | Completed | No | No | 2020-03-14 09:00 | 2020-03-14 18:00 | 2020-04-24 09:00 | 2020-04-24 18:00 |  |  | 2020-04-24 10:57 | 2020-04-24 10:57 |  |  | 100 | 100 | [15 empty] | 2.9376 | 0.009962 | 0.98 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5131 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020043
2871 | Task(Task)-->P (Procurement) | Belt Vulcanizer |  | 1.24.2.1 | Completed | No | No | 2020-01-01 09:00 | 2020-01-01 18:00 | 2020-04-28 09:00 | 2020-04-28 18:00 |  |  | 2020-04-28 10:57 | 2020-04-28 10:57 |  |  | 100 | 100 | [15 empty] | 0.89928 | 0.00305 | 0.3 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5132 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020044
2872 | Task(Task)-->P (Procurement) | HT CABLE (33KV & 6.6KV) |  | 1.24.2.1 | Completed | No | No | 2020-01-10 09:00 | 2020-01-10 18:00 | 2020-02-12 09:00 | 2020-02-12 18:00 |  |  | 2020-02-12 10:57 | 2020-02-12 10:57 |  |  | 100 | 100 | [15 empty] | 15.5276 | 0.052657 | 5.18 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5133 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020045
2873 | Task(Task)-->P (Procurement) | LT POWER CABLES |  | 1.24.2.1 | Completed | No | No | 2020-01-30 09:00 | 2020-01-30 18:00 | 2020-03-11 09:00 | 2020-03-11 18:00 |  |  | 2020-03-11 10:57 | 2020-03-11 10:57 |  |  | 100 | 100 | [15 empty] | 20.4736 | 0.06943 | 6.83 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5134 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020046
2874 | Task(Task)-->P (Procurement) | LIGHTING MAST |  | 1.24.2.1 | Completed | No | No | 2019-12-21 09:00 | 2019-12-21 18:00 | 2020-01-13 09:00 | 2020-01-13 18:00 |  |  | 2020-01-13 16:08 | 2020-01-13 16:08 |  |  | 100 | 100 | [15 empty] | 0.68945 | 0.002338 | 0.23 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5135 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020047
2875 | Task(Task)-->P (Procurement) | CABLE TRAY & ACCESSORIES |  | 1.24.2.1 | Completed | No | No | 2020-01-28 09:00 | 2020-01-28 18:00 | 2020-03-16 09:00 | 2020-03-16 18:00 |  |  | 2020-03-16 16:04 | 2020-03-16 16:04 |  |  | 100 | 100 | [15 empty] | 23.2014 | 0.07868 | 7.74 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5136 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020048
2876 | Task(Task)-->P (Procurement) | FLEXIBLE CABLE TRAY SUPPORTS |  | 1.24.2.1 | Completed | No | No | 2020-01-28 09:00 | 2020-01-28 18:00 | 2020-04-10 09:00 | 2020-04-10 18:00 |  |  | 2020-04-10 10:57 | 2020-04-10 10:57 |  |  | 100 | 100 | [15 empty] | 4.6763 | 0.015858 | 1.56 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5137 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020049
2877 | Task(Task)-->P (Procurement) | EARTHING & LIGHTNING PROTECTION MATERIALS |  | 1.24.2.1 | Completed | No | No | 2020-02-19 09:00 | 2020-02-19 18:00 | 2020-04-15 09:00 | 2020-04-15 18:00 |  |  | 2020-04-15 10:57 | 2020-04-15 10:57 |  |  | 100 | 100 | [15 empty] | 7.2842 | 0.024702 | 2.43 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5138 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020050
2878 | Task(Task)-->P (Procurement) | HT CABLE ACCESSORIES |  | 1.24.2.1 | Unscheduled | No | No | 2020-01-24 09:00 | 2020-01-24 18:00 | 2020-02-20 09:00 | 2020-02-20 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.77938 | 0.002643 | 0.26 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5139 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020051
2879 | Task(Task)-->P (Procurement) | LT CABLE ACCESSORIES |  | 1.24.2.1 | Unscheduled | No | No | 2020-02-07 09:00 | 2020-02-07 18:00 | 2020-06-20 09:00 | 2020-06-20 18:00 | [6 empty] | 100 | 0 | [15 empty] | 1.6187 | 0.005489 | 0.54 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5140 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020052
2880 | Task(Task)-->P (Procurement) | FO CABLE |  | 1.24.2.1 | Completed | No | No | 2020-02-05 09:00 | 2020-02-05 18:00 | 2020-04-15 09:00 | 2020-04-15 18:00 |  |  | 2020-04-15 10:57 | 2020-04-15 10:57 |  |  | 100 | 100 | [15 empty] | 1.4988 | 0.005083 | 0.5 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5141 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020053
2881 | Task(Task)-->P (Procurement) | RECEPTACLES |  | 1.24.2.1 | Completed | No | No | 2020-02-12 09:00 | 2020-02-12 18:00 | 2020-04-10 09:00 | 2020-04-10 18:00 |  |  | 2020-04-10 10:57 | 2020-04-10 10:57 |  |  | 100 | 100 | [15 empty] | 1.3489 | 0.004574 | 0.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5142 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020054
2882 | Task(Task)-->P (Procurement) | CONTROL CABLE |  | 1.24.2.1 | Completed | No | No | 2020-01-27 09:00 | 2020-01-27 18:00 | 2020-02-21 09:00 | 2020-02-21 18:00 |  |  | 2020-02-21 10:57 | 2020-02-21 10:57 |  |  | 100 | 100 | [15 empty] | 7.7038 | 0.026125 | 2.57 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5143 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020055
2883 | Task(Task)-->P (Procurement) | CCTV SYSTEM |  | 1.24.2.1 | Completed | No | No | 2020-01-10 09:00 | 2020-01-10 18:00 | 2020-01-14 09:00 | 2020-01-14 18:00 |  |  | 2020-01-14 10:57 | 2020-01-14 10:57 |  |  | 100 | 100 | [15 empty] | 3.8669 | 0.013113 | 1.29 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5234 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020056
2884 | Task(Task)-->P (Procurement) | PA SYSTEM |  | 1.24.2.1 | Completed | No | No | 2020-01-17 09:00 | 2020-01-17 18:00 | 2020-01-17 09:00 | 2020-01-17 18:00 |  |  | 2020-01-17 10:57 | 2020-01-17 10:57 |  |  | 100 | 100 | [15 empty] | 2.9976 | 0.010165 | 1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5233 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020057
2885 | Task(Task)-->P (Procurement) | INSTRUMENTATION CABLE |  | 1.24.2.1 | Completed | No | No | 2020-01-27 09:00 | 2020-01-27 18:00 | 2020-02-21 09:00 | 2020-02-21 18:00 |  |  | 2020-02-21 10:57 | 2020-02-21 10:57 |  |  | 100 | 100 | [15 empty] | 4.1667 | 0.01413 | 1.39 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5144 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020058
2886 | Task(Task)-->E (Engineering) | PACKAGE PR FOR 33KV OVERHEAD TRANSMISSION LINE(DOUBLE CIRCUIT) WITH 220KV MONOPOLE TOWER. |  | 1.24.2.1 | Unscheduled | No | No | [6 empty] | 2020-06-14 22:19 |  |  |  | 0 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-OHTL-001 |  | 2020-06-13 18:12 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1037864
2887 | Task(Task)-->E (Engineering) | 33/6.9kV,HT TRANSFORMER (ONAN TYPE) |  | 1.24.2.1 | Unscheduled | No | No | 2019-11-28 18:00 | 2019-11-28 18:00 | 2019-11-28 18:00 | 2019-11-28 18:00 |  |  | 2020-06-14 22:19 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-HTTRAF-002 |  | 2020-06-13 18:12 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2019-11-28 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:08 | [5 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037865
2888 | Task(Task)-->E (Engineering) | HT SWGR. (33kV & 6.6kV) |  | 1.24.2.1 | Unscheduled | No | No | 2019-11-13 18:00 | 2019-11-13 18:00 | 2019-11-13 18:00 | 2019-11-13 18:00 |  |  | 2020-06-14 22:19 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-HTBD-003 |  | 2020-06-13 18:12 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2019-11-13 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:08 | [5 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037866
2889 | Task(Task)-->E (Engineering) | 6.6kV HT VFD |  | 1.24.2.1 | Unscheduled | No | No | 2019-12-30 18:00 | 2019-12-30 18:00 | 2019-12-30 18:00 | 2019-12-30 18:00 |  |  | 2020-06-14 22:19 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-HTVFD-004 |  | 2020-06-13 18:12 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2019-12-30 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:08 | [5 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037867
2890 | Task(Task)-->E (Engineering) | 415V LT VFD |  | 1.24.2.1 | Unscheduled | No | No | 2019-12-18 18:00 | 2019-12-18 18:00 | 2019-12-18 18:00 | 2019-12-18 18:00 |  |  | 2020-06-14 22:19 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-LTVFD-005 |  | 2020-06-13 18:12 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2019-12-18 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:08 | [5 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037868
2891 | Task(Task)-->E (Engineering) | 6.6kV HT APFC PANEL |  | 1.24.2.1 | Unscheduled | No | No | 2020-01-24 18:00 | 2020-01-24 18:00 | 2020-01-24 18:00 | 2020-01-24 18:00 |  |  | 2020-06-14 22:19 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-HTAPFC-006 |  | 2020-06-13 18:12 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-01-24 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:08 | [5 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037869
2892 | Task(Task)-->E (Engineering) | HT AC MOTORS |  | 1.24.2.1 | Unscheduled | No | No | 2020-01-17 18:00 | 2020-01-17 18:00 | 2020-01-17 18:00 | 2020-01-17 18:00 |  |  | 2020-06-14 22:19 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-HTMOT-007 |  | 2020-06-13 18:12 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-01-17 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:08 | [5 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037870
2893 | Task(Task)-->E (Engineering) | 6.6kV/0.433V,LT TRANSFORMER (ONAN TYPE) |  | 1.24.2.1 | Unscheduled | No | No | 2019-11-25 18:00 | 2019-11-25 18:00 | 2019-11-25 18:00 | 2019-11-25 18:00 |  |  | 2020-06-14 22:19 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-LTTRAF-O08 |  | 2020-06-13 18:12 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2019-11-25 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:07 | [5 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037871
2894 | Task(Task)-->E (Engineering) | LT BUSDUCT |  | 1.24.2.1 | Unscheduled | No | No | 2019-12-02 18:00 | 2019-12-02 18:00 | 2019-12-02 18:00 | 2019-12-02 18:00 |  |  | 2020-06-14 22:19 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-LTBDT-009 |  | 2020-06-13 18:12 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2019-12-02 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:07 | [5 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037872
2895 | Task(Task)-->E (Engineering) | 415V PMCC |  | 1.24.2.1 | Unscheduled | No | No | 2019-11-28 18:00 | 2019-11-28 18:00 | 2019-11-28 18:00 | 2019-11-28 18:00 |  |  | 2020-06-14 22:19 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-LTMCC-010 |  | 2020-06-13 18:12 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2019-11-28 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:07 | [5 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037873
2896 | Task(Task)-->E (Engineering) | LT AC MOTORS |  | 1.24.2.1 | Unscheduled | No | No | 2019-12-16 18:00 | 2019-12-16 18:00 | 2019-12-16 18:00 | 2019-12-16 18:00 |  |  | 2020-06-14 22:19 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-LTMOT-011 |  | 2020-06-13 18:12 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2019-12-16 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:07 | [5 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037874
2897 | Task(Task)-->E (Engineering) | HT CABLE (33 kV & 6.6kV) |  | 1.24.2.1 | Unscheduled | No | No | 2020-01-10 18:00 | 2020-01-10 18:00 | 2020-01-10 18:00 | 2020-01-10 18:00 |  |  | 2020-06-14 22:19 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-HTCAB-012 |  | 2020-06-13 18:12 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-01-10 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:10 | [5 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037875
2898 | Task(Task)-->E (Engineering) | LT POWER CABLES |  | 1.24.2.1 | Unscheduled | No | No | 2020-01-30 18:00 | 2020-01-30 18:00 | 2020-01-30 18:00 | 2020-01-30 18:00 |  |  | 2020-06-14 22:19 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-LT POW. CABLE-013 |  | 2020-06-13 18:12 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-01-30 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:10 | [5 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037876
2899 | Task(Task)-->E (Engineering) | MAIN LIGHTING DISTRIBUTION BOARD |  | 1.24.2.1 | Unscheduled | No | No | 2020-03-25 18:00 | 2020-03-25 18:00 | 2020-03-25 18:00 | 2020-03-25 18:00 |  |  | 2020-06-14 22:19 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-MLDB-014 |  | 2020-06-13 18:12 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-03-25 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:10 | [5 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037877
2900 | Task(Task)-->E (Engineering) | LIGHTING PANELS |  | 1.24.2.1 | Unscheduled | No | No | 2020-03-25 18:00 | 2020-03-25 18:00 | 2020-03-25 18:00 | 2020-03-25 18:00 |  |  | 2020-06-19 11:29 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-LP-015 |  | 2020-06-13 18:12 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-03-25 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037878
2901 | Task(Task)-->E (Engineering) | LIGHTING FIXTURES |  | 1.24.2.1 | Unscheduled | No | No | 2020-03-25 18:00 | 2020-03-25 18:00 | 2020-03-25 18:00 | 2020-03-25 18:00 |  |  | 2020-06-14 22:19 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-LGT FIX.-016 |  | 2020-06-13 18:12 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-03-25 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:05 | [5 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037879
2902 | Task(Task)-->E (Engineering) | LIGHTING MAST |  | 1.24.2.1 | Unscheduled | No | No | 2019-12-21 18:00 | 2019-12-21 18:00 | 2019-12-21 18:00 | 2019-12-21 18:00 |  |  | 2020-06-14 22:19 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-LM-017 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2019-12-21 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:05 | [5 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037880
2903 | Task(Task)-->E (Engineering) | LIGHTING POLES |  | 1.24.2.1 | Unscheduled | No | No | 2020-04-30 18:00 | 2020-04-30 18:00 | 2020-04-30 18:00 | 2020-04-30 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-LP-018 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-04-30 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037881
2904 | Task(Task)-->E (Engineering) | LIGHTING WIRES |  | 1.24.2.1 | Unscheduled | No | No | 2020-04-30 18:00 | 2020-04-30 18:00 | 2020-04-30 18:00 | 2020-04-30 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-LGT. WIRE-019 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-04-30 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037882
2905 | Task(Task)-->E (Engineering) | WELDING DISTRIBUTION BOARD |  | 1.24.2.1 | Unscheduled | No | No | 2020-02-14 18:00 | 2020-02-14 18:00 | 2020-02-14 18:00 | 2020-02-14 18:00 |  |  | 2020-06-14 22:19 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-WDB-020 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-02-14 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:05 | [5 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037883
2906 | Task(Task)-->E (Engineering) | DCDB |  | 1.24.2.1 | Unscheduled | No | No | 2020-03-25 18:00 | 2020-03-25 18:00 | 2020-03-25 18:00 | 2020-03-25 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-DCDB-021 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-03-25 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037884
2907 | Task(Task)-->E (Engineering) | AC MCCB BOX |  | 1.24.2.1 | Unscheduled | No | No | 2020-03-25 18:00 | 2020-03-25 18:00 | 2020-03-25 18:00 | 2020-03-25 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-DB-022 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-03-25 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037885
2908 | Task(Task)-->E (Engineering) | 110 V DC BATTERY & BATTERY CHARGER SYSTEM |  | 1.24.2.1 | Unscheduled | No | No | 2020-01-13 18:00 | 2020-01-13 18:00 | 2020-01-13 18:00 | 2020-01-13 18:00 |  |  | 2020-06-14 22:19 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-DC SYS-023 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-01-13 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:05 | [5 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037886
2909 | Task(Task)-->E (Engineering) | LOCAL CONTROL STATIONS |  | 1.24.2.1 | Unscheduled | No | No | 2020-04-14 18:00 | 2020-04-14 18:00 | 2020-04-14 18:00 | 2020-04-14 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-LCS-024 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-04-14 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037887
2910 | Task(Task)-->E (Engineering) | RECEPTACLES |  | 1.24.2.1 | Unscheduled | No | No | 2020-03-31 18:00 | 2020-03-31 18:00 | 2020-03-31 18:00 | 2020-03-31 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-RECEPTACLES-025 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-03-31 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037888
2911 | Task(Task)-->E (Engineering) | LOCAL STARTER PANEL FOR SUMP PUMP |  | 1.24.2.1 | Unscheduled | No | No | 2020-05-30 18:00 | 2020-05-30 18:00 | 2020-05-30 18:00 | 2020-05-30 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-LSP SUMPS-026 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-05-30 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037889
2912 | Task(Task)-->E (Engineering) | SIREN |  | 1.24.2.1 | Unscheduled | No | No | 2020-04-30 18:00 | 2020-04-30 18:00 | 2020-04-30 18:00 | 2020-04-30 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-SIREN-027 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-04-30 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037890
2913 | Task(Task)-->E (Engineering) | CABLE TRAY & ACCESSORIES |  | 1.24.2.1 | Unscheduled | No | No | 2020-01-28 18:00 | 2020-01-28 18:00 | 2020-01-28 18:00 | 2020-01-28 18:00 |  |  | 2020-06-14 22:19 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-CABLETRAY & ACCS.-028 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-01-28 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:04 | [5 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037891
2914 | Task(Task)-->E (Engineering) | FLEXIBLE CABLE TRAY SUPPORTS |  | 1.24.2.1 | Unscheduled | No | No | 2020-03-31 18:00 | 2020-03-31 18:00 | 2020-03-31 18:00 | 2020-03-31 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-FLEX. CABLE TRAY-029 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-03-31 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037892
2915 | Task(Task)-->E (Engineering) | GI CONDUIT ,PIPE, LIGHTING CONDUIT & ACCESSORIES |  | 1.24.2.1 | Unscheduled | No | No | 2020-04-30 18:00 | 2020-04-30 18:00 | 2020-04-30 18:00 | 2020-04-30 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-GI/HUME PIPE-030 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-04-30 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037893
2916 | Task(Task)-->E (Engineering) | EARTHING & LIGHTNING PROTECTION MATERIALS |  | 1.24.2.1 | Unscheduled | No | No | 2020-03-31 18:00 | 2020-03-31 18:00 | 2020-03-31 18:00 | 2020-03-31 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-EARTHING& LIGHTNING-031 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-03-31 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037894
2917 | Task(Task)-->E (Engineering) | JUNCTION BOXES (POWER) |  | 1.24.2.1 | Unscheduled | No | No | 2020-04-14 18:00 | 2020-04-14 18:00 | 2020-04-14 18:00 | 2020-04-14 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-JB-032 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-04-14 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037895
2918 | Task(Task)-->E (Engineering) | LOCAL STARTERS FOR AXIAL FAN |  | 1.24.2.1 | Unscheduled | No | No | 2020-05-30 18:00 | 2020-05-30 18:00 | 2020-05-30 18:00 | 2020-05-30 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-MF1 START-033 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-05-30 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037896
2919 | Task(Task)-->E (Engineering) | STRUCTURAL STEEL FOR ELECTRICAL EQUIPMENT SUPPORT |  | 1.24.2.1 | Unscheduled | No | No | 2020-04-30 18:00 | 2020-04-30 18:00 | 2020-04-30 18:00 | 2020-04-30 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-STEEL-034 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-04-30 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037897
2920 | Task(Task)-->E (Engineering) | HT CABLE ACCESSORIES |  | 1.24.2.1 | Unscheduled | No | No | 2020-01-24 18:00 | 2020-01-24 18:00 | 2020-01-24 18:00 | 2020-01-24 18:00 |  |  | 2020-06-14 22:19 |  |  |  | 100 | 60 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-HTCABLE ACCSS.-035 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-01-24 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037898
2921 | Task(Task)-->E (Engineering) | 6.6KV NEUTRAL GROUNDING RESISTOR |  | 1.24.2.1 | Unscheduled | No | No | 2019-12-12 18:00 | 2019-12-12 18:00 | 2019-12-12 18:00 | 2019-12-12 18:00 |  |  | 2020-06-14 22:19 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-NGR-036 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2019-12-12 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:03 | [5 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037899
2922 | Task(Task)-->E (Engineering) | LT AC MOTORS FOR UTILITY SYSTEM |  | 1.24.2.1 | Unscheduled | No | No | 2020-01-16 18:00 | 2020-01-16 18:00 | 2020-01-16 18:00 | 2020-01-16 18:00 |  |  | 2020-06-14 22:19 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-UTLTMOT-037 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-01-16 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:03 | [5 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037900
2923 | Task(Task)-->E (Engineering) | LT CABLE ACCESSORIES |  | 1.24.2.1 | Unscheduled | No | No | 2020-05-15 18:00 | 2020-05-15 18:00 | 2020-05-15 18:00 | 2020-05-15 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-CABLE ACCSS.-038 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-05-15 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037901
2924 | Task(Task)-->E (Engineering) | FIRE SEALING MATERIALS |  | 1.24.2.1 | Unscheduled | No | No | 2020-04-30 18:00 | 2020-04-30 18:00 | 2020-04-30 18:00 | 2020-04-30 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-FIRESEALING-039 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-04-30 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037902
2925 | Task(Task)-->E (Engineering) | LIGHTING JUNCTION BOXES |  | 1.24.2.1 | Unscheduled | No | No | 2020-04-30 18:00 | 2020-04-30 18:00 | 2020-04-30 18:00 | 2020-04-30 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-LJB-040 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-04-30 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037903
2926 | Task(Task)-->E (Engineering) | MISCELLANEOUS ITEMS |  | 1.24.2.1 | Unscheduled | No | No | 2020-06-30 18:00 | 2020-06-30 18:00 | 2020-06-30 18:00 | 2020-06-30 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-MISC.-041 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-06-30 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037904
2927 | Task(Task)-->E (Engineering) | RUBBER MAT |  | 1.24.2.1 | Unscheduled | No | No | 2020-04-30 18:00 | 2020-04-30 18:00 | 2020-04-30 18:00 | 2020-04-30 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-RUBBER MAT-042 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-04-30 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037905
2928 | Task(Task)-->E (Engineering) | SCADA SYSTEM |  | 1.24.2.1 | Unscheduled | No | No | 2019-12-10 18:00 | 2019-12-10 18:00 | 2019-12-10 18:00 | 2019-12-10 18:00 |  |  | 2020-06-14 22:19 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-FOCAB-044 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2019-12-10 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:03 | [5 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037906
2929 | Task(Task)-->E (Engineering) | GENERAL CONDITION OF SUPPLY |  | 1.24.2.1 | Unscheduled | No | No | [6 empty] | 2020-06-14 22:26 |  |  |  | 0 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-GC01 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1037907
2930 | Task(Task)-->E (Engineering) | PRIMARY AND SECONDARY SIZERS |  | 1.24.2.1 | Completed | No | No | [6 empty] | 2020-06-14 22:26 | 2020-07-06 12:17 |  |  | 0 | 100 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-SZ01-08 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | [234 empty] | EK210PO0000012 | [9 empty] | 1037908
2931 | Task(Task)-->E (Engineering) | SECONDARY SIZER WITH MANDATORY SARES AND SLIDER BED |  | 1.24.2.1 | Unscheduled | No | No | [10 empty] | 0 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-SS01-04 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | [234 empty] | EK210PO0000012 | [9 empty] | 1037909
2932 | Task(Task)-->E (Engineering) | APRON FEEDER WITH MANDATORY SPARES |  | 1.24.2.1 | Unscheduled | No | No | [6 empty] | 2020-06-14 22:26 |  |  |  | 0 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-AF01-04 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1037910
2933 | Task(Task)-->E (Engineering) | IDLERS WITH SPARES FOR TROUGH BELT CONVEYOR |  | 1.24.2.1 | Completed | No | No | 2019-12-19 18:00 | 2019-12-19 18:00 | 2019-12-19 18:00 | 2019-12-19 18:00 |  |  | 2020-06-14 22:26 | 2020-07-06 12:17 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-ID01 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2019-12-19 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-07-06 12:13 | [5 empty] | 90 | [6 empty] | 100 | 2020-07-06 12:18 | [18 empty] | EK210PO0000040 | [9 empty] | 1037911
2934 | Task(Task)-->E (Engineering) | BELTING FOR TROUGH BELT CONVEYORS/FEEDER WITH MANDATORY SPARES |  | 1.24.2.1 | Unscheduled | No | No | 2019-11-07 18:00 | 2019-11-07 18:00 | 2019-11-07 18:00 | 2019-11-07 18:00 |  |  | 2020-06-14 22:26 |  |  |  | 100 | 60 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-BL01 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2019-11-07 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037912
2935 | Task(Task)-->E (Engineering) | PULLEYS WITH SPARES FOR TROUGH BELT CONVEYORS |  | 1.24.2.1 | Unscheduled | No | No | 2020-05-15 18:00 | 2020-05-15 18:00 | 2020-05-15 18:00 | 2020-05-15 18:00 |  |  | 2020-06-14 22:26 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-P001 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-05-15 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:36 | [5 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037913
2936 | Task(Task)-->E (Engineering) | PLUMMER BLOCKS WITH SPARES FOR TROUGH BELT CONVEYORS |  | 1.24.2.1 | Completed | No | No | 2020-05-18 | 2020-05-18 | 2020-05-17 23:59 | 2020-05-17 23:59 |  |  | 2020-06-14 22:26 | 2020-07-06 12:17 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-PL01 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-05-18 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-07-06 12:13 | [5 empty] | 90 | [6 empty] | 100 | 2020-07-06 12:18 | [18 empty] | EK210PO0000018 | [9 empty] | 1037914
2937 | Task(Task)-->E (Engineering) | BEARING WITH SAPRES FOR TROUGH BELT CONVEYOR PULLEYS |  | 1.24.2.1 | Completed | No | No | 2020-05-18 | 2020-05-18 | 2020-05-17 23:59 | 2020-05-17 23:59 |  |  | 2020-06-14 22:26 | 2020-07-06 12:17 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-B001 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-05-18 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-07-06 12:13 | [5 empty] | 90 | [6 empty] | 100 | 2020-07-06 12:18 | [18 empty] | EK210PO0000016 | [9 empty] | 1037915
2938 | Task(Task)-->E (Engineering) | FLUID COUPLINGS FOR TROUGH CONVEYORS WITH MANDATORY SPARES |  | 1.24.2.1 | Completed | No | No | 2019-11-25 18:00 | 2019-11-25 18:00 | 2019-11-25 18:00 | 2019-11-25 18:00 |  |  | 2020-06-14 22:26 | 2020-07-06 12:17 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-FC01 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2019-11-25 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-07-06 12:13 | [5 empty] | 90 | [6 empty] | 100 | 2020-07-06 12:18 | [18 empty] | EK210PO0000051 | [9 empty] | 1037916
2939 | Task(Task)-->E (Engineering) | GEARED COUPLING WITH SPARES FOR TROUGH BELT CONVEYORS |  | 1.24.2.1 | Completed | No | No | 2019-11-21 18:00 | 2019-11-21 18:00 | 2019-11-21 18:00 | 2019-11-21 18:00 |  |  | 2020-06-14 22:26 | 2020-07-06 12:17 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-GR01 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2019-11-21 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-07-06 12:13 | [5 empty] | 90 | [6 empty] | 100 | 2020-07-06 12:18 | [18 empty] | EK210PO0000022 | [9 empty] | 1037917
2940 | Task(Task)-->E (Engineering) | GEAR BOXES FOR TROUGH CONVEYORS & EQUIPMENT WITH MANDATORY SPARES |  | 1.24.2.1 | Completed | No | No | 2019-11-13 18:00 | 2019-11-13 18:00 | 2019-11-13 18:00 | 2019-11-13 18:00 |  |  | 2020-06-14 22:26 | 2020-07-06 12:17 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-GB01-06 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2019-11-13 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-07-06 12:13 | [5 empty] | 90 | [6 empty] | 100 | 2020-07-06 12:18 | [18 empty] | EK210PO0000041 | [9 empty] | 1037918
2941 | Task(Task)-->E (Engineering) | THRUSTOR BRAKE WITH SPARES FOR TROUGH BELT CONVEYOR |  | 1.24.2.1 | Unscheduled | No | No | 2019-12-18 18:00 | 2019-12-18 18:00 | 2019-12-18 18:00 | 2019-12-18 18:00 |  |  | 2020-06-14 22:26 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-BR01 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2019-12-18 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:36 | [5 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037919
2942 | Task(Task)-->E (Engineering) | INLINE MAGNETIC SEPARATOR AND SUSPENDED MAGNET WITH MANDATORY SPARES |  | 1.24.2.1 | Unscheduled | No | No | [6 empty] | 2020-06-14 22:26 |  |  |  | 0 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-MS01-08 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | [234 empty] | EK210PO0000010 | [9 empty] | 1037920
2943 | Task(Task)-->E (Engineering) | BELT WEIGH SCALE WITH MANDATORY SPARES FOR TROUGH BELT CONVEYORS |  | 1.24.2.1 | Completed | No | No | 2019-08-12 | 2019-08-12 | 2019-08-11 23:59 | 2019-08-11 23:59 |  |  | 2020-06-14 22:26 | 2020-07-06 12:17 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-BS01-04 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2019-08-12 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-07-06 12:13 | [5 empty] | 90 | [6 empty] | 100 | 2020-07-06 12:18 | [18 empty] | EK210PO0000014 | [9 empty] | 1037921
2944 | Task(Task)-->E (Engineering) | FLAP GATE |  | 1.24.2.1 | Unscheduled | No | No | 2020-02-06 18:00 | 2020-02-06 18:00 | 2020-02-06 18:00 | 2020-02-06 18:00 |  |  | 2020-06-14 22:26 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-FG01-10 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-02-06 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:21 | [5 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037922
2945 | Task(Task)-->E (Engineering) | ROD GATE |  | 1.24.2.1 | Unscheduled | No | No | 2019-09-25 18:00 | 2019-09-25 18:00 | 2019-09-25 18:00 | 2019-09-25 18:00 |  |  | 2020-06-14 22:26 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-RG01-02 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2019-09-25 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:21 | [5 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037923
2946 | Task(Task)-->E (Engineering) | RACK AND PINION GATE WITH MANDATORY SPARES |  | 1.24.2.1 | Unscheduled | No | No | 2019-09-25 18:00 | 2019-09-25 18:00 | 2019-09-25 18:00 | 2019-09-25 18:00 |  |  | 2020-06-14 22:26 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-RPG01-02 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2019-09-25 18:00 |  |  | 60 | 2020-06-14 22:54 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:21 | [5 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037924
2947 | Task(Task)-->E (Engineering) | METAL DETECTOR WITH MANDATORY SPARES |  | 1.24.2.1 | Completed | No | No | [6 empty] | 2020-06-14 22:26 | 2020-07-06 12:17 |  |  | 0 | 100 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-MD01-06 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | [234 empty] | EK210PO0000026 | [9 empty] | 1037925
2948 | Task(Task)-->E (Engineering) | ELECTRIC HOIST |  | 1.24.2.1 | Unscheduled | No | No | 2020-06-15 18:00 | 2020-06-15 18:00 | 2020-06-15 18:00 | 2020-06-15 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-EH01 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-06-15 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037926
2949 | Task(Task)-->E (Engineering) | MANUAL HOIST / CHAIN PULLEY BLOCK |  | 1.24.2.1 | Unscheduled | No | No | 2020-06-22 18:00 | 2020-06-22 18:00 | 2020-06-22 18:00 | 2020-06-22 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-MH01 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-06-22 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037927
2950 | Task(Task)-->E (Engineering) | EXTERNAL & INTERNAL SCRAPERS FOR CONVEYORS AND EQUIPMENTS WITH MANDATORY SPARES |  | 1.24.2.1 | Unscheduled | No | No | 2019-11-18 | 2019-11-18 | 2019-11-17 23:59 | 2019-11-17 23:59 |  |  | 2020-06-14 22:26 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-SC01 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2019-11-18 |  |  | 60 | 2020-06-14 22:54 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:21 | [5 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037928
2951 | Task(Task)-->E (Engineering) | FOUNDATION BOLTS WITH NUTS AND WASHERS |  | 1.24.2.1 | Unscheduled | No | No | 2020-05-15 18:00 | 2020-05-15 18:00 | 2020-05-15 18:00 | 2020-05-15 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-FB01 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-05-15 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037929
2952 | Task(Task)-->E (Engineering) | TROLLEY FOR HGTU FOR PIPE CONVEYOR |  | 1.24.2.1 | Unscheduled | No | No | 2020-05-22 18:00 | 2020-05-22 18:00 | 2020-05-22 18:00 | 2020-05-22 18:00 |  |  | 2020-07-18 23:01 |  |  |  | 100 | 60 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-TH01 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-05-22 18:00 |  |  | 60 | 2020-07-18 23:02 | [5 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037930
2953 | Task(Task)-->E (Engineering) | SCREW TAKEUP |  | 1.24.2.1 | Unscheduled | No | No | 2020-05-21 18:00 | 2020-05-21 18:00 | 2020-05-21 18:00 | 2020-05-21 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-ST01 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-05-21 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037931
2954 | Task(Task)-->E (Engineering) | ROPE SHEAVE |  | 1.24.2.1 | Unscheduled | No | No | 2020-05-19 18:00 | 2020-05-19 18:00 | 2020-05-19 18:00 | 2020-05-19 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-RS01 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-05-19 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037932
2955 | Task(Task)-->E (Engineering) | TAKE UP COMPONENTS FOR TROUGH BELT CONVEYORS |  | 1.24.2.1 | Unscheduled | No | No | 2020-05-19 18:00 | 2020-05-19 18:00 | 2020-05-19 18:00 | 2020-05-19 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-TU02 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-05-19 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037933
2956 | Task(Task)-->E (Engineering) | TIE ROD WITH FASTENERS FOR TROUGH BELT CONVEYORS |  | 1.24.2.1 | Unscheduled | No | No | 2020-05-19 18:00 | 2020-05-19 18:00 | 2020-05-19 18:00 | 2020-05-19 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-TU03 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-05-19 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037934
2957 | Task(Task)-->E (Engineering) | PRECAST CONCRETE COUNTER WEIGHT BLOCKS FOR TROUGH BELT CONVEYORS |  | 1.24.2.1 | Unscheduled | No | No | 2020-05-18 18:00 | 2020-05-18 18:00 | 2020-05-18 18:00 | 2020-05-18 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-CW01 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-05-18 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037935
2958 | Task(Task)-->E (Engineering) | CONV. TECH. STRUCTURE, CHUTES AND SKIRTS FOR TROUGH BELT CONVEYORS |  | 1.24.2.1 | Unscheduled | No | No | 2020-05-11 18:00 | 2020-05-11 18:00 | 2020-05-11 18:00 | 2020-05-11 18:00 |  |  | 2020-06-14 22:26 |  |  |  | 100 | 60 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-TS01 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-05-11 18:00 |  |  | 60 | 2020-06-14 22:54 | [5 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037936
2959 | Task(Task)-->E (Engineering) | SKIRT BOARD SEALING WITH MANDATORY SPARES |  | 1.24.2.1 | Unscheduled | No | No | 2020-05-14 18:00 | 2020-05-14 18:00 | 2020-05-14 18:00 | 2020-05-14 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-SB01 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-05-14 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037937
2960 | Task(Task)-->E (Engineering) | LUBRICANTS |  | 1.24.2.1 | Unscheduled | No | No | 2020-08-14 18:00 | 2020-08-14 18:00 | 2020-08-14 18:00 | 2020-08-14 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-LU01 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-08-14 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037938
2961 | Task(Task)-->E (Engineering) | BELT VULCANISER |  | 1.24.2.1 | Unscheduled | No | No | 2020-02-28 18:00 | 2020-02-28 18:00 | 2020-02-28 18:00 | 2020-02-28 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-BV01 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-02-28 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037939
2962 | Task(Task)-->E (Engineering) | TYRE COUPLING WITH MANDATORY SPARES FOR APRON FEEDERS |  | 1.24.2.1 | Unscheduled | No | No | 2020-03-05 18:00 | 2020-03-05 18:00 | 2020-03-05 18:00 | 2020-03-05 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-TC01 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-03-05 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [19 empty] | EK210PO0000024 | [9 empty] | 1037940
2963 | Task(Task)-->E (Engineering) | PRECAST CONCRETE COUNTER WEIGHT BLOCKS FOR PIPE CONVEYORS |  | 1.24.2.1 | Unscheduled | No | No | 2020-05-18 18:00 | 2020-05-18 18:00 | 2020-05-18 18:00 | 2020-05-18 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-PCW01 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-05-18 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037941
2964 | Task(Task)-->E (Engineering) | CONV. TECH. STRUCTURE, CHUTES AND SKIRTS FOR PIPE CONVEYORS |  | 1.24.2.1 | Unscheduled | No | No | 2020-05-11 18:00 | 2020-05-11 18:00 | 2020-05-11 18:00 | 2020-05-11 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-PTS01 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-05-11 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037942
2965 | Task(Task)-->E (Engineering) | SKIRT BOARD SEALING FOR PIPE CONVEYORS |  | 1.24.2.1 | Unscheduled | No | No | 2020-05-14 18:00 | 2020-05-14 18:00 | 2020-05-14 18:00 | 2020-05-14 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-PSB01 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-05-14 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037943
2966 | Task(Task)-->E (Engineering) | IDLERS WITH SPARES FOR PIPE CONVEYOR |  | 1.24.2.1 | Unscheduled | No | No | 2020-02-27 18:00 | 2020-02-27 18:00 | 2020-02-27 18:00 | 2020-02-27 18:00 |  |  | 2020-06-14 22:26 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-PID01 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-02-27 18:00 |  |  | 60 | 2020-06-14 22:54 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:20 | [5 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037944
2967 | Task(Task)-->E (Engineering) | BELTING WITH SPARES FOR PIPE CONVEYOR |  | 1.24.2.1 | Unscheduled | No | No | 2020-02-15 18:00 | 2020-02-15 18:00 | 2020-02-15 18:00 | 2020-02-15 18:00 |  |  | 2020-06-14 22:26 |  |  |  | 100 | 60 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-PBL01 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-02-15 18:00 |  |  | 60 | 2020-06-14 22:54 | [5 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037945
2968 | Task(Task)-->E (Engineering) | PULLEYS WITH SPARES FOR PIPE CONVEYORS |  | 1.24.2.1 | Unscheduled | No | No | 2020-05-15 18:00 | 2020-05-15 18:00 | 2020-05-15 18:00 | 2020-05-15 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-PP001 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-05-15 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037946
2969 | Task(Task)-->E (Engineering) | PLUMMER BLOCKS WITH SPARES FOR PIPE CONVEYORS |  | 1.24.2.1 | Unscheduled | No | No | 2020-05-18 | 2020-05-18 | 2020-05-17 23:59 | 2020-05-17 23:59 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-PPL01 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-05-18 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037947
2970 | Task(Task)-->E (Engineering) | BEARING WITH SAPRES FOR PIPE CONVEYOR PULLEYS |  | 1.24.2.1 | Unscheduled | No | No | 2020-05-18 | 2020-05-18 | 2020-05-17 23:59 | 2020-05-17 23:59 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-PB001 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-05-18 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037948
2971 | Task(Task)-->E (Engineering) | GEARED COUPLING WITH SPARES FOR PIPE CONVEYORS |  | 1.24.2.1 | Unscheduled | No | No | 2020-02-29 18:00 | 2020-02-29 18:00 | 2020-02-29 18:00 | 2020-02-29 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-PGR01 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-02-29 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037949
2972 | Task(Task)-->E (Engineering) | GEARBOX WITH SPARES FOR PIPE CONVEYORS |  | 1.24.2.1 | Unscheduled | No | No | 2020-02-21 18:00 | 2020-02-21 18:00 | 2020-02-21 18:00 | 2020-02-21 18:00 |  |  | 2020-06-14 22:26 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-PGB01 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-02-21 18:00 |  |  | 60 | 2020-06-14 22:54 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:21 | [5 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037950
2973 | Task(Task)-->E (Engineering) | DISC BRAKE WITH SPARES FOR PIPE CONVEYOR |  | 1.24.2.1 | Unscheduled | No | No | 2020-03-21 18:00 | 2020-03-21 18:00 | 2020-03-21 18:00 | 2020-03-21 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-PBR01 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-03-21 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037951
2974 | Task(Task)-->E (Engineering) | TAKE-UP WINCH WITH CAPSTON BRAKE FOR PIPE CONVEYORS |  | 1.24.2.1 | Unscheduled | No | No | 2020-05-19 18:00 | 2020-05-19 18:00 | 2020-05-19 18:00 | 2020-05-19 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-PTW01 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-05-19 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037952
2975 | Task(Task)-->E (Engineering) | WINCH WITH BRAKE FOR PIPE CONVEYORS |  | 1.24.2.1 | Unscheduled | No | No | 2020-05-19 18:00 | 2020-05-19 18:00 | 2020-05-19 18:00 | 2020-05-19 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-PW01 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-05-19 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037953
2976 | Task(Task)-->E (Engineering) | ROPE SHEAVE FOR PIPE CONVEYORS |  | 1.24.2.1 | Unscheduled | No | No | 2020-05-19 18:00 | 2020-05-19 18:00 | 2020-05-19 18:00 | 2020-05-19 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-PTU01 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-05-19 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037954
2977 | Task(Task)-->E (Engineering) | TAKE UP COMPONENTS FOR PIPE CONVEYORS |  | 1.24.2.1 | Unscheduled | No | No | 2020-05-19 18:00 | 2020-05-19 18:00 | 2020-05-19 18:00 | 2020-05-19 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-PTU02 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-05-19 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037955
2978 | Task(Task)-->E (Engineering) | TIE ROD WITH FASTENERS FOR PIPE CONVEYORS |  | 1.24.2.1 | Unscheduled | No | No | 2020-05-19 18:00 | 2020-05-19 18:00 | 2020-05-19 18:00 | 2020-05-19 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-PTU03 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-05-19 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037956
2979 | Task(Task)-->E (Engineering) | CONVEYOR HOOD FOR TROUGH CONVEYORS |  | 1.24.2.1 | Unscheduled | No | No | 2020-05-19 18:00 | 2020-05-19 18:00 | 2020-05-19 18:00 | 2020-05-19 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-HD01-02 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-05-19 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037957
2980 | Task(Task)-->E (Engineering) | PR FOR DS, SW & PW SYSTEM AND SPARES |  | 1.24.2.1 | Unscheduled | No | No | 2019-08-01 18:00 | 2019-08-01 18:00 | 2019-08-01 18:00 | 2019-08-01 18:00 |  |  | 2020-06-14 22:49 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->5(Equipment Design) | O19133-M-BM-CS-SP-DS01 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2019-08-01 18:00 |  |  | 60 | 2020-06-14 22:54 | [5 empty] | 70 | [6 empty] | 80 | 2020-06-16 16:44 | [5 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037958
2981 | Task(Task)-->E (Engineering) | PR FOR VENTILATION SYSTEM AND SPARES |  | 1.24.2.1 | Unscheduled | No | No | 2019-08-01 18:00 | 2019-08-01 18:00 | 2019-08-01 18:00 | 2019-08-01 18:00 |  |  | 2020-06-14 22:49 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->5(Equipment Design) | O19133-M-BM-CS-SP-VS-01 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2019-08-01 18:00 |  |  | 60 | 2020-06-14 22:54 | [5 empty] | 70 | [6 empty] | 80 | 2020-06-16 16:44 | [5 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037959
2982 | Task(Task)-->E (Engineering) | PR FOR AIR CONDITIONING SYSTEM & SPARES |  | 1.24.2.1 | Unscheduled | No | No | 2019-08-03 18:00 | 2019-08-03 18:00 | 2019-08-03 18:00 | 2019-08-03 18:00 |  |  | 2020-06-14 22:49 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->5(Equipment Design) | O19133-M-BM-CS-SP-AC-01 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2019-08-03 18:00 |  |  | 60 | 2020-06-14 22:54 | [5 empty] | 70 | [6 empty] | 80 | 2020-06-16 16:44 | [5 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037960
2983 | Task(Task)-->E (Engineering) | PR FOR FIRE FIGHTING SYSTEM AND SPARES |  | 1.24.2.1 | Unscheduled | No | No | 2019-08-13 18:00 | 2019-08-13 18:00 | 2019-08-13 18:00 | 2019-08-13 18:00 |  |  | 2020-06-14 22:49 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->5(Equipment Design) | O19133-M-BM-CS-SP-FF-01 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2019-08-13 18:00 |  |  | 60 | 2020-06-14 22:54 | [5 empty] | 70 | [6 empty] | 80 | 2020-06-16 16:44 | [5 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037961
2984 | Task(Task)-->E (Engineering) | PR FOR BOREWELL SYSTEM |  | 1.24.2.1 | Unscheduled | No | No | 2019-08-26 18:00 | 2019-08-26 18:00 | 2019-08-26 18:00 | 2019-08-26 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->5(Equipment Design) | O19133-M-BM-CS-SP-BB-01 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2019-08-26 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037962
2985 | Task(Task)-->E (Engineering) | PLC System |  | 1.24.2.1 | Unscheduled | No | No | 2019-11-12 18:00 | 2019-11-12 18:00 | 2019-11-12 18:00 | 2019-11-12 18:00 |  |  | 2020-06-14 22:45 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->4(Instrumentation & Control) | O19133-C&I-BM-CS-0001 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2019-11-12 18:00 |  |  | 60 | 2020-06-14 22:54 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:03 | [5 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037963
2986 | Task(Task)-->E (Engineering) | UPS System |  | 1.24.2.1 | Unscheduled | No | No | 2020-01-08 18:00 | 2020-01-08 18:00 | 2020-01-08 18:00 | 2020-01-08 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->4(Instrumentation & Control) | O19133-C&I-BM-CS-0002 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-01-08 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037964
2987 | Task(Task)-->E (Engineering) | 24V DC Battery and Battery Charger System |  | 1.24.2.1 | Unscheduled | No | No | 2020-01-27 18:00 | 2020-01-27 18:00 | 2020-01-27 18:00 | 2020-01-27 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->4(Instrumentation & Control) | O19133-C&I-BM-CS-0003 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-01-27 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037965
2988 | Task(Task)-->E (Engineering) | CCTV System (IP based) |  | 1.24.2.1 | Unscheduled | No | No | 2020-01-10 18:00 | 2020-01-10 18:00 | 2020-01-10 18:00 | 2020-01-10 18:00 |  |  | 2020-06-14 22:45 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->4(Instrumentation & Control) | O19133-C&I-BM-CS-0004 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-01-10 18:00 |  |  | 60 | 2020-06-14 22:54 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:02 | [5 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037966
2989 | Task(Task)-->E (Engineering) | PA System (IP based) |  | 1.24.2.1 | Unscheduled | No | No | 2020-01-17 18:00 | 2020-01-17 18:00 | 2020-01-17 18:00 | 2020-01-17 18:00 |  |  | 2020-06-14 22:45 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->4(Instrumentation & Control) | O19133-C&I-BM-CS-0005 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-01-17 18:00 |  |  | 60 | 2020-06-14 22:54 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:01 | [5 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037967
2990 | Task(Task)-->E (Engineering) | Control and Instrumentation Cable |  | 1.24.2.1 | Unscheduled | No | No | 2020-01-21 18:00 | 2020-01-21 18:00 | 2020-01-21 18:00 | 2020-01-21 18:00 |  |  | 2020-06-19 12:32 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->4(Instrumentation & Control) | O19133-C&I-BM-CS-0006 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-01-21 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037968
2991 | Task(Task)-->E (Engineering) | Addressable Conveyor Belt Protection Switches (PCS, BSS, Pull Cord Wire & I - Hooks & Pull cord indication system) |  | 1.24.2.1 | Unscheduled | No | No | 2020-01-08 18:00 | 2020-01-08 18:00 | 2020-01-08 18:00 | 2020-01-08 18:00 |  |  | 2020-06-14 22:45 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->4(Instrumentation & Control) | O19133-C&I-BM-CS-0007 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-01-08 18:00 |  |  | 60 | 2020-06-14 22:54 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:01 | [5 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037969
2992 | Task(Task)-->E (Engineering) | Zero Speed Switch |  | 1.24.2.1 | Unscheduled | No | No | 2020-12-30 18:00 | 2020-12-30 18:00 | 2020-12-30 18:00 | 2020-12-30 18:00 |  |  | 2020-06-14 22:45 |  |  |  | 0 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->4(Instrumentation & Control) | O19133-C&I-BM-CS-0008 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-12-30 18:00 |  |  | 60 | 2020-06-14 22:54 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:01 | [5 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037970
2993 | Task(Task)-->E (Engineering) | Chute Block Switch |  | 1.24.2.1 | Unscheduled | No | No | 2020-01-02 18:00 | 2020-01-02 18:00 | 2020-01-02 18:00 | 2020-01-02 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->4(Instrumentation & Control) | O19133-C&I-BM-CS-0009 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-01-02 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037971
2994 | Task(Task)-->E (Engineering) | Control Junction Box |  | 1.24.2.1 | Unscheduled | No | No | 2020-03-03 18:00 | 2020-03-03 18:00 | 2020-03-03 18:00 | 2020-03-03 18:00 |  |  | 2020-06-14 22:45 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->4(Instrumentation & Control) | O19133-C&I-BM-CS-0010 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-03-03 18:00 |  |  | 60 | 2020-06-14 22:54 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:01 | [5 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037972
2995 | Task(Task)-->E (Engineering) | UPS / 24V DC DB |  | 1.24.2.1 | Unscheduled | No | No | 2020-02-19 18:00 | 2020-02-19 18:00 | 2020-02-19 18:00 | 2020-02-19 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->4(Instrumentation & Control) | O19133-C&I-BM-CS-0011 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-02-19 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037973
2996 | Task(Task)-->E (Engineering) | Singlechannel Temperature Transmitter |  | 1.24.2.1 | Unscheduled | No | No | 2020-02-12 18:00 | 2020-02-12 18:00 | 2020-02-12 18:00 | 2020-02-12 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->4(Instrumentation & Control) | O19133-C&I-BM-CS-0012 |  | 2020-06-13 18:15 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-02-12 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037974
2997 | Task(Task)-->E (Engineering) | Communication Cable (FO) |  | 1.24.2.1 | Unscheduled | No | No | 2020-02-05 18:00 | 2020-02-05 18:00 | 2020-02-05 18:00 | 2020-02-05 18:00 |  |  | 2020-06-14 22:45 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->4(Instrumentation & Control) | O19133-C&I-BM-CS-0013 |  | 2020-06-13 18:15 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-02-05 18:00 |  |  | 60 | 2020-06-14 22:54 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:00 | [5 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037975
2998 | Task(Task)-->E (Engineering) | FDA System |  | 1.24.2.1 | Unscheduled | No | No | 2020-02-14 18:00 | 2020-02-14 18:00 | 2020-02-14 18:00 | 2020-02-14 18:00 |  |  | 2020-06-14 22:45 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->4(Instrumentation & Control) | O19133-C&I-BM-CS-0014 |  | 2020-06-13 18:15 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-02-14 18:00 |  |  | 60 | 2020-06-14 22:54 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:00 | [5 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037976
2999 | Task(Task)-->E (Engineering) | Limit Switch |  | 1.24.2.1 | Unscheduled | No | No | 2020-02-14 18:00 | 2020-02-14 18:00 | 2020-02-14 18:00 | 2020-02-14 18:00 |  |  | 2020-06-14 22:45 |  |  |  | 100 | 60 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->4(Instrumentation & Control) | OXXXXX-C&I-BM-CS-XXXX |  | 2020-06-13 18:15 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-02-14 18:00 |  |  | 60 | 2020-06-14 22:54 | [5 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [29 empty] | 1037977
3000 | Task(Task)-->E (Engineering) | CABLE LUGS AND GLANDS |  | 1.24.2.1 | Unscheduled | No | No | [6 empty] | 2020-06-30 16:32 |  |  |  | 0 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-LG-045 | [10 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1044541
3001 | Task(Task)-->E (Engineering) | RELAY TESTING KIT |  | 1.24.2.1 | Unscheduled | No | No | [6 empty] | 2020-06-30 16:45 |  |  |  | 0 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-RLYKIT-043 | [10 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1044542
3002 | Task(Task)-->E (Engineering) | Maintenance Trolley |  | 1.24.2.1 | Unscheduled | No | No | 2020-07-20 | 2020-07-20 | 2020-07-19 23:59 | 2020-07-19 23:59 |  |  | 2020-07-19 16:04 |  |  |  | 100 | 60 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-MT02 |  | 2020-07-19 16:03 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-07-20 |  |  | 60 | 2020-07-19 16:11 | [5 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [8 empty] | H - Material Handling and Equipment | [20 empty] | 1098720
3003 | Task(Task)-->P (Procurement) | PR DEMO DOCUMENT |  | 1.24.2.1 | Unscheduled | No | No | [6 empty] | 2020-07-21 12:14 |  |  |  | 0 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->1(Civil & Structural) | DEMO-001 | [10 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1098760
3004 | Task(Task)-->P (Procurement) | TECHNICAL CLEARANCE | 1.24.2.2 | 1.24.2 | Work In Progress | No | No | 2019-12-22 | 2020-05-13 18:00 | 2020-01-13 09:00 | 2020-10-15 18:00 |  |  | 2020-01-15 16:14 |  |  |  | 100 | 96.7026 | [15 empty] | 5.0004 | 0.33912 | 33.35 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5145 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020059
3005 | Task(Task)-->P (Procurement) | Manual Hoist |  | 1.24.2.2 | Completed | No | No | 2020-03-15 | 2020-03-30 18:00 | 2020-04-24 09:00 | 2020-06-10 18:00 |  |  | 2020-06-10 10:57 | 2020-06-10 10:57 |  |  | 100 | 100 | [15 empty] | 0.32974 | 0.001118 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5146 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020060
3006 | Task(Task)-->P (Procurement) | Electric Hoist |  | 1.24.2.2 | Completed | No | No | 2020-03-15 | 2020-03-25 18:00 | 2020-04-24 09:00 | 2020-06-11 18:00 |  |  | 2020-06-11 10:57 | 2020-06-11 10:57 |  |  | 100 | 100 | [15 empty] | 2.9376 | 0.009962 | 0.98 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5147 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020061
3007 | Task(Task)-->P (Procurement) | Belt Vulcanizer |  | 1.24.2.2 | Unscheduled | No | No | 2020-01-02 09:00 | 2020-05-13 18:00 | 2020-04-28 09:00 | 2020-10-15 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.89928 | 0.00305 | 0.3 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5148 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020062
3008 | Task(Task)-->P (Procurement) | HT CABLE (33KV & 6.6KV) |  | 1.24.2.2 | Completed | No | No | 2020-01-11 09:00 | 2020-01-25 18:00 | 2020-02-12 09:00 | 2020-05-03 23:59 |  |  | 2020-05-03 10:57 | 2020-05-03 10:57 |  |  | 100 | 100 | [15 empty] | 15.5276 | 0.052657 | 5.18 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5149 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020063
3009 | Task(Task)-->P (Procurement) | LT POWER CABLES |  | 1.24.2.2 | Completed | No | No | 2020-01-31 09:00 | 2020-02-13 18:00 | 2020-03-11 09:00 | 2020-05-04 18:00 |  |  | 2020-05-04 10:57 | 2020-05-04 10:57 |  |  | 100 | 100 | [15 empty] | 20.4736 | 0.06943 | 6.83 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5150 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020064
3010 | Task(Task)-->P (Procurement) | LIGHTING MAST |  | 1.24.2.2 | Completed | No | No | 2019-12-22 | 2020-01-13 18:00 | 2020-01-13 09:00 | 2020-04-28 18:00 |  |  | 2020-01-15 16:14 | 2020-04-28 16:14 |  |  | 100 | 100 | [15 empty] | 0.68945 | 0.002338 | 0.23 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5151 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020065
3011 | Task(Task)-->P (Procurement) | CABLE TRAY & ACCESSORIES |  | 1.24.2.2 | Completed | No | No | 2020-01-29 09:00 | 2020-02-05 18:00 | 2020-03-16 09:00 | 2020-05-04 18:00 |  |  | 2020-03-16 16:05 | 2020-05-04 16:05 |  |  | 100 | 100 | [15 empty] | 23.2014 | 0.07868 | 7.74 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5152 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020066
3012 | Task(Task)-->P (Procurement) | FLEXIBLE CABLE TRAY SUPPORTS |  | 1.24.2.2 | Completed | No | No | 2020-01-29 09:00 | 2020-02-06 18:00 | 2020-04-10 09:00 | 2020-05-08 18:00 |  |  | 2020-05-08 10:57 | 2020-05-08 10:57 |  |  | 100 | 100 | [15 empty] | 4.6763 | 0.015858 | 1.56 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5153 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020067
3013 | Task(Task)-->P (Procurement) | E ARTHING & LIGHTNING PROTECTION MATERIALS |  | 1.24.2.2 | Completed | No | No | 2020-02-20 09:00 | 2020-04-18 18:00 | 2020-04-15 09:00 | 2020-06-06 18:00 |  |  | 2020-04-16 17:16 | 2020-06-06 17:16 |  |  | 100 | 100 | [15 empty] | 7.2842 | 0.024702 | 2.43 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5154 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020068
3014 | Task(Task)-->P (Procurement) | HT CABLE ACCESSORIES |  | 1.24.2.2 | Unscheduled | No | No | 2020-01-25 09:00 | 2020-02-17 18:00 | 2020-02-20 09:00 | 2020-04-02 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.77938 | 0.002643 | 0.26 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5155 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020069
3015 | Task(Task)-->P (Procurement) | LT CABLE ACCESSORIES |  | 1.24.2.2 | Unscheduled | No | No | 2020-02-08 09:00 | 2020-02-15 18:00 | 2020-06-20 09:00 | 2020-06-20 18:00 | [6 empty] | 100 | 0 | [15 empty] | 1.6187 | 0.005489 | 0.54 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5156 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020070
3016 | Task(Task)-->P (Procurement) | FO CABLE |  | 1.24.2.2 | Completed | No | No | 2020-02-06 09:00 | 2020-02-14 18:00 | 2020-04-15 09:00 | 2020-07-16 18:00 |  |  | 2020-07-16 18:13 | 2020-07-16 18:14 |  |  | 100 | 100 | [15 empty] | 1.4988 | 0.005083 | 0.5 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5157 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020071
3017 | Task(Task)-->P (Procurement) | RECEPTACLES |  | 1.24.2.2 | Completed | No | No | 2020-02-13 09:00 | 2020-02-25 18:00 | 2020-04-10 09:00 | 2020-05-19 18:00 |  |  | 2020-05-19 10:57 | 2020-05-19 10:57 |  |  | 100 | 100 | [15 empty] | 1.3489 | 0.004574 | 0.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5158 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020072
3018 | Task(Task)-->P (Procurement) | CONTROL CABLE |  | 1.24.2.2 | Completed | No | No | 2020-01-28 09:00 | 2020-02-04 18:00 | 2020-02-21 09:00 | 2020-05-08 18:00 |  |  | 2020-05-08 10:57 | 2020-05-08 10:57 |  |  | 100 | 100 | [15 empty] | 7.7038 | 0.026125 | 2.57 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5159 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020073
3019 | Task(Task)-->P (Procurement) | CCTV SYSTEM |  | 1.24.2.2 | Completed | No | No | 2020-01-11 09:00 | 2020-02-17 18:00 | 2020-01-14 09:00 | 2020-05-04 18:00 |  |  | 2020-05-04 10:57 | 2020-05-04 10:57 |  |  | 100 | 100 | [15 empty] | 3.8669 | 0.013113 | 1.29 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5236 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020074
3020 | Task(Task)-->P (Procurement) | PA SYSTEM |  | 1.24.2.2 | Completed | No | No | 2020-01-18 09:00 | 2020-02-12 18:00 | 2020-01-17 09:00 | 2020-05-04 18:00 |  |  | 2020-05-04 10:57 | 2020-05-04 10:57 |  |  | 100 | 100 | [15 empty] | 2.9976 | 0.010165 | 1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5235 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020075
3021 | Task(Task)-->P (Procurement) | INSTRUMENTATION CABLE |  | 1.24.2.2 | Completed | No | No | 2020-01-28 09:00 | 2020-02-04 18:00 | 2020-02-21 09:00 | 2020-05-08 18:00 |  |  | 2020-05-08 10:57 | 2020-05-08 10:57 |  |  | 100 | 100 | [15 empty] | 4.1667 | 0.01413 | 1.39 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5160 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020076
3022 | Task(Task)-->P (Procurement) | ORDERING | 1.24.2.3 | 1.24.2 | Work In Progress | No | No | 2020-01-14 09:00 | 2020-06-16 18:00 | 2020-04-02 09:00 | 2020-11-14 18:00 |  |  | 2020-05-04 17:26 |  |  |  | 100 | 48.8159 | [15 empty] | 9.9994 | 0.67813 | 66.69 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5161 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020077
3023 | Task(Task)-->P (Procurement) | Manual Hoist |  | 1.24.2.3 | Completed | No | No | 2020-03-31 09:00 | 2020-04-29 18:00 | 2020-06-10 09:00 | 2020-07-03 18:00 |  |  | 2020-06-11 14:46 | 2020-07-03 14:46 |  |  | 100 | 100 | [15 empty] | 0.31475 | 0.002134 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5162 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020078
3024 | Task(Task)-->P (Procurement) | Electric Hoist |  | 1.24.2.3 | Completed | No | No | 2020-03-26 09:00 | 2020-04-24 18:00 | 2020-06-11 09:00 | 2020-07-17 18:00 |  |  | 2020-06-11 01:10 | 2020-07-17 01:10 |  |  | 100 | 100 | [15 empty] | 2.9526 | 0.020023 | 1.97 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5163 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020079
3025 | Task(Task)-->P (Procurement) | Belt Vulcanizer |  | 1.24.2.3 | Unscheduled | No | No | 2020-05-14 09:00 | 2020-06-12 18:00 | 2020-10-16 09:00 | 2020-11-14 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.89928 | 0.006098 | 0.6 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5164 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020080
3026 | Task(Task)-->P (Procurement) | HT CABLE (33KV & 6.6KV) |  | 1.24.2.3 | Unscheduled | No | No | 2020-01-26 | 2020-02-10 18:00 | 2020-05-03 | 2020-08-17 18:00 | [6 empty] | 100 | 0 | [15 empty] | 15.5276 | 0.1053 | 10.36 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5165 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020081
3027 | Task(Task)-->P (Procurement) | LT POWER CABLES |  | 1.24.2.3 | Unscheduled | No | No | 2020-02-14 09:00 | 2020-02-28 18:00 | 2020-05-04 09:00 | 2020-08-17 18:00 | [6 empty] | 100 | 0 | [15 empty] | 20.4886 | 0.13894 | 13.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5166 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020082
3028 | Task(Task)-->P (Procurement) | LIGHTING MAST |  | 1.24.2.3 | Completed | No | No | 2020-01-14 09:00 | 2020-02-05 18:00 | 2020-04-28 09:00 | 2020-06-11 18:00 |  |  | 2020-06-11 10:18 | 2020-06-11 10:18 |  |  | 100 | 100 | [15 empty] | 0.68945 | 0.004675 | 0.46 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5167 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020083
3029 | Task(Task)-->P (Procurement) | CABLE TRAY & ACCESSORIES |  | 1.24.2.3 | Completed | No | No | 2020-02-06 09:00 | 2020-02-15 18:00 | 2020-05-04 09:00 | 2020-08-07 18:00 |  |  | 2020-05-05 16:06 | 2020-07-06 16:06 |  |  | 100 | 100 | [15 empty] | 23.1865 | 0.15724 | 15.47 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5168 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020084
3030 | Task(Task)-->P (Procurement) | FLEXIBLE CABLE TRAY SUPPORTS |  | 1.24.2.3 | Completed | No | No | 2020-02-07 09:00 | 2020-02-15 18:00 | 2020-05-08 09:00 | 2020-08-07 18:00 |  |  | 2020-05-09 16:07 | 2020-07-06 16:07 |  |  | 100 | 100 | [15 empty] | 4.6763 | 0.031711 | 3.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5169 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020085
3031 | Task(Task)-->P (Procurement) | EARTHING & LIGHTNING PROTECTION MATERIALS |  | 1.24.2.3 | Completed | No | No | 2020-04-19 | 2020-06-16 18:00 | 2020-06-06 09:00 | 2020-08-17 18:00 |  |  | 2020-06-08 17:15 | 2020-07-06 17:15 |  |  | 100 | 100 | [15 empty] | 7.2992 | 0.049498 | 4.87 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5170 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020086
3032 | Task(Task)-->P (Procurement) | HT CABLE ACCESSORIES |  | 1.24.2.3 | Unscheduled | No | No | 2020-02-18 09:00 | 2020-03-12 18:00 | 2020-04-02 09:00 | 2020-09-09 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.77938 | 0.005285 | 0.52 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5171 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020087
3033 | Task(Task)-->P (Procurement) | LT CABLE ACCESSORIES |  | 1.24.2.3 | Unscheduled | No | No | 2020-02-16 | 2020-03-03 18:00 | 2020-06-20 09:00 | 2020-10-30 18:00 | [6 empty] | 100 | 0 | [15 empty] | 1.6187 | 0.010977 | 1.08 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5172 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020088
3034 | Task(Task)-->P (Procurement) | FO CABLE |  | 1.24.2.3 | Completed | No | No | 2020-02-15 09:00 | 2020-02-24 18:00 | 2020-07-16 09:00 | 2020-07-27 18:00 |  |  | 2020-07-27 18:14 | 2020-07-27 18:14 |  |  | 100 | 100 | [15 empty] | 1.4988 | 0.010164 | 1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5173 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020089
3035 | Task(Task)-->P (Procurement) | RECEPTACLES |  | 1.24.2.3 | Completed | No | No | 2020-02-26 09:00 | 2020-03-10 18:00 | 2020-05-19 09:00 | 2020-07-18 18:00 |  |  | 2020-07-13 22:33 | 2020-07-13 22:33 |  |  | 100 | 100 | [15 empty] | 1.3339 | 0.009046 | 0.89 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5174 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020090
3036 | Task(Task)-->P (Procurement) | CONTROL CABLE |  | 1.24.2.3 | Unscheduled | No | No | 2020-02-05 09:00 | 2020-02-12 18:00 | 2020-05-08 09:00 | 2020-10-30 18:00 | [6 empty] | 100 | 0 | [15 empty] | 7.7038 | 0.052242 | 5.14 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5175 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020091
3037 | Task(Task)-->P (Procurement) | CCTV SYSTEM |  | 1.24.2.3 | Completed | No | No | 2020-02-18 09:00 | 2020-03-27 18:00 | 2020-05-04 09:00 | 2020-07-18 18:00 |  |  | 2020-05-05 17:27 | 2020-06-24 17:27 |  |  | 100 | 100 | [15 empty] | 3.8669 | 0.026223 | 2.58 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5238 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020092
3038 | Task(Task)-->P (Procurement) | PA SYSTEM |  | 1.24.2.3 | Completed | No | No | 2020-02-13 09:00 | 2020-03-10 18:00 | 2020-05-04 09:00 | 2020-08-17 18:00 |  |  | 2020-05-04 17:26 | 2020-06-20 17:26 |  |  | 100 | 100 | [15 empty] | 2.9976 | 0.020328 | 2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5237 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020093
3039 | Task(Task)-->P (Procurement) | INSTRUMENTATION CABLE |  | 1.24.2.3 | Unscheduled | No | No | 2020-02-05 09:00 | 2020-02-12 18:00 | 2020-05-08 09:00 | 2020-10-30 18:00 | [6 empty] | 100 | 0 | [15 empty] | 4.1667 | 0.028256 | 2.78 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5176 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020094
3040 | Task(Task)-->P (Procurement) | ITP APPROVAL | 1.24.2.4 | 1.24.2 | Work In Progress | No | No | 2020-02-06 09:00 | 2020-07-26 23:59 | 2020-05-30 09:00 | 2020-12-24 18:00 |  |  | 2020-05-30 16:50 |  |  |  | 100 | 75.7792 | [15 empty] | 5.0004 | 0.33912 | 33.35 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5177 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020095
3041 | Task(Task)-->P (Procurement) | Manual Hoist |  | 1.24.2.4 | Completed | No | No | 2020-04-30 09:00 | 2020-06-08 18:00 | 2020-07-03 09:00 | 2020-08-21 18:00 |  |  | 2020-07-03 16:09 | 2020-08-21 16:08 |  |  | 100 | 100 | [15 empty] | 0.32974 | 0.001118 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5178 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020096
3042 | Task(Task)-->P (Procurement) | Electric Hoist |  | 1.24.2.4 | Unscheduled | No | No | 2020-04-25 09:00 | 2020-06-03 18:00 | 2020-07-17 09:00 | 2020-10-15 18:00 |  |  | 2020-07-17 01:13 |  |  |  | 100 | 49.99 | [15 empty] | 2.9376 | 0.009962 | 0.98 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5179 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020097
3043 | Task(Task)-->P (Procurement) | Belt Vulcanizer |  | 1.24.2.4 | Unscheduled | No | No | 2020-06-13 09:00 | 2020-07-22 18:00 | 2020-11-15 | 2020-12-24 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.89928 | 0.00305 | 0.3 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5180 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020098
3044 | Task(Task)-->P (Procurement) | HT CABLE (33KV & 6.6KV) |  | 1.24.2.4 | Completed | No | No | 2020-02-11 09:00 | 2020-03-21 18:00 | 2020-08-03 09:00 | 2020-08-21 18:00 |  |  | 2020-08-03 16:20 | 2020-08-21 12:45 |  |  | 100 | 100 | [15 empty] | 15.5276 | 0.052657 | 5.18 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5181 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020099
3045 | Task(Task)-->P (Procurement) | LT POWER CABLES |  | 1.24.2.4 | Completed | No | No | 2020-02-29 09:00 | 2020-04-08 18:00 | 2020-08-03 09:00 | 2020-08-21 18:00 |  |  | 2020-08-03 16:22 | 2020-08-21 12:46 |  |  | 100 | 100 | [15 empty] | 20.4736 | 0.06943 | 6.83 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5182 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020100
3046 | Task(Task)-->P (Procurement) | LIGHTING MAST |  | 1.24.2.4 | Completed | No | No | 2020-02-06 09:00 | 2020-03-16 18:00 | 2020-07-08 09:00 | 2020-09-23 18:00 |  |  | 2020-09-03 12:01 | 2020-09-23 16:50 |  |  | 100 | 100 | [15 empty] | 0.68945 | 0.002338 | 0.23 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5183 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020101
3047 | Task(Task)-->P (Procurement) | CABLE TRAY & ACCESSORIES |  | 1.24.2.4 | Completed | No | No | 2020-02-16 | 2020-03-26 18:00 | 2020-05-30 09:00 | 2020-07-28 18:00 |  |  | 2020-05-30 16:50 | 2020-07-28 16:50 |  |  | 100 | 100 | [15 empty] | 23.2014 | 0.07868 | 7.74 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5184 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020102
3048 | Task(Task)-->P (Procurement) | FLEXIBLE CABLE TRAY SUPPORTS |  | 1.24.2.4 | Completed | No | No | 2020-02-16 | 2020-03-26 18:00 | 2020-07-22 09:00 | 2020-08-12 18:00 |  |  | 2020-07-22 18:26 | 2020-08-12 12:49 |  |  | 100 | 100 | [15 empty] | 4.6763 | 0.015858 | 1.56 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5185 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020103
3049 | Task(Task)-->P (Procurement) | EARTHING & LIGHTNING PROTECTION MATERIALS |  | 1.24.2.4 | Completed | No | No | 2020-06-17 09:00 | 2020-07-26 23:59 | 2020-07-22 09:00 | 2020-08-13 18:00 |  |  | 2020-07-22 18:48 | 2020-08-14 13:04 |  |  | 100 | 100 | [15 empty] | 7.2842 | 0.024702 | 2.43 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5186 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020104
3050 | Task(Task)-->P (Procurement) | HT CABLE ACCESSORIES |  | 1.24.2.4 | Completed | No | No | 2020-03-13 09:00 | 2020-04-21 18:00 | 2020-09-10 09:00 | 2020-10-19 18:00 |  |  | 2020-08-03 16:21 | 2020-08-21 12:45 |  |  | 100 | 100 | [15 empty] | 0.77938 | 0.002643 | 0.26 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5187 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020105
3051 | Task(Task)-->P (Procurement) | LT CABLE ACCESSORIES |  | 1.24.2.4 | Unscheduled | No | No | 2020-03-04 09:00 | 2020-04-12 23:59 | 2020-10-31 09:00 | 2020-12-09 18:00 | [6 empty] | 100 | 0 | [15 empty] | 1.6187 | 0.005489 | 0.54 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5188 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020106
3052 | Task(Task)-->P (Procurement) | FO CABLE |  | 1.24.2.4 | Unscheduled | No | No | 2020-02-25 09:00 | 2020-04-04 18:00 | 2020-09-23 09:00 | 2020-10-10 18:00 |  |  | 2020-09-23 14:18 |  |  |  | 100 | 0 | [15 empty] | 1.4988 | 0.005083 | 0.5 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5189 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020107
3053 | Task(Task)-->P (Procurement) | RECEPTACLES |  | 1.24.2.4 | Completed | No | No | 2020-03-11 09:00 | 2020-04-19 23:59 | 2020-07-16 09:00 | 2020-07-16 18:00 |  |  | 2020-07-16 19:23 | 2020-07-16 19:44 |  |  | 100 | 100 | [15 empty] | 1.3489 | 0.004574 | 0.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5190 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020108
3054 | Task(Task)-->P (Procurement) | CONTROL CABLE |  | 1.24.2.4 | Unscheduled | No | No | 2020-02-13 09:00 | 2020-03-23 18:00 | 2020-10-31 09:00 | 2020-12-09 18:00 | [6 empty] | 100 | 0 | [15 empty] | 7.7038 | 0.026125 | 2.57 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5191 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020109
3055 | Task(Task)-->P (Procurement) | CCTV SYSTEM |  | 1.24.2.4 | Unscheduled | No | No | 2020-03-28 09:00 | 2020-05-06 18:00 | 2020-08-01 09:00 | 2020-09-09 18:00 | [6 empty] | 100 | 0 | [15 empty] | 3.8669 | 0.013113 | 1.29 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5240 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020110
3056 | Task(Task)-->P (Procurement) | PA SYSTEM |  | 1.24.2.4 | Unscheduled | No | No | 2020-03-11 09:00 | 2020-04-19 23:59 | 2020-09-24 09:00 | 2020-10-30 18:00 |  |  | 2020-09-24 09:43 |  |  |  | 100 | 0 | [15 empty] | 2.9976 | 0.010165 | 1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5239 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020111
3057 | Task(Task)-->P (Procurement) | INSTRUMENTATION CABLE |  | 1.24.2.4 | Unscheduled | No | No | 2020-02-13 09:00 | 2020-03-23 18:00 | 2020-10-31 09:00 | 2020-12-09 18:00 | [6 empty] | 100 | 0 | [15 empty] | 4.1667 | 0.01413 | 1.39 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5192 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020112
3058 | Task(Task)-->P (Procurement) | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE | 1.24.2.5 | 1.24.2 | Work In Progress | No | No | 2020-02-06 09:00 | 2020-08-10 18:00 | 2020-05-15 09:00 | 2020-12-24 18:00 |  |  | 2020-06-11 10:20 |  |  |  | 100 | 77.9809 | [15 empty] | 14.9999 | 1.0173 | 100.04 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5193 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020113
3059 | Task(Task)-->P (Procurement) | Manual Hoist |  | 1.24.2.5 | Completed | No | No | 2020-04-30 09:00 | 2020-06-28 23:59 | 2020-07-03 09:00 | 2020-09-02 18:00 |  |  | 2020-07-04 01:31 | 2020-09-02 16:09 |  |  | 100 | 100 | [15 empty] | 0.31984 | 0.003254 | 0.32 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5194 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020114
3060 | Task(Task)-->P (Procurement) | Electric Hoist |  | 1.24.2.5 | Completed | No | No | 2020-04-25 09:00 | 2020-06-23 18:00 | 2020-07-17 09:00 | 2020-09-02 18:00 |  |  | 2020-07-17 16:07 | 2020-09-02 16:07 |  |  | 100 | 100 | [15 empty] | 2.9485 | 0.029994 | 2.95 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5195 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020115
3061 | Task(Task)-->P (Procurement) | Belt Vulcanizer |  | 1.24.2.5 | Unscheduled | No | No | 2020-06-13 09:00 | 2020-07-22 18:00 | 2020-11-15 | 2020-12-24 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.89955 | 0.009151 | 0.9 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5196 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020116
3062 | Task(Task)-->P (Procurement) | HT CABLE (33KV & 6.6KV) |  | 1.24.2.5 | Completed | No | No | 2020-02-11 09:00 | 2020-03-26 18:00 | 2020-07-31 09:00 | 2020-09-15 18:00 |  |  | 2020-07-31 20:04 | 2020-09-15 16:57 |  |  | 100 | 100 | [15 empty] | 15.5322 | 0.158 | 15.54 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5197 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020117
3063 | Task(Task)-->P (Procurement) | LT POWER CABLES |  | 1.24.2.5 | Completed | No | No | 2020-02-29 09:00 | 2020-04-13 18:00 | 2020-07-31 09:00 | 2020-09-09 18:00 |  |  | 2020-07-31 20:05 | 2020-09-10 10:03 |  |  | 100 | 100 | [15 empty] | 20.4898 | 0.20843 | 20.5 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5198 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020118
3064 | Task(Task)-->P (Procurement) | LIGHTING MAST |  | 1.24.2.5 | Completed | No | No | 2020-02-06 09:00 | 2020-03-21 18:00 | 2020-05-15 09:00 | 2020-09-04 18:00 |  |  | 2020-06-11 10:20 | 2020-09-04 10:04 |  |  | 100 | 100 | [15 empty] | 0.68966 | 0.007016 | 0.69 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5199 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020119
3065 | Task(Task)-->P (Procurement) | CABLE TRAY & ACCESSORIES |  | 1.24.2.5 | Completed | No | No | 2020-02-16 | 2020-03-31 18:00 | 2020-05-30 09:00 | 2020-08-08 18:00 |  |  | 2020-07-06 10:19 | 2020-08-08 13:48 |  |  | 100 | 100 | [15 empty] | 23.1884 | 0.23589 | 23.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5200 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020120
3066 | Task(Task)-->P (Procurement) | FLEXIBLE CABLE TRAY SUPPORTS |  | 1.24.2.5 | Completed | No | No | 2020-02-16 | 2020-03-31 18:00 | 2020-07-18 09:00 | 2020-08-12 18:00 |  |  | 2020-07-22 11:43 | 2020-08-12 12:49 |  |  | 100 | 100 | [15 empty] | 4.6777 | 0.047584 | 4.68 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5201 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020121
3067 | Task(Task)-->P (Procurement) | EARTHING & LIGHTNING PROTECTION MATERIALS |  | 1.24.2.5 | Completed | No | No | 2020-06-17 09:00 | 2020-08-10 18:00 | 2020-07-07 09:00 | 2020-08-08 18:00 |  |  | 2020-07-22 18:47 | 2020-08-07 14:17 |  |  | 100 | 100 | [15 empty] | 7.2964 | 0.074222 | 7.3 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5202 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020122
3068 | Task(Task)-->P (Procurement) | HT CABLE ACCESSORIES |  | 1.24.2.5 | Unscheduled | No | No | 2020-03-13 09:00 | 2020-04-26 23:59 | 2020-09-07 09:00 | 2020-10-31 18:00 |  |  | 2020-09-07 16:56 |  |  |  | 100 | 0 | [15 empty] | 0.77961 | 0.007931 | 0.78 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5203 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020123
3069 | Task(Task)-->P (Procurement) | LT CABLE ACCESSORIES |  | 1.24.2.5 | Unscheduled | No | No | 2020-03-04 09:00 | 2020-04-17 18:00 | 2020-10-31 09:00 | 2020-12-14 18:00 | [6 empty] | 100 | 0 | [15 empty] | 1.6192 | 0.016471 | 1.62 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5204 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020124
3070 | Task(Task)-->P (Procurement) | FO CABLE |  | 1.24.2.5 | Completed | No | No | 2020-02-25 09:00 | 2020-04-09 18:00 | 2020-07-30 09:00 | 2020-09-26 18:00 |  |  | 2020-07-30 14:21 | 2020-09-26 10:37 |  |  | 100 | 100 | [15 empty] | 1.4993 | 0.015251 | 1.5 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5205 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020125
3071 | Task(Task)-->P (Procurement) | RECEPTACLES |  | 1.24.2.5 | Completed | No | No | 2020-03-11 09:00 | 2020-04-24 18:00 | 2020-05-30 09:00 | 2020-07-29 18:00 |  |  | 2020-07-18 19:22 | 2020-07-29 15:08 |  |  | 100 | 100 | [15 empty] | 1.3393 | 0.013624 | 1.34 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5206 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020126
3072 | Task(Task)-->P (Procurement) | CONTROL CABLE |  | 1.24.2.5 | Unscheduled | No | No | 2020-02-13 09:00 | 2020-03-28 18:00 | 2020-10-31 09:00 | 2020-12-14 18:00 | [6 empty] | 100 | 0 | [15 empty] | 7.7061 | 0.078391 | 7.71 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5207 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020127
3073 | Task(Task)-->P (Procurement) | CCTV SYSTEM |  | 1.24.2.5 | Unscheduled | No | No | 2020-03-28 09:00 | 2020-05-21 18:00 | 2020-05-31 | 2020-10-21 18:00 |  |  | 2020-07-01 10:39 |  |  |  | 100 | 0 | [15 empty] | 3.8681 | 0.039348 | 3.87 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5242 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020128
3074 | Task(Task)-->P (Procurement) | PA SYSTEM |  | 1.24.2.5 | Unscheduled | No | No | 2020-03-11 09:00 | 2020-05-24 23:59 | 2020-07-08 09:00 | 2020-10-21 18:00 |  |  | 2020-07-08 10:37 |  |  |  | 100 | 0 | [15 empty] | 2.9885 | 0.030401 | 2.99 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5241 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020129
3075 | Task(Task)-->P (Procurement) | INSTRUMENTATION CABLE |  | 1.24.2.5 | Unscheduled | No | No | 2020-02-13 09:00 | 2020-03-28 18:00 | 2020-10-31 09:00 | 2020-12-14 18:00 | [6 empty] | 100 | 0 | [15 empty] | 4.1579 | 0.042297 | 4.16 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5208 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020130
3076 | Task(Task)-->P (Procurement) | MANUFACTURING & RECEIPT AT SITE (MRN) | 1.24.2.6 | 1.24.2 | Unscheduled | No | No | 2020-03-22 | 2021-03-31 18:00 | 2020-07-30 09:00 | 2021-09-24 18:00 |  |  | 2020-07-30 19:58 |  |  |  | 67.2879 | 0.21054 | [15 empty] | 59.9994 | 4.069 | 400.16 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5209 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020131
3077 | Task(Task)-->P (Procurement) | Manual Hoist |  | 1.24.2.6 | Unscheduled | No | No | 2020-06-29 09:00 | 2021-01-08 18:00 | 2020-09-02 09:00 | 2020-12-31 18:00 |  |  | 2020-09-02 16:10 |  |  |  | 52.0619 | 20 | [15 empty] | 0.31487 | 0.012812 | 1.26 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5210 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020132
3078 | Task(Task)-->P (Procurement) | Electric Hoist |  | 1.24.2.6 | Unscheduled | No | No | 2020-06-24 09:00 | 2021-03-19 18:00 | 2020-09-02 09:00 | 2021-02-15 18:00 |  |  | 2020-09-02 16:08 |  |  |  | 39.4052 | 5 | [15 empty] | 2.9512 | 0.12009 | 11.81 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5211 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020133
3079 | Task(Task)-->P (Procurement) | Belt Vulcanizer |  | 1.24.2.6 | Unscheduled | No | No | 2020-07-23 09:00 | 2021-02-07 23:59 | 2020-12-25 09:00 | 2021-07-12 18:00 | [6 empty] | 38.5 | 0 | [15 empty] | 0.89962 | 0.036606 | 3.6 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5212 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020134
3080 | Task(Task)-->P (Procurement) | HT CABLE (33KV & 6.6KV) |  | 1.24.2.6 | Unscheduled | No | No | 2020-04-11 09:00 | 2021-02-03 18:00 | 2020-09-29 09:00 | 2021-07-24 18:00 |  |  | 2020-09-15 12:58 |  |  |  | 60.2007 | 0 | [15 empty] | 15.5284 | 0.63185 | 62.14 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5213 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020135
3081 | Task(Task)-->P (Procurement) | LT POWER CABLES |  | 1.24.2.6 | Unscheduled | No | No | 2020-04-14 09:00 | 2021-01-09 18:00 | 2020-09-10 09:00 | 2021-06-07 18:00 |  |  | 2020-09-10 10:04 |  |  |  | 65.3136 | 0 | [15 empty] | 20.4913 | 0.83379 | 82 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5214 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020136
3082 | Task(Task)-->P (Procurement) | LIGHTING MAST |  | 1.24.2.6 | Unscheduled | No | No | 2020-03-22 | 2020-07-03 18:00 | 2020-09-24 09:00 | 2021-01-05 18:00 |  |  | 2020-09-04 10:04 |  |  |  | 100 | 0 | [15 empty] | 0.68471 | 0.027861 | 2.74 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5215 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020137
3083 | Task(Task)-->P (Procurement) | CABLE TRAY & ACCESSORIES |  | 1.24.2.6 | Unscheduled | No | No | 2020-04-01 09:00 | 2020-09-09 18:00 | 2020-08-09 | 2021-01-17 23:59 |  |  | 2020-08-09 13:52 |  |  |  | 100 | 0 | [15 empty] | 23.1951 | 0.94381 | 92.82 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5216 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020138
3084 | Task(Task)-->P (Procurement) | FLEXIBLE CABLE TRAY SUPPORTS |  | 1.24.2.6 | Unscheduled | No | No | 2020-04-01 09:00 | 2020-08-10 18:00 | 2020-08-13 09:00 | 2020-12-22 18:00 |  |  | 2020-08-12 12:48 |  |  |  | 100 | 0 | [15 empty] | 4.6755 | 0.19025 | 18.71 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5217 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020139
3085 | Task(Task)-->P (Procurement) | EARTHING & LIGHTNING PROTECTION MATERIALS |  | 1.24.2.6 | Unscheduled | No | No | 2020-08-11 09:00 | 2021-02-08 18:00 | 2020-08-14 09:00 | 2021-02-11 18:00 |  |  | 2020-08-11 13:05 |  |  |  | 31.8681 | 0 | [15 empty] | 7.2944 | 0.29681 | 29.19 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5218 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020140
3086 | Task(Task)-->P (Procurement) | HT CABLE ACCESSORIES |  | 1.24.2.6 | Unscheduled | No | No | 2020-09-24 09:00 | 2020-12-19 18:00 | 2021-03-31 09:00 | 2021-06-25 18:00 | [6 empty] | 16.092 | 0 | [15 empty] | 0.77967 | 0.031725 | 3.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5219 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020141
3087 | Task(Task)-->P (Procurement) | LT CABLE ACCESSORIES |  | 1.24.2.6 | Unscheduled | No | No | 2020-07-17 09:00 | 2020-11-03 18:00 | 2021-03-15 09:00 | 2021-07-02 18:00 | [6 empty] | 75.4545 | 0 | [15 empty] | 1.6218 | 0.065992 | 6.49 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5220 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020142
3088 | Task(Task)-->P (Procurement) | FO CABLE |  | 1.24.2.6 | Unscheduled | No | No | 2020-04-10 09:00 | 2021-01-30 18:00 | 2020-10-11 | 2021-08-02 18:00 |  |  | 2020-09-26 10:38 |  |  |  | 61.1487 | 0 | [15 empty] | 1.4969 | 0.060907 | 5.99 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5221 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020143
3089 | Task(Task)-->P (Procurement) | RECEPTACLES |  | 1.24.2.6 | Unscheduled | No | No | 2020-04-25 09:00 | 2020-08-25 18:00 | 2020-07-30 09:00 | 2020-11-29 23:59 |  |  | 2020-07-30 19:58 |  |  |  | 100 | 0 | [15 empty] | 1.3394 | 0.054502 | 5.36 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5222 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020144
3090 | Task(Task)-->P (Procurement) | CONTROL CABLE |  | 1.24.2.6 | Unscheduled | No | No | 2020-03-29 | 2021-01-06 18:00 | 2020-12-15 09:00 | 2021-09-24 18:00 | [6 empty] | 67.9578 | 0 | [15 empty] | 7.7042 | 0.31349 | 30.83 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5223 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020145
3091 | Task(Task)-->P (Procurement) | CCTV SYSTEM |  | 1.24.2.6 | Unscheduled | No | No | 2020-10-24 09:00 | 2021-03-31 18:00 | 2021-03-26 09:00 | 2021-08-31 18:00 | [6 empty] | 0 | 0 | [15 empty] | 3.8659 | 0.1573 | 15.47 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5244 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020146
3092 | Task(Task)-->P (Procurement) | PA SYSTEM |  | 1.24.2.6 | Unscheduled | No | No | 2020-10-10 09:00 | 2021-03-31 18:00 | 2021-03-09 09:00 | 2021-08-28 18:00 | [6 empty] | 0 | 0 | [15 empty] | 2.9937 | 0.12182 | 11.98 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5243 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020147
3093 | Task(Task)-->P (Procurement) | INSTRUMENTATION CABLE |  | 1.24.2.6 | Unscheduled | No | No | 2020-03-29 | 2020-12-07 18:00 | 2020-12-15 09:00 | 2021-08-25 18:00 | [6 empty] | 75.9843 | 0 | [15 empty] | 4.1632 | 0.1694 | 16.66 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5224 | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020148
3094 | Task(Task)-->P (Procurement) | ITEM LIST | 1.24.2.7 | 1.24.2 | Unscheduled | No | No | [6 empty] | 2020-07-06 12:38 |  |  |  | 0 | 0 | [15 empty] | 0 | 0 | 0 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No |  | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1044190
3095 | Task(Task)-->P (Procurement) | PRIMARY AND SECONDARY SIZERS |  | 1.24.2.7 | Unscheduled | No | No | [6 empty] | 2020-07-06 12:38 |  |  |  | 0 | 0 |  |  |  | Documents(Documents)-->ITEM (Item List) | EK210PO0000012 | [10 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1047486
3096 | Task(Task)-->P (Procurement) | IDLERS WITH SPARES FOR TROUGH BELT CONVEYOR |  | 1.24.2.7 | Unscheduled | No | No | [6 empty] | 2020-07-06 12:38 |  |  |  | 0 | 0 |  |  |  | Documents(Documents)-->ITEM (Item List) | EK210PO0000040 | [10 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1047487
3097 | Task(Task)-->P (Procurement) | PLUMMER BLOCKS WITH SPARES FOR TROUGH BELT CONVEYORS |  | 1.24.2.7 | Unscheduled | No | No | [6 empty] | 2020-07-06 12:38 |  |  |  | 0 | 0 |  |  |  | Documents(Documents)-->ITEM (Item List) | EK210PO0000018 | [10 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1047488
3098 | Task(Task)-->P (Procurement) | BEARING WITH SAPRES FOR TROUGH BELT CONVEYOR PULLEYS |  | 1.24.2.7 | Unscheduled | No | No | [6 empty] | 2020-07-06 12:38 |  |  |  | 0 | 0 |  |  |  | Documents(Documents)-->ITEM (Item List) | EK210PO0000016 | [10 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1047489
3099 | Task(Task)-->P (Procurement) | FLUID COUPLINGS FOR TROUGH CONVEYORS WITH MANDATORY SPARES |  | 1.24.2.7 | Unscheduled | No | No | [6 empty] | 2020-07-06 12:38 |  |  |  | 0 | 0 |  |  |  | Documents(Documents)-->ITEM (Item List) | EK210PO0000051 | [10 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1047490
3100 | Task(Task)-->P (Procurement) | GEARED COUPLING WITH SPARES FOR TROUGH BELT CONVEYORS |  | 1.24.2.7 | Unscheduled | No | No | [6 empty] | 2020-07-06 12:38 |  |  |  | 0 | 0 |  |  |  | Documents(Documents)-->ITEM (Item List) | EK210PO0000022 | [10 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1047491
3101 | Task(Task)-->P (Procurement) | GEAR BOXES FOR TROUGH CONVEYORS & EQUIPMENT WITH MANDATORY SPARES |  | 1.24.2.7 | Unscheduled | No | No | [6 empty] | 2020-07-06 12:38 |  |  |  | 0 | 0 |  |  |  | Documents(Documents)-->ITEM (Item List) | EK210PO0000041 | [10 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1047492
3102 | Task(Task)-->P (Procurement) | INLINE MAGNETIC SEPARATOR AND SUSPENDED MAGNET WITH MANDATORY SPARES |  | 1.24.2.7 | Unscheduled | No | No | [6 empty] | 2020-07-06 12:38 |  |  |  | 0 | 0 |  |  |  | Documents(Documents)-->ITEM (Item List) | EK210PO0000010 | [10 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1047493
3103 | Task(Task)-->P (Procurement) | BELT WEIGH SCALE WITH MANDATORY SPARES FOR TROUGH BELT CONVEYORS |  | 1.24.2.7 | Unscheduled | No | No | [6 empty] | 2020-07-06 12:38 |  |  |  | 0 | 0 |  |  |  | Documents(Documents)-->ITEM (Item List) | EK210PO0000014 | [10 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1047494
3104 | Task(Task)-->P (Procurement) | METAL DETECTOR WITH MANDATORY SPARES |  | 1.24.2.7 | Unscheduled | No | No | [6 empty] | 2020-07-06 12:38 |  |  |  | 0 | 0 |  |  |  | Documents(Documents)-->ITEM (Item List) | EK210PO0000026 | [10 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1047495
3105 | Task(Task)-->P (Procurement) | sample item |  | 1.24.2.7 | Unscheduled | No | No | [6 empty] | 2020-07-18 11:53 |  |  |  | 0 | 0 |  |  |  | Documents(Documents)-->ITEM (Item List) | test-1 | [10 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | [244 empty] | 1098712
3106 | Task(Task)-->C (Construction) | CONSTRUCTION | 1.24.3 | 1.24 | Unscheduled | No | No | 2020-09-08 09:00 | 2021-09-26 23:59 | 2020-12-01 09:00 | 2021-11-23 18:00 | [6 empty] | 1.8751 | 0 | [15 empty] | 20.5938 | 1.8169 | 178.68 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5225 | 0 | 2 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020149
3107 | Task(Task)-->C (Construction) | PRECAST FOR TAKE-UP WEIGHT OF CONVEYORS |  | 1.24.3 | Unscheduled | No | No | 2020-09-08 09:00 | 2021-03-07 23:59 | 2020-12-01 09:00 | 2021-05-30 23:59 | [6 empty] | 16.5746 | 0 | [15 empty] | 5.9377 | 0.10788 | 10.61 | Plan & Actual | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5227 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020150
3108 | Task(Task)-->C (Construction) | PRECAST FOR DRAIN COVER |  | 1.24.3 | Unscheduled | No | No | 2020-09-08 09:00 | 2021-02-04 18:00 | 2020-12-01 09:00 | 2021-04-29 18:00 | [6 empty] | 20 | 0 | [15 empty] | 4.4546 | 0.080936 | 7.96 | Plan & Actual | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5445 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020151
3109 | Task(Task)-->C (Construction) | APPROACH ROAD |  | 1.24.3 | Unscheduled | No | No | 2021-01-07 09:00 | 2021-05-06 18:00 | 2021-04-01 09:00 | 2021-07-29 18:00 | [6 empty] | 0 | 0 | [15 empty] | 45.9511 | 0.83488 | 82.11 | Plan & Actual | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5228 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020152
3110 | Task(Task)-->C (Construction) | DRAINAGE SYSTEM - CONNECTION FROM GARLAND DRAIN TO MAIN DRAIN AND RAIN WATER HARVASTING |  | 1.24.3 | Unscheduled | No | No | 2020-12-08 09:00 | 2021-05-07 18:00 | 2021-03-02 09:00 | 2021-07-30 18:00 | [6 empty] | 0 | 0 | [15 empty] | 8.6686 | 0.1575 | 15.49 | Plan & Actual | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5229 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020153
3111 | Task(Task)-->C (Construction) | SEWAGE SYSTEM/ SOAK PIT |  | 1.24.3 | Unscheduled | No | No | 2020-12-08 09:00 | 2021-05-07 18:00 | 2021-03-02 09:00 | 2021-07-30 18:00 | [6 empty] | 0 | 0 | [15 empty] | 1.8804 | 0.034164 | 3.36 | Plan & Actual | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5230 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020154
3112 | Task(Task)-->C (Construction) | ERECTION OF MONORAIL & HOISTS |  | 1.24.3 | Unscheduled | No | No | 2021-03-20 09:00 | 2021-09-15 18:00 | 2021-02-16 09:00 | 2021-08-14 18:00 | [6 empty] | 0 | 0 | [15 empty] | 2.2217 | 0.040366 | 3.97 | Plan & Actual | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5598 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020155
3113 | Task(Task)-->C (Construction) | SHEETING WORKS |  | 1.24.3 | Unscheduled | No | No | 2021-05-30 | 2021-09-26 23:59 | 2021-04-28 09:00 | 2021-08-25 18:00 | [6 empty] | 0 | 0 | [15 empty] | 27.7184 | 0.50362 | 49.53 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 28436 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5603 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020156
3114 | Task(Task)-->C (Construction) | CCTV SYSTEM |  | 1.24.3 | Unscheduled | No | No | 2021-04-01 09:00 | 2021-05-30 23:59 | 2021-09-01 09:00 | 2021-10-30 18:00 | [6 empty] | 0 | 0 | [15 empty] | 1.7125 | 0.031114 | 3.06 | Plan & Actual | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5245 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020157
3115 | Task(Task)-->C (Construction) | PA SYSTEM |  | 1.24.3 | Unscheduled | No | No | 2021-04-01 09:00 | 2021-05-30 23:59 | 2021-09-25 09:00 | 2021-11-23 18:00 | [6 empty] | 0 | 0 | [15 empty] | 1.455 | 0.026436 | 2.6 | Plan & Actual | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5246 | 0 | 3 | Low | [7 empty] | 0 | 0 | [244 empty] | 1020158
3116 | Task(Task)-->C (Construction) | TRAIL OPERATION AND COMPLETION OF FACILITIES |  | 1 | Unscheduled | No | No | 2021-09-14 09:00 | 2021-09-27 18:00 | 2022-04-06 09:00 | 2022-04-19 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0.015659 | 0.015659 | 1.54 | Plan & Actual | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5606 | 0 | 1 | High | [7 empty] | 0 | 0 | [244 empty] | 1020159
3117 | Task(Task)-->E (Engineering) | HGTU OF PIPE CONV FOR PC 1A/1B & PC 2A/2B : DESIGN CALCULATION FOR SUPER STRUCTURE |  |  | Completed | No | No | [6 empty] | 2020-10-08 14:03 | 2020-10-09 20:10 |  |  | 0 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-DC-0047 |  | 2020-09-30 16:08 | 7012-155-PVC-U-139 | [7 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 0 | Low | [7 empty] | 0 | 0 | [244 empty] | 10105066
3118 | Task(Task)-->E (Engineering) | HGTU OF PIPE CONV FOR PC 1A/1B & PC 2A/2B : DESIGN CALCULATION FOR SUB STRUCTURE |  |  | Unscheduled | No | No | [6 empty] | 2020-10-08 14:03 |  |  |  | 0 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-DC-0048 |  | 2020-09-30 16:08 | 7012-155-PVC-U-140 | [7 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 0 | Low | [7 empty] | 0 | 0 | [244 empty] | 10105067
3119 | Task(Task)-->E (Engineering) | PIPE CONV PC 1A/1B : (TRANSITION ZONE) : DESIGN CALCULATION FOR SUPER STRUCTURE |  |  | Unscheduled | No | No | [6 empty] | 2020-10-08 14:03 |  |  |  | 0 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-DC-0049 |  | 2020-09-30 16:08 | 7012-155-PVC-U-141 | [7 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 0 | Low | [7 empty] | 0 | 0 | [244 empty] | 10105068
3120 | Task(Task)-->E (Engineering) | PIPE CONV PC 2A/2B : (TRANSITION ZONE) : DESIGN CALCULATION FOR SUPER STRUCTURE |  |  | Unscheduled | No | No | [6 empty] | 2020-10-08 14:03 |  |  |  | 0 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-DC-0050 |  | 2020-09-30 16:08 | 7012-155-PVC-U-142 | [7 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 0 | Low | [7 empty] | 0 | 0 | [244 empty] | 10105069

## LOVSheet (hidden)
|  |  |  | 101000 |  |  |  |  | -330 | India Standard Time
Task(Task)-->C (Construction) | 1.3.2.6 | V0008223 | Documents(Documents)-->CC (Client Comments) | Customer | BHEL(BHARAT HEAVY ELECTRICS LIMITED) | A | CLEARANCE WORKFLOW | Engineering | Cubic Meter | BD-Standard | For Approval | Excavation | A - Architecture | DCP 1 | B - Basic Engineering /General Notes/Standard drawings | CEC | Calculation | 001 - Plant General Engineering | Offers Evaluated | A0 | Cubic Meters
Task(Task)-->E (Engineering) | 1.3.3 | VCA00947 | Documents(Documents)-->CORRESPONDENCE (Correspondence)-->MAILS (Mails) | Internal | Buxar(Buxar) | I | ITP WORKFLOW | Internal | GEN | BID DOCUMENT | As Build | Installation | C - Civil | DCP 2 | D - Detail Engineering drawings / documents | L&T | D | 008 - Power Generation | RFQ Floated | A1 | Metric Tonnes
Task(Task)-->G (General) | 1.3.3.1 | VCA00866 | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | Other Unit | BUYER(BUYER) | R | Unguided Workflow | Vendor | Lot | CLEARANCE WORKFLOW | Good for Construction | PCC | F - Fire Fighting | DCP 3 | Fabrication | SYSTRA | Electrical SLD | 045 - STP/Water Treatment |  | A2 | Running Meters
Task(Task)-->P (Procurement) | 1.3.3.2 | AVSRUPESH | Documents(Documents)-->EXT (External)-->2(Mechanical) | Vendor | CIL(Coal India Limited) |  |  | PR STANDARD | LS | Elihaad- Client Submission WF | For information | RCC | H - Material Handling and Equipment | L&T | G - General Arrangement drawings |  | No IDC | 080 - Water Media & Utility systems |  | A3
| 1.3.3.3 | AALIBANGBANG | Documents(Documents)-->EXT (External)-->3(Electrical) |  | CIV(Civil / Structural / Geotechnica) |  |  |  | Meter | Etihad JV interface check | Preliminary |  | I - Instrumentation & Automation | L&T/SITE | Internal Document |  | P&ID | 100 - Conveying System |  | A4
| 1.3.3.5 | ABESH | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) |  | CMPC(CMPC) |  |  |  | Metric Tonnes | External | For Tender Purpose |  | M - Mechanical Process & Equipment | L&T/V | K - Calculation / Document |  |  | 250 - Fume Extraction & Plant Dedusting
| 1.4.2.6 | KALSI | Documents(Documents)-->EXT (External)-->5(Equipment Design) |  | DC(Document Controller) |  |  |  | Numbers | External-Standard |  |  | P - Pollution Control | L&T/V ACE | PR Document |  |  | 255 - Cranes and hoists
| 1.4.3 | ACHOUDHURY | Documents(Documents)-->EXT (External)-->6(General) |  | ELE(Electrical) |  |  |  | RM | Inspection Call Workflow |  |  | Q - HVAC | L&T/V AL | V - Vendor Document / drawing |  |  | 300 - Laboratory Facilities
| 1.4.3.1 | ABHIJITDAS | Documents(Documents)-->I (Internal)-->C (Civil & Structural) |  | ETIHAAD RAIL(ETIHAAD RAIL) |  |  |  | Set | Internal Standard |  |  | S - Structural | L&T/V ATC | Z - 3D Plant modelling |  |  | 450 - Gold Process
| 1.4.3.2 | ABHIJITG | Documents(Documents)-->I (Internal)-->E (Electrical) |  | FCC(Formwork) |  |  |  | Square Meter | ITP WORKFLOW |  |  | U - Water Media & Utility System | L&T/V NALCO |  |  |  | 501 - Workshop & Store Facilities
| 1.4.3.3 | ABHIJITPAL | Documents(Documents)-->I (Internal)-->EQ (Equipment Design) |  | HIL(Hindalco Industries Limited) |  |  |  | Kilometer | Maden Workflow |  |  |  | L&T/V PAHARPUR |  |  |  | 900 - General/Common Services
| 1.4.3.4 | SANPUI | Documents(Documents)-->I (Internal)-->I (Instrumentation & Control) |  | HR(Human Resources) |  |  |  | Inch Meters | PO-MRN |  |  |  | L&T/V SANDVIK |  |  |  | 910 - Plant Infrastructure
| 1.5.2.6 | ABHIKGHOSH | Documents(Documents)-->I (Internal)-->M (Mechanical) |  | HZL(Hindutan Zinc Limited) |  |  |  |  | PR FINAL STANDARD |  |  |  | L&T/V SIEMENS |  |  |  | 950 - Plant Electrics
| 1.5.3 | ABHIKMAITRA | Documents(Documents)-->IC (Inspection Call) |  | I&C(Instrumentation and Control) |  |  |  |  | Price Submission Workflow |  |  |  | L&T/V WARTSILA |  |  |  | 980 - Plant Instrumentation & Automation
| 1.5.3.1 | ABHIMANYUDAS | Documents(Documents)-->ITEM (Item List) |  | JSW(JINDAL STEEL WORKS) |  |  |  |  | PR-PO STANDARD |  |  |  | L&T/V WETICO
| 1.5.3.2 | ABHIPRIYA2020 | Documents(Documents)-->MAILS (Mails) |  | KIOCL(KIOCL LIMITED,BANGALORE) |  |  |  |  | T&C Workflow |  |  |  | OTE
| 1.5.3.3 | ABW | Documents(Documents)-->MANPOWER (Manpower) |  | L&T HYDROCARBON(L&T Hydrocarbon Engineering Limited) |  |  |  |  | Technical Document WF |  |  |  | OTE/L&T
| 1.5.3.5 | ABHII | Documents(Documents)-->PO (Purchase Order) |  | L&T MHPS(L&T MHPS) |  |  |  |  | Vendor Drawings |  |  |  | VOID
| 1.6.2.6 | APL | Documents(Documents)-->PR (Purchase Requests)-->1(Civil & Structural) |  | MA'ADEN(MA'ADEN)
| 1.6.3 | ABHSHK | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) |  | MECH(Mechanical & Utility)
| 1.6.3.1 | ATS2020 | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) |  | MMH(MMH)
| 1.6.3.2 | ABISHEK_GUPTA | Documents(Documents)-->PR (Purchase Requests)-->4(Instrumentation & Control) |  | NCL(NORTHEN COALFIELDS LIMITED)
| 1.6.3.3 | VQA00158 | Documents(Documents)-->PR (Purchase Requests)-->5(Equipment Design) |  | NTPC(NATIONAL THERMAL POWER CORPORATION LTD)
| 1.6.3.4 | ADITYASHIV | Documents(Documents)-->PR (Purchase Requests)-->6(General) |  | PH(Project Head)
| 1.7.2.6 | ADMIN | Documents(Documents)-->PRICE (Price Submission) |  | QA/QC(Quality)
| 1.7.3 | V8001276 | Documents(Documents)-->S (Services)-->CMPC (CMPC) |  | RINL(Rashtriya Ispat Nigam Limited)
| 1.7.3.1 | V0054519 | Documents(Documents)-->S (Services)-->FCC (FCC) |  | Sample Vendor(Sample Vendor)
| 1.7.3.2 | VBA00709 | Documents(Documents)-->T&C (Terms and Condition) |  | Tech. Provider(Technology Provider)
| 1.7.3.3 | V0049873 | Documents(Documents)-->TD (Tender Documents) |  | V0071399(Machino Spares)
| 1.7.3.5 | AIGUA | Documents(Documents)-->TE (Technical Evaluation Documents) |  | VENDORS(Vendors)
| 1.8.2.6 | AIRBOOST | Documents(Documents)-->V (Vendor Drawings)-->ELE (Electrical) |  | VQH00015(HMTC Engineering Company ( Kolkata ) Private Limited)
| 1.8.3 | AJITKHATUA | Documents(Documents)-->V (Vendor Drawings)-->G (General) |  | VQK00063(Krishna Gears)
| 1.8.3.1 | AJITABH | Documents(Documents)-->V (Vendor Drawings)-->I&A (Instrumentation & Automation) |  | WGG(Wrench Guest Group)
| 1.8.3.2 | AJMALP | Documents(Documents)-->V (Vendor Drawings)-->MECH (Mechanical) |  | WORLEY(Worley Design Consultant)
| 1.8.3.3 | NILAKASH
| 1.8.3.4 | AKLANKJAIN
| 1.9.2.6 | VMT00924
| 1.9.3 | AMALSINHA
| 1.9.3.1 | AMARKR
| 1.9.3.2 | AMBARISHS
| 1.9.3.3 | AMEEYARANJAN
| 1.9.3.6 | AADH
| 1.10.2.6 | DASAMIT
| 1.10.3 | AID
| 1.10.3.1 | AMITKOLEY
| 1.10.3.2 | AMITKDUTTA
| 1.10.3.3 | AMITPARASHAR
| 1.10.3.4 | AMITSAHASAHA
| 1.11.2.6 | ASW
| 1.11.3 | AMITTHAPAR
| 1.11.3.1 | AMITAVAROY
| 1.11.3.2 | AMLANBASU
| 1.11.3.3 | AMLANPRATIK
| 1.11.3.6 | V0001529
| 1.12.2.6 | AMRITAP
| 1.12.3 | ASARKHEL
| 1.12.3.1 | ANIMESH
| 1.12.3.2 | ANIMESHSANTRA
| 1.12.3.4 | ANG
| 1.13.2.6 | ANISHJAGGI
| 1.13.3 | ANISHMDR
| 1.13.3.1 | ANKHIDEY
| 1.13.3.2 | AHG
| 1.13.3.3 | AKHANDELWAL
| 1.14.2.6 | ANNAPURNA
| 1.14.3 | ANTARA
| 1.14.3.1 | V0005977
| 1.14.3.2 | ANUBHAB
| 1.14.3.3 | ANUPNASKAR
| 1.15.2.6 | VAA00566
| 1.15.3 | ANUPAMKUMAR
| 1.15.3.1 | ANUPAMM
| 1.15.3.2 | ANS
| 1.15.3.3 | AUD
| 1.16.2.6 | APURBASINGH
| 1.16.3 | ARABINDAB
| 1.16.3.1 | ARABINDA.GOUDA
| 1.16.3.2 | ARADHANASEN
| 1.16.3.3 | V0057975
| 1.17.2.6 | ARGHYARC
| 1.17.3 | ARIJITNANDY
| 1.17.3.1 | AIS
| 1.17.3.2 | ARINDAMBASAK
| 1.17.3.3 | AUB
| 1.18.2.6 | APRODHAN
| 1.18.3 | ARINDAM
| 1.18.3.1 | VQA00024
| 1.18.3.2 | ARNABDUTTA
| 1.18.3.3 | ARPITAKHAN
| 1.19.2.4 | ARUNBHORE
| 1.19.2.6 | ARUNGAYEN
| 1.19.3 | ARUNMAJI
| 1.19.3.1 | ARUN.MISHRA
| 1.19.3.2 | ARUNVERMA
| 1.19.3.3 | ARUNAVABALL
| 1.20.1 | ARUNAVAS
| 1.20.2.4 | ARC
| 1.20.2.5 | AFOUZDER
| 1.20.2.6 | AKROY
| 1.20.3 | ASHISC
| 1.20.3.1 | PALASHIS
| 1.20.3.2 | ASHOKGUPTA
| 1.21.1 | ASHOKE
| 1.21.2.4 | ASHOK.SINGHANIA
| 1.21.2.5 | ASASMAL
| 1.21.2.6 | ASIT
| 1.21.3 | ASPIRE2020
| 1.21.3.1 | ATANU.GHOSH
| 1.21.3.2 | ATANUGHOSH
| 1.21.3.3 | V8001257
| 1.22.1 | AVG
| 1.22.2.6 | AMARICK
| 1.22.3 | AVIK
| 1.23.1 | AGR
| 1.23.2.6 | ACH
| 1.23.3 | AYB
| 1.24.2.6 | AZGARH
| 1.24.3 | BSKM
| 1.3.1.4 | VCB00489
| 1.6.1.3 | BAPAN
| 1.6.1.4 | BARATH
| 1.7.1.3 | BKB
| 1.7.1.4 | BARUNC
| 1.8.1.1 | BARUNDEV
| 1.8.1.3 | BASANT
| 1.8.1.4 | BK_KUILA
| 1.9.1.4 | V8001057
| 1.10.1.1 | VCB00293
| 1.10.1.4 | V0018742
| 1.11.1.4 | DASBHASKAR
| 1.12.1.1 | YADADRI
| 1.12.1.3 | BTR
| 1.12.1.4 | V0002938
| 1.13.1.2 | BIJETREEB
| 1.14.1.2 | BHI
| 1.15.1.2 | BILAS
| 1.16.1.1 | BINU
| 1.16.1.3 | BIPIN
| 1.17.1.1 | BIPLABMUNSHI
| 1.17.1.3 | BIPLABPATRA
| 1.18.1.1 | BSHEE
| 1.18.1.3 | BSRAY
| 1.19.1.2 | BBIPUL
| 1.20.1.1 | BDATTA
| 1.20.1.2 | BSABUI
| 1.21.1.1 | BCH
| 1.21.1.2 | V0077255
| 1.22.1.1 | PRADEEP-KUMAR
| 1.22.1.2 | V0019600
| 1.22.1.3 | V9001730
| 1.23.1.1 | BRAHMAB
| 1.23.1.2 | BUXAR
| 1.23.1.3 | V8001252
| 1.24.1.3 | V0013771
| 1.24.2.7 | CDS
| 1.24.1.5 | CDINDA
| 1 | CPAIRA
| 1.2 | CPD
| 1.3 | SHEKHARCHANDRA
| 1.3.1 | TCKREDDY
| 1.3.2 | SCHANDRU
| 1.3.2.3 | V0012538
| 1.3.2.4 | CDK
| 1.3.2.5 | CHINNI
| 1.4 | CHIRANJITSAHA
| 1.4.1 | CHRISTIANK
| 1.4.2 | VBC00250O
| 1.4.2.1 | DOC.SHJ
| 1.4.2.2 | VCC00880
| 1.4.2.3 | VMC00862
| 1.4.2.4 | DVP
| 1.4.2.5 | DALVEERPANESAR
| 1.5 | DRAGHU
| 1.5.1 | DPATNAIK
| 1.5.2 | DDU
| 1.5.2.1 | DCH
| 1.5.2.2 | DASDEB
| 1.5.2.3 | DEBASISHGHOSH
| 1.5.2.4 | DEBASISHH
| 1.5.2.5 | DEBIPRASADGHOSH
| 1.6 | DEBJIT.MUKHERJEE
| 1.6.1 | DEBOSREE
| 1.6.2 | DBC
| 1.6.2.1 | DPATHANIA
| 1.6.2.2 | DJY
| 1.6.2.3 | VCD00167
| 1.6.2.4 | V0000367
| 1.6.2.5 | V0022166
| 1.7 | VLD00246
| 1.7.1 | VAD00229
| 1.7.2 | DKUMARPANDEY
| 1.7.2.1 | DHIMANM
| 1.7.2.2 | DPURKAIT
| 1.7.2.3 | DHRUBAC
| 1.7.2.4 | DMANNA
| 1.7.2.5 | DILEEPUNNI
| 1.8 | DILIPSARKAR
| 1.8.1 | DINESHMONI
| 1.8.2 | BERAD
| 1.8.2.1 | V0014391
| 1.8.2.2 | V0054587
| 1.8.2.3 | VQE00014
| 1.8.2.4 | V0024588
| 1.8.2.5 | VQE00050
| 1.9 | VQE00076
| 1.9.1 | VME00858
| 1.9.2 | VCE00198
| 1.9.2.1 | VME00891
| 1.9.2.2 | V0068269
| 1.9.2.3 | VEE00006
| 1.9.2.4 | VQE00054
| 1.9.2.5 | VCE00214
| 1.10 | ETIHAAD
| 1.10.1 | VCE00203
| 1.10.2 | V0002844
| 1.10.2.1 | V0019347
| 1.10.2.2 | V0053484
| 1.10.2.3 | V0068769
| 1.10.2.4 | FIROJKHAN
| 1.10.2.5 | FLOWLINK
| 1.11 | VBF00103
| 1.11.1 | V0018548
| 1.11.2 | VHF00767
| 1.11.2.1 | VCF00148
| 1.11.2.2 | GSR
| 1.11.2.3 | VMG00802
| 1.11.2.4 | GSRK
| 1.11.2.5 | GANESHMAITI
| 1.12 | GAN
| 1.12.1 | GANESHGKR
| 1.12.2 | BGREDDY
| 1.12.2.1 | GAUTAMAGARWAL
| 1.12.2.2 | JASHU
| 1.12.2.3 | SINGHGHANSHYAM
| 1.12.2.4 | V0072229
| 1.12.2.5 | GOBINDAG
| 1.13 | V0069846
| 1.13.1 | VDG00170
| 1.13.2 | V0050877
| 1.13.2.1 | GOPINATHC
| 1.13.2.2 | GBH
| 1.13.2.3 | G-SIVASAI
| 1.13.2.4 | GGKRAJU
| 1.13.2.5 | GGO
| 1.14 | GOUTAM.ROY
| 1.14.1 | GOUTAMS
| 1.14.2 | V0019284
| 1.14.2.1 | VQG00044
| 1.14.2.2 | GMU
| 1.14.2.3 | BHANUG
| 1.14.2.4 | HARERAM
| 1.14.2.5 | GRHK
| 1.15 | V0010071
| 1.15.1 | VCF00109
| 1.15.2 | HASANSK
| 1.15.2.1 | VLH00864
| 1.15.2.2 | HSARDER
| 1.15.2.3 | VCH00151
| 1.15.2.4 | VLH00828
| 1.15.2.5 | V0064424
| 1.16 | V0053842
| 1.16.1 | VMH00163
| 1.16.2 | HIMANSU
| 1.16.2.1 | HIMANSUBARAL
| 1.16.2.2 | VAH00143
| 1.16.2.3 | V0010114
| 1.16.2.4 | VQH00015
| 1.16.2.5 | V0020739
| 1.17 | V0019825
| 1.17.1 | INDCON
| 1.17.2 | VBI00131
| 1.17.2.1 | INDIRA
| 1.17.2.2 | IRH
| 1.17.2.3 | IMUKHERJEE
| 1.17.2.4 | C.INDRANIL
| 1.17.2.5 | VHI00075
| 1.18 | INGERSOLL
| 1.18.1 | INTERVALVE
| 1.18.2 | VQI00072
| 1.18.2.1 | V0019880
| 1.18.2.2 | JYOTI.DAS
| 1.18.2.3 | JAIGARH
| 1.18.2.4 | VLJ00772
| 1.18.2.5 | JJO
| 1.19 | JKMONDAL
| 1.19.1 | JKN
| 1.19.2 | VBJ00175
| 1.19.2.5 | JAYATI
| 1.20 | JMANNA
| 1.20.2 | JAYDIPC
| 1.21 | JAYDIPDAS
| 1.21.2 | JEEVITESH
| 1.22 | JYMI
| 1.22.2 | JOYDEEP
| 1.22.2.1 | JUSTINTHOMAS
| 1.22.2.2 | JPJ
| 1.22.2.3 | JV1
| 1.22.2.4 | JYOTIRBANMALLICK
| 1.23 | GANESHK
| 1.23.2 | KNSEN
| 1.23.2.1 | KABERI
| 1.23.2.2 | KABYA
| 1.23.2.3 | V0047110
| 1.23.2.4 | KAJALC
| 1.23.2.5 | VBK00356
| 1.24 | VCK00400
| 1.24.1 | KAMALP
| 1.24.2 | VAK00912
| 1.24.2.1 | HKANANI
| 1.24.2.2 | VCK00431
| 1.24.2.3 | KARTHIPL
| 1.24.2.4 | KARTHI.K
| 1.24.2.5 | KARTHIS
| 1.3.1.1 | V0056038
| 1.3.1.3 | KDU
| 1.4.1.1 | KAUSHIKG
| 1.4.1.2 | K.SARKAR
| 1.4.1.3 | KAUSHIKC
| 1.4.1.4 | V0020611
| 1.5.1.1 | VCK00218
| 1.5.1.4 | KERENDARI
| 1.6.1.1 | KHARAVEL
| 1.6.1.2 | V9002542
| 1.7.1.1 | KHURJA
| 1.8.1.2 | VINODKINTALI
| 1.9.1.1 | V0001608
| 1.9.1.3 | VLK00901
| 1.10.1.2 | KIKUSH
| 1.10.1.3 | VCK00224
| 1.11.1.1 | V0050684
| 1.11.1.2 | KOUSHIKGANGULY
| 1.11.1.3 | KOUSIKB
| 1.12.1.2 | VQK00063
| 1.13.1.1 | KRISHNENDUC
| 1.14.1.1 | KULDEEPSHARMA
| 1.15.1.1 | KUNALRAY
| 1.16.1.2 | KUTUB
| 1.17.1.2 | VCL00862
| 1.18.1.2 | LNTEWL
| 1.24.1.1 | LNTKBL2020
| 1.24.1.4 | V0053017
| 1.3.2.1 | LAYEE
| 1.3.2.2 | VBL00151
| 1.19.2.1 | LIJESH
| 1.19.2.2 | V9002691
| 1.19.2.3 | VDM00622
| 1.20.2.1 | V0028222
| 1.20.2.2 | MAADEN
| 1.20.2.3 | MAADENMMGP
| 1.21.2.1 | V0071399
| 1.21.2.2 | VQM00099
| 1.21.2.3 | MAHAVEER
| 1.22.2.5 | MAHESHKOMMURU
| 1.3.1.2 | MAHESH.SONKUSARE
| 1.5.1.2 | MAKLESUR
| 1.5.1.3 | MANASKHARA
| 1.7.1.2 | MANASPATRA
| 1.9.1.2 | MANIKC
| 1.19.1.1 | MANISHA
| 1.24.1.2 | MANU
MANOJ
MANOJBERA
MLDAS
MANOJTIKADAR
V0014929
VMM01153
RESHMAMATCHA
MDALI
MFS
RIZWANM
EKRAMUL
MMJUDDIN
NAWAJ
VAM00587
V0008456
VMM00875
V0005548
VAM00648
V0057586
VCM00779
MILANM
MITAGANGULY
MITHUNMONDAL
VQM00019
V0005833
MNKR
V0016802
V0073910
MONOJG
MSG
MMITRA
MRINMOY
MJM
V0012457
MUKULM
MURARIMONDAL
NABANKURD
V0061971
V9002721
VCN00153
V0061185
JANESHWOR
NTIWARI
NASH
V0056712
NAVEEN.KUMAR1
V0075941
V0022353
V0000071
VCN00273
NKAMLE
NIKITACHAUDHARY
NILADRI
NIR
NIRMALYA
NISITH
NTPC
V0007307
VQO00002
BHAWAL
PKSINHA
PKUNDU
PAMPIBISWAS
PSAHA
PSOM
VQP00037
PMB
MISHRAPARTH
PARTHAAICH
PPP
PSB
PATRATU
PAWANKUMAR
PAYEL
VLP00874
VMP00869
VMP00864
V0010524
PML
VCP00519
V0061431
PRABINMOHTA
PROBIRDUTTA
PRABIRGHOSAL
PKPAL
PRADEEPS
PRADIPDEY
DOKA-CCRO
PMAJUMDAR
PRAKASHJIS
PRS
PGUIN
PHL
PRO
PCHATTERJEE
PRATIMGHOSH
PRAVAKAR.MALIK
PHAJARE
VAP00462
VCP00381
V8000200
PRITAMADAK
PRIYATOSHDHARA
V0061237
PROMITRAY
PRONOBESH
PDAFADAR
PBAGCHI
PROSENJIT
VQP00015
RABINDRAKUMAR
TARKESH
RAJ.GUPTA
RSK
RABINDAS
VCR00874
RAJAD
DRAJA
RAJARSHI
PATHAKR
RAJAT.BORAL
RAJESHM
RAJIBD
RAJIBB
RAJIBM
RAJIBSEN
KRAKESH
RAM.KISHORE
RAMPRASAD
RAMSHARMA
RKNIT
RAMESHS
RPA
RJM
RANDHIRKUMAR
RANGANATHMKR
RANJAN
RANJITGHOSH
RANJITSAHA
RASHEDAHMED
SRATHNAKUMAR
SWAMYSG
SULTANARAZIA
V0002633
JREPUELA
VDR00301
V0010053
JRINGEVAL
RINLVIZAG
RINTUMALLICK
RITESHK
RITESHS
RWK
V0053378
VDR00408
ROHTASHSINGH
RONGALI
RUBELDHAR
RUMELI
RUPANMITRA
SATRUJIT
SOUVIKSAHA
GURUNADH
SABYASACHIC
V0013639
V0075010
SBERA
SAIBALSAHA
SAIKATROY
SAIKATSRIMANI
SAJALC
SALILBERA
V0061582
SAMB
MANNAS
SPAIKARA
SAMBITBISWAS
SAMBITGIRI
SAMIRANJAN
SAMIR
SAMIRON
SAMRATDEY
SANDEEP.BARIK
MSANDEEPKR
SANDEEP.MOZUMDAR
SANDHIREDDY
SANDIPBASAK
SANDIPDEY
SANDIPCHANDRA
SANDIPSARKAR
SANDIPANB
SRU
SANJAYHALDER
SANJAYKSAHA
SSU
SANJIBKMONDAL
BSANJOY
SJU
SANKARD
DASSANKAR
SANKAR
SANKHA
SANTANUBANIK
SANTIGOPALKAR
SANTOSHANAND
SSIKDAR
NSARAVANA
ASARAVANAN
SARAVANAN
SASWATA
SATHISHPSK
SATTWIKNAG
SATYAGV
VQF00025
V0010020
SEERAT
VMS01151
VQS00105
SETHU
SAA
SSTHAKUR
SMALLICK
SHANTANUKHAMARU
SHAONIDAS
SHARANC
SHARMILA
SHASHANK.SHEKHAR
SHASHIBKUMAR
SHATAYU
ROYSHIBASHIS
SBT
VCS01452
V0049799
SHUB
SHYAMKUMARS
SHYENJIT
SIDDHARTHAPAL
VCS00892
SILADITYAM
SIRSHAKMAJI
SISIR.CHHETRI
SITANGSHU.ROY
V0001465
SHN
MAIDUL
IFTIKAR
VCS01447
V0001771
SMC2020
SMITASHA
SYY
SOMALI
SOMESHGHOSH
HSOMNATH
MUKHERJEES
SOR
SOMRAJ
SDUBEY
SOMYAKANTABEHERA
V0044673
SONJIT
SOUMENDATTA
SOUMEN-MALLICK
SOUMOMANDAL
SYH
SOURAV.BHOUMIK
SOURAVDAS
SOURAVDUTTA
GHOSGSOURAV
SOURAV
SOURAV.MODI
SOURAVMUDI
SOURAVMUKHERJEE
SOURAVPATRA
SOURISHSEN
SOUTRIK
SOUVIK
SOVANLAL
V0025620
VMS00853
SRIKUMARAN
SRIDAM
SBANDYO
SRINATHC
VMS01758
RSINI
SRINWANTI
V0015037
VMS00882
V0046813
SUBM
SUBHAJIT
SUBHAJITGHOSH
SUBHANKARB
SUBHASISNAYAK
BARMANS
B-SUBHENDU
SUBHENDU
SUVENDUSENAPATI
SDY
SUBHRAJYOTI
SUBHRA2008
ARSUBBU
SADHIKARY
SHH
SUBRATADEY
SGAYEN
SUBRATASEN
SDM
SUDARSHAN.BEHERA
SUDEEPTANANDI
SUDIPBISWAS
SUDIPDEY
SKD
DEBNATHS
SUDIPTAPAL
SUDIPTASARKAR
DESHMUKH
CSUGATA
SUJ
SUJAY
SJW
SUJOYDEY
SUJOYDC
SUKALYANGHOSH
SUKHENDU
SUMANBANIK
SUMAN.HATI
SUMAN.K
SUMANPODDER
SUMANROY
SUMANA
SDE
SUMANTA.KM
SNASKAR
SUMITC
SUMITDAS
SUMITG
JENA
SUMITKARN
SUMITKROY
VYS00067
SUMON.MAJUMDAR
VCS00777
SUNNYCHOWDHURY
SKARMAKAR
SUPRIYOB
SAICH
SURAJITK
SURAJITPAL
SURAJIT_ROY
SURANJIT.MOHANTY
SURESHBAHADUR
SUG
SURYAKUMAR.B
SUSANTAKHAN
SUSANTAP
SUSHANTA
SUSMI
SUSMITPAUL
SUTANUBISWAS
SUTANU GANGULY
SGL
V0014340
SUVADEEP
SUVAJITGHOSH
RAKSHIT
SUVAM
SUVANKAR
SUVASISH
SUVRADIP
SWAPANB
VCS01350
TGR
KUMARESAN
TAMAGHANA
TDM
TAMALSENGUPTA
TANIA
TANMAYDAS
TB
VQT00022
TAPAND
TKU
TSADHU
TAPASKUMAR
TKC
S.TAPAS
V0042109
KUMARTARUN
TATSATDUTTA
V0000103
VCT01044
V0059516
V0048626
V0050386
TESTVENDOR
TEST VENDOR
V0008515
V0002843
TIRTHANKARSINHA
VLT00254
TRIDEEPC
V0050834
VCT01073
BARUATRIDIB
TUFAN
TUHINM
UDAYAN
UJJALM
UJJWALPAL
URA
V0013174
VMU00831
V0064928
V0061820
VCU00092
VBU00099
VCU00117
V0007942
VQU00008
UPJ
UTTAMPARIA
V0073419
V0010083
VRP
VQV00004
VSD
CPVV
V0021352
VICTORHAZRA
VIJAYAR
VINAY.SILSWAL
VINOD.CHOUDHARY
VINOTHILAYA
VISHAL-CHAUHAN
VISHAL
VIZAGPHS
V0052770
SCV00013
VCV00203
VCW00045
VCM00441
WINSTON.P
WKDC
YOU_HB
V0072337