## Task Properties
Sl.No. | Task Genealogy* | Task Name* | WBS Level Code | Parent WBS Level | Task Hierarchy | Task Status | Edit Schedule Dates | Edit Actual Dates | Planned Start | Planned Finish | Forecasted Start | Forecasted Finish | Internal Start | Internal Finish | Actual Start | Actual Finish | Constraint Start | Constraint Finish | Planned Percentage | Percentage Completed | Approval Code Based Progress | Area Description (Area Code) | System Description (System Code) | Document Genealogy | Document Number | Sheet Number | Document Created Date | Client Document Number | Vendor Document Number | Origin Type | Origin Name | Approval Requirement Code | Approval Status Code(Internal) | Approval Status Code(Client) | Task Workflow Team | Progress Contribution To Parent | Progress Contribution To Project | Weightage | Progress Towards | Progress Captured As | Task UOM | Budgeted Cost | Forecasted Cost | Actual Cost | Budgeted Duration | Forecasted Duration | Actual Duration | Budgeted Quantity | Forecasted Quantity | Actual Quantity | As Built Quantity | Baseline Duration | Conversion Factor | Alpha | Beta | Interval | Distribution Type | Customer Weightage | Milestone Task | Customer Schedule | Task Code | Task Revision Number | Task Level | Task Priority | Resource Names | Privileged Task Resources | Task Remarks | Early Start Date | Early Finish Date | Late Start Date | Late Finish Date | Early Percentage | Late Percentage | Ruleset Name | Engineering-Drawing Start(Planned Finish Date) | Engineering-Drawing Start(Forecasted Finish Date) | Engineering-Drawing Start(Schedule Code) | Engineering-Drawing Start(Percentage) | Engineering-Drawing Start(Actual Finish Date) | Engineering-Drawing Start(Early Finish Date) | Engineering-Drawing Start(Late Finish Date) | Engineering-Document Submission(Planned Finish Date) | Engineering-Document Submission(Forecasted Finish Date) | Engineering-Document Submission(Schedule Code) | Engineering-Document Submission(Percentage) | Engineering-Document Submission(Actual Finish Date) | Engineering-Document Submission(Early Finish Date) | Engineering-Document Submission(Late Finish Date) | Engineering-IDC Review(Planned Finish Date) | Engineering-IDC Review(Forecasted Finish Date) | Engineering-IDC Review(Schedule Code) | Engineering-IDC Review(Percentage) | Engineering-IDC Review(Actual Finish Date) | Engineering-IDC Review(Early Finish Date) | Engineering-IDC Review(Late Finish Date) | Engineering-Issue to Client(Planned Finish Date) | Engineering-Issue to Client(Forecasted Finish Date) | Engineering-Issue to Client(Schedule Code) | Engineering-Issue to Client(Percentage) | Engineering-Issue to Client(Actual Finish Date) | Engineering-Issue to Client(Early Finish Date) | Engineering-Issue to Client(Late Finish Date) | Engineering-Client Review(Planned Finish Date) | Engineering-Client Review(Forecasted Finish Date) | Engineering-Client Review(Schedule Code) | Engineering-Client Review(Percentage) | Engineering-Client Review(Actual Finish Date) | Engineering-Client Review(Early Finish Date) | Engineering-Client Review(Late Finish Date) | Engineering-Client Review (R1)(Planned Finish Date) | Engineering-Client Review (R1)(Forecasted Finish Date) | Engineering-Client Review (R1)(Schedule Code) | Engineering-Client Review (R1)(Percentage) | Engineering-Client Review (R1)(Actual Finish Date) | Engineering-Client Review (R1)(Early Finish Date) | Engineering-Client Review (R1)(Late Finish Date) | Engineering-Issue to Client(R1)(Planned Finish Date) | Engineering-Issue to Client(R1)(Forecasted Finish Date) | Engineering-Issue to Client(R1)(Schedule Code) | Engineering-Issue to Client(R1)(Percentage) | Engineering-Issue to Client(R1)(Actual Finish Date) | Engineering-Issue to Client(R1)(Early Finish Date) | Engineering-Issue to Client(R1)(Late Finish Date) | Engineering-Issue to Client(R2)(Planned Finish Date) | Engineering-Issue to Client(R2)(Forecasted Finish Date) | Engineering-Issue to Client(R2)(Schedule Code) | Engineering-Issue to Client(R2)(Percentage) | Engineering-Issue to Client(R2)(Actual Finish Date) | Engineering-Issue to Client(R2)(Early Finish Date) | Engineering-Issue to Client(R2)(Late Finish Date) | Engineering-Client Review (R2)(Planned Finish Date) | Engineering-Client Review (R2)(Forecasted Finish Date) | Engineering-Client Review (R2)(Schedule Code) | Engineering-Client Review (R2)(Percentage) | Engineering-Client Review (R2)(Actual Finish Date) | Engineering-Client Review (R2)(Early Finish Date) | Engineering-Client Review (R2)(Late Finish Date) | Engineering-Issue to Client (R3)(Planned Finish Date) | Engineering-Issue to Client (R3)(Forecasted Finish Date) | Engineering-Issue to Client (R3)(Schedule Code) | Engineering-Issue to Client (R3)(Percentage) | Engineering-Issue to Client (R3)(Actual Finish Date) | Engineering-Issue to Client (R3)(Early Finish Date) | Engineering-Issue to Client (R3)(Late Finish Date) | Engineering-Client Review (R3)(Planned Finish Date) | Engineering-Client Review (R3)(Forecasted Finish Date) | Engineering-Client Review (R3)(Schedule Code) | Engineering-Client Review (R3)(Percentage) | Engineering-Client Review (R3)(Actual Finish Date) | Engineering-Client Review (R3)(Early Finish Date) | Engineering-Client Review (R3)(Late Finish Date) | Engineering-Issue to Client (R4)(Planned Finish Date) | Engineering-Issue to Client (R4)(Forecasted Finish Date) | Engineering-Issue to Client (R4)(Schedule Code) | Engineering-Issue to Client (R4)(Percentage) | Engineering-Issue to Client (R4)(Actual Finish Date) | Engineering-Issue to Client (R4)(Early Finish Date) | Engineering-Issue to Client (R4)(Late Finish Date) | Engineering-Client Review (R4)(Planned Finish Date) | Engineering-Client Review (R4)(Forecasted Finish Date) | Engineering-Client Review (R4)(Schedule Code) | Engineering-Client Review (R4)(Percentage) | Engineering-Client Review (R4)(Actual Finish Date) | Engineering-Client Review (R4)(Early Finish Date) | Engineering-Client Review (R4)(Late Finish Date) | Engineering-Final Release/GFC(Planned Finish Date) | Engineering-Final Release/GFC(Forecasted Finish Date) | Engineering-Final Release/GFC(Schedule Code) | Engineering-Final Release/GFC(Percentage) | Engineering-Final Release/GFC(Actual Finish Date) | Engineering-Final Release/GFC(Early Finish Date) | Engineering-Final Release/GFC(Late Finish Date) | Internal-Draftsman submission(Planned Finish Date) | Internal-Draftsman submission(Forecasted Finish Date) | Internal-Draftsman submission(Schedule Code) | Internal-Draftsman submission(Percentage) | Internal-Draftsman submission(Actual Finish Date) | Internal-Draftsman submission(Early Finish Date) | Internal-Draftsman submission(Late Finish Date) | Internal-Discipline Review(Planned Finish Date) | Internal-Discipline Review(Forecasted Finish Date) | Internal-Discipline Review(Schedule Code) | Internal-Discipline Review(Percentage) | Internal-Discipline Review(Actual Finish Date) | Internal-Discipline Review(Early Finish Date) | Internal-Discipline Review(Late Finish Date) | Internal-IDC Review(Planned Finish Date) | Internal-IDC Review(Forecasted Finish Date) | Internal-IDC Review(Schedule Code) | Internal-IDC Review(Percentage) | Internal-IDC Review(Actual Finish Date) | Internal-IDC Review(Early Finish Date) | Internal-IDC Review(Late Finish Date) | Internal-Final Release(Planned Finish Date) | Internal-Final Release(Forecasted Finish Date) | Internal-Final Release(Schedule Code) | Internal-Final Release(Percentage) | Internal-Final Release(Actual Finish Date) | Internal-Final Release(Early Finish Date) | Internal-Final Release(Late Finish Date) | Vendor-Vendor Submission(Planned Finish Date) | Vendor-Vendor Submission(Forecasted Finish Date) | Vendor-Vendor Submission(Schedule Code) | Vendor-Vendor Submission(Percentage) | Vendor-Vendor Submission(Actual Finish Date) | Vendor-Vendor Submission(Early Finish Date) | Vendor-Vendor Submission(Late Finish Date) | Vendor-Discipline Review(Planned Finish Date) | Vendor-Discipline Review(Forecasted Finish Date) | Vendor-Discipline Review(Schedule Code) | Vendor-Discipline Review(Percentage) | Vendor-Discipline Review(Actual Finish Date) | Vendor-Discipline Review(Early Finish Date) | Vendor-Discipline Review(Late Finish Date) | Vendor-IDC Review(Planned Finish Date) | Vendor-IDC Review(Forecasted Finish Date) | Vendor-IDC Review(Schedule Code) | Vendor-IDC Review(Percentage) | Vendor-IDC Review(Actual Finish Date) | Vendor-IDC Review(Early Finish Date) | Vendor-IDC Review(Late Finish Date) | Vendor-Issue to Client(Planned Finish Date) | Vendor-Issue to Client(Forecasted Finish Date) | Vendor-Issue to Client(Schedule Code) | Vendor-Issue to Client(Percentage) | Vendor-Issue to Client(Actual Finish Date) | Vendor-Issue to Client(Early Finish Date) | Vendor-Issue to Client(Late Finish Date) | Vendor-Client Review(Planned Finish Date) | Vendor-Client Review(Forecasted Finish Date) | Vendor-Client Review(Schedule Code) | Vendor-Client Review(Percentage) | Vendor-Client Review(Actual Finish Date) | Vendor-Client Review(Early Finish Date) | Vendor-Client Review(Late Finish Date) | Vendor-Final Release(Planned Finish Date) | Vendor-Final Release(Forecasted Finish Date) | Vendor-Final Release(Schedule Code) | Vendor-Final Release(Percentage) | Vendor-Final Release(Actual Finish Date) | Vendor-Final Release(Early Finish Date) | Vendor-Final Release(Late Finish Date) | PR STANDARD-Started(Planned Finish Date) | PR STANDARD-Started(Forecasted Finish Date) | PR STANDARD-Started(Schedule Code) | PR STANDARD-Started(Percentage) | PR STANDARD-Started(Actual Finish Date) | PR STANDARD-Started(Early Finish Date) | PR STANDARD-Started(Late Finish Date) | PR STANDARD-Issued for Inter-disciplinary Check (IDC)(Planned Finish Date) | PR STANDARD-Issued for Inter-disciplinary Check (IDC)(Forecasted Finish Date) | PR STANDARD-Issued for Inter-disciplinary Check (IDC)(Schedule Code) | PR STANDARD-Issued for Inter-disciplinary Check (IDC)(Percentage) | PR STANDARD-Issued for Inter-disciplinary Check (IDC)(Actual Finish Date) | PR STANDARD-Issued for Inter-disciplinary Check (IDC)(Early Finish Date) | PR STANDARD-Issued for Inter-disciplinary Check (IDC)(Late Finish Date) | PR STANDARD-Final Release to Buiseness Unit (FRB)(Planned Finish Date) | PR STANDARD-Final Release to Buiseness Unit (FRB)(Forecasted Finish Date) | PR STANDARD-Final Release to Buiseness Unit (FRB)(Schedule Code) | PR STANDARD-Final Release to Buiseness Unit (FRB)(Percentage) | PR STANDARD-Final Release to Buiseness Unit (FRB)(Actual Finish Date) | PR STANDARD-Final Release to Buiseness Unit (FRB)(Early Finish Date) | PR STANDARD-Final Release to Buiseness Unit (FRB)(Late Finish Date) | PR STANDARD-RFQ Release(Planned Finish Date) | PR STANDARD-RFQ Release(Forecasted Finish Date) | PR STANDARD-RFQ Release(Schedule Code) | PR STANDARD-RFQ Release(Percentage) | PR STANDARD-RFQ Release(Actual Finish Date) | PR STANDARD-RFQ Release(Early Finish Date) | PR STANDARD-RFQ Release(Late Finish Date) | PR STANDARD-Technical Evaluation(Planned Finish Date) | PR STANDARD-Technical Evaluation(Forecasted Finish Date) | PR STANDARD-Technical Evaluation(Schedule Code) | PR STANDARD-Technical Evaluation(Percentage) | PR STANDARD-Technical Evaluation(Actual Finish Date) | PR STANDARD-Technical Evaluation(Early Finish Date) | PR STANDARD-Technical Evaluation(Late Finish Date) | PR STANDARD-Offer Evaluation(Planned Finish Date) | PR STANDARD-Offer Evaluation(Forecasted Finish Date) | PR STANDARD-Offer Evaluation(Schedule Code) | PR STANDARD-Offer Evaluation(Percentage) | PR STANDARD-Offer Evaluation(Actual Finish Date) | PR STANDARD-Offer Evaluation(Early Finish Date) | PR STANDARD-Offer Evaluation(Late Finish Date) | PR STANDARD-PO Release(Planned Finish Date) | PR STANDARD-PO Release(Forecasted Finish Date) | PR STANDARD-PO Release(Schedule Code) | PR STANDARD-PO Release(Percentage) | PR STANDARD-PO Release(Actual Finish Date) | PR STANDARD-PO Release(Early Finish Date) | PR STANDARD-PO Release(Late Finish Date) | Authorized By | Category | Client Doc. Num. Without Rev. No. | Client Submission Date | Construction Activity | Construction Category | Discipline Category | Document Category | Document code | Document No.Without Rev. No. | Document Owner | Document Type | Funtional Unit | O19045 Document Category | O19045 Sub Category | Outotec Document Designation Number | Plan IFC Date | PO Number | Procube Code | Procube ID | Procube project ID | Qty in Document | RFQ Status | Serial | Size | Subcontractor Name | UOM | Weight in kg | TASK_ID
1 | Task(Task)-->E (Engineering) | NTPC's CHP KERENDARI | 1 |  | NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-08-01 18:00 | 2021-09-27 18:00 | 2019-08-01 09:00 | 2022-05-20 18:00 |  |  | 2019-09-27 10:57 |  |  |  | 65.8793 | 22.0725 | [15 empty] | 0 | 100 | 100 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2279 | 0 | 0 | High | [7 empty] | 0 | 0 | [246 empty] | 1017691
2 | Task(Task)-->E (Engineering) | RECEIPT OF NOA (ZERO DATE OF THE PROJECT) |  | 1 | RECEIPT OF NOA (ZERO DATE OF THE PROJECT)-->NTPC's CHP KERENDARI | Completed | No | No | 2019-09-27 09:00 | 2019-09-27 18:00 | 2019-09-27 09:00 | 2019-09-27 18:00 |  |  | 2020-07-23 17:44 | 2020-07-23 17:44 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | Yes | No | 2280 | 0 | 1 | High | [7 empty] | 0 | 0 | [246 empty] | 1017692
3 | Task(Task)-->C (Construction) | SURVEY, GEO-TECHNICAL INVESTIGATION, TEMPORARY STRUCTURE & APPROACH | 1.2 | 1 | SURVEY, GEO-TECHNICAL INVESTIGATION, TEMPORARY STRUCTURE & APPROACH-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-09-27 09:00 | 2020-06-14 23:59 | 2019-09-27 09:00 | 2020-12-30 18:00 |  |  | 2019-09-27 12:40 |  |  |  | 100 | 100 | [15 empty] | 0.2658 | 0.2658 | 26.14 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5596 | 0 | 1 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017693
4 | Task(Task)-->C (Construction) | ROUTE SURVEY (TOPOGRAPHY) |  | 1.2 | ROUTE SURVEY (TOPOGRAPHY)-->SURVEY, GEO-TECHNICAL INVESTIGATION, TEMPORARY STRUCTURE & APPROACH-->NTPC's CHP KERENDARI | Completed | No | No | 2019-10-21 09:00 | 2019-11-13 18:00 | 2019-10-21 09:00 | 2019-11-13 18:00 |  |  | 2019-10-21 12:24 | 2019-11-13 12:24 |  |  | 100 | 100 | [15 empty] | 100 | 0.2658 | 26.14 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5579 | 0 | 2 | Low | Santosh Anand | [6 empty] | 0 | 0 | [246 empty] | 1017694
5 | Task(Task)-->C (Construction) | GEO TECHNICAL INVESTIGATION WORK & SUBMISSION OF REPORT BY AGENCY |  | 1.2 | GEO TECHNICAL INVESTIGATION WORK & SUBMISSION OF REPORT BY AGENCY-->SURVEY, GEO-TECHNICAL INVESTIGATION, TEMPORARY STRUCTURE & APPROACH-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-28 09:00 | 2020-03-27 18:00 | 2020-01-22 09:00 | 2020-07-20 18:00 |  |  | 2020-01-22 12:25 | 2020-07-20 12:25 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5574 | 0 | 2 | Low | Niharendu Kamle,Santosh Anand | [6 empty] | 0 | 0 | [246 empty] | 1017695
6 | Task(Task)-->C (Construction) | CONSTRUCTION/ ESTABLISHMENT OF SITE OFFICE |  | 1.2 | CONSTRUCTION/ ESTABLISHMENT OF SITE OFFICE-->SURVEY, GEO-TECHNICAL INVESTIGATION, TEMPORARY STRUCTURE & APPROACH-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-10-19 09:00 | 2020-01-16 18:00 | 2020-01-01 09:00 | 2020-12-01 18:00 |  |  | 2020-01-01 10:18 |  |  |  | 100 | 70 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5580 | 0 | 2 | Low | Niharendu Kamle | [6 empty] | 0 | 0 | [246 empty] | 1017696
7 | Task(Task)-->C (Construction) | FINALIZATION OF SUB-CONTRACTOR FOR CIVIL WORK |  | 1.2 | FINALIZATION OF SUB-CONTRACTOR FOR CIVIL WORK-->SURVEY, GEO-TECHNICAL INVESTIGATION, TEMPORARY STRUCTURE & APPROACH-->NTPC's CHP KERENDARI | Completed | No | No | 2019-09-27 09:00 | 2019-10-26 18:00 | 2019-09-27 09:00 | 2020-02-04 18:00 |  |  | 2019-09-27 12:40 | 2020-02-04 12:38 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5582 | 0 | 2 | Low | Santosh Anand | [6 empty] | 0 | 0 | [246 empty] | 1017697
8 | Task(Task)-->C (Construction) | LAND ACQUISITION FOR TEMPORARY STRUCTURE |  | 1.2 | LAND ACQUISITION FOR TEMPORARY STRUCTURE-->SURVEY, GEO-TECHNICAL INVESTIGATION, TEMPORARY STRUCTURE & APPROACH-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-17 09:00 | 2020-04-15 18:00 | 2020-01-01 09:00 | 2020-11-15 23:59 |  |  | 2020-01-01 10:15 |  |  |  | 100 | 75 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5604 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017698
9 | Task(Task)-->C (Construction) | ESTABLISHMENT OF BATCHING PLANT/ CEMENT GODOWN/ CONSTRUCTION WATER & QUALITY LAB |  | 1.2 | ESTABLISHMENT OF BATCHING PLANT/ CEMENT GODOWN/ CONSTRUCTION WATER & QUALITY LAB-->SURVEY, GEO-TECHNICAL INVESTIGATION, TEMPORARY STRUCTURE & APPROACH-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-16 | 2020-05-15 18:00 | 2020-04-10 09:00 | 2020-09-23 18:00 |  |  | 2020-04-10 10:16 |  |  |  | 100 | 80 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5584 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017699
10 | Task(Task)-->C (Construction) | CONSTRUCTION OF LABOUR CAMP ( CAPACITY FOR 450 LABOUR ) |  | 1.2 | CONSTRUCTION OF LABOUR CAMP ( CAPACITY FOR 450 LABOUR )-->SURVEY, GEO-TECHNICAL INVESTIGATION, TEMPORARY STRUCTURE & APPROACH-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-16 | 2020-06-14 23:59 | 2020-08-01 09:00 | 2020-11-28 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5583 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017700
11 | Task(Task)-->C (Construction) | CONSTRUCTION OF STORAGE SPACE/ SHEDS |  | 1.2 | CONSTRUCTION OF STORAGE SPACE/ SHEDS-->SURVEY, GEO-TECHNICAL INVESTIGATION, TEMPORARY STRUCTURE & APPROACH-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-16 | 2020-06-14 23:59 | 2020-01-01 09:00 | 2020-12-30 18:00 |  |  | 2020-01-01 10:20 |  |  |  | 100 | 50 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5589 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017701
12 | Task(Task)-->E (Engineering) | DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP | 1.3 | 1 | DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-09-27 09:00 | 2021-09-13 18:00 | 2019-09-27 09:00 | 2022-05-04 18:00 |  |  | 2019-09-27 10:57 |  |  |  | 63.6065 | 23.9468 | [15 empty] | 9.4645 | 9.4645 | 930.77 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2281 | 0 | 1 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017702
13 | Task(Task)-->E (Engineering) | ENGINEERING | 1.3.1 | 1.3 | ENGINEERING-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-10-26 18:00 | 2020-07-13 17:40 | 2019-11-30 18:00 | 2020-11-15 23:59 |  |  | 2019-10-31 17:40 |  |  |  | 100 | 98.0957 | [15 empty] | 3.0587 | 0.28949 | 28.47 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2282 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017703
14 | Task(Task)-->E (Engineering) | Mechanical | 1.3.1.1 | 1.3.1 | Mechanical-->ENGINEERING-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-10-26 18:00 | 2020-05-11 17:40 | 2019-11-30 18:00 | 2020-09-14 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 94.7067 | [15 empty] | 8.3275 | 0.024107 | 2.37 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No | 2283 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036070
15 | Task(Task)-->E (Engineering) | G.A. OF TYP. CHUTE & SKIRT |  | 1.3.1.1 | G.A. OF TYP. CHUTE & SKIRT-->Mechanical-->ENGINEERING-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-04 18:00 | 2020-02-21 17:40 | 2020-03-28 18:00 | 2020-05-08 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-0029 |  | 2020-02-13 10:26 | 7012-155-PVM-B-029 |  |  |  | I |  |  |  | 9.205 | 0.002219 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 80 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2290 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-04 18:00 | 2020-03-28 18:00 |  | 10 | 2020-03-28 23:31 |  |  | 2020-01-13 17:40 | 2020-04-12 23:59 |  | 30 | 2020-04-12 23:31 |  |  | 2020-01-18 17:40 | 2020-04-17 18:00 |  | 35 | 2020-04-17 23:31 |  |  | 2020-01-24 23:59 | 2020-04-17 18:00 |  | 65 | 2020-04-14 23:31 |  |  | 2020-01-30 17:40 | 2020-05-08 18:00 |  | 80 | 2020-05-08 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-02-21 17:40 | 2020-05-08 18:00 |  | 100 | [122 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 29 |  |  |  |  | 101043
16 | Task(Task)-->E (Engineering) | G.A OF GEARBOX FOR TROUGH BELT CONVEYORS |  | 1.3.1.1 | G.A OF GEARBOX FOR TROUGH BELT CONVEYORS-->Mechanical-->ENGINEERING-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-21 18:00 | 2020-05-11 17:40 | 2020-06-13 09:00 | 2020-06-30 18:00 |  |  | 2020-02-21 14:04 | 2020-07-02 11:13 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1002 |  | 2020-02-13 10:26 | 7012-155-PVM-B-102 |  |  |  | A |  |  |  | 13.3891 | 0.003228 | 0.32 | Plan & Actual | Date |  | 0 | 0 | 0 | 120 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2288 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-21 18:00 | 2020-05-18 18:00 |  | 10 | 2020-05-08 23:31 |  |  | 2020-03-31 17:40 | 2020-06-01 18:00 |  | 30 | 2020-05-23 23:31 |  |  | 2020-04-06 17:40 | 2020-06-08 18:00 |  | 35 | 2020-05-19 16:11 |  |  | 2020-04-11 23:59 | 2020-06-08 18:00 |  | 65 | 2020-05-19 16:18 |  |  | 2020-04-17 17:40 | 2020-06-29 18:00 |  | 80 | 2020-05-19 16:20 | [5 empty] | 80 | 2020-06-10 16:59 | [5 empty] | 80 | 2020-06-10 16:59 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-11 17:40 | 2020-06-29 18:00 |  | 100 | 2020-07-02 11:14 | [121 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 32 |  |  |  |  | 101046
17 | Task(Task)-->E (Engineering) | GA, BOM, WIRING AND TERMINAL DIAGRAM OF LOCAL CONTROL PANEL FOR LUBRICAION OF PRIMARY & SECONDARY SIZER |  | 1.3.1.1 | GA, BOM, WIRING AND TERMINAL DIAGRAM OF LOCAL CONTROL PANEL FOR LUBRICAION OF PRIMARY & SECONDARY SIZER-->Mechanical-->ENGINEERING-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-11 18:00 | 2020-04-23 17:40 | 2020-05-30 18:00 | 2020-09-14 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-406 |  | 2020-02-13 11:47 | 7012-155-PVE-W-142 |  |  |  | A |  |  |  | 4.6025 | 0.00111 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2286 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-11 18:00 | 2020-05-30 18:00 |  | 10 |  |  |  | 2020-03-12 17:40 | 2020-06-06 18:00 |  | 30 |  |  |  | 2020-03-19 17:40 | 2020-06-13 18:00 |  | 35 |  |  |  | 2020-03-25 23:59 | 2020-06-13 18:00 |  | 65 | 2020-09-23 13:36 |  |  | 2020-04-01 17:40 | 2020-07-04 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-23 17:40 | 2020-07-04 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 377 |  |  |  |  | 101388
18 | Task(Task)-->E (Engineering) | G.A & LOAD DATA OF DUMP HOPPER STATION (DH-1, DH-2, DH-3 & DH-4) |  | 1.3.1.1 | G.A & LOAD DATA OF DUMP HOPPER STATION (DH-1, DH-2, DH-3 & DH-4)-->Mechanical-->ENGINEERING-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-10-26 18:00 | 2019-12-30 17:40 | 2020-02-21 18:00 | 2020-05-04 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-0007 |  | 2020-02-13 10:26 | 7012-155-PVM-B-007 |  |  |  | A |  |  |  | 45.1883 | 0.010894 | 1.08 | Plan & Actual | Date |  | 0 | 0 | 0 | 400 | 0 | 100.31 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2284 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-10-26 18:00 | 2020-02-21 18:00 |  | 10 | 2020-02-21 23:31 |  |  | 2019-11-21 17:40 | 2020-03-20 18:00 |  | 30 | 2020-03-20 23:31 |  |  | 2019-11-27 17:40 | 2020-03-23 18:00 |  | 35 | 2020-03-23 23:31 |  |  | 2019-12-03 23:59 | 2020-03-30 18:00 |  | 65 | 2020-03-30 23:31 |  |  | 2019-12-09 17:40 | 2020-04-20 18:00 |  | 80 | 2020-04-20 23:31 | [5 empty] | 80 | 2020-08-21 17:37 | [5 empty] | 80 | 2020-08-21 17:37 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2019-12-30 17:40 | 2020-05-04 18:00 |  | 100 | 2020-04-23 23:31 | [121 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 7 |  |  |  |  | 101021
19 | Task(Task)-->E (Engineering) | G.A OF DRIBBLE CONVEYORS DF-1,DF-2, DF-3 & DF-4 |  | 1.3.1.1 | G.A OF DRIBBLE CONVEYORS DF-1,DF-2, DF-3 & DF-4-->Mechanical-->ENGINEERING-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-13 18:00 | 2020-02-29 17:40 | 2019-11-30 18:00 | 2020-01-17 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-0028 |  | 2020-02-13 10:26 | 7012-155-PVM-B-028 |  |  |  | A |  |  |  | 9.205 | 0.002219 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 80 | 0 | 5.05 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2289 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-13 18:00 | 2019-11-30 18:00 |  | 10 | 2019-11-30 23:31 |  |  | 2020-01-20 17:40 | 2019-12-12 18:00 |  | 30 | 2019-12-12 23:31 |  |  | 2020-01-25 17:40 | 2019-12-15 23:59 |  | 35 | 2019-12-15 23:31 |  |  | 2020-01-31 23:59 | 2019-12-18 18:00 |  | 65 | 2019-12-18 23:31 |  |  | 2020-02-06 17:40 | 2020-01-03 18:00 |  | 80 | 2020-01-03 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-02-29 17:40 | 2020-01-17 18:00 |  | 100 | [122 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 28 |  |  |  |  | 101042
20 | Task(Task)-->E (Engineering) | GA OF APRON FEEDERS AF-1,AF-2, AF-3 & AF-4 |  | 1.3.1.1 | GA OF APRON FEEDERS AF-1,AF-2, AF-3 & AF-4-->Mechanical-->ENGINEERING-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2019-10-31 18:00 | 2019-12-12 17:40 | 2020-01-30 09:00 | 2020-02-21 18:00 |  |  | 2020-02-21 14:04 | 2020-08-24 20:07 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1001 |  | 2020-02-13 10:26 | 7012-155-PVM-B-101 |  |  |  | A |  |  |  | 9.205 | 0.002219 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 80 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2287 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-10-31 18:00 | 2020-01-15 18:00 |  | 10 | 2020-01-15 23:31 |  |  | 2019-11-04 17:40 | 2020-01-22 18:00 |  | 30 | 2020-01-22 23:31 |  |  | 2019-11-09 17:40 | 2020-01-25 18:00 |  | 35 | 2020-01-25 23:31 |  |  | 2019-11-15 23:59 | 2020-01-30 18:00 |  | 65 | 2020-01-30 23:31 |  |  | 2019-11-21 17:40 | 2020-02-21 18:00 |  | 80 | 2020-02-21 23:31 | [5 empty] | 80 | 2020-08-19 18:17 | [5 empty] | 80 | 2020-08-19 11:03 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2019-12-12 17:40 | 2020-02-21 18:00 |  | 100 | 2020-08-24 20:08 | [121 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 31 |  |  |  |  | 101045
21 | Task(Task)-->E (Engineering) | GA OF PRIMARY SIZERS PS-1, PS-2, PS-3 & PS-4 |  | 1.3.1.1 | GA OF PRIMARY SIZERS PS-1, PS-2, PS-3 & PS-4-->Mechanical-->ENGINEERING-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2019-10-27 23:59 | 2019-12-21 17:40 | 2020-03-30 09:00 | 2020-06-10 18:00 |  |  | 2020-02-21 14:04 | 2020-06-29 19:15 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1006 |  | 2020-02-13 10:27 | 7012-155-PVM-B-106 |  |  |  | A |  |  |  | 9.205 | 0.002219 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 80 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2285 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-10-27 23:59 | 2020-03-18 18:00 |  | 10 | 2020-03-18 23:31 |  |  | 2019-11-13 17:40 | 2020-03-23 18:00 |  | 30 | 2020-03-23 23:31 |  |  | 2019-11-19 17:40 | 2020-03-28 18:00 |  | 35 | 2020-03-28 23:31 |  |  | 2019-11-25 23:59 | 2020-03-30 18:00 |  | 65 | 2020-03-30 23:31 |  |  | 2019-11-30 17:40 | 2020-04-20 18:00 |  | 80 | 2020-04-23 23:31 | [5 empty] | 80 | 2020-06-22 18:44 | [5 empty] | 80 | 2020-06-10 18:01 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2019-12-21 17:40 | 2020-05-04 18:00 |  | 100 | 2020-06-29 19:16 | [121 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 36 |  |  |  |  | 101050
22 | Task(Task)-->E (Engineering) | Civil | 1.3.1.2 | 1.3.1 | Civil-->ENGINEERING-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2019-10-31 17:40 | 2020-05-29 17:40 | 2020-01-04 09:00 | 2020-09-10 18:00 |  |  | 2019-10-31 17:40 | 2020-09-10 23:38 |  |  | 100 | 100 | [15 empty] | 79.2691 | 0.22948 | 22.56 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No | 2293 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036071
23 | Task(Task)-->E (Engineering) | DUMP HOPPER STATION (DH-1, DH-2, DH-3 & DH-4) - DESIGN CALCULATION FOR SUPER STRUCTURE |  | 1.3.1.2 | DUMP HOPPER STATION (DH-1, DH-2, DH-3 & DH-4) - DESIGN CALCULATION FOR SUPER STRUCTURE-->Civil-->ENGINEERING-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-21 18:00 | 2020-03-21 17:40 | 2020-05-29 09:00 | 2020-07-03 18:00 |  |  | 2020-02-21 15:30 | 2020-07-04 23:05 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0003 |  | 2020-02-13 11:41 | 7012-155-PVC-U-009 |  |  |  | A |  |  |  | 8.7284 | 0.02003 | 1.97 | Plan & Actual | Date |  | 0 | 0 | 0 | 733.13 | 0 | 38 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2297 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-21 18:00 | 2020-03-30 18:00 |  | 10 | 2020-03-30 23:31 |  |  | 2020-02-10 17:40 | 2020-05-01 18:00 |  | 30 | 2020-05-16 23:31 |  |  | 2020-02-15 17:40 | 2020-05-04 18:00 |  | 35 | 2020-05-20 23:31 |  |  | 2020-02-21 23:59 | 2020-05-11 18:00 |  | 65 | 2020-05-29 23:31 |  |  | 2020-02-28 17:40 | 2020-06-01 18:00 |  | 80 | 2020-07-04 23:03 | [5 empty] | 80 | 2020-07-04 23:03 | [5 empty] | 80 | 2020-07-04 22:58 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-21 17:40 | 2020-06-15 18:00 |  | 100 | 2020-07-04 23:06 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 110 |  |  |  |  | 101124
24 | Task(Task)-->E (Engineering) | DUMP HOPPER STATION (DH-1, DH-2, DH-3 & DH-4) - DESIGN CALCULATION FOR SUB STRUCTURE |  | 1.3.1.2 | DUMP HOPPER STATION (DH-1, DH-2, DH-3 & DH-4) - DESIGN CALCULATION FOR SUB STRUCTURE-->Civil-->ENGINEERING-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-29 18:00 | 2020-04-29 17:40 | 2020-06-29 09:00 | 2020-07-13 18:00 |  |  | 2020-02-21 15:30 | 2020-08-03 23:54 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0004 |  | 2020-02-13 11:41 | 7012-155-PVC-U-010 |  |  |  | A |  |  |  | 1.9052 | 0.004372 | 0.43 | Plan & Actual | Date |  | 0 | 0 | 0 | 158.06 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2298 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-29 18:00 | 2020-05-01 18:00 |  | 10 | 2020-05-01 23:31 |  |  | 2020-03-18 17:40 | 2020-06-02 18:00 |  | 30 |  |  |  | 2020-03-24 17:40 | 2020-06-05 18:00 |  | 35 |  |  |  | 2020-03-31 23:59 | 2020-06-12 18:00 |  | 65 | 2020-07-07 21:16 |  |  | 2020-04-06 17:40 | 2020-07-03 18:00 |  | 80 | 2020-07-07 21:22 | [5 empty] | 80 | 2020-08-03 23:50 | [5 empty] | 80 | 2020-08-03 23:50 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-29 17:40 | 2020-07-17 18:00 |  | 100 | 2020-08-03 23:54 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 111 |  |  |  |  | 101125
25 | Task(Task)-->E (Engineering) | DUMP HOPPER STATION (DH-1, DH-2, DH-3 & DH-4) - DESIGN CALCULATION FOR RETAINING WALL |  | 1.3.1.2 | DUMP HOPPER STATION (DH-1, DH-2, DH-3 & DH-4) - DESIGN CALCULATION FOR RETAINING WALL-->Civil-->ENGINEERING-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-29 18:00 | 2020-04-29 17:40 | 2020-06-17 09:00 | 2020-07-03 18:00 |  |  | 2020-07-04 22:52 | 2020-07-04 22:52 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0005 |  | 2020-02-13 11:41 | 7012-155-PVC-U-011 |  |  |  | A |  |  |  | 42.8002 | 0.098217 | 9.66 | Plan & Actual | Date |  | 0 | 0 | 0 | 3586.04 | 0 | 136 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2299 | 1 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-29 18:00 | 2020-04-16 18:00 |  | 10 | 2020-04-16 23:31 |  |  | 2020-03-18 17:40 | 2020-05-18 18:00 |  | 30 | 2020-05-12 23:31 |  |  | 2020-03-24 17:40 | 2020-05-21 18:00 |  | 35 |  |  |  | 2020-03-31 23:59 | 2020-05-28 18:00 |  | 65 | 2020-07-04 22:30 |  |  | 2020-04-06 17:40 | 2020-06-18 18:00 |  | 80 | 2020-07-04 22:37 | [5 empty] | 80 | 2020-07-04 22:53 | [5 empty] | 80 | 2020-07-04 22:53 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-29 17:40 | 2020-07-02 18:00 |  | 100 | 2020-07-04 22:40 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 112 |  |  |  |  | 101126
26 | Task(Task)-->E (Engineering) | DUMP HOPPER STATION (DH-1, DH-2, DH-3 & DH-4) - NUM & RC DETAILS OF FDN |  | 1.3.1.2 | DUMP HOPPER STATION (DH-1, DH-2, DH-3 & DH-4) - NUM & RC DETAILS OF FDN-->Civil-->ENGINEERING-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-29 18:00 | 2020-04-29 17:40 | 2020-06-29 09:00 | 2020-07-13 18:00 |  |  | 2020-02-21 15:37 | 2020-09-10 23:38 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-NR-0002 |  | 2020-02-13 11:41 | 7012-155-PVC-C-013 |  |  |  | A |  |  |  | 1.9052 | 0.004372 | 0.43 | Plan & Actual | Date |  | 0 | 0 | 0 | 158.06 | 0 | 52.15 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2294 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-29 18:00 | 2020-05-01 18:00 |  | 10 |  |  |  | 2020-03-18 17:40 | 2020-06-02 18:00 |  | 30 |  |  |  | 2020-03-24 17:40 | 2020-06-05 18:00 |  | 35 | 2020-06-29 15:58 |  |  | 2020-03-31 23:59 | 2020-06-12 18:00 |  | 65 | 2020-07-07 21:14 |  |  | 2020-04-06 17:40 | 2020-07-03 18:00 |  | 80 | 2020-07-07 21:21 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | 2020-09-10 23:23 | [5 empty] | 80 | 2020-09-10 23:23 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-29 17:40 | 2020-07-17 18:00 |  | 100 | 2020-09-10 23:39 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 114 |  |  |  |  | 101128
27 | Task(Task)-->E (Engineering) | DUMP HOPPER STATION (DH-1, DH-2, DH-3 & DH-4) - NUM & RC DETAILS OF GRADE SLAB |  | 1.3.1.2 | DUMP HOPPER STATION (DH-1, DH-2, DH-3 & DH-4) - NUM & RC DETAILS OF GRADE SLAB-->Civil-->ENGINEERING-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-30 18:00 | 2020-05-29 17:40 | 2020-08-14 09:00 | 2020-09-10 18:00 |  |  | 2020-02-21 15:37 | 2020-09-10 23:14 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-NR-0003 |  | 2020-02-13 11:41 | 7012-155-PVC-C-014 |  |  |  | A |  |  |  | 0.88613 | 0.002033 | 0.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 74.27 | 0 | 49.1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2295 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-30 18:00 | 2020-05-31 23:59 |  | 10 |  |  |  | 2020-04-17 17:40 | 2020-07-02 18:00 |  | 30 |  |  |  | 2020-04-23 17:40 | 2020-07-05 23:59 |  | 35 | 2020-08-14 23:25 |  |  | 2020-04-30 23:59 | 2020-07-12 23:59 |  | 65 | 2020-08-14 23:30 |  |  | 2020-05-06 17:40 | 2020-08-02 23:59 |  | 80 | 2020-09-10 22:17 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-29 17:40 | 2020-08-16 23:59 |  | 100 | 2020-09-10 23:15 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 115 |  |  |  |  | 101129
28 | Task(Task)-->E (Engineering) | DUMP HOPPER STATION (DH-1, DH-2, DH-3 & DH-4) - NUM & RC DETAILS OF RETAINING WALL |  | 1.3.1.2 | DUMP HOPPER STATION (DH-1, DH-2, DH-3 & DH-4) - NUM & RC DETAILS OF RETAINING WALL-->Civil-->ENGINEERING-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-29 18:00 | 2020-04-29 17:40 | 2020-06-17 09:00 | 2020-07-03 18:00 |  |  | 2020-07-04 22:41 | 2020-07-04 22:41 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-NR-0004 |  | 2020-02-13 11:41 | 7012-155-PVC-C-015 |  |  |  | A |  |  |  | 42.8002 | 0.098217 | 9.66 | Plan & Actual | Date |  | 0 | 0 | 0 | 3586.04 | 0 | 53.1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2296 | 1 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-29 18:00 | 2020-04-16 18:00 |  | 10 | 2020-04-16 23:31 |  |  | 2020-03-18 17:40 | 2020-05-18 18:00 |  | 30 |  |  |  | 2020-03-24 17:40 | 2020-05-21 18:00 |  | 35 | 2020-06-11 12:23 |  |  | 2020-03-31 23:59 | 2020-05-28 18:00 |  | 65 | 2020-07-04 22:23 |  |  | 2020-04-06 17:40 | 2020-06-18 18:00 |  | 80 | 2020-07-04 22:36 | [5 empty] | 80 | 2020-07-04 22:42 | [5 empty] | 80 | 2020-07-04 22:42 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-29 17:40 | 2020-07-02 18:00 |  | 100 | 2020-07-04 22:38 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 116 |  |  |  |  | 101130
29 | Task(Task)-->E (Engineering) | MANUAL POWER AND TENSION CALCULATION FOR TROUGH CONVEYOR SC 1A/B AND SC 2A/B |  | 1.3.1.2 | MANUAL POWER AND TENSION CALCULATION FOR TROUGH CONVEYOR SC 1A/B AND SC 2A/B-->Civil-->ENGINEERING-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2019-10-31 17:40 | 2019-12-09 17:40 | 2020-01-04 09:00 | 2020-02-25 18:00 |  |  | 2019-10-31 17:40 | 2020-03-02 10:56 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-CS-DC-0003 |  | 2020-02-13 10:26 | 7012-155-PVM-U-003 |  |  |  | A |  |  |  | 0.97475 | 0.002237 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3056 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-10-19 18:00 | 2019-12-11 18:00 |  | 10 | 2019-12-11 23:31 |  |  | 2019-10-31 17:40 | 2020-01-01 18:00 |  | 30 | 2020-01-01 23:31 |  |  | 2019-11-06 17:40 | 2020-01-04 18:00 |  | 35 | 2020-01-04 23:31 |  |  | 2019-11-12 23:59 | 2020-01-04 18:00 |  | 65 | 2020-01-04 23:31 |  |  | 2019-11-18 17:40 | 2020-02-03 18:00 |  | 80 | 2020-02-03 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2019-12-09 17:40 | 2020-02-25 18:00 |  | 100 | 2020-02-25 23:31 | [121 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 3 |  |  |  |  | 101017
30 | Task(Task)-->E (Engineering) | Structural | 1.3.1.3 | 1.3.1 | Structural-->ENGINEERING-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-01-21 18:00 | 2020-07-13 17:40 | 2020-05-29 09:00 | 2020-11-15 23:59 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 98.1489 | [15 empty] | 7.3085 | 0.021158 | 2.08 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No | 2300 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036072
31 | Task(Task)-->E (Engineering) | DUMP HOPPER STATION (DH-1, DH-2, DH-3 & DH-4) - STRUCTURAL GA |  | 1.3.1.3 | DUMP HOPPER STATION (DH-1, DH-2, DH-3 & DH-4) - STRUCTURAL GA-->Structural-->ENGINEERING-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-21 18:00 | 2020-03-21 17:40 | 2020-05-29 09:00 | 2020-07-03 18:00 |  |  | 2020-02-21 15:37 | 2020-07-04 23:07 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-GA-0004 |  | 2020-02-13 11:41 | 7012-155-PVC-B-012 |  |  |  | A |  |  |  | 94.7115 | 0.020039 | 1.97 | Plan & Actual | Date |  | 0 | 0 | 0 | 733.13 | 0 | 86 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2301 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-21 18:00 | 2020-03-30 18:00 |  | 10 | 2020-03-30 23:31 |  |  | 2020-02-10 17:40 | 2020-05-01 18:00 |  | 30 | 2020-05-16 23:31 |  |  | 2020-02-15 17:40 | 2020-05-04 18:00 |  | 35 | 2020-05-20 23:31 |  |  | 2020-02-21 23:59 | 2020-05-11 18:00 |  | 65 | 2020-05-29 23:31 |  |  | 2020-02-28 17:40 | 2020-06-01 18:00 |  | 80 | 2020-07-04 23:04 | [5 empty] | 80 | 2020-07-04 23:04 | [5 empty] | 80 | 2020-07-04 22:59 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-21 17:40 | 2020-06-15 18:00 |  | 100 | 2020-07-04 23:08 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 113 |  |  |  |  | 101127
32 | Task(Task)-->E (Engineering) | ARCHITECTURAL GA OF DUMP HOPPER STATION (DH-1, DH-2, DH-3 & DH-4) |  | 1.3.1.3 | ARCHITECTURAL GA OF DUMP HOPPER STATION (DH-1, DH-2, DH-3 & DH-4)-->Structural-->ENGINEERING-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-14 18:00 | 2020-07-13 17:40 | 2020-06-22 18:00 | 2020-11-15 23:59 |  |  | 2020-02-21 15:39 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-AR-0001 |  | 2020-02-13 11:43 | 7012-155-PVC-C-107 |  |  |  | I |  |  |  | 5.2885 | 0.001119 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 40.52 | 0 | 56 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2302 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-05-14 18:00 | 2020-06-22 18:00 |  | 10 |  |  |  | 2020-06-02 17:40 | 2020-07-17 18:00 |  | 30 |  |  |  | 2020-06-08 17:40 | 2020-07-20 18:00 |  | 35 | 2020-10-14 16:46 |  |  | 2020-06-14 23:59 | 2020-07-27 18:00 |  | 65 | 2020-10-14 17:37 |  |  | 2020-06-19 17:40 | 2020-08-17 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-07-13 17:40 | 2020-08-31 18:00 |  | 100 | [122 empty] | Chetan Khodke | [5 empty] | A - Architecture | [16 empty] | 208 |  |  |  |  | 101218
33 | Task(Task)-->E (Engineering) | ELECTRICAL | 1.3.1.4 | 1.3.1 | ELECTRICAL-->ENGINEERING-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-12-25 18:00 | 2020-04-21 17:40 | 2020-04-12 23:59 | 2020-08-18 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 73.9304 | [15 empty] | 5.0949 | 0.014749 | 1.45 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No | 2305 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036073
34 | Task(Task)-->E (Engineering) | GA, DATA SHEET, TERMINAL BOX ARRANGEMET & CHARACTERISTICS CURVES OF LT MOTOR (CONVEYING SYSTEM) |  | 1.3.1.4 | GA, DATA SHEET, TERMINAL BOX ARRANGEMET & CHARACTERISTICS CURVES OF LT MOTOR (CONVEYING SYSTEM)-->ELECTRICAL-->ENGINEERING-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-15 17:40 | 2020-03-27 17:40 | 2020-05-31 23:59 | 2020-08-18 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-162 |  | 2020-02-13 11:46 | 7012-155-PVE-W-107 |  |  |  | A |  |  |  | 7.5862 | 0.001119 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2308 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-15 18:00 | 2020-05-31 23:59 |  | 10 |  |  |  | 2020-02-15 17:40 | 2020-06-07 23:59 |  | 30 |  |  |  | 2020-02-21 17:40 | 2020-06-13 18:00 |  | 35 |  |  |  | 2020-02-28 23:59 | 2020-06-13 18:00 |  | 65 |  |  |  | 2020-03-05 17:40 | 2020-07-04 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-27 17:40 | 2020-07-04 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 342 |  |  |  |  | 101353
35 | Task(Task)-->E (Engineering) | EQUIPMENT, CABLE ROUTING, EARTHING & LIGHTNING LAYOUT WITH PLAN, SECTIONAL VIEWS & BOM OF DUMP HOPPER |  | 1.3.1.4 | EQUIPMENT, CABLE ROUTING, EARTHING & LIGHTNING LAYOUT WITH PLAN, SECTIONAL VIEWS & BOM OF DUMP HOPPER-->ELECTRICAL-->ENGINEERING-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-12-25 18:00 | 2020-02-19 17:40 | 2020-04-12 23:59 | 2020-05-31 23:59 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5052 |  | 2020-02-13 11:44 | 7012-155-PVE-F-014 |  |  |  | A |  |  |  | 46.2069 | 0.006815 | 0.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 248.42 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2306 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-12-25 18:00 | 2020-04-12 23:59 |  | 10 | 2020-04-12 23:31 |  |  | 2020-01-10 17:40 | 2020-04-26 23:59 |  | 30 | 2020-04-20 23:31 |  |  | 2020-01-16 17:40 | 2020-05-03 23:59 |  | 35 | 2020-04-27 23:31 |  |  | 2020-01-22 23:59 | 2020-05-10 23:59 |  | 65 | 2020-04-30 23:31 |  |  | 2020-01-28 17:40 | 2020-05-31 23:59 |  | 80 | 2020-05-11 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-02-19 17:40 | 2020-05-31 23:59 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 249 |  |  |  |  | 101260
36 | Task(Task)-->E (Engineering) | LIGHTING LAYOUT PLAN WITH POWER DISTRIBUTION ARRANGEMENT, SECTIONAL VIEW, BOM OF DUMP HOPPER |  | 1.3.1.4 | LIGHTING LAYOUT PLAN WITH POWER DISTRIBUTION ARRANGEMENT, SECTIONAL VIEW, BOM OF DUMP HOPPER-->ELECTRICAL-->ENGINEERING-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-02 18:00 | 2020-04-21 17:40 | 2020-04-24 18:00 | 2020-06-05 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5063 |  | 2020-02-13 11:44 | 7012-155-PVE-G-025 |  |  |  | A |  |  |  | 46.2069 | 0.006815 | 0.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 248.42 | 0 | 24.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2307 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-02 18:00 | 2020-04-24 18:00 |  | 10 | 2020-04-24 23:31 |  |  | 2020-03-10 17:40 | 2020-05-01 18:00 |  | 30 | 2020-04-28 23:31 |  |  | 2020-03-17 17:40 | 2020-05-08 18:00 |  | 35 | 2020-04-28 23:31 |  |  | 2020-03-23 23:59 | 2020-05-15 18:00 |  | 65 | 2020-04-30 23:31 |  |  | 2020-03-30 17:40 | 2020-06-05 18:00 |  | 80 | 2020-05-11 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-21 17:40 | 2020-06-05 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 260 |  |  |  |  | 101271
37 | Task(Task)-->P (Procurement) | PROCUREMENT | 1.3.2 | 1.3 | PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-09-27 09:00 | 2021-02-28 23:59 | 2019-09-27 09:00 | 2021-06-13 23:59 |  |  | 2019-09-27 10:57 |  |  |  | 89.1451 | 44.3885 | [15 empty] | 47.1465 | 4.4622 | 438.83 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2310 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017708
38 | Task(Task)-->P (Procurement) | PURCHASE REQUISITION | 1.3.2.1 | 1.3.2 | PURCHASE REQUISITION-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2019-09-27 09:00 | 2020-05-19 18:00 | 2019-09-27 09:00 | 2020-05-29 18:00 |  |  | 2019-09-27 10:57 | 2020-05-31 18:44 |  |  | 100 | 100 | [15 empty] | 4.9952 | 0.2229 | 21.92 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2311 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017709
39 | Task(Task)-->P (Procurement) | Apron Feeder |  | 1.3.2.1 | Apron Feeder-->PURCHASE REQUISITION-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2019-09-27 09:00 | 2019-09-27 18:00 | 2019-09-27 09:00 | 2019-09-27 18:00 |  |  | 2019-09-27 10:57 | 2019-09-27 10:57 |  |  | 100 | 100 | [15 empty] | 19.1062 | 0.042587 | 4.19 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2312 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017710
40 | Task(Task)-->P (Procurement) | Gear Box for Apron Feeder |  | 1.3.2.1 | Gear Box for Apron Feeder-->PURCHASE REQUISITION-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-13 09:00 | 2019-11-13 18:00 | 2020-01-20 09:00 | 2020-01-20 18:00 |  |  | 2020-01-20 11:17 | 2020-01-20 11:17 |  |  | 100 | 100 | [15 empty] | 0.91199 | 0.002033 | 0.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2313 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017711
41 | Task(Task)-->P (Procurement) | Geared Coupling for Apron Feeder |  | 1.3.2.1 | Geared Coupling for Apron Feeder-->PURCHASE REQUISITION-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-21 09:00 | 2019-11-21 18:00 | 2020-04-04 09:00 | 2020-04-04 18:00 |  |  | 2020-04-04 10:57 | 2020-04-04 10:57 |  |  | 100 | 100 | [15 empty] | 0.1824 | 0.000407 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2314 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017712
42 | Task(Task)-->P (Procurement) | Primary Sizer |  | 1.3.2.1 | Primary Sizer-->PURCHASE REQUISITION-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2019-09-27 09:00 | 2019-09-27 18:00 | 2019-09-27 09:00 | 2019-09-27 18:00 |  |  | 2019-09-27 10:57 | 2019-09-27 10:57 |  |  | 100 | 100 | [15 empty] | 37.8477 | 0.084361 | 8.3 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2315 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017713
43 | Task(Task)-->P (Procurement) | Pulley for Dribble Conveyor |  | 1.3.2.1 | Pulley for Dribble Conveyor-->PURCHASE REQUISITION-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2019-09-27 09:00 | 2019-09-27 18:00 | 2020-02-05 09:00 | 2020-02-05 18:00 |  |  | 2020-02-05 16:16 | 2020-02-05 16:16 |  |  | 100 | 100 | [15 empty] | 1.0032 | 0.002236 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2316 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017714
44 | Task(Task)-->P (Procurement) | Idler for Dribble Conveyor |  | 1.3.2.1 | Idler for Dribble Conveyor-->PURCHASE REQUISITION-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-19 09:00 | 2019-12-19 18:00 | 2020-02-13 09:00 | 2020-02-13 18:00 |  |  | 2020-02-13 14:52 | 2020-02-13 14:52 |  |  | 100 | 100 | [15 empty] | 0.228 | 0.000508 | 0.05 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2317 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017715
45 | Task(Task)-->P (Procurement) | Plummer Block for Dribble Conveyor |  | 1.3.2.1 | Plummer Block for Dribble Conveyor-->PURCHASE REQUISITION-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-17 | 2020-05-17 23:59 | 2020-02-10 09:00 | 2020-02-10 18:00 |  |  | 2020-02-10 09:26 | 2020-02-10 09:26 |  |  | 100 | 100 | [15 empty] | 0.091199 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2318 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017716
46 | Task(Task)-->P (Procurement) | Bearing for Dribble Conveyor |  | 1.3.2.1 | Bearing for Dribble Conveyor-->PURCHASE REQUISITION-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-17 | 2020-05-17 23:59 | 2020-02-10 09:00 | 2020-02-10 18:00 |  |  | 2020-02-10 09:36 | 2020-02-10 09:36 |  |  | 100 | 100 | [15 empty] | 0.1368 | 0.000305 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2319 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017717
47 | Task(Task)-->P (Procurement) | Belting for Dribble Conveyor |  | 1.3.2.1 | Belting for Dribble Conveyor-->PURCHASE REQUISITION-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-07 09:00 | 2019-11-07 18:00 | 2020-01-20 09:00 | 2020-01-20 18:00 |  |  | 2020-01-20 15:54 | 2020-01-20 15:54 |  |  | 100 | 100 | [15 empty] | 0.2736 | 0.00061 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2320 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017718
48 | Task(Task)-->P (Procurement) | Scrapper for Dribble Conveyor |  | 1.3.2.1 | Scrapper for Dribble Conveyor-->PURCHASE REQUISITION-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-17 | 2019-11-17 23:59 | 2020-03-11 09:00 | 2020-03-11 18:00 |  |  | 2020-03-11 10:57 | 2020-03-11 10:57 |  |  | 100 | 100 | [15 empty] | 0.1824 | 0.000407 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2321 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017719
49 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.3.2.1 | Technological Structure-->PURCHASE REQUISITION-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-10 09:00 | 2020-03-10 18:00 | 2020-03-11 09:00 | 2020-03-11 18:00 |  |  | 2020-03-11 12:41 | 2020-03-11 12:41 |  |  | 100 | 100 | [15 empty] | 0.86639 | 0.001931 | 0.19 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2322 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017720
50 | Task(Task)-->P (Procurement) | Chute & Skirt |  | 1.3.2.1 | Chute & Skirt-->PURCHASE REQUISITION-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-10 09:00 | 2020-03-10 18:00 | 2020-03-11 09:00 | 2020-03-11 18:00 |  |  | 2020-03-11 10:57 | 2020-03-11 10:57 |  |  | 100 | 100 | [15 empty] | 3.9672 | 0.008843 | 0.87 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2323 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017721
51 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.3.2.1 | Takeup Component-->PURCHASE REQUISITION-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-19 09:00 | 2020-05-19 18:00 | 2020-04-16 09:00 | 2020-04-16 18:00 |  |  | 2020-04-16 10:57 | 2020-04-16 10:57 |  |  | 100 | 100 | [15 empty] | 0.0456 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2324 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017722
52 | Task(Task)-->P (Procurement) | Gear Box for Dribble Conveyor |  | 1.3.2.1 | Gear Box for Dribble Conveyor-->PURCHASE REQUISITION-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-13 09:00 | 2019-11-13 18:00 | 2020-01-20 09:00 | 2020-01-20 18:00 |  |  | 2020-01-20 11:17 | 2020-01-20 11:17 |  |  | 100 | 100 | [15 empty] | 0.91199 | 0.002033 | 0.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2325 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017723
53 | Task(Task)-->P (Procurement) | Geared Coupling for Dribble Conveyor |  | 1.3.2.1 | Geared Coupling for Dribble Conveyor-->PURCHASE REQUISITION-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-21 09:00 | 2019-11-21 18:00 | 2020-01-22 09:00 | 2020-01-22 18:00 |  |  | 2020-01-22 10:41 | 2020-01-22 10:41 |  |  | 100 | 100 | [15 empty] | 0.228 | 0.000508 | 0.05 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2326 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017724
54 | Task(Task)-->P (Procurement) | Building Structure |  | 1.3.2.1 | Building Structure-->PURCHASE REQUISITION-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-21 09:00 | 2020-02-21 18:00 | 2020-05-29 09:00 | 2020-05-29 18:00 |  |  | 2020-05-31 18:44 | 2020-05-31 18:44 |  |  | 100 | 100 | [15 empty] | 31.2358 | 0.069623 | 6.85 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2327 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017725
55 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR CONVEYING SYSTEM |  | 1.3.2.1 | LT AC MOTORS FOR CONVEYING SYSTEM-->PURCHASE REQUISITION-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-16 09:00 | 2019-12-16 18:00 | 2020-01-13 09:00 | 2020-01-13 18:00 |  |  | 2020-01-13 10:57 | 2020-01-13 10:57 |  |  | 100 | 100 | [15 empty] | 0.72959 | 0.001626 | 0.16 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2328 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017726
56 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.3.2.1 | LIGHT & LIGHT FIXTURES-->PURCHASE REQUISITION-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-10 09:00 | 2020-03-10 18:00 | 2020-03-16 09:00 | 2020-03-16 18:00 |  |  | 2020-03-16 10:57 | 2020-03-16 10:57 |  |  | 100 | 100 | [15 empty] | 1.2312 | 0.002744 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2329 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017727
57 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.3.2.1 | LIGHTING POLES-->PURCHASE REQUISITION-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-27 09:00 | 2020-03-27 18:00 | 2020-04-30 09:00 | 2020-04-30 18:00 |  |  | 2020-04-30 10:57 | 2020-04-30 10:57 |  |  | 100 | 100 | [15 empty] | 0.5472 | 0.00122 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2330 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017728
58 | Task(Task)-->P (Procurement) | LPBS |  | 1.3.2.1 | LPBS-->PURCHASE REQUISITION-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-20 09:00 | 2020-03-20 18:00 | 2020-04-14 09:00 | 2020-04-14 18:00 |  |  | 2020-04-14 16:52 | 2020-04-14 16:52 |  |  | 100 | 100 | [15 empty] | 0.091199 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2331 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017729
59 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.3.2.1 | CONVEYOR BELT PROTECTION SWITCHES-->PURCHASE REQUISITION-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-08 09:00 | 2020-01-08 18:00 | 2020-01-08 09:00 | 2020-01-08 18:00 |  |  | 2020-01-08 10:57 | 2020-01-08 10:57 |  |  | 100 | 100 | [15 empty] | 0.0456 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2334 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017730
60 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.3.2.1 | ZERO SPEED SWITCH-->PURCHASE REQUISITION-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-30 09:00 | 2019-12-30 18:00 | 2019-12-30 09:00 | 2019-12-30 18:00 |  |  | 2019-12-30 10:57 | 2019-12-30 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2335 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017731
61 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.3.2.1 | CHUTE BLOCK SWITCH-->PURCHASE REQUISITION-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-03 09:00 | 2020-01-03 18:00 | 2020-01-03 09:00 | 2020-01-03 18:00 |  |  | 2020-01-03 10:57 | 2020-01-03 10:57 |  |  | 100 | 100 | [15 empty] | 0.0456 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2336 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017732
62 | Task(Task)-->P (Procurement) | CONTROL JUNCTION BOX |  | 1.3.2.1 | CONTROL JUNCTION BOX-->PURCHASE REQUISITION-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-05 09:00 | 2020-03-05 18:00 | 2020-04-18 09:00 | 2020-04-18 18:00 |  |  | 2020-04-18 10:57 | 2020-04-18 10:57 |  |  | 100 | 100 | [15 empty] | 0.091199 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2337 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017733
63 | Task(Task)-->P (Procurement) | TECHNICAL CLEARANCE | 1.3.2.2 | 1.3.2 | TECHNICAL CLEARANCE-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2019-09-28 09:00 | 2020-06-18 18:00 | 2019-09-27 09:00 | 2020-06-12 18:00 |  |  | 2019-10-31 10:57 | 2020-06-12 16:53 |  |  | 100 | 100 | [15 empty] | 4.9998 | 0.2231 | 21.94 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2338 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017734
64 | Task(Task)-->P (Procurement) | Apron Feeder |  | 1.3.2.2 | Apron Feeder-->TECHNICAL CLEARANCE-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2019-09-28 09:00 | 2019-10-11 18:00 | 2019-09-27 09:00 | 2019-10-31 18:00 |  |  | 2019-10-31 10:57 | 2019-10-31 10:57 |  |  | 100 | 100 | [15 empty] | 19.0888 | 0.042587 | 4.19 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2339 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017735
65 | Task(Task)-->P (Procurement) | Gear Box for Apron Feeder |  | 1.3.2.2 | Gear Box for Apron Feeder-->TECHNICAL CLEARANCE-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-14 09:00 | 2020-02-26 18:00 | 2020-01-20 09:00 | 2020-03-20 18:00 |  |  | 2020-01-22 11:19 | 2020-03-20 11:19 |  |  | 100 | 100 | [15 empty] | 0.91116 | 0.002033 | 0.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2340 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017736
66 | Task(Task)-->P (Procurement) | Geared Coupling for Apron Feeder |  | 1.3.2.2 | Geared Coupling for Apron Feeder-->TECHNICAL CLEARANCE-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-22 09:00 | 2020-03-19 18:00 | 2020-04-04 09:00 | 2020-04-09 18:00 |  |  | 2020-04-09 10:57 | 2020-04-09 10:57 |  |  | 100 | 100 | [15 empty] | 0.18223 | 0.000407 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2341 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017737
67 | Task(Task)-->P (Procurement) | Primary Sizer |  | 1.3.2.2 | Primary Sizer-->TECHNICAL CLEARANCE-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2019-09-28 09:00 | 2019-10-16 18:00 | 2019-09-27 09:00 | 2019-11-07 18:00 |  |  | 2019-11-07 10:57 | 2019-11-07 10:57 |  |  | 100 | 100 | [15 empty] | 37.8132 | 0.084361 | 8.3 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2342 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017738
68 | Task(Task)-->P (Procurement) | Pulley for Dribble Conveyor |  | 1.3.2.2 | Pulley for Dribble Conveyor-->TECHNICAL CLEARANCE-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2019-09-28 09:00 | 2020-01-04 18:00 | 2020-02-05 09:00 | 2020-02-10 18:00 |  |  | 2020-02-06 16:19 | 2020-02-10 16:19 |  |  | 100 | 100 | [15 empty] | 1.0023 | 0.002236 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2343 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017739
69 | Task(Task)-->P (Procurement) | Idler for Dribble Conveyor |  | 1.3.2.2 | Idler for Dribble Conveyor-->TECHNICAL CLEARANCE-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-20 09:00 | 2020-02-01 18:00 | 2020-02-13 09:00 | 2020-03-26 18:00 |  |  | 2020-02-14 14:56 | 2020-03-26 14:56 |  |  | 100 | 100 | [15 empty] | 0.22779 | 0.000508 | 0.05 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2344 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017740
70 | Task(Task)-->P (Procurement) | Plummer Block for Dribble Conveyor |  | 1.3.2.2 | Plummer Block for Dribble Conveyor-->TECHNICAL CLEARANCE-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-18 09:00 | 2020-06-01 18:00 | 2020-02-10 09:00 | 2020-02-10 18:00 |  |  | 2020-02-10 09:28 | 2020-02-10 09:28 |  |  | 100 | 100 | [15 empty] | 0.091116 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2345 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017741
71 | Task(Task)-->P (Procurement) | Bearing for Dribble Conveyor |  | 1.3.2.2 | Bearing for Dribble Conveyor-->TECHNICAL CLEARANCE-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-18 09:00 | 2020-06-16 18:00 | 2020-02-10 09:00 | 2020-02-10 18:00 |  |  | 2020-02-10 09:37 | 2020-02-10 09:37 |  |  | 100 | 100 | [15 empty] | 0.13667 | 0.000305 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2346 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017742
72 | Task(Task)-->P (Procurement) | Belting for Dribble Conveyor |  | 1.3.2.2 | Belting for Dribble Conveyor-->TECHNICAL CLEARANCE-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-08 09:00 | 2020-01-06 18:00 | 2020-01-20 09:00 | 2020-05-16 18:00 |  |  | 2020-05-16 10:57 | 2020-05-16 10:57 |  |  | 100 | 100 | [15 empty] | 0.27335 | 0.00061 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2347 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017743
73 | Task(Task)-->P (Procurement) | Scrapper for Dribble Conveyor |  | 1.3.2.2 | Scrapper for Dribble Conveyor-->TECHNICAL CLEARANCE-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-18 09:00 | 2020-03-16 18:00 | 2020-03-11 09:00 | 2020-03-26 18:00 |  |  | 2020-03-26 10:57 | 2020-03-26 10:57 |  |  | 100 | 100 | [15 empty] | 0.18223 | 0.000407 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2348 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017744
74 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.3.2.2 | Technological Structure-->TECHNICAL CLEARANCE-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-11 09:00 | 2020-03-20 18:00 | 2020-03-11 09:00 | 2020-03-17 18:00 |  |  | 2020-03-12 12:43 | 2020-03-17 12:43 |  |  | 100 | 100 | [15 empty] | 0.8656 | 0.001931 | 0.19 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2349 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017745
75 | Task(Task)-->P (Procurement) | Chute & Skirt |  | 1.3.2.2 | Chute & Skirt-->TECHNICAL CLEARANCE-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-11 09:00 | 2020-03-20 18:00 | 2020-03-11 09:00 | 2020-03-17 18:00 |  |  | 2020-03-17 10:57 | 2020-03-17 10:57 |  |  | 100 | 100 | [15 empty] | 3.9636 | 0.008843 | 0.87 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2350 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017746
76 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.3.2.2 | Takeup Component-->TECHNICAL CLEARANCE-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-20 09:00 | 2020-06-18 18:00 | 2020-04-16 09:00 | 2020-04-16 18:00 |  |  | 2020-04-16 10:57 | 2020-04-16 10:57 |  |  | 100 | 100 | [15 empty] | 0.045558 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2351 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017747
77 | Task(Task)-->P (Procurement) | Gear Box for Dribble Conveyor |  | 1.3.2.2 | Gear Box for Dribble Conveyor-->TECHNICAL CLEARANCE-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-14 09:00 | 2020-02-26 18:00 | 2020-01-20 09:00 | 2020-03-20 18:00 |  |  | 2020-01-22 11:19 | 2020-03-20 11:19 |  |  | 100 | 100 | [15 empty] | 0.91116 | 0.002033 | 0.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2352 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017748
78 | Task(Task)-->P (Procurement) | Geared Coupling for Dribble Conveyor |  | 1.3.2.2 | Geared Coupling for Dribble Conveyor-->TECHNICAL CLEARANCE-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-22 09:00 | 2020-03-19 18:00 | 2020-01-22 09:00 | 2020-04-13 18:00 |  |  | 2020-04-13 10:46 | 2020-04-13 10:46 |  |  | 100 | 100 | [15 empty] | 0.22779 | 0.000508 | 0.05 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2353 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017749
79 | Task(Task)-->P (Procurement) | Building Structure |  | 1.3.2.2 | Building Structure-->TECHNICAL CLEARANCE-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-22 09:00 | 2020-02-28 18:00 | 2020-05-29 09:00 | 2020-05-29 18:00 |  |  | 2020-05-29 17:31 | 2020-05-29 17:31 |  |  | 100 | 100 | [15 empty] | 31.2073 | 0.069623 | 6.85 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2354 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017750
80 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR CONVEYING SYSTEM |  | 1.3.2.2 | LT AC MOTORS FOR CONVEYING SYSTEM-->TECHNICAL CLEARANCE-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-17 09:00 | 2019-12-31 18:00 | 2020-01-13 09:00 | 2020-04-11 18:00 |  |  | 2020-04-11 10:57 | 2020-04-11 10:57 |  |  | 100 | 100 | [15 empty] | 0.72893 | 0.001626 | 0.16 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2355 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017751
81 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.3.2.2 | LIGHT & LIGHT FIXTURES-->TECHNICAL CLEARANCE-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-11 09:00 | 2020-03-25 18:00 | 2020-03-16 09:00 | 2020-06-02 18:00 |  |  | 2020-06-02 10:57 | 2020-06-02 10:57 |  |  | 100 | 100 | [15 empty] | 1.2301 | 0.002744 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2356 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017752
82 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.3.2.2 | LIGHTING POLES-->TECHNICAL CLEARANCE-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-28 09:00 | 2020-05-11 18:00 | 2020-04-30 09:00 | 2020-06-03 18:00 |  |  | 2020-06-03 10:57 | 2020-06-03 10:57 |  |  | 100 | 100 | [15 empty] | 0.5467 | 0.00122 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2357 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017753
83 | Task(Task)-->P (Procurement) | LPBS |  | 1.3.2.2 | LPBS-->TECHNICAL CLEARANCE-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-21 09:00 | 2020-04-04 18:00 | 2020-04-14 09:00 | 2020-06-12 18:00 |  |  | 2020-04-14 16:53 | 2020-06-12 16:53 |  |  | 100 | 100 | [15 empty] | 0.091116 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2358 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017754
84 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.3.2.2 | CONVEYOR BELT PROTECTION SWITCHES-->TECHNICAL CLEARANCE-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-09 09:00 | 2020-01-22 18:00 | 2020-01-08 09:00 | 2020-03-10 18:00 |  |  | 2020-03-10 10:57 | 2020-03-10 10:57 |  |  | 100 | 100 | [15 empty] | 0.13667 | 0.000305 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2361 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017755
85 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.3.2.2 | ZERO SPEED SWITCH-->TECHNICAL CLEARANCE-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-31 09:00 | 2020-01-14 18:00 | 2019-12-30 09:00 | 2020-03-07 18:00 |  |  | 2020-03-07 10:57 | 2020-03-07 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2362 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017756
86 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.3.2.2 | CHUTE BLOCK SWITCH-->TECHNICAL CLEARANCE-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-04 09:00 | 2020-01-18 18:00 | 2020-01-03 09:00 | 2020-01-16 18:00 |  |  | 2020-01-16 10:57 | 2020-01-16 10:57 |  |  | 100 | 100 | [15 empty] | 0.045558 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2363 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017757
87 | Task(Task)-->P (Procurement) | CONTROL JUNCTION BOX |  | 1.3.2.2 | CONTROL JUNCTION BOX-->TECHNICAL CLEARANCE-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-06 09:00 | 2020-03-13 18:00 | 2020-04-18 09:00 | 2020-06-02 18:00 |  |  | 2020-06-02 10:57 | 2020-06-02 10:57 |  |  | 100 | 100 | [15 empty] | 0.091116 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2364 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017758
88 | Task(Task)-->P (Procurement) | ORDERING | 1.3.2.3 | 1.3.2 | ORDERING-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-10-12 09:00 | 2020-07-18 18:00 | 2019-10-31 09:00 | 2020-09-04 18:00 |  |  | 2020-01-05 08:00 |  |  |  | 100 | 99.9545 | [15 empty] | 9.9995 | 0.4462 | 43.88 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2365 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017759
89 | Task(Task)-->P (Procurement) | Apron Feeder |  | 1.3.2.3 | Apron Feeder-->ORDERING-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2019-10-12 09:00 | 2019-11-10 23:59 | 2019-10-31 09:00 | 2020-01-29 18:00 |  |  | 2020-01-29 10:57 | 2020-01-29 10:57 |  |  | 100 | 100 | [15 empty] | 19.0975 | 0.085213 | 8.38 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2366 | 0 | 4 | Low | ADMINISTRATOR | [6 empty] | 0 | 0 | [246 empty] | 1017760
90 | Task(Task)-->P (Procurement) | Gear Box for Apron Feeder |  | 1.3.2.3 | Gear Box for Apron Feeder-->ORDERING-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-27 09:00 | 2020-03-27 18:00 | 2020-03-20 09:00 | 2020-04-30 18:00 |  |  | 2020-03-21 11:21 | 2020-04-30 11:21 |  |  | 100 | 100 | [15 empty] | 0.91158 | 0.004067 | 0.4 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2367 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017761
91 | Task(Task)-->P (Procurement) | Geared Coupling for Apron Feeder |  | 1.3.2.3 | Geared Coupling for Apron Feeder-->ORDERING-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-20 09:00 | 2020-04-18 18:00 | 2020-04-09 09:00 | 2020-04-30 18:00 |  |  | 2020-04-30 10:57 | 2020-04-30 10:57 |  |  | 100 | 100 | [15 empty] | 0.15953 | 0.000712 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2368 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017762
92 | Task(Task)-->P (Procurement) | Primary Sizer |  | 1.3.2.3 | Primary Sizer-->ORDERING-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2019-10-17 09:00 | 2019-11-20 18:00 | 2019-11-07 09:00 | 2020-02-25 18:00 |  |  | 2020-02-25 10:57 | 2020-02-25 10:57 |  |  | 100 | 100 | [15 empty] | 37.8532 | 0.1689 | 16.61 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2369 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017763
93 | Task(Task)-->P (Procurement) | Pulley for Dribble Conveyor |  | 1.3.2.3 | Pulley for Dribble Conveyor-->ORDERING-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-05 | 2020-02-03 18:00 | 2020-02-10 09:00 | 2020-03-21 18:00 |  |  | 2020-01-05 08:00 | 2020-03-21 16:05 |  |  | 100 | 100 | [15 empty] | 1.0255 | 0.004576 | 0.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2370 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017764
94 | Task(Task)-->P (Procurement) | Idler for Dribble Conveyor |  | 1.3.2.3 | Idler for Dribble Conveyor-->ORDERING-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-02 | 2020-03-02 18:00 | 2020-03-26 09:00 | 2020-04-30 18:00 |  |  | 2020-03-27 14:58 | 2020-04-30 14:57 |  |  | 100 | 100 | [15 empty] | 0.2051 | 0.000915 | 0.09 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2371 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017765
95 | Task(Task)-->P (Procurement) | Plummer Block for Dribble Conveyor |  | 1.3.2.3 | Plummer Block for Dribble Conveyor-->ORDERING-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-06-02 09:00 | 2020-07-01 18:00 | 2020-02-10 09:00 | 2020-03-24 18:00 |  |  | 2020-02-11 09:32 | 2020-03-24 09:32 |  |  | 100 | 100 | [15 empty] | 0.068368 | 0.000305 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2372 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017766
96 | Task(Task)-->P (Procurement) | Bearing for Dribble Conveyor |  | 1.3.2.3 | Bearing for Dribble Conveyor-->ORDERING-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-06-17 09:00 | 2020-07-16 18:00 | 2020-02-10 09:00 | 2020-03-24 18:00 |  |  | 2020-02-11 09:40 | 2020-03-24 09:40 |  |  | 100 | 100 | [15 empty] | 0.13674 | 0.00061 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2373 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017767
97 | Task(Task)-->P (Procurement) | Belting for Dribble Conveyor |  | 1.3.2.3 | Belting for Dribble Conveyor-->ORDERING-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-07 09:00 | 2020-02-20 18:00 | 2020-05-16 09:00 | 2020-09-04 18:00 |  |  | 2020-05-16 16:24 | 2020-09-04 16:24 |  |  | 100 | 100 | [15 empty] | 0.27347 | 0.00122 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2374 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017768
98 | Task(Task)-->P (Procurement) | Scrapper for Dribble Conveyor |  | 1.3.2.3 | Scrapper for Dribble Conveyor-->ORDERING-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-17 09:00 | 2020-04-15 18:00 | 2020-03-26 09:00 | 2020-05-30 18:00 |  |  | 2020-05-30 10:57 | 2020-05-30 10:57 |  |  | 100 | 100 | [15 empty] | 0.15953 | 0.000712 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2375 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017769
99 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.3.2.3 | Technological Structure-->ORDERING-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-21 09:00 | 2020-04-19 23:59 | 2020-03-17 09:00 | 2020-07-06 18:00 |  |  | 2020-03-18 12:44 | 2020-07-06 12:44 |  |  | 100 | 100 | [15 empty] | 0.866 | 0.003864 | 0.38 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2376 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017770
100 | Task(Task)-->P (Procurement) | Chute & Skirt |  | 1.3.2.3 | Chute & Skirt-->ORDERING-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-21 09:00 | 2020-04-19 23:59 | 2020-03-17 09:00 | 2020-07-06 18:00 |  |  | 2020-03-18 12:49 | 2020-07-06 12:49 |  |  | 100 | 100 | [15 empty] | 3.9426 | 0.017592 | 1.73 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2377 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017771
101 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.3.2.3 | Takeup Component-->ORDERING-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-19 09:00 | 2020-07-18 18:00 | 2020-04-16 09:00 | 2020-08-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.045579 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2378 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017772
102 | Task(Task)-->P (Procurement) | Gear Box for Dribble Conveyor |  | 1.3.2.3 | Gear Box for Dribble Conveyor-->ORDERING-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-27 09:00 | 2020-03-27 18:00 | 2020-03-20 09:00 | 2020-04-30 18:00 |  |  | 2020-03-21 11:21 | 2020-04-30 11:21 |  |  | 100 | 100 | [15 empty] | 0.91158 | 0.004067 | 0.4 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2379 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017773
103 | Task(Task)-->P (Procurement) | Geared Coupling for Dribble Conveyor |  | 1.3.2.3 | Geared Coupling for Dribble Conveyor-->ORDERING-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-20 09:00 | 2020-04-18 18:00 | 2020-04-13 09:00 | 2020-04-30 18:00 |  |  | 2020-04-14 11:11 | 2020-04-30 11:11 |  |  | 100 | 100 | [15 empty] | 0.22789 | 0.001017 | 0.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2380 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017774
104 | Task(Task)-->P (Procurement) | Building Structure |  | 1.3.2.3 | Building Structure-->ORDERING-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-29 09:00 | 2020-03-29 23:59 | 2020-05-29 09:00 | 2020-05-31 23:59 |  |  | 2020-05-31 18:49 | 2020-05-31 18:49 |  |  | 100 | 100 | [15 empty] | 31.2443 | 0.13941 | 13.71 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2381 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017775
105 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR CONVEYING SYSTEM |  | 1.3.2.3 | LT AC MOTORS FOR CONVEYING SYSTEM-->ORDERING-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-01 09:00 | 2020-01-16 18:00 | 2020-04-11 09:00 | 2020-07-20 18:00 |  |  | 2020-04-12 15:47 | 2020-06-20 15:47 |  |  | 100 | 100 | [15 empty] | 0.75205 | 0.003356 | 0.33 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2382 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017776
106 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.3.2.3 | LIGHT & LIGHT FIXTURES-->ORDERING-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-26 09:00 | 2020-04-10 18:00 | 2020-06-02 09:00 | 2020-07-31 18:00 |  |  | 2020-06-03 15:51 | 2020-06-29 15:51 |  |  | 100 | 100 | [15 empty] | 1.2078 | 0.005389 | 0.53 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2383 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017777
107 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.3.2.3 | LIGHTING POLES-->ORDERING-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-12 09:00 | 2020-06-25 18:00 | 2020-06-03 09:00 | 2020-06-24 18:00 |  |  | 2020-06-15 10:57 | 2020-06-15 10:57 |  |  | 100 | 100 | [15 empty] | 0.54695 | 0.00244 | 0.24 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2384 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017778
108 | Task(Task)-->P (Procurement) | LPBS |  | 1.3.2.3 | LPBS-->ORDERING-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-05 | 2020-04-20 18:00 | 2020-06-12 09:00 | 2020-08-19 18:00 |  |  | 2020-06-12 16:55 | 2020-08-19 16:55 |  |  | 100 | 100 | [15 empty] | 0.091158 | 0.000407 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2385 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017779
109 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.3.2.3 | CONVEYOR BELT PROTECTION SWITCHES-->ORDERING-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-23 09:00 | 2020-02-05 18:00 | 2020-03-10 09:00 | 2020-08-17 18:00 |  |  | 2020-03-10 16:54 | 2020-08-17 16:54 |  |  | 100 | 100 | [15 empty] | 0.13674 | 0.00061 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2388 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017780
110 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.3.2.3 | ZERO SPEED SWITCH-->ORDERING-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-15 09:00 | 2020-02-01 18:00 | 2020-03-07 09:00 | 2020-08-01 18:00 |  |  | 2020-03-07 16:55 | 2020-08-01 16:55 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2389 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017781
111 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.3.2.3 | CHUTE BLOCK SWITCH-->ORDERING-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-19 | 2020-01-31 18:00 | 2020-01-16 09:00 | 2020-02-01 18:00 |  |  | 2020-02-01 10:57 | 2020-02-01 10:57 |  |  | 100 | 100 | [15 empty] | 0.022789 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2390 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017782
112 | Task(Task)-->P (Procurement) | CONTROL JUNCTION BOX |  | 1.3.2.3 | CONTROL JUNCTION BOX-->ORDERING-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-14 09:00 | 2020-03-21 18:00 | 2020-06-02 09:00 | 2020-08-19 18:00 |  |  | 2020-06-02 16:56 | 2020-08-19 16:56 |  |  | 100 | 100 | [15 empty] | 0.11395 | 0.000508 | 0.05 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2391 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017783
113 | Task(Task)-->P (Procurement) | ITP APPROVAL | 1.3.2.4 | 1.3.2 | ITP APPROVAL-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-11-11 09:00 | 2020-08-27 18:00 | 2020-01-29 09:00 | 2020-11-30 18:00 |  |  | 2020-01-29 01:52 |  |  |  | 100 | 24.7382 | [15 empty] | 4.9998 | 0.2231 | 21.94 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2392 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017784
114 | Task(Task)-->P (Procurement) | Apron Feeder |  | 1.3.2.4 | Apron Feeder-->ITP APPROVAL-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-11 09:00 | 2019-12-20 18:00 | 2020-01-29 09:00 | 2020-06-11 18:00 |  |  | 2020-01-29 01:52 | 2020-06-11 01:52 |  |  | 100 | 100 | [15 empty] | 19.0888 | 0.042587 | 4.19 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2393 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017785
115 | Task(Task)-->P (Procurement) | Gear Box for Apron Feeder |  | 1.3.2.4 | Gear Box for Apron Feeder-->ITP APPROVAL-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-28 09:00 | 2020-05-06 18:00 | 2020-04-30 09:00 | 2020-06-22 18:00 |  |  | 2020-04-30 16:57 | 2020-06-22 16:57 |  |  | 100 | 100 | [15 empty] | 0.91116 | 0.002033 | 0.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2394 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017786
116 | Task(Task)-->P (Procurement) | Geared Coupling for Apron Feeder |  | 1.3.2.4 | Geared Coupling for Apron Feeder-->ITP APPROVAL-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-19 | 2020-05-28 18:00 | 2020-04-30 09:00 | 2020-08-28 18:00 |  |  | 2020-04-30 01:54 | 2020-06-18 17:30 |  |  | 100 | 100 | [15 empty] | 0.18223 | 0.000407 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2395 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017787
117 | Task(Task)-->P (Procurement) | Primary Sizer |  | 1.3.2.4 | Primary Sizer-->ITP APPROVAL-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-11-21 09:00 | 2019-12-30 18:00 | 2020-02-25 09:00 | 2020-11-15 23:59 | [6 empty] | 100 | 0 | [15 empty] | 37.8132 | 0.084361 | 8.3 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2396 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017788
118 | Task(Task)-->P (Procurement) | Pulley for Dribble Conveyor |  | 1.3.2.4 | Pulley for Dribble Conveyor-->ITP APPROVAL-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-04 09:00 | 2020-03-14 18:00 | 2020-03-21 09:00 | 2020-05-11 18:00 | [6 empty] | 100 | 0 | [15 empty] | 1.0023 | 0.002236 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2397 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017789
119 | Task(Task)-->P (Procurement) | Idler for Dribble Conveyor |  | 1.3.2.4 | Idler for Dribble Conveyor-->ITP APPROVAL-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-03 09:00 | 2020-04-11 18:00 | 2020-04-30 09:00 | 2020-05-19 18:00 |  |  | 2020-04-13 16:20 | 2020-05-19 16:20 |  |  | 100 | 100 | [15 empty] | 0.22779 | 0.000508 | 0.05 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2398 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017790
120 | Task(Task)-->P (Procurement) | Plummer Block for Dribble Conveyor |  | 1.3.2.4 | Plummer Block for Dribble Conveyor-->ITP APPROVAL-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-02 09:00 | 2020-08-10 18:00 | 2020-03-24 09:00 | 2020-08-13 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.091116 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2399 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017791
121 | Task(Task)-->P (Procurement) | Bearing for Dribble Conveyor |  | 1.3.2.4 | Bearing for Dribble Conveyor-->ITP APPROVAL-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-17 09:00 | 2020-08-25 18:00 | 2020-03-24 09:00 | 2020-03-29 23:59 | [6 empty] | 100 | 0 | [15 empty] | 0.13667 | 0.000305 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2400 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017792
122 | Task(Task)-->P (Procurement) | Belting for Dribble Conveyor |  | 1.3.2.4 | Belting for Dribble Conveyor-->ITP APPROVAL-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-21 09:00 | 2020-03-31 18:00 | 2020-09-04 09:00 | 2020-09-30 18:00 |  |  | 2020-09-04 16:30 | 2020-09-30 16:30 |  |  | 100 | 100 | [15 empty] | 0.27335 | 0.00061 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2401 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017793
123 | Task(Task)-->P (Procurement) | Scrapper for Dribble Conveyor |  | 1.3.2.4 | Scrapper for Dribble Conveyor-->ITP APPROVAL-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-16 09:00 | 2020-05-25 18:00 | 2020-05-30 09:00 | 2020-06-25 18:00 |  |  | 2020-05-13 16:26 | 2020-06-25 16:26 |  |  | 100 | 100 | [15 empty] | 0.18223 | 0.000407 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2402 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017794
124 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.3.2.4 | Technological Structure-->ITP APPROVAL-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-20 09:00 | 2020-05-29 18:00 | 2020-07-06 09:00 | 2020-07-16 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.8656 | 0.001931 | 0.19 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2403 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017795
125 | Task(Task)-->P (Procurement) | Chute & Skirt |  | 1.3.2.4 | Chute & Skirt-->ITP APPROVAL-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-20 09:00 | 2020-05-29 18:00 | 2020-07-06 09:00 | 2020-07-16 18:00 | [6 empty] | 100 | 0 | [15 empty] | 3.9636 | 0.008843 | 0.87 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2404 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017796
126 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.3.2.4 | Takeup Component-->ITP APPROVAL-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-19 | 2020-08-27 18:00 | 2020-06-25 09:00 | 2020-06-25 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.045558 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2405 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017797
127 | Task(Task)-->P (Procurement) | Gear Box for Dribble Conveyor |  | 1.3.2.4 | Gear Box for Dribble Conveyor-->ITP APPROVAL-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-28 09:00 | 2020-05-06 18:00 | 2020-04-30 09:00 | 2020-06-22 18:00 |  |  | 2020-04-30 16:57 | 2020-06-22 16:57 |  |  | 100 | 100 | [15 empty] | 0.91116 | 0.002033 | 0.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2406 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017798
128 | Task(Task)-->P (Procurement) | Geared Coupling for Dribble Conveyor |  | 1.3.2.4 | Geared Coupling for Dribble Conveyor-->ITP APPROVAL-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-19 | 2020-05-28 18:00 | 2020-04-30 09:00 | 2020-06-18 18:00 |  |  | 2020-04-30 01:54 | 2020-06-18 17:31 |  |  | 100 | 100 | [15 empty] | 0.22779 | 0.000508 | 0.05 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2407 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017799
129 | Task(Task)-->P (Procurement) | Building Structure |  | 1.3.2.4 | Building Structure-->ITP APPROVAL-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-30 09:00 | 2020-04-05 23:59 | 2020-05-31 | 2020-08-04 18:00 |  |  | 2020-06-25 19:04 |  |  |  | 100 | 0 | [15 empty] | 31.2073 | 0.069623 | 6.85 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2408 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017800
130 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR CONVEYING SYSTEM |  | 1.3.2.4 | LT AC MOTORS FOR CONVEYING SYSTEM-->ITP APPROVAL-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-17 09:00 | 2020-02-25 18:00 | 2020-09-08 09:00 | 2020-10-14 18:00 |  |  | 2020-09-08 16:58 | 2020-10-14 15:12 |  |  | 100 | 100 | [15 empty] | 0.72893 | 0.001626 | 0.16 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2409 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017801
131 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.3.2.4 | LIGHT & LIGHT FIXTURES-->ITP APPROVAL-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-11 09:00 | 2020-05-20 18:00 | 2020-07-28 09:00 | 2020-09-08 18:00 |  |  | 2020-07-08 17:23 | 2020-09-08 17:23 |  |  | 100 | 100 | [15 empty] | 1.2301 | 0.002744 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2410 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017802
132 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.3.2.4 | LIGHTING POLES-->ITP APPROVAL-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-06-26 09:00 | 2020-08-04 18:00 | 2020-06-23 09:00 | 2020-09-08 18:00 |  |  | 2020-06-23 17:21 | 2020-09-08 17:05 |  |  | 100 | 100 | [15 empty] | 0.5467 | 0.00122 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2411 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017803
133 | Task(Task)-->P (Procurement) | LPBS |  | 1.3.2.4 | LPBS-->ITP APPROVAL-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-21 09:00 | 2020-05-30 18:00 | 2020-07-29 09:00 | 2020-08-21 18:00 |  |  | 2020-07-29 14:54 | 2020-08-22 12:53 |  |  | 100 | 100 | [15 empty] | 0.091116 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2412 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017804
134 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.3.2.4 | CONVEYOR BELT PROTECTION SWITCHES-->ITP APPROVAL-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-06 09:00 | 2020-03-16 18:00 | 2020-09-24 09:00 | 2020-11-30 18:00 |  |  | 2020-09-24 09:58 |  |  |  | 100 | 0 | [15 empty] | 0.13667 | 0.000305 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2415 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017805
135 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.3.2.4 | ZERO SPEED SWITCH-->ITP APPROVAL-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-02 | 2020-03-12 18:00 | 2020-08-02 | 2020-09-10 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2416 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017806
136 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.3.2.4 | CHUTE BLOCK SWITCH-->ITP APPROVAL-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-01 09:00 | 2020-03-11 18:00 | 2020-07-02 09:00 | 2020-08-04 18:00 |  |  | 2020-07-17 16:57 | 2020-08-04 16:57 |  |  | 100 | 100 | [15 empty] | 0.045558 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2417 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017807
137 | Task(Task)-->P (Procurement) | CONTROL JUNCTION BOX |  | 1.3.2.4 | CONTROL JUNCTION BOX-->ITP APPROVAL-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-22 | 2020-04-30 18:00 | 2020-07-29 09:00 | 2020-09-21 18:00 |  |  | 2020-07-29 14:51 | 2020-09-22 16:57 |  |  | 100 | 100 | [15 empty] | 0.091116 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2418 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017808
138 | Task(Task)-->P (Procurement) | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE | 1.3.2.5 | 1.3.2 | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-11-11 09:00 | 2020-09-16 18:00 | 2020-01-29 09:00 | 2020-11-16 18:00 |  |  | 2020-01-30 12:41 |  |  |  | 100 | 67.2489 | [15 empty] | 15.0016 | 0.6694 | 65.83 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2419 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017809
139 | Task(Task)-->P (Procurement) | Apron Feeder |  | 1.3.2.5 | Apron Feeder-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-11 09:00 | 2020-02-08 18:00 | 2020-01-29 09:00 | 2020-03-16 18:00 |  |  | 2020-01-30 12:41 | 2020-03-16 10:57 |  |  | 100 | 100 | [15 empty] | 19.0946 | 0.12782 | 12.57 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2420 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017810
140 | Task(Task)-->P (Procurement) | Gear Box for Apron Feeder |  | 1.3.2.5 | Gear Box for Apron Feeder-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-28 09:00 | 2020-05-26 18:00 | 2020-04-30 09:00 | 2020-07-01 18:00 |  |  | 2020-04-30 19:12 | 2020-07-01 19:12 |  |  | 100 | 100 | [15 empty] | 0.91144 | 0.006101 | 0.6 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2421 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017811
141 | Task(Task)-->P (Procurement) | Geared Coupling for Apron Feeder |  | 1.3.2.5 | Geared Coupling for Apron Feeder-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-19 | 2020-06-17 18:00 | 2020-04-30 09:00 | 2020-07-23 18:00 |  |  | 2020-04-30 01:56 | 2020-07-23 01:57 |  |  | 100 | 100 | [15 empty] | 0.1671 | 0.001119 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2422 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017812
142 | Task(Task)-->P (Procurement) | Primary Sizer |  | 1.3.2.5 | Primary Sizer-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-21 09:00 | 2020-02-18 18:00 | 2020-02-25 09:00 | 2020-06-22 18:00 |  |  | 2020-02-26 14:48 | 2020-06-22 14:48 |  |  | 100 | 100 | [15 empty] | 37.8399 | 0.2533 | 24.91 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2423 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017813
143 | Task(Task)-->P (Procurement) | Pulley for Dribble Conveyor |  | 1.3.2.5 | Pulley for Dribble Conveyor-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-04 09:00 | 2020-03-29 23:59 | 2020-03-21 09:00 | 2020-03-25 18:00 |  |  | 2020-03-22 18:03 | 2020-03-25 18:03 |  |  | 100 | 100 | [15 empty] | 1.0178 | 0.006813 | 0.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2424 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017814
144 | Task(Task)-->P (Procurement) | Idler for Dribble Conveyor |  | 1.3.2.5 | Idler for Dribble Conveyor-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-03 09:00 | 2020-05-01 18:00 | 2020-04-30 09:00 | 2020-06-25 18:00 |  |  | 2020-05-04 14:59 | 2020-06-25 15:00 |  |  | 100 | 100 | [15 empty] | 0.21267 | 0.001424 | 0.14 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2425 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017815
145 | Task(Task)-->P (Procurement) | Plummer Block for Dribble Conveyor |  | 1.3.2.5 | Plummer Block for Dribble Conveyor-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-07-02 09:00 | 2020-08-30 23:59 | 2020-03-24 09:00 | 2020-06-29 18:00 |  |  | 2020-05-14 10:06 | 2020-06-29 10:06 |  |  | 100 | 100 | [15 empty] | 0.075953 | 0.000508 | 0.05 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2426 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017816
146 | Task(Task)-->P (Procurement) | Bearing for Dribble Conveyor |  | 1.3.2.5 | Bearing for Dribble Conveyor-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-07-17 09:00 | 2020-07-17 18:00 | 2020-03-24 09:00 | 2020-03-24 18:00 |  |  | 2020-03-24 10:05 | 2020-03-24 10:05 |  |  | 100 | 100 | [15 empty] | 0.12153 | 0.000813 | 0.08 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2427 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017817
147 | Task(Task)-->P (Procurement) | Belting for Dribble Conveyor |  | 1.3.2.5 | Belting for Dribble Conveyor-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-21 09:00 | 2020-04-20 18:00 | 2020-09-04 09:00 | 2020-11-15 23:59 |  |  | 2020-09-04 16:36 |  |  |  | 100 | 50 | [15 empty] | 0.27343 | 0.00183 | 0.18 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2428 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017818
148 | Task(Task)-->P (Procurement) | Scrapper for Dribble Conveyor |  | 1.3.2.5 | Scrapper for Dribble Conveyor-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-16 09:00 | 2020-06-14 23:59 | 2020-05-30 09:00 | 2020-07-30 18:00 |  |  | 2020-05-30 16:33 | 2020-07-30 16:33 |  |  | 100 | 100 | [15 empty] | 0.1671 | 0.001119 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2429 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017819
149 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.3.2.5 | Technological Structure-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-20 09:00 | 2020-09-16 18:00 | 2020-07-06 09:00 | 2020-07-06 18:00 |  |  | 2020-07-06 12:45 | 2020-07-06 12:45 |  |  | 100 | 100 | [15 empty] | 0.86587 | 0.005796 | 0.57 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2430 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017820
150 | Task(Task)-->P (Procurement) | Chute & Skirt |  | 1.3.2.5 | Chute & Skirt-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-20 09:00 | 2020-09-16 18:00 | 2020-07-06 09:00 | 2020-07-06 18:00 |  |  | 2020-07-06 12:51 | 2020-07-06 12:51 |  |  | 100 | 100 | [15 empty] | 3.9496 | 0.026438 | 2.6 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2431 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017821
151 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.3.2.5 | Takeup Component-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-19 | 2020-08-27 18:00 | 2020-08-04 09:00 | 2020-08-04 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.045572 | 0.000305 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2432 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017822
152 | Task(Task)-->P (Procurement) | Gear Box for Dribble Conveyor |  | 1.3.2.5 | Gear Box for Dribble Conveyor-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-28 09:00 | 2020-05-26 18:00 | 2020-04-30 09:00 | 2020-07-01 18:00 |  |  | 2020-04-30 19:12 | 2020-07-01 19:12 |  |  | 100 | 100 | [15 empty] | 0.91144 | 0.006101 | 0.6 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2433 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017823
153 | Task(Task)-->P (Procurement) | Geared Coupling for Dribble Conveyor |  | 1.3.2.5 | Geared Coupling for Dribble Conveyor-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-19 | 2020-06-17 18:00 | 2020-04-30 09:00 | 2020-07-30 18:00 |  |  | 2020-04-30 10:09 | 2020-07-07 10:10 |  |  | 100 | 100 | [15 empty] | 0.22786 | 0.001525 | 0.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2434 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017824
154 | Task(Task)-->P (Procurement) | Building Structure |  | 1.3.2.5 | Building Structure-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-28 09:00 | 2020-04-03 18:00 | 2020-05-31 | 2020-07-11 18:00 | [6 empty] | 100 | 0 | [15 empty] | 31.232 | 0.20907 | 20.56 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2435 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017825
155 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR CONVEYING SYSTEM |  | 1.3.2.5 | LT AC MOTORS FOR CONVEYING SYSTEM-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-17 09:00 | 2020-03-01 23:59 | 2020-07-07 09:00 | 2020-09-29 18:00 |  |  | 2020-07-07 10:15 | 2020-09-21 12:52 |  |  | 100 | 100 | [15 empty] | 0.74434 | 0.004983 | 0.49 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2436 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017826
156 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.3.2.5 | LIGHT & LIGHT FIXTURES-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-11 09:00 | 2020-05-25 18:00 | 2020-07-10 09:00 | 2020-11-16 18:00 |  |  | 2020-07-14 10:44 |  |  |  | 100 | 0 | [15 empty] | 1.2153 | 0.008135 | 0.8 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2437 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017827
157 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.3.2.5 | LIGHTING POLES-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-06-26 09:00 | 2020-08-09 23:59 | 2020-05-30 09:00 | 2020-08-08 18:00 |  |  | 2020-06-18 | 2020-08-07 15:00 |  |  | 100 | 100 | [15 empty] | 0.54686 | 0.003661 | 0.36 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2438 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017828
158 | Task(Task)-->P (Procurement) | LPBS |  | 1.3.2.5 | LPBS-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-21 09:00 | 2020-06-04 18:00 | 2020-07-25 09:00 | 2020-08-22 18:00 |  |  | 2020-07-24 18:32 | 2020-08-22 12:56 |  |  | 100 | 100 | [15 empty] | 0.091144 | 0.00061 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2439 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017829
159 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.3.2.5 | CONVEYOR BELT PROTECTION SWITCHES-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-06 09:00 | 2020-03-21 18:00 | 2020-08-11 09:00 | 2020-09-19 18:00 |  |  | 2020-08-11 13:11 | 2020-09-19 12:57 |  |  | 100 | 100 | [15 empty] | 0.13672 | 0.000915 | 0.09 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2442 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017830
160 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.3.2.5 | ZERO SPEED SWITCH-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-02 | 2020-03-17 18:00 | 2020-08-09 | 2020-10-29 18:00 |  |  | 2020-08-09 13:13 |  |  |  | 100 | 0 | [15 empty] | 0.015191 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2443 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017831
161 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.3.2.5 | CHUTE BLOCK SWITCH-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-01 09:00 | 2020-03-16 18:00 | 2020-02-01 09:00 | 2020-07-15 18:00 |  |  | 2020-02-11 21:24 | 2020-07-15 21:24 |  |  | 100 | 100 | [15 empty] | 0.030381 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2444 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017832
162 | Task(Task)-->P (Procurement) | CONTROL JUNCTION BOX |  | 1.3.2.5 | CONTROL JUNCTION BOX-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-22 | 2020-05-05 18:00 | 2020-07-25 09:00 | 2020-11-10 18:00 |  |  | 2020-07-25 12:12 |  |  |  | 100 | 0 | [15 empty] | 0.10633 | 0.000712 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2445 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017833
163 | Task(Task)-->P (Procurement) | MANUFACTURING & RECEIPT AT SITE (MRN) | 1.3.2.6 | 1.3.2 | MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-09 | 2021-02-28 23:59 | 2020-03-16 09:00 | 2021-06-13 23:59 |  |  | 2020-03-16 02:00 |  |  |  | 81.9097 | 21.7872 | [15 empty] | 60.0041 | 2.6775 | 263.31 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2446 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017834
164 | Task(Task)-->P (Procurement) | Apron Feeder |  | 1.3.2.6 | Apron Feeder-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-09 | 2021-02-03 18:00 | 2020-03-16 09:00 | 2020-12-31 18:00 |  |  | 2020-03-16 02:00 |  |  |  | 76.4543 | 40 | [15 empty] | 19.0954 | 0.51128 | 50.28 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2447 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017835
165 | Task(Task)-->P (Procurement) | Gear Box for Apron Feeder |  | 1.3.2.6 | Gear Box for Apron Feeder-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-27 09:00 | 2020-12-22 18:00 | 2020-07-01 09:00 | 2020-12-31 18:00 |  |  | 2020-07-01 17:25 |  |  |  | 80 | 30 | [15 empty] | 0.91527 | 0.024506 | 2.41 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2448 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017836
166 | Task(Task)-->P (Procurement) | Geared Coupling for Apron Feeder |  | 1.3.2.6 | Geared Coupling for Apron Feeder-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-18 09:00 | 2020-12-15 18:00 | 2020-07-23 09:00 | 2020-11-30 18:00 |  |  | 2020-07-30 17:44 |  |  |  | 80.663 | 90 | [15 empty] | 0.1671 | 0.004474 | 0.44 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2449 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017837
167 | Task(Task)-->P (Procurement) | Primary Sizer |  | 1.3.2.6 | Primary Sizer-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-19 09:00 | 2021-02-28 23:59 | 2020-06-22 09:00 | 2021-02-28 23:59 |  |  | 2020-06-22 01:48 |  |  |  | 70.7447 | 35 | [15 empty] | 37.8413 | 1.0132 | 99.64 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2450 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017838
168 | Task(Task)-->P (Procurement) | Pulley for Dribble Conveyor |  | 1.3.2.6 | Pulley for Dribble Conveyor-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-30 09:00 | 2020-11-20 18:00 | 2020-03-25 09:00 | 2020-11-30 18:00 |  |  | 2020-03-25 18:05 |  |  |  | 95.7627 | 0 | [15 empty] | 1.014 | 0.02715 | 2.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2451 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017839
169 | Task(Task)-->P (Procurement) | Idler for Dribble Conveyor |  | 1.3.2.6 | Idler for Dribble Conveyor-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-02 09:00 | 2020-11-13 18:00 | 2020-06-25 09:00 | 2020-12-31 18:00 | [6 empty] | 98.4694 | 0 | [15 empty] | 0.21268 | 0.005694 | 0.56 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2452 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017840
170 | Task(Task)-->P (Procurement) | Plummer Block for Dribble Conveyor |  | 1.3.2.6 | Plummer Block for Dribble Conveyor-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-31 09:00 | 2020-12-23 18:00 | 2020-06-29 09:00 | 2020-12-31 18:00 | [6 empty] | 62.6087 | 0 | [15 empty] | 0.075956 | 0.002034 | 0.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2453 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017841
171 | Task(Task)-->P (Procurement) | Bearing for Dribble Conveyor |  | 1.3.2.6 | Bearing for Dribble Conveyor-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-26 09:00 | 2020-12-23 18:00 | 2020-03-24 09:00 | 2020-09-09 18:00 | [6 empty] | 64.1667 | 0 | [15 empty] | 0.12533 | 0.003356 | 0.33 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2454 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017842
172 | Task(Task)-->P (Procurement) | Belting for Dribble Conveyor |  | 1.3.2.6 | Belting for Dribble Conveyor-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-21 09:00 | 2020-11-16 18:00 | 2020-11-16 09:00 | 2021-06-13 23:59 | [6 empty] | 97.1429 | 0 | [15 empty] | 0.28104 | 0.007525 | 0.74 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2455 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017843
173 | Task(Task)-->P (Procurement) | Scrapper for Dribble Conveyor |  | 1.3.2.6 | Scrapper for Dribble Conveyor-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-15 09:00 | 2020-12-11 18:00 | 2020-07-30 09:00 | 2020-12-31 18:00 | [6 empty] | 82.7778 | 0 | [15 empty] | 0.1671 | 0.004474 | 0.44 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2456 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017844
174 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.3.2.6 | Technological Structure-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-19 09:00 | 2021-02-13 18:00 | 2020-07-06 09:00 | 2021-01-31 23:59 | [6 empty] | 60.4167 | 0 | [15 empty] | 0.8621 | 0.023083 | 2.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2457 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017845
175 | Task(Task)-->P (Procurement) | Chute & Skirt |  | 1.3.2.6 | Chute & Skirt-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-19 09:00 | 2021-02-13 18:00 | 2020-07-06 09:00 | 2021-01-31 23:59 | [6 empty] | 60.4167 | 0 | [15 empty] | 3.9535 | 0.10586 | 10.41 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2458 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017846
176 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.3.2.6 | Takeup Component-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-28 09:00 | 2020-12-25 18:00 | 2020-08-04 09:00 | 2020-12-25 18:00 | [6 empty] | 62.5 | 0 | [15 empty] | 0.049371 | 0.001322 | 0.13 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2459 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017847
177 | Task(Task)-->P (Procurement) | Gear Box for Dribble Conveyor |  | 1.3.2.6 | Gear Box for Dribble Conveyor-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-27 09:00 | 2020-12-22 18:00 | 2020-07-01 09:00 | 2020-12-31 18:00 |  |  | 2020-07-01 17:25 |  |  |  | 80 | 30 | [15 empty] | 0.91527 | 0.024506 | 2.41 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2460 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017848
178 | Task(Task)-->P (Procurement) | Geared Coupling for Dribble Conveyor |  | 1.3.2.6 | Geared Coupling for Dribble Conveyor-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-18 09:00 | 2020-12-15 18:00 | 2020-07-30 09:00 | 2020-11-30 18:00 |  |  | 2020-07-30 17:44 |  |  |  | 80.663 | 90 | [15 empty] | 0.22787 | 0.006101 | 0.6 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2461 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017849
179 | Task(Task)-->P (Procurement) | Building Structure |  | 1.3.2.6 | Building Structure-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-06 09:00 | 2020-10-05 18:00 | 2020-07-11 09:00 | 2021-03-31 18:00 | [6 empty] | 100 | 0 | [15 empty] | 31.2293 | 0.83616 | 82.23 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2462 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017850
180 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR CONVEYING SYSTEM |  | 1.3.2.6 | LT AC MOTORS FOR CONVEYING SYSTEM-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-02 09:00 | 2020-09-26 18:00 | 2020-10-15 09:00 | 2021-05-11 18:00 |  |  | 2020-09-22 12:54 |  |  |  | 100 | 0 | [15 empty] | 0.74437 | 0.01993 | 1.96 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2463 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017851
181 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.3.2.6 | LIGHT & LIGHT FIXTURES-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-26 09:00 | 2020-10-21 18:00 | 2020-11-17 09:00 | 2021-04-14 18:00 | [6 empty] | 100 | 0 | [15 empty] | 1.2115 | 0.032438 | 3.19 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2464 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017852
182 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.3.2.6 | LIGHTING POLES-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-10 09:00 | 2020-11-07 18:00 | 2020-09-09 09:00 | 2020-12-07 18:00 |  |  | 2020-08-07 15:47 |  |  |  | 100 | 0 | [15 empty] | 0.55068 | 0.014744 | 1.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2465 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017853
183 | Task(Task)-->P (Procurement) | LPBS |  | 1.3.2.6 | LPBS-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-05 09:00 | 2020-09-16 18:00 | 2020-08-23 | 2020-12-04 18:00 |  |  | 2020-08-22 12:56 |  |  |  | 100 | 0 | [15 empty] | 0.08735 | 0.002339 | 0.23 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2466 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017854
184 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.3.2.6 | CONVEYOR BELT PROTECTION SWITCHES-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-22 | 2020-08-05 18:00 | 2020-12-01 09:00 | 2021-04-16 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.13672 | 0.003661 | 0.36 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2469 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017855
185 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.3.2.6 | ZERO SPEED SWITCH-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-18 09:00 | 2020-07-27 18:00 | 2020-10-30 09:00 | 2021-03-10 18:00 |  |  | 2020-10-29 12:55 |  |  |  | 100 | 0 | [15 empty] | 0.011393 | 0.000305 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2470 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017856
186 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.3.2.6 | CHUTE BLOCK SWITCH-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-17 09:00 | 2020-07-31 18:00 | 2020-07-02 09:00 | 2020-11-15 23:59 |  |  | 2020-07-15 21:33 |  |  |  | 100 | 0 | [15 empty] | 0.022787 | 0.00061 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2471 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017857
187 | Task(Task)-->P (Procurement) | CONTROL JUNCTION BOX |  | 1.3.2.6 | CONTROL JUNCTION BOX-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-06 09:00 | 2020-09-16 18:00 | 2020-11-11 09:00 | 2021-03-24 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.10254 | 0.002746 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2472 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017858
188 | Task(Task)-->C (Construction) | CONSTRUCTION | 1.3.3 | 1.3 | CONSTRUCTION-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-10-11 | 2021-09-13 18:00 | 2020-04-26 | 2022-05-04 18:00 |  |  | 2020-04-26 14:54 |  |  |  | 37.1907 | 0.03749 | [15 empty] | 49.7948 | 4.7128 | 463.48 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2473 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017859
189 | Task(Task)-->C (Construction) | CIVIL WORKS | 1.3.3.1 | 1.3.3 | CIVIL WORKS-->CONSTRUCTION-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-10-11 | 2021-06-04 18:00 | 2020-04-26 | 2022-01-23 23:59 |  |  | 2020-04-26 14:54 |  |  |  | 38.2227 | 0.04899 | [15 empty] | 76.5276 | 3.6066 | 354.69 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2474 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017860
190 | Task(Task)-->C (Construction) | AVAILABILITY OF FRONT BY NTPC |  | 1.3.3.1 | AVAILABILITY OF FRONT BY NTPC-->CIVIL WORKS-->CONSTRUCTION-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-14 09:00 | 2020-04-14 18:00 | 2020-07-11 09:00 | 2020-11-25 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2475 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017861
191 | Task(Task)-->C (Construction) | APPROACH TO DUMP HOPPER |  | 1.3.3.1 | APPROACH TO DUMP HOPPER-->CIVIL WORKS-->CONSTRUCTION-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-15 09:00 | 2020-07-13 18:00 | 2020-04-26 | 2020-12-10 18:00 |  |  | 2020-04-26 14:54 |  |  |  | 100 | 34 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5608 | 0 | 4 | Low | Niharendu Kamle | [6 empty] | 0 | 0 | [246 empty] | 1017862
192 | Task(Task)-->C (Construction) | EXCAVATION |  | 1.3.3.1 | EXCAVATION-->CIVIL WORKS-->CONSTRUCTION-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-21 09:00 | 2020-05-06 18:00 | 2020-07-13 09:00 | 2020-12-25 18:00 |  |  | 2020-07-13 14:55 |  |  |  | 100 | 7.4576 | [15 empty] | 0.65689 | 0.023692 | 2.33 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 8716 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2476 | 0 | 4 | Low | Niharendu Kamle | [6 empty] | 0 | 0 | [246 empty] | 1017863
193 | Task(Task)-->C (Construction) | PCC |  | 1.3.3.1 | PCC-->CIVIL WORKS-->CONSTRUCTION-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-10-11 | 2020-05-13 18:00 | 2020-12-17 09:00 | 2021-01-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 2.8729 | 0.10361 | 10.19 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 1127 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | Weekly | Cumulative | 0 | No | No | 2477 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | PCC | [23 empty] | 1017864
194 | Task(Task)-->C (Construction) | RAFT |  | 1.3.3.1 | RAFT-->CIVIL WORKS-->CONSTRUCTION-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-06 09:00 | 2020-06-06 18:00 | 2020-12-25 09:00 | 2021-01-25 18:00 | [6 empty] | 100 | 0 | [15 empty] | 2.0581 | 0.074227 | 7.3 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 275 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2478 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017865
195 | Task(Task)-->C (Construction) | PEDESTALS FOR DHS STR. |  | 1.3.3.1 | PEDESTALS FOR DHS STR.-->CIVIL WORKS-->CONSTRUCTION-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-26 09:00 | 2020-07-03 18:00 | 2021-01-14 09:00 | 2021-02-21 23:59 | [6 empty] | 100 | 0 | [15 empty] | 0.89089 | 0.032131 | 3.16 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 119 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2479 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017866
196 | Task(Task)-->C (Construction) | PRIMARY SIZER FLOOR (WITH CONNECTED RETAINING WALL) |  | 1.3.3.1 | PRIMARY SIZER FLOOR (WITH CONNECTED RETAINING WALL)-->CIVIL WORKS-->CONSTRUCTION-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-03-29 09:00 | 2021-04-28 18:00 | 2021-11-17 09:00 | 2021-12-17 18:00 | [6 empty] | 0 | 0 | [15 empty] | 1.607 | 0.057958 | 5.7 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 215 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2480 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017867
197 | Task(Task)-->C (Construction) | APPRON FEEDER FLOOR (WITH CONNECTED RETAINING WALL) |  | 1.3.3.1 | APPRON FEEDER FLOOR (WITH CONNECTED RETAINING WALL)-->CIVIL WORKS-->CONSTRUCTION-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-04-14 09:00 | 2021-05-14 18:00 | 2021-12-03 09:00 | 2022-01-02 23:59 | [6 empty] | 0 | 0 | [15 empty] | 1.607 | 0.057958 | 5.7 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 215 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2482 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017868
198 | Task(Task)-->C (Construction) | SC 1A, SC 1B, SC 2A & SC 2B TAIL PULLEY FLOOR (GRADE SLAB) |  | 1.3.3.1 | SC 1A, SC 1B, SC 2A & SC 2B TAIL PULLEY FLOOR (GRADE SLAB)-->CIVIL WORKS-->CONSTRUCTION-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-03-29 09:00 | 2021-06-04 18:00 | 2021-11-17 09:00 | 2022-01-23 23:59 | [6 empty] | 0 | 0 | [15 empty] | 11.6972 | 0.42187 | 41.49 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 2216 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2483 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017869
199 | Task(Task)-->C (Construction) | RCC FOR BALANCE RETAINING WALL |  | 1.3.3.1 | RCC FOR BALANCE RETAINING WALL-->CIVIL WORKS-->CONSTRUCTION-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-14 | 2021-06-01 18:00 | 2021-02-02 09:00 | 2022-01-20 18:00 | [6 empty] | 42.4929 | 0 | [15 empty] | 47.5359 | 1.7144 | 168.61 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 6355 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2484 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | RCC | [23 empty] | 1017870
200 | Task(Task)-->C (Construction) | RAMP (FILLING WITH EARTH) |  | 1.3.3.1 | RAMP (FILLING WITH EARTH)-->CIVIL WORKS-->CONSTRUCTION-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-14 09:00 | 2021-06-01 18:00 | 2021-03-04 09:00 | 2022-01-20 18:00 | [6 empty] | 37.1517 | 0 | [15 empty] | 31.0741 | 1.1207 | 110.22 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 249100 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2485 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017871
201 | Task(Task)-->C (Construction) | STRUCTURAL WORKS | 1.3.3.2 | 1.3.3 | STRUCTURAL WORKS-->CONSTRUCTION-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-01 09:00 | 2021-03-28 23:59 | 2021-03-22 09:00 | 2021-11-16 18:00 | [6 empty] | 54.9327 | 0 | [15 empty] | 14.4537 | 0.68118 | 66.99 |  | Quantity | Metric Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 1035 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2486 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017872
202 | Task(Task)-->C (Construction) | STRL. ERECTION FOR RCC CASTING OF PRIMARY SIZER FLOOR & FOUNDATION |  | 1.3.3.2 | STRL. ERECTION FOR RCC CASTING OF PRIMARY SIZER FLOOR & FOUNDATION-->STRUCTURAL WORKS-->CONSTRUCTION-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-01 09:00 | 2020-09-29 18:00 | 2021-03-22 09:00 | 2021-05-20 18:00 | [6 empty] | 100 | 0 | [15 empty] | 38.713 | 0.2637 | 25.93 | Plan & Actual | Quantity | Metric Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2487 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017873
203 | Task(Task)-->C (Construction) | STRL. ERECTION FOR APPRON FEEDERS RCC FLOOR |  | 1.3.3.2 | STRL. ERECTION FOR APPRON FEEDERS RCC FLOOR-->STRUCTURAL WORKS-->CONSTRUCTION-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-09-30 09:00 | 2020-12-13 23:59 | 2021-05-21 09:00 | 2021-08-03 18:00 | [6 empty] | 56 | 0 | [15 empty] | 28.9639 | 0.19729 | 19.4 | Plan & Actual | Quantity | Metric Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5585 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017874
204 | Task(Task)-->C (Construction) | STRL. ERECTION FOR DUMP HOPPER STEEL FLOOR |  | 1.3.3.2 | STRL. ERECTION FOR DUMP HOPPER STEEL FLOOR-->STRUCTURAL WORKS-->CONSTRUCTION-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-12-14 09:00 | 2021-01-27 18:00 | 2021-08-04 09:00 | 2021-09-17 18:00 | [6 empty] | 0 | 0 | [15 empty] | 24.1266 | 0.16434 | 16.16 | Plan & Actual | Quantity | Metric Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2489 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017875
205 | Task(Task)-->C (Construction) | BALANCE STRUCTURAL ERECTION |  | 1.3.3.2 | BALANCE STRUCTURAL ERECTION-->STRUCTURAL WORKS-->CONSTRUCTION-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-01-28 09:00 | 2021-03-28 23:59 | 2021-09-18 09:00 | 2021-11-16 18:00 | [6 empty] | 0 | 0 | [15 empty] | 8.1965 | 0.055833 | 5.49 | Plan & Actual | Quantity | Metric Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2490 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017876
206 | Task(Task)-->C (Construction) | MECHANICAL EQUIPMENT WORKS | 1.3.3.3 | 1.3.3 | MECHANICAL EQUIPMENT WORKS-->CONSTRUCTION-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-05-27 09:00 | 2021-09-13 18:00 | 2022-01-15 09:00 | 2022-05-04 18:00 | [6 empty] | 0 | 0 | [15 empty] | 7.2042 | 0.33952 | 33.39 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5447 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017877
207 | Task(Task)-->C (Construction) | ERECTION OF PRIMARY SIZER |  | 1.3.3.3 | ERECTION OF PRIMARY SIZER-->MECHANICAL EQUIPMENT WORKS-->CONSTRUCTION-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-05-27 09:00 | 2021-07-05 18:00 | 2022-01-15 09:00 | 2022-02-23 18:00 | [6 empty] | 0 | 0 | [15 empty] | 21.018 | 0.07136 | 7.02 | Plan & Actual | Quantity | Metric Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 191 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2491 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017878
208 | Task(Task)-->C (Construction) | ERECTION OF APRRON FEEDERS |  | 1.3.3.3 | ERECTION OF APRRON FEEDERS-->MECHANICAL EQUIPMENT WORKS-->CONSTRUCTION-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-06-05 09:00 | 2021-07-19 18:00 | 2022-01-24 09:00 | 2022-03-09 18:00 | [6 empty] | 0 | 0 | [15 empty] | 10.5689 | 0.035884 | 3.53 | Plan & Actual | Quantity | Metric Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2492 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017879
209 | Task(Task)-->C (Construction) | ERECTION OF STEEL DUMP HOPPER |  | 1.3.3.3 | ERECTION OF STEEL DUMP HOPPER-->MECHANICAL EQUIPMENT WORKS-->CONSTRUCTION-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-07-20 09:00 | 2021-09-07 18:00 | 2022-03-10 09:00 | 2022-04-28 18:00 | [6 empty] | 0 | 0 | [15 empty] | 52.5749 | 0.1785 | 17.56 | Plan & Actual | Quantity | Metric Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 478 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2493 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017880
210 | Task(Task)-->C (Construction) | ERECTION OF DRIBBLE CONVEYOR |  | 1.3.3.3 | ERECTION OF DRIBBLE CONVEYOR-->MECHANICAL EQUIPMENT WORKS-->CONSTRUCTION-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-06-20 | 2021-08-03 18:00 | 2022-02-08 09:00 | 2022-03-24 18:00 | [6 empty] | 0 | 0 | [15 empty] | 10.5689 | 0.035884 | 3.53 | Plan & Actual | Quantity | Metric Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2494 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017881
211 | Task(Task)-->C (Construction) | ERECTION OF CHUTES/ HOODS & SUPPORTS |  | 1.3.3.3 | ERECTION OF CHUTES/ HOODS & SUPPORTS-->MECHANICAL EQUIPMENT WORKS-->CONSTRUCTION-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-07-06 09:00 | 2021-09-13 18:00 | 2022-02-24 09:00 | 2022-05-04 18:00 | [6 empty] | 0 | 0 | [15 empty] | 5.2695 | 0.017891 | 1.76 | Plan & Actual | Quantity | Metric Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2495 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017882
212 | Task(Task)-->C (Construction) | BELTING WORKS |  | 1.3.3 | BELTING WORKS-->CONSTRUCTION-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-07-29 09:00 | 2021-08-28 18:00 | 2022-03-19 09:00 | 2022-04-18 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0.034521 | 0.001627 | 0.16 | Plan & Actual | Quantity | Meter | 0 | 0 | 0 | 0 | 0 | 0 | 104 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2498 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017883
213 | Task(Task)-->C (Construction) | ELECTRICAL & INSTRUMENTATION WORKS | 1.3.3.5 | 1.3.3 | ELECTRICAL & INSTRUMENTATION WORKS-->CONSTRUCTION-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-01-19 09:00 | 2021-08-25 18:00 | 2021-09-09 09:00 | 2022-04-17 23:59 | [6 empty] | 0 | 0 | [15 empty] | 1.4477 | 0.06823 | 6.71 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2499 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017884
214 | Task(Task)-->C (Construction) | CABLE TRAY |  | 1.3.3.5 | CABLE TRAY-->ELECTRICAL & INSTRUMENTATION WORKS-->CONSTRUCTION-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-01-19 09:00 | 2021-02-17 18:00 | 2021-09-09 09:00 | 2021-10-08 18:00 | [6 empty] | 0 | 0 | [15 empty] | 7.0149 | 0.004786 | 0.47 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 1100 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2500 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017885
215 | Task(Task)-->C (Construction) | POWER CABLE |  | 1.3.3.5 | POWER CABLE-->ELECTRICAL & INSTRUMENTATION WORKS-->CONSTRUCTION-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-08-04 09:00 | 2021-08-07 18:00 | 2022-03-25 09:00 | 2022-03-28 18:00 | [6 empty] | 0 | 0 | [15 empty] | 15.5224 | 0.010591 | 1.04 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 7366 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2501 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017886
216 | Task(Task)-->C (Construction) | C&I CABLE |  | 1.3.3.5 | C&I CABLE-->ELECTRICAL & INSTRUMENTATION WORKS-->CONSTRUCTION-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-08-05 09:00 | 2021-08-07 18:00 | 2022-03-26 09:00 | 2022-03-28 18:00 | [6 empty] | 0 | 0 | [15 empty] | 22.8358 | 0.015581 | 1.53 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 10800 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5276 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017887
217 | Task(Task)-->C (Construction) | EARTHING |  | 1.3.3.5 | EARTHING-->ELECTRICAL & INSTRUMENTATION WORKS-->CONSTRUCTION-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-08-03 09:00 | 2021-08-07 18:00 | 2022-03-24 09:00 | 2022-03-28 18:00 | [6 empty] | 0 | 0 | [15 empty] | 2.8358 | 0.001935 | 0.19 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 850 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5277 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017888
218 | Task(Task)-->C (Construction) | EARTH PIT |  | 1.3.3.5 | EARTH PIT-->ELECTRICAL & INSTRUMENTATION WORKS-->CONSTRUCTION-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-05-30 | 2021-06-01 18:00 | 2022-01-18 09:00 | 2022-01-20 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5278 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017889
219 | Task(Task)-->C (Construction) | LIGHTING |  | 1.3.3.5 | LIGHTING-->ELECTRICAL & INSTRUMENTATION WORKS-->CONSTRUCTION-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-03-23 09:00 | 2021-04-07 18:00 | 2021-11-11 09:00 | 2021-11-26 18:00 | [6 empty] | 0 | 0 | [15 empty] | 27.9104 | 0.019043 | 1.87 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 192 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5279 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017890
220 | Task(Task)-->C (Construction) | FIELD INSTRUMENTS |  | 1.3.3.5 | FIELD INSTRUMENTS-->ELECTRICAL & INSTRUMENTATION WORKS-->CONSTRUCTION-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-08-06 09:00 | 2021-08-08 23:59 | 2022-03-27 | 2022-03-29 18:00 | [6 empty] | 0 | 0 | [15 empty] | 13.5821 | 0.009267 | 0.91 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5280 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017891
221 | Task(Task)-->C (Construction) | MOTOR TERMINATION |  | 1.3.3.5 | MOTOR TERMINATION-->ELECTRICAL & INSTRUMENTATION WORKS-->CONSTRUCTION-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-08-04 09:00 | 2021-08-10 18:00 | 2022-03-25 09:00 | 2022-03-31 18:00 | [6 empty] | 0 | 0 | [15 empty] | 10.2985 | 0.007027 | 0.69 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5281 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017892
222 | Task(Task)-->C (Construction) | NO LOAD RUN OF MOTOR |  | 1.3.3.5 | NO LOAD RUN OF MOTOR-->ELECTRICAL & INSTRUMENTATION WORKS-->CONSTRUCTION-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-08-22 | 2021-08-25 18:00 | 2022-04-14 09:00 | 2022-04-17 23:59 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5282 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017893
223 | Task(Task)-->C (Construction) | NO LOAD COMMISSIONING & SYSTEM READYNESS FOR LOAD & TRIAL OPERATION |  | 1.3.3 | NO LOAD COMMISSIONING & SYSTEM READYNESS FOR LOAD & TRIAL OPERATION-->CONSTRUCTION-->DUMP HOPPER STATION (DHS), RETAINING WALL & RAMP-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-08-19 09:00 | 2021-09-01 18:00 | 2022-04-11 09:00 | 2022-04-24 23:59 | [6 empty] | 0 | 0 | [15 empty] | 0.33227 | 0.015659 | 1.54 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2502 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017894
224 | Task(Task)-->E (Engineering) | KDTP-1 | 1.4 | 1 | KDTP-1-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-09-27 09:00 | 2021-08-28 18:00 | 2019-09-27 09:00 | 2022-04-20 18:00 |  |  | 2019-09-27 10:57 |  |  |  | 75.2176 | 33.2681 | [15 empty] | 4.0727 | 4.0727 | 400.52 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2504 | 0 | 1 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017895
225 | Task(Task)-->E (Engineering) | ENGINEERING | 1.4.1 | 1.4 | ENGINEERING-->KDTP-1-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-10-27 23:59 | 2020-07-07 17:40 | 2020-03-02 09:00 | 2020-11-15 23:59 |  |  | 2020-02-17 17:40 |  |  |  | 100 | 82.6272 | [15 empty] | 1.9075 | 0.077687 | 7.64 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2505 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017896
226 | Task(Task)-->E (Engineering) | MECHANICAL | 1.4.1.1 | 1.4.1 | MECHANICAL-->ENGINEERING-->KDTP-1-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-10-27 23:59 | 2020-06-04 17:40 | 2020-03-02 09:00 | 2020-08-21 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 61.9442 | [15 empty] | 29.6199 | 0.023011 | 2.26 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No | 2506 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036074
227 | Task(Task)-->E (Engineering) | GA OF FLAP GATE |  | 1.4.1.1 | GA OF FLAP GATE-->MECHANICAL-->ENGINEERING-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-04 18:00 | 2020-06-04 17:40 | 2020-05-20 18:00 | 2020-08-21 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1021 |  | 2020-02-13 10:27 | 7012-155-PVM-B-121 |  |  |  | A |  |  |  | 25 | 0.005753 | 0.54 | Plan & Actual | Date |  | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2510 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-04 18:00 | 2020-05-20 18:00 |  | 10 |  |  |  | 2020-04-23 17:40 | 2020-06-10 18:00 |  | 30 |  |  |  | 2020-04-30 17:40 | 2020-06-16 18:00 |  | 35 |  |  |  | 2020-05-06 23:59 | 2020-06-21 23:59 |  | 65 |  |  |  | 2020-05-13 17:40 | 2020-07-12 23:59 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-04 17:40 | 2020-07-12 23:59 |  | 100 | [122 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 51 |  |  |  |  | 101065
228 | Task(Task)-->E (Engineering) | THRUST & ACTUATOR SELECTION FOR FLAP GATE ACTUATOR |  | 1.4.1.1 | THRUST & ACTUATOR SELECTION FOR FLAP GATE ACTUATOR-->MECHANICAL-->ENGINEERING-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-04 18:00 | 2020-06-04 17:40 | 2020-05-20 18:00 | 2020-08-21 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-DC-1022 |  | 2020-02-13 10:27 | 7012-155-PVM-B-122 |  |  |  | A |  |  |  | 5.0926 | 0.001172 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2511 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-04 18:00 | 2020-05-20 18:00 |  | 10 |  |  |  | 2020-04-23 17:40 | 2020-06-10 18:00 |  | 30 |  |  |  | 2020-04-30 17:40 | 2020-06-16 18:00 |  | 35 |  |  |  | 2020-05-06 23:59 | 2020-06-21 23:59 |  | 65 |  |  |  | 2020-05-13 17:40 | 2020-07-12 23:59 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-04 17:40 | 2020-07-12 23:59 |  | 100 | [122 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 52 |  |  |  |  | 101066
229 | Task(Task)-->E (Engineering) | G.A & LOAD DATA OF TRANSFER POINT KDTP-1 |  | 1.4.1.1 | G.A & LOAD DATA OF TRANSFER POINT KDTP-1-->MECHANICAL-->ENGINEERING-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-10-29 18:00 | 2020-01-02 17:40 | 2020-03-07 18:00 | 2020-05-19 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-0008 |  | 2020-02-13 10:26 | 7012-155-PVM-B-008 |  |  |  | A |  |  |  | 39.8148 | 0.009162 | 0.86 | Plan & Actual | Date |  | 0 | 0 | 0 | 320 | 0 | 149.1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2507 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-10-29 18:00 | 2020-03-07 18:00 |  | 10 | 2020-03-07 23:31 |  |  | 2019-11-25 17:40 | 2020-04-04 18:00 |  | 30 | 2020-04-04 23:31 |  |  | 2019-11-30 17:40 | 2020-04-07 18:00 |  | 35 | 2020-04-07 23:31 |  |  | 2019-12-06 23:59 | 2020-04-14 18:00 |  | 65 | 2020-04-14 23:31 |  |  | 2019-12-12 17:40 | 2020-05-05 18:00 |  | 80 | 2020-05-08 23:31 | [5 empty] | 80 | 2020-09-17 15:51 | [5 empty] | 80 | 2020-09-17 15:51 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-01-02 17:40 | 2020-05-19 18:00 |  | 100 | [122 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 8 |  |  |  |  | 101022
230 | Task(Task)-->E (Engineering) | GA OF SECONDARY SIZERS SS-1, SS-2, SS-3 & SS-4 |  | 1.4.1.1 | GA OF SECONDARY SIZERS SS-1, SS-2, SS-3 & SS-4-->MECHANICAL-->ENGINEERING-->KDTP-1-->NTPC's CHP KERENDARI | Completed | No | No | 2019-10-27 23:59 | 2019-12-21 17:40 | 2020-03-30 09:00 | 2020-06-10 18:00 |  |  | 2020-02-21 14:04 | 2020-06-29 19:15 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1007 |  | 2020-02-13 10:27 | 7012-155-PVM-B-107 |  |  |  | A |  |  |  | 10.1852 | 0.002344 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 80 | 0 | 13.2 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2508 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-10-27 23:59 | 2020-03-18 18:00 |  | 10 | 2020-03-18 23:31 |  |  | 2019-11-13 17:40 | 2020-03-22 23:59 |  | 30 | 2020-03-22 23:31 |  |  | 2019-11-19 17:40 | 2020-03-28 18:00 |  | 35 | 2020-03-28 23:31 |  |  | 2019-11-25 23:59 | 2020-03-30 18:00 |  | 65 | 2020-03-30 23:31 |  |  | 2019-11-30 17:40 | 2020-04-20 18:00 |  | 80 | 2020-04-23 23:31 | [5 empty] | 80 | 2020-06-22 18:44 | [5 empty] | 80 | 2020-06-10 18:01 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2019-12-21 17:40 | 2020-05-04 18:00 |  | 100 | 2020-06-29 19:16 | [121 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 37 |  |  |  |  | 101051
231 | Task(Task)-->E (Engineering) | GA OF INLINE MAGNETIC SEPERATOR |  | 1.4.1.1 | GA OF INLINE MAGNETIC SEPERATOR-->MECHANICAL-->ENGINEERING-->KDTP-1-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-30 18:00 | 2020-03-25 17:40 | 2020-03-02 09:00 | 2020-04-11 18:00 |  |  | 2020-02-21 14:04 | 2020-06-19 15:47 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1030 |  | 2020-02-13 10:27 | 7012-155-PVM-B-130 |  |  |  | A |  |  |  | 19.9074 | 0.004581 | 0.43 | Plan & Actual | Date |  | 0 | 0 | 0 | 160 | 0 | 8.1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2512 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-30 18:00 | 2020-02-06 18:00 |  | 10 | 2020-02-06 23:31 |  |  | 2020-02-13 17:40 | 2020-02-19 18:00 |  | 30 | 2020-02-19 23:31 |  |  | 2020-02-19 17:40 | 2020-02-24 18:00 |  | 35 | 2020-02-24 23:31 |  |  | 2020-02-26 23:59 | 2020-03-02 18:00 |  | 65 | 2020-03-02 23:31 |  |  | 2020-03-03 17:40 | 2020-03-20 18:00 |  | 80 | 2020-03-20 23:31 | [5 empty] | 80 | 2020-06-10 19:07 | [5 empty] | 80 | 2020-06-10 19:07 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-25 17:40 | 2020-04-25 18:00 |  | 100 | 2020-04-23 23:31 | [121 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 60 |  |  |  |  | 101074
232 | Task(Task)-->E (Engineering) | CIVIL | 1.4.1.2 | 1.4.1 | CIVIL-->ENGINEERING-->KDTP-1-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-01-19 23:59 | 2020-05-25 17:40 | 2020-06-26 18:00 | 2020-09-23 18:00 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 98.0715 | [15 empty] | 33.2896 | 0.025862 | 2.54 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No | 2515 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036075
233 | Task(Task)-->E (Engineering) | TRANSFER POINT KDTP-1 - DESIGN CALCULATION OF SUPER STRUCTURE |  | 1.4.1.2 | TRANSFER POINT KDTP-1 - DESIGN CALCULATION OF SUPER STRUCTURE-->CIVIL-->ENGINEERING-->KDTP-1-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-19 23:59 | 2020-03-19 17:40 | 2020-06-30 09:00 | 2020-07-15 18:00 |  |  | 2020-02-21 15:37 | 2020-07-15 15:00 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-DC-0006 |  | 2020-02-13 11:41 | 7012-155-PVC-U-016 |  |  |  | A |  |  |  | 45.6693 | 0.011811 | 1.16 | Plan & Actual | Date |  | 0 | 0 | 0 | 431.02 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2519 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-19 23:59 | 2020-04-17 18:00 |  | 10 | 2020-05-05 23:31 |  |  | 2020-02-06 17:40 | 2020-05-07 18:00 |  | 30 |  |  |  | 2020-02-13 17:40 | 2020-05-10 23:59 |  | 35 |  |  |  | 2020-02-19 23:59 | 2020-05-17 23:59 |  | 65 | 2020-07-15 14:52 |  |  | 2020-02-26 17:40 | 2020-06-07 23:59 |  | 80 | 2020-07-15 14:55 | [5 empty] | 80 | 2020-07-15 15:00 | [5 empty] | 80 | 2020-07-15 15:00 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-19 17:40 | 2020-06-21 23:59 |  | 100 | 2020-07-15 15:01 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 117 |  |  |  |  | 101131
234 | Task(Task)-->E (Engineering) | TRANSFER POINT KDTP-1 - DESIGN CALCULATION OF SUB STRUCTURE |  | 1.4.1.2 | TRANSFER POINT KDTP-1 - DESIGN CALCULATION OF SUB STRUCTURE-->CIVIL-->ENGINEERING-->KDTP-1-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-23 23:59 | 2020-04-23 17:40 | 2020-07-11 09:00 | 2020-08-04 18:00 |  |  | 2020-02-21 15:37 | 2020-08-04 20:42 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-DC-0007 |  | 2020-02-13 11:41 | 7012-155-PVC-U-017 |  |  |  | A |  |  |  | 27.1654 | 0.007026 | 0.69 | Plan & Actual | Date |  | 0 | 0 | 0 | 257.12 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2520 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-23 23:59 | 2020-05-22 18:00 |  | 10 |  |  |  | 2020-03-12 17:40 | 2020-06-11 18:00 |  | 30 |  |  |  | 2020-03-19 17:40 | 2020-06-14 23:59 |  | 35 |  |  |  | 2020-03-25 23:59 | 2020-06-21 23:59 |  | 65 | 2020-08-04 20:23 |  |  | 2020-04-01 17:40 | 2020-07-12 23:59 |  | 80 | 2020-08-04 20:37 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-23 17:40 | 2020-07-26 23:59 |  | 100 | 2020-08-04 20:42 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 118 |  |  |  |  | 101132
235 | Task(Task)-->E (Engineering) | TRANSFER POINT KDTP-1 - NUM & RC DETAILS OF FDN |  | 1.4.1.2 | TRANSFER POINT KDTP-1 - NUM & RC DETAILS OF FDN-->CIVIL-->ENGINEERING-->KDTP-1-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-23 23:59 | 2020-04-23 17:40 | 2020-07-11 09:00 | 2020-08-04 18:00 |  |  | 2020-02-21 15:37 | 2020-08-04 20:41 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-NR-0005 |  | 2020-02-13 11:41 | 7012-155-PVC-C-019 |  |  |  | A |  |  |  | 16.1417 | 0.004175 | 0.41 | Plan & Actual | Date |  | 0 | 0 | 0 | 154.22 | 0 | 8.15 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2516 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-23 23:59 | 2020-05-22 18:00 |  | 10 |  |  |  | 2020-03-12 17:40 | 2020-06-11 18:00 |  | 30 |  |  |  | 2020-03-19 17:40 | 2020-06-14 23:59 |  | 35 | 2020-07-11 16:17 |  |  | 2020-03-25 23:59 | 2020-06-21 23:59 |  | 65 | 2020-08-04 20:24 |  |  | 2020-04-01 17:40 | 2020-07-12 23:59 |  | 80 | 2020-08-04 20:38 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-23 17:40 | 2020-07-26 23:59 |  | 100 | 2020-08-04 20:41 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 120 |  |  |  |  | 101134
236 | Task(Task)-->E (Engineering) | TRANSFER POINT KDTP-1 - NUM & RC DETAILS OF FLOOR SLABS |  | 1.4.1.2 | TRANSFER POINT KDTP-1 - NUM & RC DETAILS OF FLOOR SLABS-->CIVIL-->ENGINEERING-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-24 18:00 | 2020-05-25 17:40 | 2020-06-26 18:00 | 2020-09-23 18:00 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-NR-0006 |  | 2020-02-13 11:41 | 7012-155-PVC-C-020 |  |  |  | A |  |  |  | 5.5118 | 0.001425 | 0.14 | Plan & Actual | Date |  | 0 | 0 | 0 | 51.26 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2517 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-24 18:00 | 2020-06-26 18:00 |  | 10 |  |  |  | 2020-04-13 17:40 | 2020-07-16 18:00 |  | 30 |  |  |  | 2020-04-18 17:40 | 2020-07-19 23:59 |  | 35 | 2020-08-30 20:44 |  |  | 2020-04-24 23:59 | 2020-07-26 23:59 |  | 65 | 2020-08-31 23:46 |  |  | 2020-05-01 17:40 | 2020-08-16 23:59 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-25 17:40 | 2020-08-30 23:59 |  | 100 | [122 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 121 |  |  |  |  | 101135
237 | Task(Task)-->E (Engineering) | TRANSFER POINT KDTP-1 - NUM & RC DETAILS OF GRADE SLAB |  | 1.4.1.2 | TRANSFER POINT KDTP-1 - NUM & RC DETAILS OF GRADE SLAB-->CIVIL-->ENGINEERING-->KDTP-1-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-24 18:00 | 2020-05-25 17:40 | 2020-08-06 09:00 | 2020-08-17 18:00 |  |  | 2020-02-21 15:37 | 2020-08-17 22:47 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-NR-0007 |  | 2020-02-13 11:41 | 7012-155-PVC-C-021 |  |  |  | A |  |  |  | 5.5118 | 0.001425 | 0.14 | Plan & Actual | Date |  | 0 | 0 | 0 | 51.26 | 0 | 40.1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2518 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-24 18:00 | 2020-07-16 18:00 |  | 10 |  |  |  | 2020-04-13 17:40 | 2020-08-05 18:00 |  | 30 |  |  |  | 2020-04-18 17:40 | 2020-08-08 18:00 |  | 35 | 2020-08-06 08:51 |  |  | 2020-04-24 23:59 | 2020-08-15 18:00 |  | 65 | 2020-08-13 19:52 |  |  | 2020-05-01 17:40 | 2020-09-05 18:00 |  | 80 | 2020-08-17 22:42 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-25 17:40 | 2020-09-19 18:00 |  | 100 | 2020-08-17 22:48 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 122 |  |  |  |  | 101136
238 | Task(Task)-->E (Engineering) | STRUCTURAL | 1.4.1.3 | 1.4.1 | STRUCTURAL-->ENGINEERING-->KDTP-1-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-01-19 23:59 | 2020-07-07 17:40 | 2020-07-01 09:00 | 2020-11-15 23:59 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 96.9685 | [15 empty] | 16.6448 | 0.012931 | 1.27 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No | 2521 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036076
239 | Task(Task)-->E (Engineering) | TRANSFER POINT KDTP-1 - STRUCTURAL GA |  | 1.4.1.3 | TRANSFER POINT KDTP-1 - STRUCTURAL GA-->STRUCTURAL-->ENGINEERING-->KDTP-1-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-19 23:59 | 2020-03-19 17:40 | 2020-07-01 09:00 | 2020-07-15 18:00 |  |  | 2020-02-21 15:37 | 2020-07-15 20:59 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-GA-0005 |  | 2020-02-13 11:41 | 7012-155-PVC-B-018 |  |  |  | A |  |  |  | 91.3386 | 0.011811 | 1.16 | Plan & Actual | Date |  | 0 | 0 | 0 | 431.02 | 0 | 38.3 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2523 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-19 23:59 | 2020-04-17 18:00 |  | 10 | 2020-05-05 23:31 |  |  | 2020-02-06 17:40 | 2020-05-07 18:00 |  | 30 |  |  |  | 2020-02-13 17:40 | 2020-05-10 23:59 |  | 35 | 2020-06-29 10:36 |  |  | 2020-02-19 23:59 | 2020-05-17 23:59 |  | 65 | 2020-07-15 20:46 |  |  | 2020-02-26 17:40 | 2020-06-07 23:59 |  | 80 | 2020-07-15 20:54 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-19 17:40 | 2020-06-21 23:59 |  | 100 | 2020-07-15 21:00 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 119 |  |  |  |  | 101133
240 | Task(Task)-->E (Engineering) | ARCHITECTURAL GA OF TRANSFER POINT KDTP-1 |  | 1.4.1.3 | ARCHITECTURAL GA OF TRANSFER POINT KDTP-1-->STRUCTURAL-->ENGINEERING-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-08 18:00 | 2020-07-07 17:40 | 2020-07-01 18:00 | 2020-11-15 23:59 |  |  | 2020-02-21 15:39 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-AR-0002 |  | 2020-02-13 11:43 | 7012-155-PVC-C-108 |  |  |  | I |  |  |  | 8.6614 | 0.00112 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 40.52 | 0 | 73 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2522 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-05-08 18:00 | 2020-07-01 18:00 |  | 10 |  |  |  | 2020-05-27 17:40 | 2020-07-26 23:59 |  | 30 |  |  |  | 2020-06-02 17:40 | 2020-07-29 18:00 |  | 35 | 2020-09-16 19:09 |  |  | 2020-06-08 23:59 | 2020-08-05 18:00 |  | 65 | 2020-09-19 20:58 |  |  | 2020-06-15 17:40 | 2020-08-26 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-07-07 17:40 | 2020-09-09 18:00 |  | 100 | [122 empty] | Chetan Khodke | [5 empty] | A - Architecture | [16 empty] | 209 |  |  |  |  | 101219
241 | Task(Task)-->E (Engineering) | ELECTRICAL | 1.4.1.4 | 1.4.1 | ELECTRICAL-->ENGINEERING-->KDTP-1-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-01-09 18:00 | 2020-06-10 17:40 | 2020-03-02 09:00 | 2020-08-21 18:00 |  |  | 2020-02-17 17:40 |  |  |  | 100 | 75.7693 | [15 empty] | 20.4456 | 0.015884 | 1.56 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No | 2526 | 1 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036077
242 | Task(Task)-->E (Engineering) | GA,SLD,WIRING & BOM OF ILMS |  | 1.4.1.4 | GA,SLD,WIRING & BOM OF ILMS-->ELECTRICAL-->ENGINEERING-->KDTP-1-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-17 17:40 | 2020-03-30 17:40 | 2020-03-02 09:00 | 2020-04-02 18:00 |  |  | 2020-02-17 17:40 | 2020-04-18 12:40 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-401 |  | 2020-02-13 11:47 | 7012-155-PVE-W-137 |  |  |  | A |  |  |  | 7.0513 | 0.00112 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2529 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-16 23:59 | 2020-02-18 18:00 |  | 10 | 2020-02-18 23:31 |  |  | 2020-02-17 17:40 | 2020-02-25 18:00 |  | 30 | 2020-02-25 23:31 |  |  | 2020-02-24 17:40 | 2020-02-29 18:00 |  | 35 | 2020-02-29 23:31 |  |  | 2020-02-29 23:59 | 2020-03-02 18:00 |  | 65 | 2020-03-02 23:31 |  |  | 2020-03-06 17:40 | 2020-03-17 18:00 |  | 80 | 2020-03-17 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-30 17:40 | 2020-04-09 18:00 |  | 100 | 2020-04-09 23:31 | [121 empty] | Varun Parihari | [22 empty] | 372 |  |  |  |  | 101383
243 | Task(Task)-->E (Engineering) | DATASHEET & TERMINAL WIRING DIAGRAM FOR FLAP GATE |  | 1.4.1.4 | DATASHEET & TERMINAL WIRING DIAGRAM FOR FLAP GATE-->ELECTRICAL-->ENGINEERING-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-30 17:40 | 2020-06-10 17:40 | 2020-05-15 18:00 | 2020-08-21 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-405 |  | 2020-02-13 11:47 | 7012-155-PVE-W-141 |  |  |  | A |  |  |  | 7.0513 | 0.00112 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2530 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-30 18:00 | 2020-05-15 18:00 |  | 10 |  |  |  | 2020-04-30 17:40 | 2020-05-22 18:00 |  | 30 |  |  |  | 2020-05-06 17:40 | 2020-05-28 18:00 |  | 35 |  |  |  | 2020-05-13 23:59 | 2020-05-28 18:00 |  | 65 |  |  |  | 2020-05-19 17:40 | 2020-06-18 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-10 17:40 | 2020-06-18 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 376 |  |  |  |  | 101387
244 | Task(Task)-->E (Engineering) | EQUIPMENT, CABLE ROUTING, EARTHING & LIGHTNING LAYOUT WITH PLAN, SECTIONAL VIEWS & BOM OF KDTP-1 |  | 1.4.1.4 | EQUIPMENT, CABLE ROUTING, EARTHING & LIGHTNING LAYOUT WITH PLAN, SECTIONAL VIEWS & BOM OF KDTP-1-->ELECTRICAL-->ENGINEERING-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-09 18:00 | 2020-03-06 17:40 | 2020-04-18 18:00 | 2020-06-08 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5054 |  | 2020-02-13 11:44 | 7012-155-PVE-F-016 |  |  |  | A |  |  |  | 42.9487 | 0.006822 | 0.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 248.42 | 0 | 38.33 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2527 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-09 18:00 | 2020-04-18 18:00 |  | 10 | 2020-04-18 23:31 |  |  | 2020-01-25 17:40 | 2020-05-02 18:00 |  | 30 | 2020-05-12 23:31 |  |  | 2020-01-31 17:40 | 2020-05-09 18:00 |  | 35 | 2020-05-19 23:31 |  |  | 2020-02-06 23:59 | 2020-05-16 18:00 |  | 65 | 2020-05-29 23:31 |  |  | 2020-02-13 17:40 | 2020-06-06 18:00 |  | 80 | 2020-07-28 17:52 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-06 17:40 | 2020-06-06 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 251 |  |  |  |  | 101262
245 | Task(Task)-->E (Engineering) | LIGHTING LAYOUT PLAN WITH POWER DISTRIBUTION ARRANGEMENT, SECTIONAL VIEW, BOM OF KDTP-1 |  | 1.4.1.4 | LIGHTING LAYOUT PLAN WITH POWER DISTRIBUTION ARRANGEMENT, SECTIONAL VIEW, BOM OF KDTP-1-->ELECTRICAL-->ENGINEERING-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-16 18:00 | 2020-05-05 17:40 | 2020-04-29 18:00 | 2020-06-10 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5065 |  | 2020-02-13 11:44 | 7012-155-PVE-G-027 |  |  |  | A |  |  |  | 42.9487 | 0.006822 | 0.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 248.42 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2528 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-16 18:00 | 2020-04-29 18:00 |  | 10 | 2020-04-29 23:31 |  |  | 2020-03-24 17:40 | 2020-05-06 18:00 |  | 30 | 2020-05-02 23:31 |  |  | 2020-03-31 17:40 | 2020-05-13 18:00 |  | 35 | 2020-05-04 23:31 |  |  | 2020-04-06 23:59 | 2020-05-20 18:00 |  | 65 | 2020-05-05 23:31 |  |  | 2020-04-13 17:40 | 2020-06-10 18:00 |  | 80 | 2020-05-19 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-05 17:40 | 2020-06-10 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 262 |  |  |  |  | 101273
246 | Task(Task)-->P (Procurement) | PROCUREMENT | 1.4.2 | 1.4 | PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-09-27 09:00 | 2021-03-20 18:00 | 2019-09-27 09:00 | 2021-06-13 23:59 |  |  | 2019-09-27 10:57 |  |  |  | 87.1448 | 42.9141 | [15 empty] | 73.3172 | 2.986 | 293.65 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2532 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017901
247 | Task(Task)-->P (Procurement) | PURCHASE REQUISITION | 1.4.2.1 | 1.4.2 | PURCHASE REQUISITION-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-09-27 09:00 | 2020-03-27 18:00 | 2019-09-27 09:00 | 2020-05-29 18:00 |  |  | 2019-09-27 10:57 |  |  |  | 100 | 99.9321 | [15 empty] | 5.03 | 0.15019 | 14.77 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2533 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017902
248 | Task(Task)-->P (Procurement) | Secondary Sizer |  | 1.4.2.1 | Secondary Sizer-->PURCHASE REQUISITION-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Completed | No | No | 2019-09-27 09:00 | 2019-09-27 18:00 | 2019-09-27 09:00 | 2019-09-27 18:00 |  |  | 2019-09-27 10:57 | 2019-09-27 10:57 |  |  | 100 | 100 | [15 empty] | 56.157 | 0.084344 | 8.3 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2534 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017903
249 | Task(Task)-->P (Procurement) | ILMS |  | 1.4.2.1 | ILMS-->PURCHASE REQUISITION-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Completed | No | No | 2019-09-27 09:00 | 2019-09-27 18:00 | 2019-09-27 09:00 | 2019-09-27 18:00 |  |  | 2019-09-27 10:57 | 2019-09-27 10:57 |  |  | 100 | 100 | [15 empty] | 6.157 | 0.009247 | 0.91 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2535 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017904
250 | Task(Task)-->P (Procurement) | Flap Gate |  | 1.4.2.1 | Flap Gate-->PURCHASE REQUISITION-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-06 09:00 | 2020-02-06 18:00 | 2020-03-20 09:00 | 2020-03-20 18:00 |  |  | 2020-03-20 10:57 | 2020-03-20 10:57 |  |  | 100 | 100 | [15 empty] | 1.9621 | 0.002947 | 0.29 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2536 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017905
251 | Task(Task)-->P (Procurement) | Chute & Skirt |  | 1.4.2.1 | Chute & Skirt-->PURCHASE REQUISITION-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-10 09:00 | 2020-03-10 18:00 | 2020-03-11 09:00 | 2020-03-11 18:00 |  |  | 2020-03-11 10:57 | 2020-03-11 10:57 |  |  | 100 | 100 | [15 empty] | 5.8863 | 0.008841 | 0.87 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2537 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017906
252 | Task(Task)-->P (Procurement) | Building Structure |  | 1.4.2.1 | Building Structure-->PURCHASE REQUISITION-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-19 09:00 | 2020-02-19 18:00 | 2020-05-29 09:00 | 2020-05-29 18:00 |  |  | 2020-05-31 18:44 | 2020-05-31 18:44 |  |  | 100 | 100 | [15 empty] | 26.387 | 0.039631 | 3.9 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2538 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017907
253 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR CONVEYING SYSTEM |  | 1.4.2.1 | LT AC MOTORS FOR CONVEYING SYSTEM-->PURCHASE REQUISITION-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-16 09:00 | 2019-12-16 18:00 | 2020-01-13 09:00 | 2020-01-13 18:00 |  |  | 2020-01-13 10:57 | 2020-01-13 10:57 |  |  | 100 | 100 | [15 empty] | 0.54127 | 0.000813 | 0.08 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2539 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017908
254 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.4.2.1 | LIGHT & LIGHT FIXTURES-->PURCHASE REQUISITION-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-10 09:00 | 2020-03-10 18:00 | 2020-03-16 09:00 | 2020-03-16 18:00 |  |  | 2020-03-16 10:57 | 2020-03-16 10:57 |  |  | 100 | 100 | [15 empty] | 1.8268 | 0.002744 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2540 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017909
255 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.4.2.1 | LIGHTING POLES-->PURCHASE REQUISITION-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-27 09:00 | 2020-03-27 18:00 | 2020-04-30 09:00 | 2020-04-30 18:00 |  |  | 2020-04-30 10:57 | 2020-04-30 10:57 |  |  | 100 | 100 | [15 empty] | 0.81191 | 0.001219 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2541 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017910
256 | Task(Task)-->P (Procurement) | LPBS |  | 1.4.2.1 | LPBS-->PURCHASE REQUISITION-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-20 09:00 | 2020-03-20 18:00 | 2020-04-14 09:00 | 2020-04-14 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.067659 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2542 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017911
257 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.4.2.1 | CHUTE BLOCK SWITCH-->PURCHASE REQUISITION-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-03 09:00 | 2020-01-03 18:00 | 2020-01-03 09:00 | 2020-01-03 18:00 |  |  | 2020-01-03 10:57 | 2020-01-03 10:57 |  |  | 100 | 100 | [15 empty] | 0.067659 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2545 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017912
258 | Task(Task)-->P (Procurement) | CONTROL JUNCTION BOX |  | 1.4.2.1 | CONTROL JUNCTION BOX-->PURCHASE REQUISITION-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-05 09:00 | 2020-03-05 18:00 | 2020-04-18 09:00 | 2020-04-18 18:00 |  |  | 2020-04-18 10:57 | 2020-04-18 10:57 |  |  | 100 | 100 | [15 empty] | 0.13532 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2546 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017913
259 | Task(Task)-->P (Procurement) | TECHNICAL CLEARANCE | 1.4.2.2 | 1.4.2 | TECHNICAL CLEARANCE-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-09-28 09:00 | 2020-05-11 18:00 | 2019-09-27 09:00 | 2020-06-12 18:00 |  |  | 2019-11-07 10:57 |  |  |  | 100 | 99.9225 | [15 empty] | 4.4068 | 0.13158 | 12.94 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2547 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017914
260 | Task(Task)-->P (Procurement) | Secondary Sizer |  | 1.4.2.2 | Secondary Sizer-->TECHNICAL CLEARANCE-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Completed | No | No | 2019-09-28 09:00 | 2019-10-16 18:00 | 2019-09-27 09:00 | 2019-11-07 18:00 |  |  | 2019-11-07 10:57 | 2019-11-07 10:57 |  |  | 100 | 100 | [15 empty] | 49.9614 | 0.065741 | 6.47 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2548 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017915
261 | Task(Task)-->P (Procurement) | ILMS |  | 1.4.2.2 | ILMS-->TECHNICAL CLEARANCE-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Completed | No | No | 2019-09-28 09:00 | 2020-01-07 18:00 | 2019-09-27 09:00 | 2019-12-04 18:00 |  |  | 2019-12-04 10:57 | 2019-12-04 10:57 |  |  | 100 | 100 | [15 empty] | 7.027 | 0.009246 | 0.91 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2549 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017916
262 | Task(Task)-->P (Procurement) | Flap Gate |  | 1.4.2.2 | Flap Gate-->TECHNICAL CLEARANCE-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-07 09:00 | 2020-03-22 23:59 | 2020-03-20 09:00 | 2020-04-28 18:00 |  |  | 2020-04-28 10:57 | 2020-04-28 10:57 |  |  | 100 | 100 | [15 empty] | 2.2394 | 0.002947 | 0.29 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2550 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017917
263 | Task(Task)-->P (Procurement) | Chute & Skirt |  | 1.4.2.2 | Chute & Skirt-->TECHNICAL CLEARANCE-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-11 09:00 | 2020-03-20 18:00 | 2020-03-11 09:00 | 2020-03-17 18:00 |  |  | 2020-03-17 10:57 | 2020-03-17 10:57 |  |  | 100 | 100 | [15 empty] | 6.7181 | 0.00884 | 0.87 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2551 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017918
264 | Task(Task)-->P (Procurement) | Building Structure |  | 1.4.2.2 | Building Structure-->TECHNICAL CLEARANCE-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-20 09:00 | 2020-02-26 18:00 | 2020-05-29 09:00 | 2020-05-29 18:00 |  |  | 2020-05-29 17:31 | 2020-05-29 17:31 |  |  | 100 | 100 | [15 empty] | 30.1158 | 0.039628 | 3.9 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2552 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017919
265 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR CONVEYING SYSTEM |  | 1.4.2.2 | LT AC MOTORS FOR CONVEYING SYSTEM-->TECHNICAL CLEARANCE-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-17 09:00 | 2019-12-31 18:00 | 2020-01-13 09:00 | 2020-04-11 18:00 |  |  | 2020-04-11 10:57 | 2020-04-11 10:57 |  |  | 100 | 100 | [15 empty] | 0.61776 | 0.000813 | 0.08 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2553 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017920
266 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.4.2.2 | LIGHT & LIGHT FIXTURES-->TECHNICAL CLEARANCE-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-11 09:00 | 2020-03-25 18:00 | 2020-03-16 09:00 | 2020-06-02 18:00 |  |  | 2020-06-02 10:57 | 2020-06-02 10:57 |  |  | 100 | 100 | [15 empty] | 2.0849 | 0.002743 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2554 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017921
267 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.4.2.2 | LIGHTING POLES-->TECHNICAL CLEARANCE-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-28 09:00 | 2020-05-11 18:00 | 2020-04-30 09:00 | 2020-06-03 18:00 |  |  | 2020-06-03 10:57 | 2020-06-03 10:57 |  |  | 100 | 100 | [15 empty] | 0.92664 | 0.001219 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2555 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017922
268 | Task(Task)-->P (Procurement) | LPBS |  | 1.4.2.2 | LPBS-->TECHNICAL CLEARANCE-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-21 09:00 | 2020-04-04 18:00 | 2020-04-14 09:00 | 2020-06-12 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.07722 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2556 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017923
269 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.4.2.2 | CHUTE BLOCK SWITCH-->TECHNICAL CLEARANCE-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-04 09:00 | 2020-01-18 18:00 | 2020-01-03 09:00 | 2020-01-16 18:00 |  |  | 2020-01-16 10:57 | 2020-01-16 10:57 |  |  | 100 | 100 | [15 empty] | 0.07722 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2559 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017924
270 | Task(Task)-->P (Procurement) | CONTROL JUNCTION BOX |  | 1.4.2.2 | CONTROL JUNCTION BOX-->TECHNICAL CLEARANCE-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-06 09:00 | 2020-03-13 18:00 | 2020-04-18 09:00 | 2020-06-02 18:00 |  |  | 2020-06-02 10:57 | 2020-06-02 10:57 |  |  | 100 | 100 | [15 empty] | 0.15444 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2560 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017925
271 | Task(Task)-->P (Procurement) | ORDERING | 1.4.2.3 | 1.4.2 | ORDERING-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-10-17 09:00 | 2020-06-25 18:00 | 2019-11-07 09:00 | 2020-08-28 18:00 |  |  | 2020-02-01 10:57 |  |  |  | 100 | 99.7294 | [15 empty] | 10.0633 | 0.30049 | 29.55 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2561 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017926
272 | Task(Task)-->P (Procurement) | Secondary Sizer |  | 1.4.2.3 | Secondary Sizer-->ORDERING-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Completed | No | No | 2019-10-17 09:00 | 2019-11-20 18:00 | 2019-11-07 09:00 | 2020-02-25 18:00 |  |  | 2020-02-25 10:57 | 2020-02-25 10:57 |  |  | 100 | 100 | [15 empty] | 56.2098 | 0.1689 | 16.61 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2562 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017927
273 | Task(Task)-->P (Procurement) | ILMS |  | 1.4.2.3 | ILMS-->ORDERING-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-08 09:00 | 2020-02-06 18:00 | 2019-12-04 09:00 | 2020-02-03 18:00 |  |  | 2020-02-03 10:57 | 2020-02-03 10:57 |  |  | 100 | 100 | [15 empty] | 6.1591 | 0.018507 | 1.82 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2563 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017928
274 | Task(Task)-->P (Procurement) | Flap Gate |  | 1.4.2.3 | Flap Gate-->ORDERING-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-23 09:00 | 2020-04-21 18:00 | 2020-04-28 09:00 | 2020-08-28 18:00 |  |  | 2020-04-28 16:11 | 2020-08-22 16:11 |  |  | 100 | 100 | [15 empty] | 1.9289 | 0.005796 | 0.57 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2564 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017929
275 | Task(Task)-->P (Procurement) | Chute & Skirt |  | 1.4.2.3 | Chute & Skirt-->ORDERING-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-21 09:00 | 2020-04-19 23:59 | 2020-03-17 09:00 | 2020-07-06 18:00 |  |  | 2020-03-18 12:49 | 2020-07-06 12:49 |  |  | 100 | 100 | [15 empty] | 5.8545 | 0.017592 | 1.73 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2565 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017930
276 | Task(Task)-->P (Procurement) | Building Structure |  | 1.4.2.3 | Building Structure-->ORDERING-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-27 09:00 | 2020-03-27 18:00 | 2020-05-29 09:00 | 2020-05-31 23:59 |  |  | 2020-05-31 18:49 | 2020-05-31 18:49 |  |  | 100 | 100 | [15 empty] | 26.3959 | 0.079317 | 7.8 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2566 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017931
277 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR CONVEYING SYSTEM |  | 1.4.2.3 | LT AC MOTORS FOR CONVEYING SYSTEM-->ORDERING-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-01 09:00 | 2020-01-16 18:00 | 2020-04-11 09:00 | 2020-07-20 18:00 |  |  | 2020-04-12 15:47 | 2020-06-20 15:47 |  |  | 100 | 100 | [15 empty] | 0.54146 | 0.001627 | 0.16 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2567 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017932
278 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.4.2.3 | LIGHT & LIGHT FIXTURES-->ORDERING-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-26 09:00 | 2020-04-10 18:00 | 2020-06-02 09:00 | 2020-07-31 18:00 |  |  | 2020-06-03 15:51 | 2020-06-29 15:51 |  |  | 100 | 100 | [15 empty] | 1.7936 | 0.005389 | 0.53 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2568 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017933
279 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.4.2.3 | LIGHTING POLES-->ORDERING-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-12 09:00 | 2020-06-25 18:00 | 2020-06-03 09:00 | 2020-06-24 18:00 |  |  | 2020-06-15 10:57 | 2020-06-15 10:57 |  |  | 100 | 100 | [15 empty] | 0.81218 | 0.002441 | 0.24 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2569 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017934
280 | Task(Task)-->P (Procurement) | LPBS |  | 1.4.2.3 | LPBS-->ORDERING-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-05 | 2020-04-20 18:00 | 2020-06-12 09:00 | 2020-08-19 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.10152 | 0.000305 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2570 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017935
281 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.4.2.3 | CHUTE BLOCK SWITCH-->ORDERING-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-19 | 2020-01-31 18:00 | 2020-01-16 09:00 | 2020-02-01 18:00 |  |  | 2020-02-01 10:57 | 2020-02-01 10:57 |  |  | 100 | 100 | [15 empty] | 0.033841 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5611 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017936
282 | Task(Task)-->P (Procurement) | CONTROL JUNCTION BOX |  | 1.4.2.3 | CONTROL JUNCTION BOX-->ORDERING-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-14 09:00 | 2020-03-21 18:00 | 2020-06-02 09:00 | 2020-08-19 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.1692 | 0.000508 | 0.05 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2574 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017937
283 | Task(Task)-->P (Procurement) | ITP APPROVAL | 1.4.2.4 | 1.4.2 | ITP APPROVAL-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-09-27 09:00 | 2020-08-04 18:00 | 2020-02-03 09:00 | 2020-11-30 18:00 |  |  | 2020-02-03 15:18 |  |  |  | 100 | 9.4725 | [15 empty] | 5.03 | 0.15019 | 14.77 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2575 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017938
284 | Task(Task)-->P (Procurement) | Secondary Sizer |  | 1.4.2.4 | Secondary Sizer-->ITP APPROVAL-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-11-21 09:00 | 2019-12-30 18:00 | 2020-02-25 09:00 | 2020-11-15 23:59 | [6 empty] | 100 | 0 | [15 empty] | 56.157 | 0.084344 | 8.3 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2576 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017939
285 | Task(Task)-->P (Procurement) | ILMS |  | 1.4.2.4 | ILMS-->ITP APPROVAL-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-07 09:00 | 2020-03-17 18:00 | 2020-02-03 09:00 | 2020-02-24 18:00 |  |  | 2020-02-03 15:18 | 2020-02-24 15:18 |  |  | 100 | 100 | [15 empty] | 6.157 | 0.009247 | 0.91 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2577 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017940
286 | Task(Task)-->P (Procurement) | Flap Gate |  | 1.4.2.4 | Flap Gate-->ITP APPROVAL-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-22 09:00 | 2020-05-31 23:59 | 2020-08-22 09:00 | 2020-11-30 18:00 |  |  | 2020-08-22 16:15 |  |  |  | 100 | 0 | [15 empty] | 1.9621 | 0.002947 | 0.29 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2578 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017941
287 | Task(Task)-->P (Procurement) | Chute & Skirt |  | 1.4.2.4 | Chute & Skirt-->ITP APPROVAL-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-20 09:00 | 2020-05-29 18:00 | 2020-07-06 09:00 | 2020-07-16 18:00 | [6 empty] | 100 | 0 | [15 empty] | 5.8863 | 0.008841 | 0.87 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2579 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017942
288 | Task(Task)-->P (Procurement) | Building Structure |  | 1.4.2.4 | Building Structure-->ITP APPROVAL-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-28 09:00 | 2020-04-03 18:00 | 2020-05-31 | 2020-08-04 18:00 |  |  | 2020-06-25 19:04 |  |  |  | 100 | 0 | [15 empty] | 26.387 | 0.039631 | 3.9 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2580 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017943
289 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR CONVEYING SYSTEM |  | 1.4.2.4 | LT AC MOTORS FOR CONVEYING SYSTEM-->ITP APPROVAL-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-17 09:00 | 2020-02-25 18:00 | 2020-09-08 09:00 | 2020-10-14 18:00 |  |  | 2020-09-08 15:13 | 2020-10-14 15:13 |  |  | 100 | 100 | [15 empty] | 0.54127 | 0.000813 | 0.08 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2581 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017944
290 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.4.2.4 | LIGHT & LIGHT FIXTURES-->ITP APPROVAL-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-11 09:00 | 2020-05-20 18:00 | 2020-07-28 09:00 | 2020-09-08 18:00 |  |  | 2020-07-08 17:23 | 2020-09-08 17:23 |  |  | 100 | 100 | [15 empty] | 1.8268 | 0.002744 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2582 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017945
291 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.4.2.4 | LIGHTING POLES-->ITP APPROVAL-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Completed | No | No | 2020-06-26 09:00 | 2020-08-04 18:00 | 2020-06-23 09:00 | 2020-09-08 18:00 |  |  | 2020-06-23 17:26 | 2020-09-08 17:05 |  |  | 100 | 100 | [15 empty] | 0.81191 | 0.001219 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2583 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017946
292 | Task(Task)-->P (Procurement) | LPBS |  | 1.4.2.4 | LPBS-->ITP APPROVAL-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-21 09:00 | 2020-05-30 18:00 | 2020-07-29 09:00 | 2020-08-21 18:00 |  |  | 2020-07-29 14:56 | 2020-08-22 12:53 |  |  | 100 | 100 | [15 empty] | 0.067659 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2584 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017947
293 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.4.2.4 | CHUTE BLOCK SWITCH-->ITP APPROVAL-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Completed | No | No | 2019-09-27 09:00 | 2019-11-05 18:00 | 2020-07-02 09:00 | 2020-08-04 18:00 |  |  | 2020-07-17 16:57 | 2020-08-04 16:57 |  |  | 100 | 100 | [15 empty] | 0.067659 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2587 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017948
294 | Task(Task)-->P (Procurement) | CONTROL JUNCTION BOX |  | 1.4.2.4 | CONTROL JUNCTION BOX-->ITP APPROVAL-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-22 | 2020-04-30 18:00 | 2020-07-29 09:00 | 2020-09-21 18:00 |  |  | 2020-07-29 14:52 |  |  |  | 100 | 0 | [15 empty] | 0.13532 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2588 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017949
295 | Task(Task)-->P (Procurement) | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE | 1.4.2.5 | 1.4.2 | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-09-27 09:00 | 2020-09-16 18:00 | 2020-02-01 09:00 | 2020-11-16 18:00 |  |  | 2020-02-04 12:46 |  |  |  | 100 | 69.9956 | [15 empty] | 15.0933 | 0.45068 | 44.32 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2589 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017950
296 | Task(Task)-->P (Procurement) | Secondary Sizer |  | 1.4.2.5 | Secondary Sizer-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-21 09:00 | 2020-02-18 18:00 | 2020-02-25 09:00 | 2020-06-22 18:00 |  |  | 2020-02-26 14:50 | 2020-06-22 14:50 |  |  | 100 | 100 | [15 empty] | 56.1922 | 0.25325 | 24.91 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2590 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017951
297 | Task(Task)-->P (Procurement) | ILMS |  | 1.4.2.5 | ILMS-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-07 09:00 | 2020-04-06 18:00 | 2020-02-03 09:00 | 2020-04-24 18:00 |  |  | 2020-02-04 12:46 | 2020-04-24 10:57 |  |  | 100 | 100 | [15 empty] | 6.1584 | 0.027755 | 2.73 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2591 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017952
298 | Task(Task)-->P (Procurement) | Flap Gate |  | 1.4.2.5 | Flap Gate-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-22 09:00 | 2020-06-20 18:00 | 2020-08-22 09:00 | 2020-11-15 23:59 |  |  | 2020-08-22 16:13 |  |  |  | 100 | 15 | [15 empty] | 1.94 | 0.008743 | 0.86 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2592 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017953
299 | Task(Task)-->P (Procurement) | Chute & Skirt |  | 1.4.2.5 | Chute & Skirt-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-20 09:00 | 2020-09-16 18:00 | 2020-07-06 09:00 | 2020-07-06 18:00 |  |  | 2020-07-06 12:51 | 2020-07-06 12:51 |  |  | 100 | 100 | [15 empty] | 5.8651 | 0.026433 | 2.6 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2593 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017954
300 | Task(Task)-->P (Procurement) | Building Structure |  | 1.4.2.5 | Building Structure-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-26 09:00 | 2020-04-01 18:00 | 2020-05-31 | 2020-07-25 18:00 | [6 empty] | 100 | 0 | [15 empty] | 26.393 | 0.11895 | 11.7 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2594 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017955
301 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR CONVEYING SYSTEM |  | 1.4.2.5 | LT AC MOTORS FOR CONVEYING SYSTEM-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-17 09:00 | 2020-03-01 23:59 | 2020-07-07 09:00 | 2020-09-29 18:00 |  |  | 2020-07-07 10:15 | 2020-09-21 12:52 |  |  | 100 | 100 | [15 empty] | 0.54139 | 0.00244 | 0.24 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2595 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017956
302 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.4.2.5 | LIGHT & LIGHT FIXTURES-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-11 09:00 | 2020-05-25 18:00 | 2020-07-10 09:00 | 2020-11-16 18:00 |  |  | 2020-07-14 10:44 |  |  |  | 100 | 0 | [15 empty] | 1.8046 | 0.008133 | 0.8 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2596 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017957
303 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.4.2.5 | LIGHTING POLES-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Completed | No | No | 2020-06-26 09:00 | 2020-08-09 23:59 | 2020-05-30 09:00 | 2020-08-08 18:00 |  |  | 2020-06-18 17:04 | 2020-08-07 15:00 |  |  | 100 | 100 | [15 empty] | 0.81209 | 0.00366 | 0.36 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2597 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017958
304 | Task(Task)-->P (Procurement) | LPBS |  | 1.4.2.5 | LPBS-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-21 09:00 | 2020-06-04 18:00 | 2020-07-25 09:00 | 2020-08-22 18:00 |  |  | 2020-07-24 18:37 | 2020-08-22 12:57 |  |  | 100 | 100 | [15 empty] | 0.090232 | 0.000407 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2598 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017959
305 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.4.2.5 | CHUTE BLOCK SWITCH-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Completed | No | No | 2019-09-27 09:00 | 2019-11-10 23:59 | 2020-02-01 09:00 | 2020-07-15 18:00 |  |  | 2020-02-11 21:25 | 2020-07-15 21:25 |  |  | 100 | 100 | [15 empty] | 0.045116 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2601 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017960
306 | Task(Task)-->P (Procurement) | CONTROL JUNCTION BOX |  | 1.4.2.5 | CONTROL JUNCTION BOX-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-22 | 2020-05-05 18:00 | 2020-07-25 09:00 | 2020-11-10 18:00 |  |  | 2020-07-25 12:52 |  |  |  | 100 | 0 | [15 empty] | 0.15791 | 0.000712 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2602 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017961
307 | Task(Task)-->P (Procurement) | MANUFACTURING & RECEIPT AT SITE (MRN) | 1.4.2.6 | 1.4.2 | MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-11-11 09:00 | 2021-03-20 18:00 | 2020-04-24 09:00 | 2021-06-13 23:59 |  |  | 2020-04-24 15:19 |  |  |  | 78.7083 | 20.5494 | [15 empty] | 60.3767 | 1.8028 | 177.29 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2603 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017962
308 | Task(Task)-->P (Procurement) | Secondary Sizer |  | 1.4.2.6 | Secondary Sizer-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-19 09:00 | 2021-03-20 18:00 | 2020-06-22 09:00 | 2021-03-20 18:00 |  |  | 2020-06-22 01:45 |  |  |  | 67.1717 | 30 | [15 empty] | 56.2017 | 1.0132 | 99.64 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2604 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017963
309 | Task(Task)-->P (Procurement) | ILMS |  | 1.4.2.6 | ILMS-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-07 09:00 | 2020-10-03 18:00 | 2020-04-24 09:00 | 2020-11-15 23:59 |  |  | 2020-04-24 15:19 |  |  |  | 100 | 60 | [15 empty] | 6.1481 | 0.11084 | 10.9 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2605 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017964
310 | Task(Task)-->P (Procurement) | Flap Gate |  | 1.4.2.6 | Flap Gate-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-21 | 2021-01-01 18:00 | 2020-12-01 09:00 | 2021-06-13 23:59 | [6 empty] | 73.3333 | 0 | [15 empty] | 1.9403 | 0.034981 | 3.44 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2606 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017965
311 | Task(Task)-->P (Procurement) | Chute & Skirt |  | 1.4.2.6 | Chute & Skirt-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-19 09:00 | 2021-02-13 18:00 | 2020-07-06 09:00 | 2021-01-31 23:59 | [6 empty] | 60.4167 | 0 | [15 empty] | 5.8717 | 0.10586 | 10.41 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2607 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017966
312 | Task(Task)-->P (Procurement) | Building Structure |  | 1.4.2.6 | Building Structure-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-04 09:00 | 2020-10-05 18:00 | 2020-07-25 09:00 | 2020-12-31 18:00 | [6 empty] | 100 | 0 | [15 empty] | 26.3974 | 0.4759 | 46.8 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2608 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017967
313 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR CONVEYING SYSTEM |  | 1.4.2.6 | LT AC MOTORS FOR CONVEYING SYSTEM-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-02 09:00 | 2020-09-26 18:00 | 2020-10-15 09:00 | 2021-05-11 18:00 |  |  | 2020-09-22 12:54 |  |  |  | 100 | 0 | [15 empty] | 0.55277 | 0.009965 | 0.98 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2609 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017968
314 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.4.2.6 | LIGHT & LIGHT FIXTURES-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-26 09:00 | 2020-10-21 18:00 | 2020-11-17 09:00 | 2021-04-14 18:00 | [6 empty] | 100 | 0 | [15 empty] | 1.7993 | 0.032438 | 3.19 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2610 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017969
315 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.4.2.6 | LIGHTING POLES-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-10 09:00 | 2020-11-07 18:00 | 2020-09-09 09:00 | 2020-12-07 18:00 |  |  | 2020-08-07 15:00 |  |  |  | 100 | 0 | [15 empty] | 0.81787 | 0.014745 | 1.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2611 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017970
316 | Task(Task)-->P (Procurement) | LPBS |  | 1.4.2.6 | LPBS-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-05 09:00 | 2020-09-16 18:00 | 2020-08-23 | 2020-12-04 18:00 |  |  | 2020-08-22 13:00 |  |  |  | 100 | 0 | [15 empty] | 0.084607 | 0.001525 | 0.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2612 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017971
317 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.4.2.6 | CHUTE BLOCK SWITCH-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-11-11 09:00 | 2020-03-09 18:00 | 2020-07-02 09:00 | 2020-10-29 18:00 |  |  | 2020-07-15 21:33 |  |  |  | 100 | 0 | [15 empty] | 0.033843 | 0.00061 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2615 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017972
318 | Task(Task)-->P (Procurement) | CONTROL JUNCTION BOX |  | 1.4.2.6 | CONTROL JUNCTION BOX-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-06 09:00 | 2020-09-16 18:00 | 2020-11-11 09:00 | 2021-03-24 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.15229 | 0.002746 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2616 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017973
319 | Task(Task)-->C (Construction) | CONSTRUCTION | 1.4.3 | 1.4 | CONSTRUCTION-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-08 09:00 | 2021-08-28 18:00 | 2020-09-08 09:00 | 2022-04-20 18:00 |  |  | 2020-09-07 15:50 |  |  |  | 38.0134 | 0.92253 | [15 empty] | 24.7753 | 1.009 | 99.23 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2617 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017974
320 | Task(Task)-->C (Construction) | CIVIL | 1.4.3.1 | 1.4.3 | CIVIL-->CONSTRUCTION-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-08 09:00 | 2021-03-21 23:59 | 2020-09-08 09:00 | 2021-08-23 18:00 |  |  | 2020-09-07 15:50 |  |  |  | 36.1986 | 2.1329 | [15 empty] | 43.253 | 0.43643 | 42.92 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2618 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017975
321 | Task(Task)-->C (Construction) | AVAILABILITY OF FRONT BY NTPC |  | 1.4.3.1 | AVAILABILITY OF FRONT BY NTPC-->CIVIL-->CONSTRUCTION-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-08 09:00 | 2020-04-08 18:00 | 2020-09-08 09:00 | 2020-11-10 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2619 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017976
322 | Task(Task)-->C (Construction) | EXCAVATION |  | 1.4.3.1 | EXCAVATION-->CIVIL-->CONSTRUCTION-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-15 09:00 | 2020-04-29 18:00 | 2020-10-08 09:00 | 2020-11-22 23:59 |  |  | 2020-09-07 15:50 |  |  |  | 100 | 39.1294 | [15 empty] | 5.4507 | 0.023789 | 2.34 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 8753 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2620 | 0 | 4 | Low | Niharendu Kamle | [6 empty] | 0 | 0 | [222 empty] | Excavation | Construction-Civil | [22 empty] | 1017977
323 | Task(Task)-->C (Construction) | PCC |  | 1.4.3.1 | PCC-->CIVIL-->CONSTRUCTION-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-16 09:00 | 2020-05-21 18:00 | 2020-10-18 | 2020-10-23 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.76869 | 0.003355 | 0.33 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2621 | 0 | 4 | Low | ADMINISTRATOR | [6 empty] | 0 | 0 | [222 empty] | PCC | [23 empty] | 1017978
324 | Task(Task)-->C (Construction) | RAFT |  | 1.4.3.1 | RAFT-->CIVIL-->CONSTRUCTION-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-22 09:00 | 2020-06-03 18:00 | 2020-10-24 09:00 | 2020-11-05 18:00 | [6 empty] | 100 | 0 | [15 empty] | 21.6399 | 0.094443 | 9.29 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2622 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017979
325 | Task(Task)-->C (Construction) | PADESTALS FOR KDTP-1 STR. |  | 1.4.3.1 | PADESTALS FOR KDTP-1 STR.-->CIVIL-->CONSTRUCTION-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-04 09:00 | 2020-06-24 18:00 | 2020-11-06 09:00 | 2020-11-26 18:00 | [6 empty] | 100 | 0 | [15 empty] | 4.6355 | 0.020231 | 1.99 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2623 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017980
326 | Task(Task)-->C (Construction) | SECONDARY SIZER FOUNDATION WITH SLAB |  | 1.4.3.1 | SECONDARY SIZER FOUNDATION WITH SLAB-->CIVIL-->CONSTRUCTION-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-10-21 09:00 | 2020-11-05 18:00 | 2021-03-25 09:00 | 2021-04-09 18:00 | [6 empty] | 100 | 0 | [15 empty] | 3.7037 | 0.016164 | 1.59 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2625 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017981
327 | Task(Task)-->C (Construction) | HEAD PULLEY FLOOR OF SC 1A/B & SC 2A/B |  | 1.4.3.1 | HEAD PULLEY FLOOR OF SC 1A/B & SC 2A/B-->CIVIL-->CONSTRUCTION-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-01-19 09:00 | 2021-01-29 18:00 | 2021-06-23 09:00 | 2021-07-03 18:00 | [6 empty] | 0 | 0 | [15 empty] | 3.7037 | 0.016164 | 1.59 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2626 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017982
328 | Task(Task)-->C (Construction) | GRADE SLAB FOR TAIL PULLEY OF SC 3 A/B |  | 1.4.3.1 | GRADE SLAB FOR TAIL PULLEY OF SC 3 A/B-->CIVIL-->CONSTRUCTION-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-01-30 09:00 | 2021-03-21 23:59 | 2021-07-04 | 2021-08-23 18:00 | [6 empty] | 0 | 0 | [15 empty] | 60.0978 | 0.26228 | 25.8 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 1378 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2628 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017983
329 | Task(Task)-->C (Construction) | STRUCTURAL WORKS | 1.4.3.2 | 1.4.3 | STRUCTURAL WORKS-->CONSTRUCTION-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-23 09:00 | 2021-03-04 18:00 | 2020-12-25 09:00 | 2021-08-06 18:00 | [6 empty] | 58.318 | 0 | [15 empty] | 38.3352 | 0.38681 | 38.04 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2629 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017984
330 | Task(Task)-->C (Construction) | STRL. ERECTION FOR RCC CASTING UP TO SECONDARY SIZER FLOOR & FOUNDATION |  | 1.4.3.2 | STRL. ERECTION FOR RCC CASTING UP TO SECONDARY SIZER FLOOR & FOUNDATION-->STRUCTURAL WORKS-->CONSTRUCTION-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-23 09:00 | 2020-10-20 18:00 | 2020-12-25 09:00 | 2021-03-24 18:00 | [6 empty] | 100 | 0 | [15 empty] | 49.1454 | 0.1901 | 18.69 | Plan & Actual | Quantity | Metric Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 289 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2630 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017985
331 | Task(Task)-->C (Construction) | STRL. ERECTION FOR RCC CASTING UP TO HEAD PULLEY (SC 1A/B & SC 2A/B) FLOOR |  | 1.4.3.2 | STRL. ERECTION FOR RCC CASTING UP TO HEAD PULLEY (SC 1A/B & SC 2A/B) FLOOR-->STRUCTURAL WORKS-->CONSTRUCTION-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-10-21 09:00 | 2021-01-18 18:00 | 2021-03-25 09:00 | 2021-06-22 18:00 | [6 empty] | 23.3333 | 0 | [15 empty] | 39.3111 | 0.15206 | 14.95 | Plan & Actual | Quantity | Metric Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 231 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2631 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017986
332 | Task(Task)-->C (Construction) | BALANCE STRUCTURAL ERECTION |  | 1.4.3.2 | BALANCE STRUCTURAL ERECTION-->STRUCTURAL WORKS-->CONSTRUCTION-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-01-19 09:00 | 2021-03-04 18:00 | 2021-06-23 09:00 | 2021-08-06 18:00 | [6 empty] | 0 | 0 | [15 empty] | 11.5435 | 0.044651 | 4.39 | Plan & Actual | Quantity | Metric Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2632 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017987
333 | Task(Task)-->C (Construction) | MECHANICAL EQUIPMENT WORKS | 1.4.3.3 | 1.4.3 | MECHANICAL EQUIPMENT WORKS-->CONSTRUCTION-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-03-05 09:00 | 2021-06-18 18:00 | 2021-05-08 09:00 | 2021-09-14 18:00 | [6 empty] | 0 | 0 | [15 empty] | 9.1404 | 0.092228 | 9.07 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5449 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017988
334 | Task(Task)-->C (Construction) | ERECTION OF SECONDARY SIZER |  | 1.4.3.3 | ERECTION OF SECONDARY SIZER-->MECHANICAL EQUIPMENT WORKS-->CONSTRUCTION-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-03-21 | 2021-05-04 18:00 | 2021-05-08 09:00 | 2021-06-21 18:00 | [6 empty] | 0 | 0 | [15 empty] | 77.398 | 0.071383 | 7.02 | Plan & Actual | Quantity | Metric Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 191 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2633 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017989
335 | Task(Task)-->C (Construction) | ERECTION OF CHUTES/ HOODS & SUPPORTS |  | 1.4.3.3 | ERECTION OF CHUTES/ HOODS & SUPPORTS-->MECHANICAL EQUIPMENT WORKS-->CONSTRUCTION-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-05-05 09:00 | 2021-06-18 18:00 | 2021-08-01 | 2021-09-14 18:00 | [6 empty] | 0 | 0 | [15 empty] | 19.4046 | 0.017897 | 1.76 | Plan & Actual | Quantity | Metric Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2634 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017990
336 | Task(Task)-->C (Construction) | ERECTION OF ILMS |  | 1.4.3.3 | ERECTION OF ILMS-->MECHANICAL EQUIPMENT WORKS-->CONSTRUCTION-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-03-05 09:00 | 2021-03-18 18:00 | 2021-08-07 09:00 | 2021-08-20 18:00 | [6 empty] | 0 | 0 | [15 empty] | 3.1974 | 0.002949 | 0.29 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5406 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017991
337 | Task(Task)-->C (Construction) | ELECTRICAL & INSTRUMENTATION WORKS | 1.4.3.4 | 1.4.3 | ELECTRICAL & INSTRUMENTATION WORKS-->CONSTRUCTION-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-02-25 09:00 | 2021-08-25 18:00 | 2021-07-30 09:00 | 2022-04-17 23:59 | [6 empty] | 0 | 0 | [15 empty] | 7.7194 | 0.07789 | 7.66 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2636 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017992
338 | Task(Task)-->C (Construction) | CABLE TRAY |  | 1.4.3.4 | CABLE TRAY-->ELECTRICAL & INSTRUMENTATION WORKS-->CONSTRUCTION-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-02-25 09:00 | 2021-03-11 18:00 | 2021-07-30 09:00 | 2021-08-13 18:00 | [6 empty] | 0 | 0 | [15 empty] | 8.366 | 0.006516 | 0.64 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2637 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017993
339 | Task(Task)-->C (Construction) | POWER CABLE |  | 1.4.3.4 | POWER CABLE-->ELECTRICAL & INSTRUMENTATION WORKS-->CONSTRUCTION-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-03-12 09:00 | 2021-03-21 23:59 | 2021-08-14 09:00 | 2021-08-23 18:00 | [6 empty] | 0 | 0 | [15 empty] | 32.6797 | 0.025454 | 2.5 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 17687 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2638 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017994
340 | Task(Task)-->C (Construction) | C&I CABLE |  | 1.4.3.4 | C&I CABLE-->ELECTRICAL & INSTRUMENTATION WORKS-->CONSTRUCTION-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-03-17 09:00 | 2021-03-21 23:59 | 2021-10-26 09:00 | 2021-10-30 18:00 | [6 empty] | 0 | 0 | [15 empty] | 30.719 | 0.023927 | 2.35 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 16600 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5283 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017995
341 | Task(Task)-->C (Construction) | EARTHING |  | 1.4.3.4 | EARTHING-->ELECTRICAL & INSTRUMENTATION WORKS-->CONSTRUCTION-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-03-07 | 2021-03-11 18:00 | 2021-08-09 09:00 | 2021-08-13 18:00 | [6 empty] | 0 | 0 | [15 empty] | 2.4837 | 0.001935 | 0.19 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 873 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5284 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017996
342 | Task(Task)-->C (Construction) | EARTH PIT |  | 1.4.3.4 | EARTH PIT-->ELECTRICAL & INSTRUMENTATION WORKS-->CONSTRUCTION-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-03-19 09:00 | 2021-03-21 23:59 | 2021-08-21 09:00 | 2021-08-23 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5285 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017997
343 | Task(Task)-->C (Construction) | LIGHTING |  | 1.4.3.4 | LIGHTING-->ELECTRICAL & INSTRUMENTATION WORKS-->CONSTRUCTION-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-02-28 | 2021-03-14 23:59 | 2021-08-02 09:00 | 2021-08-16 18:00 | [6 empty] | 0 | 0 | [15 empty] | 13.7255 | 0.010691 | 1.05 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 108 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5286 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017998
344 | Task(Task)-->C (Construction) | FIELD INTRUMENTS |  | 1.4.3.4 | FIELD INTRUMENTS-->ELECTRICAL & INSTRUMENTATION WORKS-->CONSTRUCTION-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-03-19 09:00 | 2021-03-22 18:00 | 2021-10-28 09:00 | 2021-10-31 23:59 | [6 empty] | 0 | 0 | [15 empty] | 12.0261 | 0.009367 | 0.92 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5287 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1017999
345 | Task(Task)-->C (Construction) | MOTOR TERMINATION |  | 1.4.3.4 | MOTOR TERMINATION-->ELECTRICAL & INSTRUMENTATION WORKS-->CONSTRUCTION-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-05-19 09:00 | 2021-05-25 18:00 | 2022-01-02 | 2022-01-08 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5288 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018000
346 | Task(Task)-->C (Construction) | NO LOAD RUN OF MOTOR |  | 1.4.3.4 | NO LOAD RUN OF MOTOR-->ELECTRICAL & INSTRUMENTATION WORKS-->CONSTRUCTION-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-08-22 | 2021-08-25 18:00 | 2022-04-14 09:00 | 2022-04-17 23:59 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5450 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018001
347 | Task(Task)-->C (Construction) | NO LOAD COMMISSIONING & SYSTEM READYNESS FOR LOAD & TRIAL OPERATION |  | 1.4.3 | NO LOAD COMMISSIONING & SYSTEM READYNESS FOR LOAD & TRIAL OPERATION-->CONSTRUCTION-->KDTP-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-08-13 09:00 | 2021-08-28 18:00 | 2022-04-05 09:00 | 2022-04-20 18:00 | [6 empty] | 0 | 0 | [15 empty] | 1.552 | 0.015659 | 1.54 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2639 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018002
348 | Task(Task)-->E (Engineering) | TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B | 1.5 | 1 | TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-09-27 09:00 | 2021-09-08 18:00 | 2019-09-27 09:00 | 2022-05-01 23:59 |  |  | 2019-09-27 10:57 |  |  |  | 77.9367 | 34.0729 | [15 empty] | 2.1555 | 2.1555 | 211.98 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2641 | 0 | 1 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018003
349 | Task(Task)-->E (Engineering) | ENGINEERING | 1.5.1 | 1.5 | ENGINEERING-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-10-02 18:00 | 2020-08-14 17:40 | 2019-10-20 23:59 | 2020-10-09 18:00 |  |  | 2019-11-02 17:40 |  |  |  | 100 | 90.9886 | [15 empty] | 6.2792 | 0.13535 | 13.31 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2642 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018004
350 | Task(Task)-->E (Engineering) | MECHANICAL | 1.5.1.1 | 1.5.1 | MECHANICAL-->ENGINEERING-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-10-02 18:00 | 2020-08-14 17:40 | 2019-10-20 23:59 | 2020-10-09 18:00 |  |  | 2019-11-02 17:40 |  |  |  | 100 | 95.1065 | [15 empty] | 54.3077 | 0.073504 | 7.06 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No | 2643 | 3 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036078
351 | Task(Task)-->E (Engineering) | SELECTION OF BELT AND DRIVE COMPONENTS FOR TROUGH BELTS CONVEYORS |  | 1.5.1.1 | SELECTION OF BELT AND DRIVE COMPONENTS FOR TROUGH BELTS CONVEYORS-->MECHANICAL-->ENGINEERING-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-14 17:40 | 2019-12-23 17:40 | 2020-01-06 09:00 | 2020-02-17 18:00 |  |  | 2019-11-14 17:40 | 2020-03-04 10:30 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-CS-DC-0012 |  | 2020-02-13 10:26 | 7012-155-PVM-B-012 |  |  |  | A |  |  |  | 1.4589 | 0.001072 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2649 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-11-08 18:00 | 2019-12-19 18:00 |  | 10 | 2019-12-19 23:31 |  |  | 2019-11-14 17:40 | 2020-01-03 18:00 |  | 30 | 2020-01-03 23:31 |  |  | 2019-11-20 17:40 | 2020-01-03 18:00 |  | 35 | 2020-01-03 23:31 |  |  | 2019-11-26 23:59 | 2020-01-06 18:00 |  | 65 | 2020-01-06 23:31 |  |  | 2019-12-02 17:40 | 2020-02-17 18:00 |  | 80 | 2020-02-17 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2019-12-23 17:40 | 2020-02-17 18:00 |  | 100 | 2020-02-17 23:31 | [121 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 12 |  |  |  |  | 101026
352 | Task(Task)-->E (Engineering) | TROUGH BELT CONVEYOR PROFILES FOR SC 1A/B, SC 2A/B, SC 3A/B, SY 1A/B AND BELT FEEDER BF1/2 & BF3/4 |  | 1.5.1.1 | TROUGH BELT CONVEYOR PROFILES FOR SC 1A/B, SC 2A/B, SC 3A/B, SY 1A/B AND BELT FEEDER BF1/2 & BF3/4-->MECHANICAL-->ENGINEERING-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-10-21 18:00 | 2019-12-05 17:40 | 2019-11-13 09:00 | 2020-01-03 18:00 |  |  | 2020-06-15 17:24 | 2020-06-19 15:47 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-CS-GA-0013 |  | 2020-02-13 10:26 | 7012-155-PVM-B-013 |  |  |  | A |  |  |  | 1.4589 | 0.001072 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 40 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2644 | 1 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-10-21 18:00 | 2019-10-26 18:00 |  | 10 | 2019-10-26 23:31 |  |  | 2019-10-28 17:40 | 2019-11-10 23:59 |  | 30 | 2019-11-10 23:31 |  |  | 2019-11-02 17:40 | 2019-11-10 23:59 |  | 35 | 2019-11-10 23:31 |  |  | 2019-11-08 23:59 | 2019-11-13 18:00 |  | 65 | 2019-11-13 23:31 |  |  | 2019-11-14 17:40 | 2019-12-23 18:00 |  | 80 | 2019-12-23 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | 2020-06-15 17:24 | [5 empty] | 80 | 2020-06-15 17:24 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2019-12-05 17:40 | 2020-01-20 18:00 |  | 100 | 2020-01-20 23:31 | [121 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 13 |  |  |  |  | 101027
353 | Task(Task)-->E (Engineering) | COASTING TIME CALCULATION AND BRAKE REQUIREMENT FOR TROUGH BELT CONVEYORS |  | 1.5.1.1 | COASTING TIME CALCULATION AND BRAKE REQUIREMENT FOR TROUGH BELT CONVEYORS-->MECHANICAL-->ENGINEERING-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-11-07 18:00 | 2019-12-23 17:40 | 2020-04-07 18:00 | 2020-05-19 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-DC-0027 |  | 2020-02-13 10:26 | 7012-155-PVM-U-027 |  |  |  | A |  |  |  | 1.4589 | 0.001072 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 40 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2661 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-11-07 18:00 | 2020-04-07 18:00 |  | 10 | 2020-04-07 23:31 |  |  | 2019-11-14 17:40 | 2020-04-21 18:00 |  | 30 | 2020-04-21 23:31 |  |  | 2019-11-20 17:40 | 2020-04-26 23:59 |  | 35 | 2020-04-26 23:31 |  |  | 2019-11-26 23:59 | 2020-04-26 23:59 |  | 65 | 2020-04-28 23:31 |  |  | 2019-12-02 17:40 | 2020-05-17 23:59 |  | 80 | 2020-05-19 23:31 | [5 empty] | 80 | 2020-09-17 17:15 | [5 empty] | 80 | 2020-09-17 17:15 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2019-12-23 17:40 | 2020-05-17 23:59 |  | 100 | [122 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 27 |  |  |  |  | 101041
354 | Task(Task)-->E (Engineering) | G.A OF FLUID COUPLING WITH PERFORMANCE CURVES |  | 1.5.1.1 | G.A OF FLUID COUPLING WITH PERFORMANCE CURVES-->MECHANICAL-->ENGINEERING-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-19 18:00 | 2020-05-15 17:40 | 2020-07-31 09:00 | 2020-08-21 18:00 |  |  | 2020-02-21 14:04 | 2020-08-25 17:43 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1004 |  | 2020-02-13 10:27 | 7012-155-PVM-B-104 |  |  |  | A |  |  |  | 5.7029 | 0.004192 | 0.43 | Plan & Actual | Date |  | 0 | 0 | 0 | 160 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2664 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-19 18:00 | 2020-05-20 18:00 |  | 10 | 2020-05-29 23:31 |  |  | 2020-04-03 17:40 | 2020-06-03 18:00 |  | 30 |  |  |  | 2020-04-09 17:40 | 2020-06-10 18:00 |  | 35 |  |  |  | 2020-04-16 23:59 | 2020-06-17 18:00 |  | 65 | 2020-07-31 21:54 |  |  | 2020-04-22 17:40 | 2020-07-08 18:00 |  | 80 | 2020-08-25 11:16 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-15 17:40 | 2020-07-08 18:00 |  | 100 | 2020-08-25 17:44 | [121 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 34 |  |  |  |  | 101048
355 | Task(Task)-->E (Engineering) | SECTION VIEW, P&ID AND GA OF FLUID COUPLING |  | 1.5.1.1 | SECTION VIEW, P&ID AND GA OF FLUID COUPLING-->MECHANICAL-->ENGINEERING-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-19 18:00 | 2020-05-15 17:40 | 2020-07-31 09:00 | 2020-08-21 18:00 |  |  | 2020-02-21 14:04 | 2020-08-25 17:43 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1005 |  | 2020-02-13 10:27 | 7012-155-PVM-B-105 |  |  |  | I |  |  |  | 5.7029 | 0.004192 | 0.43 | Plan & Actual | Date |  | 0 | 0 | 0 | 160 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2665 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-19 18:00 | 2020-05-20 18:00 |  | 10 | 2020-05-29 23:31 |  |  | 2020-04-03 17:40 | 2020-06-03 18:00 |  | 30 |  |  |  | 2020-04-09 17:40 | 2020-06-10 18:00 |  | 35 |  |  |  | 2020-04-16 23:59 | 2020-06-17 18:00 |  | 65 | 2020-07-31 21:54 |  |  | 2020-04-22 17:40 | 2020-07-08 18:00 |  | 80 | 2020-08-25 11:17 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-15 17:40 | 2020-07-08 18:00 |  | 100 | 2020-08-25 17:44 | [121 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 35 |  |  |  |  | 101049
356 | Task(Task)-->E (Engineering) | GA & DIMENSION SHEET FOR TROUGHING IDLERS OF TROUGH BELT CONVEYOR |  | 1.5.1.1 | GA & DIMENSION SHEET FOR TROUGHING IDLERS OF TROUGH BELT CONVEYOR-->MECHANICAL-->ENGINEERING-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-20 18:00 | 2020-04-16 17:40 | 2020-05-29 09:00 | 2020-06-22 18:00 |  |  | 2020-02-21 14:04 | 2020-06-29 19:15 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1008 |  | 2020-02-13 10:27 | 7012-155-PVM-B-108 |  |  |  | I |  |  |  | 9.9469 | 0.007311 | 0.75 | Plan & Actual | Date |  | 0 | 0 | 0 | 280 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2650 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-20 18:00 | 2020-05-15 18:00 |  | 10 | 2020-05-11 23:31 |  |  | 2020-03-05 17:40 | 2020-06-05 18:00 |  | 30 | 2020-05-15 23:31 |  |  | 2020-03-11 17:40 | 2020-06-11 18:00 |  | 35 | 2020-05-18 23:31 |  |  | 2020-03-18 23:59 | 2020-06-11 18:00 |  | 65 | 2020-05-29 23:31 |  |  | 2020-03-24 17:40 | 2020-07-02 18:00 |  | 80 | 2020-06-24 06:47 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-16 17:40 | 2020-07-02 18:00 |  | 100 | 2020-06-29 19:16 | [121 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 38 |  |  |  |  | 101052
357 | Task(Task)-->E (Engineering) | GA & DIMENSION SHEET FOR IMPACT IDLER FOR TROUGH BELT CONVEYORS |  | 1.5.1.1 | GA & DIMENSION SHEET FOR IMPACT IDLER FOR TROUGH BELT CONVEYORS-->MECHANICAL-->ENGINEERING-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-20 18:00 | 2020-04-16 17:40 | 2020-06-06 09:00 | 2020-06-22 18:00 |  |  | 2020-02-21 14:04 | 2020-06-29 19:15 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1010 |  | 2020-02-13 10:27 | 7012-155-PVM-B-110 |  |  |  | I |  |  |  | 2.9178 | 0.002145 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 80 | 0 | 11.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2651 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-20 18:00 | 2020-05-18 18:00 |  | 10 | 2020-05-11 23:31 |  |  | 2020-03-05 17:40 | 2020-06-08 18:00 |  | 30 | 2020-05-23 23:31 |  |  | 2020-03-11 17:40 | 2020-06-14 23:59 |  | 35 | 2020-05-31 23:31 |  |  | 2020-03-18 23:59 | 2020-06-14 23:59 |  | 65 | 2020-06-08 18:43 |  |  | 2020-03-24 17:40 | 2020-07-05 23:59 |  | 80 | 2020-06-24 06:45 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-16 17:40 | 2020-07-05 23:59 |  | 100 | 2020-06-29 19:16 | [121 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 40 |  |  |  |  | 101054
358 | Task(Task)-->E (Engineering) | GA & DIMENSION SHEET FOR FLAT RETURN IDLER FOR TROUGH BELT CONVEYORS |  | 1.5.1.1 | GA & DIMENSION SHEET FOR FLAT RETURN IDLER FOR TROUGH BELT CONVEYORS-->MECHANICAL-->ENGINEERING-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-20 18:00 | 2020-04-16 17:40 | 2020-05-20 18:00 | 2020-07-07 18:00 |  |  | 2020-08-28 17:04 |  |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1012 |  | 2020-02-13 10:27 | 7012-155-PVM-B-112 |  |  |  | I |  |  |  | 2.9178 | 0.002145 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 80 | 0 | 9.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2652 | 1 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-20 18:00 | 2020-05-20 18:00 |  | 10 | 2020-05-11 23:31 |  |  | 2020-03-05 17:40 | 2020-06-10 18:00 |  | 30 | 2020-05-23 23:31 |  |  | 2020-03-11 17:40 | 2020-06-16 18:00 |  | 35 | 2020-05-31 23:31 |  |  | 2020-03-18 23:59 | 2020-06-16 18:00 |  | 65 | 2020-06-08 18:43 |  |  | 2020-03-24 17:40 | 2020-07-07 18:00 |  | 80 | 2020-06-24 06:47 | [5 empty] | 80 | 2020-08-28 17:04 | [5 empty] | 80 | 2020-08-28 17:04 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-16 17:40 | 2020-07-07 18:00 |  | 100 | 2020-06-29 19:16 | [121 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 42 |  |  |  |  | 101056
359 | Task(Task)-->E (Engineering) | GA & DIMENSION SHEET FOR V-RETURN IDLERS FOR TROUGH BELT CONVEYORS |  | 1.5.1.1 | GA & DIMENSION SHEET FOR V-RETURN IDLERS FOR TROUGH BELT CONVEYORS-->MECHANICAL-->ENGINEERING-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-20 18:00 | 2020-04-16 17:40 | 2020-06-15 09:00 | 2020-07-03 18:00 |  |  | 2020-02-21 14:04 | 2020-07-04 14:55 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1013 |  | 2020-02-13 10:27 | 7012-155-PVM-B-113 |  |  |  | I |  |  |  | 2.9178 | 0.002145 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 80 | 0 | 2.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2653 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-20 18:00 | 2020-05-26 18:00 |  | 10 | 2020-05-14 23:31 |  |  | 2020-03-05 17:40 | 2020-06-16 18:00 |  | 30 | 2020-05-23 23:31 |  |  | 2020-03-11 17:40 | 2020-06-22 18:00 |  | 35 | 2020-05-31 23:31 |  |  | 2020-03-18 23:59 | 2020-06-22 18:00 |  | 65 | 2020-06-15 18:11 |  |  | 2020-03-24 17:40 | 2020-07-13 18:00 |  | 80 | 2020-07-03 15:34 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-16 17:40 | 2020-07-13 18:00 |  | 100 | 2020-07-04 14:56 | [121 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 43 |  |  |  |  | 101057
360 | Task(Task)-->E (Engineering) | GA & DIMENSION SHEET FOR RUBBER DISC RETURN IDLER FOR BELT CONVEYORS |  | 1.5.1.1 | GA & DIMENSION SHEET FOR RUBBER DISC RETURN IDLER FOR BELT CONVEYORS-->MECHANICAL-->ENGINEERING-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-20 18:00 | 2020-04-16 17:40 | 2020-06-06 09:00 | 2020-06-29 18:00 |  |  | 2020-02-21 14:04 | 2020-07-07 18:40 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1014 |  | 2020-02-13 10:27 | 7012-155-PVM-B-114 |  |  |  | I |  |  |  | 2.9178 | 0.002145 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 80 | 0 | 7.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2663 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-20 18:00 | 2020-05-15 18:00 |  | 10 | 2020-05-14 23:31 |  |  | 2020-03-05 17:40 | 2020-06-05 18:00 |  | 30 | 2020-05-23 23:31 |  |  | 2020-03-11 17:40 | 2020-06-11 18:00 |  | 35 | 2020-05-31 23:31 |  |  | 2020-03-18 23:59 | 2020-06-11 18:00 |  | 65 | 2020-06-08 18:43 |  |  | 2020-03-24 17:40 | 2020-07-02 18:00 |  | 80 | 2020-06-24 06:46 | [5 empty] | 80 | 2020-06-29 18:35 | [5 empty] | 80 | 2020-06-29 18:35 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-16 17:40 | 2020-07-02 18:00 |  | 100 | 2020-07-07 18:41 | [121 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 44 |  |  |  |  | 101058
361 | Task(Task)-->E (Engineering) | GA & DIMENSION SHEET FOR S.A CARRAYING AND S.A RETURN IDLER FOR TROUGH BELT CONVEYORS |  | 1.5.1.1 | GA & DIMENSION SHEET FOR S.A CARRAYING AND S.A RETURN IDLER FOR TROUGH BELT CONVEYORS-->MECHANICAL-->ENGINEERING-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-20 18:00 | 2020-04-16 17:40 | 2020-06-15 09:00 | 2020-07-03 18:00 |  |  | 2020-02-21 14:04 | 2020-07-04 14:55 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1016 |  | 2020-02-13 10:27 | 7012-155-PVM-B-116 |  |  |  | I |  |  |  | 2.9178 | 0.002145 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 80 | 0 | 2.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2654 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-20 18:00 | 2020-05-22 18:00 |  | 10 | 2020-05-11 23:31 |  |  | 2020-03-05 17:40 | 2020-06-12 18:00 |  | 30 | 2020-05-23 23:31 |  |  | 2020-03-11 17:40 | 2020-06-18 18:00 |  | 35 | 2020-05-31 23:31 |  |  | 2020-03-18 23:59 | 2020-06-18 18:00 |  | 65 | 2020-06-15 18:11 |  |  | 2020-03-24 17:40 | 2020-07-09 18:00 |  | 80 | 2020-07-03 15:33 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-16 17:40 | 2020-07-09 18:00 |  | 100 | 2020-07-04 14:56 | [121 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 46 |  |  |  |  | 101060
362 | Task(Task)-->E (Engineering) | GA & DIMENSION SHEET FOR TROUGHING TRANSITION IDLER FOR TROUGH BELT CONVEYORS |  | 1.5.1.1 | GA & DIMENSION SHEET FOR TROUGHING TRANSITION IDLER FOR TROUGH BELT CONVEYORS-->MECHANICAL-->ENGINEERING-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-20 18:00 | 2020-04-16 17:40 | 2020-06-06 09:00 | 2020-06-29 18:00 |  |  | 2020-02-21 14:04 | 2020-07-07 18:40 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1018 |  | 2020-02-13 10:27 | 7012-155-PVM-B-118 |  |  |  | I |  |  |  | 2.9178 | 0.002145 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 80 | 0 | 7.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2655 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-20 18:00 | 2020-05-26 18:00 |  | 10 | 2020-05-11 23:31 |  |  | 2020-03-05 17:40 | 2020-06-16 18:00 |  | 30 | 2020-05-23 23:31 |  |  | 2020-03-11 17:40 | 2020-06-22 18:00 |  | 35 | 2020-05-31 23:31 |  |  | 2020-03-18 23:59 | 2020-06-22 18:00 |  | 65 | 2020-06-08 18:43 |  |  | 2020-03-24 17:40 | 2020-07-13 18:00 |  | 80 | 2020-06-25 08:20 | [5 empty] | 80 | 2020-06-29 18:46 | [5 empty] | 80 | 2020-06-29 18:46 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-16 17:40 | 2020-07-13 18:00 |  | 100 | 2020-07-07 18:41 | [121 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 48 |  |  |  |  | 101062
363 | Task(Task)-->E (Engineering) | BELT DATA SHEET WITH SCHEDULE FOR TROUGH BELT CONVEYORS |  | 1.5.1.1 | BELT DATA SHEET WITH SCHEDULE FOR TROUGH BELT CONVEYORS-->MECHANICAL-->ENGINEERING-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-07 18:00 | 2020-04-04 17:40 | 2020-05-10 23:59 | 2020-10-09 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-DC-1024 |  | 2020-02-13 10:27 | 7012-155-PVM-Y-124 |  |  |  | A |  |  |  | 1.4589 | 0.001072 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 40 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2662 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-07 18:00 | 2020-05-10 23:59 |  | 10 |  |  |  | 2020-02-24 17:40 | 2020-05-31 23:59 |  | 30 |  |  |  | 2020-02-29 17:40 | 2020-06-07 23:59 |  | 35 |  |  |  | 2020-03-06 23:59 | 2020-06-07 23:59 |  | 65 | 2020-09-19 13:18 |  |  | 2020-03-12 17:40 | 2020-06-28 23:59 |  | 80 | 2020-10-14 15:22 | [5 empty] | 80 | 2020-10-16 19:16 | [5 empty] | 80 | 2020-10-16 19:16 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-04 17:40 | 2020-06-28 23:59 |  | 100 | [122 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 54 |  |  |  |  | 101068
364 | Task(Task)-->E (Engineering) | SCHEDULE OF DRIVE AND NON DRIVE PULLEY FOR TROUGH BELT CONVEYORS |  | 1.5.1.1 | SCHEDULE OF DRIVE AND NON DRIVE PULLEY FOR TROUGH BELT CONVEYORS-->MECHANICAL-->ENGINEERING-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-11 18:00 | 2020-03-07 17:40 | 2020-02-18 09:00 | 2020-03-27 18:00 |  |  | 2020-02-21 14:04 | 2020-06-19 18:48 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1026 |  | 2020-02-13 10:27 | 7012-155-PVM-H-126 |  |  |  | A |  |  |  | 4.244 | 0.00312 | 0.32 | Plan & Actual | Date |  | 0 | 0 | 0 | 120 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2659 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-11 18:00 | 2020-01-25 18:00 |  | 10 | 2020-01-25 23:31 |  |  | 2020-01-28 17:40 | 2020-02-15 18:00 |  | 30 | 2020-02-15 23:31 |  |  | 2020-02-03 17:40 | 2020-02-18 18:00 |  | 35 | 2020-02-18 23:31 |  |  | 2020-02-08 23:59 | 2020-02-18 18:00 |  | 65 | 2020-02-18 23:31 |  |  | 2020-02-14 17:40 | 2020-03-19 18:00 |  | 80 | 2020-03-19 23:31 | [5 empty] | 80 | 2020-06-13 12:03 | [5 empty] | 80 | 2020-06-13 12:03 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-07 17:40 | 2020-03-27 18:00 |  | 100 | 2020-04-19 23:31 | [121 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 56 |  |  |  |  | 101070
365 | Task(Task)-->E (Engineering) | G.A OF BRAKES FOR TROUGH BELT CONVEYORS |  | 1.5.1.1 | G.A OF BRAKES FOR TROUGH BELT CONVEYORS-->MECHANICAL-->ENGINEERING-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-25 18:00 | 2020-05-22 17:40 | 2020-07-21 09:00 | 2020-08-12 18:00 |  |  | 2020-02-21 14:04 | 2020-08-24 20:07 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1028 |  | 2020-02-13 10:27 | 7012-155-PVM-B-128 |  |  |  | I |  |  |  | 2.9178 | 0.002145 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 80 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2656 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-25 18:00 | 2020-05-25 18:00 |  | 10 |  |  |  | 2020-04-10 17:40 | 2020-06-15 18:00 |  | 30 |  |  |  | 2020-04-17 17:40 | 2020-06-18 18:00 |  | 35 |  |  |  | 2020-04-23 23:59 | 2020-06-23 18:00 |  | 65 | 2020-07-29 00:16 |  |  | 2020-04-30 17:40 | 2020-07-14 18:00 |  | 80 | 2020-08-19 18:23 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-22 17:40 | 2020-07-14 18:00 |  | 100 | 2020-08-24 20:08 | [121 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 58 |  |  |  |  | 101072
366 | Task(Task)-->E (Engineering) | GA OF SCRAPPERS- INTERNAL & EXTERNAL FOR BOTH TROUGH BELT & PIPE CONVEYOR |  | 1.5.1.1 | GA OF SCRAPPERS- INTERNAL & EXTERNAL FOR BOTH TROUGH BELT & PIPE CONVEYOR-->MECHANICAL-->ENGINEERING-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-12 23:59 | 2020-05-29 17:40 | 2020-07-08 09:00 | 2020-07-28 18:00 |  |  | 2020-02-21 14:04 | 2020-07-30 19:53 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1033 |  | 2020-02-13 10:27 | 7012-155-PVM-B-133 |  |  |  | I |  |  |  | 14.3236 | 0.010528 | 1.08 | Plan & Actual | Date |  | 0 | 0 | 0 | 400 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2646 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-12 23:59 | 2020-05-10 23:59 |  | 10 |  |  |  | 2020-04-17 17:40 | 2020-05-25 18:00 |  | 30 |  |  |  | 2020-04-23 17:40 | 2020-05-28 18:00 |  | 35 |  |  |  | 2020-04-30 23:59 | 2020-05-28 18:00 |  | 65 | 2020-07-08 17:20 |  |  | 2020-05-06 17:40 | 2020-06-18 18:00 |  | 80 | 2020-07-28 10:14 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-29 17:40 | 2020-06-18 18:00 |  | 100 | 2020-07-30 19:53 | [121 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 63 |  |  |  |  | 101077
367 | Task(Task)-->E (Engineering) | G.A OF PLUMMER BLOCKS FOR BELT FEEDER, TROUGH & PIPE CONVEYOR |  | 1.5.1.1 | G.A OF PLUMMER BLOCKS FOR BELT FEEDER, TROUGH & PIPE CONVEYOR-->MECHANICAL-->ENGINEERING-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-06-28 23:59 | 2020-08-14 17:40 | 2020-06-09 09:00 | 2020-06-24 18:00 |  |  | 2020-02-21 14:04 | 2020-06-29 19:15 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1040 |  | 2020-02-13 10:27 | 7012-155-PVM-B-140 |  |  |  | I |  |  |  | 2.9178 | 0.002145 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 80 | 0 | 6.15 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2647 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-06-28 23:59 | 2020-06-15 18:00 |  | 10 |  |  |  | 2020-07-03 17:40 | 2020-06-30 18:00 |  | 30 |  |  |  | 2020-07-09 17:40 | 2020-07-03 18:00 |  | 35 |  |  |  | 2020-07-16 23:59 | 2020-07-03 18:00 |  | 65 | 2020-06-13 12:14 |  |  | 2020-07-22 17:40 | 2020-07-24 18:00 |  | 80 | 2020-06-25 08:23 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-08-14 17:40 | 2020-07-24 18:00 |  | 100 | 2020-06-29 19:16 | [121 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 70 |  |  |  |  | 101084
368 | Task(Task)-->E (Engineering) | G.A OF GEAR COUPLING FOR TROUGH CONVEYORS |  | 1.5.1.1 | G.A OF GEAR COUPLING FOR TROUGH CONVEYORS-->MECHANICAL-->ENGINEERING-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-20 18:00 | 2020-06-06 17:40 | 2020-06-15 09:00 | 2020-07-04 18:00 |  |  | 2020-02-21 14:04 | 2020-07-30 19:53 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1043 |  | 2020-02-13 10:27 | 7012-155-PVM-B-143 |  |  |  | I |  |  |  | 1.4589 | 0.001072 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 40 | 0 | 16.3 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2657 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-20 18:00 | 2020-05-18 18:00 |  | 10 | 2020-05-04 23:31 |  |  | 2020-04-27 17:40 | 2020-06-02 18:00 |  | 30 | 2020-05-23 23:31 |  |  | 2020-05-02 17:40 | 2020-06-05 18:00 |  | 35 | 2020-05-31 23:31 |  |  | 2020-05-08 23:59 | 2020-06-05 18:00 |  | 65 | 2020-07-06 12:27 |  |  | 2020-05-15 17:40 | 2020-06-26 18:00 |  | 80 | 2020-07-06 12:28 | [5 empty] | 80 | 2020-07-14 10:32 | [5 empty] | 80 | 2020-07-14 10:32 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-06 17:40 | 2020-06-26 18:00 |  | 100 | 2020-07-30 19:53 | [121 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 73 |  |  |  |  | 101087
369 | Task(Task)-->E (Engineering) | GA, DATA SHEET, TERMINAL BOX ARRANGEMET & CHARACTERISTICS CURVES OF HT MOTOR FOR CONVEYING SYSTEM |  | 1.5.1.1 | GA, DATA SHEET, TERMINAL BOX ARRANGEMET & CHARACTERISTICS CURVES OF HT MOTOR FOR CONVEYING SYSTEM-->MECHANICAL-->ENGINEERING-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-27 17:40 | 2020-05-08 17:40 | 2020-05-31 23:59 | 2020-09-01 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-161 |  | 2020-02-13 11:46 | 7012-155-PVE-W-106 |  |  |  | A |  |  |  | 1.4589 | 0.001072 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2669 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-28 18:00 | 2020-05-31 23:59 |  | 10 |  |  |  | 2020-03-27 17:40 | 2020-06-07 23:59 |  | 30 |  |  |  | 2020-04-03 17:40 | 2020-06-12 18:00 |  | 35 |  |  |  | 2020-04-09 23:59 | 2020-06-12 18:00 |  | 65 |  |  |  | 2020-04-16 17:40 | 2020-07-03 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-08 17:40 | 2020-07-03 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 341 |  |  |  |  | 101352
370 | Task(Task)-->E (Engineering) | GA, DATA SHEET, BOM, WIRING AND TERMINAL DIAGRAM OF LOCAL CONTROL PANEL FOR SCOOP COUPLING |  | 1.5.1.1 | GA, DATA SHEET, BOM, WIRING AND TERMINAL DIAGRAM OF LOCAL CONTROL PANEL FOR SCOOP COUPLING-->MECHANICAL-->ENGINEERING-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-04 17:40 | 2020-05-16 17:40 | 2020-05-20 18:00 | 2020-08-21 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-400 |  | 2020-02-13 11:47 | 7012-155-PVE-W-136 |  |  |  | A |  |  |  | 0.79576 | 0.000585 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2670 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-05 23:59 | 2020-05-20 18:00 |  | 10 |  |  |  | 2020-04-04 17:40 | 2020-05-27 18:00 |  | 30 |  |  |  | 2020-04-10 17:40 | 2020-06-01 18:00 |  | 35 |  |  |  | 2020-04-17 23:59 | 2020-06-01 18:00 |  | 65 | 2020-08-03 10:41 |  |  | 2020-04-23 17:40 | 2020-06-22 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-16 17:40 | 2020-06-22 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 371 |  |  |  |  | 101382
371 | Task(Task)-->E (Engineering) | G.A & MARKING OF CONV. SC 1A /B AND SC 2A/B |  | 1.5.1.1 | G.A & MARKING OF CONV. SC 1A /B AND SC 2A/B-->MECHANICAL-->ENGINEERING-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-11-18 18:00 | 2020-01-08 17:40 | 2020-01-27 18:00 | 2020-04-09 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-0019 |  | 2020-02-13 10:26 | 7012-155-PVM-B-019 |  |  |  | A |  |  |  | 8.6207 | 0.006337 | 0.65 | Plan & Actual | Date |  | 0 | 0 | 0 | 240 | 0 | 24.15 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2645 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-11-18 18:00 | 2020-01-27 18:00 |  | 10 | 2020-01-27 23:31 |  |  | 2019-11-30 17:40 | 2020-02-11 18:00 |  | 30 | 2020-02-11 23:31 |  |  | 2019-12-06 17:40 | 2020-02-13 18:00 |  | 35 | 2020-02-13 23:31 |  |  | 2019-12-12 23:59 | 2020-02-20 18:00 |  | 65 | 2020-02-20 23:31 |  |  | 2019-12-18 17:40 | 2020-03-19 18:00 |  | 80 | 2020-03-19 23:31 | [5 empty] | 80 | 2020-03-23 11:08 | [5 empty] | 80 | 2020-03-23 11:08 | [5 empty] | 80 | 2020-09-21 11:08 | [5 empty] | 80 | 2020-09-21 11:08 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-01-08 17:40 | 2020-04-09 18:00 |  | 100 | [122 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 19 |  |  |  |  | 101033
372 | Task(Task)-->E (Engineering) | GA OF BELT WEIGH SCALE |  | 1.5.1.1 | GA OF BELT WEIGH SCALE-->MECHANICAL-->ENGINEERING-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-05 17:40 | 2020-04-16 17:40 | 2020-04-14 09:00 | 2020-05-08 18:00 |  |  | 2020-02-21 14:04 | 2020-06-29 19:15 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1023 |  | 2020-02-13 10:27 | 7012-155-PVM-B-123 |  |  |  | A |  |  |  | 1.4589 | 0.001072 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 40 | 0 | 3.3 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2666 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-08 23:59 | 2020-04-10 18:00 |  | 10 | 2020-04-10 23:31 |  |  | 2020-03-05 17:40 | 2020-04-17 18:00 |  | 30 | 2020-04-11 23:31 |  |  | 2020-03-11 17:40 | 2020-04-20 18:00 |  | 35 | 2020-04-14 23:31 |  |  | 2020-03-18 23:59 | 2020-04-20 18:00 |  | 65 | 2020-04-14 23:31 |  |  | 2020-03-24 17:40 | 2020-05-11 18:00 |  | 80 | 2020-05-08 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | 2020-06-09 12:33 | [5 empty] | 80 | 2020-06-22 18:45 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-16 17:40 | 2020-05-11 18:00 |  | 100 | 2020-06-01 23:31 | [121 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 53 |  |  |  |  | 101067
373 | Task(Task)-->E (Engineering) | GA OF SUSPENDED MAGNET |  | 1.5.1.1 | GA OF SUSPENDED MAGNET-->MECHANICAL-->ENGINEERING-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-30 18:00 | 2020-03-25 17:40 | 2020-03-02 09:00 | 2020-04-11 18:00 |  |  | 2020-02-21 14:04 | 2020-06-19 22:44 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1031 |  | 2020-02-13 10:27 | 7012-155-PVM-B-131 |  |  |  | A |  |  |  | 5.7029 | 0.004192 | 0.43 | Plan & Actual | Date |  | 0 | 0 | 0 | 160 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2667 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-30 18:00 | 2020-02-06 18:00 |  | 10 | 2020-02-06 23:31 |  |  | 2020-02-13 17:40 | 2020-02-19 18:00 |  | 30 | 2020-02-19 23:31 |  |  | 2020-02-19 17:40 | 2020-02-24 18:00 |  | 35 | 2020-02-24 23:31 |  |  | 2020-02-26 23:59 | 2020-03-02 18:00 |  | 65 | 2020-03-02 23:31 |  |  | 2020-03-03 17:40 | 2020-03-20 18:00 |  | 80 | 2020-03-20 23:31 | [5 empty] | 80 | 2020-06-10 19:01 | [5 empty] | 80 | 2020-06-10 19:01 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-25 17:40 | 2020-04-25 18:00 |  | 100 | 2020-04-19 23:31 | [121 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 61 |  |  |  |  | 101075
374 | Task(Task)-->E (Engineering) | GA OF METAL DETECTOR |  | 1.5.1.1 | GA OF METAL DETECTOR-->MECHANICAL-->ENGINEERING-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-28 18:00 | 2020-03-20 17:40 | 2020-07-08 09:00 | 2020-07-24 18:00 |  |  | 2020-02-21 14:04 | 2020-07-30 19:52 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1032 |  | 2020-02-13 10:27 | 7012-155-PVM-B-132 |  |  |  | A |  |  |  | 5.7029 | 0.004192 | 0.43 | Plan & Actual | Date |  | 0 | 0 | 0 | 160 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2668 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-28 18:00 | 2020-05-14 18:00 |  | 10 | 2020-05-29 23:31 |  |  | 2020-02-07 17:40 | 2020-05-29 18:00 |  | 30 |  |  |  | 2020-02-14 17:40 | 2020-06-01 18:00 |  | 35 |  |  |  | 2020-02-20 23:59 | 2020-06-06 18:00 |  | 65 | 2020-07-08 17:20 |  |  | 2020-02-27 17:40 | 2020-06-27 18:00 |  | 80 | 2020-07-27 18:45 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-20 17:40 | 2020-06-27 18:00 |  | 100 | 2020-07-30 19:53 | [121 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 62 |  |  |  |  | 101076
375 | Task(Task)-->E (Engineering) | POWER AND TENSION CALCULATION FOR TROUGH BELT CONVEYORS (COMPUTERISED) |  | 1.5.1.1 | POWER AND TENSION CALCULATION FOR TROUGH BELT CONVEYORS (COMPUTERISED)-->MECHANICAL-->ENGINEERING-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-02 17:40 | 2019-12-11 17:40 | 2020-01-04 09:00 | 2020-02-25 18:00 |  |  | 2019-11-02 17:40 | 2020-03-04 10:30 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-CS-DC-0004 |  | 2020-02-13 10:26 | 7012-155-PVM-U-004 |  |  |  | A |  |  |  | 1.4589 | 0.001072 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2660 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-10-21 18:00 | 2019-12-11 18:00 |  | 10 | 2019-12-11 23:31 |  |  | 2019-11-02 17:40 | 2020-01-01 18:00 |  | 30 | 2020-01-01 23:31 |  |  | 2019-11-08 17:40 | 2020-01-04 18:00 |  | 35 | 2020-01-04 23:31 |  |  | 2019-11-14 23:59 | 2020-01-04 18:00 |  | 65 | 2020-01-04 23:31 |  |  | 2019-11-20 17:40 | 2020-02-17 18:00 |  | 80 | 2020-02-17 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2019-12-11 17:40 | 2020-02-25 18:00 |  | 100 | 2020-02-25 23:31 | [121 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 4 |  |  |  |  | 101018
376 | Task(Task)-->E (Engineering) | TYP. CROSS SECTION DETAILS OF TROUGH CONV. GALLERY |  | 1.5.1.1 | TYP. CROSS SECTION DETAILS OF TROUGH CONV. GALLERY-->MECHANICAL-->ENGINEERING-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-10-02 18:00 | 2019-11-21 17:40 | 2019-10-20 23:59 | 2019-12-23 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-CS-GA-0005 |  | 2020-02-13 10:26 | 7012-155-PVM-B-005 |  |  |  | A |  |  |  | 4.244 | 0.00312 | 0.32 | Plan & Actual | Date |  | 0 | 0 | 0 | 120 | 0 | 10.15 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2648 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-10-02 18:00 | 2019-10-20 23:59 |  | 10 | 2019-10-20 23:31 |  |  | 2019-10-14 17:40 | 2019-11-04 18:00 |  | 30 | 2019-11-04 23:31 |  |  | 2019-10-19 17:40 | 2019-11-09 18:00 |  | 35 | 2019-11-09 23:31 |  |  | 2019-10-25 23:59 | 2019-11-12 18:00 |  | 65 | 2019-11-12 23:31 |  |  | 2019-10-31 17:40 | 2019-12-11 18:00 |  | 80 | 2019-12-11 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2019-11-21 17:40 | 2019-12-23 18:00 |  | 100 | [122 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 5 |  |  |  |  | 101019
377 | Task(Task)-->E (Engineering) | CIVIL | 1.5.1.2 | 1.5.1 | CIVIL-->ENGINEERING-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-20 18:00 | 2020-06-02 17:40 | 2020-05-30 09:00 | 2020-07-15 18:00 |  |  | 2020-02-21 15:37 | 2020-07-15 20:57 |  |  | 100 | 100 | [15 empty] | 8.1538 | 0.011036 | 1.06 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No | 2671 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036079
378 | Task(Task)-->E (Engineering) | CONV. SC 1A/B : DESIGN CALCULATION OF SUPER STRUCTURE |  | 1.5.1.2 | CONV. SC 1A/B : DESIGN CALCULATION OF SUPER STRUCTURE-->CIVIL-->ENGINEERING-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-20 18:00 | 2020-03-20 17:40 | 2020-05-31 | 2020-07-03 18:00 |  |  | 2020-07-03 22:30 | 2020-07-03 22:30 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0016 |  | 2020-02-13 11:42 | 7012-155-PVC-U-058 |  |  |  | A |  |  |  | 29.6296 | 0.00327 | 0.32 | Plan & Actual | Date |  | 0 | 0 | 0 | 117.35 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2672 | 1 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-20 18:00 | 2020-03-24 18:00 |  | 10 | 2020-03-24 23:31 |  |  | 2020-02-07 17:40 | 2020-04-28 18:00 |  | 30 | 2020-05-25 23:31 |  |  | 2020-02-14 17:40 | 2020-05-01 18:00 |  | 35 | 2020-05-28 23:31 |  |  | 2020-02-20 23:59 | 2020-05-08 18:00 |  | 65 | 2020-05-31 23:31 |  |  | 2020-02-27 17:40 | 2020-05-29 18:00 |  | 80 | 2020-07-03 22:23 | [5 empty] | 80 | 2020-07-03 22:31 | [5 empty] | 80 | 2020-07-03 22:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-20 17:40 | 2020-06-12 18:00 |  | 100 | 2020-07-03 22:27 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 159 |  |  |  |  | 101171
379 | Task(Task)-->E (Engineering) | CONV. SC 1A/B : DESIGN CALCULATION OF SUB STRUCTURE |  | 1.5.1.2 | CONV. SC 1A/B : DESIGN CALCULATION OF SUB STRUCTURE-->CIVIL-->ENGINEERING-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-19 18:00 | 2020-04-20 17:40 | 2020-07-02 09:00 | 2020-07-15 18:00 |  |  | 2020-02-21 15:37 | 2020-07-15 20:56 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0017 |  | 2020-02-13 11:42 | 7012-155-PVC-U-059 |  |  |  | A |  |  |  | 10.1852 | 0.001124 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 38.49 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2673 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-19 18:00 | 2020-04-23 18:00 |  | 10 | 2020-04-23 23:31 |  |  | 2020-03-09 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-03-16 17:40 | 2020-05-31 23:59 |  | 35 |  |  |  | 2020-03-21 23:59 | 2020-06-07 23:59 |  | 65 | 2020-07-15 20:47 |  |  | 2020-03-27 17:40 | 2020-06-28 23:59 |  | 80 | 2020-07-15 20:55 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-20 17:40 | 2020-07-12 23:59 |  | 100 | 2020-07-15 20:57 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 160 |  |  |  |  | 101172
380 | Task(Task)-->E (Engineering) | CONV. SC 1A/B : NUM & RC DETAILS OF FDN |  | 1.5.1.2 | CONV. SC 1A/B : NUM & RC DETAILS OF FDN-->CIVIL-->ENGINEERING-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-19 18:00 | 2020-04-20 17:40 | 2020-07-02 09:00 | 2020-07-15 18:00 |  |  | 2020-02-21 15:37 | 2020-07-15 20:57 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-NR-0021 |  | 2020-02-13 11:42 | 7012-155-PVC-C-061 |  |  |  | A |  |  |  | 10.1852 | 0.001124 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 38.49 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2676 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-19 18:00 | 2020-04-23 18:00 |  | 10 | 2020-04-23 23:31 |  |  | 2020-03-09 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-03-16 17:40 | 2020-05-31 23:59 |  | 35 |  |  |  | 2020-03-21 23:59 | 2020-06-07 23:59 |  | 65 | 2020-07-15 20:49 |  |  | 2020-03-27 17:40 | 2020-06-28 23:59 |  | 80 | 2020-07-15 20:55 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-20 17:40 | 2020-07-12 23:59 |  | 100 | 2020-07-15 20:58 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 162 |  |  |  |  | 101174
381 | Task(Task)-->E (Engineering) | CONV. SC 2A/B : DESIGN CALCULATION OF SUPER STRUCTURE |  | 1.5.1.2 | CONV. SC 2A/B : DESIGN CALCULATION OF SUPER STRUCTURE-->CIVIL-->ENGINEERING-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-23 17:40 | 2020-05-04 17:40 | 2020-05-30 09:00 | 2020-06-16 18:00 |  |  | 2020-02-21 15:37 | 2020-06-16 22:21 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0018 |  | 2020-02-13 11:42 | 7012-155-PVC-U-062 |  |  |  | A |  |  |  | 29.6296 | 0.00327 | 0.32 | Plan & Actual | Date |  | 0 | 0 | 0 | 117.35 | 0 | 56 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2674 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-04 18:00 | 2020-03-24 18:00 |  | 10 | 2020-03-24 23:31 |  |  | 2020-03-23 17:40 | 2020-04-28 18:00 |  | 30 | 2020-05-25 23:31 |  |  | 2020-03-30 17:40 | 2020-05-01 18:00 |  | 35 | 2020-05-28 23:31 |  |  | 2020-04-04 23:59 | 2020-05-08 18:00 |  | 65 | 2020-05-30 23:31 |  |  | 2020-04-10 17:40 | 2020-05-29 18:00 |  | 80 | 2020-06-16 22:19 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-04 17:40 | 2020-06-12 18:00 |  | 100 | 2020-06-16 22:22 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 163 |  |  |  |  | 101175
382 | Task(Task)-->E (Engineering) | CONV. SC 2A/B : DESIGN CALCULATION OF SUB STRUCTURE |  | 1.5.1.2 | CONV. SC 2A/B : DESIGN CALCULATION OF SUB STRUCTURE-->CIVIL-->ENGINEERING-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-03 18:00 | 2020-06-02 17:40 | 2020-06-30 09:00 | 2020-07-13 18:00 |  |  | 2020-02-21 15:37 | 2020-07-13 23:03 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0019 |  | 2020-02-13 11:42 | 7012-155-PVC-U-063 |  |  |  | A |  |  |  | 10.1852 | 0.001124 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 38.49 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2675 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-03 18:00 | 2020-04-23 18:00 |  | 10 | 2020-04-23 23:31 |  |  | 2020-04-21 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-04-28 17:40 | 2020-05-31 23:59 |  | 35 |  |  |  | 2020-05-04 23:59 | 2020-06-07 23:59 |  | 65 | 2020-07-13 22:53 |  |  | 2020-05-11 17:40 | 2020-06-28 23:59 |  | 80 | 2020-07-13 23:01 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-02 17:40 | 2020-07-12 23:59 |  | 100 | 2020-07-13 23:04 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 164 |  |  |  |  | 101176
383 | Task(Task)-->E (Engineering) | CONV. SC 2A/B : NUM & RC DETAILS OF FDN |  | 1.5.1.2 | CONV. SC 2A/B : NUM & RC DETAILS OF FDN-->CIVIL-->ENGINEERING-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-03 18:00 | 2020-06-02 17:40 | 2020-07-01 09:00 | 2020-07-13 18:00 |  |  | 2020-02-21 15:37 | 2020-07-13 23:04 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-NR-0022 |  | 2020-02-13 11:42 | 7012-155-PVC-C-065 |  |  |  | A |  |  |  | 10.1852 | 0.001124 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 38.49 | 0 | 5.15 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2677 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-03 18:00 | 2020-04-23 18:00 |  | 10 | 2020-04-23 23:31 |  |  | 2020-04-21 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-04-28 17:40 | 2020-05-31 23:59 |  | 35 | 2020-07-01 20:59 |  |  | 2020-05-04 23:59 | 2020-06-07 23:59 |  | 65 | 2020-07-13 22:54 |  |  | 2020-05-11 17:40 | 2020-06-28 23:59 |  | 80 | 2020-07-13 23:00 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-02 17:40 | 2020-07-12 23:59 |  | 100 | 2020-07-13 23:05 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 166 |  |  |  |  | 101178
384 | Task(Task)-->E (Engineering) | STRUCTURAL | 1.5.1.3 | 1.5.1 | STRUCTURAL-->ENGINEERING-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-20 18:00 | 2020-05-04 17:40 | 2020-05-30 09:00 | 2020-07-03 18:00 |  |  | 2020-02-21 15:37 | 2020-07-03 22:31 |  |  | 100 | 100 | [15 empty] | 4.9231 | 0.006663 | 0.64 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No | 2678 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036080
385 | Task(Task)-->E (Engineering) | CONV. SC 1A/B : STRUCTURAL GA |  | 1.5.1.3 | CONV. SC 1A/B : STRUCTURAL GA-->STRUCTURAL-->ENGINEERING-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-20 18:00 | 2020-03-20 17:40 | 2020-05-31 | 2020-07-03 18:00 |  |  | 2020-07-03 22:31 | 2020-07-03 22:31 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-GA-0019 |  | 2020-02-13 11:42 | 7012-155-PVC-B-060 |  |  |  | A |  |  |  | 50 | 0.003332 | 0.32 | Plan & Actual | Date |  | 0 | 0 | 0 | 117.35 | 0 | 176.3 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2679 | 1 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-20 18:00 | 2020-03-24 18:00 |  | 10 | 2020-03-24 23:31 |  |  | 2020-02-07 17:40 | 2020-04-28 18:00 |  | 30 | 2020-05-25 23:31 |  |  | 2020-02-14 17:40 | 2020-05-01 18:00 |  | 35 | 2020-05-28 23:31 |  |  | 2020-02-20 23:59 | 2020-05-08 18:00 |  | 65 | 2020-05-31 23:31 |  |  | 2020-02-27 17:40 | 2020-05-29 18:00 |  | 80 | 2020-07-03 22:22 | [5 empty] | 80 | 2020-07-03 22:32 | [5 empty] | 80 | 2020-07-03 22:32 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-20 17:40 | 2020-06-12 18:00 |  | 100 | 2020-07-03 22:26 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 161 |  |  |  |  | 101173
386 | Task(Task)-->E (Engineering) | CONV. SC 2A/B : STRUCTURAL GA |  | 1.5.1.3 | CONV. SC 2A/B : STRUCTURAL GA-->STRUCTURAL-->ENGINEERING-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-23 17:40 | 2020-05-04 17:40 | 2020-05-30 09:00 | 2020-06-16 18:00 |  |  | 2020-02-21 15:37 | 2020-06-16 22:20 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-GA-0020 |  | 2020-02-13 11:42 | 7012-155-PVC-B-064 |  |  |  | A |  |  |  | 50 | 0.003332 | 0.32 | Plan & Actual | Date |  | 0 | 0 | 0 | 117.35 | 0 | 56 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2680 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-04 18:00 | 2020-03-24 18:00 |  | 10 | 2020-03-24 23:31 |  |  | 2020-03-23 17:40 | 2020-04-28 18:00 |  | 30 | 2020-05-25 23:31 |  |  | 2020-03-30 17:40 | 2020-05-01 18:00 |  | 35 | 2020-05-28 23:31 |  |  | 2020-04-04 23:59 | 2020-05-08 18:00 |  | 65 | 2020-05-30 23:31 |  |  | 2020-04-10 17:40 | 2020-05-29 18:00 |  | 80 | 2020-06-16 22:18 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-04 17:40 | 2020-06-12 18:00 |  | 100 | 2020-06-16 22:21 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 165 |  |  |  |  | 101177
387 | Task(Task)-->E (Engineering) | ELECTRICAL | 1.5.1.4 | 1.5.1 | ELECTRICAL-->ENGINEERING-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-02-11 17:40 | 2020-06-23 17:40 | 2020-03-02 09:00 | 2020-07-01 18:00 |  |  | 2020-02-24 17:40 |  |  |  | 100 | 80.5188 | [15 empty] | 32.6154 | 0.044144 | 4.24 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No | 2683 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036081
388 | Task(Task)-->E (Engineering) | LIGHTING LAYOUT PLAN WITH POWER DISTRIBUTION ARRANGEMENT, SECTIONAL VIEW, BOM OF CONVEYOR CONV. SC 1A /B |  | 1.5.1.4 | LIGHTING LAYOUT PLAN WITH POWER DISTRIBUTION ARRANGEMENT, SECTIONAL VIEW, BOM OF CONVEYOR CONV. SC 1A /B-->ELECTRICAL-->ENGINEERING-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-01 18:00 | 2020-06-20 17:40 | 2020-04-17 09:00 | 2020-06-14 23:59 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5079 |  | 2020-02-13 11:45 | 7012-155-PVE-G-041 |  |  |  | A |  |  |  | 47.4057 | 0.020927 | 2.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 746.44 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2684 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-05-01 18:00 | 2020-05-03 23:59 |  | 10 | 2020-04-11 23:31 |  |  | 2020-05-11 17:40 | 2020-05-10 23:59 |  | 30 | 2020-04-15 23:31 |  |  | 2020-05-16 17:40 | 2020-05-17 23:59 |  | 35 | 2020-04-17 23:31 |  |  | 2020-05-22 23:59 | 2020-05-24 23:59 |  | 65 | 2020-04-17 23:31 |  |  | 2020-05-29 17:40 | 2020-06-14 23:59 |  | 80 | 2020-04-23 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-20 17:40 | 2020-06-14 23:59 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 276 |  |  |  |  | 101287
389 | Task(Task)-->E (Engineering) | LIGHTING LAYOUT PLAN WITH POWER DISTRIBUTION ARRANGEMENT, SECTIONAL VIEW, BOM OF CONVEYOR CONV. SC 2A/B |  | 1.5.1.4 | LIGHTING LAYOUT PLAN WITH POWER DISTRIBUTION ARRANGEMENT, SECTIONAL VIEW, BOM OF CONVEYOR CONV. SC 2A/B-->ELECTRICAL-->ENGINEERING-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-05 18:00 | 2020-06-23 17:40 | 2020-04-17 09:00 | 2020-06-18 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5080 |  | 2020-02-13 11:45 | 7012-155-PVE-G-042 |  |  |  | A |  |  |  | 47.4057 | 0.020927 | 2.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 746.44 | 0 | 24.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2685 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-05-05 18:00 | 2020-05-07 18:00 |  | 10 | 2020-04-12 23:31 |  |  | 2020-05-13 17:40 | 2020-05-14 18:00 |  | 30 | 2020-04-14 23:31 |  |  | 2020-05-19 17:40 | 2020-05-21 18:00 |  | 35 | 2020-04-17 23:31 |  |  | 2020-05-26 23:59 | 2020-05-28 18:00 |  | 65 | 2020-04-17 23:31 |  |  | 2020-06-01 17:40 | 2020-06-18 18:00 |  | 80 | 2020-04-23 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-23 17:40 | 2020-06-18 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 277 |  |  |  |  | 101288
390 | Task(Task)-->E (Engineering) | GA,SLD,WIRING & BOM OF SUSPENDED MAGNET |  | 1.5.1.4 | GA,SLD,WIRING & BOM OF SUSPENDED MAGNET-->ELECTRICAL-->ENGINEERING-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-24 17:40 | 2020-04-04 17:40 | 2020-03-02 09:00 | 2020-04-02 18:00 |  |  | 2020-02-24 17:40 | 2020-04-18 12:40 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-402 |  | 2020-02-13 11:47 | 7012-155-PVE-W-138 |  |  |  | A |  |  |  | 2.5943 | 0.001145 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2686 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-22 18:00 | 2020-02-22 18:00 |  | 10 | 2020-02-22 23:31 |  |  | 2020-02-24 17:40 | 2020-02-29 18:00 |  | 30 | 2020-02-29 23:31 |  |  | 2020-02-29 17:40 | 2020-03-02 18:00 |  | 35 | 2020-03-02 23:31 |  |  | 2020-03-06 23:59 | 2020-03-02 18:00 |  | 65 | 2020-03-02 23:31 |  |  | 2020-03-12 17:40 | 2020-03-17 18:00 |  | 80 | 2020-03-17 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-04 17:40 | 2020-04-09 18:00 |  | 100 | 2020-04-09 23:31 | [121 empty] | Varun Parihari | [22 empty] | 373 |  |  |  |  | 101384
391 | Task(Task)-->E (Engineering) | GA,SLD,WIRING & BOM OF METAL DETECTOR |  | 1.5.1.4 | GA,SLD,WIRING & BOM OF METAL DETECTOR-->ELECTRICAL-->ENGINEERING-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-11 17:40 | 2020-03-23 17:40 | 2020-05-14 18:00 | 2020-07-01 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-403 |  | 2020-02-13 11:47 | 7012-155-PVE-W-139 |  |  |  | A |  |  |  | 2.5943 | 0.001145 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2687 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-13 18:00 | 2020-05-14 18:00 |  | 10 |  |  |  | 2020-02-11 17:40 | 2020-05-21 18:00 |  | 30 |  |  |  | 2020-02-17 17:40 | 2020-05-25 18:00 |  | 35 |  |  |  | 2020-02-24 23:59 | 2020-05-25 18:00 |  | 65 | 2020-07-28 15:44 |  |  | 2020-02-29 17:40 | 2020-06-15 18:00 |  | 80 | 2020-07-28 17:46 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-23 17:40 | 2020-06-15 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 374 |  |  |  |  | 101385
392 | Task(Task)-->P (Procurement) | PROCUREMENT | 1.5.2 | 1.5 | PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-09-27 09:00 | 2021-02-13 18:00 | 2019-09-27 09:00 | 2021-06-13 23:59 |  |  | 2019-09-27 10:57 |  |  |  | 97.309 | 40.744 | [15 empty] | 69.6042 | 1.5003 | 147.54 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2688 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018009
393 | Task(Task)-->P (Procurement) | PURCHASE REQUISITION | 1.5.2.1 | 1.5.2 | PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-09-27 09:00 | 2020-05-19 18:00 | 2019-09-27 09:00 | 2020-05-29 18:00 |  |  | 2019-09-27 10:57 |  |  |  | 100 | 99.8654 | [15 empty] | 5.002 | 0.075047 | 7.38 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2689 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018010
394 | Task(Task)-->P (Procurement) | Suspended Magnet |  | 1.5.2.1 | Suspended Magnet-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-09-27 09:00 | 2019-09-27 18:00 | 2019-09-27 09:00 | 2019-09-27 18:00 |  |  | 2019-09-27 10:57 | 2019-09-27 10:57 |  |  | 100 | 100 | [15 empty] | 10.4054 | 0.007809 | 0.77 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2690 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018011
395 | Task(Task)-->P (Procurement) | Belt Scale |  | 1.5.2.1 | Belt Scale-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-09-27 09:00 | 2019-09-27 18:00 | 2019-09-27 09:00 | 2019-09-27 18:00 |  |  | 2019-09-27 14:37 | 2019-09-27 14:37 |  |  | 100 | 100 | [15 empty] | 2.027 | 0.001521 | 0.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2691 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018012
396 | Task(Task)-->P (Procurement) | Metal Detector |  | 1.5.2.1 | Metal Detector-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-09-27 09:00 | 2019-09-27 18:00 | 2019-09-27 09:00 | 2019-09-27 18:00 |  |  | 2019-09-27 10:57 | 2019-09-27 10:57 |  |  | 100 | 100 | [15 empty] | 2.027 | 0.001521 | 0.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2692 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018013
397 | Task(Task)-->P (Procurement) | Pulley |  | 1.5.2.1 | Pulley-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-09-27 09:00 | 2019-09-27 18:00 | 2020-02-05 09:00 | 2020-02-05 18:00 |  |  | 2020-02-05 16:16 | 2020-02-05 16:16 |  |  | 100 | 100 | [15 empty] | 12.027 | 0.009026 | 0.89 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2693 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018014
398 | Task(Task)-->P (Procurement) | Idler |  | 1.5.2.1 | Idler-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-19 09:00 | 2019-12-19 18:00 | 2020-02-13 09:00 | 2020-02-13 18:00 |  |  | 2020-02-13 15:44 | 2020-02-13 15:44 |  |  | 100 | 100 | [15 empty] | 8.5135 | 0.006389 | 0.63 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2694 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018015
399 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.5.2.1 | Plummer Block-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-17 | 2020-05-17 23:59 | 2020-02-10 09:00 | 2020-02-10 18:00 |  |  | 2020-02-10 09:26 | 2020-02-10 09:26 |  |  | 100 | 100 | [15 empty] | 0.94595 | 0.00071 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2695 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018016
400 | Task(Task)-->P (Procurement) | Bearing |  | 1.5.2.1 | Bearing-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-17 | 2020-05-17 23:59 | 2020-02-10 09:00 | 2020-02-10 18:00 |  |  | 2020-02-10 09:36 | 2020-02-10 09:36 |  |  | 100 | 100 | [15 empty] | 1.4865 | 0.001116 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2696 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018017
401 | Task(Task)-->P (Procurement) | Belting |  | 1.5.2.1 | Belting-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-07 09:00 | 2019-11-07 18:00 | 2020-01-20 09:00 | 2020-01-20 18:00 |  |  | 2020-01-20 15:54 | 2020-01-20 15:54 |  |  | 100 | 100 | [15 empty] | 8.7838 | 0.006592 | 0.65 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2697 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018018
402 | Task(Task)-->P (Procurement) | Scrapper |  | 1.5.2.1 | Scrapper-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-17 | 2019-11-17 23:59 | 2020-03-11 09:00 | 2020-03-11 18:00 |  |  | 2020-03-11 10:57 | 2020-03-11 10:57 |  |  | 100 | 100 | [15 empty] | 0.54054 | 0.000406 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2698 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018019
403 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.5.2.1 | Technological Structure-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-10 09:00 | 2020-03-10 18:00 | 2020-03-11 09:00 | 2020-03-11 18:00 |  |  | 2020-03-11 12:41 | 2020-03-11 12:41 |  |  | 100 | 100 | [15 empty] | 2.5676 | 0.001927 | 0.19 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2699 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018020
404 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.5.2.1 | Takeup Component-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-19 09:00 | 2020-05-19 18:00 | 2020-04-16 09:00 | 2020-04-16 18:00 |  |  | 2020-04-16 10:57 | 2020-04-16 10:57 |  |  | 100 | 100 | [15 empty] | 0.13514 | 0.000101 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2700 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018021
405 | Task(Task)-->P (Procurement) | Gear Box |  | 1.5.2.1 | Gear Box-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-13 09:00 | 2019-11-13 18:00 | 2020-01-20 09:00 | 2020-01-20 18:00 |  |  | 2020-01-20 11:17 | 2020-01-20 11:17 |  |  | 100 | 100 | [15 empty] | 2.7027 | 0.002028 | 0.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2701 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018022
406 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.5.2.1 | Geared Coupling-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-21 09:00 | 2019-11-21 18:00 | 2020-01-22 09:00 | 2020-01-22 18:00 |  |  | 2020-01-22 10:41 | 2020-01-22 10:41 |  |  | 100 | 100 | [15 empty] | 0.40541 | 0.000304 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2702 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018023
407 | Task(Task)-->P (Procurement) | Fluid Coupling |  | 1.5.2.1 | Fluid Coupling-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-25 09:00 | 2019-11-25 18:00 | 2020-01-22 09:00 | 2020-01-22 18:00 |  |  | 2020-01-22 09:54 | 2020-01-22 09:54 |  |  | 100 | 100 | [15 empty] | 2.8378 | 0.00213 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2703 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018024
408 | Task(Task)-->P (Procurement) | Brake |  | 1.5.2.1 | Brake-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-18 09:00 | 2019-12-18 18:00 | 2020-04-04 09:00 | 2020-04-04 18:00 |  |  | 2020-04-04 11:33 | 2020-04-04 11:33 |  |  | 100 | 100 | [15 empty] | 0.27027 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2704 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018025
409 | Task(Task)-->P (Procurement) | Building Structure |  | 1.5.2.1 | Building Structure-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-04 09:00 | 2020-04-04 18:00 | 2020-05-29 09:00 | 2020-05-29 18:00 |  |  | 2020-05-31 18:44 | 2020-05-31 18:44 |  |  | 100 | 100 | [15 empty] | 29.7297 | 0.022311 | 2.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2705 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018026
410 | Task(Task)-->P (Procurement) | HT AC MOTORS |  | 1.5.2.1 | HT AC MOTORS-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-07 09:00 | 2020-01-07 18:00 | 2020-01-17 09:00 | 2020-01-17 18:00 |  |  | 2020-01-17 10:57 | 2020-01-17 10:57 |  |  | 100 | 100 | [15 empty] | 7.8378 | 0.005882 | 0.58 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2706 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018027
411 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.5.2.1 | LIGHT & LIGHT FIXTURES-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-10 09:00 | 2020-03-10 18:00 | 2020-03-16 09:00 | 2020-03-16 18:00 |  |  | 2020-03-16 10:57 | 2020-03-16 10:57 |  |  | 100 | 100 | [15 empty] | 3.6486 | 0.002738 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2707 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018028
412 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.5.2.1 | LIGHTING POLES-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-27 09:00 | 2020-03-27 18:00 | 2020-04-30 09:00 | 2020-04-30 18:00 |  |  | 2020-04-30 10:57 | 2020-04-30 10:57 |  |  | 100 | 100 | [15 empty] | 1.6216 | 0.001217 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2708 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018029
413 | Task(Task)-->P (Procurement) | LPBS |  | 1.5.2.1 | LPBS-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-20 09:00 | 2020-03-20 18:00 | 2020-04-14 09:00 | 2020-04-14 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.13514 | 0.000101 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2709 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018030
414 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.5.2.1 | CONVEYOR BELT PROTECTION SWITCHES-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-08 09:00 | 2020-01-08 18:00 | 2020-01-08 09:00 | 2020-01-08 18:00 |  |  | 2020-01-08 10:57 | 2020-01-08 10:57 |  |  | 100 | 100 | [15 empty] | 1.3514 | 0.001014 | 0.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2711 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018031
415 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.5.2.1 | ZERO SPEED SWITCH-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-30 09:00 | 2019-12-30 18:00 | 2019-12-30 09:00 | 2019-12-30 18:00 |  |  | 2019-12-30 10:57 | 2019-12-30 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2712 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018032
416 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.5.2.1 | CHUTE BLOCK SWITCH-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-03 09:00 | 2020-01-03 18:00 | 2020-01-03 09:00 | 2020-01-03 18:00 |  |  | 2020-01-03 10:57 | 2020-01-03 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2713 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018033
417 | Task(Task)-->P (Procurement) | TECHNICAL CLEARANCE | 1.5.2.2 | 1.5.2 | TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-09-28 09:00 | 2020-06-18 18:00 | 2019-09-27 09:00 | 2020-06-12 18:00 |  |  | 2019-09-30 14:37 |  |  |  | 100 | 99.8654 | [15 empty] | 5.002 | 0.075047 | 7.38 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2714 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018034
418 | Task(Task)-->P (Procurement) | Suspended Magnet |  | 1.5.2.2 | Suspended Magnet-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-09-28 09:00 | 2020-01-07 18:00 | 2019-09-27 09:00 | 2019-12-04 18:00 |  |  | 2019-12-04 10:57 | 2019-12-04 10:57 |  |  | 100 | 100 | [15 empty] | 10.4054 | 0.007809 | 0.77 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2715 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018035
419 | Task(Task)-->P (Procurement) | Belt Scale |  | 1.5.2.2 | Belt Scale-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-09-28 09:00 | 2020-02-02 23:59 | 2019-09-27 09:00 | 2019-12-17 18:00 |  |  | 2019-09-30 14:37 | 2019-12-17 14:38 |  |  | 100 | 100 | [15 empty] | 2.027 | 0.001521 | 0.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2716 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018036
420 | Task(Task)-->P (Procurement) | Metal Detector |  | 1.5.2.2 | Metal Detector-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-09-28 09:00 | 2020-01-06 18:00 | 2019-09-27 09:00 | 2019-12-27 18:00 |  |  | 2019-12-27 10:57 | 2019-12-27 10:57 |  |  | 100 | 100 | [15 empty] | 2.027 | 0.001521 | 0.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2717 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018037
421 | Task(Task)-->P (Procurement) | Pulley |  | 1.5.2.2 | Pulley-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-09-28 09:00 | 2020-01-04 18:00 | 2020-02-05 09:00 | 2020-02-10 18:00 |  |  | 2020-02-06 16:19 | 2020-02-10 16:19 |  |  | 100 | 100 | [15 empty] | 12.027 | 0.009026 | 0.89 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2718 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018038
422 | Task(Task)-->P (Procurement) | Idler |  | 1.5.2.2 | Idler-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-20 09:00 | 2020-02-01 18:00 | 2020-02-13 09:00 | 2020-03-26 18:00 |  |  | 2020-02-14 10:57 | 2020-03-26 10:57 |  |  | 100 | 100 | [15 empty] | 8.5135 | 0.006389 | 0.63 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2719 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018039
423 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.5.2.2 | Plummer Block-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-18 09:00 | 2020-06-01 18:00 | 2020-02-10 09:00 | 2020-02-10 18:00 |  |  | 2020-02-10 09:28 | 2020-02-10 09:28 |  |  | 100 | 100 | [15 empty] | 0.94595 | 0.00071 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2720 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018040
424 | Task(Task)-->P (Procurement) | Bearing |  | 1.5.2.2 | Bearing-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-18 09:00 | 2020-06-16 18:00 | 2020-02-10 09:00 | 2020-02-10 18:00 |  |  | 2020-02-10 09:37 | 2020-02-10 09:37 |  |  | 100 | 100 | [15 empty] | 1.4865 | 0.001116 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2721 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018041
425 | Task(Task)-->P (Procurement) | Belting |  | 1.5.2.2 | Belting-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-08 09:00 | 2020-01-06 18:00 | 2020-01-20 09:00 | 2020-05-16 18:00 |  |  | 2020-05-16 10:57 | 2020-05-16 10:57 |  |  | 100 | 100 | [15 empty] | 8.7838 | 0.006592 | 0.65 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2722 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018042
426 | Task(Task)-->P (Procurement) | Scrapper |  | 1.5.2.2 | Scrapper-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-18 09:00 | 2020-03-16 18:00 | 2020-03-11 09:00 | 2020-03-26 18:00 |  |  | 2020-03-26 10:57 | 2020-03-26 10:57 |  |  | 100 | 100 | [15 empty] | 0.54054 | 0.000406 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2723 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018043
427 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.5.2.2 | Technological Structure-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-11 09:00 | 2020-03-20 18:00 | 2020-03-11 09:00 | 2020-03-17 18:00 |  |  | 2020-03-12 12:43 | 2020-03-17 12:43 |  |  | 100 | 100 | [15 empty] | 2.5676 | 0.001927 | 0.19 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2724 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018044
428 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.5.2.2 | Takeup Component-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-20 09:00 | 2020-06-18 18:00 | 2020-04-16 09:00 | 2020-04-16 18:00 |  |  | 2020-04-16 10:57 | 2020-04-16 10:57 |  |  | 100 | 100 | [15 empty] | 0.13514 | 0.000101 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2725 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018045
429 | Task(Task)-->P (Procurement) | Gear Box |  | 1.5.2.2 | Gear Box-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-14 09:00 | 2020-02-26 18:00 | 2020-01-20 09:00 | 2020-03-20 18:00 |  |  | 2020-01-22 11:19 | 2020-03-20 11:19 |  |  | 100 | 100 | [15 empty] | 2.7027 | 0.002028 | 0.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2726 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018046
430 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.5.2.2 | Geared Coupling-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-22 09:00 | 2020-03-19 18:00 | 2020-01-22 09:00 | 2020-04-13 18:00 |  |  | 2020-04-13 10:46 | 2020-04-13 10:46 |  |  | 100 | 100 | [15 empty] | 0.40541 | 0.000304 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2727 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018047
431 | Task(Task)-->P (Procurement) | Fluid Coupling |  | 1.5.2.2 | Fluid Coupling-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-26 09:00 | 2020-03-01 23:59 | 2020-01-22 09:00 | 2020-04-13 18:00 |  |  | 2020-01-23 09:54 | 2020-04-13 09:54 |  |  | 100 | 100 | [15 empty] | 2.8378 | 0.00213 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2728 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018048
432 | Task(Task)-->P (Procurement) | Brake |  | 1.5.2.2 | Brake-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-19 09:00 | 2020-03-09 18:00 | 2020-04-04 09:00 | 2020-04-22 18:00 |  |  | 2020-04-05 11:34 | 2020-04-22 11:34 |  |  | 100 | 100 | [15 empty] | 0.27027 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2729 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018049
433 | Task(Task)-->P (Procurement) | Building Structure |  | 1.5.2.2 | Building Structure-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-05 | 2020-04-11 18:00 | 2020-05-29 09:00 | 2020-05-29 18:00 |  |  | 2020-05-29 17:31 | 2020-05-29 17:31 |  |  | 100 | 100 | [15 empty] | 29.7297 | 0.022311 | 2.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2730 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018050
434 | Task(Task)-->P (Procurement) | HT AC MOTORS |  | 1.5.2.2 | HT AC MOTORS-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-08 09:00 | 2020-02-06 18:00 | 2020-01-17 09:00 | 2020-04-11 18:00 |  |  | 2020-04-11 10:57 | 2020-04-11 10:57 |  |  | 100 | 100 | [15 empty] | 7.8378 | 0.005882 | 0.58 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2731 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018051
435 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.5.2.2 | LIGHT & LIGHT FIXTURES-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-11 09:00 | 2020-03-25 18:00 | 2020-03-16 09:00 | 2020-06-02 18:00 |  |  | 2020-06-02 10:57 | 2020-06-02 10:57 |  |  | 100 | 100 | [15 empty] | 3.6486 | 0.002738 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2732 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018052
436 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.5.2.2 | LIGHTING POLES-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-28 09:00 | 2020-05-11 18:00 | 2020-04-30 09:00 | 2020-06-03 18:00 |  |  | 2020-06-03 10:57 | 2020-06-03 10:57 |  |  | 100 | 100 | [15 empty] | 1.6216 | 0.001217 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2733 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018053
437 | Task(Task)-->P (Procurement) | LPBS |  | 1.5.2.2 | LPBS-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-21 09:00 | 2020-04-04 18:00 | 2020-04-14 09:00 | 2020-06-12 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.13514 | 0.000101 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2734 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018054
438 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.5.2.2 | CONVEYOR BELT PROTECTION SWITCHES-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-09 09:00 | 2020-01-22 18:00 | 2020-01-08 09:00 | 2020-03-10 18:00 |  |  | 2020-03-10 10:57 | 2020-03-10 10:57 |  |  | 100 | 100 | [15 empty] | 1.3514 | 0.001014 | 0.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2736 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018055
439 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.5.2.2 | ZERO SPEED SWITCH-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-31 09:00 | 2020-01-16 18:00 | 2019-12-30 09:00 | 2020-03-07 18:00 |  |  | 2020-03-07 10:57 | 2020-03-07 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2737 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018056
440 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.5.2.2 | CHUTE BLOCK SWITCH-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-04 09:00 | 2020-01-18 18:00 | 2020-01-03 09:00 | 2020-01-16 18:00 |  |  | 2020-01-16 10:57 | 2020-01-16 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2738 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018057
441 | Task(Task)-->P (Procurement) | ORDERING | 1.5.2.3 | 1.5.2 | ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-01-05 | 2020-07-18 18:00 | 2019-12-04 09:00 | 2020-09-04 18:00 |  |  | 2020-01-05 08:00 |  |  |  | 100 | 98.4406 | [15 empty] | 9.9973 | 0.14999 | 14.75 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2739 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018058
442 | Task(Task)-->P (Procurement) | Suspended Magnet |  | 1.5.2.3 | Suspended Magnet-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-08 09:00 | 2020-02-06 18:00 | 2019-12-04 09:00 | 2020-02-03 18:00 |  |  | 2020-02-03 10:57 | 2020-02-03 10:57 |  |  | 100 | 100 | [15 empty] | 10.4407 | 0.01566 | 1.54 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2740 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018059
443 | Task(Task)-->P (Procurement) | Belt Scale |  | 1.5.2.3 | Belt Scale-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-03 09:00 | 2020-03-03 18:00 | 2019-12-17 09:00 | 2020-02-03 18:00 |  |  | 2020-02-03 08:00 | 2020-02-03 16:05 |  |  | 100 | 100 | [15 empty] | 2.0339 | 0.003051 | 0.3 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2741 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018060
444 | Task(Task)-->P (Procurement) | Metal Detector |  | 1.5.2.3 | Metal Detector-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-07 09:00 | 2020-02-05 18:00 | 2019-12-27 09:00 | 2020-03-20 18:00 |  |  | 2020-03-20 10:57 | 2020-03-20 10:57 |  |  | 100 | 100 | [15 empty] | 2.0339 | 0.003051 | 0.3 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2742 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018061
445 | Task(Task)-->P (Procurement) | Pulley |  | 1.5.2.3 | Pulley-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-05 | 2020-02-03 18:00 | 2020-02-10 09:00 | 2020-03-21 18:00 |  |  | 2020-01-05 08:00 | 2020-03-21 16:05 |  |  | 100 | 100 | [15 empty] | 12.0678 | 0.018101 | 1.78 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2743 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018062
446 | Task(Task)-->P (Procurement) | Idler |  | 1.5.2.3 | Idler-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-02 | 2020-03-02 18:00 | 2020-03-26 09:00 | 2020-04-30 18:00 |  |  | 2020-02-02 08:00 | 2020-04-29 16:05 |  |  | 100 | 100 | [15 empty] | 8.4746 | 0.012711 | 1.25 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2744 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018063
447 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.5.2.3 | Plummer Block-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-06-02 09:00 | 2020-07-01 18:00 | 2020-02-10 09:00 | 2020-03-24 18:00 |  |  | 2020-02-11 09:32 | 2020-03-24 09:32 |  |  | 100 | 100 | [15 empty] | 0.88136 | 0.001322 | 0.13 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2745 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018064
448 | Task(Task)-->P (Procurement) | Bearing |  | 1.5.2.3 | Bearing-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-06-17 09:00 | 2020-07-16 18:00 | 2020-02-10 09:00 | 2020-03-24 18:00 |  |  | 2020-02-11 09:40 | 2020-03-24 09:40 |  |  | 100 | 100 | [15 empty] | 1.4915 | 0.002237 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2746 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018065
449 | Task(Task)-->P (Procurement) | Belting |  | 1.5.2.3 | Belting-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-07 09:00 | 2020-02-20 18:00 | 2020-05-16 09:00 | 2020-09-04 18:00 |  |  | 2020-05-16 16:24 | 2020-09-04 16:24 |  |  | 100 | 100 | [15 empty] | 8.8136 | 0.01322 | 1.3 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2747 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018066
450 | Task(Task)-->P (Procurement) | Scrapper |  | 1.5.2.3 | Scrapper-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-17 09:00 | 2020-04-15 18:00 | 2020-03-26 09:00 | 2020-05-30 18:00 |  |  | 2020-05-30 10:57 | 2020-05-30 10:57 |  |  | 100 | 100 | [15 empty] | 0.47458 | 0.000712 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2748 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018067
451 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.5.2.3 | Technological Structure-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-21 09:00 | 2020-04-19 23:59 | 2020-03-17 09:00 | 2020-07-06 18:00 |  |  | 2020-03-18 12:44 | 2020-07-06 12:44 |  |  | 100 | 100 | [15 empty] | 2.5763 | 0.003864 | 0.38 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2749 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018068
452 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.5.2.3 | Takeup Component-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-19 09:00 | 2020-07-18 18:00 | 2020-04-16 09:00 | 2020-08-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.13559 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2750 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018069
453 | Task(Task)-->P (Procurement) | Gear Box |  | 1.5.2.3 | Gear Box-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-27 09:00 | 2020-03-27 18:00 | 2020-03-20 09:00 | 2020-04-30 18:00 |  |  | 2020-03-21 11:21 | 2020-04-30 11:21 |  |  | 100 | 100 | [15 empty] | 2.7119 | 0.004068 | 0.4 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2751 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018070
454 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.5.2.3 | Geared Coupling-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-20 09:00 | 2020-04-18 18:00 | 2020-04-13 09:00 | 2020-04-30 18:00 |  |  | 2020-04-14 11:11 | 2020-04-30 11:11 |  |  | 100 | 100 | [15 empty] | 0.33898 | 0.000508 | 0.05 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2752 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018071
455 | Task(Task)-->P (Procurement) | Fluid Coupling |  | 1.5.2.3 | Fluid Coupling-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-02 09:00 | 2020-03-31 18:00 | 2020-04-13 09:00 | 2020-05-18 18:00 |  |  | 2020-04-14 09:54 | 2020-05-18 16:05 |  |  | 100 | 100 | [15 empty] | 2.8475 | 0.004271 | 0.42 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2753 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018072
456 | Task(Task)-->P (Procurement) | Brake |  | 1.5.2.3 | Brake-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-10 09:00 | 2020-04-08 18:00 | 2020-04-22 09:00 | 2020-05-18 18:00 |  |  | 2020-04-23 11:38 | 2020-05-18 16:05 |  |  | 100 | 100 | [15 empty] | 0.27119 | 0.000407 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2754 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018073
457 | Task(Task)-->P (Procurement) | Building Structure |  | 1.5.2.3 | Building Structure-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-12 | 2020-05-11 18:00 | 2020-05-29 09:00 | 2020-05-31 23:59 |  |  | 2020-05-31 18:49 | 2020-05-31 18:49 |  |  | 100 | 100 | [15 empty] | 29.8305 | 0.044743 | 4.4 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2755 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018074
458 | Task(Task)-->P (Procurement) | HT AC MOTORS |  | 1.5.2.3 | HT AC MOTORS-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-07 09:00 | 2020-03-07 18:00 | 2020-04-11 09:00 | 2020-06-25 18:00 |  |  | 2020-04-13 09:41 | 2020-06-25 09:41 |  |  | 100 | 100 | [15 empty] | 7.8644 | 0.011796 | 1.16 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2756 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018075
459 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.5.2.3 | LIGHT & LIGHT FIXTURES-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-26 09:00 | 2020-04-10 18:00 | 2020-06-02 09:00 | 2020-07-31 18:00 |  |  | 2020-06-03 15:51 | 2020-06-29 15:51 |  |  | 100 | 100 | [15 empty] | 3.5932 | 0.00539 | 0.53 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2757 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018076
460 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.5.2.3 | LIGHTING POLES-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-12 09:00 | 2020-06-25 18:00 | 2020-06-03 09:00 | 2020-06-24 18:00 |  |  | 2020-06-15 10:57 | 2020-06-15 10:57 |  |  | 100 | 100 | [15 empty] | 1.6271 | 0.002441 | 0.24 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2758 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018077
461 | Task(Task)-->P (Procurement) | LPBS |  | 1.5.2.3 | LPBS-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-05 | 2020-04-20 18:00 | 2020-06-12 09:00 | 2020-08-19 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.067797 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2759 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018078
462 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.5.2.3 | CONVEYOR BELT PROTECTION SWITCHES-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-23 09:00 | 2020-02-05 18:00 | 2020-03-10 09:00 | 2020-08-17 18:00 | [6 empty] | 100 | 0 | [15 empty] | 1.3559 | 0.002034 | 0.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2761 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018079
463 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.5.2.3 | ZERO SPEED SWITCH-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-17 09:00 | 2020-02-01 18:00 | 2020-03-07 09:00 | 2020-08-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2762 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018080
464 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.5.2.3 | CHUTE BLOCK SWITCH-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-19 | 2020-01-31 18:00 | 2020-01-16 09:00 | 2020-02-01 18:00 |  |  | 2020-02-01 10:57 | 2020-02-01 10:57 |  |  | 100 | 100 | [15 empty] | 0.067797 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2763 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018081
465 | Task(Task)-->P (Procurement) | ITP APPROVAL | 1.5.2.4 | 1.5.2 | ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-02-01 09:00 | 2020-08-25 18:00 | 2020-02-03 09:00 | 2020-11-30 18:00 |  |  | 2020-02-03 15:21 |  |  |  | 100 | 39.7963 | [15 empty] | 5.002 | 0.075047 | 7.38 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2764 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018082
466 | Task(Task)-->P (Procurement) | Suspended Magnet |  | 1.5.2.4 | Suspended Magnet-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-07 09:00 | 2020-03-17 18:00 | 2020-02-03 09:00 | 2020-02-24 18:00 |  |  | 2020-02-03 15:21 | 2020-02-24 15:21 |  |  | 100 | 100 | [15 empty] | 10.4054 | 0.007809 | 0.77 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2765 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018083
467 | Task(Task)-->P (Procurement) | Belt Scale |  | 1.5.2.4 | Belt Scale-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-04 09:00 | 2020-04-12 23:59 | 2020-02-03 09:00 | 2020-09-09 18:00 |  |  | 2020-02-03 15:27 |  |  |  | 100 | 50 | [15 empty] | 2.027 | 0.001521 | 0.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2766 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018084
468 | Task(Task)-->P (Procurement) | Metal Detector |  | 1.5.2.4 | Metal Detector-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-06 09:00 | 2020-03-16 18:00 | 2020-03-20 09:00 | 2020-09-02 18:00 |  |  | 2020-03-20 16:01 | 2020-09-02 16:01 |  |  | 100 | 100 | [15 empty] | 2.027 | 0.001521 | 0.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2767 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018085
469 | Task(Task)-->P (Procurement) | Pulley |  | 1.5.2.4 | Pulley-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-04 09:00 | 2020-03-14 18:00 | 2020-03-21 09:00 | 2020-05-11 18:00 | [6 empty] | 100 | 0 | [15 empty] | 12.027 | 0.009026 | 0.89 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2768 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018086
470 | Task(Task)-->P (Procurement) | Idler |  | 1.5.2.4 | Idler-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-03 09:00 | 2020-04-11 18:00 | 2020-04-30 09:00 | 2020-05-19 18:00 |  |  | 2020-04-13 16:20 | 2020-05-19 16:20 |  |  | 100 | 100 | [15 empty] | 8.5135 | 0.006389 | 0.63 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2769 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018087
471 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.5.2.4 | Plummer Block-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-02 09:00 | 2020-08-10 18:00 | 2020-03-24 09:00 | 2020-08-13 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.94595 | 0.00071 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2770 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018088
472 | Task(Task)-->P (Procurement) | Bearing |  | 1.5.2.4 | Bearing-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-17 09:00 | 2020-08-25 18:00 | 2020-03-24 09:00 | 2020-03-29 23:59 | [6 empty] | 100 | 0 | [15 empty] | 1.4865 | 0.001116 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2771 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018089
473 | Task(Task)-->P (Procurement) | Belting |  | 1.5.2.4 | Belting-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-21 09:00 | 2020-03-31 18:00 | 2020-09-04 09:00 | 2020-09-30 18:00 |  |  | 2020-09-04 16:30 | 2020-09-30 16:30 |  |  | 100 | 100 | [15 empty] | 8.7838 | 0.006592 | 0.65 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2772 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018090
474 | Task(Task)-->P (Procurement) | Scrapper |  | 1.5.2.4 | Scrapper-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-16 09:00 | 2020-05-25 18:00 | 2020-05-30 09:00 | 2020-06-25 18:00 |  |  | 2020-05-30 16:31 | 2020-06-25 16:31 |  |  | 100 | 100 | [15 empty] | 0.54054 | 0.000406 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2773 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018091
475 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.5.2.4 | Technological Structure-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-20 09:00 | 2020-05-29 18:00 | 2020-07-06 09:00 | 2020-07-16 18:00 | [6 empty] | 100 | 0 | [15 empty] | 2.5676 | 0.001927 | 0.19 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2774 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018092
476 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.5.2.4 | Takeup Component-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-19 | 2020-08-17 18:00 | 2020-06-25 09:00 | 2020-06-25 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.13514 | 0.000101 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2775 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018093
477 | Task(Task)-->P (Procurement) | Gear Box |  | 1.5.2.4 | Gear Box-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-28 09:00 | 2020-05-06 18:00 | 2020-04-30 09:00 | 2020-06-22 18:00 |  |  | 2020-04-30 16:57 | 2020-06-22 16:57 |  |  | 100 | 100 | [15 empty] | 2.7027 | 0.002028 | 0.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2776 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018094
478 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.5.2.4 | Geared Coupling-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-19 | 2020-05-28 18:00 | 2020-04-30 09:00 | 2020-06-18 18:00 |  |  | 2020-04-30 01:54 | 2020-06-18 17:31 |  |  | 100 | 100 | [15 empty] | 0.40541 | 0.000304 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2777 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018095
479 | Task(Task)-->P (Procurement) | Fluid Coupling |  | 1.5.2.4 | Fluid Coupling-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-01 09:00 | 2020-05-10 23:59 | 2020-05-18 09:00 | 2020-08-18 18:00 | [6 empty] | 100 | 0 | [15 empty] | 2.8378 | 0.00213 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2778 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018096
480 | Task(Task)-->P (Procurement) | Brake |  | 1.5.2.4 | Brake-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-09 09:00 | 2020-05-18 18:00 | 2020-05-18 09:00 | 2020-10-14 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.27027 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2779 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018097
481 | Task(Task)-->P (Procurement) | Building Structure |  | 1.5.2.4 | Building Structure-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-12 09:00 | 2020-05-18 18:00 | 2020-05-31 | 2020-08-04 18:00 |  |  | 2020-06-25 19:04 |  |  |  | 100 | 0 | [15 empty] | 29.7297 | 0.022311 | 2.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2780 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018098
482 | Task(Task)-->P (Procurement) | HT AC MOTORS |  | 1.5.2.4 | HT AC MOTORS-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-08 | 2020-04-16 18:00 | 2020-09-11 09:00 | 2020-11-10 18:00 |  |  | 2020-09-11 15:19 |  |  |  | 100 | 0 | [15 empty] | 7.8378 | 0.005882 | 0.58 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2781 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018099
483 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.5.2.4 | LIGHT & LIGHT FIXTURES-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-11 09:00 | 2020-05-20 18:00 | 2020-07-28 09:00 | 2020-09-08 18:00 |  |  | 2020-07-08 17:23 | 2020-09-08 17:23 |  |  | 100 | 100 | [15 empty] | 3.6486 | 0.002738 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2782 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018100
484 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.5.2.4 | LIGHTING POLES-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-06-26 09:00 | 2020-08-04 18:00 | 2020-06-23 09:00 | 2020-09-08 18:00 |  |  | 2020-06-23 17:28 | 2020-09-08 17:05 |  |  | 100 | 100 | [15 empty] | 1.6216 | 0.001217 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2783 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018101
485 | Task(Task)-->P (Procurement) | LPBS |  | 1.5.2.4 | LPBS-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-21 09:00 | 2020-05-30 18:00 | 2020-07-29 09:00 | 2020-08-21 18:00 |  |  | 2020-07-29 14:57 | 2020-08-22 12:53 |  |  | 100 | 100 | [15 empty] | 0.13514 | 0.000101 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2784 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018102
486 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.5.2.4 | CONVEYOR BELT PROTECTION SWITCHES-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-06 09:00 | 2020-03-16 18:00 | 2020-09-24 09:00 | 2020-11-30 18:00 | [6 empty] | 100 | 0 | [15 empty] | 1.3514 | 0.001014 | 0.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2786 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018103
487 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.5.2.4 | ZERO SPEED SWITCH-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-02 | 2020-02-22 18:00 | 2020-08-02 | 2020-08-22 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2787 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018104
488 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.5.2.4 | CHUTE BLOCK SWITCH-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-01 09:00 | 2020-03-11 18:00 | 2020-07-02 09:00 | 2020-08-04 18:00 |  |  | 2020-07-17 16:57 | 2020-08-04 16:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2788 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018105
489 | Task(Task)-->P (Procurement) | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE | 1.5.2.5 | 1.5.2 | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-02-01 09:00 | 2020-09-16 18:00 | 2020-02-01 09:00 | 2020-11-16 18:00 |  |  | 2020-02-04 12:47 |  |  |  | 100 | 88.9066 | [15 empty] | 14.9993 | 0.22504 | 22.13 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2789 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018106
490 | Task(Task)-->P (Procurement) | Suspended Magnet |  | 1.5.2.5 | Suspended Magnet-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-07 09:00 | 2020-04-06 18:00 | 2020-02-03 09:00 | 2020-04-24 18:00 |  |  | 2020-02-04 12:47 | 2020-04-24 10:57 |  |  | 100 | 100 | [15 empty] | 10.4383 | 0.02349 | 2.31 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2790 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018107
491 | Task(Task)-->P (Procurement) | Belt Scale |  | 1.5.2.5 | Belt Scale-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-04 09:00 | 2020-05-02 18:00 | 2020-02-03 09:00 | 2020-07-25 18:00 |  |  | 2020-06-16 15:39 | 2020-07-25 00:58 |  |  | 100 | 100 | [15 empty] | 2.0334 | 0.004576 | 0.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2791 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018108
492 | Task(Task)-->P (Procurement) | Metal Detector |  | 1.5.2.5 | Metal Detector-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-06 09:00 | 2020-04-05 23:59 | 2020-03-20 09:00 | 2020-08-13 18:00 |  |  | 2020-07-03 15:41 | 2020-07-27 01:07 |  |  | 100 | 100 | [15 empty] | 2.0334 | 0.004576 | 0.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2792 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018109
493 | Task(Task)-->P (Procurement) | Pulley |  | 1.5.2.5 | Pulley-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-04 09:00 | 2020-03-29 23:59 | 2020-03-21 09:00 | 2020-03-25 18:00 |  |  | 2020-03-22 18:03 | 2020-03-25 18:03 |  |  | 100 | 100 | [15 empty] | 12.0651 | 0.027151 | 2.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2793 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018110
494 | Task(Task)-->P (Procurement) | Idler |  | 1.5.2.5 | Idler-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-03 09:00 | 2020-05-01 18:00 | 2020-04-30 09:00 | 2020-06-25 18:00 |  |  | 2020-06-25 14:53 | 2020-06-25 14:53 |  |  | 100 | 100 | [15 empty] | 8.4953 | 0.019118 | 1.88 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2794 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018111
495 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.5.2.5 | Plummer Block-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-07-02 09:00 | 2020-08-30 23:59 | 2020-03-24 09:00 | 2020-06-29 18:00 |  |  | 2020-05-14 14:59 | 2020-06-29 14:59 |  |  | 100 | 100 | [15 empty] | 0.90375 | 0.002034 | 0.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2795 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018112
496 | Task(Task)-->P (Procurement) | Bearing |  | 1.5.2.5 | Bearing-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-07-17 09:00 | 2020-07-17 18:00 | 2020-03-24 09:00 | 2020-03-24 18:00 |  |  | 2020-03-24 10:05 | 2020-03-24 10:05 |  |  | 100 | 100 | [15 empty] | 1.4912 | 0.003356 | 0.33 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2796 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018113
497 | Task(Task)-->P (Procurement) | Belting |  | 1.5.2.5 | Belting-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-21 09:00 | 2020-04-20 18:00 | 2020-09-04 09:00 | 2020-11-15 23:59 |  |  | 2020-09-04 16:36 |  |  |  | 100 | 50 | [15 empty] | 8.8116 | 0.019829 | 1.95 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2797 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018114
498 | Task(Task)-->P (Procurement) | Scrapper |  | 1.5.2.5 | Scrapper-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-16 09:00 | 2020-06-14 23:59 | 2020-05-30 09:00 | 2020-07-30 18:00 |  |  | 2020-05-30 16:36 | 2020-07-30 16:36 |  |  | 100 | 100 | [15 empty] | 0.49706 | 0.001119 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2798 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018115
499 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.5.2.5 | Technological Structure-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-20 09:00 | 2020-09-16 18:00 | 2020-07-06 09:00 | 2020-07-06 18:00 |  |  | 2020-07-06 12:45 | 2020-07-06 12:45 |  |  | 100 | 100 | [15 empty] | 2.5757 | 0.005796 | 0.57 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2799 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018116
500 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.5.2.5 | Takeup Component-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-19 | 2020-08-27 18:00 | 2020-08-04 09:00 | 2020-08-04 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.13556 | 0.000305 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2800 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018117
501 | Task(Task)-->P (Procurement) | Gear Box |  | 1.5.2.5 | Gear Box-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-28 09:00 | 2020-05-26 18:00 | 2020-04-30 09:00 | 2020-07-01 18:00 |  |  | 2020-04-30 15:33 | 2020-07-01 15:33 |  |  | 100 | 100 | [15 empty] | 2.7113 | 0.006101 | 0.6 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2801 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018118
502 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.5.2.5 | Geared Coupling-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-19 | 2020-06-17 18:00 | 2020-04-30 09:00 | 2020-07-30 18:00 |  |  | 2020-04-30 15:31 | 2020-07-06 15:31 |  |  | 100 | 100 | [15 empty] | 0.3615 | 0.000814 | 0.08 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2802 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018119
503 | Task(Task)-->P (Procurement) | Fluid Coupling |  | 1.5.2.5 | Fluid Coupling-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-01 09:00 | 2020-05-30 18:00 | 2020-05-18 09:00 | 2020-08-21 18:00 | [6 empty] | 100 | 0 | [15 empty] | 2.8016 | 0.006305 | 0.62 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2803 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018120
504 | Task(Task)-->P (Procurement) | Brake |  | 1.5.2.5 | Brake-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-09 09:00 | 2020-06-07 23:59 | 2020-05-18 09:00 | 2020-08-13 18:00 |  |  | 2020-06-18 17:35 |  |  |  | 100 | 50 | [15 empty] | 0.27113 | 0.00061 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2804 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018121
505 | Task(Task)-->P (Procurement) | Building Structure |  | 1.5.2.5 | Building Structure-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-10 | 2020-05-16 18:00 | 2020-05-31 | 2020-06-23 18:00 |  |  | 2020-05-31 18:54 | 2020-06-27 18:54 |  |  | 100 | 100 | [15 empty] | 29.7786 | 0.067013 | 6.59 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2805 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018122
506 | Task(Task)-->P (Procurement) | HT AC MOTORS |  | 1.5.2.5 | HT AC MOTORS-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-08 | 2020-05-21 18:00 | 2020-07-18 09:00 | 2020-09-28 18:00 |  |  | 2020-07-18 09:04 | 2020-09-28 10:23 |  |  | 100 | 100 | [15 empty] | 7.8626 | 0.017694 | 1.74 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2806 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018123
507 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.5.2.5 | LIGHT & LIGHT FIXTURES-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-11 09:00 | 2020-05-25 18:00 | 2020-07-10 09:00 | 2020-11-16 18:00 |  |  | 2020-07-14 10:44 |  |  |  | 100 | 0 | [15 empty] | 3.615 | 0.008135 | 0.8 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2807 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018124
508 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.5.2.5 | LIGHTING POLES-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-06-26 09:00 | 2020-08-09 23:59 | 2020-05-30 09:00 | 2020-08-08 18:00 |  |  | 2020-06-18 17:06 | 2020-08-07 15:00 |  |  | 100 | 100 | [15 empty] | 1.6268 | 0.003661 | 0.36 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2808 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018125
509 | Task(Task)-->P (Procurement) | LPBS |  | 1.5.2.5 | LPBS-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-21 09:00 | 2020-06-04 18:00 | 2020-07-25 09:00 | 2020-08-22 18:00 |  |  | 2020-07-24 18:42 | 2020-08-22 12:57 |  |  | 100 | 100 | [15 empty] | 0.090375 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2809 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018126
510 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.5.2.5 | CONVEYOR BELT PROTECTION SWITCHES-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-06 09:00 | 2020-03-21 18:00 | 2020-08-11 09:00 | 2020-09-19 18:00 |  |  | 2020-08-11 13:11 | 2020-09-19 12:57 |  |  | 100 | 100 | [15 empty] | 1.3556 | 0.003051 | 0.3 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2811 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018127
511 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.5.2.5 | ZERO SPEED SWITCH-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-02 | 2020-03-03 18:00 | 2020-08-09 | 2020-10-29 18:00 |  |  | 2020-08-09 13:14 | 2020-10-29 12:56 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2812 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018128
512 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.5.2.5 | CHUTE BLOCK SWITCH-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-01 09:00 | 2020-03-16 18:00 | 2020-02-01 09:00 | 2020-07-15 18:00 |  |  | 2020-02-11 21:26 | 2020-07-15 21:26 |  |  | 100 | 100 | [15 empty] | 0.045188 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2813 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018129
513 | Task(Task)-->P (Procurement) | MANUFACTURING & RECEIPT AT SITE (MRN) | 1.5.2.6 | 1.5.2 | MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-04 09:00 | 2021-02-13 18:00 | 2020-03-24 09:00 | 2021-06-13 23:59 |  |  | 2020-03-25 18:05 |  |  |  | 95.5148 | 9.3104 | [15 empty] | 59.9973 | 0.90015 | 88.52 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2814 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018130
514 | Task(Task)-->P (Procurement) | Suspended Magnet |  | 1.5.2.6 | Suspended Magnet-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-07 09:00 | 2020-10-03 18:00 | 2020-04-24 09:00 | 2020-11-30 18:00 |  |  | 2020-04-24 15:22 |  |  |  | 100 | 60 | [15 empty] | 10.4597 | 0.094154 | 9.26 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2815 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018131
515 | Task(Task)-->P (Procurement) | Belt Scale |  | 1.5.2.6 | Belt Scale-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-03 | 2020-10-29 18:00 | 2020-07-25 09:00 | 2020-11-30 18:00 |  |  | 2020-07-25 15:31 |  |  |  | 100 | 70 | [15 empty] | 2.0106 | 0.018099 | 1.78 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2816 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018132
516 | Task(Task)-->P (Procurement) | Metal Detector |  | 1.5.2.6 | Metal Detector-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-06 09:00 | 2020-10-02 18:00 | 2020-08-13 09:00 | 2020-12-31 18:00 |  |  | 2020-08-13 16:02 |  |  |  | 100 | 25 | [15 empty] | 2.0219 | 0.0182 | 1.79 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2817 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018133
517 | Task(Task)-->P (Procurement) | Pulley |  | 1.5.2.6 | Pulley-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-30 09:00 | 2020-11-20 18:00 | 2020-03-25 09:00 | 2020-11-30 18:00 |  |  | 2020-03-25 18:05 |  |  |  | 95.7627 | 0 | [15 empty] | 12.0637 | 0.10859 | 10.68 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2818 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018134
518 | Task(Task)-->P (Procurement) | Idler |  | 1.5.2.6 | Idler-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-02 09:00 | 2020-11-13 18:00 | 2020-06-25 09:00 | 2020-12-31 18:00 | [6 empty] | 98.4694 | 0 | [15 empty] | 8.5056 | 0.076563 | 7.53 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2819 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018135
519 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.5.2.6 | Plummer Block-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-31 09:00 | 2020-12-23 18:00 | 2020-06-29 09:00 | 2020-12-31 18:00 | [6 empty] | 62.6087 | 0 | [15 empty] | 0.88106 | 0.007931 | 0.78 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2820 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018136
520 | Task(Task)-->P (Procurement) | Bearing |  | 1.5.2.6 | Bearing-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-26 09:00 | 2020-12-23 18:00 | 2020-03-24 09:00 | 2020-09-09 18:00 | [6 empty] | 64.1667 | 0 | [15 empty] | 1.5023 | 0.013523 | 1.33 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2821 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018137
521 | Task(Task)-->P (Procurement) | Belting |  | 1.5.2.6 | Belting-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-21 09:00 | 2020-11-16 18:00 | 2020-11-16 09:00 | 2021-06-13 23:59 | [6 empty] | 97.1429 | 0 | [15 empty] | 8.7993 | 0.079207 | 7.79 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2822 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018138
522 | Task(Task)-->P (Procurement) | Scrapper |  | 1.5.2.6 | Scrapper-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-15 09:00 | 2020-12-11 18:00 | 2020-07-30 09:00 | 2020-12-31 18:00 | [6 empty] | 82.7778 | 0 | [15 empty] | 0.49701 | 0.004474 | 0.44 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2823 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018139
523 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.5.2.6 | Technological Structure-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-19 09:00 | 2021-02-13 18:00 | 2020-07-06 09:00 | 2021-01-31 23:59 | [6 empty] | 60.4167 | 0 | [15 empty] | 2.5641 | 0.023081 | 2.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2824 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018140
524 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.5.2.6 | Takeup Component-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-28 09:00 | 2020-12-25 18:00 | 2020-08-04 09:00 | 2020-12-25 18:00 | [6 empty] | 62.5 | 0 | [15 empty] | 0.14684 | 0.001322 | 0.13 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2825 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018141
525 | Task(Task)-->P (Procurement) | Gear Box |  | 1.5.2.6 | Gear Box-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-27 09:00 | 2020-12-22 18:00 | 2020-07-01 09:00 | 2020-12-31 18:00 |  |  | 2020-07-01 17:25 |  |  |  | 80 | 30 | [15 empty] | 2.7222 | 0.024504 | 2.41 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2826 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018142
526 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.5.2.6 | Geared Coupling-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-18 09:00 | 2020-12-15 18:00 | 2020-07-30 09:00 | 2020-11-30 18:00 |  |  | 2020-07-30 17:44 |  |  |  | 80.663 | 90 | [15 empty] | 0.33887 | 0.00305 | 0.3 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2827 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018143
527 | Task(Task)-->P (Procurement) | Fluid Coupling |  | 1.5.2.6 | Fluid Coupling-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-31 | 2020-12-26 18:00 | 2020-08-21 09:00 | 2021-01-31 23:59 | [6 empty] | 78.0952 | 0 | [15 empty] | 2.8126 | 0.025318 | 2.49 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2828 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018144
528 | Task(Task)-->P (Procurement) | Brake |  | 1.5.2.6 | Brake-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-08 09:00 | 2020-12-04 18:00 | 2020-08-13 09:00 | 2020-11-30 18:00 | [6 empty] | 86.6667 | 0 | [15 empty] | 0.28239 | 0.002542 | 0.25 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2829 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018145
529 | Task(Task)-->P (Procurement) | Building Structure |  | 1.5.2.6 | Building Structure-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-19 09:00 | 2020-10-19 18:00 | 2020-06-23 09:00 | 2021-03-31 18:00 | [6 empty] | 100 | 0 | [15 empty] | 29.7978 | 0.26823 | 26.38 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2830 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018146
530 | Task(Task)-->P (Procurement) | HT AC MOTORS |  | 1.5.2.6 | HT AC MOTORS-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-22 09:00 | 2020-11-17 18:00 | 2020-11-11 09:00 | 2021-05-09 23:59 |  |  | 2020-09-28 10:25 |  |  |  | 96.1111 | 0 | [15 empty] | 7.8504 | 0.070666 | 6.95 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2831 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018147
531 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.5.2.6 | LIGHT & LIGHT FIXTURES-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-26 09:00 | 2020-10-21 18:00 | 2020-11-17 09:00 | 2021-04-14 18:00 | [6 empty] | 100 | 0 | [15 empty] | 3.6033 | 0.032435 | 3.19 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2832 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018148
532 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.5.2.6 | LIGHTING POLES-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-10 09:00 | 2020-11-07 18:00 | 2020-09-09 09:00 | 2020-12-07 18:00 |  |  | 2020-08-07 15:00 |  |  |  | 100 | 0 | [15 empty] | 1.6379 | 0.014743 | 1.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2833 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018149
533 | Task(Task)-->P (Procurement) | LPBS |  | 1.5.2.6 | LPBS-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-05 09:00 | 2020-09-16 18:00 | 2020-08-23 | 2020-12-04 18:00 |  |  | 2020-08-22 13:00 |  |  |  | 100 | 0 | [15 empty] | 0.090365 | 0.000813 | 0.08 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2834 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018150
534 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.5.2.6 | CONVEYOR BELT PROTECTION SWITCHES-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-22 | 2020-08-05 18:00 | 2020-12-01 09:00 | 2021-04-16 18:00 | [6 empty] | 100 | 0 | [15 empty] | 1.3668 | 0.012303 | 1.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2836 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018151
535 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.5.2.6 | ZERO SPEED SWITCH-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-04 09:00 | 2020-07-02 18:00 | 2020-10-30 09:00 | 2021-02-27 18:00 |  |  | 2020-10-29 12:56 |  |  |  | 100 | 0 | [15 empty] | 0.011296 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2837 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018152
536 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.5.2.6 | CHUTE BLOCK SWITCH-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-17 09:00 | 2020-07-31 18:00 | 2020-07-02 09:00 | 2020-11-15 23:59 |  |  | 2020-07-15 21:34 |  |  |  | 100 | 0 | [15 empty] | 0.033887 | 0.000305 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2838 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018153
537 | Task(Task)-->C (Construction) | CONSTRUCTION | 1.5.3 | 1.5 | CONSTRUCTION-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-04 09:00 | 2021-09-08 18:00 | 2020-08-01 09:00 | 2022-05-01 23:59 | [6 empty] | 16.2809 | 0 | [15 empty] | 24.1166 | 0.51984 | 51.12 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2839 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018154
538 | Task(Task)-->C (Construction) | CIVIL | 1.5.3.1 | 1.5.3 | CIVIL-->CONSTRUCTION-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-04 09:00 | 2020-07-08 18:00 | 2020-08-01 09:00 | 2020-11-03 18:00 | [6 empty] | 100 | 0 | [15 empty] | 10.1526 | 0.052777 | 5.19 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2840 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018155
539 | Task(Task)-->C (Construction) | AVAILABILITY OF FRONT BY NTPC |  | 1.5.3.1 | AVAILABILITY OF FRONT BY NTPC-->CIVIL-->CONSTRUCTION-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-04 09:00 | 2020-04-04 18:00 | 2020-08-01 09:00 | 2020-08-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2841 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018156
540 | Task(Task)-->C (Construction) | EXCAVATION |  | 1.5.3.1 | EXCAVATION-->CIVIL-->CONSTRUCTION-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-25 09:00 | 2020-06-06 18:00 | 2020-08-02 | 2020-08-14 18:00 | [6 empty] | 100 | 0 | [15 empty] | 12.3314 | 0.006508 | 0.64 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 2408 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2842 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | Excavation | [23 empty] | 1018157
541 | Task(Task)-->C (Construction) | PCC |  | 1.5.3.1 | PCC-->CIVIL-->CONSTRUCTION-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-29 09:00 | 2020-06-08 18:00 | 2020-09-24 09:00 | 2020-10-04 23:59 | [6 empty] | 100 | 0 | [15 empty] | 3.8536 | 0.002034 | 0.2 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2843 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | PCC | [23 empty] | 1018158
542 | Task(Task)-->C (Construction) | FOUNDATIONS - RAFT |  | 1.5.3.1 | FOUNDATIONS - RAFT-->CIVIL-->CONSTRUCTION-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-05 09:00 | 2020-06-23 18:00 | 2020-10-01 09:00 | 2020-10-19 18:00 | [6 empty] | 100 | 0 | [15 empty] | 58.1888 | 0.03071 | 3.02 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 114 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2844 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018159
543 | Task(Task)-->C (Construction) | PADESTALS FOR SC-1A,SC-1B, SC-2A & SC-2B CONV. STR. |  | 1.5.3.1 | PADESTALS FOR SC-1A,SC-1B, SC-2A & SC-2B CONV. STR.-->CIVIL-->CONSTRUCTION-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-15 09:00 | 2020-07-08 18:00 | 2020-10-11 | 2020-11-03 18:00 | [6 empty] | 100 | 0 | [15 empty] | 25.6262 | 0.013525 | 1.33 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2845 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018160
544 | Task(Task)-->C (Construction) | STRUCTURAL WORKS | 1.5.3.2 | 1.5.3 | STRUCTURAL WORKS-->CONSTRUCTION-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-10-20 09:00 | 2021-03-18 18:00 | 2021-04-01 09:00 | 2021-08-28 18:00 | [6 empty] | 14.6667 | 0 | [15 empty] | 41.784 | 0.21721 | 21.36 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2846 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018161
545 | Task(Task)-->C (Construction) | ERECTION OF STRUCTURAL STEEL |  | 1.5.3.2 | ERECTION OF STRUCTURAL STEEL-->STRUCTURAL WORKS-->CONSTRUCTION-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-10-20 09:00 | 2021-03-18 18:00 | 2021-04-01 09:00 | 2021-08-28 18:00 | [6 empty] | 14.6667 | 0 | [15 empty] | 100 | 0.21721 | 21.36 | Plan & Actual | Quantity | Metric Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 330 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2847 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018162
546 | Task(Task)-->C (Construction) | MECHANICAL EQUIPMENT WORKS | 1.5.3.3 | 1.5.3 | MECHANICAL EQUIPMENT WORKS-->CONSTRUCTION-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-03-19 09:00 | 2021-07-28 18:00 | 2021-08-29 | 2022-01-07 18:00 | [6 empty] | 0 | 0 | [15 empty] | 21.2637 | 0.11054 | 10.87 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5451 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018163
547 | Task(Task)-->C (Construction) | ERECTION OF CONVEYOR SC 1A |  | 1.5.3.3 | ERECTION OF CONVEYOR SC 1A-->MECHANICAL EQUIPMENT WORKS-->CONSTRUCTION-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-03-19 09:00 | 2021-05-17 18:00 | 2021-08-29 | 2021-10-27 18:00 | [6 empty] | 0 | 0 | [15 empty] | 23.6648 | 0.026158 | 2.57 | Plan & Actual | Quantity | Meter | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2848 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018164
548 | Task(Task)-->C (Construction) | ERECTION OF CONVEYOR SC 1B |  | 1.5.3.3 | ERECTION OF CONVEYOR SC 1B-->MECHANICAL EQUIPMENT WORKS-->CONSTRUCTION-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-03-19 09:00 | 2021-05-17 18:00 | 2021-08-29 | 2021-10-27 18:00 | [6 empty] | 0 | 0 | [15 empty] | 23.6648 | 0.026158 | 2.57 | Plan & Actual | Quantity | Meter | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5407 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018165
549 | Task(Task)-->C (Construction) | ERECTION OF CONVEYOR SC 2A |  | 1.5.3.3 | ERECTION OF CONVEYOR SC 2A-->MECHANICAL EQUIPMENT WORKS-->CONSTRUCTION-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-05-18 09:00 | 2021-07-16 18:00 | 2021-10-28 09:00 | 2021-12-26 23:59 | [6 empty] | 0 | 0 | [15 empty] | 23.6648 | 0.026158 | 2.57 | Plan & Actual | Quantity | Meter | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5408 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018166
550 | Task(Task)-->C (Construction) | ERECTION OF CONVEYOR SC 2B |  | 1.5.3.3 | ERECTION OF CONVEYOR SC 2B-->MECHANICAL EQUIPMENT WORKS-->CONSTRUCTION-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-05-18 09:00 | 2021-07-16 18:00 | 2021-10-28 09:00 | 2021-12-26 23:59 | [6 empty] | 0 | 0 | [15 empty] | 23.6648 | 0.026158 | 2.57 | Plan & Actual | Quantity | Meter | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5409 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018167
551 | Task(Task)-->C (Construction) | ERECTION OF SUSPENDED MAGNET |  | 1.5.3.3 | ERECTION OF SUSPENDED MAGNET-->MECHANICAL EQUIPMENT WORKS-->CONSTRUCTION-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-07-17 09:00 | 2021-07-28 18:00 | 2021-12-27 09:00 | 2022-01-07 18:00 | [6 empty] | 0 | 0 | [15 empty] | 2.0258 | 0.002239 | 0.22 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5411 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018168
552 | Task(Task)-->C (Construction) | ERECTION OF METAL DETECTOR |  | 1.5.3.3 | ERECTION OF METAL DETECTOR-->MECHANICAL EQUIPMENT WORKS-->CONSTRUCTION-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-07-17 09:00 | 2021-07-28 18:00 | 2021-12-27 09:00 | 2022-01-07 18:00 | [6 empty] | 0 | 0 | [15 empty] | 1.6575 | 0.001832 | 0.18 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5412 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018169
553 | Task(Task)-->C (Construction) | ERECTION OF BELT SCALE |  | 1.5.3.3 | ERECTION OF BELT SCALE-->MECHANICAL EQUIPMENT WORKS-->CONSTRUCTION-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-07-17 09:00 | 2021-07-28 18:00 | 2021-12-27 09:00 | 2022-01-07 18:00 | [6 empty] | 0 | 0 | [15 empty] | 1.6575 | 0.001832 | 0.18 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5410 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018170
554 | Task(Task)-->C (Construction) | BELT LAYING & JOINTING WORK |  | 1.5.3 | BELT LAYING & JOINTING WORK-->CONSTRUCTION-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-06-02 09:00 | 2021-07-31 18:00 | 2021-11-12 09:00 | 2022-01-10 18:00 | [6 empty] | 0 | 0 | [15 empty] | 3.3451 | 0.017389 | 1.71 | Plan & Actual | Quantity | Meter | 0 | 0 | 0 | 0 | 0 | 0 | 1100 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5452 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018171
555 | Task(Task)-->C (Construction) | ELECTRICAL & INSTRUMENTATION | 1.5.3.5 | 1.5.3 | ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-03-14 | 2021-08-25 18:00 | 2021-08-24 09:00 | 2022-04-17 23:59 | [6 empty] | 0 | 0 | [15 empty] | 11.4241 | 0.059387 | 5.84 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2850 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018172
556 | Task(Task)-->C (Construction) | CABLE TRAY |  | 1.5.3.5 | CABLE TRAY-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-03-19 09:00 | 2021-03-23 18:00 | 2021-08-29 | 2021-09-02 18:00 | [6 empty] | 0 | 0 | [15 empty] | 5.4889 | 0.00326 | 0.32 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2851 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018173
557 | Task(Task)-->C (Construction) | POWER CABLE |  | 1.5.3.5 | POWER CABLE-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-07-29 09:00 | 2021-08-01 23:59 | 2022-01-08 09:00 | 2022-01-11 18:00 | [6 empty] | 0 | 0 | [15 empty] | 15.4374 | 0.009168 | 0.9 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 6387 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2852 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018174
558 | Task(Task)-->C (Construction) | CONTROL CABLE |  | 1.5.3.5 | CONTROL CABLE-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-07-31 09:00 | 2021-08-01 23:59 | 2022-01-10 09:00 | 2022-01-11 18:00 | [6 empty] | 0 | 0 | [15 empty] | 4.1166 | 0.002445 | 0.24 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 1700 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2853 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018175
559 | Task(Task)-->C (Construction) | EARTHING |  | 1.5.3.5 | EARTHING-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-03-19 09:00 | 2021-03-23 18:00 | 2021-08-29 | 2021-09-02 18:00 | [6 empty] | 0 | 0 | [15 empty] | 6.6895 | 0.003973 | 0.39 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 1760 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2854 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018176
560 | Task(Task)-->C (Construction) | LIGHTING |  | 1.5.3.5 | LIGHTING-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-03-14 | 2021-03-28 23:59 | 2021-08-24 09:00 | 2021-09-07 18:00 | [6 empty] | 0 | 0 | [15 empty] | 18.6964 | 0.011103 | 1.09 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 112 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5290 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018177
561 | Task(Task)-->C (Construction) | FIELD INTRUMENTS |  | 1.5.3.5 | FIELD INTRUMENTS-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-07-27 09:00 | 2021-08-02 18:00 | 2022-01-06 09:00 | 2022-01-12 18:00 | [6 empty] | 0 | 0 | [15 empty] | 49.5712 | 0.029439 | 2.89 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5291 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018178
562 | Task(Task)-->C (Construction) | MOTOR TERMINATION |  | 1.5.3.5 | MOTOR TERMINATION-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-08-02 09:00 | 2021-08-03 18:00 | 2022-01-12 09:00 | 2022-01-13 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5292 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018179
563 | Task(Task)-->C (Construction) | NO LOAD RUN OF MOTOR |  | 1.5.3.5 | NO LOAD RUN OF MOTOR-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-08-22 | 2021-08-25 18:00 | 2022-04-14 09:00 | 2022-04-17 23:59 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5453 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018180
564 | Task(Task)-->C (Construction) | NO LOAD COMMISSIONING & SYSTEM READYNESS FOR LOAD & TRIAL OPERATION |  | 1.5.3 | NO LOAD COMMISSIONING & SYSTEM READYNESS FOR LOAD & TRIAL OPERATION-->CONSTRUCTION-->TROUGH CONVEYOR SC 1A, SC 1B, SC 2A & SC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-08-26 09:00 | 2021-09-08 18:00 | 2022-04-18 09:00 | 2022-05-01 23:59 | [6 empty] | 0 | 0 | [15 empty] | 12.0305 | 0.062539 | 6.15 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5293 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018181
565 | Task(Task)-->E (Engineering) | SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2) | 1.6 | 1 | SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-09-27 09:00 | 2021-09-09 18:00 | 2019-12-30 09:00 | 2022-05-02 18:00 |  |  | 2019-12-30 10:57 |  |  |  | 66.6196 | 16.9323 | [15 empty] | 1.6884 | 1.6884 | 166.04 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2855 | 0 | 1 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018182
566 | Task(Task)-->E (Engineering) | ENGINEERING | 1.6.1 | 1.6 | ENGINEERING-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-10-16 18:00 | 2020-06-19 17:40 | 2020-02-26 18:00 | 2020-11-15 23:59 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 75.3173 | [15 empty] | 3.3183 | 0.056025 | 5.51 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2856 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018183
567 | Task(Task)-->E (Engineering) | MECHANICAL | 1.6.1.1 | 1.6.1 | MECHANICAL-->ENGINEERING-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-10-16 18:00 | 2020-05-30 17:40 | 2020-02-26 18:00 | 2020-08-21 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 79.9976 | [15 empty] | 29.4011 | 0.016472 | 1.62 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No | 2857 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036082
568 | Task(Task)-->E (Engineering) | G.A & LOAD DATA OF SURGE HOPPER BUILDING |  | 1.6.1.1 | G.A & LOAD DATA OF SURGE HOPPER BUILDING-->MECHANICAL-->ENGINEERING-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-10-16 18:00 | 2019-12-20 17:40 | 2020-02-26 18:00 | 2020-05-11 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-0009 |  | 2020-02-13 10:26 | 7012-155-PVM-B-009 |  |  |  | A |  |  |  | 66.2577 | 0.010914 | 1.08 | Plan & Actual | Date |  | 0 | 0 | 0 | 400 | 0 | 125.3 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2858 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-10-16 18:00 | 2020-02-26 18:00 |  | 10 | 2020-02-26 23:31 |  |  | 2019-11-12 17:40 | 2020-03-25 18:00 |  | 30 | 2020-03-25 23:31 |  |  | 2019-11-18 17:40 | 2020-03-28 18:00 |  | 35 | 2020-03-28 23:31 |  |  | 2019-11-23 23:59 | 2020-04-04 18:00 |  | 65 | 2020-04-04 23:31 |  |  | 2019-11-29 17:40 | 2020-04-25 18:00 |  | 80 | 2020-05-11 23:31 | [5 empty] | 80 | 2020-09-05 13:09 | [5 empty] | 80 | 2020-09-05 13:09 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2019-12-20 17:40 | 2020-05-09 18:00 |  | 100 | [122 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 9 |  |  |  |  | 101023
569 | Task(Task)-->E (Engineering) | G.A & MARKING OF BELT FEEDER BF-1 & BF-2 (INSIDE THE SURGE HOPPER BUILDING) |  | 1.6.1.1 | G.A & MARKING OF BELT FEEDER BF-1 & BF-2 (INSIDE THE SURGE HOPPER BUILDING)-->MECHANICAL-->ENGINEERING-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-12-28 18:00 | 2020-02-14 17:40 | 2020-03-15 23:59 | 2020-05-09 18:00 |  |  | 2020-09-21 12:14 |  |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-0022 |  | 2020-02-13 10:26 | 7012-155-PVM-B-022 |  |  |  | A |  |  |  | 13.4969 | 0.002223 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 80 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2859 | 1 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-12-28 18:00 | 2020-03-15 23:59 |  | 10 | 2020-03-15 23:31 |  |  | 2020-01-06 17:40 | 2020-03-30 18:00 |  | 30 | 2020-03-30 23:31 |  |  | 2020-01-11 17:40 | 2020-04-01 18:00 |  | 35 | 2020-04-01 23:31 |  |  | 2020-01-17 23:59 | 2020-04-04 18:00 |  | 65 | 2020-04-04 23:31 |  |  | 2020-01-23 17:40 | 2020-04-25 18:00 |  | 80 | 2020-04-23 23:31 | [5 empty] | 80 | 2020-09-21 12:14 | [5 empty] | 80 | 2020-09-21 12:14 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-02-14 17:40 | 2020-05-09 18:00 |  | 100 | 2020-04-23 23:31 | [121 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 22 |  |  |  |  | 101036
570 | Task(Task)-->E (Engineering) | G.A OF RACK & PINION GATE |  | 1.6.1.1 | G.A OF RACK & PINION GATE-->MECHANICAL-->ENGINEERING-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-08 18:00 | 2020-05-30 17:40 | 2020-05-15 18:00 | 2020-08-21 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1037 |  | 2020-02-13 10:27 | 7012-155-PVM-B-137 |  |  |  | I |  |  |  | 6.7485 | 0.001112 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2865 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-08 18:00 | 2020-05-15 18:00 |  | 10 |  |  |  | 2020-04-18 17:40 | 2020-05-30 18:00 |  | 30 |  |  |  | 2020-04-24 17:40 | 2020-06-02 18:00 |  | 35 |  |  |  | 2020-05-01 23:59 | 2020-06-07 23:59 |  | 65 |  |  |  | 2020-05-07 17:40 | 2020-06-28 23:59 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-30 17:40 | 2020-06-28 23:59 |  | 100 | [122 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 67 |  |  |  |  | 101081
571 | Task(Task)-->E (Engineering) | G.A OF ROD GATE |  | 1.6.1.1 | G.A OF ROD GATE-->MECHANICAL-->ENGINEERING-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-01 17:40 | 2020-03-13 17:40 | 2020-08-18 09:00 | 2020-08-21 18:00 |  |  | 2020-02-21 14:04 | 2020-08-25 17:43 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1042 |  | 2020-02-13 10:27 | 7012-155-PVM-B-142 |  |  |  | I |  |  |  | 13.4969 | 0.002223 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2866 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-01 18:00 | 2020-04-17 18:00 |  | 10 | 2020-04-06 23:31 |  |  | 2020-02-01 17:40 | 2020-04-27 18:00 |  | 30 | 2020-04-11 23:31 |  |  | 2020-02-07 17:40 | 2020-04-30 18:00 |  | 35 | 2020-04-14 23:31 |  |  | 2020-02-14 23:59 | 2020-04-30 18:00 |  | 65 | 2020-08-19 18:58 |  |  | 2020-02-20 17:40 | 2020-05-21 18:00 |  | 80 | 2020-08-25 11:13 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-13 17:40 | 2020-05-21 18:00 |  | 100 | 2020-08-25 17:44 | [121 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 72 |  |  |  |  | 101086
572 | Task(Task)-->E (Engineering) | CIVIL | 1.6.1.2 | 1.6.1 | CIVIL-->ENGINEERING-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-01-01 18:00 | 2020-05-05 17:40 | 2020-04-05 23:59 | 2020-09-10 18:00 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 77.0242 | [15 empty] | 29.5826 | 0.016574 | 1.63 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No | 2868 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036083
573 | Task(Task)-->E (Engineering) | SURGE HOPPER BUILDING - DESIGN CALCULATION OF SUPER STRUCTURE |  | 1.6.1.2 | SURGE HOPPER BUILDING - DESIGN CALCULATION OF SUPER STRUCTURE-->CIVIL-->ENGINEERING-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-01 18:00 | 2020-03-02 17:40 | 2020-04-05 23:59 | 2020-07-17 18:00 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-DC-0008 |  | 2020-02-13 11:41 | 7012-155-PVC-U-022 |  |  |  | A |  |  |  | 42.9448 | 0.007118 | 0.7 | Plan & Actual | Date |  | 0 | 0 | 0 | 259.05 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2869 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-01 18:00 | 2020-04-05 23:59 |  | 10 | 2020-04-07 23:31 |  |  | 2020-01-21 17:40 | 2020-05-01 18:00 |  | 30 | 2020-05-07 23:31 |  |  | 2020-01-27 17:40 | 2020-05-04 18:00 |  | 35 |  |  |  | 2020-02-01 23:59 | 2020-05-11 18:00 |  | 65 | 2020-08-13 20:01 |  |  | 2020-02-07 17:40 | 2020-06-01 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-02 17:40 | 2020-06-15 18:00 |  | 100 | [122 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 123 |  |  |  |  | 101137
574 | Task(Task)-->E (Engineering) | SURGE HOPPER BUILDING - DESIGN CALCULATION OF SUB STRUCTURE |  | 1.6.1.2 | SURGE HOPPER BUILDING - DESIGN CALCULATION OF SUB STRUCTURE-->CIVIL-->ENGINEERING-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-05 18:00 | 2020-04-06 17:40 | 2020-05-10 23:59 | 2020-07-29 18:00 |  |  | 2020-02-21 15:37 | 2020-11-10 18:02 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-DC-0009 |  | 2020-02-13 11:41 | 7012-155-PVC-U-023 |  |  |  | A |  |  |  | 28.8344 | 0.004779 | 0.47 | Plan & Actual | Date |  | 0 | 0 | 0 | 173.12 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2870 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-05 18:00 | 2020-05-10 23:59 |  | 10 |  |  |  | 2020-02-25 17:40 | 2020-06-05 18:00 |  | 30 |  |  |  | 2020-03-02 17:40 | 2020-06-08 18:00 |  | 35 |  |  |  | 2020-03-07 23:59 | 2020-06-15 18:00 |  | 65 | 2020-08-13 20:01 |  |  | 2020-03-13 17:40 | 2020-07-06 18:00 |  | 80 | 2020-11-10 18:00 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-06 17:40 | 2020-07-20 18:00 |  | 100 | 2020-11-10 18:02 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 124 |  |  |  |  | 101138
575 | Task(Task)-->E (Engineering) | SURGE HOPPER BUILDING - NUM & RC DETAILS OF FDN |  | 1.6.1.2 | SURGE HOPPER BUILDING - NUM & RC DETAILS OF FDN-->CIVIL-->ENGINEERING-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-05 18:00 | 2020-04-06 17:40 | 2020-05-10 23:59 | 2020-07-29 18:00 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-NR-0008 |  | 2020-02-13 11:41 | 7012-155-PVC-C-025 |  |  |  | A |  |  |  | 17.1779 | 0.002847 | 0.28 | Plan & Actual | Date |  | 0 | 0 | 0 | 103.56 | 0 | 8.15 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2871 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-05 18:00 | 2020-05-10 23:59 |  | 10 |  |  |  | 2020-02-25 17:40 | 2020-06-05 18:00 |  | 30 |  |  |  | 2020-03-02 17:40 | 2020-06-08 18:00 |  | 35 | 2020-07-11 16:24 |  |  | 2020-03-07 23:59 | 2020-06-15 18:00 |  | 65 | 2020-08-13 20:01 |  |  | 2020-03-13 17:40 | 2020-07-06 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-06 17:40 | 2020-07-20 18:00 |  | 100 | [122 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 126 |  |  |  |  | 101140
576 | Task(Task)-->E (Engineering) | SURGE HOPPER BUILDING - NUM & RC DETAILS OF FLOOR SLABS |  | 1.6.1.2 | SURGE HOPPER BUILDING - NUM & RC DETAILS OF FLOOR SLABS-->CIVIL-->ENGINEERING-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-06 18:00 | 2020-05-05 17:40 | 2020-06-14 23:59 | 2020-09-10 18:00 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-NR-0009 |  | 2020-02-13 11:41 | 7012-155-PVC-C-026 |  |  |  | A |  |  |  | 5.5215 | 0.000915 | 0.09 | Plan & Actual | Date |  | 0 | 0 | 0 | 34.39 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2872 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-06 18:00 | 2020-06-14 23:59 |  | 10 |  |  |  | 2020-03-24 17:40 | 2020-07-10 18:00 |  | 30 | 2020-08-24 15:19 |  |  | 2020-03-31 17:40 | 2020-07-13 18:00 |  | 35 | 2020-08-29 11:05 |  |  | 2020-04-06 23:59 | 2020-07-20 18:00 |  | 65 | 2020-08-30 19:30 |  |  | 2020-04-13 17:40 | 2020-08-10 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-05 17:40 | 2020-08-24 18:00 |  | 100 | [122 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 127 |  |  |  |  | 101141
577 | Task(Task)-->E (Engineering) | SURGE HOPPER BUILDING - NUM & RC DETAILS OF GRADE SLAB |  | 1.6.1.2 | SURGE HOPPER BUILDING - NUM & RC DETAILS OF GRADE SLAB-->CIVIL-->ENGINEERING-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-06 18:00 | 2020-05-05 17:40 | 2020-08-06 09:00 | 2020-08-31 18:00 |  |  | 2020-02-21 15:37 | 2020-09-01 00:08 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-NR-0010 |  | 2020-02-13 11:41 | 7012-155-PVC-C-027 |  |  |  | A |  |  |  | 5.5215 | 0.000915 | 0.09 | Plan & Actual | Date |  | 0 | 0 | 0 | 34.39 | 0 | 28.11 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2873 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-06 18:00 | 2020-07-04 18:00 |  | 10 |  |  |  | 2020-03-24 17:40 | 2020-07-30 18:00 |  | 30 |  |  |  | 2020-03-31 17:40 | 2020-08-02 23:59 |  | 35 | 2020-08-05 16:50 |  |  | 2020-04-06 23:59 | 2020-08-09 23:59 |  | 65 | 2020-08-13 19:52 |  |  | 2020-04-13 17:40 | 2020-08-30 23:59 |  | 80 | 2020-09-01 00:06 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-05 17:40 | 2020-09-13 23:59 |  | 100 | 2020-09-01 00:09 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 128 |  |  |  |  | 101142
578 | Task(Task)-->E (Engineering) | STRUCTURAL | 1.6.1.3 | 1.6.1 | STRUCTURAL-->ENGINEERING-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-01 18:00 | 2020-06-19 17:40 | 2020-04-05 23:59 | 2020-11-15 23:59 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 65 | [15 empty] | 14.7005 | 0.008236 | 0.81 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No | 2874 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036084
579 | Task(Task)-->E (Engineering) | SURGE HOPPER BUILDING - STRUCTURAL GA |  | 1.6.1.3 | SURGE HOPPER BUILDING - STRUCTURAL GA-->STRUCTURAL-->ENGINEERING-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-01 18:00 | 2020-03-02 17:40 | 2020-04-05 23:59 | 2020-07-17 18:00 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-GA-0006 |  | 2020-02-13 11:41 | 7012-155-PVC-B-024 |  |  |  | A |  |  |  | 86.4198 | 0.007118 | 0.7 | Plan & Actual | Date |  | 0 | 0 | 0 | 259.05 | 0 | 93.1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2875 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-01 18:00 | 2020-04-05 23:59 |  | 10 | 2020-04-07 23:31 |  |  | 2020-01-21 17:40 | 2020-05-01 18:00 |  | 30 | 2020-05-07 23:31 |  |  | 2020-01-27 17:40 | 2020-05-04 18:00 |  | 35 | 2020-06-26 13:23 |  |  | 2020-02-01 23:59 | 2020-05-11 18:00 |  | 65 | 2020-08-13 20:01 |  |  | 2020-02-07 17:40 | 2020-06-01 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-02 17:40 | 2020-06-15 18:00 |  | 100 | [122 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 125 |  |  |  |  | 101139
580 | Task(Task)-->E (Engineering) | ARCHITECTURAL GA OF SURGE HOPPER BUILDING |  | 1.6.1.3 | ARCHITECTURAL GA OF SURGE HOPPER BUILDING-->STRUCTURAL-->ENGINEERING-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-20 18:00 | 2020-06-19 17:40 | 2020-06-25 18:00 | 2020-11-15 23:59 |  |  | 2020-02-21 15:39 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-AR-0003 |  | 2020-02-13 11:43 | 7012-155-PVC-C-109 |  |  |  | I |  |  |  | 13.5802 | 0.001118 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 40.52 | 0 | 89 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2876 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-20 18:00 | 2020-06-25 18:00 |  | 10 |  |  |  | 2020-05-08 17:40 | 2020-07-20 18:00 |  | 30 |  |  |  | 2020-05-15 17:40 | 2020-07-23 18:00 |  | 35 | 2020-09-23 17:59 |  |  | 2020-05-21 23:59 | 2020-07-30 18:00 |  | 65 | 2020-09-24 20:18 |  |  | 2020-05-28 17:40 | 2020-08-20 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-19 17:40 | 2020-09-03 18:00 |  | 100 | [122 empty] | Chetan Khodke | [5 empty] | A - Architecture | [16 empty] | 210 |  |  |  |  | 101220
581 | Task(Task)-->E (Engineering) | ELECTRICAL | 1.6.1.4 | 1.6.1 | ELECTRICAL-->ENGINEERING-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-12-13 18:00 | 2020-06-08 17:40 | 2020-04-14 18:00 | 2020-08-21 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 73.933 | [15 empty] | 26.3158 | 0.014743 | 1.45 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No | 2879 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036085
582 | Task(Task)-->E (Engineering) | DATASHEET & TERMINAL WIRING DIAGRAM FOR RACK & PINION GATE |  | 1.6.1.4 | DATASHEET & TERMINAL WIRING DIAGRAM FOR RACK & PINION GATE-->ELECTRICAL-->ENGINEERING-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-28 17:40 | 2020-06-08 17:40 | 2020-05-15 18:00 | 2020-08-21 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-404 |  | 2020-02-13 11:47 | 7012-155-PVE-W-140 |  |  |  | A |  |  |  | 7.5862 | 0.001118 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2882 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-28 18:00 | 2020-05-15 18:00 |  | 10 |  |  |  | 2020-04-28 17:40 | 2020-05-22 18:00 |  | 30 |  |  |  | 2020-05-04 17:40 | 2020-05-28 18:00 |  | 35 |  |  |  | 2020-05-11 23:59 | 2020-05-28 18:00 |  | 65 |  |  |  | 2020-05-16 17:40 | 2020-06-18 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-08 17:40 | 2020-06-18 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 375 |  |  |  |  | 101386
583 | Task(Task)-->E (Engineering) | EQUIPMENT, CABLE ROUTING, EARTHING & LIGHTNING LAYOUT WITH PLAN, SECTIONAL VIEWS & BOM OF SURGE HOPPER |  | 1.6.1.4 | EQUIPMENT, CABLE ROUTING, EARTHING & LIGHTNING LAYOUT WITH PLAN, SECTIONAL VIEWS & BOM OF SURGE HOPPER-->ELECTRICAL-->ENGINEERING-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-12-13 18:00 | 2020-02-06 17:40 | 2020-04-14 18:00 | 2020-06-04 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5053 |  | 2020-02-13 11:44 | 7012-155-PVE-F-015 |  |  |  | A |  |  |  | 46.2069 | 0.006812 | 0.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 248.42 | 0 | 24.16 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2880 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-12-13 18:00 | 2020-04-14 18:00 |  | 10 | 2020-04-14 23:31 |  |  | 2019-12-30 17:40 | 2020-04-28 18:00 |  | 30 | 2020-05-08 23:31 |  |  | 2020-01-04 17:40 | 2020-05-05 18:00 |  | 35 | 2020-05-11 23:31 |  |  | 2020-01-10 23:59 | 2020-05-12 18:00 |  | 65 | 2020-05-25 23:31 |  |  | 2020-01-16 17:40 | 2020-06-02 18:00 |  | 80 | 2020-07-28 17:08 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-02-06 17:40 | 2020-06-02 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 250 |  |  |  |  | 101261
584 | Task(Task)-->E (Engineering) | LIGHTING LAYOUT PLAN WITH POWER DISTRIBUTION ARRANGEMENT, SECTIONAL VIEW, BOM OF SURGE HOPPER |  | 1.6.1.4 | LIGHTING LAYOUT PLAN WITH POWER DISTRIBUTION ARRANGEMENT, SECTIONAL VIEW, BOM OF SURGE HOPPER-->ELECTRICAL-->ENGINEERING-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-18 18:00 | 2020-04-08 17:40 | 2020-04-27 18:00 | 2020-06-08 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5064 |  | 2020-02-13 11:44 | 7012-155-PVE-G-026 |  |  |  | A |  |  |  | 46.2069 | 0.006812 | 0.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 248.42 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2881 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-18 18:00 | 2020-04-27 18:00 |  | 10 | 2020-04-27 23:31 |  |  | 2020-02-27 17:40 | 2020-05-04 18:00 |  | 30 | 2020-05-03 23:31 |  |  | 2020-03-04 17:40 | 2020-05-11 18:00 |  | 35 | 2020-05-03 23:31 |  |  | 2020-03-10 23:59 | 2020-05-18 18:00 |  | 65 | 2020-05-05 23:31 |  |  | 2020-03-17 17:40 | 2020-06-08 18:00 |  | 80 | 2020-05-18 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-08 17:40 | 2020-06-08 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 261 |  |  |  |  | 101272
585 | Task(Task)-->P (Procurement) | PROCUREMENT | 1.6.2 | 1.6 | PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-09-27 09:00 | 2021-02-13 18:00 | 2019-12-30 09:00 | 2021-06-13 23:59 |  |  | 2019-12-30 10:57 |  |  |  | 93.0981 | 26.0813 | [15 empty] | 55.3388 | 0.93432 | 91.89 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2885 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018188
586 | Task(Task)-->P (Procurement) | PURCHASE REQUISITION | 1.6.2.1 | 1.6.2 | PURCHASE REQUISITION-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-09-27 09:00 | 2020-05-19 18:00 | 2019-12-30 09:00 | 2020-05-29 18:00 |  |  | 2019-12-30 10:57 |  |  |  | 100 | 94.1301 | [15 empty] | 4.9962 | 0.046681 | 4.59 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2886 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018189
587 | Task(Task)-->P (Procurement) | Rack & Pinion Gate |  | 1.6.2.1 | Rack & Pinion Gate-->PURCHASE REQUISITION-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2019-09-27 09:00 | 2019-09-27 18:00 | 2020-02-21 09:00 | 2020-02-21 18:00 |  |  | 2020-02-21 14:39 | 2020-02-21 14:39 |  |  | 100 | 100 | [15 empty] | 3.0435 | 0.001421 | 0.14 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2887 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018190
588 | Task(Task)-->P (Procurement) | Rod Gate |  | 1.6.2.1 | Rod Gate-->PURCHASE REQUISITION-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2019-09-27 09:00 | 2019-09-27 18:00 | 2020-02-19 09:00 | 2020-02-19 18:00 |  |  | 2020-02-19 10:57 | 2020-02-19 10:57 |  |  | 100 | 100 | [15 empty] | 0.65217 | 0.000304 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2888 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018191
589 | Task(Task)-->P (Procurement) | Flap Gate |  | 1.6.2.1 | Flap Gate-->PURCHASE REQUISITION-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-06 09:00 | 2020-02-06 18:00 | 2020-03-20 09:00 | 2020-03-20 18:00 |  |  | 2020-03-20 10:57 | 2020-03-20 10:57 |  |  | 100 | 100 | [15 empty] | 3.0435 | 0.001421 | 0.14 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2889 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018192
590 | Task(Task)-->P (Procurement) | Pulley |  | 1.6.2.1 | Pulley-->PURCHASE REQUISITION-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2019-09-27 09:00 | 2019-09-27 18:00 | 2020-02-05 09:00 | 2020-02-05 18:00 |  |  | 2020-02-05 16:16 | 2020-02-05 16:16 |  |  | 100 | 100 | [15 empty] | 2.3913 | 0.001116 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2890 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018193
591 | Task(Task)-->P (Procurement) | Idler |  | 1.6.2.1 | Idler-->PURCHASE REQUISITION-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-19 09:00 | 2019-12-19 18:00 | 2020-02-13 09:00 | 2020-02-13 18:00 |  |  | 2020-02-13 15:44 | 2020-02-13 15:44 |  |  | 100 | 100 | [15 empty] | 0.86957 | 0.000406 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2891 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018194
592 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.6.2.1 | Plummer Block-->PURCHASE REQUISITION-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-17 | 2020-05-17 23:59 | 2020-02-10 09:00 | 2020-02-10 18:00 |  |  | 2020-02-10 09:26 | 2020-02-10 09:26 |  |  | 100 | 100 | [15 empty] | 0.21739 | 0.000101 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2892 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018195
593 | Task(Task)-->P (Procurement) | Bearing |  | 1.6.2.1 | Bearing-->PURCHASE REQUISITION-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-17 | 2020-05-17 23:59 | 2020-02-10 09:00 | 2020-02-10 18:00 |  |  | 2020-02-10 09:36 | 2020-02-10 09:36 |  |  | 100 | 100 | [15 empty] | 0.21739 | 0.000101 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2893 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018196
594 | Task(Task)-->P (Procurement) | Belting |  | 1.6.2.1 | Belting-->PURCHASE REQUISITION-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-07 09:00 | 2019-11-07 18:00 | 2020-01-20 09:00 | 2020-01-20 18:00 |  |  | 2020-01-20 15:54 | 2020-01-20 15:54 |  |  | 100 | 100 | [15 empty] | 0.86957 | 0.000406 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2894 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018197
595 | Task(Task)-->P (Procurement) | Scrapper |  | 1.6.2.1 | Scrapper-->PURCHASE REQUISITION-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-17 | 2019-11-17 23:59 | 2020-03-11 09:00 | 2020-03-11 18:00 |  |  | 2020-03-11 10:57 | 2020-03-11 10:57 |  |  | 100 | 100 | [15 empty] | 0.43478 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2895 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018198
596 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.6.2.1 | Technological Structure-->PURCHASE REQUISITION-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-10 09:00 | 2020-03-10 18:00 | 2020-03-11 09:00 | 2020-03-11 18:00 |  |  | 2020-03-11 12:41 | 2020-03-11 12:41 |  |  | 100 | 100 | [15 empty] | 4.1304 | 0.001928 | 0.19 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2896 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018199
597 | Task(Task)-->P (Procurement) | Chute & Skirt |  | 1.6.2.1 | Chute & Skirt-->PURCHASE REQUISITION-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-10 09:00 | 2020-03-10 18:00 | 2020-03-11 09:00 | 2020-03-11 18:00 |  |  | 2020-03-11 10:57 | 2020-03-11 10:57 |  |  | 100 | 100 | [15 empty] | 18.913 | 0.008829 | 0.87 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2897 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018200
598 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.6.2.1 | Takeup Component-->PURCHASE REQUISITION-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-19 09:00 | 2020-05-19 18:00 | 2020-04-16 09:00 | 2020-04-16 18:00 |  |  | 2020-04-16 10:57 | 2020-04-16 10:57 |  |  | 100 | 100 | [15 empty] | 0.21739 | 0.000101 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2898 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018201
599 | Task(Task)-->P (Procurement) | Gear Box |  | 1.6.2.1 | Gear Box-->PURCHASE REQUISITION-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-13 09:00 | 2019-11-13 18:00 | 2020-01-20 09:00 | 2020-01-20 18:00 |  |  | 2020-01-20 11:17 | 2020-01-20 11:17 |  |  | 100 | 100 | [15 empty] | 2.1739 | 0.001015 | 0.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2899 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018202
600 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.6.2.1 | Geared Coupling-->PURCHASE REQUISITION-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-21 09:00 | 2019-11-21 18:00 | 2020-01-22 09:00 | 2020-01-22 18:00 |  |  | 2020-01-22 10:41 | 2020-01-22 10:41 |  |  | 100 | 100 | [15 empty] | 0.65217 | 0.000304 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2900 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018203
601 | Task(Task)-->P (Procurement) | Building Structure |  | 1.6.2.1 | Building Structure-->PURCHASE REQUISITION-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-01 09:00 | 2020-02-01 18:00 | 2020-05-29 09:00 | 2020-05-29 18:00 |  |  | 2020-05-31 18:44 | 2020-05-31 18:44 |  |  | 100 | 100 | [15 empty] | 52.6087 | 0.024558 | 2.42 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2901 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018204
602 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR CONVEYING SYSTEM |  | 1.6.2.1 | LT AC MOTORS FOR CONVEYING SYSTEM-->PURCHASE REQUISITION-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-16 09:00 | 2019-12-16 18:00 | 2020-01-13 09:00 | 2020-01-13 18:00 |  |  | 2020-01-13 10:57 | 2020-01-13 10:57 |  |  | 100 | 100 | [15 empty] | 0.43478 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2902 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018205
603 | Task(Task)-->P (Procurement) | LIGHT & LIGHT F IXTURES |  | 1.6.2.1 | LIGHT & LIGHT F IXTURES-->PURCHASE REQUISITION-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-10 09:00 | 2020-03-10 18:00 | 2020-03-16 09:00 | 2020-03-16 18:00 | [6 empty] | 100 | 0 | [15 empty] | 5.8696 | 0.00274 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2903 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018206
604 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.6.2.1 | LIGHTING POLES-->PURCHASE REQUISITION-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-27 09:00 | 2020-03-27 18:00 | 2020-04-30 09:00 | 2020-04-30 18:00 |  |  | 2020-04-30 10:57 | 2020-04-30 10:57 |  |  | 100 | 100 | [15 empty] | 2.6087 | 0.001218 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2904 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018207
605 | Task(Task)-->P (Procurement) | LPBS |  | 1.6.2.1 | LPBS-->PURCHASE REQUISITION-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-20 09:00 | 2020-03-20 18:00 | 2020-04-14 09:00 | 2020-04-14 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2905 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018208
606 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.6.2.1 | CONVEYOR BELT PROTECTION SWITCHES-->PURCHASE REQUISITION-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-08 09:00 | 2020-01-08 18:00 | 2020-01-08 09:00 | 2020-01-08 18:00 |  |  | 2020-01-08 10:57 | 2020-01-08 10:57 |  |  | 100 | 100 | [15 empty] | 0.43478 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2908 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018209
607 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.6.2.1 | ZERO SPEED SWITCH-->PURCHASE REQUISITION-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-30 09:00 | 2019-12-30 18:00 | 2019-12-30 09:00 | 2019-12-30 18:00 |  |  | 2019-12-30 10:57 | 2019-12-30 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2909 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018210
608 | Task(Task)-->P (Procurement) | CONTROL JUNCTION BOX |  | 1.6.2.1 | CONTROL JUNCTION BOX-->PURCHASE REQUISITION-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-05 09:00 | 2020-03-05 18:00 | 2020-04-18 09:00 | 2020-04-18 18:00 |  |  | 2020-04-18 10:57 | 2020-04-18 10:57 |  |  | 100 | 100 | [15 empty] | 0.21739 | 0.000101 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2910 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018211
609 | Task(Task)-->P (Procurement) | TECHNICAL CLEARANCE | 1.6.2.2 | 1.6.2 | TECHNICAL CLEARANCE-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-09-28 09:00 | 2020-06-18 18:00 | 2019-12-30 09:00 | 2020-06-12 18:00 |  |  | 2020-01-22 11:19 |  |  |  | 100 | 94.1301 | [15 empty] | 4.9962 | 0.046681 | 4.59 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2911 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018212
610 | Task(Task)-->P (Procurement) | Rack & Pinion Gate |  | 1.6.2.2 | Rack & Pinion Gate-->TECHNICAL CLEARANCE-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2019-09-28 09:00 | 2020-03-12 18:00 | 2020-02-21 09:00 | 2020-04-28 18:00 |  |  | 2020-02-24 14:39 | 2020-04-28 14:39 |  |  | 100 | 100 | [15 empty] | 3.0435 | 0.001421 | 0.14 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2912 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018213
611 | Task(Task)-->P (Procurement) | Rod Gate |  | 1.6.2.2 | Rod Gate-->TECHNICAL CLEARANCE-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2019-09-28 09:00 | 2019-12-31 18:00 | 2020-02-19 09:00 | 2020-03-06 18:00 |  |  | 2020-03-06 10:57 | 2020-03-06 10:57 |  |  | 100 | 100 | [15 empty] | 0.65217 | 0.000304 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2913 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018214
612 | Task(Task)-->P (Procurement) | Flap Gate |  | 1.6.2.2 | Flap Gate-->TECHNICAL CLEARANCE-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-07 09:00 | 2020-03-22 23:59 | 2020-03-20 09:00 | 2020-04-28 18:00 |  |  | 2020-04-28 10:57 | 2020-04-28 10:57 |  |  | 100 | 100 | [15 empty] | 3.0435 | 0.001421 | 0.14 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2914 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018215
613 | Task(Task)-->P (Procurement) | Pulley |  | 1.6.2.2 | Pulley-->TECHNICAL CLEARANCE-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2019-09-28 09:00 | 2020-01-04 18:00 | 2020-02-05 09:00 | 2020-02-10 18:00 |  |  | 2020-02-06 16:19 | 2020-02-10 16:19 |  |  | 100 | 100 | [15 empty] | 2.3913 | 0.001116 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2915 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018216
614 | Task(Task)-->P (Procurement) | Idler |  | 1.6.2.2 | Idler-->TECHNICAL CLEARANCE-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-20 09:00 | 2020-02-01 18:00 | 2020-02-13 09:00 | 2020-03-26 18:00 |  |  | 2020-02-14 10:57 | 2020-03-26 10:57 |  |  | 100 | 100 | [15 empty] | 0.86957 | 0.000406 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2916 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018217
615 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.6.2.2 | Plummer Block-->TECHNICAL CLEARANCE-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-18 09:00 | 2020-06-01 18:00 | 2020-02-10 09:00 | 2020-02-10 18:00 |  |  | 2020-02-10 09:28 | 2020-02-10 09:28 |  |  | 100 | 100 | [15 empty] | 0.21739 | 0.000101 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2917 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018218
616 | Task(Task)-->P (Procurement) | Bearing |  | 1.6.2.2 | Bearing-->TECHNICAL CLEARANCE-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-18 09:00 | 2020-06-16 18:00 | 2020-02-10 09:00 | 2020-02-10 18:00 |  |  | 2020-02-10 09:37 | 2020-02-10 09:37 |  |  | 100 | 100 | [15 empty] | 0.21739 | 0.000101 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2918 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018219
617 | Task(Task)-->P (Procurement) | Belting |  | 1.6.2.2 | Belting-->TECHNICAL CLEARANCE-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-08 09:00 | 2020-01-06 18:00 | 2020-01-20 09:00 | 2020-05-16 18:00 |  |  | 2020-05-16 10:57 | 2020-05-16 10:57 |  |  | 100 | 100 | [15 empty] | 0.86957 | 0.000406 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2919 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018220
618 | Task(Task)-->P (Procurement) | Scrapper |  | 1.6.2.2 | Scrapper-->TECHNICAL CLEARANCE-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-18 09:00 | 2020-03-16 18:00 | 2020-03-11 09:00 | 2020-03-26 18:00 |  |  | 2020-03-26 10:57 | 2020-03-26 10:57 |  |  | 100 | 100 | [15 empty] | 0.43478 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2920 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018221
619 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.6.2.2 | Technological Structure-->TECHNICAL CLEARANCE-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-11 09:00 | 2020-03-20 18:00 | 2020-03-11 09:00 | 2020-03-17 18:00 |  |  | 2020-03-12 12:43 | 2020-03-17 12:43 |  |  | 100 | 100 | [15 empty] | 4.1304 | 0.001928 | 0.19 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2921 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018222
620 | Task(Task)-->P (Procurement) | Chute & Skirt |  | 1.6.2.2 | Chute & Skirt-->TECHNICAL CLEARANCE-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-11 09:00 | 2020-03-20 18:00 | 2020-03-11 09:00 | 2020-03-17 18:00 |  |  | 2020-03-17 10:57 | 2020-03-17 10:57 |  |  | 100 | 100 | [15 empty] | 18.913 | 0.008829 | 0.87 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2922 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018223
621 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.6.2.2 | Takeup Component-->TECHNICAL CLEARANCE-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-20 09:00 | 2020-06-18 18:00 | 2020-04-16 09:00 | 2020-04-16 18:00 |  |  | 2020-04-16 10:57 | 2020-04-16 10:57 |  |  | 100 | 100 | [15 empty] | 0.21739 | 0.000101 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2923 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018224
622 | Task(Task)-->P (Procurement) | Gear Box |  | 1.6.2.2 | Gear Box-->TECHNICAL CLEARANCE-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-14 09:00 | 2020-02-26 18:00 | 2020-01-20 09:00 | 2020-03-20 18:00 |  |  | 2020-01-22 11:19 | 2020-03-20 11:19 |  |  | 100 | 100 | [15 empty] | 2.1739 | 0.001015 | 0.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2924 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018225
623 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.6.2.2 | Geared Coupling-->TECHNICAL CLEARANCE-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-22 09:00 | 2020-03-19 18:00 | 2020-01-22 09:00 | 2020-04-13 18:00 |  |  | 2020-04-13 10:46 | 2020-04-13 10:46 |  |  | 100 | 100 | [15 empty] | 0.65217 | 0.000304 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2925 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018226
624 | Task(Task)-->P (Procurement) | Building Structure |  | 1.6.2.2 | Building Structure-->TECHNICAL CLEARANCE-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-02 | 2020-02-08 18:00 | 2020-05-29 09:00 | 2020-05-29 18:00 |  |  | 2020-05-29 17:31 | 2020-05-29 17:31 |  |  | 100 | 100 | [15 empty] | 52.6087 | 0.024558 | 2.42 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2926 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018227
625 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR CONVEYING SYSTEM |  | 1.6.2.2 | LT AC MOTORS FOR CONVEYING SYSTEM-->TECHNICAL CLEARANCE-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-17 09:00 | 2019-12-31 18:00 | 2020-01-13 09:00 | 2020-04-11 18:00 |  |  | 2020-04-11 10:57 | 2020-04-11 10:57 |  |  | 100 | 100 | [15 empty] | 0.43478 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2927 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018228
626 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.6.2.2 | LIGHT & LIGHT FIXTURES-->TECHNICAL CLEARANCE-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-11 09:00 | 2020-03-25 18:00 | 2020-03-16 09:00 | 2020-06-02 18:00 | [6 empty] | 100 | 0 | [15 empty] | 5.8696 | 0.00274 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2928 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018229
627 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.6.2.2 | LIGHTING POLES-->TECHNICAL CLEARANCE-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-28 09:00 | 2020-05-11 18:00 | 2020-04-30 09:00 | 2020-06-03 18:00 |  |  | 2020-06-03 10:57 | 2020-06-03 10:57 |  |  | 100 | 100 | [15 empty] | 2.6087 | 0.001218 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2929 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018230
628 | Task(Task)-->P (Procurement) | LPBS |  | 1.6.2.2 | LPBS-->TECHNICAL CLEARANCE-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-21 09:00 | 2020-04-04 18:00 | 2020-04-14 09:00 | 2020-06-12 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2930 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018231
629 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.6.2.2 | CONVEYOR BELT PROTECTION SWITCHES-->TECHNICAL CLEARANCE-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-09 09:00 | 2020-01-22 18:00 | 2020-01-08 09:00 | 2020-03-10 18:00 |  |  | 2020-03-10 10:57 | 2020-03-10 10:57 |  |  | 100 | 100 | [15 empty] | 0.43478 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2933 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018232
630 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.6.2.2 | ZERO SPEED SWITCH-->TECHNICAL CLEARANCE-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-31 09:00 | 2020-01-16 18:00 | 2019-12-30 09:00 | 2020-03-07 18:00 |  |  | 2020-03-07 10:57 | 2020-03-07 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2934 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018233
631 | Task(Task)-->P (Procurement) | CONTROL JUNCTION BOX |  | 1.6.2.2 | CONTROL JUNCTION BOX-->TECHNICAL CLEARANCE-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-06 09:00 | 2020-03-13 18:00 | 2020-04-18 09:00 | 2020-06-02 18:00 |  |  | 2020-06-02 10:57 | 2020-06-02 10:57 |  |  | 100 | 100 | [15 empty] | 0.21739 | 0.000101 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2935 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018234
632 | Task(Task)-->P (Procurement) | ORDERING | 1.6.2.3 | 1.6.2 | ORDERING-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-01-01 09:00 | 2020-07-18 18:00 | 2020-02-10 09:00 | 2020-09-04 18:00 |  |  | 2020-01-05 08:00 |  |  |  | 100 | 99.1301 | [15 empty] | 10.0033 | 0.093463 | 9.19 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2936 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018235
633 | Task(Task)-->P (Procurement) | Rack & Pinion Gate |  | 1.6.2.3 | Rack & Pinion Gate-->ORDERING-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-13 09:00 | 2020-04-11 18:00 | 2020-04-28 09:00 | 2020-08-22 18:00 |  |  | 2020-04-28 15:39 | 2020-08-22 15:39 |  |  | 100 | 100 | [15 empty] | 3.0435 | 0.002845 | 0.28 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2937 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018236
634 | Task(Task)-->P (Procurement) | Rod Gate |  | 1.6.2.3 | Rod Gate-->ORDERING-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-01 09:00 | 2020-01-30 18:00 | 2020-03-06 09:00 | 2020-08-22 18:00 |  |  | 2020-03-06 16:47 | 2020-08-22 16:47 |  |  | 100 | 100 | [15 empty] | 0.65217 | 0.00061 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2938 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018237
635 | Task(Task)-->P (Procurement) | Flap Gate |  | 1.6.2.3 | Flap Gate-->ORDERING-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-23 09:00 | 2020-04-21 18:00 | 2020-04-28 09:00 | 2020-08-22 18:00 |  |  | 2020-04-28 16:12 | 2020-08-22 16:12 |  |  | 100 | 100 | [15 empty] | 3.1522 | 0.002946 | 0.29 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2939 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018238
636 | Task(Task)-->P (Procurement) | Pulley |  | 1.6.2.3 | Pulley-->ORDERING-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-05 | 2020-02-03 18:00 | 2020-02-10 09:00 | 2020-03-21 18:00 |  |  | 2020-01-05 08:00 | 2020-03-21 16:05 |  |  | 100 | 100 | [15 empty] | 2.3913 | 0.002235 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2940 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018239
637 | Task(Task)-->P (Procurement) | Idler |  | 1.6.2.3 | Idler-->ORDERING-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-02 | 2020-03-02 18:00 | 2020-03-26 09:00 | 2020-04-30 18:00 |  |  | 2020-02-02 08:00 | 2020-04-29 16:05 |  |  | 100 | 100 | [15 empty] | 0.86957 | 0.000813 | 0.08 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2941 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018240
638 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.6.2.3 | Plummer Block-->ORDERING-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-06-02 09:00 | 2020-07-01 18:00 | 2020-02-10 09:00 | 2020-03-24 18:00 |  |  | 2020-02-11 09:32 | 2020-03-24 09:32 |  |  | 100 | 100 | [15 empty] | 0.21739 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2942 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018241
639 | Task(Task)-->P (Procurement) | Bearing |  | 1.6.2.3 | Bearing-->ORDERING-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-06-17 09:00 | 2020-07-16 18:00 | 2020-02-10 09:00 | 2020-03-24 18:00 |  |  | 2020-02-11 09:40 | 2020-03-24 09:40 |  |  | 100 | 100 | [15 empty] | 0.32609 | 0.000305 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2943 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018242
640 | Task(Task)-->P (Procurement) | Belting |  | 1.6.2.3 | Belting-->ORDERING-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-07 09:00 | 2020-02-20 18:00 | 2020-05-16 09:00 | 2020-09-04 18:00 |  |  | 2020-05-16 16:24 | 2020-09-04 16:24 |  |  | 100 | 100 | [15 empty] | 0.86957 | 0.000813 | 0.08 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2944 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018243
641 | Task(Task)-->P (Procurement) | Scrapper |  | 1.6.2.3 | Scrapper-->ORDERING-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-17 09:00 | 2020-04-15 18:00 | 2020-03-26 09:00 | 2020-05-30 18:00 |  |  | 2020-05-30 10:57 | 2020-05-30 10:57 |  |  | 100 | 100 | [15 empty] | 0.43478 | 0.000406 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2945 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018244
642 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.6.2.3 | Technological Structure-->ORDERING-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-21 09:00 | 2020-04-19 23:59 | 2020-03-17 09:00 | 2020-07-06 18:00 |  |  | 2020-03-18 12:44 | 2020-07-06 12:44 |  |  | 100 | 100 | [15 empty] | 4.1304 | 0.00386 | 0.38 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2946 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018245
643 | Task(Task)-->P (Procurement) | Chute & Skirt |  | 1.6.2.3 | Chute & Skirt-->ORDERING-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-21 09:00 | 2020-04-19 23:59 | 2020-03-17 09:00 | 2020-07-06 18:00 |  |  | 2020-03-18 12:49 | 2020-07-06 12:49 |  |  | 100 | 100 | [15 empty] | 18.8043 | 0.017575 | 1.73 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2947 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018246
644 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.6.2.3 | Takeup Component-->ORDERING-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-19 09:00 | 2020-07-18 18:00 | 2020-04-16 09:00 | 2020-08-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.21739 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2948 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018247
645 | Task(Task)-->P (Procurement) | Gear Box |  | 1.6.2.3 | Gear Box-->ORDERING-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-27 09:00 | 2020-03-27 18:00 | 2020-03-20 09:00 | 2020-04-30 18:00 |  |  | 2020-03-21 11:21 | 2020-04-30 11:21 |  |  | 100 | 100 | [15 empty] | 2.1739 | 0.002032 | 0.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2949 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018248
646 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.6.2.3 | Geared Coupling-->ORDERING-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-20 09:00 | 2020-04-18 18:00 | 2020-04-13 09:00 | 2020-04-30 18:00 |  |  | 2020-04-14 11:11 | 2020-04-30 11:11 |  |  | 100 | 100 | [15 empty] | 0.54348 | 0.000508 | 0.05 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2950 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018249
647 | Task(Task)-->P (Procurement) | Building Structure |  | 1.6.2.3 | Building Structure-->ORDERING-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-09 | 2020-03-09 18:00 | 2020-05-29 09:00 | 2020-05-31 23:59 |  |  | 2020-05-31 18:49 | 2020-05-31 18:49 |  |  | 100 | 100 | [15 empty] | 52.7174 | 0.049271 | 4.85 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2951 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018250
648 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR CONVEYING SYSTEM |  | 1.6.2.3 | LT AC MOTORS FOR CONVEYING SYSTEM-->ORDERING-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-01 09:00 | 2020-01-16 18:00 | 2020-04-11 09:00 | 2020-07-20 18:00 |  |  | 2020-04-12 15:47 | 2020-06-20 15:47 |  |  | 100 | 100 | [15 empty] | 0.43478 | 0.000406 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2952 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018251
649 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.6.2.3 | LIGHT & LIGHT FIXTURES-->ORDERING-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-26 09:00 | 2020-04-10 18:00 | 2020-06-02 09:00 | 2020-07-31 18:00 |  |  | 2020-06-03 15:51 | 2020-06-29 15:51 |  |  | 100 | 100 | [15 empty] | 5.7609 | 0.005384 | 0.53 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2953 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018252
650 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.6.2.3 | LIGHTING POLES-->ORDERING-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-12 09:00 | 2020-06-25 18:00 | 2020-06-03 09:00 | 2020-06-24 18:00 |  |  | 2020-06-15 10:57 | 2020-06-15 10:57 |  |  | 100 | 100 | [15 empty] | 2.6087 | 0.002438 | 0.24 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2954 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018253
651 | Task(Task)-->P (Procurement) | LPBS |  | 1.6.2.3 | LPBS-->ORDERING-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-05 | 2020-04-20 18:00 | 2020-06-12 09:00 | 2020-08-19 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.1087 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2955 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018254
652 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.6.2.3 | CONVEYOR BELT PROTECTION SWITCHES-->ORDERING-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-23 09:00 | 2020-02-05 18:00 | 2020-03-10 09:00 | 2020-08-17 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.32609 | 0.000305 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2958 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018255
653 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.6.2.3 | ZERO SPEED SWITCH-->ORDERING-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-17 09:00 | 2020-02-01 18:00 | 2020-03-07 09:00 | 2020-08-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2959 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018256
654 | Task(Task)-->P (Procurement) | CONTROL JUNCTION BOX |  | 1.6.2.3 | CONTROL JUNCTION BOX-->ORDERING-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-14 09:00 | 2020-03-21 18:00 | 2020-06-02 09:00 | 2020-08-19 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.21739 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2960 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018257
655 | Task(Task)-->P (Procurement) | ITP APPROVAL | 1.6.2.4 | 1.6.2 | ITP APPROVAL-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-01-17 09:00 | 2020-08-25 18:00 | 2020-03-21 09:00 | 2020-11-30 18:00 |  |  | 2020-04-13 16:21 |  |  |  | 100 | 14.5654 | [15 empty] | 4.9962 | 0.046681 | 4.59 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2961 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018258
656 | Task(Task)-->P (Procurement) | Rack & Pinion Gate |  | 1.6.2.4 | Rack & Pinion Gate-->ITP APPROVAL-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-12 | 2020-05-21 18:00 | 2020-08-22 09:00 | 2020-11-30 18:00 | [6 empty] | 100 | 0 | [15 empty] | 3.0435 | 0.001421 | 0.14 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2962 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018259
657 | Task(Task)-->P (Procurement) | Rod Gate |  | 1.6.2.4 | Rod Gate-->ITP APPROVAL-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-31 09:00 | 2020-03-10 18:00 | 2020-06-25 09:00 | 2020-06-25 18:00 |  |  | 2020-06-25 15:36 | 2020-06-25 15:36 |  |  | 100 | 100 | [15 empty] | 0.65217 | 0.000304 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2963 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018260
658 | Task(Task)-->P (Procurement) | Flap Gate |  | 1.6.2.4 | Flap Gate-->ITP APPROVAL-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-22 09:00 | 2020-05-31 23:59 | 2020-08-22 09:00 | 2020-11-30 18:00 |  |  | 2020-08-22 16:16 |  |  |  | 100 | 0 | [15 empty] | 3.0435 | 0.001421 | 0.14 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2964 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018261
659 | Task(Task)-->P (Procurement) | Pulley |  | 1.6.2.4 | Pulley-->ITP APPROVAL-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-04 09:00 | 2020-03-14 18:00 | 2020-03-21 09:00 | 2020-05-11 18:00 | [6 empty] | 100 | 0 | [15 empty] | 2.3913 | 0.001116 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2965 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018262
660 | Task(Task)-->P (Procurement) | Idler |  | 1.6.2.4 | Idler-->ITP APPROVAL-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-03 09:00 | 2020-04-11 18:00 | 2020-04-30 09:00 | 2020-05-19 18:00 |  |  | 2020-04-13 16:21 | 2020-05-19 16:21 |  |  | 100 | 100 | [15 empty] | 0.86957 | 0.000406 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2966 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018263
661 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.6.2.4 | Plummer Block-->ITP APPROVAL-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-02 09:00 | 2020-08-10 18:00 | 2020-03-24 09:00 | 2020-08-13 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.21739 | 0.000101 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2967 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018264
662 | Task(Task)-->P (Procurement) | Bearing |  | 1.6.2.4 | Bearing-->ITP APPROVAL-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-17 09:00 | 2020-08-25 18:00 | 2020-03-24 09:00 | 2020-03-29 23:59 | [6 empty] | 100 | 0 | [15 empty] | 0.21739 | 0.000101 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2968 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018265
663 | Task(Task)-->P (Procurement) | Belting |  | 1.6.2.4 | Belting-->ITP APPROVAL-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-21 09:00 | 2020-03-31 18:00 | 2020-09-04 09:00 | 2020-09-30 18:00 |  |  | 2020-09-04 16:30 | 2020-09-30 16:30 |  |  | 100 | 100 | [15 empty] | 0.86957 | 0.000406 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2969 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018266
664 | Task(Task)-->P (Procurement) | Scrapper |  | 1.6.2.4 | Scrapper-->ITP APPROVAL-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-16 09:00 | 2020-05-25 18:00 | 2020-05-30 09:00 | 2020-06-25 18:00 |  |  | 2020-05-30 16:30 | 2020-06-25 16:31 |  |  | 100 | 100 | [15 empty] | 0.43478 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2970 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018267
665 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.6.2.4 | Technological Structure-->ITP APPROVAL-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-20 09:00 | 2020-05-29 18:00 | 2020-07-06 09:00 | 2020-07-16 18:00 | [6 empty] | 100 | 0 | [15 empty] | 4.1304 | 0.001928 | 0.19 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2971 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018268
666 | Task(Task)-->P (Procurement) | Chute & Skirt |  | 1.6.2.4 | Chute & Skirt-->ITP APPROVAL-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-20 09:00 | 2020-05-29 18:00 | 2020-07-06 09:00 | 2020-07-16 18:00 | [6 empty] | 100 | 0 | [15 empty] | 18.913 | 0.008829 | 0.87 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2972 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018269
667 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.6.2.4 | Takeup Component-->ITP APPROVAL-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-19 | 2020-08-17 18:00 | 2020-06-25 09:00 | 2020-06-25 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.21739 | 0.000101 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2973 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018270
668 | Task(Task)-->P (Procurement) | Gear Box |  | 1.6.2.4 | Gear Box-->ITP APPROVAL-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-28 09:00 | 2020-05-06 18:00 | 2020-04-30 09:00 | 2020-06-22 18:00 |  |  | 2020-04-30 16:57 | 2020-06-22 16:57 |  |  | 100 | 100 | [15 empty] | 2.1739 | 0.001015 | 0.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2974 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018271
669 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.6.2.4 | Geared Coupling-->ITP APPROVAL-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-19 | 2020-05-28 18:00 | 2020-04-30 09:00 | 2020-06-18 18:00 |  |  | 2020-04-30 01:54 | 2020-06-18 17:31 |  |  | 100 | 100 | [15 empty] | 0.65217 | 0.000304 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2975 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018272
670 | Task(Task)-->P (Procurement) | Building Structure |  | 1.6.2.4 | Building Structure-->ITP APPROVAL-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-10 09:00 | 2020-03-16 18:00 | 2020-05-31 | 2020-08-04 18:00 |  |  | 2020-06-25 19:04 |  |  |  | 100 | 0 | [15 empty] | 52.6087 | 0.024558 | 2.42 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2976 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018273
671 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR CONVEYING SYSTEM |  | 1.6.2.4 | LT AC MOTORS FOR CONVEYING SYSTEM-->ITP APPROVAL-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-17 09:00 | 2020-02-25 18:00 | 2020-09-08 09:00 | 2020-10-14 18:00 |  |  | 2020-09-08 15:15 | 2020-10-14 15:15 |  |  | 100 | 100 | [15 empty] | 0.43478 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2977 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018274
672 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.6.2.4 | LIGHT & LIGHT FIXTURES-->ITP APPROVAL-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-11 09:00 | 2020-05-20 18:00 | 2020-07-28 09:00 | 2020-09-08 18:00 |  |  | 2020-07-08 17:23 | 2020-09-08 17:23 |  |  | 100 | 100 | [15 empty] | 5.8696 | 0.00274 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2978 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018275
673 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.6.2.4 | LIGHTING POLES-->ITP APPROVAL-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-06-26 09:00 | 2020-08-04 18:00 | 2020-06-23 09:00 | 2020-09-08 18:00 |  |  | 2020-06-23 17:32 | 2020-09-08 17:05 |  |  | 100 | 100 | [15 empty] | 2.6087 | 0.001218 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2979 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018276
674 | Task(Task)-->P (Procurement) | LPBS |  | 1.6.2.4 | LPBS-->ITP APPROVAL-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-21 09:00 | 2020-05-30 18:00 | 2020-07-29 09:00 | 2020-08-21 18:00 |  |  | 2020-07-29 14:58 | 2020-08-22 12:54 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2980 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018277
675 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.6.2.4 | CONVEYOR BELT PROTECTION SWITCHES-->ITP APPROVAL-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-06 09:00 | 2020-03-16 18:00 | 2020-09-24 09:00 | 2020-11-30 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.43478 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2983 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018278
676 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.6.2.4 | ZERO SPEED SWITCH-->ITP APPROVAL-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-02 | 2020-02-22 18:00 | 2020-08-02 | 2020-08-22 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2984 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018279
677 | Task(Task)-->P (Procurement) | CONTROL JUNCTION BOX |  | 1.6.2.4 | CONTROL JUNCTION BOX-->ITP APPROVAL-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-22 | 2020-04-30 18:00 | 2020-07-29 09:00 | 2020-09-21 18:00 |  |  | 2020-07-29 14:53 |  |  |  | 100 | 0 | [15 empty] | 0.21739 | 0.000101 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2985 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018280
678 | Task(Task)-->P (Procurement) | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE | 1.6.2.5 | 1.6.2 | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-01-17 09:00 | 2020-09-16 18:00 | 2020-03-21 09:00 | 2020-11-16 18:00 |  |  | 2020-03-22 18:03 |  |  |  | 100 | 35.3592 | [15 empty] | 14.9995 | 0.14014 | 13.78 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2986 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018281
679 | Task(Task)-->P (Procurement) | Rack & Pinion Gate |  | 1.6.2.5 | Rack & Pinion Gate-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-12 | 2020-06-10 18:00 | 2020-08-22 09:00 | 2020-11-15 23:59 |  |  | 2020-08-22 16:45 |  |  |  | 100 | 15 | [15 empty] | 3.0479 | 0.004271 | 0.42 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2987 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018282
680 | Task(Task)-->P (Procurement) | Rod Gate |  | 1.6.2.5 | Rod Gate-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-31 09:00 | 2020-03-30 18:00 | 2020-08-22 09:00 | 2020-08-22 18:00 |  |  | 2020-08-22 15:37 | 2020-08-22 15:37 |  |  | 100 | 100 | [15 empty] | 0.65312 | 0.000915 | 0.09 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2988 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018283
681 | Task(Task)-->P (Procurement) | Flap Gate |  | 1.6.2.5 | Flap Gate-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-22 09:00 | 2020-06-20 18:00 | 2020-08-22 09:00 | 2020-11-15 23:59 |  |  | 2020-08-22 16:14 |  |  |  | 100 | 15 | [15 empty] | 3.1205 | 0.004373 | 0.43 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2989 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018284
682 | Task(Task)-->P (Procurement) | Pulley |  | 1.6.2.5 | Pulley-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-04 09:00 | 2020-03-29 23:59 | 2020-03-21 09:00 | 2020-03-25 18:00 |  |  | 2020-03-22 18:03 | 2020-03-25 18:03 |  |  | 100 | 100 | [15 empty] | 2.3948 | 0.003356 | 0.33 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2990 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018285
683 | Task(Task)-->P (Procurement) | Idler |  | 1.6.2.5 | Idler-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-03 09:00 | 2020-05-01 18:00 | 2020-04-30 09:00 | 2020-06-25 18:00 |  |  | 2020-06-25 14:53 | 2020-06-25 14:53 |  |  | 100 | 100 | [15 empty] | 0.87083 | 0.00122 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2991 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018286
684 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.6.2.5 | Plummer Block-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-07-02 09:00 | 2020-08-30 23:59 | 2020-03-24 09:00 | 2020-06-29 18:00 |  |  | 2020-05-14 14:59 | 2020-06-29 14:59 |  |  | 100 | 100 | [15 empty] | 0.14514 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2992 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018287
685 | Task(Task)-->P (Procurement) | Bearing |  | 1.6.2.5 | Bearing-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-07-17 09:00 | 2020-07-17 18:00 | 2020-03-24 09:00 | 2020-03-24 18:00 |  |  | 2020-03-24 10:05 | 2020-03-24 10:05 |  |  | 100 | 100 | [15 empty] | 0.29028 | 0.000407 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2993 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018288
686 | Task(Task)-->P (Procurement) | Belting |  | 1.6.2.5 | Belting-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-21 09:00 | 2020-04-20 18:00 | 2020-09-04 09:00 | 2020-11-15 23:59 |  |  | 2020-09-04 16:36 |  |  |  | 100 | 50 | [15 empty] | 0.79826 | 0.001119 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2994 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018289
687 | Task(Task)-->P (Procurement) | Scrapper |  | 1.6.2.5 | Scrapper-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-16 09:00 | 2020-06-14 23:59 | 2020-05-30 09:00 | 2020-07-30 18:00 |  |  | 2020-05-30 16:35 | 2020-07-30 16:35 |  |  | 100 | 100 | [15 empty] | 0.43541 | 0.00061 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2995 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018290
688 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.6.2.5 | Technological Structure-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-20 09:00 | 2020-09-16 18:00 | 2020-07-06 09:00 | 2020-07-06 18:00 |  |  | 2020-07-06 12:45 | 2020-07-06 12:45 |  |  | 100 | 100 | [15 empty] | 4.1364 | 0.005797 | 0.57 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2996 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018291
689 | Task(Task)-->P (Procurement) | Chute & Skirt |  | 1.6.2.5 | Chute & Skirt-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-20 09:00 | 2020-09-16 18:00 | 2020-07-06 09:00 | 2020-07-06 18:00 |  |  | 2020-07-06 12:51 | 2020-07-06 12:51 |  |  | 100 | 100 | [15 empty] | 18.8679 | 0.026442 | 2.6 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2997 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018292
690 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.6.2.5 | Takeup Component-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-19 | 2020-08-27 18:00 | 2020-08-04 09:00 | 2020-08-04 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.21771 | 0.000305 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2998 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018293
691 | Task(Task)-->P (Procurement) | Gear Box |  | 1.6.2.5 | Gear Box-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-28 09:00 | 2020-05-26 18:00 | 2020-04-30 09:00 | 2020-07-01 18:00 |  |  | 2020-04-30 15:33 | 2020-07-01 15:33 |  |  | 100 | 100 | [15 empty] | 2.1771 | 0.003051 | 0.3 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2999 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018294
692 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.6.2.5 | Geared Coupling-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-19 | 2020-06-17 18:00 | 2020-04-30 09:00 | 2020-07-30 18:00 |  |  | 2020-04-30 15:31 | 2020-07-06 15:31 |  |  | 100 | 100 | [15 empty] | 0.58055 | 0.000814 | 0.08 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3000 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018295
693 | Task(Task)-->P (Procurement) | Building Structure |  | 1.6.2.5 | Building Structure-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-08 | 2020-03-14 18:00 | 2020-05-31 | 2020-07-29 18:00 | [6 empty] | 100 | 0 | [15 empty] | 52.7576 | 0.073936 | 7.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3001 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018296
694 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR CONVEYING SYSTEM |  | 1.6.2.5 | LT AC MOTORS FOR CONVEYING SYSTEM-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-17 09:00 | 2020-03-01 23:59 | 2020-07-07 09:00 | 2020-09-29 18:00 |  |  | 2020-07-07 10:15 | 2020-09-21 12:52 |  |  | 100 | 100 | [15 empty] | 0.43541 | 0.00061 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3002 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018297
695 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.6.2.5 | LIGHT & LIGHT FIXTURES-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-11 09:00 | 2020-05-25 18:00 | 2020-07-10 09:00 | 2020-11-16 18:00 |  |  | 2020-07-14 10:44 |  |  |  | 100 | 0 | [15 empty] | 5.8055 | 0.008136 | 0.8 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3003 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018298
696 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.6.2.5 | LIGHTING POLES-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-06-26 09:00 | 2020-08-09 23:59 | 2020-05-30 09:00 | 2020-08-08 18:00 |  |  | 2020-06-18 17:08 | 2020-08-07 15:00 |  |  | 100 | 100 | [15 empty] | 2.6125 | 0.003661 | 0.36 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3004 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018299
697 | Task(Task)-->P (Procurement) | LPBS |  | 1.6.2.5 | LPBS-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-21 09:00 | 2020-06-04 18:00 | 2020-07-25 09:00 | 2020-08-22 18:00 |  |  | 2020-07-24 18:43 | 2020-08-22 12:57 |  |  | 100 | 100 | [15 empty] | 0.072569 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3005 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018300
698 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.6.2.5 | CONVEYOR BELT PROTECTION SWITCHES-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-06 09:00 | 2020-03-21 18:00 | 2020-08-11 09:00 | 2020-09-19 18:00 |  |  | 2020-08-11 13:11 | 2020-09-19 12:57 |  |  | 100 | 100 | [15 empty] | 0.36284 | 0.000509 | 0.05 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3008 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018301
699 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.6.2.5 | ZERO SPEED SWITCH-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-02 | 2020-03-03 18:00 | 2020-08-09 | 2020-10-29 18:00 |  |  | 2020-08-09 13:14 | 2020-10-29 12:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3009 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018302
700 | Task(Task)-->P (Procurement) | CONTROL JUNCTION BOX |  | 1.6.2.5 | CONTROL JUNCTION BOX-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-22 | 2020-05-05 18:00 | 2020-07-25 09:00 | 2020-11-10 18:00 |  |  | 2020-07-25 12:53 |  |  |  | 100 | 0 | [15 empty] | 0.21771 | 0.000305 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3010 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018303
701 | Task(Task)-->P (Procurement) | MANUFACTURING & RECEIPT AT SITE (MRN) | 1.6.2.6 | 1.6.2 | MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-02 09:00 | 2021-02-13 18:00 | 2020-03-24 09:00 | 2021-06-13 23:59 |  |  | 2020-03-25 18:05 |  |  |  | 88.4985 | 1.2128 | [15 empty] | 60.0087 | 0.56068 | 55.13 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3011 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018304
702 | Task(Task)-->P (Procurement) | Rack & Pinion Gate |  | 1.6.2.6 | Rack & Pinion Gate-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-11 09:00 | 2020-12-07 18:00 | 2020-12-01 09:00 | 2021-05-29 18:00 | [6 empty] | 85 | 0 | [15 empty] | 3.0276 | 0.016975 | 1.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3012 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018305
703 | Task(Task)-->P (Procurement) | Rod Gate |  | 1.6.2.6 | Rod Gate-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-11 09:00 | 2020-12-07 18:00 | 2020-08-22 09:00 | 2021-03-25 18:00 |  |  | 2020-08-22 15:38 |  |  |  | 85 | 10 | [15 empty] | 0.65265 | 0.003659 | 0.36 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3013 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018306
704 | Task(Task)-->P (Procurement) | Flap Gate |  | 1.6.2.6 | Flap Gate-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-21 | 2021-01-01 18:00 | 2020-12-01 09:00 | 2021-06-13 23:59 | [6 empty] | 73.3333 | 0 | [15 empty] | 3.1182 | 0.017483 | 1.72 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3014 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018307
705 | Task(Task)-->P (Procurement) | Pulley |  | 1.6.2.6 | Pulley-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-30 09:00 | 2020-11-20 18:00 | 2020-03-25 09:00 | 2020-11-30 18:00 |  |  | 2020-03-25 18:05 |  |  |  | 95.7627 | 0 | [15 empty] | 2.4293 | 0.01362 | 1.34 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3015 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018308
706 | Task(Task)-->P (Procurement) | Idler |  | 1.6.2.6 | Idler-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-02 09:00 | 2020-11-13 18:00 | 2020-06-25 09:00 | 2020-12-31 18:00 | [6 empty] | 98.4694 | 0 | [15 empty] | 0.8702 | 0.004879 | 0.48 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3016 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018309
707 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.6.2.6 | Plummer Block-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-31 09:00 | 2020-12-23 18:00 | 2020-06-29 09:00 | 2020-12-31 18:00 | [6 empty] | 62.6087 | 0 | [15 empty] | 0.18129 | 0.001016 | 0.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3017 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018310
708 | Task(Task)-->P (Procurement) | Bearing |  | 1.6.2.6 | Bearing-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-26 09:00 | 2020-12-23 18:00 | 2020-03-24 09:00 | 2020-09-09 18:00 | [6 empty] | 64.1667 | 0 | [15 empty] | 0.30819 | 0.001728 | 0.17 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3018 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018311
709 | Task(Task)-->P (Procurement) | Belting |  | 1.6.2.6 | Belting-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-21 09:00 | 2020-11-16 18:00 | 2020-11-16 09:00 | 2021-06-13 23:59 | [6 empty] | 97.1429 | 0 | [15 empty] | 0.81581 | 0.004574 | 0.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3019 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018312
710 | Task(Task)-->P (Procurement) | Scrapper |  | 1.6.2.6 | Scrapper-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-15 09:00 | 2020-12-11 18:00 | 2020-07-30 09:00 | 2020-12-31 18:00 | [6 empty] | 82.7778 | 0 | [15 empty] | 0.39884 | 0.002236 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3020 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018313
711 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.6.2.6 | Technological Structure-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-19 09:00 | 2021-02-13 18:00 | 2020-07-06 09:00 | 2021-01-31 23:59 | [6 empty] | 60.4167 | 0 | [15 empty] | 4.1153 | 0.023073 | 2.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3021 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018314
712 | Task(Task)-->P (Procurement) | Chute & Skirt |  | 1.6.2.6 | Chute & Skirt-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-19 09:00 | 2021-02-13 18:00 | 2020-07-06 09:00 | 2021-01-31 23:59 | [6 empty] | 60.4167 | 0 | [15 empty] | 18.8724 | 0.10581 | 10.41 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3022 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018315
713 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.6.2.6 | Takeup Component-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-28 09:00 | 2020-12-25 18:00 | 2020-08-04 09:00 | 2020-12-25 18:00 | [6 empty] | 62.5 | 0 | [15 empty] | 0.23568 | 0.001321 | 0.13 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3023 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018316
714 | Task(Task)-->P (Procurement) | Gear Box |  | 1.6.2.6 | Gear Box-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-27 09:00 | 2020-12-22 18:00 | 2020-07-01 09:00 | 2020-12-31 18:00 |  |  | 2020-07-01 17:25 |  |  |  | 80 | 30 | [15 empty] | 2.1936 | 0.012299 | 1.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3024 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018317
715 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.6.2.6 | Geared Coupling-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-18 09:00 | 2020-12-15 18:00 | 2020-07-30 09:00 | 2020-11-30 18:00 |  |  | 2020-07-30 17:44 |  |  |  | 80.663 | 90 | [15 empty] | 0.54387 | 0.003049 | 0.3 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3025 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018318
716 | Task(Task)-->P (Procurement) | Building Structure |  | 1.6.2.6 | Building Structure-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-17 09:00 | 2020-09-04 18:00 | 2020-07-29 09:00 | 2021-03-31 18:00 | [6 empty] | 100 | 0 | [15 empty] | 52.7194 | 0.29558 | 29.08 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3026 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018319
717 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR CONVEYING SYSTEM |  | 1.6.2.6 | LT AC MOTORS FOR CONVEYING SYSTEM-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-02 09:00 | 2020-09-26 18:00 | 2020-10-15 09:00 | 2021-05-11 18:00 |  |  | 2020-09-22 12:53 |  |  |  | 100 | 0 | [15 empty] | 0.4351 | 0.002439 | 0.24 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3027 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018320
718 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.6.2.6 | LIGHT & LIGHT FIXTURES-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-26 09:00 | 2020-10-21 18:00 | 2020-11-17 09:00 | 2021-04-14 18:00 | [6 empty] | 100 | 0 | [15 empty] | 5.7832 | 0.032425 | 3.19 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3028 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018321
719 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.6.2.6 | LIGHTING POLES-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-10 09:00 | 2020-11-07 18:00 | 2020-09-09 09:00 | 2020-12-07 18:00 |  |  | 2020-08-07 15:00 |  |  |  | 100 | 0 | [15 empty] | 2.6287 | 0.014739 | 1.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3029 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018322
720 | Task(Task)-->P (Procurement) | LPBS |  | 1.6.2.6 | LPBS-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-05 09:00 | 2020-09-16 18:00 | 2020-08-23 | 2020-12-04 18:00 |  |  | 2020-08-22 13:00 |  |  |  | 100 | 0 | [15 empty] | 0.072516 | 0.000407 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3030 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018323
721 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.6.2.6 | CONVEYOR BELT PROTECTION SWITCHES-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-22 | 2020-08-05 18:00 | 2020-12-01 09:00 | 2021-04-16 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.32632 | 0.00183 | 0.18 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3033 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018324
722 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.6.2.6 | ZERO SPEED SWITCH-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-04 09:00 | 2020-07-02 18:00 | 2020-10-30 09:00 | 2021-02-27 18:00 |  |  | 2020-10-29 12:58 |  |  |  | 100 | 0 | [15 empty] | 0.018129 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3034 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018325
723 | Task(Task)-->P (Procurement) | CONTROL JUNCTION BOX |  | 1.6.2.6 | CONTROL JUNCTION BOX-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-06 09:00 | 2020-09-16 18:00 | 2020-11-11 09:00 | 2021-03-24 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.25381 | 0.001423 | 0.14 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3035 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018326
724 | Task(Task)-->C (Construction) | CONSTRUCTION | 1.6.3 | 1.6 | CONSTRUCTION-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-21 09:00 | 2021-09-09 18:00 | 2020-08-01 09:00 | 2022-05-02 18:00 | [6 empty] | 28.4982 | 0 | [15 empty] | 41.343 | 0.69802 | 68.65 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3036 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018327
725 | Task(Task)-->C (Construction) | CIVIL | 1.6.3.1 | 1.6.3 | CIVIL-->CONSTRUCTION-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-21 09:00 | 2021-02-04 18:00 | 2020-08-01 09:00 | 2021-06-15 18:00 | [6 empty] | 36.0694 | 0 | [15 empty] | 42.7677 | 0.29853 | 29.36 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3037 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018328
726 | Task(Task)-->C (Construction) | AVAILABILITY OF FRONT BY NTPC |  | 1.6.3.1 | AVAILABILITY OF FRONT BY NTPC-->CIVIL-->CONSTRUCTION-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-21 09:00 | 2020-03-21 18:00 | 2020-08-01 09:00 | 2020-08-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3038 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018329
727 | Task(Task)-->C (Construction) | EXCAVATION |  | 1.6.3.1 | EXCAVATION-->CIVIL-->CONSTRUCTION-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-28 09:00 | 2020-04-09 18:00 | 2020-08-02 | 2020-08-14 18:00 | [6 empty] | 100 | 0 | [15 empty] | 5.4155 | 0.016167 | 1.59 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 5978 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3039 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | Excavation | [23 empty] | 1018330
728 | Task(Task)-->C (Construction) | PCC |  | 1.6.3.1 | PCC-->CIVIL-->CONSTRUCTION-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-16 09:00 | 2020-05-20 18:00 | 2020-09-24 09:00 | 2020-09-28 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.81744 | 0.00244 | 0.24 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3040 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | PCC | [23 empty] | 1018331
729 | Task(Task)-->C (Construction) | RAFT |  | 1.6.3.1 | RAFT-->CIVIL-->CONSTRUCTION-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-20 09:00 | 2020-06-04 18:00 | 2020-09-28 09:00 | 2020-10-13 18:00 | [6 empty] | 100 | 0 | [15 empty] | 19.891 | 0.05938 | 5.84 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3041 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018332
730 | Task(Task)-->C (Construction) | PADESTALS FOR SURGE HOPPER BLDG. STR. |  | 1.6.3.1 | PADESTALS FOR SURGE HOPPER BLDG. STR.-->CIVIL-->CONSTRUCTION-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-05 09:00 | 2020-06-30 18:00 | 2020-10-14 09:00 | 2020-11-08 23:59 | [6 empty] | 100 | 0 | [15 empty] | 3.5082 | 0.010473 | 1.03 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3042 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018333
731 | Task(Task)-->C (Construction) | RCC FLOOR FOR TAIL PULLEY OF PC-1A/B |  | 1.6.3.1 | RCC FLOOR FOR TAIL PULLEY OF PC-1A/B-->CIVIL-->CONSTRUCTION-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-09-12 09:00 | 2020-09-22 18:00 | 2021-01-21 09:00 | 2021-01-31 23:59 | [6 empty] | 100 | 0 | [15 empty] | 3.1676 | 0.009456 | 0.93 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3043 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | RCC | [23 empty] | 1018334
732 | Task(Task)-->C (Construction) | RCC FLOOR FOR BELT FEEDER |  | 1.6.3.1 | RCC FLOOR FOR BELT FEEDER-->CIVIL-->CONSTRUCTION-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-10-12 09:00 | 2020-10-24 18:00 | 2021-02-20 09:00 | 2021-03-04 18:00 | [6 empty] | 100 | 0 | [15 empty] | 3.2698 | 0.009761 | 0.96 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3044 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | RCC | [23 empty] | 1018335
733 | Task(Task)-->C (Construction) | RCC FLOOR FOR SURGE HOPPER |  | 1.6.3.1 | RCC FLOOR FOR SURGE HOPPER-->CIVIL-->CONSTRUCTION-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-11-11 09:00 | 2020-11-26 18:00 | 2021-03-22 09:00 | 2021-04-06 18:00 | [6 empty] | 0 | 0 | [15 empty] | 3.3379 | 0.009964 | 0.98 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3045 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | RCC | [23 empty] | 1018336
734 | Task(Task)-->C (Construction) | GRADE SLAB FLOOR FOR TAIL END DRIVE OF PC-1A/B |  | 1.6.3.1 | GRADE SLAB FLOOR FOR TAIL END DRIVE OF PC-1A/B-->CIVIL-->CONSTRUCTION-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-12-26 09:00 | 2021-02-04 18:00 | 2021-05-06 09:00 | 2021-06-15 18:00 | [6 empty] | 0 | 0 | [15 empty] | 60.5926 | 0.18089 | 17.79 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 950 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3046 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018337
735 | Task(Task)-->C (Construction) | STRUCTURAL WORKS | 1.6.3.2 | 1.6.3 | STRUCTURAL WORKS-->CONSTRUCTION-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-29 09:00 | 2021-04-24 18:00 | 2020-12-07 09:00 | 2021-09-02 18:00 | [6 empty] | 37.9934 | 0 | [15 empty] | 34.4064 | 0.24016 | 23.62 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3047 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018338
736 | Task(Task)-->C (Construction) | ERECTION OF STRUCTURAL STEEL |  | 1.6.3.2 | ERECTION OF STRUCTURAL STEEL-->STRUCTURAL WORKS-->CONSTRUCTION-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-29 09:00 | 2020-12-25 18:00 | 2020-12-07 09:00 | 2021-05-05 18:00 | [6 empty] | 70 | 0 | [15 empty] | 54.276 | 0.13035 | 12.82 | Plan & Actual | Quantity | Metric Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 198 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3048 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018339
737 | Task(Task)-->C (Construction) | ERECTION OF SURGE HOPPER |  | 1.6.3.2 | ERECTION OF SURGE HOPPER-->STRUCTURAL WORKS-->CONSTRUCTION-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-11-26 09:00 | 2021-04-24 18:00 | 2021-04-06 09:00 | 2021-09-02 18:00 | [6 empty] | 0 | 0 | [15 empty] | 45.724 | 0.10981 | 10.8 | Plan & Actual | Quantity | Metric Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 168 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5413 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018340
738 | Task(Task)-->C (Construction) | MECHANICAL EQUIPMENT WORKS | 1.6.3.3 | 1.6.3 | MECHANICAL EQUIPMENT WORKS-->CONSTRUCTION-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-04-25 | 2021-05-24 18:00 | 2021-09-03 09:00 | 2021-10-02 18:00 | [6 empty] | 0 | 0 | [15 empty] | 8.5652 | 0.059787 | 5.88 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5456 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018341
739 | Task(Task)-->C (Construction) | ERECTION OF CHUTES/ HOODS & SUPPORTS |  | 1.6.3.3 | ERECTION OF CHUTES/ HOODS & SUPPORTS-->MECHANICAL EQUIPMENT WORKS-->CONSTRUCTION-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-04-25 | 2021-05-24 18:00 | 2021-09-03 09:00 | 2021-10-02 18:00 | [6 empty] | 0 | 0 | [15 empty] | 75.1278 | 0.044917 | 4.41 | Plan & Actual | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3049 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018342
740 | Task(Task)-->C (Construction) | ERECTION OF BF-1 |  | 1.6.3.3 | ERECTION OF BF-1-->MECHANICAL EQUIPMENT WORKS-->CONSTRUCTION-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-04-25 | 2021-05-09 23:59 | 2021-09-03 09:00 | 2021-09-17 18:00 | [6 empty] | 0 | 0 | [15 empty] | 12.4361 | 0.007435 | 0.73 | Plan & Actual | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5414 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018343
741 | Task(Task)-->C (Construction) | ERECTION OF BF-2 |  | 1.6.3.3 | ERECTION OF BF-2-->MECHANICAL EQUIPMENT WORKS-->CONSTRUCTION-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-05-10 09:00 | 2021-05-24 18:00 | 2021-09-18 09:00 | 2021-10-02 18:00 | [6 empty] | 0 | 0 | [15 empty] | 12.4361 | 0.007435 | 0.73 | Plan & Actual | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5415 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018344
742 | Task(Task)-->C (Construction) | ELECTRICAL & INSTRUMENTATION | 1.6.3.4 | 1.6.3 | ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-12-18 09:00 | 2021-08-25 18:00 | 2021-04-28 09:00 | 2022-04-17 23:59 | [6 empty] | 0 | 0 | [15 empty] | 12.0175 | 0.083885 | 8.25 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5268 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018345
743 | Task(Task)-->C (Construction) | CABLE TRAY |  | 1.6.3.4 | CABLE TRAY-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-12-18 09:00 | 2021-01-01 18:00 | 2021-04-28 09:00 | 2021-05-12 18:00 | [6 empty] | 0 | 0 | [15 empty] | 9.3333 | 0.007829 | 0.77 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3050 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018346
744 | Task(Task)-->C (Construction) | POWER CABLE LAYING |  | 1.6.3.4 | POWER CABLE LAYING-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-05-25 09:00 | 2021-06-07 18:00 | 2021-10-03 | 2021-10-16 18:00 | [6 empty] | 0 | 0 | [15 empty] | 39.2727 | 0.032944 | 3.24 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 22891 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5269 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018347
745 | Task(Task)-->C (Construction) | CONTROL CABLE |  | 1.6.3.4 | CONTROL CABLE-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-06-05 09:00 | 2021-06-07 18:00 | 2021-10-26 09:00 | 2021-10-28 18:00 | [6 empty] | 0 | 0 | [15 empty] | 28.3636 | 0.023793 | 2.34 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 16500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3051 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018348
746 | Task(Task)-->C (Construction) | EARTHING |  | 1.6.3.4 | EARTHING-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-06-03 09:00 | 2021-06-07 18:00 | 2021-10-12 09:00 | 2021-10-16 18:00 | [6 empty] | 0 | 0 | [15 empty] | 2.1818 | 0.00183 | 0.18 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 827 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5296 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018349
747 | Task(Task)-->C (Construction) | EARTH PIT |  | 1.6.3.4 | EARTH PIT-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-02-02 09:00 | 2021-02-04 18:00 | 2021-06-13 | 2021-06-15 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5297 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018350
748 | Task(Task)-->C (Construction) | LIGHTING |  | 1.6.3.4 | LIGHTING-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-12-21 09:00 | 2021-01-04 18:00 | 2021-05-01 09:00 | 2021-05-15 18:00 | [6 empty] | 0 | 0 | [15 empty] | 13.697 | 0.01149 | 1.13 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 116 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5298 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018351
749 | Task(Task)-->C (Construction) | FIELD INTRUMENTS |  | 1.6.3.4 | FIELD INTRUMENTS-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-06-04 09:00 | 2021-06-07 18:00 | 2021-10-25 09:00 | 2021-10-28 18:00 | [6 empty] | 0 | 0 | [15 empty] | 7.1515 | 0.005999 | 0.59 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5299 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018352
750 | Task(Task)-->C (Construction) | MOTOR TERMINATION |  | 1.6.3.4 | MOTOR TERMINATION-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-06-06 | 2021-06-09 18:00 | 2022-01-02 | 2022-01-05 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5300 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018353
751 | Task(Task)-->C (Construction) | NO LOAD RUN OF MOTOR |  | 1.6.3.4 | NO LOAD RUN OF MOTOR-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-08-22 | 2021-08-25 18:00 | 2022-04-14 09:00 | 2022-04-17 23:59 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5457 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018354
752 | Task(Task)-->C (Construction) | NO LOAD COMMISSIONING & SYSTEM READYNESS FOR LOAD & TRIAL OPERATION |  | 1.6.3 | NO LOAD COMMISSIONING & SYSTEM READYNESS FOR LOAD & TRIAL OPERATION-->CONSTRUCTION-->SURGE HOPPER BUILDING (SHB) & BELT FEEDER (BF-1 & 2)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-08-26 09:00 | 2021-09-09 18:00 | 2022-04-18 09:00 | 2022-05-02 18:00 | [6 empty] | 0 | 0 | [15 empty] | 2.2433 | 0.015658 | 1.54 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5301 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018355
753 | Task(Task)-->E (Engineering) | TROUGH CONVEYOR SC 3A & SC 3B | 1.7 | 1 | TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-09-27 09:00 | 2021-08-25 18:00 | 2019-09-27 09:00 | 2022-04-17 23:59 |  |  | 2019-09-27 10:57 |  |  |  | 83.4053 | 30.217 | [15 empty] | 1.0742 | 1.0742 | 105.64 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3052 | 0 | 1 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018356
754 | Task(Task)-->E (Engineering) | ENGINEERING | 1.7.1 | 1.7 | ENGINEERING-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-12-06 18:00 | 2020-06-26 17:40 | 2020-01-13 18:00 | 2020-07-10 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 83.6683 | [15 empty] | 1.5998 | 0.017185 | 1.69 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3053 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018357
755 | Task(Task)-->E (Engineering) | MECHANICAL | 1.7.1.1 | 1.7.1 | MECHANICAL-->ENGINEERING-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-12-06 18:00 | 2020-03-23 17:40 | 2020-01-13 18:00 | 2020-04-09 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 86.7685 | [15 empty] | 38.4615 | 0.00661 | 0.65 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No | 3054 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036086
756 | Task(Task)-->E (Engineering) | PULLEY SHAFT DIAMETER, SHELL THICKNESS, DIAPHRAGM THICKNESS CALCULATION WITH BEARING SELECTION FOR TROUGH BELT CONVEYORS |  | 1.7.1.1 | PULLEY SHAFT DIAMETER, SHELL THICKNESS, DIAPHRAGM THICKNESS CALCULATION WITH BEARING SELECTION FOR TROUGH BELT CONVEYORS-->MECHANICAL-->ENGINEERING-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-20 18:00 | 2020-03-23 17:40 | 2020-02-18 09:00 | 2020-03-13 18:00 |  |  | 2020-02-21 14:04 | 2020-06-19 22:39 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-DC-0026 |  | 2020-02-13 10:26 | 7012-155-PVM-H-026 |  |  |  | A |  |  |  | 33.8462 | 0.002237 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 80 | 0 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 2658 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-20 18:00 | 2020-01-14 18:00 |  | 10 | 2020-01-14 23:31 |  |  | 2020-02-11 17:40 | 2020-02-13 18:00 |  | 30 | 2020-02-13 23:31 |  |  | 2020-02-17 17:40 | 2020-02-18 18:00 |  | 35 | 2020-02-18 23:31 |  |  | 2020-02-24 23:59 | 2020-02-18 18:00 |  | 65 | 2020-02-18 23:31 |  |  | 2020-02-29 17:40 | 2020-03-13 18:00 |  | 80 | 2020-03-13 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-23 17:40 | 2020-03-13 18:00 |  | 100 | 2020-06-19 22:40 | [121 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 26 |  |  |  |  | 101040
757 | Task(Task)-->E (Engineering) | G.A & MARKING OF CONV. SC 3A/B |  | 1.7.1.1 | G.A & MARKING OF CONV. SC 3A/B-->MECHANICAL-->ENGINEERING-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-12-06 18:00 | 2020-01-25 17:40 | 2020-01-13 18:00 | 2020-04-09 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-0020 |  | 2020-02-13 10:26 | 7012-155-PVM-B-020 |  |  |  | A |  |  |  | 66.1538 | 0.004373 | 0.43 | Plan & Actual | Date |  | 0 | 0 | 0 | 160 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3055 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-12-06 18:00 | 2020-01-13 18:00 |  | 10 | 2020-01-13 23:31 |  |  | 2019-12-18 17:40 | 2020-01-28 18:00 |  | 30 | 2020-01-28 23:31 |  |  | 2019-12-24 17:40 | 2020-01-30 18:00 |  | 35 | 2020-01-30 23:31 |  |  | 2019-12-30 23:59 | 2020-02-06 18:00 |  | 65 | 2020-02-06 23:31 |  |  | 2020-01-04 17:40 | 2020-02-26 18:00 |  | 80 | 2020-02-26 23:31 | [5 empty] | 80 | 2020-06-10 17:39 | [5 empty] | 80 | 2020-05-16 18:41 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-01-25 17:40 | 2020-04-09 18:00 |  | 100 | [122 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 20 |  |  |  |  | 101034
758 | Task(Task)-->E (Engineering) | CIVIL | 1.7.1.2 | 1.7.1 | CIVIL-->ENGINEERING-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-03 17:40 | 2020-05-12 17:40 | 2020-04-11 09:00 | 2020-07-10 18:00 |  |  | 2020-02-21 15:37 | 2020-07-17 15:22 |  |  | 100 | 100 | [15 empty] | 5.3254 | 0.000915 | 0.09 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No | 3080 | 2 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036087
759 | Task(Task)-->E (Engineering) | CONV. SC 3A/B : NUM & RC DETAILS OF FDN |  | 1.7.1.2 | CONV. SC 3A/B : NUM & RC DETAILS OF FDN-->CIVIL-->ENGINEERING-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-13 18:00 | 2020-05-12 17:40 | 2020-06-21 | 2020-07-10 18:00 |  |  | 2020-02-21 15:37 | 2020-07-17 15:22 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-NR-0023 |  | 2020-02-13 11:42 | 7012-155-PVC-C-069 |  |  |  | A |  |  |  | 19.5652 | 0.000179 | 0.09 | Plan & Actual | Date |  | 0 | 0 | 0 | 34.57 | 0 | 90.31 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3081 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-13 18:00 | 2020-03-27 18:00 |  | 10 | 2020-03-27 23:31 |  |  | 2020-03-31 17:40 | 2020-05-01 18:00 |  | 30 |  |  |  | 2020-04-06 17:40 | 2020-05-04 18:00 |  | 35 | 2020-06-19 10:27 |  |  | 2020-04-13 23:59 | 2020-05-11 18:00 |  | 65 | 2020-07-07 21:13 |  |  | 2020-04-18 17:40 | 2020-06-01 18:00 |  | 80 | 2020-07-07 21:25 | [5 empty] | 80 | 2020-07-17 15:07 | [5 empty] | 80 | 2020-07-17 15:07 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-12 17:40 | 2020-06-15 18:00 |  | 100 | 2020-07-17 15:14 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 170 |  |  |  |  | 101182
760 | Task(Task)-->E (Engineering) | CONV. SC 3A/B : DESIGN CALCULATION OF SUPER STRUCTURE |  | 1.7.1.2 | CONV. SC 3A/B : DESIGN CALCULATION OF SUPER STRUCTURE-->CIVIL-->ENGINEERING-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-03 17:40 | 2020-04-13 17:40 | 2020-04-11 09:00 | 2020-05-01 18:00 |  |  | 2020-03-03 17:40 | 2020-05-16 17:38 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0020A |  | 2020-02-13 11:42 | 7012-155-PVC-U-066 |  |  |  | A |  |  |  | 60.8696 | 0.000557 | 0.28 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3082 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-12 18:00 | 2020-03-11 18:00 |  | 10 | 2020-03-11 23:31 |  |  | 2020-03-03 17:40 | 2020-04-01 18:00 |  | 30 | 2020-04-01 23:31 |  |  | 2020-03-09 17:40 | 2020-04-04 18:00 |  | 35 | 2020-04-04 23:31 |  |  | 2020-03-14 23:59 | 2020-04-11 18:00 |  | 65 | 2020-04-11 23:31 |  |  | 2020-03-20 17:40 | 2020-05-16 18:00 |  | 80 | 2020-05-01 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-13 17:40 | 2020-05-30 18:00 |  | 100 | 2020-05-16 17:38 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 167 |  |  |  |  | 101179
761 | Task(Task)-->E (Engineering) | CONV. SC 3A/B : DESIGN CALCULATION OF SUB STRUCTURE |  | 1.7.1.2 | CONV. SC 3A/B : DESIGN CALCULATION OF SUB STRUCTURE-->CIVIL-->ENGINEERING-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-13 18:00 | 2020-05-12 17:40 | 2020-06-21 | 2020-07-07 18:00 |  |  | 2020-02-21 15:37 | 2020-07-07 21:26 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0021A |  | 2020-02-13 11:42 | 7012-155-PVC-U-067 |  |  |  | A |  |  |  | 19.5652 | 0.000179 | 0.09 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3083 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-13 18:00 | 2020-03-27 18:00 |  | 10 | 2020-03-27 23:31 |  |  | 2020-03-31 17:40 | 2020-05-01 18:00 |  | 30 |  |  |  | 2020-04-06 17:40 | 2020-05-04 18:00 |  | 35 |  |  |  | 2020-04-13 23:59 | 2020-05-11 18:00 |  | 65 | 2020-07-07 21:11 |  |  | 2020-04-18 17:40 | 2020-06-01 18:00 |  | 80 | 2020-07-07 21:24 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-12 17:40 | 2020-06-15 18:00 |  | 100 | 2020-07-07 21:27 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 168 |  |  |  |  | 101180
762 | Task(Task)-->E (Engineering) | STRUCTURAL | 1.7.1.3 | 1.7.1 | STRUCTURAL-->ENGINEERING-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-12 18:00 | 2020-04-13 17:40 | 2020-03-11 18:00 | 2020-05-30 18:00 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 80 | [15 empty] | 16.568 | 0.002847 | 0.28 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No | 3084 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036088
763 | Task(Task)-->E (Engineering) | CONV. SC 3A/B : STRUCTURAL GA |  | 1.7.1.3 | CONV. SC 3A/B : STRUCTURAL GA-->STRUCTURAL-->ENGINEERING-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-12 18:00 | 2020-04-13 17:40 | 2020-03-11 18:00 | 2020-05-30 18:00 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-GA-0021 |  | 2020-02-13 11:42 | 7012-155-PVC-B-068 |  |  |  | A |  |  |  | 100 | 0.002847 | 0.28 | Plan & Actual | Date |  | 0 | 0 | 0 | 105.1 | 0 | 100.4 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3085 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-12 18:00 | 2020-03-11 18:00 |  | 10 | 2020-03-11 23:31 |  |  | 2020-03-03 17:40 | 2020-04-01 18:00 |  | 30 | 2020-04-01 23:31 |  |  | 2020-03-09 17:40 | 2020-04-04 18:00 |  | 35 | 2020-04-04 23:31 |  |  | 2020-03-14 23:59 | 2020-04-11 18:00 |  | 65 | 2020-04-11 23:31 |  |  | 2020-03-20 17:40 | 2020-05-16 18:00 |  | 80 | 2020-05-26 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | 2020-10-13 21:59 | [5 empty] | 80 | 2020-10-13 21:59 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-13 17:40 | 2020-05-30 18:00 |  | 100 | [122 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 169 |  |  |  |  | 101181
764 | Task(Task)-->E (Engineering) | ELECTRICAL | 1.7.1.4 | 1.7.1 | ELECTRICAL-->ENGINEERING-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-08 18:00 | 2020-06-26 17:40 | 2020-04-12 | 2020-06-22 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 | [15 empty] | 39.645 | 0.006813 | 0.67 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No | 3088 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036089
765 | Task(Task)-->E (Engineering) | LIGHTING LAYOUT PLAN WITH POWER DISTRIBUTION ARRANGEMENT, SECTIONAL VIEW, BOM OF CONV. SC 3A/B |  | 1.7.1.4 | LIGHTING LAYOUT PLAN WITH POWER DISTRIBUTION ARRANGEMENT, SECTIONAL VIEW, BOM OF CONV. SC 3A/B-->ELECTRICAL-->ENGINEERING-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-08 18:00 | 2020-06-26 17:40 | 2020-04-12 | 2020-06-22 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5081 |  | 2020-02-13 11:45 | 7012-155-PVE-G-043 |  |  |  | A |  |  |  | 100 | 0.006813 | 0.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 248.42 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3089 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-05-08 18:00 | 2020-05-11 18:00 |  | 10 | 2020-04-06 23:31 |  |  | 2020-05-16 17:40 | 2020-05-18 18:00 |  | 30 | 2020-04-10 23:31 |  |  | 2020-05-22 17:40 | 2020-05-25 18:00 |  | 35 | 2020-04-12 23:31 |  |  | 2020-05-29 23:59 | 2020-06-01 18:00 |  | 65 | 2020-04-12 23:31 |  |  | 2020-06-04 17:40 | 2020-06-22 18:00 |  | 80 | 2020-04-23 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-26 17:40 | 2020-06-22 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 278 |  |  |  |  | 101289
766 | Task(Task)-->P (Procurement) | PROCUREMENT | 1.7.2 | 1.7 | PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-09-27 09:00 | 2021-02-13 18:00 | 2019-09-27 09:00 | 2021-06-13 23:59 |  |  | 2019-09-27 10:57 |  |  |  | 96.7388 | 35.3912 | [15 empty] | 76.2779 | 0.81937 | 80.58 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3091 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018362
767 | Task(Task)-->P (Procurement) | PURCHASE REQUISITION | 1.7.2.1 | 1.7.2 | PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-09-27 09:00 | 2020-05-19 18:00 | 2019-09-27 09:00 | 2020-05-29 18:00 |  |  | 2019-09-27 10:57 |  |  |  | 100 | 100 | [15 empty] | 5.0006 | 0.040974 | 4.03 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3092 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018363
768 | Task(Task)-->P (Procurement) | Metal Detector |  | 1.7.2.1 | Metal Detector-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-09-27 09:00 | 2019-09-27 18:00 | 2019-09-27 09:00 | 2019-09-27 18:00 |  |  | 2019-09-27 10:57 | 2019-09-27 10:57 |  |  | 100 | 100 | [15 empty] | 1.7413 | 0.000713 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3093 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018364
769 | Task(Task)-->P (Procurement) | Pulley |  | 1.7.2.1 | Pulley-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-09-27 09:00 | 2019-09-27 18:00 | 2020-02-05 09:00 | 2020-02-05 18:00 |  |  | 2020-02-05 16:16 | 2020-02-05 16:16 |  |  | 100 | 100 | [15 empty] | 11.194 | 0.004587 | 0.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3094 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018365
770 | Task(Task)-->P (Procurement) | Idler |  | 1.7.2.1 | Idler-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-19 09:00 | 2019-12-19 18:00 | 2020-02-13 09:00 | 2020-02-13 18:00 |  |  | 2020-02-13 15:44 | 2020-02-13 15:44 |  |  | 100 | 100 | [15 empty] | 15.4229 | 0.006319 | 0.62 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3095 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018366
771 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.7.2.1 | Plummer Block-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-17 | 2020-05-17 23:59 | 2020-02-10 09:00 | 2020-02-10 18:00 |  |  | 2020-02-10 09:26 | 2020-02-10 09:26 |  |  | 100 | 100 | [15 empty] | 0.74627 | 0.000306 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3096 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018367
772 | Task(Task)-->P (Procurement) | Bearing |  | 1.7.2.1 | Bearing-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-17 | 2020-05-17 23:59 | 2020-02-10 09:00 | 2020-02-10 18:00 |  |  | 2020-02-10 09:36 | 2020-02-10 09:36 |  |  | 100 | 100 | [15 empty] | 1.4925 | 0.000612 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3097 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018368
773 | Task(Task)-->P (Procurement) | Belting |  | 1.7.2.1 | Belting-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-07 09:00 | 2019-11-07 18:00 | 2020-01-20 09:00 | 2020-01-20 18:00 |  |  | 2020-01-20 15:54 | 2020-01-20 15:54 |  |  | 100 | 100 | [15 empty] | 15.9204 | 0.006523 | 0.64 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3098 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018369
774 | Task(Task)-->P (Procurement) | Scrapper |  | 1.7.2.1 | Scrapper-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-17 | 2019-11-17 23:59 | 2020-03-11 09:00 | 2020-03-11 18:00 |  |  | 2020-03-11 10:57 | 2020-03-11 10:57 |  |  | 100 | 100 | [15 empty] | 0.49751 | 0.000204 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3099 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018370
775 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.7.2.1 | Technological Structure-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-10 09:00 | 2020-03-10 18:00 | 2020-03-11 09:00 | 2020-03-11 18:00 |  |  | 2020-03-11 12:41 | 2020-03-11 12:41 |  |  | 100 | 100 | [15 empty] | 4.7264 | 0.001937 | 0.19 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3100 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018371
776 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.7.2.1 | Takeup Component-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-19 09:00 | 2020-05-19 18:00 | 2020-04-16 09:00 | 2020-04-16 18:00 |  |  | 2020-04-16 10:57 | 2020-04-16 10:57 |  |  | 100 | 100 | [15 empty] | 0.24876 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3101 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018372
777 | Task(Task)-->P (Procurement) | Gear Box |  | 1.7.2.1 | Gear Box-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-13 09:00 | 2019-11-13 18:00 | 2020-01-20 09:00 | 2020-01-20 18:00 |  |  | 2020-01-20 11:17 | 2020-01-20 11:17 |  |  | 100 | 100 | [15 empty] | 2.4876 | 0.001019 | 0.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3102 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018373
778 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.7.2.1 | Geared Coupling-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-21 09:00 | 2019-11-21 18:00 | 2020-01-22 09:00 | 2020-01-22 18:00 |  |  | 2020-01-22 10:41 | 2020-01-22 10:41 |  |  | 100 | 100 | [15 empty] | 0.24876 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3103 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018374
779 | Task(Task)-->P (Procurement) | Fluid Coupling |  | 1.7.2.1 | Fluid Coupling-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-25 09:00 | 2019-11-25 18:00 | 2020-01-22 09:00 | 2020-01-22 18:00 |  |  | 2020-01-22 09:54 | 2020-01-22 09:54 |  |  | 100 | 100 | [15 empty] | 2.4876 | 0.001019 | 0.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3104 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018375
780 | Task(Task)-->P (Procurement) | Brake |  | 1.7.2.1 | Brake-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-18 09:00 | 2019-12-18 18:00 | 2020-04-04 09:00 | 2020-04-04 18:00 |  |  | 2020-04-04 11:33 | 2020-04-04 11:33 |  |  | 100 | 100 | [15 empty] | 0.24876 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3105 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018376
781 | Task(Task)-->P (Procurement) | Building Structure |  | 1.7.2.1 | Building Structure-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-14 09:00 | 2020-03-14 18:00 | 2020-05-29 09:00 | 2020-05-29 18:00 |  |  | 2020-05-31 18:44 | 2020-05-31 18:44 |  |  | 100 | 100 | [15 empty] | 24.3781 | 0.009989 | 0.98 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3106 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018377
782 | Task(Task)-->P (Procurement) | HT AC MOTORS |  | 1.7.2.1 | HT AC MOTORS-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-07 09:00 | 2020-01-07 18:00 | 2020-01-17 09:00 | 2020-01-17 18:00 |  |  | 2020-01-17 10:57 | 2020-01-17 10:57 |  |  | 100 | 100 | [15 empty] | 7.2139 | 0.002956 | 0.29 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3107 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018378
783 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.7.2.1 | LIGHT & LIGHT FIXTURES-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-10 09:00 | 2020-03-10 18:00 | 2020-03-16 09:00 | 2020-03-16 18:00 |  |  | 2020-03-16 10:57 | 2020-03-16 10:57 |  |  | 100 | 100 | [15 empty] | 6.7164 | 0.002752 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3108 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018379
784 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.7.2.1 | LIGHTING POLES-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-27 09:00 | 2020-03-27 18:00 | 2020-04-30 09:00 | 2020-04-30 18:00 |  |  | 2020-04-30 10:57 | 2020-04-30 10:57 |  |  | 100 | 100 | [15 empty] | 2.9851 | 0.001223 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3109 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018380
785 | Task(Task)-->P (Procurement) | LPBS |  | 1.7.2.1 | LPBS-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-20 09:00 | 2020-03-20 18:00 | 2020-04-14 09:00 | 2020-04-14 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3110 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018381
786 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.7.2.1 | CONVEYOR BELT PROTECTION SWITCHES-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-08 09:00 | 2020-01-08 18:00 | 2020-01-08 09:00 | 2020-01-08 18:00 |  |  | 2020-01-08 10:57 | 2020-01-08 10:57 |  |  | 100 | 100 | [15 empty] | 1.2438 | 0.00051 | 0.05 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3111 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018382
787 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.7.2.1 | ZERO SPEED SWITCH-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-30 09:00 | 2019-12-30 18:00 | 2019-12-30 09:00 | 2019-12-30 18:00 |  |  | 2019-12-30 10:57 | 2019-12-30 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3112 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018383
788 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.7.2.1 | CHUTE BLOCK SWITCH-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-03 09:00 | 2020-01-03 18:00 | 2020-01-03 09:00 | 2020-01-03 18:00 |  |  | 2020-01-03 10:57 | 2020-01-03 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3113 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018384
789 | Task(Task)-->P (Procurement) | TECHNICAL CLEARANCE | 1.7.2.2 | 1.7.2 | TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-09-28 09:00 | 2020-06-18 18:00 | 2019-09-27 09:00 | 2020-06-12 18:00 |  |  | 2019-12-27 10:57 |  |  |  | 100 | 100 | [15 empty] | 5.0006 | 0.040974 | 4.03 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3114 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018385
790 | Task(Task)-->P (Procurement) | Metal Detector |  | 1.7.2.2 | Metal Detector-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-09-28 09:00 | 2020-01-06 18:00 | 2019-09-27 09:00 | 2019-12-27 18:00 |  |  | 2019-12-27 10:57 | 2019-12-27 10:57 |  |  | 100 | 100 | [15 empty] | 1.7413 | 0.000713 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3115 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018386
791 | Task(Task)-->P (Procurement) | Pulley |  | 1.7.2.2 | Pulley-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-09-28 09:00 | 2020-01-04 18:00 | 2020-02-05 09:00 | 2020-02-10 18:00 |  |  | 2020-02-06 16:19 | 2020-02-10 16:19 |  |  | 100 | 100 | [15 empty] | 11.194 | 0.004587 | 0.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3116 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018387
792 | Task(Task)-->P (Procurement) | Idler |  | 1.7.2.2 | Idler-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-20 09:00 | 2020-02-01 18:00 | 2020-02-13 09:00 | 2020-03-26 18:00 |  |  | 2020-02-14 10:57 | 2020-03-26 10:57 |  |  | 100 | 100 | [15 empty] | 15.4229 | 0.006319 | 0.62 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3117 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018388
793 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.7.2.2 | Plummer Block-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-18 09:00 | 2020-06-01 18:00 | 2020-02-10 09:00 | 2020-02-10 18:00 |  |  | 2020-02-10 09:28 | 2020-02-10 09:28 |  |  | 100 | 100 | [15 empty] | 0.74627 | 0.000306 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3118 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018389
794 | Task(Task)-->P (Procurement) | Bearing |  | 1.7.2.2 | Bearing-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-18 09:00 | 2020-06-16 18:00 | 2020-02-10 09:00 | 2020-02-10 18:00 |  |  | 2020-02-10 09:37 | 2020-02-10 09:37 |  |  | 100 | 100 | [15 empty] | 1.4925 | 0.000612 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3119 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018390
795 | Task(Task)-->P (Procurement) | Belting |  | 1.7.2.2 | Belting-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-08 09:00 | 2020-01-06 18:00 | 2020-01-20 09:00 | 2020-05-16 18:00 |  |  | 2020-05-16 10:57 | 2020-05-16 10:57 |  |  | 100 | 100 | [15 empty] | 15.9204 | 0.006523 | 0.64 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3120 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018391
796 | Task(Task)-->P (Procurement) | Scrapper |  | 1.7.2.2 | Scrapper-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-18 09:00 | 2020-03-16 18:00 | 2020-03-11 09:00 | 2020-03-26 18:00 |  |  | 2020-03-26 10:57 | 2020-03-26 10:57 |  |  | 100 | 100 | [15 empty] | 0.49751 | 0.000204 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3121 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018392
797 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.7.2.2 | Technological Structure-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-11 09:00 | 2020-03-20 18:00 | 2020-03-11 09:00 | 2020-03-17 18:00 |  |  | 2020-03-12 12:43 | 2020-03-17 12:43 |  |  | 100 | 100 | [15 empty] | 4.7264 | 0.001937 | 0.19 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3122 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018393
798 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.7.2.2 | Takeup Component-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-20 09:00 | 2020-06-18 18:00 | 2020-04-16 09:00 | 2020-04-16 18:00 |  |  | 2020-04-16 10:57 | 2020-04-16 10:57 |  |  | 100 | 100 | [15 empty] | 0.24876 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3123 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018394
799 | Task(Task)-->P (Procurement) | Gear Box |  | 1.7.2.2 | Gear Box-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-14 09:00 | 2020-02-26 18:00 | 2020-01-20 09:00 | 2020-03-20 18:00 |  |  | 2020-01-22 11:19 | 2020-03-20 11:19 |  |  | 100 | 100 | [15 empty] | 2.4876 | 0.001019 | 0.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3124 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018395
800 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.7.2.2 | Geared Coupling-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-22 09:00 | 2020-03-19 18:00 | 2020-01-22 09:00 | 2020-04-13 18:00 |  |  | 2020-04-13 10:46 | 2020-04-13 10:46 |  |  | 100 | 100 | [15 empty] | 0.24876 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3125 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018396
801 | Task(Task)-->P (Procurement) | Fluid Coupling |  | 1.7.2.2 | Fluid Coupling-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-26 09:00 | 2020-03-01 23:59 | 2020-01-22 09:00 | 2020-04-13 18:00 |  |  | 2020-01-23 09:54 | 2020-04-13 09:54 |  |  | 100 | 100 | [15 empty] | 2.4876 | 0.001019 | 0.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3126 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018397
802 | Task(Task)-->P (Procurement) | Brake |  | 1.7.2.2 | Brake-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-19 09:00 | 2020-03-09 18:00 | 2020-04-04 09:00 | 2020-04-22 18:00 |  |  | 2020-04-05 11:34 | 2020-04-22 11:34 |  |  | 100 | 100 | [15 empty] | 0.24876 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3127 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018398
803 | Task(Task)-->P (Procurement) | Building Structure |  | 1.7.2.2 | Building Structure-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-15 | 2020-03-21 18:00 | 2020-05-29 09:00 | 2020-05-29 18:00 |  |  | 2020-05-29 17:31 | 2020-05-29 17:31 |  |  | 100 | 100 | [15 empty] | 24.3781 | 0.009989 | 0.98 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3128 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018399
804 | Task(Task)-->P (Procurement) | HT AC MOTORS |  | 1.7.2.2 | HT AC MOTORS-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-08 09:00 | 2020-02-06 18:00 | 2020-01-17 09:00 | 2020-04-11 18:00 |  |  | 2020-04-11 10:57 | 2020-04-11 10:57 |  |  | 100 | 100 | [15 empty] | 7.2139 | 0.002956 | 0.29 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3129 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018400
805 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.7.2.2 | LIGHT & LIGHT FIXTURES-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-11 09:00 | 2020-03-25 18:00 | 2020-03-16 09:00 | 2020-06-02 18:00 |  |  | 2020-06-02 10:57 | 2020-06-02 10:57 |  |  | 100 | 100 | [15 empty] | 6.7164 | 0.002752 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3130 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018401
806 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.7.2.2 | LIGHTING POLES-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-28 09:00 | 2020-05-11 18:00 | 2020-04-30 09:00 | 2020-06-03 18:00 |  |  | 2020-06-03 10:57 | 2020-06-03 10:57 |  |  | 100 | 100 | [15 empty] | 2.9851 | 0.001223 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3131 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018402
807 | Task(Task)-->P (Procurement) | LPBS |  | 1.7.2.2 | LPBS-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-21 09:00 | 2020-04-04 18:00 | 2020-04-14 09:00 | 2020-06-12 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3132 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018403
808 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.7.2.2 | CONVEYOR BELT PROTECTION SWITCHES-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-09 09:00 | 2020-01-22 18:00 | 2020-01-08 09:00 | 2020-03-10 18:00 |  |  | 2020-03-10 10:57 | 2020-03-10 10:57 |  |  | 100 | 100 | [15 empty] | 1.2438 | 0.00051 | 0.05 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3133 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018404
809 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.7.2.2 | ZERO SPEED SWITCH-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-31 09:00 | 2020-01-14 18:00 | 2019-12-30 09:00 | 2020-03-07 18:00 |  |  | 2020-03-07 10:57 | 2020-03-07 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3134 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018405
810 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.7.2.2 | CHUTE BLOCK SWITCH-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-04 09:00 | 2020-01-18 18:00 | 2020-01-03 09:00 | 2020-01-16 18:00 |  |  | 2020-01-16 10:57 | 2020-01-16 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3135 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018406
811 | Task(Task)-->P (Procurement) | ORDERING | 1.7.2.3 | 1.7.2 | ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-01-05 | 2020-07-18 18:00 | 2019-12-27 09:00 | 2020-09-04 18:00 |  |  | 2020-01-05 08:00 |  |  |  | 100 | 98.3916 | [15 empty] | 10.0012 | 0.081948 | 8.06 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3136 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018407
812 | Task(Task)-->P (Procurement) | Metal Detector |  | 1.7.2.3 | Metal Detector-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-07 09:00 | 2020-02-05 18:00 | 2019-12-27 09:00 | 2020-03-20 18:00 |  |  | 2020-03-20 10:57 | 2020-03-20 10:57 |  |  | 100 | 100 | [15 empty] | 1.8564 | 0.001521 | 0.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3137 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018408
813 | Task(Task)-->P (Procurement) | Pulley |  | 1.7.2.3 | Pulley-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-05 | 2020-02-03 18:00 | 2020-02-10 09:00 | 2020-03-21 18:00 |  |  | 2020-01-05 08:00 | 2020-03-21 16:05 |  |  | 100 | 100 | [15 empty] | 11.0149 | 0.009026 | 0.89 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3138 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018409
814 | Task(Task)-->P (Procurement) | Idler |  | 1.7.2.3 | Idler-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-02 | 2020-03-02 18:00 | 2020-03-26 09:00 | 2020-04-30 18:00 |  |  | 2020-02-02 08:00 | 2020-04-29 16:05 |  |  | 100 | 100 | [15 empty] | 15.3465 | 0.012576 | 1.24 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3139 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018410
815 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.7.2.3 | Plummer Block-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-06-02 09:00 | 2020-07-01 18:00 | 2020-02-10 09:00 | 2020-03-24 18:00 |  |  | 2020-02-11 09:32 | 2020-03-24 09:32 |  |  | 100 | 100 | [15 empty] | 0.86634 | 0.00071 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3140 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018411
816 | Task(Task)-->P (Procurement) | Bearing |  | 1.7.2.3 | Bearing-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-06-17 09:00 | 2020-07-16 18:00 | 2020-02-10 09:00 | 2020-03-24 18:00 |  |  | 2020-02-11 09:40 | 2020-03-24 09:40 |  |  | 100 | 100 | [15 empty] | 1.3614 | 0.001116 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3141 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018412
817 | Task(Task)-->P (Procurement) | Belting |  | 1.7.2.3 | Belting-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-07 09:00 | 2020-02-20 18:00 | 2020-05-16 09:00 | 2020-09-04 18:00 |  |  | 2020-05-16 16:24 | 2020-09-04 16:24 |  |  | 100 | 100 | [15 empty] | 15.9653 | 0.013083 | 1.29 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3142 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018413
818 | Task(Task)-->P (Procurement) | Scrapper |  | 1.7.2.3 | Scrapper-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-17 09:00 | 2020-04-15 18:00 | 2020-03-26 09:00 | 2020-05-30 18:00 |  |  | 2020-05-30 10:57 | 2020-05-30 10:57 |  |  | 100 | 100 | [15 empty] | 0.49505 | 0.000406 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3143 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018414
819 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.7.2.3 | Technological Structure-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-21 09:00 | 2020-04-19 23:59 | 2020-03-17 09:00 | 2020-07-06 18:00 |  |  | 2020-03-18 12:44 | 2020-07-06 12:44 |  |  | 100 | 100 | [15 empty] | 4.703 | 0.003854 | 0.38 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3144 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018415
820 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.7.2.3 | Takeup Component-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-19 09:00 | 2020-07-18 18:00 | 2020-04-16 09:00 | 2020-08-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.24752 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3145 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018416
821 | Task(Task)-->P (Procurement) | Gear Box |  | 1.7.2.3 | Gear Box-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-27 09:00 | 2020-03-27 18:00 | 2020-03-20 09:00 | 2020-04-30 18:00 |  |  | 2020-03-21 11:21 | 2020-04-30 11:21 |  |  | 100 | 100 | [15 empty] | 2.4752 | 0.002028 | 0.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3146 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018417
822 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.7.2.3 | Geared Coupling-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-20 09:00 | 2020-04-18 18:00 | 2020-04-13 09:00 | 2020-04-30 18:00 |  |  | 2020-04-14 11:11 | 2020-04-30 11:11 |  |  | 100 | 100 | [15 empty] | 0.37129 | 0.000304 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3147 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018418
823 | Task(Task)-->P (Procurement) | Fluid Coupling |  | 1.7.2.3 | Fluid Coupling-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-02 09:00 | 2020-03-31 18:00 | 2020-04-13 09:00 | 2020-05-18 18:00 |  |  | 2020-04-14 09:54 | 2020-05-18 16:05 |  |  | 100 | 100 | [15 empty] | 2.599 | 0.00213 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3148 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018419
824 | Task(Task)-->P (Procurement) | Brake |  | 1.7.2.3 | Brake-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-10 09:00 | 2020-04-08 18:00 | 2020-04-22 09:00 | 2020-05-18 18:00 |  |  | 2020-04-23 11:38 | 2020-05-18 16:05 |  |  | 100 | 100 | [15 empty] | 0.24752 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3149 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018420
825 | Task(Task)-->P (Procurement) | Building Structure |  | 1.7.2.3 | Building Structure-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-22 | 2020-04-20 18:00 | 2020-05-29 09:00 | 2020-05-31 23:59 |  |  | 2020-05-31 18:49 | 2020-05-31 18:49 |  |  | 100 | 100 | [15 empty] | 24.2574 | 0.019878 | 1.96 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3150 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018421
826 | Task(Task)-->P (Procurement) | HT AC MOTORS |  | 1.7.2.3 | HT AC MOTORS-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-07 09:00 | 2020-03-07 18:00 | 2020-04-11 09:00 | 2020-06-25 18:00 |  |  | 2020-04-13 09:41 | 2020-06-25 09:41 |  |  | 100 | 100 | [15 empty] | 7.1782 | 0.005882 | 0.58 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3151 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018422
827 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.7.2.3 | LIGHT & LIGHT FIXTURES-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-26 09:00 | 2020-04-10 18:00 | 2020-06-02 09:00 | 2020-07-31 18:00 |  |  | 2020-06-03 15:51 | 2020-06-29 15:51 |  |  | 100 | 100 | [15 empty] | 6.5594 | 0.005375 | 0.53 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3152 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018423
828 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.7.2.3 | LIGHTING POLES-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-12 09:00 | 2020-06-25 18:00 | 2020-06-03 09:00 | 2020-06-24 18:00 |  |  | 2020-06-15 10:57 | 2020-06-15 10:57 |  |  | 100 | 100 | [15 empty] | 2.9703 | 0.002434 | 0.24 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3153 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018424
829 | Task(Task)-->P (Procurement) | LPBS |  | 1.7.2.3 | LPBS-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-05 | 2020-04-20 18:00 | 2020-06-12 09:00 | 2020-08-19 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.12376 | 0.000101 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3154 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018425
830 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.7.2.3 | CONVEYOR BELT PROTECTION SWITCHES-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-23 09:00 | 2020-02-05 18:00 | 2020-03-10 09:00 | 2020-08-17 18:00 | [6 empty] | 100 | 0 | [15 empty] | 1.2376 | 0.001014 | 0.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3155 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018426
831 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.7.2.3 | ZERO SPEED SWITCH-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-15 09:00 | 2020-02-01 18:00 | 2020-03-07 09:00 | 2020-08-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3156 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018427
832 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.7.2.3 | CHUTE BLOCK SWITCH-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-19 | 2020-01-31 18:00 | 2020-01-16 09:00 | 2020-02-01 18:00 |  |  | 2020-02-01 10:57 | 2020-02-01 10:57 |  |  | 100 | 100 | [15 empty] | 0.12376 | 0.000101 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3157 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018428
833 | Task(Task)-->P (Procurement) | ITP APPROVAL | 1.7.2.4 | 1.7.2 | ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-02-01 09:00 | 2020-08-25 18:00 | 2020-03-20 09:00 | 2020-11-30 18:00 |  |  | 2020-03-20 16:01 |  |  |  | 100 | 46.0159 | [15 empty] | 5.0006 | 0.040974 | 4.03 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3158 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018429
834 | Task(Task)-->P (Procurement) | Metal Detector |  | 1.7.2.4 | Metal Detector-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-06 09:00 | 2020-03-16 18:00 | 2020-03-20 09:00 | 2020-09-02 18:00 |  |  | 2020-03-20 16:01 | 2020-09-02 16:01 |  |  | 100 | 100 | [15 empty] | 1.7413 | 0.000713 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3159 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018430
835 | Task(Task)-->P (Procurement) | Pulley |  | 1.7.2.4 | Pulley-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-04 09:00 | 2020-03-14 18:00 | 2020-03-21 09:00 | 2020-05-11 18:00 | [6 empty] | 100 | 0 | [15 empty] | 11.194 | 0.004587 | 0.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3160 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018431
836 | Task(Task)-->P (Procurement) | Idler |  | 1.7.2.4 | Idler-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-03 09:00 | 2020-04-11 18:00 | 2020-04-30 09:00 | 2020-05-19 18:00 |  |  | 2020-04-13 16:21 | 2020-05-19 16:21 |  |  | 100 | 100 | [15 empty] | 15.4229 | 0.006319 | 0.62 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3161 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018432
837 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.7.2.4 | Plummer Block-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-02 09:00 | 2020-08-10 18:00 | 2020-03-24 09:00 | 2020-08-13 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.74627 | 0.000306 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3162 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018433
838 | Task(Task)-->P (Procurement) | Bearing |  | 1.7.2.4 | Bearing-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-17 09:00 | 2020-08-25 18:00 | 2020-03-24 09:00 | 2020-03-29 23:59 | [6 empty] | 100 | 0 | [15 empty] | 1.4925 | 0.000612 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3163 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018434
839 | Task(Task)-->P (Procurement) | Belting |  | 1.7.2.4 | Belting-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-21 09:00 | 2020-03-31 18:00 | 2020-09-04 09:00 | 2020-09-30 18:00 |  |  | 2020-09-04 16:30 | 2020-09-30 16:30 |  |  | 100 | 100 | [15 empty] | 15.9204 | 0.006523 | 0.64 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3164 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018435
840 | Task(Task)-->P (Procurement) | Scrapper |  | 1.7.2.4 | Scrapper-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-16 09:00 | 2020-05-25 18:00 | 2020-05-30 09:00 | 2020-06-25 18:00 |  |  | 2020-05-30 16:29 | 2020-06-25 16:30 |  |  | 100 | 100 | [15 empty] | 0.49751 | 0.000204 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3165 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018436
841 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.7.2.4 | Technological Structure-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-20 09:00 | 2020-05-29 18:00 | 2020-07-06 09:00 | 2020-07-16 18:00 | [6 empty] | 100 | 0 | [15 empty] | 4.7264 | 0.001937 | 0.19 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3166 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018437
842 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.7.2.4 | Takeup Component-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-19 | 2020-08-17 18:00 | 2020-06-25 09:00 | 2020-06-25 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.24876 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3167 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018438
843 | Task(Task)-->P (Procurement) | Gear Box |  | 1.7.2.4 | Gear Box-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-28 09:00 | 2020-05-06 18:00 | 2020-04-30 09:00 | 2020-06-22 18:00 |  |  | 2020-04-30 16:57 | 2020-06-22 16:57 |  |  | 100 | 100 | [15 empty] | 2.4876 | 0.001019 | 0.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3168 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018439
844 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.7.2.4 | Geared Coupling-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-19 | 2020-05-28 18:00 | 2020-04-30 09:00 | 2020-06-18 18:00 |  |  | 2020-04-30 01:54 | 2020-06-18 17:31 |  |  | 100 | 100 | [15 empty] | 0.24876 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3169 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018440
845 | Task(Task)-->P (Procurement) | Fluid Coupling |  | 1.7.2.4 | Fluid Coupling-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-01 09:00 | 2020-05-10 23:59 | 2020-05-18 09:00 | 2020-08-18 18:00 | [6 empty] | 100 | 0 | [15 empty] | 2.4876 | 0.001019 | 0.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3170 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018441
846 | Task(Task)-->P (Procurement) | Brake |  | 1.7.2.4 | Brake-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-09 09:00 | 2020-05-18 18:00 | 2020-05-18 09:00 | 2020-10-14 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.24876 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3171 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018442
847 | Task(Task)-->P (Procurement) | Building Structure |  | 1.7.2.4 | Building Structure-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-21 09:00 | 2020-04-27 18:00 | 2020-05-31 | 2020-08-04 18:00 |  |  | 2020-06-25 19:04 |  |  |  | 100 | 0 | [15 empty] | 24.3781 | 0.009989 | 0.98 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3172 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018443
848 | Task(Task)-->P (Procurement) | HT AC MOTORS |  | 1.7.2.4 | HT AC MOTORS-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-08 | 2020-04-16 18:00 | 2020-09-11 09:00 | 2020-11-10 18:00 |  |  | 2020-09-11 15:20 |  |  |  | 100 | 0 | [15 empty] | 7.2139 | 0.002956 | 0.29 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3173 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018444
849 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.7.2.4 | LIGHT & LIGHT FIXTURES-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-11 09:00 | 2020-05-20 18:00 | 2020-07-28 09:00 | 2020-09-08 18:00 |  |  | 2020-07-08 17:23 | 2020-09-08 17:23 |  |  | 100 | 100 | [15 empty] | 6.7164 | 0.002752 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3174 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018445
850 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.7.2.4 | LIGHTING POLES-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-06-26 09:00 | 2020-08-04 18:00 | 2020-06-23 09:00 | 2020-09-08 18:00 |  |  | 2020-06-23 17:33 | 2020-09-08 17:05 |  |  | 100 | 100 | [15 empty] | 2.9851 | 0.001223 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3175 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018446
851 | Task(Task)-->P (Procurement) | LPBS |  | 1.7.2.4 | LPBS-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-21 09:00 | 2020-05-30 18:00 | 2020-07-29 09:00 | 2020-08-21 18:00 |  |  | 2020-07-29 14:59 | 2020-08-22 12:54 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3176 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018447
852 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.7.2.4 | CONVEYOR BELT PROTECTION SWITCHES-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-06 09:00 | 2020-03-16 18:00 | 2020-09-24 09:00 | 2020-11-30 18:00 | [6 empty] | 100 | 0 | [15 empty] | 1.2438 | 0.00051 | 0.05 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3177 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018448
853 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.7.2.4 | ZERO SPEED SWITCH-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-02 | 2020-03-12 18:00 | 2020-08-02 | 2020-09-10 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3178 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018449
854 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.7.2.4 | CHUTE BLOCK SWITCH-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-01 09:00 | 2020-03-11 18:00 | 2020-07-02 09:00 | 2020-08-04 18:00 |  |  | 2020-07-17 16:57 | 2020-08-04 16:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3179 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018450
855 | Task(Task)-->P (Procurement) | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE | 1.7.2.5 | 1.7.2 | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-02-01 09:00 | 2020-09-16 18:00 | 2020-02-01 09:00 | 2020-11-16 18:00 |  |  | 2020-02-11 21:29 |  |  |  | 100 | 82.3555 | [15 empty] | 15.0019 | 0.12292 | 12.09 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3180 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018451
856 | Task(Task)-->P (Procurement) | Metal Detector |  | 1.7.2.5 | Metal Detector-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-06 09:00 | 2020-04-05 23:59 | 2020-03-20 09:00 | 2020-08-13 18:00 |  |  | 2020-07-03 15:41 | 2020-07-27 01:06 |  |  | 100 | 100 | [15 empty] | 1.8182 | 0.002235 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3181 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018452
857 | Task(Task)-->P (Procurement) | Pulley |  | 1.7.2.5 | Pulley-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-04 09:00 | 2020-03-29 23:59 | 2020-03-21 09:00 | 2020-03-25 18:00 |  |  | 2020-03-22 18:03 | 2020-03-25 18:03 |  |  | 100 | 100 | [15 empty] | 11.0744 | 0.013613 | 1.34 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3182 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018453
858 | Task(Task)-->P (Procurement) | Idler |  | 1.7.2.5 | Idler-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-03 09:00 | 2020-05-01 18:00 | 2020-04-30 09:00 | 2020-06-25 18:00 |  |  | 2020-06-25 14:53 | 2020-06-25 14:53 |  |  | 100 | 100 | [15 empty] | 15.3719 | 0.018895 | 1.86 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3183 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018454
859 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.7.2.5 | Plummer Block-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-07-02 09:00 | 2020-08-30 23:59 | 2020-03-24 09:00 | 2020-06-29 18:00 |  |  | 2020-05-14 14:59 | 2020-06-29 14:59 |  |  | 100 | 100 | [15 empty] | 0.82645 | 0.001016 | 0.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3184 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018455
860 | Task(Task)-->P (Procurement) | Bearing |  | 1.7.2.5 | Bearing-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-07-17 09:00 | 2020-07-17 18:00 | 2020-03-24 09:00 | 2020-03-24 18:00 |  |  | 2020-03-24 10:05 | 2020-03-24 10:05 |  |  | 100 | 100 | [15 empty] | 1.405 | 0.001727 | 0.17 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3185 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018456
861 | Task(Task)-->P (Procurement) | Belting |  | 1.7.2.5 | Belting-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-21 09:00 | 2020-04-20 18:00 | 2020-09-04 09:00 | 2020-11-15 23:59 |  |  | 2020-09-04 16:36 |  |  |  | 100 | 50 | [15 empty] | 15.9504 | 0.019606 | 1.93 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3186 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018457
862 | Task(Task)-->P (Procurement) | Scrapper |  | 1.7.2.5 | Scrapper-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-16 09:00 | 2020-06-14 23:59 | 2020-05-30 09:00 | 2020-07-30 18:00 |  |  | 2020-05-30 16:35 | 2020-07-30 16:35 |  |  | 100 | 100 | [15 empty] | 0.49587 | 0.00061 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3187 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018458
863 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.7.2.5 | Technological Structure-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-20 09:00 | 2020-09-16 18:00 | 2020-07-06 09:00 | 2020-07-06 18:00 |  |  | 2020-07-06 12:45 | 2020-07-06 12:45 |  |  | 100 | 100 | [15 empty] | 4.7107 | 0.00579 | 0.57 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3188 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018459
864 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.7.2.5 | Takeup Component-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-19 | 2020-08-27 18:00 | 2020-08-04 09:00 | 2020-08-04 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.24793 | 0.000305 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3189 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018460
865 | Task(Task)-->P (Procurement) | Gear Box |  | 1.7.2.5 | Gear Box-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-28 09:00 | 2020-05-26 18:00 | 2020-04-30 09:00 | 2020-07-01 18:00 |  |  | 2020-04-30 15:33 | 2020-07-01 15:33 |  |  | 100 | 100 | [15 empty] | 2.4793 | 0.003048 | 0.3 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3190 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018461
866 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.7.2.5 | Geared Coupling-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-19 | 2020-06-17 18:00 | 2020-04-30 09:00 | 2020-07-30 18:00 |  |  | 2020-04-30 15:31 | 2020-07-06 15:31 |  |  | 100 | 100 | [15 empty] | 0.33058 | 0.000406 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3191 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018462
867 | Task(Task)-->P (Procurement) | Fluid Coupling |  | 1.7.2.5 | Fluid Coupling-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-01 09:00 | 2020-05-30 18:00 | 2020-05-18 09:00 | 2020-08-21 18:00 | [6 empty] | 100 | 0 | [15 empty] | 2.562 | 0.003149 | 0.31 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3192 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018463
868 | Task(Task)-->P (Procurement) | Brake |  | 1.7.2.5 | Brake-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-09 09:00 | 2020-06-07 23:59 | 2020-05-18 09:00 | 2020-08-13 18:00 |  |  | 2020-06-16 17:39 |  |  |  | 100 | 0 | [15 empty] | 0.24793 | 0.000305 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3193 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018464
869 | Task(Task)-->P (Procurement) | Building Structure |  | 1.7.2.5 | Building Structure-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-19 | 2020-04-25 18:00 | 2020-05-31 | 2020-05-31 23:59 |  |  | 2020-05-31 18:54 | 2020-06-22 18:54 |  |  | 100 | 100 | [15 empty] | 24.2975 | 0.029867 | 2.94 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3194 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018465
870 | Task(Task)-->P (Procurement) | HT AC MOTORS |  | 1.7.2.5 | HT AC MOTORS-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-08 | 2020-05-21 18:00 | 2020-07-18 09:00 | 2020-09-28 18:00 |  |  | 2020-07-18 09:04 | 2020-09-28 10:23 |  |  | 100 | 100 | [15 empty] | 7.1901 | 0.008838 | 0.87 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3195 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018466
871 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.7.2.5 | LIGHT & LIGHT FIXTURES-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-11 09:00 | 2020-05-25 18:00 | 2020-07-10 09:00 | 2020-11-16 18:00 |  |  | 2020-07-14 10:44 |  |  |  | 100 | 0 | [15 empty] | 6.6116 | 0.008127 | 0.8 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3196 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018467
872 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.7.2.5 | LIGHTING POLES-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-06-26 09:00 | 2020-08-09 23:59 | 2020-05-30 09:00 | 2020-08-08 18:00 |  |  | 2020-06-18 17:09 | 2020-08-07 15:00 |  |  | 100 | 100 | [15 empty] | 2.9752 | 0.003657 | 0.36 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3197 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018468
873 | Task(Task)-->P (Procurement) | LPBS |  | 1.7.2.5 | LPBS-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-21 09:00 | 2020-06-04 18:00 | 2020-07-25 09:00 | 2020-08-22 18:00 |  |  | 2020-07-24 18:44 | 2020-08-22 12:57 |  |  | 100 | 100 | [15 empty] | 0.082645 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3198 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018469
874 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.7.2.5 | CONVEYOR BELT PROTECTION SWITCHES-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-06 09:00 | 2020-03-21 18:00 | 2020-08-11 09:00 | 2020-09-19 18:00 |  |  | 2020-08-11 13:11 | 2020-09-19 12:58 |  |  | 100 | 100 | [15 empty] | 1.2397 | 0.001524 | 0.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3199 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018470
875 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.7.2.5 | ZERO SPEED SWITCH-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-02 | 2020-03-17 18:00 | 2020-08-09 | 2020-10-29 18:00 |  |  | 2020-08-09 13:16 | 2020-10-29 12:59 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3200 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018471
876 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.7.2.5 | CHUTE BLOCK SWITCH-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-01 09:00 | 2020-03-16 18:00 | 2020-02-01 09:00 | 2020-07-15 18:00 |  |  | 2020-02-11 21:29 | 2020-07-15 21:29 |  |  | 100 | 100 | [15 empty] | 0.082645 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3201 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018472
877 | Task(Task)-->P (Procurement) | MANUFACTURING & RECEIPT AT SITE (MRN) | 1.7.2.6 | 1.7.2 | MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-17 09:00 | 2021-02-13 18:00 | 2020-03-24 09:00 | 2021-06-13 23:59 |  |  | 2020-03-25 18:05 |  |  |  | 94.5642 | 1.4895 | [15 empty] | 59.995 | 0.49158 | 48.35 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3202 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018473
878 | Task(Task)-->P (Procurement) | Metal Detector |  | 1.7.2.6 | Metal Detector-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-06 09:00 | 2020-10-02 18:00 | 2020-08-13 09:00 | 2020-12-31 18:00 |  |  | 2020-08-13 16:03 |  |  |  | 100 | 25 | [15 empty] | 1.84 | 0.009045 | 0.89 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3203 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018474
879 | Task(Task)-->P (Procurement) | Pulley |  | 1.7.2.6 | Pulley-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-30 09:00 | 2020-11-20 18:00 | 2020-03-25 09:00 | 2020-11-30 18:00 |  |  | 2020-03-25 18:05 |  |  |  | 95.7627 | 0 | [15 empty] | 11.0399 | 0.05427 | 5.34 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3204 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018475
880 | Task(Task)-->P (Procurement) | Idler |  | 1.7.2.6 | Idler-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-02 09:00 | 2020-11-13 18:00 | 2020-06-25 09:00 | 2020-12-31 18:00 | [6 empty] | 98.4694 | 0 | [15 empty] | 15.3814 | 0.075613 | 7.44 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3205 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018476
881 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.7.2.6 | Plummer Block-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-31 09:00 | 2020-12-23 18:00 | 2020-06-29 09:00 | 2020-12-31 18:00 | [6 empty] | 62.6087 | 0 | [15 empty] | 0.80628 | 0.003964 | 0.39 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3206 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018477
882 | Task(Task)-->P (Procurement) | Bearing |  | 1.7.2.6 | Bearing-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-26 09:00 | 2020-12-23 18:00 | 2020-03-24 09:00 | 2020-09-09 18:00 | [6 empty] | 64.1667 | 0 | [15 empty] | 1.3852 | 0.006809 | 0.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3207 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018478
883 | Task(Task)-->P (Procurement) | Belting |  | 1.7.2.6 | Belting-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-21 09:00 | 2020-11-16 18:00 | 2020-11-16 09:00 | 2021-06-13 23:59 | [6 empty] | 97.1429 | 0 | [15 empty] | 15.9603 | 0.078458 | 7.72 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3208 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018479
884 | Task(Task)-->P (Procurement) | Scrapper |  | 1.7.2.6 | Scrapper-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-15 09:00 | 2020-12-11 18:00 | 2020-07-30 09:00 | 2020-12-31 18:00 | [6 empty] | 82.7778 | 0 | [15 empty] | 0.45483 | 0.002236 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3209 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018480
885 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.7.2.6 | Technological Structure-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-19 09:00 | 2021-02-13 18:00 | 2020-07-06 09:00 | 2021-01-31 23:59 | [6 empty] | 60.4167 | 0 | [15 empty] | 4.693 | 0.02307 | 2.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3210 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018481
886 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.7.2.6 | Takeup Component-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-28 09:00 | 2020-12-25 18:00 | 2020-08-04 09:00 | 2020-12-25 18:00 | [6 empty] | 62.5 | 0 | [15 empty] | 0.26876 | 0.001321 | 0.13 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3211 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018482
887 | Task(Task)-->P (Procurement) | Gear Box |  | 1.7.2.6 | Gear Box-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-27 09:00 | 2020-12-22 18:00 | 2020-07-01 09:00 | 2020-12-31 18:00 |  |  | 2020-07-01 17:25 |  |  |  | 80 | 30 | [15 empty] | 2.5016 | 0.012297 | 1.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3212 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018483
888 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.7.2.6 | Geared Coupling-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-18 09:00 | 2020-12-15 18:00 | 2020-07-30 09:00 | 2020-11-30 18:00 |  |  | 2020-07-30 17:44 |  |  |  | 80.663 | 90 | [15 empty] | 0.31011 | 0.001524 | 0.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3213 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018484
889 | Task(Task)-->P (Procurement) | Fluid Coupling |  | 1.7.2.6 | Fluid Coupling-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-31 | 2020-12-26 18:00 | 2020-08-21 09:00 | 2021-01-31 23:59 | [6 empty] | 78.0952 | 0 | [15 empty] | 2.5842 | 0.012704 | 1.25 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3214 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018485
890 | Task(Task)-->P (Procurement) | Brake |  | 1.7.2.6 | Brake-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-08 09:00 | 2020-12-04 18:00 | 2020-08-13 09:00 | 2020-11-30 18:00 | [6 empty] | 86.6667 | 0 | [15 empty] | 0.26876 | 0.001321 | 0.13 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3215 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018486
891 | Task(Task)-->P (Procurement) | Building Structure |  | 1.7.2.6 | Building Structure-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-28 09:00 | 2020-09-18 18:00 | 2020-05-31 | 2021-03-31 18:00 | [6 empty] | 100 | 0 | [15 empty] | 24.3126 | 0.11952 | 11.76 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3216 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018487
892 | Task(Task)-->P (Procurement) | HT AC MOTORS |  | 1.7.2.6 | HT AC MOTORS-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-22 09:00 | 2020-11-17 18:00 | 2020-11-11 09:00 | 2021-05-09 23:59 |  |  | 2020-09-28 10:24 |  |  |  | 96.1111 | 0 | [15 empty] | 7.1945 | 0.035367 | 3.48 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3217 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018488
893 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.7.2.6 | LIGHT & LIGHT FIXTURES-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-26 09:00 | 2020-10-21 18:00 | 2020-11-17 09:00 | 2021-04-14 18:00 | [6 empty] | 100 | 0 | [15 empty] | 6.595 | 0.03242 | 3.19 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3218 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018489
894 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.7.2.6 | LIGHTING POLES-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-10 09:00 | 2020-11-07 18:00 | 2020-09-09 09:00 | 2020-12-07 18:00 |  |  | 2020-08-07 15:00 |  |  |  | 100 | 0 | [15 empty] | 2.9977 | 0.014736 | 1.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3219 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018490
895 | Task(Task)-->P (Procurement) | LPBS |  | 1.7.2.6 | LPBS-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-05 09:00 | 2020-09-16 18:00 | 2020-08-23 | 2020-12-04 18:00 |  |  | 2020-08-22 13:00 |  |  |  | 100 | 0 | [15 empty] | 0.082696 | 0.000407 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3220 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018491
896 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.7.2.6 | CONVEYOR BELT PROTECTION SWITCHES-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-22 | 2020-08-05 18:00 | 2020-12-01 09:00 | 2021-04-16 18:00 | [6 empty] | 100 | 0 | [15 empty] | 1.2404 | 0.006098 | 0.6 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3221 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018492
897 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.7.2.6 | ZERO SPEED SWITCH-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-18 09:00 | 2020-07-27 18:00 | 2020-10-30 09:00 | 2021-03-10 18:00 |  |  | 2020-10-29 13:03 |  |  |  | 100 | 0 | [15 empty] | 0.020674 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3222 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018493
898 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.7.2.6 | CHUTE BLOCK SWITCH-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-17 09:00 | 2020-07-31 18:00 | 2020-07-02 09:00 | 2020-11-15 23:59 |  |  | 2020-07-15 21:36 |  |  |  | 100 | 0 | [15 empty] | 0.062022 | 0.000305 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3223 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018494
899 | Task(Task)-->C (Construction) | CONSTRUCTION | 1.7.3 | 1.7 | CONSTRUCTION-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-27 09:00 | 2021-08-25 18:00 | 2020-07-14 09:00 | 2022-04-17 23:59 |  |  | 2020-07-15 14:57 |  |  |  | 36.2313 | 8.5111 | [15 empty] | 22.1223 | 0.23764 | 23.37 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3224 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018495
900 | Task(Task)-->C (Construction) | CIVIL | 1.7.3.1 | 1.7.3 | CIVIL-->CONSTRUCTION-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-27 09:00 | 2020-06-21 23:59 | 2020-07-14 09:00 | 2020-12-02 18:00 |  |  | 2020-07-15 14:57 |  |  |  | 100 | 74.9174 | [15 empty] | 11.3605 | 0.026997 | 2.48 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3225 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018496
901 | Task(Task)-->C (Construction) | AVAILABILITY OF FRONT BY NTPC |  | 1.7.3.1 | AVAILABILITY OF FRONT BY NTPC-->CIVIL-->CONSTRUCTION-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-27 09:00 | 2020-04-27 18:00 | 2020-07-14 09:00 | 2020-11-10 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3226 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018497
902 | Task(Task)-->C (Construction) | EXCAVATION |  | 1.7.3.1 | EXCAVATION-->CIVIL-->CONSTRUCTION-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-04 09:00 | 2020-05-12 18:00 | 2020-07-15 09:00 | 2020-11-15 23:59 |  |  | 2020-07-15 14:57 |  |  |  | 100 | 97.1963 | [15 empty] | 17.3387 | 0.004681 | 0.43 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 1605 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3227 | 0 | 4 | Low | Niharendu Kamle | [6 empty] | 0 | 0 | [222 empty] | Excavation | [23 empty] | 1018498
903 | Task(Task)-->C (Construction) | PCC |  | 1.7.3.1 | PCC-->CIVIL-->CONSTRUCTION-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-16 09:00 | 2020-05-22 18:00 | 2020-07-24 09:00 | 2020-11-17 18:00 | [6 empty] | 100 | 70 | [15 empty] | 3.629 | 0.00098 | 0.09 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3228 | 0 | 4 | Low | Niharendu Kamle | [6 empty] | 0 | 0 | [222 empty] | PCC | [23 empty] | 1018499
904 | Task(Task)-->C (Construction) | FOUNDATIONS - RAFT |  | 1.7.3.1 | FOUNDATIONS - RAFT-->CIVIL-->CONSTRUCTION-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-23 09:00 | 2020-06-06 18:00 | 2020-08-20 09:00 | 2020-12-02 18:00 | [6 empty] | 100 | 96.2963 | [15 empty] | 57.6613 | 0.015567 | 1.43 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3229 | 0 | 4 | Low | Niharendu Kamle | [6 empty] | 0 | 0 | [246 empty] | 1018500
905 | Task(Task)-->C (Construction) | PADESTALS FOR SC-1A,SC-1B, SC-2A & SC-2B CONV. STR. |  | 1.7.3.1 | PADESTALS FOR SC-1A,SC-1B, SC-2A & SC-2B CONV. STR.-->CIVIL-->CONSTRUCTION-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-02 09:00 | 2020-06-21 23:59 | 2020-08-30 | 2020-09-18 18:00 | [6 empty] | 100 | 0 | [15 empty] | 21.371 | 0.00577 | 0.53 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3230 | 0 | 4 | Low | Niharendu Kamle | [6 empty] | 0 | 0 | [246 empty] | 1018501
906 | Task(Task)-->C (Construction) | STRUCTURAL WORKS | 1.7.3.2 | 1.7.3 | STRUCTURAL WORKS-->CONSTRUCTION-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-27 09:00 | 2021-01-31 23:59 | 2020-10-17 09:00 | 2021-04-23 18:00 | [6 empty] | 56.6138 | 0 | [15 empty] | 43.9304 | 0.1044 | 9.59 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3231 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018502
907 | Task(Task)-->C (Construction) | ERECTION OF STRUCTURAL STEEL |  | 1.7.3.2 | ERECTION OF STRUCTURAL STEEL-->STRUCTURAL WORKS-->CONSTRUCTION-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-27 09:00 | 2021-01-31 23:59 | 2020-10-17 09:00 | 2021-04-23 18:00 | [6 empty] | 56.6138 | 0 | [15 empty] | 100 | 0.1044 | 9.59 | Plan & Actual | Quantity | Metric Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 148 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3232 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018503
908 | Task(Task)-->C (Construction) | MECHANICAL EQUIPMENT WORKS | 1.7.3.3 | 1.7.3 | MECHANICAL EQUIPMENT WORKS-->CONSTRUCTION-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-02-14 | 2021-06-15 18:00 | 2021-04-24 09:00 | 2021-07-17 18:00 | [6 empty] | 0 | 0 | [15 empty] | 17.3156 | 0.041148 | 3.78 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5458 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018504
909 | Task(Task)-->C (Construction) | ERECTION OF SC 3A |  | 1.7.3.3 | ERECTION OF SC 3A-->MECHANICAL EQUIPMENT WORKS-->CONSTRUCTION-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-02-14 | 2021-03-20 18:00 | 2021-04-24 09:00 | 2021-05-28 18:00 | [6 empty] | 0 | 0 | [15 empty] | 48.5488 | 0.019977 | 1.84 | Plan & Actual | Quantity | Meter | 0 | 0 | 0 | 0 | 0 | 0 | 130 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3233 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018505
910 | Task(Task)-->C (Construction) | ERECTION OF SC 3B |  | 1.7.3.3 | ERECTION OF SC 3B-->MECHANICAL EQUIPMENT WORKS-->CONSTRUCTION-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-03-21 | 2021-04-24 18:00 | 2021-05-29 09:00 | 2021-07-02 18:00 | [6 empty] | 0 | 0 | [15 empty] | 48.5488 | 0.019977 | 1.84 | Plan & Actual | Quantity | Meter | 0 | 0 | 0 | 0 | 0 | 0 | 130 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5417 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018506
911 | Task(Task)-->C (Construction) | ERECTION OF METAL DETECTOR |  | 1.7.3.3 | ERECTION OF METAL DETECTOR-->MECHANICAL EQUIPMENT WORKS-->CONSTRUCTION-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-06-01 09:00 | 2021-06-15 18:00 | 2021-07-03 09:00 | 2021-07-17 18:00 | [6 empty] | 0 | 0 | [15 empty] | 2.9024 | 0.001194 | 0.11 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5459 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018507
912 | Task(Task)-->C (Construction) | BELT LAYING & JOINTING WORK |  | 1.7.3 | BELT LAYING & JOINTING WORK-->CONSTRUCTION-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-06-16 09:00 | 2021-08-13 18:00 | 2021-07-18 | 2021-09-14 18:00 | [6 empty] | 0 | 0 | [15 empty] | 7.7416 | 0.018397 | 1.69 | Plan & Actual | Quantity | Meter | 0 | 0 | 0 | 0 | 0 | 0 | 1090 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3234 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018508
913 | Task(Task)-->C (Construction) | ELECTRICAL & INSTRUMENTATION | 1.7.3.5 | 1.7.3 | ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-01-27 09:00 | 2021-08-25 18:00 | 2021-04-19 09:00 | 2022-04-17 23:59 | [6 empty] | 0 | 0 | [15 empty] | 19.6519 | 0.0467 | 4.29 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3235 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018509
914 | Task(Task)-->C (Construction) | CABLE TRAY |  | 1.7.3.5 | CABLE TRAY-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-02-01 09:00 | 2021-02-02 18:00 | 2021-04-24 09:00 | 2021-04-25 23:59 | [6 empty] | 0 | 0 | [15 empty] | 4.9065 | 0.002291 | 0.21 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3236 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018510
915 | Task(Task)-->C (Construction) | POWER CABLE |  | 1.7.3.5 | POWER CABLE-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-06-16 09:00 | 2021-06-16 18:00 | 2021-07-25 | 2021-07-25 23:59 | [6 empty] | 0 | 0 | [15 empty] | 3.7383 | 0.001746 | 0.16 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 1158 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3237 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018511
916 | Task(Task)-->C (Construction) | CONTROL CABLE |  | 1.7.3.5 | CONTROL CABLE-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-06-16 09:00 | 2021-06-16 18:00 | 2021-10-26 09:00 | 2021-10-26 18:00 | [6 empty] | 0 | 0 | [15 empty] | 5.3738 | 0.00251 | 0.23 | Plan & Actual | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 1608 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3238 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018512
917 | Task(Task)-->C (Construction) | EARTHING |  | 1.7.3.5 | EARTHING-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-02-09 09:00 | 2021-02-13 18:00 | 2021-04-21 09:00 | 2021-04-25 23:59 | [6 empty] | 0 | 0 | [15 empty] | 3.972 | 0.001855 | 0.17 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 770 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3239 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018513
918 | Task(Task)-->C (Construction) | LIGHTING |  | 1.7.3.5 | LIGHTING-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-01-27 09:00 | 2021-02-10 18:00 | 2021-04-19 09:00 | 2021-05-03 18:00 | [6 empty] | 0 | 0 | [15 empty] | 30.8411 | 0.014403 | 1.32 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 135 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5302 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018514
919 | Task(Task)-->C (Construction) | FIELD INTRUMENTS |  | 1.7.3.5 | FIELD INTRUMENTS-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-06-14 09:00 | 2021-06-17 18:00 | 2021-10-24 | 2021-10-27 18:00 | [6 empty] | 0 | 0 | [15 empty] | 51.1682 | 0.023896 | 2.19 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 66 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5303 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018515
920 | Task(Task)-->C (Construction) | MOTOR TERMINATION |  | 1.7.3.5 | MOTOR TERMINATION-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-06-17 09:00 | 2021-06-17 18:00 | 2022-01-02 | 2022-01-02 23:59 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5304 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018516
921 | Task(Task)-->C (Construction) | NO LOAD RUN OF MOTOR |  | 1.7.3.5 | NO LOAD RUN OF MOTOR-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->TROUGH CONVEYOR SC 3A & SC 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-08-22 | 2021-08-25 18:00 | 2022-04-14 09:00 | 2022-04-17 23:59 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5460 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018517
922 | Task(Task)-->E (Engineering) | KDTP-2 & DRIVE HOUSE-1 | 1.8 | 1 | KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-11-16 18:00 | 2021-09-06 18:00 | 2020-03-11 09:00 | 2022-04-29 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 63.2118 | 6.346 | [15 empty] | 2.0678 | 2.0678 | 203.35 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3240 | 0 | 1 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018518
923 | Task(Task)-->E (Engineering) | ENGINEERING | 1.8.1 | 1.8 | ENGINEERING-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-11-16 18:00 | 2020-07-20 17:40 | 2020-04-15 18:00 | 2020-10-12 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 75.7378 | [15 empty] | 2.5275 | 0.052263 | 5.14 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3241 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018519
924 | Task(Task)-->E (Engineering) | MECHANICAL | 1.8.1.1 | 1.8.1 | MECHANICAL-->ENGINEERING-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-11-16 18:00 | 2020-01-20 17:40 | 2020-04-15 18:00 | 2020-05-26 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 80 | [15 empty] | 16.7641 | 0.008761 | 0.86 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No | 3242 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036090
925 | Task(Task)-->E (Engineering) | G.A & LOAD DATA OF TRANSFER POINT KDTP-2 |  | 1.8.1.1 | G.A & LOAD DATA OF TRANSFER POINT KDTP-2-->MECHANICAL-->ENGINEERING-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-11-16 18:00 | 2020-01-20 17:40 | 2020-04-15 18:00 | 2020-05-26 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-0010 |  | 2020-02-13 10:26 | 7012-155-PVM-B-010 |  |  |  | A |  |  |  | 100 | 0.008761 | 0.86 | Plan & Actual | Date |  | 0 | 0 | 0 | 320 | 0 | 186.1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3243 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-11-16 18:00 | 2020-04-15 18:00 |  | 10 | 2020-04-15 23:31 |  |  | 2019-12-12 17:40 | 2020-04-17 18:00 |  | 30 | 2020-04-21 23:31 |  |  | 2019-12-18 17:40 | 2020-04-19 23:59 |  | 35 | 2020-04-23 23:31 |  |  | 2019-12-24 23:59 | 2020-04-21 18:00 |  | 65 | 2020-04-25 23:31 |  |  | 2019-12-30 17:40 | 2020-05-12 18:00 |  | 80 | 2020-05-11 23:31 | [5 empty] | 80 | 2020-07-27 18:25 | [5 empty] | 80 | 2020-07-27 18:25 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-01-20 17:40 | 2020-05-26 18:00 |  | 100 | [122 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 10 |  |  |  |  | 101024
926 | Task(Task)-->E (Engineering) | CIVIL | 1.8.1.2 | 1.8.1 | CIVIL-->ENGINEERING-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-02-01 18:00 | 2020-06-05 17:40 | 2020-04-21 18:00 | 2020-10-12 18:00 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 78.7256 | [15 empty] | 40.7407 | 0.021292 | 2.09 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No | 3249 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036091
927 | Task(Task)-->E (Engineering) | TRANSFER POINT KDTP-2 - DESIGN CALCULATION OF SUPER STRUCTURE |  | 1.8.1.2 | TRANSFER POINT KDTP-2 - DESIGN CALCULATION OF SUPER STRUCTURE-->CIVIL-->ENGINEERING-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-01 18:00 | 2020-04-01 17:40 | 2020-04-21 18:00 | 2020-09-03 18:00 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-DC-0010 |  | 2020-02-13 11:41 | 7012-155-PVC-U-028 |  |  |  | A |  |  |  | 45.6731 | 0.009725 | 0.95 | Plan & Actual | Date |  | 0 | 0 | 0 | 354.21 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3253 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-01 18:00 | 2020-04-21 18:00 |  | 10 | 2020-05-08 23:31 |  |  | 2020-02-19 17:40 | 2020-05-11 18:00 |  | 30 |  |  |  | 2020-02-26 17:40 | 2020-05-14 18:00 |  | 35 |  |  |  | 2020-03-03 23:59 | 2020-05-21 18:00 |  | 65 | 2020-08-13 19:54 |  |  | 2020-03-09 17:40 | 2020-06-11 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-01 17:40 | 2020-06-25 18:00 |  | 100 | [122 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 129 |  |  |  |  | 101143
928 | Task(Task)-->E (Engineering) | TRANSFER POINT KDTP-2 - DESIGN CALCULATION OF SUB STRUCTURE |  | 1.8.1.2 | TRANSFER POINT KDTP-2 - DESIGN CALCULATION OF SUB STRUCTURE-->CIVIL-->ENGINEERING-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-07 18:00 | 2020-05-06 17:40 | 2020-08-19 09:00 | 2020-09-01 18:00 |  |  | 2020-02-21 15:37 | 2020-09-02 00:50 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-DC-0011 |  | 2020-02-13 11:41 | 7012-155-PVC-U-029 |  |  |  | A |  |  |  | 27.4038 | 0.005835 | 0.57 | Plan & Actual | Date |  | 0 | 0 | 0 | 212.29 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3254 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-07 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-25 17:40 | 2020-06-10 18:00 |  | 30 |  |  |  | 2020-04-01 17:40 | 2020-06-13 18:00 |  | 35 |  |  |  | 2020-04-07 23:59 | 2020-06-20 18:00 |  | 65 | 2020-08-19 21:24 |  |  | 2020-04-14 17:40 | 2020-07-11 18:00 |  | 80 | 2020-09-02 00:45 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-06 17:40 | 2020-07-25 18:00 |  | 100 | 2020-09-02 00:51 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 130 |  |  |  |  | 101144
929 | Task(Task)-->E (Engineering) | TRANSFER POINT KDTP-2 - NUM & RC DETAILS OF FDN |  | 1.8.1.2 | TRANSFER POINT KDTP-2 - NUM & RC DETAILS OF FDN-->CIVIL-->ENGINEERING-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-07 18:00 | 2020-05-06 17:40 | 2020-08-19 09:00 | 2020-09-01 18:00 |  |  | 2020-02-21 15:37 | 2020-09-02 00:50 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-NR-0011 |  | 2020-02-13 11:41 | 7012-155-PVC-C-031 |  |  |  | A |  |  |  | 16.3462 | 0.00348 | 0.34 | Plan & Actual | Date |  | 0 | 0 | 0 | 127.29 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3250 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-07 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-25 17:40 | 2020-06-10 18:00 |  | 30 |  |  |  | 2020-04-01 17:40 | 2020-06-13 18:00 |  | 35 | 2020-08-19 17:48 |  |  | 2020-04-07 23:59 | 2020-06-20 18:00 |  | 65 | 2020-08-19 21:24 |  |  | 2020-04-14 17:40 | 2020-07-11 18:00 |  | 80 | 2020-09-02 00:43 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-06 17:40 | 2020-07-25 18:00 |  | 100 | 2020-09-02 00:51 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 132 |  |  |  |  | 101146
930 | Task(Task)-->E (Engineering) | TRANSFER POINT KDTP-2 - NUM & RC DETAILS OF FLOOR SLABS |  | 1.8.1.2 | TRANSFER POINT KDTP-2 - NUM & RC DETAILS OF FLOOR SLABS-->CIVIL-->ENGINEERING-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-06 18:00 | 2020-06-05 17:40 | 2020-06-25 18:00 | 2020-10-12 18:00 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-NR-0012 |  | 2020-02-13 11:41 | 7012-155-PVC-C-032 |  |  |  | A |  |  |  | 5.2885 | 0.001126 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 42.3 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3251 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-06 18:00 | 2020-06-25 18:00 |  | 10 |  |  |  | 2020-04-24 17:40 | 2020-07-15 18:00 |  | 30 |  |  |  | 2020-05-01 17:40 | 2020-07-18 18:00 |  | 35 | 2020-09-26 14:51 |  |  | 2020-05-07 23:59 | 2020-07-25 18:00 |  | 65 | 2020-09-27 11:10 |  |  | 2020-05-14 17:40 | 2020-08-15 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-05 17:40 | 2020-08-29 18:00 |  | 100 | [122 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 133 |  |  |  |  | 101147
931 | Task(Task)-->E (Engineering) | TRANSFER POINT KDTP-2 - NUM & RC DETAILS OF GRADE SLAB |  | 1.8.1.2 | TRANSFER POINT KDTP-2 - NUM & RC DETAILS OF GRADE SLAB-->CIVIL-->ENGINEERING-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-06 18:00 | 2020-06-05 17:40 | 2020-07-15 18:00 | 2020-09-18 18:00 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 35 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-NR-0013 |  | 2020-02-13 11:41 | 7012-155-PVC-C-033 |  |  |  | A |  |  |  | 5.2885 | 0.001126 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 42.3 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3252 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-06 18:00 | 2020-07-15 18:00 |  | 10 |  |  |  | 2020-04-24 17:40 | 2020-08-04 18:00 |  | 30 |  |  |  | 2020-05-01 17:40 | 2020-08-07 18:00 |  | 35 | 2020-11-11 15:14 |  |  | 2020-05-07 23:59 | 2020-08-14 18:00 |  | 65 |  |  |  | 2020-05-14 17:40 | 2020-09-04 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-05 17:40 | 2020-09-18 18:00 |  | 100 | [122 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 134 |  |  |  |  | 101148
932 | Task(Task)-->E (Engineering) | STRUCTURAL | 1.8.1.3 | 1.8.1 | STRUCTURAL-->ENGINEERING-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-01 18:00 | 2020-07-20 17:40 | 2020-04-21 18:00 | 2020-09-08 18:00 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 61.8858 | [15 empty] | 20.6628 | 0.010799 | 1.06 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No | 3255 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036092
933 | Task(Task)-->E (Engineering) | TRANSFER POINT KDTP-2 - STRUCTURAL GA |  | 1.8.1.3 | TRANSFER POINT KDTP-2 - STRUCTURAL GA-->STRUCTURAL-->ENGINEERING-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-01 18:00 | 2020-04-01 17:40 | 2020-04-21 18:00 | 2020-09-03 18:00 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-GA-0007 |  | 2020-02-13 11:41 | 7012-155-PVC-B-030 |  |  |  | A |  |  |  | 89.6226 | 0.009678 | 0.95 | Plan & Actual | Date |  | 0 | 0 | 0 | 354.21 | 0 | 195.4 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3257 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-01 18:00 | 2020-04-21 18:00 |  | 10 | 2020-05-08 23:31 |  |  | 2020-02-19 17:40 | 2020-05-11 18:00 |  | 30 |  |  |  | 2020-02-26 17:40 | 2020-05-14 18:00 |  | 35 | 2020-08-10 17:31 |  |  | 2020-03-03 23:59 | 2020-05-21 18:00 |  | 65 | 2020-08-13 19:54 |  |  | 2020-03-09 17:40 | 2020-06-11 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-01 17:40 | 2020-06-25 18:00 |  | 100 | [122 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 131 |  |  |  |  | 101145
934 | Task(Task)-->E (Engineering) | ARCHITECTURAL GA OF TRANSFER POINT KDTP-2 |  | 1.8.1.3 | ARCHITECTURAL GA OF TRANSFER POINT KDTP-2-->STRUCTURAL-->ENGINEERING-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-21 18:00 | 2020-07-20 17:40 | 2020-06-30 18:00 | 2020-09-08 18:00 |  |  | 2020-02-21 15:39 |  |  |  | 100 | 35 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-AR-0004 |  | 2020-02-13 11:43 | 7012-155-PVC-C-110 |  |  |  | I |  |  |  | 10.3774 | 0.001121 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 40.52 | 0 | 114 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3256 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-05-21 18:00 | 2020-06-30 18:00 |  | 10 |  |  |  | 2020-06-09 17:40 | 2020-07-25 18:00 |  | 30 |  |  |  | 2020-06-16 17:40 | 2020-07-28 18:00 |  | 35 | 2020-11-11 14:54 |  |  | 2020-06-21 23:59 | 2020-08-04 18:00 |  | 65 |  |  |  | 2020-06-26 17:40 | 2020-08-25 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-07-20 17:40 | 2020-09-08 18:00 |  | 100 | [122 empty] | Chetan Khodke | [5 empty] | A - Architecture | [16 empty] | 211 |  |  |  |  | 101221
935 | Task(Task)-->E (Engineering) | ELECTRICAL | 1.8.1.4 | 1.8.1 | ELECTRICAL-->ENGINEERING-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-28 18:00 | 2020-05-22 17:40 | 2020-04-20 18:00 | 2020-06-14 23:59 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 | [15 empty] | 21.8324 | 0.01141 | 1.12 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No | 3260 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036093
936 | Task(Task)-->E (Engineering) | EQUIPMENT, CABLE ROUTING, EARTHING & LIGHTNING LAYOUT WITH PLAN, SECTIONAL VIEWS & BOM OF KDTP-2 |  | 1.8.1.4 | EQUIPMENT, CABLE ROUTING, EARTHING & LIGHTNING LAYOUT WITH PLAN, SECTIONAL VIEWS & BOM OF KDTP-2-->ELECTRICAL-->ENGINEERING-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-28 18:00 | 2020-03-24 17:40 | 2020-04-20 18:00 | 2020-06-12 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5055 |  | 2020-02-13 11:44 | 7012-155-PVE-F-017 |  |  |  | A |  |  |  | 40.1786 | 0.004584 | 0.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 165.48 | 0 | 45.31 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3261 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-28 18:00 | 2020-04-20 18:00 |  | 10 | 2020-04-20 23:31 |  |  | 2020-02-12 17:40 | 2020-05-04 18:00 |  | 30 | 2020-05-30 23:31 |  |  | 2020-02-18 17:40 | 2020-05-11 18:00 |  | 35 | 2020-05-30 23:31 |  |  | 2020-02-25 23:59 | 2020-05-18 18:00 |  | 65 | 2020-07-20 12:39 |  |  | 2020-03-02 17:40 | 2020-06-08 18:00 |  | 80 | 2020-07-28 17:52 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-24 17:40 | 2020-06-08 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 252 |  |  |  |  | 101263
937 | Task(Task)-->E (Engineering) | LIGHTING LAYOUT PLAN WITH POWER DISTRIBUTION ARRANGEMENT, SECTIONAL VIEW, BOM OF KDTP-2 |  | 1.8.1.4 | LIGHTING LAYOUT PLAN WITH POWER DISTRIBUTION ARRANGEMENT, SECTIONAL VIEW, BOM OF KDTP-2-->ELECTRICAL-->ENGINEERING-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-02 18:00 | 2020-05-22 17:40 | 2020-05-03 23:59 | 2020-06-14 23:59 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5066 |  | 2020-02-13 11:44 | 7012-155-PVE-G-028 |  |  |  | A |  |  |  | 59.8214 | 0.006826 | 0.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 248.42 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3262 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-02 18:00 | 2020-05-03 23:59 |  | 10 | 2020-05-03 23:31 |  |  | 2020-04-10 17:40 | 2020-05-10 23:59 |  | 30 | 2020-05-10 23:31 |  |  | 2020-04-17 17:40 | 2020-05-17 23:59 |  | 35 | 2020-05-17 23:31 |  |  | 2020-04-23 23:59 | 2020-05-24 23:59 |  | 65 | 2020-05-14 23:31 |  |  | 2020-04-30 17:40 | 2020-06-14 23:59 |  | 80 | 2020-05-22 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-22 17:40 | 2020-06-14 23:59 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 263 |  |  |  |  | 101274
938 | Task(Task)-->P (Procurement) | PROCUREMENT | 1.8.2 | 1.8 | PROCUREMENT-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-02-06 09:00 | 2021-02-13 18:00 | 2020-03-11 09:00 | 2021-06-13 23:59 |  |  | 2020-03-11 10:57 |  |  |  | 95.1362 | 9.5639 | [15 empty] | 46.2972 | 0.95731 | 94.15 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3265 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018524
939 | Task(Task)-->P (Procurement) | PURCHASE REQUISITION | 1.8.2.1 | 1.8.2 | PURCHASE REQUISITION-->PROCUREMENT-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-02-06 09:00 | 2020-03-27 18:00 | 2020-03-11 09:00 | 2020-05-29 18:00 |  |  | 2020-03-11 10:57 |  |  |  | 100 | 29.7237 | [15 empty] | 5.0027 | 0.047891 | 4.71 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3266 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018525
940 | Task(Task)-->P (Procurement) | Flap Gate |  | 1.8.2.1 | Flap Gate-->PURCHASE REQUISITION-->PROCUREMENT-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-06 09:00 | 2020-02-06 18:00 | 2020-03-20 09:00 | 2020-03-20 18:00 |  |  | 2020-03-20 10:57 | 2020-03-20 10:57 |  |  | 100 | 100 | [15 empty] | 2.9724 | 0.001424 | 0.14 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3267 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018526
941 | Task(Task)-->P (Procurement) | Chute & Skirt |  | 1.8.2.1 | Chute & Skirt-->PURCHASE REQUISITION-->PROCUREMENT-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-10 09:00 | 2020-03-10 18:00 | 2020-03-11 09:00 | 2020-03-11 18:00 |  |  | 2020-03-11 10:57 | 2020-03-11 10:57 |  |  | 100 | 100 | [15 empty] | 18.4713 | 0.008846 | 0.87 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3268 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018527
942 | Task(Task)-->P (Procurement) | Building Structure |  | 1.8.2.1 | Building Structure-->PURCHASE REQUISITION-->PROCUREMENT-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-03 09:00 | 2020-03-03 18:00 | 2020-05-29 09:00 | 2020-05-29 18:00 | [6 empty] | 100 | 0 | [15 empty] | 70.276 | 0.033656 | 3.31 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3269 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018528
943 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.8.2.1 | LIGHT & LIGHT FIXTURES-->PURCHASE REQUISITION-->PROCUREMENT-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-10 09:00 | 2020-03-10 18:00 | 2020-03-16 09:00 | 2020-03-16 18:00 |  |  | 2020-03-16 10:57 | 2020-03-16 10:57 |  |  | 100 | 100 | [15 empty] | 5.7325 | 0.002745 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3270 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018529
944 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.8.2.1 | LIGHTING POLES-->PURCHASE REQUISITION-->PROCUREMENT-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-27 09:00 | 2020-03-27 18:00 | 2020-04-30 09:00 | 2020-04-30 18:00 |  |  | 2020-04-30 10:57 | 2020-04-30 10:57 |  |  | 100 | 100 | [15 empty] | 2.5478 | 0.00122 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3271 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018530
945 | Task(Task)-->P (Procurement) | TECHNICAL CLEARANCE | 1.8.2.2 | 1.8.2 | TECHNICAL CLEARANCE-->PROCUREMENT-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-02-07 09:00 | 2020-05-11 18:00 | 2020-03-11 09:00 | 2020-06-03 18:00 |  |  | 2020-03-17 10:57 |  |  |  | 100 | 29.7237 | [15 empty] | 5.0027 | 0.047891 | 4.71 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3274 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018531
946 | Task(Task)-->P (Procurement) | Flap Gate |  | 1.8.2.2 | Flap Gate-->TECHNICAL CLEARANCE-->PROCUREMENT-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-07 09:00 | 2020-03-22 23:59 | 2020-03-21 09:00 | 2020-04-28 18:00 |  |  | 2020-04-28 10:57 | 2020-04-28 10:57 |  |  | 100 | 100 | [15 empty] | 2.9724 | 0.001424 | 0.14 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3275 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018532
947 | Task(Task)-->P (Procurement) | Chute & Skirt |  | 1.8.2.2 | Chute & Skirt-->TECHNICAL CLEARANCE-->PROCUREMENT-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-11 09:00 | 2020-03-20 18:00 | 2020-03-11 09:00 | 2020-03-17 18:00 |  |  | 2020-03-17 10:57 | 2020-03-17 10:57 |  |  | 100 | 100 | [15 empty] | 18.4713 | 0.008846 | 0.87 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3276 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018533
948 | Task(Task)-->P (Procurement) | Building Structure |  | 1.8.2.2 | Building Structure-->TECHNICAL CLEARANCE-->PROCUREMENT-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-04 09:00 | 2020-03-10 18:00 | 2020-05-29 09:00 | 2020-05-29 18:00 | [6 empty] | 100 | 0 | [15 empty] | 70.276 | 0.033656 | 3.31 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3277 | 1 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018534
949 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.8.2.2 | LIGHT & LIGHT FIXTURES-->TECHNICAL CLEARANCE-->PROCUREMENT-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-11 09:00 | 2020-03-25 18:00 | 2020-03-16 09:00 | 2020-06-02 18:00 |  |  | 2020-06-02 10:57 | 2020-06-02 10:57 |  |  | 100 | 100 | [15 empty] | 5.7325 | 0.002745 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3278 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018535
950 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.8.2.2 | LIGHTING POLES-->TECHNICAL CLEARANCE-->PROCUREMENT-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-28 09:00 | 2020-05-11 18:00 | 2020-04-30 09:00 | 2020-06-03 18:00 |  |  | 2020-06-03 10:57 | 2020-06-03 10:57 |  |  | 100 | 100 | [15 empty] | 2.5478 | 0.00122 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3279 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018536
951 | Task(Task)-->P (Procurement) | ORDERING | 1.8.2.3 | 1.8.2 | ORDERING-->PROCUREMENT-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-03-11 09:00 | 2020-06-25 18:00 | 2020-03-17 09:00 | 2020-08-22 18:00 |  |  | 2020-03-18 12:49 |  |  |  | 100 | 29.6488 | [15 empty] | 9.9947 | 0.09568 | 9.41 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3282 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018537
952 | Task(Task)-->P (Procurement) | Flap Gate |  | 1.8.2.3 | Flap Gate-->ORDERING-->PROCUREMENT-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-23 09:00 | 2020-04-21 18:00 | 2020-04-28 09:00 | 2020-08-22 18:00 |  |  | 2020-04-28 16:12 | 2020-08-22 16:12 |  |  | 100 | 100 | [15 empty] | 3.0818 | 0.002949 | 0.29 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3283 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018538
953 | Task(Task)-->P (Procurement) | Chute & Skirt |  | 1.8.2.3 | Chute & Skirt-->ORDERING-->PROCUREMENT-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-21 09:00 | 2020-04-19 23:59 | 2020-03-17 09:00 | 2020-07-06 18:00 |  |  | 2020-03-18 12:49 | 2020-07-06 12:49 |  |  | 100 | 100 | [15 empty] | 18.3847 | 0.01759 | 1.73 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3284 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018539
954 | Task(Task)-->P (Procurement) | Building Structure |  | 1.8.2.3 | Building Structure-->ORDERING-->PROCUREMENT-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-11 09:00 | 2020-04-09 18:00 | 2020-05-29 09:00 | 2020-07-28 18:00 | [6 empty] | 100 | 0 | [15 empty] | 70.3507 | 0.067312 | 6.62 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3285 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018540
955 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.8.2.3 | LIGHT & LIGHT FIXTURES-->ORDERING-->PROCUREMENT-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-26 09:00 | 2020-04-10 18:00 | 2020-06-02 09:00 | 2020-07-31 18:00 |  |  | 2020-06-03 15:51 | 2020-06-29 15:51 |  |  | 100 | 100 | [15 empty] | 5.6323 | 0.005389 | 0.53 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3286 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018541
956 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.8.2.3 | LIGHTING POLES-->ORDERING-->PROCUREMENT-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-12 09:00 | 2020-06-25 18:00 | 2020-06-03 09:00 | 2020-06-24 18:00 |  |  | 2020-06-15 10:57 | 2020-06-15 10:57 |  |  | 100 | 100 | [15 empty] | 2.5505 | 0.00244 | 0.24 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3287 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018542
957 | Task(Task)-->P (Procurement) | ITP APPROVAL | 1.8.2.4 | 1.8.2 | ITP APPROVAL-->PROCUREMENT-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-04-10 09:00 | 2020-08-04 18:00 | 2020-06-23 09:00 | 2020-11-30 18:00 |  |  | 2020-06-23 17:39 |  |  |  | 100 | 8.2792 | [15 empty] | 5.0027 | 0.047891 | 4.71 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3290 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018543
958 | Task(Task)-->P (Procurement) | Flap Gate |  | 1.8.2.4 | Flap Gate-->ITP APPROVAL-->PROCUREMENT-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-22 09:00 | 2020-05-31 23:59 | 2020-08-22 09:00 | 2020-11-30 18:00 |  |  | 2020-08-22 16:16 |  |  |  | 100 | 0 | [15 empty] | 2.9724 | 0.001424 | 0.14 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3291 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018544
959 | Task(Task)-->P (Procurement) | Chute & Skirt |  | 1.8.2.4 | Chute & Skirt-->ITP APPROVAL-->PROCUREMENT-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-20 09:00 | 2020-05-29 18:00 | 2020-07-06 09:00 | 2020-07-16 18:00 | [6 empty] | 100 | 0 | [15 empty] | 18.4713 | 0.008846 | 0.87 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3292 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018545
960 | Task(Task)-->P (Procurement) | Building Structure |  | 1.8.2.4 | Building Structure-->ITP APPROVAL-->PROCUREMENT-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-10 09:00 | 2020-04-16 18:00 | 2020-07-28 09:00 | 2020-08-03 18:00 | [6 empty] | 100 | 0 | [15 empty] | 70.276 | 0.033656 | 3.31 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3293 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018546
961 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.8.2.4 | LIGHT & LIGHT FIXTURES-->ITP APPROVAL-->PROCUREMENT-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-11 09:00 | 2020-05-20 18:00 | 2020-07-28 09:00 | 2020-09-08 18:00 |  |  | 2020-07-08 17:23 | 2020-09-08 17:23 |  |  | 100 | 100 | [15 empty] | 5.7325 | 0.002745 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3294 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018547
962 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.8.2.4 | LIGHTING POLES-->ITP APPROVAL-->PROCUREMENT-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Completed | No | No | 2020-06-26 09:00 | 2020-08-04 18:00 | 2020-06-23 09:00 | 2020-09-08 18:00 |  |  | 2020-06-23 17:39 | 2020-09-08 17:05 |  |  | 100 | 100 | [15 empty] | 2.5478 | 0.00122 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3295 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018548
963 | Task(Task)-->P (Procurement) | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE | 1.8.2.5 | 1.8.2 | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-04-08 09:00 | 2020-09-16 18:00 | 2020-05-30 09:00 | 2020-11-16 18:00 |  |  | 2020-06-18 17:10 |  |  |  | 100 | 21.4201 | [15 empty] | 14.9973 | 0.14357 | 14.12 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3298 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018549
964 | Task(Task)-->P (Procurement) | Flap Gate |  | 1.8.2.5 | Flap Gate-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-22 09:00 | 2020-06-20 18:00 | 2020-08-22 09:00 | 2020-11-15 23:59 |  |  | 2020-08-22 16:14 |  |  |  | 100 | 15 | [15 empty] | 3.0453 | 0.004372 | 0.43 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3299 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018550
965 | Task(Task)-->P (Procurement) | Chute & Skirt |  | 1.8.2.5 | Chute & Skirt-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-20 09:00 | 2020-09-16 18:00 | 2020-07-06 09:00 | 2020-07-06 18:00 |  |  | 2020-07-06 12:51 | 2020-07-06 12:51 |  |  | 100 | 100 | [15 empty] | 18.4136 | 0.026437 | 2.6 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3300 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018551
966 | Task(Task)-->P (Procurement) | Building Structure |  | 1.8.2.5 | Building Structure-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-08 09:00 | 2020-04-14 18:00 | 2020-07-28 09:00 | 2020-08-25 18:00 | [6 empty] | 100 | 0 | [15 empty] | 70.3258 | 0.10097 | 9.93 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3301 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018552
967 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.8.2.5 | LIGHT & LIGHT FIXTURES-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-11 09:00 | 2020-05-25 18:00 | 2020-07-10 09:00 | 2020-11-16 18:00 |  |  | 2020-07-14 10:44 |  |  |  | 100 | 0 | [15 empty] | 5.6657 | 0.008134 | 0.8 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3302 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018553
968 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.8.2.5 | LIGHTING POLES-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Completed | No | No | 2020-06-26 09:00 | 2020-08-09 23:59 | 2020-05-30 09:00 | 2020-08-08 18:00 |  |  | 2020-06-18 17:10 | 2020-08-07 15:00 |  |  | 100 | 100 | [15 empty] | 2.5496 | 0.00366 | 0.36 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3303 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018554
969 | Task(Task)-->P (Procurement) | MANUFACTURING & RECEIPT AT SITE (MRN) | 1.8.2.6 | 1.8.2 | MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-17 09:00 | 2021-02-13 18:00 | 2020-07-06 09:00 | 2021-06-13 23:59 |  |  | 2020-08-07 15:00 |  |  |  | 91.8936 | 0 | [15 empty] | 60 | 0.57439 | 56.49 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3306 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018555
970 | Task(Task)-->P (Procurement) | Flap Gate |  | 1.8.2.6 | Flap Gate-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-21 | 2021-01-01 18:00 | 2020-12-01 09:00 | 2021-06-13 23:59 | [6 empty] | 73.3333 | 0 | [15 empty] | 3.0448 | 0.017489 | 1.72 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3307 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018556
971 | Task(Task)-->P (Procurement) | Chute & Skirt |  | 1.8.2.6 | Chute & Skirt-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-19 09:00 | 2021-02-13 18:00 | 2020-07-06 09:00 | 2021-01-31 23:59 | [6 empty] | 60.4167 | 0 | [15 empty] | 18.428 | 0.10585 | 10.41 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3308 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018557
972 | Task(Task)-->P (Procurement) | Building Structure |  | 1.8.2.6 | Building Structure-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-17 09:00 | 2020-10-05 18:00 | 2020-08-25 09:00 | 2021-03-31 18:00 | [6 empty] | 100 | 0 | [15 empty] | 70.3133 | 0.40387 | 39.72 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3309 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018558
973 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.8.2.6 | LIGHT & LIGHT FIXTURES-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-26 09:00 | 2020-10-21 18:00 | 2020-11-17 09:00 | 2021-04-14 18:00 | [6 empty] | 100 | 0 | [15 empty] | 5.647 | 0.032436 | 3.19 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3310 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018559
974 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.8.2.6 | LIGHTING POLES-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-10 09:00 | 2020-11-07 18:00 | 2020-09-09 09:00 | 2020-12-07 18:00 |  |  | 2020-08-07 15:00 |  |  |  | 100 | 0 | [15 empty] | 2.5668 | 0.014744 | 1.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3311 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018560
975 | Task(Task)-->C (Construction) | CONSTRUCTION | 1.8.3 | 1.8 | CONSTRUCTION-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-21 09:00 | 2021-09-06 18:00 | 2020-08-26 09:00 | 2022-04-29 18:00 | [6 empty] | 32.5136 | 0.0077 | [15 empty] | 51.1753 | 1.0582 | 104.07 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3314 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018561
976 | Task(Task)-->C (Construction) | CIVIL | 1.8.3.1 | 1.8.3 | CIVIL-->CONSTRUCTION-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-21 09:00 | 2021-05-02 23:59 | 2020-08-26 09:00 | 2021-09-07 18:00 | [6 empty] | 35.6028 | 0.01603 | [15 empty] | 48.03 | 0.50824 | 49.98 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3315 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018562
977 | Task(Task)-->C (Construction) | AVAILABILITY OF FRONT BY NTPC |  | 1.8.3.1 | AVAILABILITY OF FRONT BY NTPC-->CIVIL-->CONSTRUCTION-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-21 09:00 | 2020-04-21 18:00 | 2020-08-26 09:00 | 2020-08-26 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3316 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018563
978 | Task(Task)-->C (Construction) | EXCAVATION |  | 1.8.3.1 | EXCAVATION-->CIVIL-->CONSTRUCTION-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-28 09:00 | 2020-06-04 18:00 | 2020-09-02 09:00 | 2020-10-09 18:00 | [6 empty] | 100 | 0.26619 | [15 empty] | 6.0224 | 0.030608 | 3.01 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 11270 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3317 | 0 | 4 | Low | ADMINISTRATOR | [6 empty] | 0 | 0 | [222 empty] | Excavation | [23 empty] | 1018564
979 | Task(Task)-->C (Construction) | PCC |  | 1.8.3.1 | PCC-->CIVIL-->CONSTRUCTION-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-19 09:00 | 2020-05-28 18:00 | 2020-09-24 09:00 | 2020-10-03 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.7403 | 0.003763 | 0.37 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3318 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | PCC | [23 empty] | 1018565
980 | Task(Task)-->C (Construction) | RAFT |  | 1.8.3.1 | RAFT-->CIVIL-->CONSTRUCTION-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-29 09:00 | 2020-06-11 18:00 | 2020-10-04 | 2020-10-17 18:00 | [6 empty] | 100 | 0 | [15 empty] | 14.3257 | 0.07281 | 7.16 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 270 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3319 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018566
981 | Task(Task)-->C (Construction) | PADESTALS FOR KDTP-2 STR. |  | 1.8.3.1 | PADESTALS FOR KDTP-2 STR.-->CIVIL-->CONSTRUCTION-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-12 09:00 | 2020-07-07 18:00 | 2020-10-18 | 2020-11-12 18:00 | [6 empty] | 100 | 0 | [15 empty] | 2.6611 | 0.013525 | 1.33 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3320 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018567
982 | Task(Task)-->C (Construction) | RCC FLOOR FOR TAIL PULLEY OF PC-2A/B |  | 1.8.3.1 | RCC FLOOR FOR TAIL PULLEY OF PC-2A/B-->CIVIL-->CONSTRUCTION-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-10-04 | 2020-10-19 18:00 | 2021-02-09 09:00 | 2021-02-24 18:00 | [6 empty] | 100 | 0 | [15 empty] | 3.4414 | 0.017491 | 1.72 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3322 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | RCC | [23 empty] | 1018568
983 | Task(Task)-->C (Construction) | RCC FLOOR FOR HEAD PULLEY OF PC-1A/B |  | 1.8.3.1 | RCC FLOOR FOR HEAD PULLEY OF PC-1A/B-->CIVIL-->CONSTRUCTION-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-11-03 09:00 | 2020-11-21 18:00 | 2021-03-11 09:00 | 2021-03-29 18:00 | [6 empty] | 42.1053 | 0 | [15 empty] | 3.4414 | 0.017491 | 1.72 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3323 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | RCC | [23 empty] | 1018569
984 | Task(Task)-->C (Construction) | DRIVE HOUSE FOUNDATION |  | 1.8.3.1 | DRIVE HOUSE FOUNDATION-->CIVIL-->CONSTRUCTION-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-12 09:00 | 2020-07-12 23:59 | 2020-10-18 | 2020-11-17 18:00 | [6 empty] | 100 | 0 | [15 empty] | 2.9812 | 0.015152 | 1.49 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3324 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018570
985 | Task(Task)-->C (Construction) | HGTU FOUNDATION |  | 1.8.3.1 | HGTU FOUNDATION-->CIVIL-->CONSTRUCTION-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-26 09:00 | 2020-07-25 18:00 | 2020-11-01 | 2020-11-30 18:00 | [6 empty] | 100 | 0 | [15 empty] | 3.9816 | 0.020236 | 1.99 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5474 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018571
986 | Task(Task)-->C (Construction) | GRADE SLAB FLOOR |  | 1.8.3.1 | GRADE SLAB FLOOR-->CIVIL-->CONSTRUCTION-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-04-02 09:00 | 2021-05-02 23:59 | 2021-08-08 | 2021-09-07 18:00 | [6 empty] | 0 | 0 | [15 empty] | 62.405 | 0.31717 | 31.19 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 1666 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3325 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018572
987 | Task(Task)-->C (Construction) | STRUCTURAL WORKS | 1.8.3.2 | 1.8.3 | STRUCTURAL WORKS-->CONSTRUCTION-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-05 09:00 | 2021-04-01 18:00 | 2020-12-11 09:00 | 2021-08-07 18:00 | [6 empty] | 40.8333 | 0 | [15 empty] | 37.7475 | 0.39943 | 39.28 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3326 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018573
988 | Task(Task)-->C (Construction) | ERECTION OF STRUCTURAL STEEL |  | 1.8.3.2 | ERECTION OF STRUCTURAL STEEL-->STRUCTURAL WORKS-->CONSTRUCTION-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-05 09:00 | 2021-04-01 18:00 | 2020-12-11 09:00 | 2021-08-07 18:00 | [6 empty] | 40.8333 | 0 | [15 empty] | 100 | 0.39943 | 39.28 | Plan & Actual | Quantity | Metric Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 608 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3327 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018574
989 | Task(Task)-->C (Construction) | MECHANICAL EQUIPMENT WORKS | 1.8.3.3 | 1.8.3 | MECHANICAL EQUIPMENT WORKS-->CONSTRUCTION-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-05-03 09:00 | 2021-07-31 18:00 | 2021-09-08 09:00 | 2021-12-06 18:00 | [6 empty] | 0 | 0 | [15 empty] | 5.295 | 0.056031 | 5.51 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5461 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018575
990 | Task(Task)-->C (Construction) | ERECTION OF CHUTES/ HOODS & SUPPORTS |  | 1.8.3.3 | ERECTION OF CHUTES/ HOODS & SUPPORTS-->MECHANICAL EQUIPMENT WORKS-->CONSTRUCTION-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-05-03 09:00 | 2021-07-31 18:00 | 2021-09-08 09:00 | 2021-12-06 18:00 | [6 empty] | 0 | 0 | [15 empty] | 100 | 0.056031 | 5.51 | Plan & Actual | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3328 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018576
991 | Task(Task)-->C (Construction) | ELECTRICAL & INSTRUMENTATION (E&I) | 1.8.3.4 | 1.8.3 | ELECTRICAL & INSTRUMENTATION (E&I)-->CONSTRUCTION-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-03-28 | 2021-08-30 18:00 | 2021-08-03 09:00 | 2022-04-22 18:00 | [6 empty] | 0 | 0 | [15 empty] | 7.4476 | 0.078809 | 7.75 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5247 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018577
992 | Task(Task)-->C (Construction) | CABLE TRAY |  | 1.8.3.4 | CABLE TRAY-->ELECTRICAL & INSTRUMENTATION (E&I)-->CONSTRUCTION-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-03-28 | 2021-04-11 23:59 | 2021-08-03 09:00 | 2021-08-17 18:00 | [6 empty] | 0 | 0 | [15 empty] | 8.2474 | 0.0065 | 0.64 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3329 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018578
993 | Task(Task)-->C (Construction) | POWER CABLE |  | 1.8.3.4 | POWER CABLE-->ELECTRICAL & INSTRUMENTATION (E&I)-->CONSTRUCTION-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-07-25 | 2021-08-03 18:00 | 2021-11-30 09:00 | 2021-12-09 18:00 | [6 empty] | 0 | 0 | [15 empty] | 39.3041 | 0.030975 | 3.05 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 21520 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5248 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018579
994 | Task(Task)-->C (Construction) | CONTROL CABLE |  | 1.8.3.4 | CONTROL CABLE-->ELECTRICAL & INSTRUMENTATION (E&I)-->CONSTRUCTION-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-07-30 09:00 | 2021-08-03 18:00 | 2021-12-05 | 2021-12-09 18:00 | [6 empty] | 0 | 0 | [15 empty] | 27.0619 | 0.021327 | 2.1 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 14860 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3330 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018580
995 | Task(Task)-->C (Construction) | EARTHING |  | 1.8.3.4 | EARTHING-->ELECTRICAL & INSTRUMENTATION (E&I)-->CONSTRUCTION-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-04-05 09:00 | 2021-04-11 23:59 | 2021-08-11 09:00 | 2021-08-17 18:00 | [6 empty] | 0 | 0 | [15 empty] | 3.866 | 0.003047 | 0.3 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 1325 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5306 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018581
996 | Task(Task)-->C (Construction) | EARTH PIT |  | 1.8.3.4 | EARTH PIT-->ELECTRICAL & INSTRUMENTATION (E&I)-->CONSTRUCTION-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-04-28 09:00 | 2021-05-02 23:59 | 2021-09-03 09:00 | 2021-09-07 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5307 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018582
997 | Task(Task)-->C (Construction) | LIGHTING |  | 1.8.3.4 | LIGHTING-->ELECTRICAL & INSTRUMENTATION (E&I)-->CONSTRUCTION-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-04-02 09:00 | 2021-04-16 18:00 | 2021-08-08 | 2021-08-22 23:59 | [6 empty] | 0 | 0 | [15 empty] | 12.6289 | 0.009953 | 0.98 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5308 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018583
998 | Task(Task)-->C (Construction) | FIELD INTRUMENTS |  | 1.8.3.4 | FIELD INTRUMENTS-->ELECTRICAL & INSTRUMENTATION (E&I)-->CONSTRUCTION-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-07-31 09:00 | 2021-08-04 18:00 | 2021-12-06 09:00 | 2021-12-10 18:00 | [6 empty] | 0 | 0 | [15 empty] | 8.8918 | 0.007008 | 0.69 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5309 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018584
999 | Task(Task)-->C (Construction) | MOTOR TERMINATION |  | 1.8.3.4 | MOTOR TERMINATION-->ELECTRICAL & INSTRUMENTATION (E&I)-->CONSTRUCTION-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-08-04 09:00 | 2021-08-07 18:00 | 2022-01-02 | 2022-01-05 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5310 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018585
1000 | Task(Task)-->C (Construction) | NO LOAD RUN OF MOTOR |  | 1.8.3.4 | NO LOAD RUN OF MOTOR-->ELECTRICAL & INSTRUMENTATION (E&I)-->CONSTRUCTION-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-08-27 09:00 | 2021-08-30 18:00 | 2022-04-19 09:00 | 2022-04-22 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5462 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018586
1001 | Task(Task)-->C (Construction) | NO LOAD COMMISSIONING & SYSTEM READYNESS FOR LOAD & TRIAL OPERATION |  | 1.8.3 | NO LOAD COMMISSIONING & SYSTEM READYNESS FOR LOAD & TRIAL OPERATION-->CONSTRUCTION-->KDTP-2 & DRIVE HOUSE-1-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-08-31 09:00 | 2021-09-06 18:00 | 2022-04-23 09:00 | 2022-04-29 18:00 | [6 empty] | 0 | 0 | [15 empty] | 1.4799 | 0.01566 | 1.54 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5311 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018587
1002 | Task(Task)-->E (Engineering) | PIPE CONVEYOR PC 1A & PC 1B | 1.9 | 1 | PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-10-25 18:00 | 2021-09-13 18:00 | 2019-11-08 09:00 | 2022-05-06 18:00 |  |  | 2019-11-08 17:06 |  |  |  | 62.578 | 24.0279 | [15 empty] | 23.0338 | 23.0338 | 2265.22 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3331 | 0 | 1 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018588
1003 | Task(Task)-->E (Engineering) | ENGINEERING | 1.9.1 | 1.9 | ENGINEERING-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-10-25 18:00 | 2020-08-21 17:40 | 2020-01-13 18:00 | 2020-11-21 18:00 |  |  | 2020-02-11 17:40 |  |  |  | 100 | 83.9324 | [15 empty] | 1.7045 | 0.39261 | 38.61 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3332 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018589
1004 | Task(Task)-->E (Engineering) | MECHANICAL | 1.9.1.1 | 1.9.1 | MECHANICAL-->ENGINEERING-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-10-25 18:00 | 2020-08-10 17:40 | 2020-01-13 18:00 | 2020-11-21 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 73.9465 | [15 empty] | 20.3574 | 0.079924 | 7.86 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3333 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036094
1005 | Task(Task)-->E (Engineering) | TYP. CROSS SECTION DETAILS OF PIPE CONV. GALLERY |  | 1.9.1.1 | TYP. CROSS SECTION DETAILS OF PIPE CONV. GALLERY-->MECHANICAL-->ENGINEERING-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-10-25 18:00 | 2019-12-26 17:40 | 2020-01-13 18:00 | 2020-03-03 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-CS-GA-0006 |  | 2020-02-13 10:26 | 7012-155-PVM-B-006 |  |  |  | A |  |  |  | 5.5917 | 0.004469 | 0.43 | Plan & Actual | Date |  | 0 | 0 | 0 | 160 | 0 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3352 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-10-25 18:00 | 2020-01-13 18:00 |  | 10 | 2020-01-13 23:31 |  |  | 2019-11-18 17:40 | 2020-02-03 18:00 |  | 30 | 2020-02-03 23:31 |  |  | 2019-11-23 17:40 | 2020-02-10 18:00 |  | 35 | 2020-02-10 23:31 |  |  | 2019-11-29 23:59 | 2020-02-17 18:00 |  | 65 | 2020-02-17 23:31 |  |  | 2019-12-05 17:40 | 2020-03-03 18:00 |  | 80 | 2020-03-03 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2019-12-26 17:40 | 2020-03-03 18:00 |  | 100 | [122 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 6 |  |  |  |  | 101020
1006 | Task(Task)-->E (Engineering) | PIPE CONVEYOR PROFILES FOR PC 1A/B |  | 1.9.1.1 | PIPE CONVEYOR PROFILES FOR PC 1A/B-->MECHANICAL-->ENGINEERING-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-12 18:00 | 2020-01-22 17:40 | 2020-02-21 09:00 | 2020-04-04 18:00 |  |  | 2020-02-21 14:04 | 2020-06-19 14:55 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-CS-DC-0014 |  | 2020-02-13 10:26 | 7012-155-PVM-B-014 |  |  |  | A |  |  |  | 2.8609 | 0.002287 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 80 | 0 | 93 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3334 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-11-12 18:00 | 2020-01-08 18:00 |  | 10 | 2020-01-08 23:31 |  |  | 2019-12-14 17:40 | 2020-02-07 18:00 |  | 30 | 2020-02-07 23:31 |  |  | 2019-12-20 17:40 | 2020-02-14 18:00 |  | 35 | 2020-02-14 23:31 |  |  | 2019-12-26 23:59 | 2020-02-21 18:00 |  | 65 | 2020-02-21 23:31 |  |  | 2020-01-01 17:40 | 2020-03-19 18:00 |  | 80 | 2020-03-19 23:31 | [5 empty] | 80 | 2020-03-30 18:34 | [5 empty] | 80 | 2020-03-30 18:34 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-01-22 17:40 | 2020-04-18 18:00 |  | 100 | 2020-04-23 23:31 | [121 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 14 |  |  |  |  | 101028
1007 | Task(Task)-->E (Engineering) | POWER AND TENSION CALCULATION FOR PIPE CONVEYORS PC 1A/B |  | 1.9.1.1 | POWER AND TENSION CALCULATION FOR PIPE CONVEYORS PC 1A/B-->MECHANICAL-->ENGINEERING-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-12 18:00 | 2020-01-22 17:40 | 2020-04-28 09:00 | 2020-06-10 18:00 |  |  | 2020-02-21 14:04 | 2020-06-29 19:15 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-CS-DC-0016 |  | 2020-02-13 10:26 | 7012-155-PVM-U-016 |  |  |  | I |  |  |  | 1.4304 | 0.001143 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 40 | 0 | 18.2 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3337 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-11-12 18:00 | 2020-03-18 18:00 |  | 10 | 2020-03-18 23:31 |  |  | 2019-12-14 17:40 | 2020-04-17 18:00 |  | 30 | 2020-04-17 23:31 |  |  | 2019-12-20 17:40 | 2020-04-17 18:00 |  | 35 | 2020-04-17 23:31 |  |  | 2019-12-26 23:59 | 2020-04-24 18:00 |  | 65 | 2020-04-28 23:31 |  |  | 2020-01-01 17:40 | 2020-05-15 18:00 |  | 80 | 2020-05-16 23:31 | [5 empty] | 80 | 2020-06-10 15:15 | [5 empty] | 80 | 2020-06-10 15:15 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-01-22 17:40 | 2020-05-15 18:00 |  | 100 | 2020-06-29 19:16 | [121 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 16 |  |  |  |  | 101030
1008 | Task(Task)-->E (Engineering) | SELECTION OF BELT AND DRIVE COMPONENTS FOR PIPE CONVEYORS (PC 1A/B AND PC 2A/B) |  | 1.9.1.1 | SELECTION OF BELT AND DRIVE COMPONENTS FOR PIPE CONVEYORS (PC 1A/B AND PC 2A/B)-->MECHANICAL-->ENGINEERING-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-12-14 17:40 | 2020-01-22 17:40 | 2020-04-18 18:00 | 2020-05-22 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-CS-DC-0018 |  | 2020-02-13 10:26 | 7012-155-PVM-H-018 |  |  |  | I |  |  |  | 1.4304 | 0.001143 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 40 | 0 | 29.1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3336 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-12-14 18:00 | 2020-04-18 18:00 |  | 10 | 2020-04-18 23:31 |  |  | 2019-12-14 17:40 | 2020-04-23 18:00 |  | 30 | 2020-04-23 23:31 |  |  | 2019-12-20 17:40 | 2020-04-25 18:00 |  | 35 | 2020-04-25 23:31 |  |  | 2019-12-26 23:59 | 2020-04-28 18:00 |  | 65 | 2020-05-02 23:31 |  |  | 2020-01-01 17:40 | 2020-05-19 18:00 |  | 80 | 2020-05-22 23:31 | [5 empty] | 80 | 2020-08-28 14:53 | [5 empty] | 80 | 2020-08-28 14:53 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-01-22 17:40 | 2020-05-19 18:00 |  | 100 | [122 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 18 |  |  |  |  | 101032
1009 | Task(Task)-->E (Engineering) | G.A AND MARKING OF PIPE CONV. PC 1A/B WITH ELEVATION AND PLAN DETAILS |  | 1.9.1.1 | G.A AND MARKING OF PIPE CONV. PC 1A/B WITH ELEVATION AND PLAN DETAILS-->MECHANICAL-->ENGINEERING-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-12-19 18:00 | 2020-03-04 17:40 | 2020-04-03 18:00 | 2020-06-24 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-0024 |  | 2020-02-13 10:26 | 7012-155-PVM-B-024 |  |  |  | A |  |  |  | 14.0442 | 0.011225 | 1.08 | Plan & Actual | Date |  | 0 | 0 | 0 | 400 | 0 | 82.3 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3335 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-12-19 18:00 | 2020-04-03 18:00 |  | 10 | 2020-04-03 23:31 |  |  | 2020-01-23 17:40 | 2020-05-08 18:00 |  | 30 | 2020-05-11 23:31 |  |  | 2020-01-29 17:40 | 2020-05-13 18:00 |  | 35 | 2020-05-11 23:31 |  |  | 2020-02-04 23:59 | 2020-05-20 18:00 |  | 65 | 2020-05-28 23:31 |  |  | 2020-02-11 17:40 | 2020-06-10 18:00 |  | 80 | 2020-06-23 22:16 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-04 17:40 | 2020-06-24 18:00 |  | 100 | [122 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 24 |  |  |  |  | 101038
1010 | Task(Task)-->E (Engineering) | G.A OF GEARBOX FOR PIPE BELT CONVEYORS |  | 1.9.1.1 | G.A OF GEARBOX FOR PIPE BELT CONVEYORS-->MECHANICAL-->ENGINEERING-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-03 18:00 | 2020-08-10 17:40 | 2020-06-13 18:00 | 2020-11-15 23:59 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1003 |  | 2020-02-13 10:27 | 7012-155-PVM-B-103 |  |  |  | A |  |  |  | 2.8609 | 0.002287 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 80 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3351 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-06-03 18:00 | 2020-06-13 18:00 |  | 10 |  |  |  | 2020-06-29 17:40 | 2020-07-03 18:00 |  | 30 |  |  |  | 2020-07-04 17:40 | 2020-07-10 18:00 |  | 35 |  |  |  | 2020-07-10 23:59 | 2020-07-20 18:00 |  | 65 | 2020-09-15 15:30 |  |  | 2020-07-17 17:40 | 2020-08-10 18:00 |  | 80 | 2020-10-07 10:33 | [5 empty] | 80 | 2020-10-07 18:01 | [5 empty] | 80 | 2020-10-07 18:01 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-08-10 17:40 | 2020-08-10 18:00 |  | 100 | [122 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 33 |  |  |  |  | 101047
1011 | Task(Task)-->E (Engineering) | GA & DIMENSION SHEET FOR TROUGHING IDLERS FOR PIPE CONVEYOR IDLER |  | 1.9.1.1 | GA & DIMENSION SHEET FOR TROUGHING IDLERS FOR PIPE CONVEYOR IDLER-->MECHANICAL-->ENGINEERING-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-20 18:00 | 2020-04-16 17:40 | 2020-05-30 18:00 | 2020-10-16 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1009 |  | 2020-02-13 10:27 | 7012-155-PVM-B-109 |  |  |  | I |  |  |  | 9.7529 | 0.007795 | 0.75 | Plan & Actual | Date |  | 0 | 0 | 0 | 280 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3338 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-20 18:00 | 2020-05-30 18:00 |  | 10 |  |  |  | 2020-03-05 17:40 | 2020-06-20 18:00 |  | 30 |  |  |  | 2020-03-11 17:40 | 2020-06-26 18:00 |  | 35 |  |  |  | 2020-03-18 23:59 | 2020-06-26 18:00 |  | 65 | 2020-10-30 14:32 |  |  | 2020-03-24 17:40 | 2020-07-17 18:00 |  | 80 | 2020-10-30 15:25 | [5 empty] | 80 | 2020-11-06 09:33 | [5 empty] | 80 | 2020-11-06 09:33 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-16 17:40 | 2020-07-17 18:00 |  | 100 | [122 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 39 |  |  |  |  | 101053
1012 | Task(Task)-->E (Engineering) | GA & DIMENSION SHEET FOR IMPACT IDLER FOR PIPE CONVEYORS |  | 1.9.1.1 | GA & DIMENSION SHEET FOR IMPACT IDLER FOR PIPE CONVEYORS-->MECHANICAL-->ENGINEERING-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-20 18:00 | 2020-04-16 17:40 | 2020-05-30 18:00 | 2020-10-16 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1011 |  | 2020-02-13 10:27 | 7012-155-PVM-B-111 |  |  |  | I |  |  |  | 2.8609 | 0.002287 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 80 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3339 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-20 18:00 | 2020-05-30 18:00 |  | 10 |  |  |  | 2020-03-05 17:40 | 2020-06-20 18:00 |  | 30 |  |  |  | 2020-03-11 17:40 | 2020-06-26 18:00 |  | 35 |  |  |  | 2020-03-18 23:59 | 2020-06-26 18:00 |  | 65 | 2020-10-30 14:32 |  |  | 2020-03-24 17:40 | 2020-07-17 18:00 |  | 80 | 2020-10-30 15:26 | [5 empty] | 80 | 2020-11-06 09:31 | [5 empty] | 80 | 2020-11-06 09:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-16 17:40 | 2020-07-17 18:00 |  | 100 | [122 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 41 |  |  |  |  | 101055
1013 | Task(Task)-->E (Engineering) | GA & DIMENSION SHEET FOR 2 ROLL FLAT RETURN IDLERS FOR PIPE CONVEYORS |  | 1.9.1.1 | GA & DIMENSION SHEET FOR 2 ROLL FLAT RETURN IDLERS FOR PIPE CONVEYORS-->MECHANICAL-->ENGINEERING-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-20 18:00 | 2020-04-16 17:40 | 2020-05-30 18:00 | 2020-10-16 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1015 |  | 2020-02-13 10:27 | 7012-155-PVM-B-115 |  |  |  | I |  |  |  | 2.8609 | 0.002287 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 80 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3340 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-20 18:00 | 2020-05-30 18:00 |  | 10 |  |  |  | 2020-03-05 17:40 | 2020-06-20 18:00 |  | 30 |  |  |  | 2020-03-11 17:40 | 2020-06-26 18:00 |  | 35 | 2020-05-31 23:31 |  |  | 2020-03-18 23:59 | 2020-06-26 18:00 |  | 65 | 2020-10-30 14:32 |  |  | 2020-03-24 17:40 | 2020-07-17 18:00 |  | 80 | 2020-10-30 15:26 | [5 empty] | 80 | 2020-11-06 09:30 | [5 empty] | 80 | 2020-11-06 09:30 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-16 17:40 | 2020-07-17 18:00 |  | 100 | [122 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 45 |  |  |  |  | 101059
1014 | Task(Task)-->E (Engineering) | GA & DIMENSION SHEET FOR S.A CARRAYING AND S.A RETURN IDLER FOR PIPE CONVEYORS |  | 1.9.1.1 | GA & DIMENSION SHEET FOR S.A CARRAYING AND S.A RETURN IDLER FOR PIPE CONVEYORS-->MECHANICAL-->ENGINEERING-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-20 18:00 | 2020-04-16 17:40 | 2020-05-30 18:00 | 2020-08-21 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1017 |  | 2020-02-13 10:27 | 7012-155-PVM-B-117 |  |  |  | I |  |  |  | 2.8609 | 0.002287 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 80 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3341 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-20 18:00 | 2020-05-30 18:00 |  | 10 |  |  |  | 2020-03-05 17:40 | 2020-06-20 18:00 |  | 30 |  |  |  | 2020-03-11 17:40 | 2020-06-26 18:00 |  | 35 |  |  |  | 2020-03-18 23:59 | 2020-06-26 18:00 |  | 65 |  |  |  | 2020-03-24 17:40 | 2020-07-17 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-16 17:40 | 2020-07-17 18:00 |  | 100 | [122 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 47 |  |  |  |  | 101061
1015 | Task(Task)-->E (Engineering) | GA & DIMENSION SHEET FOR TROUGHING TRANSITION IDLER FOR PIPE CONVEYORS |  | 1.9.1.1 | GA & DIMENSION SHEET FOR TROUGHING TRANSITION IDLER FOR PIPE CONVEYORS-->MECHANICAL-->ENGINEERING-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-20 18:00 | 2020-04-16 17:40 | 2020-05-30 18:00 | 2020-11-21 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1019 |  | 2020-02-13 10:27 | 7012-155-PVM-B-119 |  |  |  | I |  |  |  | 2.8609 | 0.002287 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 80 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3342 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-20 18:00 | 2020-05-30 18:00 |  | 10 |  |  |  | 2020-03-05 17:40 | 2020-06-20 18:00 |  | 30 |  |  |  | 2020-03-11 17:40 | 2020-06-26 18:00 |  | 35 |  |  |  | 2020-03-18 23:59 | 2020-06-26 18:00 |  | 65 | 2020-10-30 14:32 |  |  | 2020-03-24 17:40 | 2020-07-17 18:00 |  | 80 | 2020-11-04 09:52 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-16 17:40 | 2020-07-17 18:00 |  | 100 | [122 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 49 |  |  |  |  | 101063
1016 | Task(Task)-->E (Engineering) | GA & DIMENSION SHEET FOR PSK IDLERS FOR PIPE CONVEYOR |  | 1.9.1.1 | GA & DIMENSION SHEET FOR PSK IDLERS FOR PIPE CONVEYOR-->MECHANICAL-->ENGINEERING-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-20 18:00 | 2020-04-16 17:40 | 2020-06-15 18:00 | 2020-08-02 23:59 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1020A |  | 2020-02-13 10:27 | 7012-155-PVM-B-120 |  |  |  | I |  |  |  | 2.8609 | 0.002287 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 80 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3343 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-20 18:00 | 2020-06-15 18:00 |  | 10 |  |  |  | 2020-03-05 17:40 | 2020-07-06 18:00 |  | 30 |  |  |  | 2020-03-11 17:40 | 2020-07-12 23:59 |  | 35 |  |  |  | 2020-03-18 23:59 | 2020-07-12 23:59 |  | 65 | 2020-10-30 14:32 |  |  | 2020-03-24 17:40 | 2020-08-02 23:59 |  | 80 | 2020-10-30 15:25 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-16 17:40 | 2020-08-02 23:59 |  | 100 | [122 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 50 |  |  |  |  | 101064
1017 | Task(Task)-->E (Engineering) | BELT DATA SHEET WITH SCHEDULE FOR PIPE CONVEYORS |  | 1.9.1.1 | BELT DATA SHEET WITH SCHEDULE FOR PIPE CONVEYORS-->MECHANICAL-->ENGINEERING-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-13 18:00 | 2020-06-23 17:40 | 2020-06-15 18:00 | 2020-10-14 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-DC-1025 |  | 2020-02-13 10:27 | 7012-155-PVM-Y-125 |  |  |  | I |  |  |  | 1.4304 | 0.001143 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 40 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3350 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-13 18:00 | 2020-06-15 18:00 |  | 10 |  |  |  | 2020-05-13 17:40 | 2020-07-06 18:00 |  | 30 |  |  |  | 2020-05-19 17:40 | 2020-07-13 18:00 |  | 35 |  |  |  | 2020-05-26 23:59 | 2020-07-28 18:00 |  | 65 | 2020-09-22 11:28 |  |  | 2020-06-01 17:40 | 2020-08-18 18:00 |  | 80 | 2020-10-14 15:23 | [5 empty] | 80 | 2020-10-16 19:16 | [5 empty] | 80 | 2020-10-16 19:16 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-23 17:40 | 2020-08-18 18:00 |  | 100 | [122 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 55 |  |  |  |  | 101069
1018 | Task(Task)-->E (Engineering) | SCHEDULE OF DRIVE AND NON DRIVE PULLEY FOR PIPE CONVEYORS |  | 1.9.1.1 | SCHEDULE OF DRIVE AND NON DRIVE PULLEY FOR PIPE CONVEYORS-->MECHANICAL-->ENGINEERING-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-11 18:00 | 2020-05-07 17:40 | 2020-06-15 18:00 | 2020-08-03 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1027 |  | 2020-02-13 10:27 | 7012-155-PVM-H-127 |  |  |  | A |  |  |  | 5.5917 | 0.004469 | 0.43 | Plan & Actual | Date |  | 0 | 0 | 0 | 160 | 0 | 51 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3349 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-11 18:00 | 2020-06-15 18:00 |  | 10 |  |  |  | 2020-03-26 17:40 | 2020-07-06 18:00 |  | 30 |  |  |  | 2020-04-02 17:40 | 2020-07-13 18:00 |  | 35 |  |  |  | 2020-04-08 23:59 | 2020-07-13 18:00 |  | 65 | 2020-07-14 12:43 |  |  | 2020-04-15 17:40 | 2020-08-03 18:00 |  | 80 | 2020-08-19 18:20 | [5 empty] | 80 | 2020-08-19 18:33 | [5 empty] | 80 | 2020-08-19 18:33 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-07 17:40 | 2020-08-03 18:00 |  | 100 | [122 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 57 |  |  |  |  | 101071
1019 | Task(Task)-->E (Engineering) | G.A OF BRAKES FOR PIPE CONVEYORS |  | 1.9.1.1 | G.A OF BRAKES FOR PIPE CONVEYORS-->MECHANICAL-->ENGINEERING-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-21 18:00 | 2020-06-18 17:40 | 2020-06-30 18:00 | 2020-09-29 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1029 |  | 2020-02-13 10:27 | 7012-155-PVM-B-129 |  |  |  | I |  |  |  | 5.5917 | 0.004469 | 0.43 | Plan & Actual | Date |  | 0 | 0 | 0 | 160 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3344 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-21 18:00 | 2020-06-30 18:00 |  | 10 |  |  |  | 2020-05-07 17:40 | 2020-07-21 18:00 |  | 30 |  |  |  | 2020-05-14 17:40 | 2020-07-24 18:00 |  | 35 |  |  |  | 2020-05-20 23:59 | 2020-07-29 18:00 |  | 65 | 2020-09-09 10:01 |  |  | 2020-05-27 17:40 | 2020-08-19 18:00 |  | 80 | 2020-10-03 16:27 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-18 17:40 | 2020-08-19 18:00 |  | 100 | [122 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 59 |  |  |  |  | 101073
1020 | Task(Task)-->E (Engineering) | G.A OF MAINTENANCE TROLLEY |  | 1.9.1.1 | G.A OF MAINTENANCE TROLLEY-->MECHANICAL-->ENGINEERING-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-12-28 18:00 | 2020-02-19 17:40 | 2020-05-20 18:00 | 2020-08-12 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1038 |  | 2020-02-13 10:27 | 7012-155-PVM-B-138 |  |  |  | I |  |  |  | 2.8609 | 0.002287 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 80 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3353 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-12-28 18:00 | 2020-05-20 18:00 |  | 10 |  |  |  | 2020-01-10 17:40 | 2020-06-04 18:00 |  | 30 |  |  |  | 2020-01-16 17:40 | 2020-06-07 23:59 |  | 35 |  |  |  | 2020-01-22 23:59 | 2020-06-14 23:59 |  | 65 | 2020-08-28 17:34 |  |  | 2020-01-28 17:40 | 2020-07-05 23:59 |  | 80 | 2020-08-28 17:42 | [5 empty] | 80 | 2020-08-28 17:45 | [5 empty] | 80 | 2020-08-28 17:45 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-02-19 17:40 | 2020-07-05 23:59 |  | 100 | [122 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 68 |  |  |  |  | 101082
1021 | Task(Task)-->E (Engineering) | G.A OF GEAR COUPLING FOR PIPE CONVEYORS |  | 1.9.1.1 | G.A OF GEAR COUPLING FOR PIPE CONVEYORS-->MECHANICAL-->ENGINEERING-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-20 18:00 | 2020-06-06 17:40 | 2020-06-15 18:00 | 2020-09-01 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1044 |  | 2020-02-13 10:27 | 7012-155-PVM-B-144 |  |  |  | I |  |  |  | 1.4304 | 0.001143 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 40 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3347 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-20 18:00 | 2020-06-15 18:00 |  | 10 |  |  |  | 2020-04-27 17:40 | 2020-06-30 18:00 |  | 30 |  |  |  | 2020-05-02 17:40 | 2020-07-03 18:00 |  | 35 |  |  |  | 2020-05-08 23:59 | 2020-07-03 18:00 |  | 65 | 2020-08-14 23:27 |  |  | 2020-05-15 17:40 | 2020-07-24 18:00 |  | 80 | 2020-09-02 16:10 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-06 17:40 | 2020-07-24 18:00 |  | 100 | [122 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 74 |  |  |  |  | 101088
1022 | Task(Task)-->E (Engineering) | GA & DIMENSION SHEET FOR SPECIAL IDLERS FOR PIPE CONVEYOR |  | 1.9.1.1 | GA & DIMENSION SHEET FOR SPECIAL IDLERS FOR PIPE CONVEYOR-->MECHANICAL-->ENGINEERING-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-23 23:59 | 2020-04-16 17:40 | 2020-04-07 18:00 | 2020-11-15 23:59 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1045 |  | 2020-02-13 10:27 | 7012-155-PVM-B-145 |  |  |  | I |  |  |  | 30.8192 | 0.024632 | 2.37 | Plan & Actual | Date |  | 0 | 0 | 0 | 880 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3348 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-23 23:59 | 2020-04-07 18:00 |  | 10 | 2020-04-07 23:31 |  |  | 2020-03-05 17:40 | 2020-04-28 18:00 |  | 30 | 2020-04-28 23:31 |  |  | 2020-03-11 17:40 | 2020-04-28 18:00 |  | 35 | 2020-04-28 23:31 |  |  | 2020-03-18 23:59 | 2020-04-28 18:00 |  | 65 | 2020-10-30 14:32 |  |  | 2020-03-24 17:40 | 2020-05-19 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-16 17:40 | 2020-05-19 18:00 |  | 100 | [122 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 75 |  |  |  |  | 101089
1023 | Task(Task)-->E (Engineering) | CIVIL | 1.9.1.2 | 1.9.1 | CIVIL-->ENGINEERING-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-03 18:00 | 2020-07-07 17:40 | 2020-05-31 | 2020-10-02 18:00 |  |  | 2020-02-21 15:37 | 2020-10-03 12:27 |  |  | 100 | 100 | [15 empty] | 14.1155 | 0.055418 | 5.45 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3356 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036095
1024 | Task(Task)-->E (Engineering) | PIPE CONVEYOR FOR PC 1A/B : NUM & RC DETAILS OF FDN (SHT 1) |  | 1.9.1.2 | PIPE CONVEYOR FOR PC 1A/B : NUM & RC DETAILS OF FDN (SHT 1)-->CIVIL-->ENGINEERING-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-27 17:40 | 2020-07-07 17:40 | 2020-05-31 | 2020-06-04 18:00 |  |  | 2020-05-27 17:40 | 2020-06-04 14:46 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-NR-0017 |  | 2020-02-13 11:42 | 7012-155-PVC-C-047 |  |  |  | A |  |  |  | 17.4552 | 0.009673 | 2.73 | Plan & Actual | Date |  | 0 | 0 | 0 | 1012.26 | 0 | 54 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3357 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-05-08 18:00 | 2020-04-21 18:00 |  | 10 | 2020-04-21 23:31 |  |  | 2020-05-27 17:40 | 2020-05-26 18:00 |  | 30 | 2020-05-24 23:31 |  |  | 2020-06-02 17:40 | 2020-05-29 18:00 |  | 35 | 2020-05-26 23:31 |  |  | 2020-06-08 23:59 | 2020-06-05 18:00 |  | 65 | 2020-05-31 23:31 |  |  | 2020-06-15 17:40 | 2020-06-26 18:00 |  | 80 | 2020-06-04 14:41 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-07-07 17:40 | 2020-07-10 18:00 |  | 100 | 2020-06-04 14:47 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 148 |  |  |  |  | 101162
1025 | Task(Task)-->E (Engineering) | PIPE CONVEYOR FOR PC 1A/B : NUM & RC DETAILS OF FDN (SHT 2) |  | 1.9.1.2 | PIPE CONVEYOR FOR PC 1A/B : NUM & RC DETAILS OF FDN (SHT 2)-->CIVIL-->ENGINEERING-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-08 18:00 | 2020-07-07 17:40 | 2020-07-24 09:00 | 2020-08-04 18:00 |  |  | 2020-02-21 15:37 | 2020-08-04 20:40 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-NR-0018 |  | 2020-02-13 11:42 | 7012-155-PVC-C-048 |  |  |  | A |  |  |  | 17.4552 | 0.009673 | 2.73 | Plan & Actual | Date |  | 0 | 0 | 0 | 1012.26 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3358 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-05-08 18:00 | 2020-06-19 18:00 |  | 10 |  |  |  | 2020-05-27 17:40 | 2020-07-24 18:00 |  | 30 |  |  |  | 2020-06-02 17:40 | 2020-07-27 18:00 |  | 35 |  |  |  | 2020-06-08 23:59 | 2020-08-03 18:00 |  | 65 | 2020-08-04 20:26 |  |  | 2020-06-15 17:40 | 2020-08-24 18:00 |  | 80 | 2020-08-04 20:37 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-07-07 17:40 | 2020-09-07 18:00 |  | 100 | 2020-08-04 20:40 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 149 |  |  |  |  | 101163
1026 | Task(Task)-->E (Engineering) | PIPE CONVEYOR FOR PC 1A/B : DESIGN CALCULATION OF SUPER STRUCTURE |  | 1.9.1.2 | PIPE CONVEYOR FOR PC 1A/B : DESIGN CALCULATION OF SUPER STRUCTURE-->CIVIL-->ENGINEERING-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-03 18:00 | 2020-06-02 17:40 | 2020-09-03 09:00 | 2020-10-02 18:00 |  |  | 2020-02-21 15:37 | 2020-10-03 12:27 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0014A |  | 2020-02-13 11:41 | 7012-155-PVC-U-040 |  |  |  | A |  |  |  | 30.243 | 0.01676 | 4.73 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3359 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-03 18:00 | 2020-05-20 18:00 |  | 10 |  |  |  | 2020-04-21 17:40 | 2020-06-24 18:00 |  | 30 |  |  |  | 2020-04-28 17:40 | 2020-06-27 18:00 |  | 35 |  |  |  | 2020-05-04 23:59 | 2020-07-04 18:00 |  | 65 | 2020-09-06 17:32 |  |  | 2020-05-11 17:40 | 2020-07-25 18:00 |  | 80 | 2020-10-03 12:25 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-02 17:40 | 2020-08-08 18:00 |  | 100 | 2020-10-03 12:27 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 141 |  |  |  |  | 101155
1027 | Task(Task)-->E (Engineering) | PIPE CONVEYOR FOR PC 1A/B : DESIGN CALCULATION OF SUB STRUCTURE |  | 1.9.1.2 | PIPE CONVEYOR FOR PC 1A/B : DESIGN CALCULATION OF SUB STRUCTURE-->CIVIL-->ENGINEERING-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-27 17:40 | 2020-07-07 17:40 | 2020-05-31 | 2020-06-04 18:00 |  |  | 2020-05-27 17:40 | 2020-06-04 14:47 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0015A |  | 2020-02-13 11:41 | 7012-155-PVC-U-041 |  |  |  | A |  |  |  | 34.8465 | 0.019311 | 5.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 63 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3360 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-05-08 18:00 | 2020-04-21 18:00 |  | 10 | 2020-05-15 23:31 |  |  | 2020-05-27 17:40 | 2020-05-26 18:00 |  | 30 | 2020-05-24 23:31 |  |  | 2020-06-02 17:40 | 2020-05-29 18:00 |  | 35 | 2020-05-26 23:31 |  |  | 2020-06-08 23:59 | 2020-06-05 18:00 |  | 65 | 2020-05-31 23:31 |  |  | 2020-06-15 17:40 | 2020-06-26 18:00 |  | 80 | 2020-06-04 14:42 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-07-07 17:40 | 2020-07-10 18:00 |  | 100 | 2020-06-04 14:48 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 142 |  |  |  |  | 101156
1028 | Task(Task)-->E (Engineering) | STRUCTURAL | 1.9.1.3 | 1.9.1 | STRUCTURAL-->ENGINEERING-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-02-11 17:40 | 2020-08-21 17:40 | 2020-04-13 09:00 | 2020-10-09 18:00 |  |  | 2020-02-11 17:40 |  |  |  | 100 | 85.8078 | [15 empty] | 60.0363 | 0.23571 | 23.18 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3361 | 3 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036096
1029 | Task(Task)-->E (Engineering) | GA. OF STANDARD GALLERY FOR PIPE CONV. |  | 1.9.1.3 | GA. OF STANDARD GALLERY FOR PIPE CONV.-->STRUCTURAL-->ENGINEERING-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-11 17:40 | 2020-03-21 17:40 | 2020-04-13 09:00 | 2020-07-28 18:00 |  |  | 2020-07-28 09:11 | 2020-07-28 09:11 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-GA-0002 |  | 2020-02-13 11:41 | 7012-155-PVC-B-005 |  |  |  | A |  |  |  | 31.6379 | 0.074573 | 7.34 | Plan & Actual | Date |  | 0 | 0 | 0 | 2724 | 0 | 393 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3365 | 1 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-22 18:00 | 2020-03-15 23:59 |  | 10 | 2020-02-18 23:31 |  |  | 2020-02-11 17:40 | 2020-04-05 23:59 |  | 30 | 2020-04-03 23:31 |  |  | 2020-02-17 17:40 | 2020-04-08 18:00 |  | 35 | 2020-04-06 23:31 |  |  | 2020-02-22 23:59 | 2020-04-15 18:00 |  | 65 | 2020-04-13 23:31 |  |  | 2020-02-28 17:40 | 2020-05-04 18:00 |  | 80 | 2020-05-11 23:31 | [5 empty] | 80 | 2020-07-28 09:12 | [5 empty] | 80 | 2020-07-28 09:12 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-21 17:40 | 2020-05-18 18:00 |  | 100 | 2020-05-11 23:31 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 106 |  |  |  |  | 101120
1030 | Task(Task)-->E (Engineering) | GA. OF STANDARD TRESTLES SUPPORTING PIPE CONV.GALLERIES |  | 1.9.1.3 | GA. OF STANDARD TRESTLES SUPPORTING PIPE CONV.GALLERIES-->STRUCTURAL-->ENGINEERING-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-07 17:40 | 2020-04-18 17:40 | 2020-04-13 09:00 | 2020-07-28 18:00 |  |  | 2020-03-07 17:40 | 2020-05-16 16:34 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-GA-0003 |  | 2020-02-13 11:41 | 7012-155-PVC-B-006 |  |  |  | A |  |  |  | 7.8879 | 0.018592 | 1.83 | Plan & Actual | Date |  | 0 | 0 | 0 | 681 | 0 | 121 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3366 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-18 18:00 | 2020-03-15 23:59 |  | 10 | 2020-02-23 23:31 |  |  | 2020-03-07 17:40 | 2020-04-05 23:59 |  | 30 | 2020-04-03 23:31 |  |  | 2020-03-13 17:40 | 2020-04-08 18:00 |  | 35 | 2020-04-06 23:31 |  |  | 2020-03-20 23:59 | 2020-04-15 18:00 |  | 65 | 2020-04-13 23:31 |  |  | 2020-03-26 17:40 | 2020-05-04 18:00 |  | 80 | 2020-05-11 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-18 17:40 | 2020-05-18 18:00 |  | 100 | 2020-05-11 23:31 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 107 |  |  |  |  | 101121
1031 | Task(Task)-->E (Engineering) | DESIGN CALCULATION FOR STANDARD PIPE CONV.GALLERIES |  | 1.9.1.3 | DESIGN CALCULATION FOR STANDARD PIPE CONV.GALLERIES-->STRUCTURAL-->ENGINEERING-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-11 17:40 | 2020-03-21 17:40 | 2020-04-13 09:00 | 2020-07-21 18:00 |  |  | 2020-02-11 17:40 | 2020-05-16 17:27 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0001 |  | 2020-02-13 11:41 | 7012-155-PVC-U-007 |  |  |  | A |  |  |  | 31.6379 | 0.074573 | 7.34 | Plan & Actual | Date |  | 0 | 0 | 0 | 2724 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3362 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-22 18:00 | 2020-03-15 23:59 |  | 10 | 2020-02-18 23:31 |  |  | 2020-02-11 17:40 | 2020-04-05 23:59 |  | 30 | 2020-04-03 23:31 |  |  | 2020-02-17 17:40 | 2020-04-08 18:00 |  | 35 | 2020-04-06 23:31 |  |  | 2020-02-22 23:59 | 2020-04-15 18:00 |  | 65 | 2020-04-13 23:31 |  |  | 2020-02-28 17:40 | 2020-05-04 18:00 |  | 80 | 2020-05-11 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-21 17:40 | 2020-05-18 18:00 |  | 100 | 2020-05-11 23:31 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 108 |  |  |  |  | 101122
1032 | Task(Task)-->E (Engineering) | DESIGN CALCULATION FOR STANDARD PIPE CONV.GALLERIES SUPPORTING TRESTLES |  | 1.9.1.3 | DESIGN CALCULATION FOR STANDARD PIPE CONV.GALLERIES SUPPORTING TRESTLES-->STRUCTURAL-->ENGINEERING-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-18 18:00 | 2020-04-18 17:40 | 2020-04-13 09:00 | 2020-07-28 18:00 |  |  | 2020-02-21 15:30 | 2020-07-28 09:59 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0002 |  | 2020-02-13 11:41 | 7012-155-PVC-U-008 |  |  |  | A |  |  |  | 7.8879 | 0.018592 | 1.83 | Plan & Actual | Date |  | 0 | 0 | 0 | 681 | 0 | 59 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3363 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-18 18:00 | 2020-03-15 23:59 |  | 10 | 2020-02-23 23:31 |  |  | 2020-03-07 17:40 | 2020-04-05 23:59 |  | 30 | 2020-04-03 23:31 |  |  | 2020-03-13 17:40 | 2020-04-08 18:00 |  | 35 | 2020-04-06 23:31 |  |  | 2020-03-20 23:59 | 2020-04-15 18:00 |  | 65 | 2020-04-13 23:31 |  |  | 2020-03-26 17:40 | 2020-05-04 18:00 |  | 80 | 2020-05-25 23:31 | [5 empty] | 80 | 2020-07-28 09:20 | [5 empty] | 80 | 2020-07-28 09:20 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-18 17:40 | 2020-05-18 18:00 |  | 100 | 2020-07-28 10:00 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 109 |  |  |  |  | 101123
1033 | Task(Task)-->E (Engineering) | PIPE CONVEYOR FOR PC 1A/B : STRUCTURAL GA (SHT 1) |  | 1.9.1.3 | PIPE CONVEYOR FOR PC 1A/B : STRUCTURAL GA (SHT 1)-->STRUCTURAL-->ENGINEERING-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-03 18:00 | 2020-06-02 17:40 | 2020-05-20 18:00 | 2020-10-09 18:00 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-GA-0009 |  | 2020-02-13 11:42 | 7012-155-PVC-B-042 |  |  |  | A |  |  |  | 4.0948 | 0.009652 | 0.95 | Plan & Actual | Date |  | 0 | 0 | 0 | 351.15 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3367 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-03 18:00 | 2020-05-20 18:00 |  | 10 |  |  |  | 2020-04-21 17:40 | 2020-06-24 18:00 |  | 30 |  |  |  | 2020-04-28 17:40 | 2020-06-27 18:00 |  | 35 |  |  |  | 2020-05-04 23:59 | 2020-07-04 18:00 |  | 65 | 2020-09-25 22:40 |  |  | 2020-05-11 17:40 | 2020-07-25 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-02 17:40 | 2020-08-08 18:00 |  | 100 | [122 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 143 |  |  |  |  | 101157
1034 | Task(Task)-->E (Engineering) | PIPE CONVEYOR FOR PC 1A/B : STRUCTURAL GA (SHT 2) |  | 1.9.1.3 | PIPE CONVEYOR FOR PC 1A/B : STRUCTURAL GA (SHT 2)-->STRUCTURAL-->ENGINEERING-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-03 18:00 | 2020-06-02 17:40 | 2020-05-20 18:00 | 2020-08-21 18:00 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-GA-0010 |  | 2020-02-13 11:42 | 7012-155-PVC-B-043 |  |  |  | A |  |  |  | 4.0948 | 0.009652 | 0.95 | Plan & Actual | Date |  | 0 | 0 | 0 | 351.15 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3368 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-03 18:00 | 2020-05-20 18:00 |  | 10 |  |  |  | 2020-04-21 17:40 | 2020-06-24 18:00 |  | 30 |  |  |  | 2020-04-28 17:40 | 2020-06-27 18:00 |  | 35 |  |  |  | 2020-05-04 23:59 | 2020-07-04 18:00 |  | 65 |  |  |  | 2020-05-11 17:40 | 2020-07-25 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-02 17:40 | 2020-08-08 18:00 |  | 100 | [122 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 144 |  |  |  |  | 101158
1035 | Task(Task)-->E (Engineering) | PIPE CONVEYOR FOR PC 1A/B : STRUCTURAL GA (SHT 3) |  | 1.9.1.3 | PIPE CONVEYOR FOR PC 1A/B : STRUCTURAL GA (SHT 3)-->STRUCTURAL-->ENGINEERING-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-03 18:00 | 2020-06-02 17:40 | 2020-05-20 18:00 | 2020-08-21 18:00 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-GA-0011 |  | 2020-02-13 11:42 | 7012-155-PVC-B-044 |  |  |  | A |  |  |  | 4.0948 | 0.009652 | 0.95 | Plan & Actual | Date |  | 0 | 0 | 0 | 351.15 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3369 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-03 18:00 | 2020-05-20 18:00 |  | 10 |  |  |  | 2020-04-21 17:40 | 2020-06-24 18:00 |  | 30 |  |  |  | 2020-04-28 17:40 | 2020-06-27 18:00 |  | 35 |  |  |  | 2020-05-04 23:59 | 2020-07-04 18:00 |  | 65 |  |  |  | 2020-05-11 17:40 | 2020-07-25 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-02 17:40 | 2020-08-08 18:00 |  | 100 | [122 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 145 |  |  |  |  | 101159
1036 | Task(Task)-->E (Engineering) | PIPE CONVEYOR FOR PC 1A/B : STRUCTURAL GA (SHT 4) |  | 1.9.1.3 | PIPE CONVEYOR FOR PC 1A/B : STRUCTURAL GA (SHT 4)-->STRUCTURAL-->ENGINEERING-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-03 18:00 | 2020-06-02 17:40 | 2020-05-20 18:00 | 2020-08-21 18:00 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-GA-0012 |  | 2020-02-13 11:42 | 7012-155-PVC-B-045 |  |  |  | A |  |  |  | 4.0948 | 0.009652 | 0.95 | Plan & Actual | Date |  | 0 | 0 | 0 | 351.15 | 0 | 122 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3370 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-03 18:00 | 2020-05-20 18:00 |  | 10 |  |  |  | 2020-04-21 17:40 | 2020-06-24 18:00 |  | 30 |  |  |  | 2020-04-28 17:40 | 2020-06-27 18:00 |  | 35 |  |  |  | 2020-05-04 23:59 | 2020-07-04 18:00 |  | 65 |  |  |  | 2020-05-11 17:40 | 2020-07-25 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-02 17:40 | 2020-08-08 18:00 |  | 100 | [122 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 146 |  |  |  |  | 101160
1037 | Task(Task)-->E (Engineering) | PIPE CONVEYOR FOR PC 1A/B : STRUCTURAL GA (SHT 5) |  | 1.9.1.3 | PIPE CONVEYOR FOR PC 1A/B : STRUCTURAL GA (SHT 5)-->STRUCTURAL-->ENGINEERING-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-03 18:00 | 2020-06-02 17:40 | 2020-09-03 09:00 | 2020-10-01 18:00 |  |  | 2020-02-21 15:37 | 2020-10-14 20:53 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-GA-0013 |  | 2020-02-13 11:42 | 7012-155-PVC-B-046 |  |  |  | A |  |  |  | 4.0948 | 0.009652 | 0.95 | Plan & Actual | Date |  | 0 | 0 | 0 | 351.15 | 0 | 94.1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3371 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-03 18:00 | 2020-05-20 18:00 |  | 10 |  |  |  | 2020-04-21 17:40 | 2020-06-24 18:00 |  | 30 |  |  |  | 2020-04-28 17:40 | 2020-06-27 18:00 |  | 35 | 2020-07-29 11:37 |  |  | 2020-05-04 23:59 | 2020-07-04 18:00 |  | 65 | 2020-09-06 17:32 |  |  | 2020-05-11 17:40 | 2020-07-25 18:00 |  | 80 | 2020-10-14 20:43 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-02 17:40 | 2020-08-08 18:00 |  | 100 | 2020-10-14 20:53 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 147 |  |  |  |  | 101161
1038 | Task(Task)-->E (Engineering) | ARCHITECTURAL GA OF PIPE CONVEYOR FOR PC 1A/B |  | 1.9.1.3 | ARCHITECTURAL GA OF PIPE CONVEYOR FOR PC 1A/B-->STRUCTURAL-->ENGINEERING-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-22 18:00 | 2020-08-21 17:40 | 2020-07-19 23:59 | 2020-09-27 23:59 |  |  | 2020-02-21 15:39 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-AR-0006 |  | 2020-02-13 11:43 | 7012-155-PVC-C-112 |  |  |  | I |  |  |  | 0.47414 | 0.001118 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 40.52 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3364 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-06-22 18:00 | 2020-07-19 23:59 |  | 10 |  |  |  | 2020-07-10 17:40 | 2020-08-13 18:00 |  | 30 |  |  |  | 2020-07-17 17:40 | 2020-08-16 23:59 |  | 35 |  |  |  | 2020-07-23 23:59 | 2020-08-23 23:59 |  | 65 |  |  |  | 2020-07-30 17:40 | 2020-09-13 23:59 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-08-21 17:40 | 2020-09-27 23:59 |  | 100 | [122 empty] | Chetan Khodke | [5 empty] | A - Architecture | [16 empty] | 213 |  |  |  |  | 101223
1039 | Task(Task)-->E (Engineering) | ELECTRICAL | 1.9.1.4 | 1.9.1 | ELECTRICAL-->ENGINEERING-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-27 17:40 | 2020-06-10 17:40 | 2020-04-24 18:00 | 2020-09-23 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 59.1446 | [15 empty] | 5.4908 | 0.021557 | 2.12 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3374 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036097
1040 | Task(Task)-->E (Engineering) | GAD, WIRING DIAGRAM, DATA SHEET & BOM OF 6.6kV MV VFD FOR CHP PIPE CONVEYORS |  | 1.9.1.4 | GAD, WIRING DIAGRAM, DATA SHEET & BOM OF 6.6kV MV VFD FOR CHP PIPE CONVEYORS-->ELECTRICAL-->ENGINEERING-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-16 18:00 | 2020-05-29 17:40 | 2020-06-05 18:00 | 2020-08-17 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-153 |  | 2020-02-13 11:46 | 7012-155-PVE-W-098 |  |  |  | A |  |  |  | 10.4265 | 0.002248 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 82.54 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3377 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-16 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-04-17 17:40 | 2020-06-12 18:00 |  | 30 |  |  |  | 2020-04-23 17:40 | 2020-06-19 18:00 |  | 35 |  |  |  | 2020-04-30 23:59 | 2020-06-19 18:00 |  | 65 |  |  |  | 2020-05-06 17:40 | 2020-07-10 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-29 17:40 | 2020-07-10 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 333 |  |  |  |  | 101344
1041 | Task(Task)-->E (Engineering) | GA, DATA SHEET, TERMINAL BOX ARRANGEMET & CHARACTERISTICS CURVES OF HT MOTOR FOR PIPE CONVEYING SYSTEM |  | 1.9.1.4 | GA, DATA SHEET, TERMINAL BOX ARRANGEMET & CHARACTERISTICS CURVES OF HT MOTOR FOR PIPE CONVEYING SYSTEM-->ELECTRICAL-->ENGINEERING-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-27 17:40 | 2020-05-08 17:40 | 2020-06-05 18:00 | 2020-09-11 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-160 |  | 2020-02-13 11:46 | 7012-155-PVE-W-105 |  |  |  | A |  |  |  | 10.4265 | 0.002248 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 82.54 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3378 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-27 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-03-27 17:40 | 2020-06-12 18:00 |  | 30 |  |  |  | 2020-04-03 17:40 | 2020-06-18 18:00 |  | 35 |  |  |  | 2020-04-09 23:59 | 2020-06-18 18:00 |  | 65 |  |  |  | 2020-04-16 17:40 | 2020-07-09 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-08 17:40 | 2020-07-09 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 340 |  |  |  |  | 101351
1042 | Task(Task)-->E (Engineering) | GA & FOUNDATION DRAWING , DATA SHEET,SLD , SCHEME DRAWING AND BOM OF 6.6kV APFC SYSTEM FOR CHP. |  | 1.9.1.4 | GA & FOUNDATION DRAWING , DATA SHEET,SLD , SCHEME DRAWING AND BOM OF 6.6kV APFC SYSTEM FOR CHP.-->ELECTRICAL-->ENGINEERING-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-09 18:00 | 2020-05-25 17:40 | 2020-06-21 23:59 | 2020-09-23 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-186 |  | 2020-02-13 11:47 | 7012-155-PVE-W-131 |  |  |  | A |  |  |  | 5.2133 | 0.001124 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3375 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-09 18:00 | 2020-06-21 23:59 |  | 10 |  |  |  | 2020-04-13 17:40 | 2020-06-28 23:59 |  | 30 |  |  |  | 2020-04-18 17:40 | 2020-07-06 18:00 |  | 35 |  |  |  | 2020-04-24 23:59 | 2020-07-06 18:00 |  | 65 |  |  |  | 2020-05-01 17:40 | 2020-07-27 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-25 17:40 | 2020-07-27 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 366 |  |  |  |  | 101377
1043 | Task(Task)-->E (Engineering) | LIGHTING LAYOUT PLAN WITH POWER DISTRIBUTION ARRANGEMENT, SECTIONAL VIEW, BOM OF PIPE CONVEYOR 1A/B |  | 1.9.1.4 | LIGHTING LAYOUT PLAN WITH POWER DISTRIBUTION ARRANGEMENT, SECTIONAL VIEW, BOM OF PIPE CONVEYOR 1A/B-->ELECTRICAL-->ENGINEERING-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-22 18:00 | 2020-06-10 17:40 | 2020-04-24 18:00 | 2020-06-24 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5077 |  | 2020-02-13 11:45 | 7012-155-PVE-G-039 |  |  |  | A |  |  |  | 73.9336 | 0.015938 | 1.56 | Plan & Actual | Date |  | 0 | 0 | 0 | 580.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3376 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-22 18:00 | 2020-04-24 18:00 |  | 10 | 2020-05-30 23:31 |  |  | 2020-04-30 17:40 | 2020-05-01 18:00 |  | 30 |  |  |  | 2020-05-06 17:40 | 2020-05-08 18:00 |  | 35 |  |  |  | 2020-05-13 23:59 | 2020-05-15 18:00 |  | 65 | 2020-08-03 11:52 |  |  | 2020-05-19 17:40 | 2020-06-05 18:00 |  | 80 | 2020-08-03 12:05 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-10 17:40 | 2020-06-05 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 274 |  |  |  |  | 101285
1044 | Task(Task)-->P (Procurement) | PROCUREMENT | 1.9.2 | 1.9 | PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-11-07 09:00 | 2021-03-31 18:00 | 2019-11-08 09:00 | 2022-02-22 18:00 |  |  | 2019-11-08 17:06 |  |  |  | 72.7403 | 30.3262 | [15 empty] | 74.5141 | 17.1634 | 1687.9 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3379 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018594
1045 | Task(Task)-->P (Procurement) | PURCHASE REQUISITION | 1.9.2.1 | 1.9.2 | PURCHASE REQUISITION-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-11-07 09:00 | 2020-05-19 18:00 | 2019-11-08 09:00 | 2020-07-19 23:59 |  |  | 2019-11-08 17:06 |  |  |  | 100 | 99.4668 | [15 empty] | 5.0002 | 0.85821 | 84.4 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3380 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018595
1046 | Task(Task)-->P (Procurement) | Pulley |  | 1.9.2.1 | Pulley-->PURCHASE REQUISITION-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-03 09:00 | 2020-03-03 18:00 | 2020-04-26 | 2020-04-26 23:59 |  |  | 2020-04-26 10:57 | 2020-04-26 10:57 |  |  | 100 | 100 | [15 empty] | 4.3133 | 0.037017 | 3.64 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3381 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018596
1047 | Task(Task)-->P (Procurement) | Idler |  | 1.9.2.1 | Idler-->PURCHASE REQUISITION-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-19 09:00 | 2019-11-19 18:00 | 2020-03-21 09:00 | 2020-03-21 18:00 |  |  | 2020-03-21 10:57 | 2020-03-21 10:57 |  |  | 100 | 100 | [15 empty] | 16.2579 | 0.13953 | 13.72 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3382 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018597
1048 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.9.2.1 | Plummer Block-->PURCHASE REQUISITION-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-17 | 2020-05-17 23:59 | 2020-04-26 | 2020-04-26 23:59 |  |  | 2020-04-26 10:57 | 2020-04-26 10:57 |  |  | 100 | 100 | [15 empty] | 0.34364 | 0.002949 | 0.29 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3383 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018598
1049 | Task(Task)-->P (Procurement) | Bearing |  | 1.9.2.1 | Bearing-->PURCHASE REQUISITION-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-17 | 2020-05-17 23:59 | 2020-04-26 | 2020-04-26 23:59 |  |  | 2020-04-26 10:57 | 2020-04-26 10:57 |  |  | 100 | 100 | [15 empty] | 0.78208 | 0.006712 | 0.66 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3384 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018599
1050 | Task(Task)-->P (Procurement) | Belting |  | 1.9.2.1 | Belting-->PURCHASE REQUISITION-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-07 09:00 | 2019-11-07 18:00 | 2020-02-21 09:00 | 2020-02-21 18:00 |  |  | 2020-02-21 16:00 | 2020-02-21 16:00 |  |  | 100 | 100 | [15 empty] | 28.9489 | 0.24844 | 24.43 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3385 | 1 | 4 | High | [7 empty] | 0 | 0 | [246 empty] | 1018600
1051 | Task(Task)-->P (Procurement) | Scrapper |  | 1.9.2.1 | Scrapper-->PURCHASE REQUISITION-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-17 | 2019-11-17 23:59 | 2020-03-11 09:00 | 2020-03-11 18:00 |  |  | 2020-03-11 10:57 | 2020-03-11 10:57 |  |  | 100 | 100 | [15 empty] | 0.023699 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3386 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018601
1052 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.9.2.1 | Technological Structure-->PURCHASE REQUISITION-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-10 09:00 | 2020-03-10 18:00 | 2020-03-11 09:00 | 2020-03-11 18:00 |  |  | 2020-03-11 12:41 | 2020-03-11 12:41 |  |  | 100 | 100 | [15 empty] | 1.5049 | 0.012915 | 1.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3387 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018602
1053 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.9.2.1 | Takeup Component-->PURCHASE REQUISITION-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-19 09:00 | 2020-05-19 18:00 | 2020-06-08 09:00 | 2020-06-08 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.53324 | 0.004576 | 0.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3388 | 1 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018603
1054 | Task(Task)-->P (Procurement) | Gear Box |  | 1.9.2.1 | Gear Box-->PURCHASE REQUISITION-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-13 09:00 | 2019-11-13 18:00 | 2020-02-21 09:00 | 2020-02-21 18:00 |  |  | 2020-02-21 10:57 | 2020-02-21 10:57 |  |  | 100 | 100 | [15 empty] | 2.7017 | 0.023187 | 2.28 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3389 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018604
1055 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.9.2.1 | Geared Coupling-->PURCHASE REQUISITION-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-21 09:00 | 2019-11-21 18:00 | 2020-04-27 09:00 | 2020-04-27 18:00 |  |  | 2020-04-27 10:41 | 2020-04-27 10:41 |  |  | 100 | 100 | [15 empty] | 0.58064 | 0.004983 | 0.49 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3390 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018605
1056 | Task(Task)-->P (Procurement) | Brake |  | 1.9.2.1 | Brake-->PURCHASE REQUISITION-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-18 09:00 | 2019-12-18 18:00 | 2020-05-01 09:00 | 2020-05-01 18:00 |  |  | 2020-04-23 11:33 | 2020-04-23 11:33 |  |  | 100 | 100 | [15 empty] | 0.17775 | 0.001525 | 0.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3391 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018606
1057 | Task(Task)-->P (Procurement) | Maintenance Trolley |  | 1.9.2.1 | Maintenance Trolley-->PURCHASE REQUISITION-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-30 09:00 | 2019-11-30 18:00 | 2020-07-19 | 2020-07-19 23:59 |  |  | 2020-07-28 11:45 | 2020-07-28 11:45 |  |  | 100 | 100 | [15 empty] | 0.36734 | 0.003153 | 0.31 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3392 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018607
1058 | Task(Task)-->P (Procurement) | Building Structure |  | 1.9.2.1 | Building Structure-->PURCHASE REQUISITION-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-20 09:00 | 2020-03-20 18:00 | 2020-04-06 09:00 | 2020-04-06 18:00 |  |  | 2020-04-06 17:30 | 2020-04-06 17:30 |  |  | 100 | 100 | [15 empty] | 32.6579 | 0.28027 | 27.56 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3393 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018608
1059 | Task(Task)-->P (Procurement) | 6.6KV HT VFD with Motors |  | 1.9.2.1 | 6.6KV HT VFD with Motors-->PURCHASE REQUISITION-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-30 09:00 | 2019-12-30 18:00 | 2020-01-24 09:00 | 2020-01-24 18:00 |  |  | 2019-11-21 10:57 | 2019-11-21 10:57 |  |  | 100 | 100 | [15 empty] | 9.9064 | 0.085018 | 8.36 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3394 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018609
1060 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.9.2.1 | LIGHT & LIGHT FIXTURES-->PURCHASE REQUISITION-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-10 09:00 | 2020-03-10 18:00 | 2020-03-16 09:00 | 2020-03-16 18:00 |  |  | 2020-03-16 10:57 | 2020-03-16 10:57 |  |  | 100 | 100 | [15 empty] | 0.31994 | 0.002746 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3395 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018610
1061 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.9.2.1 | LIGHTING POLES-->PURCHASE REQUISITION-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-27 09:00 | 2020-03-27 18:00 | 2020-04-30 09:00 | 2020-04-30 18:00 |  |  | 2020-04-30 10:57 | 2020-04-30 10:57 |  |  | 100 | 100 | [15 empty] | 0.1422 | 0.00122 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3396 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018611
1062 | Task(Task)-->P (Procurement) | WELDING DISTRIBUTION BOARD |  | 1.9.2.1 | WELDING DISTRIBUTION BOARD-->PURCHASE REQUISITION-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-14 09:00 | 2020-02-14 18:00 | 2019-11-08 09:00 | 2019-11-08 18:00 |  |  | 2019-11-08 17:06 | 2019-11-08 17:06 |  |  | 100 | 100 | [15 empty] | 0.39104 | 0.003356 | 0.33 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3397 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018612
1063 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.9.2.1 | CONVEYOR BELT PROTECTION SWITCHES-->PURCHASE REQUISITION-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-08 09:00 | 2020-01-08 18:00 | 2020-01-08 09:00 | 2020-01-08 18:00 |  |  | 2020-01-08 10:57 | 2020-01-08 10:57 |  |  | 100 | 100 | [15 empty] | 0.047399 | 0.000407 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3399 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018613
1064 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.9.2.1 | ZERO SPEED SWITCH-->PURCHASE REQUISITION-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-30 09:00 | 2019-12-30 18:00 | 2019-12-30 09:00 | 2019-12-30 18:00 |  |  | 2019-12-30 10:57 | 2019-12-30 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3400 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018614
1065 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.9.2.1 | CHUTE BLOCK SWITCH-->PURCHASE REQUISITION-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-03 09:00 | 2020-01-03 18:00 | 2020-01-03 09:00 | 2020-01-03 18:00 |  |  | 2020-01-03 10:57 | 2020-01-03 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3401 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018615
1066 | Task(Task)-->P (Procurement) | TECHNICAL CLEARANCE | 1.9.2.2 | 1.9.2 | TECHNICAL CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-11-08 09:00 | 2020-06-18 18:00 | 2019-11-08 09:00 | 2020-11-15 23:59 |  |  | 2019-11-09 17:07 |  |  |  | 100 | 99.0994 | [15 empty] | 5.0002 | 0.85821 | 84.4 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3402 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018616
1067 | Task(Task)-->P (Procurement) | Pulley |  | 1.9.2.2 | Pulley-->TECHNICAL CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-04 09:00 | 2020-03-04 18:00 | 2020-04-26 | 2020-04-26 23:59 |  |  | 2020-04-26 10:57 | 2020-04-26 10:57 |  |  | 100 | 100 | [15 empty] | 4.3133 | 0.037017 | 3.64 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3403 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018617
1068 | Task(Task)-->P (Procurement) | Idler |  | 1.9.2.2 | Idler-->TECHNICAL CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-20 09:00 | 2020-02-01 18:00 | 2020-03-21 09:00 | 2020-05-16 18:00 |  |  | 2020-03-23 15:48 | 2020-05-16 15:48 |  |  | 100 | 100 | [15 empty] | 16.2579 | 0.13953 | 13.72 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3404 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018618
1069 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.9.2.2 | Plummer Block-->TECHNICAL CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-18 09:00 | 2020-06-01 18:00 | 2020-04-26 | 2020-04-26 23:59 |  |  | 2020-04-26 10:57 | 2020-04-26 10:57 |  |  | 100 | 100 | [15 empty] | 0.34364 | 0.002949 | 0.29 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3405 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018619
1070 | Task(Task)-->P (Procurement) | Bearing |  | 1.9.2.2 | Bearing-->TECHNICAL CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-18 09:00 | 2020-06-16 18:00 | 2020-04-26 | 2020-04-26 23:59 |  |  | 2020-04-26 10:57 | 2020-04-26 10:57 |  |  | 100 | 100 | [15 empty] | 0.78208 | 0.006712 | 0.66 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3406 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018620
1071 | Task(Task)-->P (Procurement) | Belting |  | 1.9.2.2 | Belting-->TECHNICAL CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-08 09:00 | 2020-03-27 18:00 | 2020-02-21 09:00 | 2020-05-16 18:00 |  |  | 2020-05-16 10:57 | 2020-05-16 10:57 |  |  | 100 | 100 | [15 empty] | 28.9489 | 0.24844 | 24.43 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3407 | 0 | 4 | High | [7 empty] | 0 | 0 | [246 empty] | 1018621
1072 | Task(Task)-->P (Procurement) | Scrapper |  | 1.9.2.2 | Scrapper-->TECHNICAL CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-18 09:00 | 2020-03-16 18:00 | 2020-03-11 09:00 | 2020-03-26 18:00 |  |  | 2020-03-26 10:57 | 2020-03-26 10:57 |  |  | 100 | 100 | [15 empty] | 0.023699 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3408 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018622
1073 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.9.2.2 | Technological Structure-->TECHNICAL CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-11 09:00 | 2020-03-20 18:00 | 2020-03-11 09:00 | 2020-03-17 18:00 |  |  | 2020-03-12 12:43 | 2020-03-17 12:43 |  |  | 100 | 100 | [15 empty] | 1.5049 | 0.012915 | 1.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3409 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018623
1074 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.9.2.2 | Takeup Component-->TECHNICAL CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-20 09:00 | 2020-06-18 18:00 | 2020-06-08 09:00 | 2020-08-13 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.53324 | 0.004576 | 0.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3410 | 1 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018624
1075 | Task(Task)-->P (Procurement) | Gear Box |  | 1.9.2.2 | Gear Box-->TECHNICAL CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-14 09:00 | 2020-05-21 18:00 | 2020-02-21 09:00 | 2020-05-29 18:00 |  |  | 2020-02-22 11:19 | 2020-05-29 10:57 |  |  | 100 | 100 | [15 empty] | 2.7017 | 0.023187 | 2.28 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3411 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018625
1076 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.9.2.2 | Geared Coupling-->TECHNICAL CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-22 09:00 | 2020-03-19 18:00 | 2020-04-27 09:00 | 2020-05-30 18:00 |  |  | 2020-05-30 10:46 | 2020-05-30 10:46 |  |  | 100 | 100 | [15 empty] | 0.58064 | 0.004983 | 0.49 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3412 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018626
1077 | Task(Task)-->P (Procurement) | Brake |  | 1.9.2.2 | Brake-->TECHNICAL CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-19 09:00 | 2020-04-05 23:59 | 2020-05-01 09:00 | 2020-06-15 18:00 |  |  | 2020-04-24 11:34 | 2020-06-15 10:57 |  |  | 100 | 100 | [15 empty] | 0.17775 | 0.001525 | 0.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3413 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018627
1078 | Task(Task)-->P (Procurement) | Maintenance Trolley |  | 1.9.2.2 | Maintenance Trolley-->TECHNICAL CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-12-01 | 2019-12-18 18:00 | 2020-07-19 | 2020-11-15 23:59 | [6 empty] | 100 | 0 | [15 empty] | 0.36734 | 0.003153 | 0.31 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3414 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018628
1079 | Task(Task)-->P (Procurement) | Building Structure |  | 1.9.2.2 | Building Structure-->TECHNICAL CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-21 09:00 | 2020-03-27 18:00 | 2020-04-06 09:00 | 2020-04-13 18:00 |  |  | 2020-04-07 17:31 | 2020-04-13 17:31 |  |  | 100 | 100 | [15 empty] | 32.6579 | 0.28027 | 27.56 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3415 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018629
1080 | Task(Task)-->P (Procurement) | 6.6KV HT VFD with Motors |  | 1.9.2.2 | 6.6KV HT VFD with Motors-->TECHNICAL CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-31 09:00 | 2020-01-29 18:00 | 2020-01-24 09:00 | 2020-04-16 18:00 |  |  | 2020-02-26 10:57 | 2020-02-26 10:57 |  |  | 100 | 100 | [15 empty] | 9.9064 | 0.085018 | 8.36 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3416 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018630
1081 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.9.2.2 | LIGHT & LIGHT FIXTURES-->TECHNICAL CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-11 09:00 | 2020-03-25 18:00 | 2020-03-16 09:00 | 2020-06-02 18:00 |  |  | 2020-06-02 10:57 | 2020-06-02 10:57 |  |  | 100 | 100 | [15 empty] | 0.31994 | 0.002746 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3417 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018631
1082 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.9.2.2 | LIGHTING POLES-->TECHNICAL CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-28 09:00 | 2020-05-11 18:00 | 2020-04-30 09:00 | 2020-06-03 18:00 |  |  | 2020-06-03 10:57 | 2020-06-03 10:57 |  |  | 100 | 100 | [15 empty] | 0.1422 | 0.00122 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3418 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018632
1083 | Task(Task)-->P (Procurement) | WELDING DISTRIBUTION BOARD |  | 1.9.2.2 | WELDING DISTRIBUTION BOARD-->TECHNICAL CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-15 09:00 | 2020-02-28 18:00 | 2019-11-08 09:00 | 2020-02-13 18:00 |  |  | 2019-11-09 17:07 | 2020-02-13 17:07 |  |  | 100 | 100 | [15 empty] | 0.39104 | 0.003356 | 0.33 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3419 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018633
1084 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.9.2.2 | CONVEYOR BELT PROTECTION SWITCHES-->TECHNICAL CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-09 09:00 | 2020-01-22 18:00 | 2020-01-08 09:00 | 2020-03-10 18:00 |  |  | 2020-03-10 10:57 | 2020-03-10 10:57 |  |  | 100 | 100 | [15 empty] | 0.047399 | 0.000407 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3421 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018634
1085 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.9.2.2 | ZERO SPEED SWITCH-->TECHNICAL CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-31 09:00 | 2020-01-14 18:00 | 2019-12-30 09:00 | 2020-03-07 18:00 |  |  | 2020-03-07 10:57 | 2020-03-07 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3422 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018635
1086 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.9.2.2 | CHUTE BLOCK SWITCH-->TECHNICAL CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-04 09:00 | 2020-01-18 18:00 | 2020-01-03 09:00 | 2020-01-16 18:00 |  |  | 2020-01-16 10:57 | 2020-01-16 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3423 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018636
1087 | Task(Task)-->P (Procurement) | ORDERING | 1.9.2.3 | 1.9.2 | ORDERING-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-12-19 09:00 | 2020-07-18 18:00 | 2020-01-16 09:00 | 2020-12-05 18:00 |  |  | 2020-02-01 10:57 |  |  |  | 100 | 93.9458 | [15 empty] | 9.9999 | 1.7163 | 168.79 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3424 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018637
1088 | Task(Task)-->P (Procurement) | Pulley |  | 1.9.2.3 | Pulley-->ORDERING-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-05 09:00 | 2020-04-03 18:00 | 2020-04-26 | 2020-07-16 18:00 | [6 empty] | 100 | 0 | [15 empty] | 4.3185 | 0.074119 | 7.29 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3425 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018638
1089 | Task(Task)-->P (Procurement) | Idler |  | 1.9.2.3 | Idler-->ORDERING-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-02 | 2020-03-02 18:00 | 2020-05-16 09:00 | 2020-08-22 18:00 |  |  | 2020-05-16 16:18 | 2020-08-22 16:18 |  |  | 100 | 100 | [15 empty] | 16.255 | 0.27899 | 27.44 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3426 | 1 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018639
1090 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.9.2.3 | Plummer Block-->ORDERING-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-06-02 09:00 | 2020-07-01 18:00 | 2020-04-26 | 2020-07-07 18:00 |  |  | 2020-04-27 09:32 | 2020-07-07 09:32 |  |  | 100 | 100 | [15 empty] | 0.34951 | 0.005999 | 0.59 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3427 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018640
1091 | Task(Task)-->P (Procurement) | Bearing |  | 1.9.2.3 | Bearing-->ORDERING-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-17 09:00 | 2020-07-16 18:00 | 2020-04-26 | 2020-08-22 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.78194 | 0.013421 | 1.32 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3428 | 1 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018641
1092 | Task(Task)-->P (Procurement) | Belting |  | 1.9.2.3 | Belting-->ORDERING-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-28 09:00 | 2020-05-11 18:00 | 2020-05-16 09:00 | 2020-09-04 18:00 |  |  | 2020-05-16 16:24 | 2020-09-04 16:24 |  |  | 100 | 100 | [15 empty] | 28.9379 | 0.49667 | 48.85 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3429 | 0 | 4 | High | [7 empty] | 0 | 0 | [246 empty] | 1018642
1093 | Task(Task)-->P (Procurement) | Scrapper |  | 1.9.2.3 | Scrapper-->ORDERING-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-17 09:00 | 2020-04-15 18:00 | 2020-03-26 09:00 | 2020-05-30 18:00 |  |  | 2020-05-30 10:57 | 2020-05-30 10:57 |  |  | 100 | 100 | [15 empty] | 0.023695 | 0.000407 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3430 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018643
1094 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.9.2.3 | Technological Structure-->ORDERING-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-21 09:00 | 2020-04-19 23:59 | 2020-03-17 09:00 | 2020-07-06 18:00 |  |  | 2020-03-18 12:44 | 2020-07-06 12:44 |  |  | 100 | 100 | [15 empty] | 1.4987 | 0.025723 | 2.53 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3431 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018644
1095 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.9.2.3 | Takeup Component-->ORDERING-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-19 09:00 | 2020-07-18 18:00 | 2020-08-13 09:00 | 2020-11-30 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.53907 | 0.009252 | 0.91 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3432 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018645
1096 | Task(Task)-->P (Procurement) | Gear Box |  | 1.9.2.3 | Gear Box-->ORDERING-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-22 09:00 | 2020-06-20 18:00 | 2020-05-29 09:00 | 2020-06-23 18:00 |  |  | 2020-05-30 11:21 | 2020-06-23 16:51 |  |  | 100 | 100 | [15 empty] | 2.6953 | 0.046261 | 4.55 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3433 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018646
1097 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.9.2.3 | Geared Coupling-->ORDERING-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-20 09:00 | 2020-04-18 18:00 | 2020-05-30 09:00 | 2020-06-16 18:00 |  |  | 2020-06-01 11:11 | 2020-06-16 16:05 |  |  | 100 | 100 | [15 empty] | 0.58646 | 0.010065 | 0.99 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3434 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018647
1098 | Task(Task)-->P (Procurement) | Brake |  | 1.9.2.3 | Brake-->ORDERING-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-06 09:00 | 2020-05-05 18:00 | 2020-06-15 09:00 | 2020-07-03 18:00 |  |  | 2020-06-16 11:39 | 2020-07-03 11:39 |  |  | 100 | 100 | [15 empty] | 0.18364 | 0.003152 | 0.31 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3435 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018648
1099 | Task(Task)-->P (Procurement) | Maintenance Trolley |  | 1.9.2.3 | Maintenance Trolley-->ORDERING-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-12-19 09:00 | 2020-01-07 18:00 | 2020-11-16 09:00 | 2020-12-05 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.3732 | 0.006405 | 0.63 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3436 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018649
1100 | Task(Task)-->P (Procurement) | Building Structure |  | 1.9.2.3 | Building Structure-->ORDERING-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-28 09:00 | 2020-04-26 23:59 | 2020-04-13 09:00 | 2020-05-31 23:59 |  |  | 2020-05-31 18:49 | 2020-05-31 18:49 |  |  | 100 | 100 | [15 empty] | 32.6462 | 0.56031 | 55.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3437 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018650
1101 | Task(Task)-->P (Procurement) | 6.6KV HT VFD with Motors |  | 1.9.2.3 | 6.6KV HT VFD with Motors-->ORDERING-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-30 09:00 | 2020-02-28 18:00 | 2020-04-16 09:00 | 2020-07-18 18:00 |  |  | 2020-04-29 10:57 | 2020-04-29 10:57 |  |  | 100 | 100 | [15 empty] | 9.9106 | 0.1701 | 16.73 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3438 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018651
1102 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.9.2.3 | LIGHT & LIGHT FIXTURES-->ORDERING-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-26 09:00 | 2020-04-10 18:00 | 2020-06-02 09:00 | 2020-07-31 18:00 |  |  | 2020-06-03 15:51 | 2020-06-29 15:51 |  |  | 100 | 100 | [15 empty] | 0.31396 | 0.005389 | 0.53 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3439 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018652
1103 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.9.2.3 | LIGHTING POLES-->ORDERING-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-12 09:00 | 2020-06-25 18:00 | 2020-06-03 09:00 | 2020-06-24 18:00 |  |  | 2020-06-15 10:57 | 2020-06-15 10:57 |  |  | 100 | 100 | [15 empty] | 0.14217 | 0.00244 | 0.24 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3440 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018653
1104 | Task(Task)-->P (Procurement) | WELDING DISTRIBUTION BOARD |  | 1.9.2.3 | WELDING DISTRIBUTION BOARD-->ORDERING-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-29 09:00 | 2020-03-14 18:00 | 2020-02-13 09:00 | 2020-06-17 18:00 |  |  | 2020-02-29 08:00 | 2020-03-24 16:05 |  |  | 100 | 100 | [15 empty] | 0.3969 | 0.006812 | 0.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3441 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018654
1105 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.9.2.3 | CONVEYOR BELT PROTECTION SWITCHES-->ORDERING-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-23 09:00 | 2020-02-05 18:00 | 2020-03-10 09:00 | 2020-08-17 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.041467 | 0.000712 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3443 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018655
1106 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.9.2.3 | ZERO SPEED SWITCH-->ORDERING-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-15 09:00 | 2020-02-01 18:00 | 2020-03-07 09:00 | 2020-08-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3444 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018656
1107 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.9.2.3 | CHUTE BLOCK SWITCH-->ORDERING-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-19 | 2020-01-31 18:00 | 2020-01-16 09:00 | 2020-02-01 18:00 |  |  | 2020-02-01 10:57 | 2020-02-01 10:57 |  |  | 100 | 100 | [15 empty] | 0.0059238 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3445 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018657
1108 | Task(Task)-->P (Procurement) | ITP APPROVAL | 1.9.2.4 | 1.9.2 | ITP APPROVAL-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-01-08 09:00 | 2020-08-27 18:00 | 2020-05-01 09:00 | 2021-01-14 18:00 |  |  | 2020-05-01 10:26 |  |  |  | 100 | 34.734 | [15 empty] | 5.0002 | 0.85821 | 84.4 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3446 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018658
1109 | Task(Task)-->P (Procurement) | Pulley |  | 1.9.2.4 | Pulley-->ITP APPROVAL-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-04 09:00 | 2020-05-13 18:00 | 2020-07-16 09:00 | 2020-07-16 18:00 | [6 empty] | 100 | 0 | [15 empty] | 4.3133 | 0.037017 | 3.64 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3447 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018659
1110 | Task(Task)-->P (Procurement) | Idler |  | 1.9.2.4 | Idler-->ITP APPROVAL-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-03 09:00 | 2020-04-11 18:00 | 2020-08-22 09:00 | 2020-10-10 18:00 |  |  | 2020-08-22 16:22 |  |  |  | 100 | 10 | [15 empty] | 16.2579 | 0.13953 | 13.72 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3448 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018660
1111 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.9.2.4 | Plummer Block-->ITP APPROVAL-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-02 09:00 | 2020-08-10 18:00 | 2020-07-07 09:00 | 2020-08-13 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.34364 | 0.002949 | 0.29 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3449 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018661
1112 | Task(Task)-->P (Procurement) | Bearing |  | 1.9.2.4 | Bearing-->ITP APPROVAL-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-17 09:00 | 2020-08-25 18:00 | 2020-05-18 09:00 | 2020-05-25 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.78208 | 0.006712 | 0.66 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3450 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018662
1113 | Task(Task)-->P (Procurement) | Belting |  | 1.9.2.4 | Belting-->ITP APPROVAL-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-12 09:00 | 2020-06-20 18:00 | 2020-09-04 09:00 | 2020-11-10 18:00 |  |  | 2020-09-04 16:30 | 2020-09-30 16:30 |  |  | 100 | 100 | [15 empty] | 28.9489 | 0.24844 | 24.43 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3451 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018663
1114 | Task(Task)-->P (Procurement) | Scrapper |  | 1.9.2.4 | Scrapper-->ITP APPROVAL-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-16 09:00 | 2020-05-25 18:00 | 2020-05-30 09:00 | 2020-06-25 18:00 |  |  | 2020-05-30 16:32 | 2020-06-25 16:32 |  |  | 100 | 100 | [15 empty] | 0.023699 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3452 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018664
1115 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.9.2.4 | Technological Structure-->ITP APPROVAL-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-20 09:00 | 2020-05-29 18:00 | 2020-07-06 09:00 | 2020-07-16 18:00 | [6 empty] | 100 | 0 | [15 empty] | 1.5049 | 0.012915 | 1.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3453 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018665
1116 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.9.2.4 | Takeup Component-->ITP APPROVAL-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-19 | 2020-08-27 18:00 | 2020-08-13 09:00 | 2020-11-15 23:59 | [6 empty] | 100 | 0 | [15 empty] | 0.53324 | 0.004576 | 0.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3454 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018666
1117 | Task(Task)-->P (Procurement) | Gear Box |  | 1.9.2.4 | Gear Box-->ITP APPROVAL-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-06-21 | 2020-07-30 18:00 | 2020-06-23 09:00 | 2020-06-23 18:00 |  |  | 2020-06-22 16:57 | 2020-06-22 16:57 |  |  | 100 | 100 | [15 empty] | 2.7017 | 0.023187 | 2.28 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3455 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018667
1118 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.9.2.4 | Geared Coupling-->ITP APPROVAL-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-19 | 2020-05-28 18:00 | 2020-06-16 09:00 | 2020-06-18 18:00 |  |  | 2020-06-16 17:31 | 2020-06-18 17:31 |  |  | 100 | 100 | [15 empty] | 0.58064 | 0.004983 | 0.49 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3456 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018668
1119 | Task(Task)-->P (Procurement) | Brake |  | 1.9.2.4 | Brake-->ITP APPROVAL-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-06 09:00 | 2020-06-14 23:59 | 2020-07-03 09:00 | 2020-10-27 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.17775 | 0.001525 | 0.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3457 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018669
1120 | Task(Task)-->P (Procurement) | Maintenance Trolley |  | 1.9.2.4 | Maintenance Trolley-->ITP APPROVAL-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-08 09:00 | 2020-02-16 23:59 | 2020-12-06 | 2021-01-14 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.36734 | 0.003153 | 0.31 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3458 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018670
1121 | Task(Task)-->P (Procurement) | Building Structure |  | 1.9.2.4 | Building Structure-->ITP APPROVAL-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-27 09:00 | 2020-05-03 23:59 | 2020-05-31 | 2020-08-04 18:00 |  |  | 2020-06-25 19:04 |  |  |  | 100 | 0 | [15 empty] | 32.6579 | 0.28027 | 27.56 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3459 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018671
1122 | Task(Task)-->P (Procurement) | 6.6KV HT VFD with Motors |  | 1.9.2.4 | 6.6KV HT VFD with Motors-->ITP APPROVAL-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-29 09:00 | 2020-04-08 18:00 | 2020-08-01 09:00 | 2020-09-09 18:00 | [6 empty] | 100 | 0 | [15 empty] | 9.9064 | 0.085018 | 8.36 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3460 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018672
1123 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.9.2.4 | LIGHT & LIGHT FIXTURES-->ITP APPROVAL-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-11 09:00 | 2020-05-20 18:00 | 2020-07-28 09:00 | 2020-09-08 18:00 |  |  | 2020-07-08 17:23 | 2020-09-08 17:23 |  |  | 100 | 100 | [15 empty] | 0.31994 | 0.002746 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3461 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018673
1124 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.9.2.4 | LIGHTING POLES-->ITP APPROVAL-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-06-26 09:00 | 2020-08-04 18:00 | 2020-06-23 09:00 | 2020-09-08 18:00 |  |  | 2020-06-23 17:41 | 2020-09-08 17:05 |  |  | 100 | 100 | [15 empty] | 0.1422 | 0.00122 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3462 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018674
1125 | Task(Task)-->P (Procurement) | WELDING DISTRIBUTION BOARD |  | 1.9.2.4 | WELDING DISTRIBUTION BOARD-->ITP APPROVAL-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-15 | 2020-04-23 18:00 | 2020-05-01 09:00 | 2020-05-19 18:00 |  |  | 2020-05-01 10:26 | 2020-05-19 10:26 |  |  | 100 | 100 | [15 empty] | 0.39104 | 0.003356 | 0.33 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3463 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018675
1126 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.9.2.4 | CONVEYOR BELT PROTECTION SWITCHES-->ITP APPROVAL-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-06 09:00 | 2020-03-16 18:00 | 2020-09-24 09:00 | 2020-11-30 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.047399 | 0.000407 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3465 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018676
1127 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.9.2.4 | ZERO SPEED SWITCH-->ITP APPROVAL-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-02 | 2020-03-12 18:00 | 2020-08-02 | 2020-09-10 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3466 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018677
1128 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.9.2.4 | CHUTE BLOCK SWITCH-->ITP APPROVAL-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-01 09:00 | 2020-03-11 18:00 | 2020-07-02 09:00 | 2020-08-04 18:00 |  |  | 2020-07-17 16:57 | 2020-08-04 16:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3467 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018678
1129 | Task(Task)-->P (Procurement) | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE | 1.9.2.5 | 1.9.2 | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-01-08 09:00 | 2020-09-01 18:00 | 2020-02-01 09:00 | 2021-02-13 18:00 |  |  | 2020-02-11 21:31 |  |  |  | 100 | 61.0723 | [15 empty] | 15.0001 | 2.5745 | 253.19 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3468 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018679
1130 | Task(Task)-->P (Procurement) | Pulley |  | 1.9.2.5 | Pulley-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-04 09:00 | 2020-06-02 18:00 | 2020-07-16 09:00 | 2020-07-16 18:00 | [6 empty] | 100 | 0 | [15 empty] | 4.3167 | 0.11114 | 10.93 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3469 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018680
1131 | Task(Task)-->P (Procurement) | Idler |  | 1.9.2.5 | Idler-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-03 09:00 | 2020-05-01 18:00 | 2020-08-22 09:00 | 2020-11-15 23:59 | [6 empty] | 100 | 0 | [15 empty] | 16.2559 | 0.41851 | 41.16 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3470 | 1 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018681
1132 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.9.2.5 | Plummer Block-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-02 09:00 | 2020-08-30 23:59 | 2020-07-07 09:00 | 2020-09-28 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.34755 | 0.008948 | 0.88 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3471 | 1 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018682
1133 | Task(Task)-->P (Procurement) | Bearing |  | 1.9.2.5 | Bearing-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-17 09:00 | 2020-07-17 18:00 | 2020-07-18 09:00 | 2020-08-22 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.78199 | 0.020133 | 1.98 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3472 | 1 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018683
1134 | Task(Task)-->P (Procurement) | Belting |  | 1.9.2.5 | Belting-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-12 09:00 | 2020-07-20 18:00 | 2020-09-04 09:00 | 2020-11-15 23:59 |  |  | 2020-09-04 16:36 |  |  |  | 100 | 50 | [15 empty] | 28.9415 | 0.74511 | 73.28 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3473 | 0 | 4 | High | [7 empty] | 0 | 0 | [246 empty] | 1018684
1135 | Task(Task)-->P (Procurement) | Scrapper |  | 1.9.2.5 | Scrapper-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-16 09:00 | 2020-06-14 23:59 | 2020-05-30 09:00 | 2020-07-30 18:00 |  |  | 2020-05-30 16:35 | 2020-07-30 16:35 |  |  | 100 | 100 | [15 empty] | 0.023697 | 0.00061 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3474 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018685
1136 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.9.2.5 | Technological Structure-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-20 09:00 | 2020-08-17 18:00 | 2020-07-06 09:00 | 2020-07-06 18:00 |  |  | 2020-07-06 12:45 | 2020-07-06 12:45 |  |  | 100 | 100 | [15 empty] | 1.5008 | 0.038638 | 3.8 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3475 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018686
1137 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.9.2.5 | Takeup Component-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-19 | 2020-09-01 18:00 | 2020-12-01 09:00 | 2021-01-14 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.53712 | 0.013828 | 1.36 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3476 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018687
1138 | Task(Task)-->P (Procurement) | Gear Box |  | 1.9.2.5 | Gear Box-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-21 | 2020-08-19 18:00 | 2020-06-23 09:00 | 2020-11-16 18:00 |  |  | 2020-06-23 16:55 |  |  |  | 100 | 50 | [15 empty] | 2.6975 | 0.069447 | 6.83 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3477 | 1 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018688
1139 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.9.2.5 | Geared Coupling-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-19 | 2020-06-17 18:00 | 2020-06-16 09:00 | 2020-09-02 18:00 |  |  | 2020-06-16 17:31 | 2020-09-02 17:31 |  |  | 100 | 100 | [15 empty] | 0.58452 | 0.015049 | 1.48 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3478 | 1 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018689
1140 | Task(Task)-->P (Procurement) | Brake |  | 1.9.2.5 | Brake-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-06 09:00 | 2020-07-04 18:00 | 2020-07-03 09:00 | 2020-10-12 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.18167 | 0.004677 | 0.46 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3479 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018690
1141 | Task(Task)-->P (Procurement) | Maintenance Trolley |  | 1.9.2.5 | Maintenance Trolley-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-08 09:00 | 2020-03-17 18:00 | 2020-12-06 | 2021-02-13 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.37125 | 0.009558 | 0.94 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3480 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018691
1142 | Task(Task)-->P (Procurement) | Building Structure |  | 1.9.2.5 | Building Structure-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-25 09:00 | 2020-05-01 18:00 | 2020-05-31 | 2020-06-27 18:00 |  |  | 2020-05-31 18:54 | 2020-06-23 18:54 |  |  | 100 | 100 | [15 empty] | 32.6501 | 0.84059 | 82.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3481 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018692
1143 | Task(Task)-->P (Procurement) | 6.6KV HT VFD with Motors |  | 1.9.2.5 | 6.6KV HT VFD with Motors-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-29 09:00 | 2020-05-13 18:00 | 2020-08-08 09:00 | 2020-11-10 18:00 |  |  | 2020-07-28 11:51 | 2020-09-23 15:24 |  |  | 100 | 100 | [15 empty] | 9.9092 | 0.25511 | 25.09 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3482 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018693
1144 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.9.2.5 | LIGHT & LIGHT FIXTURES-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-11 09:00 | 2020-05-25 18:00 | 2020-07-10 09:00 | 2020-11-16 18:00 |  |  | 2020-07-14 10:44 |  |  |  | 100 | 0 | [15 empty] | 0.31596 | 0.008134 | 0.8 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3483 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018694
1145 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.9.2.5 | LIGHTING POLES-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-06-26 09:00 | 2020-08-09 23:59 | 2020-05-30 09:00 | 2020-08-08 18:00 |  |  | 2020-06-18 17:11 | 2020-08-07 15:00 |  |  | 100 | 100 | [15 empty] | 0.14218 | 0.00366 | 0.36 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3484 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018695
1146 | Task(Task)-->P (Procurement) | WELDING DISTRIBUTION BOARD |  | 1.9.2.5 | WELDING DISTRIBUTION BOARD-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-15 | 2020-04-28 18:00 | 2020-04-25 09:00 | 2020-07-17 18:00 |  |  | 2020-04-25 10:24 | 2020-07-17 10:23 |  |  | 100 | 100 | [15 empty] | 0.39494 | 0.010168 | 1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3485 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018696
1147 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.9.2.5 | CONVEYOR BELT PROTECTION SWITCHES-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-06 09:00 | 2020-03-21 18:00 | 2020-08-11 09:00 | 2020-09-19 18:00 |  |  | 2020-08-11 13:12 | 2020-09-19 12:58 |  |  | 100 | 100 | [15 empty] | 0.043444 | 0.001118 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3487 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018697
1148 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.9.2.5 | ZERO SPEED SWITCH-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-02 | 2020-03-17 18:00 | 2020-08-09 | 2020-10-29 18:00 |  |  | 2020-08-09 13:16 | 2020-10-29 13:00 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3488 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018698
1149 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.9.2.5 | CHUTE BLOCK SWITCH-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-01 09:00 | 2020-03-16 18:00 | 2020-02-01 09:00 | 2020-07-15 18:00 |  |  | 2020-02-11 21:31 | 2020-07-15 21:31 |  |  | 100 | 100 | [15 empty] | 0.0039495 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3489 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018699
1150 | Task(Task)-->P (Procurement) | MANUFACTURING & RECEIPT AT SITE (MRN) | 1.9.2.6 | 1.9.2 | MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-17 09:00 | 2021-03-31 18:00 | 2020-06-27 09:00 | 2022-02-22 18:00 |  |  | 2020-07-15 21:37 |  |  |  | 54.5665 | 0.17537 | [15 empty] | 59.9993 | 10.2979 | 1012.74 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3490 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018700
1151 | Task(Task)-->P (Procurement) | Pulley |  | 1.9.2.6 | Pulley-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-03 09:00 | 2021-03-31 18:00 | 2020-07-16 09:00 | 2021-03-31 18:00 | [6 empty] | 53.3113 | 0 | [15 empty] | 4.318 | 0.44466 | 43.73 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3491 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018701
1152 | Task(Task)-->P (Procurement) | Idler |  | 1.9.2.6 | Idler-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-02 09:00 | 2021-03-28 23:59 | 2020-11-16 09:00 | 2021-10-12 18:00 | [6 empty] | 58.3082 | 0 | [15 empty] | 16.2559 | 1.674 | 164.63 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3492 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018702
1153 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.9.2.6 | Plummer Block-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-31 09:00 | 2021-02-01 18:00 | 2020-09-28 09:00 | 2021-03-15 18:00 | [6 empty] | 46.4516 | 0 | [15 empty] | 0.34955 | 0.035996 | 3.54 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3493 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018703
1154 | Task(Task)-->P (Procurement) | Bearing |  | 1.9.2.6 | Bearing-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-26 09:00 | 2021-01-22 18:00 | 2020-08-22 09:00 | 2021-03-31 18:00 | [6 empty] | 51.3333 | 0 | [15 empty] | 0.78302 | 0.080635 | 7.93 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3494 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018704
1155 | Task(Task)-->P (Procurement) | Belting |  | 1.9.2.6 | Belting-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-21 09:00 | 2021-03-31 18:00 | 2020-11-16 09:00 | 2021-07-27 18:00 | [6 empty] | 44.4882 | 0 | [15 empty] | 28.9413 | 2.9804 | 293.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3495 | 0 | 4 | High | [7 empty] | 0 | 0 | [246 empty] | 1018705
1156 | Task(Task)-->P (Procurement) | Scrapper |  | 1.9.2.6 | Scrapper-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-15 09:00 | 2020-12-11 18:00 | 2020-07-30 09:00 | 2020-12-31 18:00 | [6 empty] | 82.7778 | 0 | [15 empty] | 0.021723 | 0.002237 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3496 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018706
1157 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.9.2.6 | Technological Structure-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-19 09:00 | 2021-03-15 18:00 | 2020-07-06 09:00 | 2021-01-31 23:59 | [6 empty] | 53.7037 | 0 | [15 empty] | 1.5009 | 0.15456 | 15.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3497 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018707
1158 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.9.2.6 | Takeup Component-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-09-02 09:00 | 2021-01-29 18:00 | 2021-01-15 09:00 | 2021-06-13 23:59 | [6 empty] | 46.6667 | 0 | [15 empty] | 0.53814 | 0.055418 | 5.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3498 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018708
1159 | Task(Task)-->P (Procurement) | Gear Box |  | 1.9.2.6 | Gear Box-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-20 09:00 | 2021-02-20 18:00 | 2020-11-17 09:00 | 2021-05-20 18:00 | [6 empty] | 44.8649 | 0 | [15 empty] | 2.6957 | 0.2776 | 27.3 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3499 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018709
1160 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.9.2.6 | Geared Coupling-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-18 09:00 | 2020-12-15 18:00 | 2020-09-02 09:00 | 2021-02-09 18:00 |  |  | 2020-09-02 17:44 |  |  |  | 80.663 | 30 | [15 empty] | 0.58455 | 0.060197 | 5.92 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3500 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018710
1161 | Task(Task)-->P (Procurement) | Brake |  | 1.9.2.6 | Brake-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-05 | 2021-02-10 18:00 | 2020-10-12 09:00 | 2021-02-10 18:00 | [6 empty] | 58.371 | 0 | [15 empty] | 0.18169 | 0.01871 | 1.84 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3501 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018711
1162 | Task(Task)-->P (Procurement) | Maintenance Trolley |  | 1.9.2.6 | Maintenance Trolley-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-18 09:00 | 2021-03-26 18:00 | 2021-02-14 | 2022-02-22 18:00 | [6 empty] | 63.6364 | 0 | [15 empty] | 0.37028 | 0.038131 | 3.75 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3502 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018712
1163 | Task(Task)-->P (Procurement) | Building Structure |  | 1.9.2.6 | Building Structure-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-04 09:00 | 2021-03-19 18:00 | 2020-06-27 09:00 | 2021-03-31 18:00 | [6 empty] | 59.6875 | 0 | [15 empty] | 32.651 | 3.3624 | 330.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3503 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018713
1164 | Task(Task)-->P (Procurement) | 6.6KV HT VFD with Motors |  | 1.9.2.6 | 6.6KV HT VFD with Motors-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-14 09:00 | 2021-03-09 18:00 | 2020-11-11 09:00 | 2021-09-06 18:00 | [6 empty] | 60.3333 | 0 | [15 empty] | 9.9107 | 1.0206 | 100.37 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3504 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018714
1165 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.9.2.6 | LIGHT & LIGHT FIXTURES-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-26 09:00 | 2021-02-18 18:00 | 2020-11-17 09:00 | 2021-08-12 18:00 | [6 empty] | 62.8253 | 0 | [15 empty] | 0.31499 | 0.032437 | 3.19 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3505 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018715
1166 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.9.2.6 | LIGHTING POLES-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-10 09:00 | 2020-11-07 18:00 | 2020-09-09 09:00 | 2020-12-07 18:00 |  |  | 2020-08-07 15:00 |  |  |  | 100 | 0 | [15 empty] | 0.14318 | 0.014744 | 1.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3506 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018716
1167 | Task(Task)-->P (Procurement) | WELDING DISTRIBUTION BOARD |  | 1.9.2.6 | WELDING DISTRIBUTION BOARD-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-29 09:00 | 2020-09-26 18:00 | 2020-07-18 09:00 | 2020-12-15 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.39398 | 0.040572 | 3.99 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3507 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018717
1168 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.9.2.6 | CONVEYOR BELT PROTECTION SWITCHES-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-22 | 2020-07-05 23:59 | 2020-12-01 09:00 | 2021-03-16 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.041472 | 0.004271 | 0.42 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3509 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018718
1169 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.9.2.6 | ZERO SPEED SWITCH-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-18 09:00 | 2020-07-27 18:00 | 2020-10-30 09:00 | 2021-03-10 18:00 |  |  | 2020-10-29 13:03 |  |  |  | 100 | 0 | [15 empty] | 0.00098742 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3510 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018719
1170 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.9.2.6 | CHUTE BLOCK SWITCH-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-17 09:00 | 2020-07-31 18:00 | 2020-07-02 09:00 | 2020-11-15 23:59 |  |  | 2020-07-15 21:37 |  |  |  | 100 | 0 | [15 empty] | 0.0029623 | 0.000305 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3511 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018720
1171 | Task(Task)-->C (Construction) | CONSTRUCTION | 1.9.3 | 1.9 | CONSTRUCTION-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-30 09:00 | 2021-09-13 18:00 | 2020-08-01 09:00 | 2022-05-06 18:00 | [6 empty] | 28.0547 | 0 | [15 empty] | 23.7815 | 5.4778 | 538.7 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3512 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018721
1172 | Task(Task)-->C (Construction) | CIVIL | 1.9.3.1 | 1.9.3 | CIVIL-->CONSTRUCTION-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-30 09:00 | 2021-04-02 18:00 | 2020-08-01 09:00 | 2021-06-25 18:00 | [6 empty] | 49.1911 | 0 | [15 empty] | 25.0782 | 1.3737 | 134.71 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3513 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018722
1173 | Task(Task)-->C (Construction) | AVAILABILITY OF FRONT BY NTPC |  | 1.9.3.1 | AVAILABILITY OF FRONT BY NTPC-->CIVIL-->CONSTRUCTION-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-30 09:00 | 2020-05-30 18:00 | 2020-08-01 09:00 | 2020-08-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3514 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018723
1174 | Task(Task)-->C (Construction) | APPROACH IN PIPE CONVEYOR CORRIDOR |  | 1.9.3.1 | APPROACH IN PIPE CONVEYOR CORRIDOR-->CIVIL-->CONSTRUCTION-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-31 | 2021-02-14 23:59 | 2020-08-02 | 2021-04-18 23:59 | [6 empty] | 63.0769 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5609 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018724
1175 | Task(Task)-->C (Construction) | EXCAVATION |  | 1.9.3.1 | EXCAVATION-->CIVIL-->CONSTRUCTION-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-29 09:00 | 2021-03-15 18:00 | 2020-08-05 09:00 | 2021-04-21 18:00 | [6 empty] | 51.9231 | 0 | [15 empty] | 9.6875 | 0.13308 | 13.05 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 48921 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3515 | 0 | 4 | Low | Niharendu Kamle | [6 empty] | 0 | 0 | [222 empty] | Excavation | [23 empty] | 1018725
1176 | Task(Task)-->C (Construction) | PCC |  | 1.9.3.1 | PCC-->CIVIL-->CONSTRUCTION-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-02 09:00 | 2021-03-18 18:00 | 2020-09-24 09:00 | 2021-06-10 18:00 | [6 empty] | 50.7692 | 0 | [15 empty] | 5.8348 | 0.080154 | 7.86 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 870 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3516 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | PCC | [23 empty] | 1018726
1177 | Task(Task)-->C (Construction) | FOUNDATIONS - RAFT |  | 1.9.3.1 | FOUNDATIONS - RAFT-->CIVIL-->CONSTRUCTION-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-03 09:00 | 2021-03-19 18:00 | 2020-09-25 09:00 | 2021-06-11 18:00 | [6 empty] | 50.3846 | 0 | [15 empty] | 59.127 | 0.81224 | 79.65 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 3002 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3517 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018727
1178 | Task(Task)-->C (Construction) | PADESTALS FOR PC-1A & PC-1B CONV. STR. |  | 1.9.3.1 | PADESTALS FOR PC-1A & PC-1B CONV. STR.-->CIVIL-->CONSTRUCTION-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-17 09:00 | 2021-04-02 18:00 | 2020-10-09 09:00 | 2021-06-25 18:00 | [6 empty] | 45 | 0 | [15 empty] | 25.3508 | 0.34825 | 34.15 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 1287 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3518 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018728
1179 | Task(Task)-->C (Construction) | STRUCTURAL WORKS | 1.9.3.2 | 1.9.3 | STRUCTURAL WORKS-->CONSTRUCTION-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-14 09:00 | 2021-04-30 18:00 | 2020-11-06 09:00 | 2021-07-23 18:00 | [6 empty] | 34.2308 | 0 | [15 empty] | 45.9193 | 2.5154 | 246.66 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3519 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018729
1180 | Task(Task)-->C (Construction) | ERECTION OF STRUCTURAL STEEL |  | 1.9.3.2 | ERECTION OF STRUCTURAL STEEL-->STRUCTURAL WORKS-->CONSTRUCTION-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-14 09:00 | 2021-04-30 18:00 | 2020-11-06 09:00 | 2021-07-23 18:00 | [6 empty] | 34.2308 | 0 | [15 empty] | 100 | 2.5154 | 246.66 | Plan & Actual | Quantity | Metric Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 3813 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3520 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018730
1181 | Task(Task)-->C (Construction) | MECHANICAL EQUIPMENT WORKS | 1.9.3.3 | 1.9.3 | MECHANICAL EQUIPMENT WORKS-->CONSTRUCTION-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-03-06 09:00 | 2021-06-04 18:00 | 2021-05-29 09:00 | 2021-10-06 18:00 | [6 empty] | 0 | 0 | [15 empty] | 8.7907 | 0.48153 | 47.22 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5463 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018731
1182 | Task(Task)-->C (Construction) | ERECTION OF TECHNOLOGICAL STR. & IDLERS |  | 1.9.3.3 | ERECTION OF TECHNOLOGICAL STR. & IDLERS-->MECHANICAL EQUIPMENT WORKS-->CONSTRUCTION-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-03-06 09:00 | 2021-05-14 18:00 | 2021-05-29 09:00 | 2021-08-06 18:00 | [6 empty] | 0 | 0 | [15 empty] | 60.0042 | 0.28894 | 28.34 | Plan & Actual | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3521 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018732
1183 | Task(Task)-->C (Construction) | ERECTION OF PULLEYS WITH FRAME |  | 1.9.3.3 | ERECTION OF PULLEYS WITH FRAME-->MECHANICAL EQUIPMENT WORKS-->CONSTRUCTION-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-04-01 09:00 | 2021-04-21 18:00 | 2021-07-14 09:00 | 2021-08-03 18:00 | [6 empty] | 0 | 0 | [15 empty] | 10.3536 | 0.049856 | 4.89 | Plan & Actual | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5429 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018733
1184 | Task(Task)-->C (Construction) | ERECTION OF DRIVES (MOTOR, GEAR BOX, COUPLING) |  | 1.9.3.3 | ERECTION OF DRIVES (MOTOR, GEAR BOX, COUPLING)-->MECHANICAL EQUIPMENT WORKS-->CONSTRUCTION-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-03-10 09:00 | 2021-04-08 18:00 | 2021-09-07 09:00 | 2021-10-06 18:00 | [6 empty] | 0 | 0 | [15 empty] | 11.751 | 0.056585 | 5.55 | Plan & Actual | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5427 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018734
1185 | Task(Task)-->C (Construction) | ERECTION OF TAKE-UP COMPONENTS |  | 1.9.3.3 | ERECTION OF TAKE-UP COMPONENTS-->MECHANICAL EQUIPMENT WORKS-->CONSTRUCTION-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-05-01 09:00 | 2021-06-04 18:00 | 2021-07-24 09:00 | 2021-08-27 18:00 | [6 empty] | 0 | 0 | [15 empty] | 17.8912 | 0.086152 | 8.45 | Plan & Actual | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5428 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018735
1186 | Task(Task)-->C (Construction) | BELT LAYING & JOINTING WORK |  | 1.9.3 | BELT LAYING & JOINTING WORK-->CONSTRUCTION-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-04-06 09:00 | 2021-08-03 18:00 | 2021-07-28 09:00 | 2021-11-24 18:00 | [6 empty] | 0 | 0 | [15 empty] | 8.8875 | 0.48684 | 47.74 | Plan & Actual | Quantity | Meter | 0 | 0 | 0 | 0 | 0 | 0 | 16400 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3522 | 0 | 3 | High | [7 empty] | 0 | 0 | [246 empty] | 1018736
1187 | Task(Task)-->C (Construction) | MAINTENANCE TROLLEY |  | 1.9.3 | MAINTENANCE TROLLEY-->CONSTRUCTION-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-05-01 09:00 | 2021-05-14 18:00 | 2022-02-23 09:00 | 2022-03-08 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0.053988 | 0.002957 | 0.29 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5475 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018737
1188 | Task(Task)-->C (Construction) | ELECTRICAL & INSTRUMENTATION | 1.9.3.6 | 1.9.3 | ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-03-30 09:00 | 2021-08-30 18:00 | 2021-06-22 09:00 | 2022-04-22 18:00 | [6 empty] | 0 | 0 | [15 empty] | 11.2704 | 0.61737 | 60.54 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3523 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018738
1189 | Task(Task)-->C (Construction) | CABLE TRAY |  | 1.9.3.6 | CABLE TRAY-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-04-13 09:00 | 2021-05-14 18:00 | 2021-07-06 09:00 | 2021-08-06 18:00 | [6 empty] | 0 | 0 | [15 empty] | 22.0185 | 0.13594 | 13.33 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 31200 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3524 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018739
1190 | Task(Task)-->C (Construction) | POWER CABLE |  | 1.9.3.6 | POWER CABLE-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-05-15 09:00 | 2021-05-31 18:00 | 2021-09-27 09:00 | 2021-10-13 18:00 | [6 empty] | 0 | 0 | [15 empty] | 16.0555 | 0.099121 | 9.72 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 68645 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3525 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018740
1191 | Task(Task)-->C (Construction) | CONTROL CABLE |  | 1.9.3.6 | CONTROL CABLE-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-05-29 09:00 | 2021-05-31 18:00 | 2021-10-26 09:00 | 2021-10-28 18:00 | [6 empty] | 0 | 0 | [15 empty] | 5.3023 | 0.032734 | 3.21 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 22700 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3526 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018741
1192 | Task(Task)-->C (Construction) | EARTHING |  | 1.9.3.6 | EARTHING-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-04-21 09:00 | 2021-05-14 18:00 | 2021-07-14 09:00 | 2021-08-06 18:00 | [6 empty] | 0 | 0 | [15 empty] | 8.6224 | 0.053232 | 5.22 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 23400 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3527 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018742
1193 | Task(Task)-->C (Construction) | EARTH PIT |  | 1.9.3.6 | EARTH PIT-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-03-30 09:00 | 2021-04-02 18:00 | 2021-06-22 09:00 | 2021-06-25 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5313 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018743
1194 | Task(Task)-->C (Construction) | FIELD INTRUMENTS |  | 1.9.3.6 | FIELD INTRUMENTS-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-05-30 | 2021-06-01 18:00 | 2021-10-27 09:00 | 2021-10-29 18:00 | [6 empty] | 0 | 0 | [15 empty] | 45.1437 | 0.2787 | 27.33 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5315 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018744
1195 | Task(Task)-->C (Construction) | MOTOR TERMINATION |  | 1.9.3.6 | MOTOR TERMINATION-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-05-29 09:00 | 2021-06-01 18:00 | 2021-10-11 09:00 | 2021-10-14 18:00 | [6 empty] | 0 | 0 | [15 empty] | 2.1308 | 0.013155 | 1.29 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5316 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018745
1196 | Task(Task)-->C (Construction) | NO LOAD RUN OF MOTOR |  | 1.9.3.6 | NO LOAD RUN OF MOTOR-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-08-27 09:00 | 2021-08-30 18:00 | 2022-04-19 09:00 | 2022-04-22 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0.72679 | 0.004487 | 0.44 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5464 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018746
1197 | Task(Task)-->C (Construction) | NO LOAD COMMISSIONING & SYSTEM READYNESS FOR LOAD & TRIAL OPERATION |  | 1.9.3 | NO LOAD COMMISSIONING & SYSTEM READYNESS FOR LOAD & TRIAL OPERATION-->CONSTRUCTION-->PIPE CONVEYOR PC 1A & PC 1B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-08-31 09:00 | 2021-09-13 18:00 | 2022-04-23 09:00 | 2022-05-06 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5317 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018747
1198 | Task(Task)-->E (Engineering) | KDTP-3 & DRIVE HOUSE-2 | 1.10 | 1 | KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-11-22 18:00 | 2021-09-08 18:00 | 2020-03-11 09:00 | 2022-04-06 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 66.5169 | 6.7656 | [15 empty] | 2.0178 | 2.0178 | 198.44 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3528 | 0 | 1 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018748
1199 | Task(Task)-->E (Engineering) | ENGINEERING | 1.10.1 | 1.10 | ENGINEERING-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-11-22 18:00 | 2020-07-14 17:40 | 2020-04-15 18:00 | 2020-11-15 23:59 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 90.8421 | [15 empty] | 2.575 | 0.051958 | 5.11 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3529 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018749
1200 | Task(Task)-->E (Engineering) | MECHANICAL | 1.10.1.1 | 1.10.1 | MECHANICAL-->ENGINEERING-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-11-22 18:00 | 2020-01-25 17:40 | 2020-04-15 18:00 | 2020-06-04 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 80 | [15 empty] | 8.3984 | 0.004364 | 0.43 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3530 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036098
1201 | Task(Task)-->E (Engineering) | G.A & LOAD DATA OF TRANSFER POINT KDTP-3 |  | 1.10.1.1 | G.A & LOAD DATA OF TRANSFER POINT KDTP-3-->MECHANICAL-->ENGINEERING-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-11-22 18:00 | 2020-01-25 17:40 | 2020-04-15 18:00 | 2020-06-04 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-0011 |  | 2020-02-13 10:26 | 7012-155-PVM-B-011 |  |  |  | A |  |  |  | 100 | 0.004364 | 0.43 | Plan & Actual | Date |  | 0 | 0 | 0 | 160 | 0 | 104 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3531 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-11-22 18:00 | 2020-04-15 18:00 |  | 10 | 2020-04-15 23:31 |  |  | 2019-12-18 17:40 | 2020-04-20 18:00 |  | 30 | 2020-04-22 23:31 |  |  | 2019-12-24 17:40 | 2020-04-23 18:00 |  | 35 | 2020-04-25 23:31 |  |  | 2019-12-30 23:59 | 2020-04-30 18:00 |  | 65 | 2020-05-02 23:31 |  |  | 2020-01-04 17:40 | 2020-05-21 18:00 |  | 80 | 2020-05-21 23:31 | [5 empty] | 80 | 2020-10-22 15:29 | [5 empty] | 80 | 2020-10-22 15:29 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-01-25 17:40 | 2020-06-04 18:00 |  | 100 | [122 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 11 |  |  |  |  | 101025
1202 | Task(Task)-->E (Engineering) | CIVIL | 1.10.1.2 | 1.10.1 | CIVIL-->ENGINEERING-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-02-07 18:00 | 2020-05-30 17:40 | 2020-07-04 18:00 | 2020-11-15 23:59 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 96.4183 | [15 empty] | 47.6562 | 0.024761 | 2.44 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3537 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036099
1203 | Task(Task)-->E (Engineering) | TRANSFER POINT KDTP-3 - DESIGN CALCULATION OF SUPER STRUCTURE |  | 1.10.1.2 | TRANSFER POINT KDTP-3 - DESIGN CALCULATION OF SUPER STRUCTURE-->CIVIL-->ENGINEERING-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-07 18:00 | 2020-04-07 17:40 | 2020-08-07 09:00 | 2020-09-01 18:00 |  |  | 2020-02-21 15:37 | 2020-09-02 00:38 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-DC-0012 |  | 2020-02-13 11:41 | 7012-155-PVC-U-034 |  |  |  | A |  |  |  | 47.4419 | 0.011747 | 1.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 377.29 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3541 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-07 18:00 | 2020-04-30 18:00 |  | 10 |  |  |  | 2020-02-26 17:40 | 2020-05-20 18:00 |  | 30 |  |  |  | 2020-03-03 17:40 | 2020-05-23 18:00 |  | 35 |  |  |  | 2020-03-09 23:59 | 2020-05-30 18:00 |  | 65 | 2020-08-13 19:54 |  |  | 2020-03-16 17:40 | 2020-06-20 18:00 |  | 80 | 2020-09-01 23:24 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-07 17:40 | 2020-07-04 18:00 |  | 100 | 2020-09-02 00:39 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 135 |  |  |  |  | 101149
1204 | Task(Task)-->E (Engineering) | TRANSFER POINT KDTP-3 - DESIGN CALCULATION OF SUB STRUCTURE |  | 1.10.1.2 | TRANSFER POINT KDTP-3 - DESIGN CALCULATION OF SUB STRUCTURE-->CIVIL-->ENGINEERING-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-13 18:00 | 2020-05-12 17:40 | 2020-08-18 09:00 | 2020-09-08 18:00 |  |  | 2020-02-21 15:37 | 2020-09-10 23:14 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-DC-0013 |  | 2020-02-13 11:41 | 7012-155-PVC-U-035 |  |  |  | A |  |  |  | 26.5116 | 0.006565 | 0.57 | Plan & Actual | Date |  | 0 | 0 | 0 | 212.29 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3542 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-13 18:00 | 2020-05-30 18:00 |  | 10 |  |  |  | 2020-03-31 17:40 | 2020-06-19 18:00 |  | 30 |  |  |  | 2020-04-06 17:40 | 2020-06-22 18:00 |  | 35 |  |  |  | 2020-04-13 23:59 | 2020-06-29 18:00 |  | 65 | 2020-08-18 18:00 |  |  | 2020-04-18 17:40 | 2020-07-20 18:00 |  | 80 | 2020-09-10 22:45 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-12 17:40 | 2020-08-03 18:00 |  | 100 | 2020-09-10 23:15 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 136 |  |  |  |  | 101150
1205 | Task(Task)-->E (Engineering) | TRANSFER POINT KDTP-3 - NUM & RC DETAILS OF FDN |  | 1.10.1.2 | TRANSFER POINT KDTP-3 - NUM & RC DETAILS OF FDN-->CIVIL-->ENGINEERING-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-13 18:00 | 2020-05-12 17:40 | 2020-08-18 09:00 | 2020-09-09 18:00 |  |  | 2020-02-21 15:37 | 2020-09-10 23:14 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-NR-0014 |  | 2020-02-13 11:41 | 7012-155-PVC-C-037 |  |  |  | A |  |  |  | 15.814 | 0.003916 | 0.34 | Plan & Actual | Date |  | 0 | 0 | 0 | 127.29 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3538 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-13 18:00 | 2020-05-30 18:00 |  | 10 |  |  |  | 2020-03-31 17:40 | 2020-06-19 18:00 |  | 30 |  |  |  | 2020-04-06 17:40 | 2020-06-22 18:00 |  | 35 | 2020-08-17 18:46 |  |  | 2020-04-13 23:59 | 2020-06-29 18:00 |  | 65 | 2020-08-18 18:00 |  |  | 2020-04-18 17:40 | 2020-07-20 18:00 |  | 80 | 2020-09-10 22:41 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-12 17:40 | 2020-08-03 18:00 |  | 100 | 2020-09-10 23:15 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 138 |  |  |  |  | 101152
1206 | Task(Task)-->E (Engineering) | TRANSFER POINT KDTP-3 - NUM & RC DETAILS OF FLOOR SLABS |  | 1.10.1.2 | TRANSFER POINT KDTP-3 - NUM & RC DETAILS OF FLOOR SLABS-->CIVIL-->ENGINEERING-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-31 18:00 | 2020-05-30 17:40 | 2020-07-04 18:00 | 2020-11-15 23:59 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-NR-0015 |  | 2020-02-13 11:41 | 7012-155-PVC-C-038 |  |  |  | A |  |  |  | 5.1163 | 0.001267 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 42.3 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3539 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-31 18:00 | 2020-07-04 18:00 |  | 10 |  |  |  | 2020-04-18 17:40 | 2020-07-24 18:00 |  | 30 |  |  |  | 2020-04-24 17:40 | 2020-07-27 18:00 |  | 35 | 2020-10-22 16:19 |  |  | 2020-05-01 23:59 | 2020-08-03 18:00 |  | 65 | 2020-10-22 23:07 |  |  | 2020-05-07 17:40 | 2020-08-24 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-30 17:40 | 2020-09-07 18:00 |  | 100 | [122 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 139 |  |  |  |  | 101153
1207 | Task(Task)-->E (Engineering) | TRANSFER POINT KDTP-3 - NUM & RC DETAILS OF GRADE SLAB |  | 1.10.1.2 | TRANSFER POINT KDTP-3 - NUM & RC DETAILS OF GRADE SLAB-->CIVIL-->ENGINEERING-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-31 18:00 | 2020-05-30 17:40 | 2020-07-24 18:00 | 2020-09-27 23:59 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-NR-0016 |  | 2020-02-13 11:41 | 7012-155-PVC-C-039 |  |  |  | A |  |  |  | 5.1163 | 0.001267 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 42.3 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3540 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-31 18:00 | 2020-07-24 18:00 |  | 10 |  |  |  | 2020-04-18 17:40 | 2020-08-13 18:00 |  | 30 |  |  |  | 2020-04-24 17:40 | 2020-08-16 23:59 |  | 35 | 2020-11-04 19:17 |  |  | 2020-05-01 23:59 | 2020-08-23 23:59 |  | 65 | 2020-11-11 11:00 |  |  | 2020-05-07 17:40 | 2020-09-13 23:59 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-30 17:40 | 2020-09-27 23:59 |  | 100 | [122 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 140 |  |  |  |  | 101154
1208 | Task(Task)-->E (Engineering) | STRUCTURAL | 1.10.1.3 | 1.10.1 | STRUCTURAL-->ENGINEERING-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-02-07 18:00 | 2020-07-14 17:40 | 2020-07-09 18:00 | 2020-09-17 18:00 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 93.674 | [15 empty] | 22.0703 | 0.011467 | 1.13 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3543 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036100
1209 | Task(Task)-->E (Engineering) | TRANSFER POINT KDTP-3 - STRUCTURAL GA |  | 1.10.1.3 | TRANSFER POINT KDTP-3 - STRUCTURAL GA-->STRUCTURAL-->ENGINEERING-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-07 18:00 | 2020-04-07 17:40 | 2020-08-07 09:00 | 2020-09-01 18:00 |  |  | 2020-02-21 15:37 | 2020-09-02 00:38 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-GA-0008 |  | 2020-02-13 11:41 | 7012-155-PVC-B-036 |  |  |  | A |  |  |  | 90.2655 | 0.010351 | 1.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 377.29 | 0 | 35.3 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3545 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-07 18:00 | 2020-04-30 18:00 |  | 10 |  |  |  | 2020-02-26 17:40 | 2020-05-20 18:00 |  | 30 |  |  |  | 2020-03-03 17:40 | 2020-05-23 18:00 |  | 35 | 2020-08-06 10:50 |  |  | 2020-03-09 23:59 | 2020-05-30 18:00 |  | 65 | 2020-08-13 19:54 |  |  | 2020-03-16 17:40 | 2020-06-20 18:00 |  | 80 | 2020-09-01 23:25 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-07 17:40 | 2020-07-04 18:00 |  | 100 | 2020-09-02 00:39 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 137 |  |  |  |  | 101151
1210 | Task(Task)-->E (Engineering) | ARCHITECTURAL GA OF TRANSFER POINT KDTP-3 |  | 1.10.1.3 | ARCHITECTURAL GA OF TRANSFER POINT KDTP-3-->STRUCTURAL-->ENGINEERING-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-15 18:00 | 2020-07-14 17:40 | 2020-07-09 18:00 | 2020-09-17 18:00 |  |  | 2020-02-21 15:39 |  |  |  | 100 | 35 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-AR-0005 |  | 2020-02-13 11:43 | 7012-155-PVC-C-111 |  |  |  | I |  |  |  | 9.7345 | 0.001116 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 40.52 | 0 | 114 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3544 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-05-15 18:00 | 2020-07-09 18:00 |  | 10 |  |  |  | 2020-06-02 17:40 | 2020-08-03 18:00 |  | 30 |  |  |  | 2020-06-08 17:40 | 2020-08-06 18:00 |  | 35 | 2020-11-12 10:35 |  |  | 2020-06-15 23:59 | 2020-08-13 18:00 |  | 65 |  |  |  | 2020-06-20 17:40 | 2020-09-03 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-07-14 17:40 | 2020-09-17 18:00 |  | 100 | [122 empty] | Chetan Khodke | [5 empty] | A - Architecture | [16 empty] | 212 |  |  |  |  | 101222
1211 | Task(Task)-->E (Engineering) | ELECTRICAL | 1.10.1.4 | 1.10.1 | ELECTRICAL-->ENGINEERING-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-06 18:00 | 2020-06-02 17:40 | 2020-04-22 18:00 | 2020-06-18 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 | [15 empty] | 21.875 | 0.011366 | 1.12 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3548 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036101
1212 | Task(Task)-->E (Engineering) | EQUIPMENT, CABLE ROUTING, EARTHING & LIGHTNING LAYOUT WITH PLAN, SECTIONAL VIEWS & BOM OF KDTP-3 |  | 1.10.1.4 | EQUIPMENT, CABLE ROUTING, EARTHING & LIGHTNING LAYOUT WITH PLAN, SECTIONAL VIEWS & BOM OF KDTP-3-->ELECTRICAL-->ENGINEERING-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-06 18:00 | 2020-04-03 17:40 | 2020-04-22 18:00 | 2020-06-18 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5056 |  | 2020-02-13 11:44 | 7012-155-PVE-F-018 |  |  |  | A |  |  |  | 40.1786 | 0.004567 | 0.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 165.48 | 0 | 13.45 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3549 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-06 18:00 | 2020-04-22 18:00 |  | 10 | 2020-04-22 23:31 |  |  | 2020-02-21 17:40 | 2020-05-06 18:00 |  | 30 | 2020-06-02 23:31 |  |  | 2020-02-28 17:40 | 2020-05-13 18:00 |  | 35 | 2020-06-19 12:47 |  |  | 2020-03-05 23:59 | 2020-05-20 18:00 |  | 65 | 2020-08-03 11:16 |  |  | 2020-03-11 17:40 | 2020-06-10 18:00 |  | 80 | 2020-08-03 11:27 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-03 17:40 | 2020-06-10 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 253 |  |  |  |  | 101264
1213 | Task(Task)-->E (Engineering) | LIGHTING LAYOUT PLAN WITH POWER DISTRIBUTION ARRANGEMENT, SECTIONAL VIEW, BOM OF KDTP-3 |  | 1.10.1.4 | LIGHTING LAYOUT PLAN WITH POWER DISTRIBUTION ARRANGEMENT, SECTIONAL VIEW, BOM OF KDTP-3-->ELECTRICAL-->ENGINEERING-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-13 18:00 | 2020-06-02 17:40 | 2020-05-07 18:00 | 2020-06-18 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5067 |  | 2020-02-13 11:44 | 7012-155-PVE-G-029 |  |  |  | A |  |  |  | 59.8214 | 0.006799 | 0.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 248.42 | 0 | 24.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3550 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-13 18:00 | 2020-05-07 18:00 |  | 10 | 2020-05-04 23:31 |  |  | 2020-04-21 17:40 | 2020-05-14 18:00 |  | 30 | 2020-05-14 23:31 |  |  | 2020-04-28 17:40 | 2020-05-21 18:00 |  | 35 | 2020-05-21 23:31 |  |  | 2020-05-04 23:59 | 2020-05-28 18:00 |  | 65 | 2020-05-22 23:31 |  |  | 2020-05-11 17:40 | 2020-06-18 18:00 |  | 80 | 2020-06-17 14:58 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-02 17:40 | 2020-06-18 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 264 |  |  |  |  | 101275
1214 | Task(Task)-->P (Procurement) | PROCUREMENT | 1.10.2 | 1.10 | PROCUREMENT-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-02-06 09:00 | 2021-02-13 18:00 | 2020-03-11 09:00 | 2021-06-13 23:59 |  |  | 2020-03-11 10:57 |  |  |  | 94.7562 | 9.1398 | [15 empty] | 48.4303 | 0.97724 | 96.11 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3553 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018754
1215 | Task(Task)-->P (Procurement) | PURCHASE REQUISITION | 1.10.2.1 | 1.10.2 | PURCHASE REQUISITION-->PROCUREMENT-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-02-06 09:00 | 2020-03-27 18:00 | 2020-03-11 09:00 | 2020-05-29 18:00 |  |  | 2020-03-11 10:57 |  |  |  | 100 | 28.397 | [15 empty] | 5.0042 | 0.048903 | 4.81 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3554 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018755
1216 | Task(Task)-->P (Procurement) | Flap Gate |  | 1.10.2.1 | Flap Gate-->PURCHASE REQUISITION-->PROCUREMENT-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-06 09:00 | 2020-02-06 18:00 | 2020-03-20 09:00 | 2020-03-20 18:00 |  |  | 2020-03-20 10:57 | 2020-03-20 10:57 |  |  | 100 | 100 | [15 empty] | 2.8398 | 0.001389 | 0.14 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3555 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018756
1217 | Task(Task)-->P (Procurement) | Chute & Skirt |  | 1.10.2.1 | Chute & Skirt-->PURCHASE REQUISITION-->PROCUREMENT-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-10 09:00 | 2020-03-10 18:00 | 2020-03-11 09:00 | 2020-03-11 18:00 |  |  | 2020-03-11 10:57 | 2020-03-11 10:57 |  |  | 100 | 100 | [15 empty] | 17.6471 | 0.00863 | 0.87 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3556 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018757
1218 | Task(Task)-->P (Procurement) | Building Structure |  | 1.10.2.1 | Building Structure-->PURCHASE REQUISITION-->PROCUREMENT-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-09 09:00 | 2020-03-09 18:00 | 2020-05-29 09:00 | 2020-05-29 18:00 | [6 empty] | 100 | 0 | [15 empty] | 71.6024 | 0.035016 | 3.53 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3557 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018758
1219 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.10.2.1 | LIGHT & LIGHT FIXTURES-->PURCHASE REQUISITION-->PROCUREMENT-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-10 09:00 | 2020-03-10 18:00 | 2020-03-16 09:00 | 2020-03-16 18:00 |  |  | 2020-03-16 10:57 | 2020-03-16 10:57 |  |  | 100 | 100 | [15 empty] | 5.4767 | 0.002678 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3558 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018759
1220 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.10.2.1 | LIGHTING POLES-->PURCHASE REQUISITION-->PROCUREMENT-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-27 09:00 | 2020-03-27 18:00 | 2020-04-30 09:00 | 2020-04-30 18:00 |  |  | 2020-04-30 10:57 | 2020-04-30 10:57 |  |  | 100 | 100 | [15 empty] | 2.4341 | 0.00119 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3559 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018760
1221 | Task(Task)-->P (Procurement) | TECHNICAL CLEARANCE | 1.10.2.2 | 1.10.2 | TECHNICAL CLEARANCE-->PROCUREMENT-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-02-07 09:00 | 2020-05-11 18:00 | 2020-03-11 09:00 | 2020-06-03 18:00 |  |  | 2020-03-17 10:57 |  |  |  | 100 | 28.397 | [15 empty] | 5.0042 | 0.048903 | 4.81 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3562 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018761
1222 | Task(Task)-->P (Procurement) | Flap Gate |  | 1.10.2.2 | Flap Gate-->TECHNICAL CLEARANCE-->PROCUREMENT-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-07 09:00 | 2020-03-22 23:59 | 2020-03-20 09:00 | 2020-04-28 18:00 |  |  | 2020-04-28 10:57 | 2020-04-28 10:57 |  |  | 100 | 100 | [15 empty] | 2.8398 | 0.001389 | 0.14 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3563 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018762
1223 | Task(Task)-->P (Procurement) | Chute & Skirt |  | 1.10.2.2 | Chute & Skirt-->TECHNICAL CLEARANCE-->PROCUREMENT-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-11 09:00 | 2020-03-20 18:00 | 2020-03-11 09:00 | 2020-03-17 18:00 |  |  | 2020-03-17 10:57 | 2020-03-17 10:57 |  |  | 100 | 100 | [15 empty] | 17.6471 | 0.00863 | 0.87 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3564 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018763
1224 | Task(Task)-->P (Procurement) | Building Structure |  | 1.10.2.2 | Building Structure-->TECHNICAL CLEARANCE-->PROCUREMENT-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-10 09:00 | 2020-03-16 18:00 | 2020-05-29 09:00 | 2020-05-29 18:00 | [6 empty] | 100 | 0 | [15 empty] | 71.6024 | 0.035016 | 3.53 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3565 | 1 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018764
1225 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.10.2.2 | LIGHT & LIGHT FIXTURES-->TECHNICAL CLEARANCE-->PROCUREMENT-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-11 09:00 | 2020-03-25 18:00 | 2020-03-16 09:00 | 2020-06-02 18:00 |  |  | 2020-06-02 10:57 | 2020-06-02 10:57 |  |  | 100 | 100 | [15 empty] | 5.4767 | 0.002678 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3566 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018765
1226 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.10.2.2 | LIGHTING POLES-->TECHNICAL CLEARANCE-->PROCUREMENT-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-28 09:00 | 2020-05-11 18:00 | 2020-04-30 09:00 | 2020-06-03 18:00 |  |  | 2020-06-03 10:57 | 2020-06-03 10:57 |  |  | 100 | 100 | [15 empty] | 2.4341 | 0.00119 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3567 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018766
1227 | Task(Task)-->P (Procurement) | ORDERING | 1.10.2.3 | 1.10.2 | ORDERING-->PROCUREMENT-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-03-17 09:00 | 2020-06-25 18:00 | 2020-03-17 09:00 | 2020-08-22 18:00 |  |  | 2020-03-18 12:49 |  |  |  | 100 | 28.3254 | [15 empty] | 9.9979 | 0.097704 | 9.61 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3570 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018767
1228 | Task(Task)-->P (Procurement) | Flap Gate |  | 1.10.2.3 | Flap Gate-->ORDERING-->PROCUREMENT-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-23 09:00 | 2020-04-21 18:00 | 2020-04-28 09:00 | 2020-08-22 18:00 |  |  | 2020-04-28 16:13 | 2020-08-22 16:13 |  |  | 100 | 100 | [15 empty] | 2.9442 | 0.002877 | 0.29 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3571 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018768
1229 | Task(Task)-->P (Procurement) | Chute & Skirt |  | 1.10.2.3 | Chute & Skirt-->ORDERING-->PROCUREMENT-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-21 09:00 | 2020-04-19 23:59 | 2020-03-17 09:00 | 2020-07-06 18:00 |  |  | 2020-03-18 12:49 | 2020-07-06 12:49 |  |  | 100 | 100 | [15 empty] | 17.5635 | 0.01716 | 1.73 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3572 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018769
1230 | Task(Task)-->P (Procurement) | Building Structure |  | 1.10.2.3 | Building Structure-->ORDERING-->PROCUREMENT-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-17 09:00 | 2020-04-15 18:00 | 2020-05-29 09:00 | 2020-07-28 18:00 | [6 empty] | 100 | 0 | [15 empty] | 71.6751 | 0.070029 | 7.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3573 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018770
1231 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.10.2.3 | LIGHT & LIGHT FIXTURES-->ORDERING-->PROCUREMENT-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-26 09:00 | 2020-04-10 18:00 | 2020-06-02 09:00 | 2020-07-31 18:00 |  |  | 2020-06-03 15:51 | 2020-06-29 15:51 |  |  | 100 | 100 | [15 empty] | 5.3807 | 0.005257 | 0.53 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3574 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018771
1232 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.10.2.3 | LIGHTING POLES-->ORDERING-->PROCUREMENT-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-12 09:00 | 2020-06-25 18:00 | 2020-06-03 09:00 | 2020-06-24 18:00 |  |  | 2020-06-15 10:57 | 2020-06-15 10:57 |  |  | 100 | 100 | [15 empty] | 2.4365 | 0.002381 | 0.24 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3575 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018772
1233 | Task(Task)-->P (Procurement) | ITP APPROVAL | 1.10.2.4 | 1.10.2 | ITP APPROVAL-->PROCUREMENT-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-04-11 09:00 | 2020-08-04 18:00 | 2020-06-23 09:00 | 2020-11-30 18:00 |  |  | 2020-06-23 17:42 |  |  |  | 100 | 7.9095 | [15 empty] | 5.0042 | 0.048903 | 4.81 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3578 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018773
1234 | Task(Task)-->P (Procurement) | Flap Gate |  | 1.10.2.4 | Flap Gate-->ITP APPROVAL-->PROCUREMENT-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-22 09:00 | 2020-05-31 23:59 | 2020-08-22 09:00 | 2020-11-30 18:00 |  |  | 2020-08-22 16:16 |  |  |  | 100 | 0 | [15 empty] | 2.8398 | 0.001389 | 0.14 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3579 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018774
1235 | Task(Task)-->P (Procurement) | Chute & Skirt |  | 1.10.2.4 | Chute & Skirt-->ITP APPROVAL-->PROCUREMENT-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-20 09:00 | 2020-05-29 18:00 | 2020-07-06 09:00 | 2020-07-16 18:00 | [6 empty] | 100 | 0 | [15 empty] | 17.6471 | 0.00863 | 0.87 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3580 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018775
1236 | Task(Task)-->P (Procurement) | Building Structure |  | 1.10.2.4 | Building Structure-->ITP APPROVAL-->PROCUREMENT-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-16 09:00 | 2020-04-22 18:00 | 2020-07-28 09:00 | 2020-08-03 18:00 | [6 empty] | 100 | 0 | [15 empty] | 71.6024 | 0.035016 | 3.53 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3581 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018776
1237 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.10.2.4 | LIGHT & LIGHT FIXTURES-->ITP APPROVAL-->PROCUREMENT-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-11 09:00 | 2020-05-20 18:00 | 2020-07-28 09:00 | 2020-09-08 18:00 |  |  | 2020-07-08 17:23 | 2020-09-08 17:23 |  |  | 100 | 100 | [15 empty] | 5.4767 | 0.002678 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3582 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018777
1238 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.10.2.4 | LIGHTING POLES-->ITP APPROVAL-->PROCUREMENT-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-06-26 09:00 | 2020-08-04 18:00 | 2020-06-23 09:00 | 2020-09-08 18:00 |  |  | 2020-06-23 17:42 | 2020-09-08 17:05 |  |  | 100 | 100 | [15 empty] | 2.4341 | 0.00119 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3583 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018778
1239 | Task(Task)-->P (Procurement) | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE | 1.10.2.5 | 1.10.2 | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-04-11 09:00 | 2020-09-16 18:00 | 2020-05-30 09:00 | 2020-11-16 18:00 |  |  | 2020-06-18 17:12 |  |  |  | 100 | 20.4637 | [15 empty] | 15.0021 | 0.14661 | 14.42 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3586 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018779
1240 | Task(Task)-->P (Procurement) | Flap Gate |  | 1.10.2.5 | Flap Gate-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-22 09:00 | 2020-06-20 18:00 | 2020-08-22 09:00 | 2020-11-15 23:59 |  |  | 2020-08-22 16:15 |  |  |  | 100 | 15 | [15 empty] | 2.9093 | 0.004265 | 0.43 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3587 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018780
1241 | Task(Task)-->P (Procurement) | Chute & Skirt |  | 1.10.2.5 | Chute & Skirt-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-20 09:00 | 2020-09-16 18:00 | 2020-07-06 09:00 | 2020-07-06 18:00 |  |  | 2020-07-06 12:51 | 2020-07-06 12:51 |  |  | 100 | 100 | [15 empty] | 17.5913 | 0.02579 | 2.6 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3588 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018781
1242 | Task(Task)-->P (Procurement) | Building Structure |  | 1.10.2.5 | Building Structure-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-14 09:00 | 2020-04-20 18:00 | 2020-07-28 09:00 | 2020-08-25 18:00 | [6 empty] | 100 | 0 | [15 empty] | 71.6509 | 0.10504 | 10.59 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3589 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018782
1243 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.10.2.5 | LIGHT & LIGHT FIXTURES-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-11 09:00 | 2020-05-25 18:00 | 2020-07-10 09:00 | 2020-11-16 18:00 |  |  | 2020-07-14 10:44 |  |  |  | 100 | 0 | [15 empty] | 5.4127 | 0.007935 | 0.8 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3590 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018783
1244 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.10.2.5 | LIGHTING POLES-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-06-26 09:00 | 2020-08-09 23:59 | 2020-05-30 09:00 | 2020-08-08 18:00 |  |  | 2020-06-18 17:12 | 2020-08-07 15:00 |  |  | 100 | 100 | [15 empty] | 2.4357 | 0.003571 | 0.36 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3591 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018784
1245 | Task(Task)-->P (Procurement) | MANUFACTURING & RECEIPT AT SITE (MRN) | 1.10.2.6 | 1.10.2 | MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-23 09:00 | 2021-02-13 18:00 | 2020-07-06 09:00 | 2021-06-13 23:59 |  |  | 2020-08-07 15:02 |  |  |  | 91.2586 | 0 | [15 empty] | 59.9875 | 0.58622 | 57.66 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3594 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018785
1246 | Task(Task)-->P (Procurement) | Flap Gate |  | 1.10.2.6 | Flap Gate-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-21 | 2021-01-01 18:00 | 2020-12-01 09:00 | 2021-06-13 23:59 | [6 empty] | 73.3333 | 0 | [15 empty] | 2.9093 | 0.017055 | 1.72 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3595 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018786
1247 | Task(Task)-->P (Procurement) | Chute & Skirt |  | 1.10.2.6 | Chute & Skirt-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-19 | 2021-02-13 18:00 | 2020-07-06 09:00 | 2021-01-31 23:59 | [6 empty] | 54.7619 | 0 | [15 empty] | 17.6083 | 0.10322 | 10.41 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3596 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018787
1248 | Task(Task)-->P (Procurement) | Building Structure |  | 1.10.2.6 | Building Structure-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-23 09:00 | 2020-10-05 18:00 | 2020-08-25 09:00 | 2021-03-31 18:00 | [6 empty] | 100 | 0 | [15 empty] | 71.634 | 0.41993 | 42.35 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3597 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018788
1249 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.10.2.6 | LIGHT & LIGHT FIXTURES-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-26 09:00 | 2020-10-21 18:00 | 2020-11-17 09:00 | 2021-04-14 18:00 | [6 empty] | 100 | 0 | [15 empty] | 5.3958 | 0.031631 | 3.19 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3598 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018789
1250 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.10.2.6 | LIGHTING POLES-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-10 09:00 | 2020-11-07 18:00 | 2020-09-09 09:00 | 2020-12-07 18:00 |  |  | 2020-08-07 15:02 |  |  |  | 100 | 0 | [15 empty] | 2.4526 | 0.014378 | 1.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3599 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018790
1251 | Task(Task)-->C (Construction) | CONSTRUCTION | 1.10.3 | 1.10 | CONSTRUCTION-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-27 09:00 | 2021-09-08 18:00 | 2020-09-03 09:00 | 2022-04-06 18:00 | [6 empty] | 36.843 | 0 | [15 empty] | 48.9947 | 0.98863 | 97.23 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3602 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018791
1252 | Task(Task)-->C (Construction) | CIVIL | 1.10.3.1 | 1.10.3 | CIVIL-->CONSTRUCTION-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-27 09:00 | 2021-05-05 18:00 | 2020-09-03 09:00 | 2021-09-28 18:00 | [6 empty] | 35.2504 | 0 | [15 empty] | 44.7645 | 0.44255 | 43.52 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3603 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018792
1253 | Task(Task)-->C (Construction) | AVAILABILITY OF FRONT BY NTPC |  | 1.10.3.1 | AVAILABILITY OF FRONT BY NTPC-->CIVIL-->CONSTRUCTION-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-27 09:00 | 2020-04-27 18:00 | 2020-09-03 09:00 | 2020-09-03 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3604 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018793
1254 | Task(Task)-->C (Construction) | EXCAVATION |  | 1.10.3.1 | EXCAVATION-->CIVIL-->CONSTRUCTION-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-04 09:00 | 2020-06-03 18:00 | 2020-09-10 09:00 | 2020-10-10 18:00 | [6 empty] | 100 | 0 | [15 empty] | 5.7228 | 0.025327 | 2.49 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 9335 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3605 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | Excavation | [23 empty] | 1018794
1255 | Task(Task)-->C (Construction) | PCC |  | 1.10.3.1 | PCC-->CIVIL-->CONSTRUCTION-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-25 09:00 | 2020-05-29 18:00 | 2020-10-01 09:00 | 2020-10-05 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.85038 | 0.003763 | 0.37 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3606 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | PCC | [23 empty] | 1018795
1256 | Task(Task)-->C (Construction) | RAFT |  | 1.10.3.1 | RAFT-->CIVIL-->CONSTRUCTION-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-30 09:00 | 2020-06-14 23:59 | 2020-10-06 09:00 | 2020-10-21 18:00 | [6 empty] | 100 | 0 | [15 empty] | 15.7895 | 0.069877 | 6.87 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 259 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3607 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018796
1257 | Task(Task)-->C (Construction) | PADESTALS FOR KDTP-3 STR. |  | 1.10.3.1 | PADESTALS FOR KDTP-3 STR.-->CIVIL-->CONSTRUCTION-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-15 09:00 | 2020-07-10 18:00 | 2020-10-22 09:00 | 2020-11-16 18:00 | [6 empty] | 100 | 0 | [15 empty] | 3.6543 | 0.016172 | 1.59 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3608 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018797
1258 | Task(Task)-->C (Construction) | RCC FLOOR FOR TAIL PULLEY OF SY-1A/B |  | 1.10.3.1 | RCC FLOOR FOR TAIL PULLEY OF SY-1A/B-->CIVIL-->CONSTRUCTION-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-11-06 09:00 | 2020-11-21 18:00 | 2021-03-15 09:00 | 2021-03-30 18:00 | [6 empty] | 31.25 | 0 | [15 empty] | 3.9531 | 0.017495 | 1.72 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3610 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018798
1259 | Task(Task)-->C (Construction) | RCC FLOOR FOR HEAD PULLEY OF PC-2A/B |  | 1.10.3.1 | RCC FLOOR FOR HEAD PULLEY OF PC-2A/B-->CIVIL-->CONSTRUCTION-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-02-04 09:00 | 2021-02-22 18:00 | 2021-06-30 09:00 | 2021-07-18 23:59 | [6 empty] | 0 | 0 | [15 empty] | 3.9531 | 0.017495 | 1.72 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3611 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018799
1260 | Task(Task)-->C (Construction) | DRIVE HOUSE FOUNDATION |  | 1.10.3.1 | DRIVE HOUSE FOUNDATION-->CIVIL-->CONSTRUCTION-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-13 09:00 | 2020-07-13 18:00 | 2020-10-20 09:00 | 2020-11-19 18:00 | [6 empty] | 100 | 0 | [15 empty] | 3.4245 | 0.015155 | 1.49 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3612 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018800
1261 | Task(Task)-->C (Construction) | HGTU FOUNDATION OF PC-2A/B |  | 1.10.3.1 | HGTU FOUNDATION OF PC-2A/B-->CIVIL-->CONSTRUCTION-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-27 09:00 | 2020-07-27 18:00 | 2020-11-03 09:00 | 2020-12-03 18:00 | [6 empty] | 100 | 0 | [15 empty] | 4.5737 | 0.020241 | 1.99 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5470 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018801
1262 | Task(Task)-->C (Construction) | GRADE SLAB FLOOR |  | 1.10.3.1 | GRADE SLAB FLOOR-->CIVIL-->CONSTRUCTION-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-04-05 09:00 | 2021-05-05 18:00 | 2021-08-29 | 2021-09-28 18:00 | [6 empty] | 0 | 0 | [15 empty] | 58.0786 | 0.25703 | 25.27 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 1350 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3613 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018802
1263 | Task(Task)-->C (Construction) | STRUCTURAL WORKS | 1.10.3.2 | 1.10.3 | STRUCTURAL WORKS-->CONSTRUCTION-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-08 09:00 | 2021-04-04 23:59 | 2020-12-15 09:00 | 2021-08-28 18:00 | [6 empty] | 49.523 | 0 | [15 empty] | 42.5324 | 0.42049 | 41.35 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3614 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018803
1264 | Task(Task)-->C (Construction) | STRUCTURAL WORKS FOR TAIL PULLEY FLOOR OF SY-1A/B |  | 1.10.3.2 | STRUCTURAL WORKS FOR TAIL PULLEY FLOOR OF SY-1A/B-->STRUCTURAL WORKS-->CONSTRUCTION-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-08 09:00 | 2020-11-05 18:00 | 2020-12-15 09:00 | 2021-03-14 23:59 | [6 empty] | 100 | 0 | [15 empty] | 46.9166 | 0.19728 | 19.4 | Plan & Actual | Quantity | Metric Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3615 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018804
1265 | Task(Task)-->C (Construction) | STRUCTURAL WORKS FOR HEAD PULLEY FLOOR OF PCN-2A/B |  | 1.10.3.2 | STRUCTURAL WORKS FOR HEAD PULLEY FLOOR OF PCN-2A/B-->STRUCTURAL WORKS-->CONSTRUCTION-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-11-06 09:00 | 2021-02-03 18:00 | 2021-04-01 09:00 | 2021-06-29 18:00 | [6 empty] | 5.5556 | 0 | [15 empty] | 46.9166 | 0.19728 | 19.4 | Plan & Actual | Quantity | Metric Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5466 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018805
1266 | Task(Task)-->C (Construction) | BALANCE STRUCTURAL WORKS |  | 1.10.3.2 | BALANCE STRUCTURAL WORKS-->STRUCTURAL WORKS-->CONSTRUCTION-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-02-04 09:00 | 2021-04-04 23:59 | 2021-06-30 09:00 | 2021-08-28 18:00 | [6 empty] | 0 | 0 | [15 empty] | 6.1669 | 0.025931 | 2.55 | Plan & Actual | Quantity | Metric Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5467 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018806
1267 | Task(Task)-->C (Construction) | MECHANICAL EQUIPMENT WORKS | 1.10.3.3 | 1.10.3 | MECHANICAL EQUIPMENT WORKS-->CONSTRUCTION-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-03-23 09:00 | 2021-06-20 23:59 | 2021-08-16 09:00 | 2021-11-13 18:00 | [6 empty] | 0 | 0 | [15 empty] | 4.5361 | 0.044845 | 4.41 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5465 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018807
1268 | Task(Task)-->C (Construction) | ERECTION OF CHUTES/ HOODS & SUPPORTS |  | 1.10.3.3 | ERECTION OF CHUTES/ HOODS & SUPPORTS-->MECHANICAL EQUIPMENT WORKS-->CONSTRUCTION-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-03-23 09:00 | 2021-06-20 23:59 | 2021-08-16 09:00 | 2021-11-13 18:00 | [6 empty] | 0 | 0 | [15 empty] | 100 | 0.044845 | 4.41 | Plan & Actual | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3616 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018808
1269 | Task(Task)-->C (Construction) | ELECTRICAL & INSTRUMENTATION | 1.10.3.4 | 1.10.3 | ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-03-31 09:00 | 2021-08-25 18:00 | 2021-08-24 09:00 | 2022-03-23 18:00 | [6 empty] | 0 | 0 | [15 empty] | 6.583 | 0.065081 | 6.4 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5249 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018809
1270 | Task(Task)-->C (Construction) | CABLE TRAY |  | 1.10.3.4 | CABLE TRAY-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-03-31 09:00 | 2021-04-09 18:00 | 2021-08-24 09:00 | 2021-09-02 18:00 | [6 empty] | 0 | 0 | [15 empty] | 5 | 0.003254 | 0.32 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3617 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018810
1271 | Task(Task)-->C (Construction) | POWER CABLE |  | 1.10.3.4 | POWER CABLE-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-06-21 09:00 | 2021-06-27 23:59 | 2021-11-14 | 2021-11-20 18:00 | [6 empty] | 0 | 0 | [15 empty] | 30.3125 | 0.019728 | 1.94 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 13710 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5250 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018811
1272 | Task(Task)-->C (Construction) | CONTROL CABLE |  | 1.10.3.4 | CONTROL CABLE-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-06-25 09:00 | 2021-06-27 23:59 | 2021-11-18 09:00 | 2021-11-20 18:00 | [6 empty] | 0 | 0 | [15 empty] | 23.5938 | 0.015355 | 1.51 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 10700 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3618 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018812
1273 | Task(Task)-->C (Construction) | EARTHING |  | 1.10.3.4 | EARTHING-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-03-31 09:00 | 2021-04-09 18:00 | 2021-08-24 09:00 | 2021-09-02 18:00 | [6 empty] | 0 | 0 | [15 empty] | 4.5312 | 0.002949 | 0.29 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 1282 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5318 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018813
1274 | Task(Task)-->C (Construction) | EARTH PIT |  | 1.10.3.4 | EARTH PIT-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-05-01 09:00 | 2021-05-05 18:00 | 2021-09-24 09:00 | 2021-09-28 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5319 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018814
1275 | Task(Task)-->C (Construction) | LIGHTING |  | 1.10.3.4 | LIGHTING-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-04-05 09:00 | 2021-04-19 18:00 | 2021-08-29 | 2021-09-12 23:59 | [6 empty] | 0 | 0 | [15 empty] | 26.875 | 0.017491 | 1.72 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 176 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5320 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018815
1276 | Task(Task)-->C (Construction) | FIELD INTRUMENTS |  | 1.10.3.4 | FIELD INTRUMENTS-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-06-28 09:00 | 2021-06-30 18:00 | 2021-11-21 | 2021-11-23 18:00 | [6 empty] | 0 | 0 | [15 empty] | 9.6875 | 0.006305 | 0.62 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5321 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018816
1277 | Task(Task)-->C (Construction) | MOTOR TERMINATION |  | 1.10.3.4 | MOTOR TERMINATION-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-06-28 09:00 | 2021-07-01 18:00 | 2022-01-02 | 2022-01-05 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5322 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018817
1278 | Task(Task)-->C (Construction) | NO LOAD RUN OF MOTOR |  | 1.10.3.4 | NO LOAD RUN OF MOTOR-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-08-22 | 2021-08-25 18:00 | 2022-03-20 | 2022-03-23 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5468 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018818
1279 | Task(Task)-->C (Construction) | NO LOAD COMMISSIONING & SYSTEM READYNESS FOR LOAD & TRIAL OPERATION |  | 1.10.3 | NO LOAD COMMISSIONING & SYSTEM READYNESS FOR LOAD & TRIAL OPERATION-->CONSTRUCTION-->KDTP-3 & DRIVE HOUSE-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-08-26 09:00 | 2021-09-08 18:00 | 2022-03-24 09:00 | 2022-04-06 18:00 | [6 empty] | 0 | 0 | [15 empty] | 1.584 | 0.01566 | 1.54 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5323 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018819
1280 | Task(Task)-->E (Engineering) | PIPE CONVEYOR PC 2A & PC 2B | 1.11 | 1 | PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-11-07 09:00 | 2021-09-13 18:00 | 2019-11-08 09:00 | 2022-05-06 18:00 |  |  | 2019-11-08 17:07 |  |  |  | 61.6493 | 22.4885 | [15 empty] | 28.6358 | 28.6358 | 2816.14 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3619 | 0 | 1 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018820
1281 | Task(Task)-->E (Engineering) | ENGINEERING | 1.11.1 | 1.11 | ENGINEERING-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-11-12 18:00 | 2020-09-04 17:40 | 2020-02-21 09:00 | 2020-11-15 23:59 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 96.1932 | [15 empty] | 0.5298 | 0.15171 | 14.92 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3620 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018821
1282 | Task(Task)-->E (Engineering) | MECHANICAL | 1.11.1.1 | 1.11.1 | MECHANICAL-->ENGINEERING-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-11-12 18:00 | 2020-03-18 17:40 | 2020-02-21 09:00 | 2020-06-10 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 84.6811 | [15 empty] | 9.3834 | 0.014236 | 1.4 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3621 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036102
1283 | Task(Task)-->E (Engineering) | PIPE CONVEYOR PROFILES FOR PC 2A/B |  | 1.11.1.1 | PIPE CONVEYOR PROFILES FOR PC 2A/B-->MECHANICAL-->ENGINEERING-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-12 18:00 | 2020-01-22 17:40 | 2020-02-21 09:00 | 2020-04-04 18:00 |  |  | 2020-02-21 14:04 | 2020-06-19 14:55 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-CS-DC-0015 |  | 2020-02-13 10:26 | 7012-155-PVM-B-015 |  |  |  | A |  |  |  | 15.6028 | 0.002221 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 80 | 0 | 69 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3622 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-11-12 18:00 | 2020-01-08 18:00 |  | 10 | 2020-01-08 23:31 |  |  | 2019-12-14 17:40 | 2020-02-07 18:00 |  | 30 | 2020-02-07 23:31 |  |  | 2019-12-20 17:40 | 2020-02-14 18:00 |  | 35 | 2020-02-14 23:31 |  |  | 2019-12-26 23:59 | 2020-02-21 18:00 |  | 65 | 2020-02-21 23:31 |  |  | 2020-01-01 17:40 | 2020-03-19 18:00 |  | 80 | 2020-03-19 23:31 | [5 empty] | 80 | 2020-03-30 18:45 | [5 empty] | 80 | 2020-03-30 18:45 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-01-22 17:40 | 2020-04-18 18:00 |  | 100 | 2020-04-23 23:31 | [121 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 15 |  |  |  |  | 101029
1284 | Task(Task)-->E (Engineering) | POWER AND TENSION CALCULATION FOR PIPE CONVEYORS PC 2A/B |  | 1.11.1.1 | POWER AND TENSION CALCULATION FOR PIPE CONVEYORS PC 2A/B-->MECHANICAL-->ENGINEERING-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-12 18:00 | 2020-01-22 17:40 | 2020-04-28 09:00 | 2020-06-10 18:00 |  |  | 2020-02-21 14:04 | 2020-06-29 19:15 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-CS-DC-0017 |  | 2020-02-13 10:26 | 7012-155-PVM-U-017 |  |  |  | I |  |  |  | 7.8014 | 0.001111 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 40 | 0 | 21.12 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3624 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-11-12 18:00 | 2020-03-18 18:00 |  | 10 | 2020-03-18 23:31 |  |  | 2019-12-14 17:40 | 2020-04-17 18:00 |  | 30 | 2020-04-17 23:31 |  |  | 2019-12-20 17:40 | 2020-04-17 18:00 |  | 35 | 2020-04-17 23:31 |  |  | 2019-12-26 23:59 | 2020-04-24 18:00 |  | 65 | 2020-04-28 23:31 |  |  | 2020-01-01 17:40 | 2020-05-15 18:00 |  | 80 | 2020-05-16 23:31 | [5 empty] | 80 | 2020-06-10 15:19 | [5 empty] | 80 | 2020-06-10 15:19 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-01-22 17:40 | 2020-05-15 18:00 |  | 100 | 2020-06-29 19:16 | [121 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 17 |  |  |  |  | 101031
1285 | Task(Task)-->E (Engineering) | G.A AND MARKING OF PIPE CONV. PC 2A/B WITH ELEVATION AND PLAN DETAILS |  | 1.11.1.1 | G.A AND MARKING OF PIPE CONV. PC 2A/B WITH ELEVATION AND PLAN DETAILS-->MECHANICAL-->ENGINEERING-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-12-28 18:00 | 2020-03-18 17:40 | 2020-03-15 23:59 | 2020-06-10 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-0025 |  | 2020-02-13 10:26 | 7012-155-PVM-B-025 |  |  |  | A |  |  |  | 76.5957 | 0.010904 | 1.08 | Plan & Actual | Date |  | 0 | 0 | 0 | 400 | 0 | 103 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3623 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-12-28 18:00 | 2020-03-15 23:59 |  | 10 | 2020-03-15 23:31 |  |  | 2020-02-05 17:40 | 2020-04-24 18:00 |  | 30 | 2020-05-01 23:31 |  |  | 2020-02-12 17:40 | 2020-04-29 18:00 |  | 35 | 2020-05-09 23:31 |  |  | 2020-02-18 23:59 | 2020-05-06 18:00 |  | 65 | 2020-05-12 23:31 |  |  | 2020-02-25 17:40 | 2020-05-27 18:00 |  | 80 | 2020-06-10 17:36 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-18 17:40 | 2020-06-10 18:00 |  | 100 | [122 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 25 |  |  |  |  | 101039
1286 | Task(Task)-->E (Engineering) | CIVIL | 1.11.1.2 | 1.11.1 | CIVIL-->ENGINEERING-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-22 18:00 | 2020-07-21 17:40 | 2020-08-17 09:00 | 2020-10-27 18:00 |  |  | 2020-02-21 15:37 | 2020-10-27 19:17 |  |  | 100 | 100 | [15 empty] | 47.7212 | 0.072399 | 7.12 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3643 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036103
1287 | Task(Task)-->E (Engineering) | PIPE CONVEYOR FOR PC 2A/B : NUM & RC DETAILS OF FDN (SHT 1) |  | 1.11.1.2 | PIPE CONVEYOR FOR PC 2A/B : NUM & RC DETAILS OF FDN (SHT 1)-->CIVIL-->ENGINEERING-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-22 18:00 | 2020-07-21 17:40 | 2020-08-17 09:00 | 2020-09-01 18:00 |  |  | 2020-02-21 15:37 | 2020-09-02 00:50 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-NR-0019 |  | 2020-02-13 11:42 | 7012-155-PVC-C-056 |  |  |  | A |  |  |  | 50 | 0.0362 | 3.51 | Plan & Actual | Date |  | 0 | 0 | 0 | 1303.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3644 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-05-22 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-06-09 17:40 | 2020-07-10 18:00 |  | 30 |  |  |  | 2020-06-16 17:40 | 2020-07-13 18:00 |  | 35 |  |  |  | 2020-06-22 23:59 | 2020-07-20 18:00 |  | 65 | 2020-08-17 22:24 |  |  | 2020-06-29 17:40 | 2020-08-10 18:00 |  | 80 | 2020-09-02 00:43 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-07-21 17:40 | 2020-08-24 18:00 |  | 100 | 2020-09-02 00:51 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 157 |  |  |  |  | 101169
1288 | Task(Task)-->E (Engineering) | PIPE CONVEYOR FOR PC 2A/B : NUM & RC DETAILS OF FDN (SHT 2) |  | 1.11.1.2 | PIPE CONVEYOR FOR PC 2A/B : NUM & RC DETAILS OF FDN (SHT 2)-->CIVIL-->ENGINEERING-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-22 18:00 | 2020-07-21 17:40 | 2020-09-30 09:00 | 2020-10-27 18:00 |  |  | 2020-02-21 15:37 | 2020-10-27 19:17 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-NR-0020 |  | 2020-02-13 11:42 | 7012-155-PVC-C-057 |  |  |  | A |  |  |  | 50 | 0.0362 | 3.51 | Plan & Actual | Date |  | 0 | 0 | 0 | 1303.33 | 0 | 208 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3645 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-05-22 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-06-09 17:40 | 2020-07-10 18:00 |  | 30 |  |  |  | 2020-06-16 17:40 | 2020-07-13 18:00 |  | 35 |  |  |  | 2020-06-22 23:59 | 2020-07-20 18:00 |  | 65 | 2020-10-01 19:38 |  |  | 2020-06-29 17:40 | 2020-08-10 18:00 |  | 80 | 2020-10-14 20:44 | [5 empty] | 80 | 2020-10-14 20:49 | [5 empty] | 80 | 2020-10-14 20:49 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-07-21 17:40 | 2020-08-24 18:00 |  | 100 | 2020-10-27 19:16 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 158 |  |  |  |  | 101170
1289 | Task(Task)-->E (Engineering) | STRUCTURAL | 1.11.1.3 | 1.11.1 | STRUCTURAL-->ENGINEERING-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-04-17 18:00 | 2020-09-04 17:40 | 2020-07-06 18:00 | 2020-11-15 23:59 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 99.1425 | [15 empty] | 32.4397 | 0.049215 | 4.84 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3648 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036104
1290 | Task(Task)-->E (Engineering) | PIPE CONVEYOR FOR PC 2A/B : STRUCTURAL GA (SHT 1) |  | 1.11.1.3 | PIPE CONVEYOR FOR PC 2A/B : STRUCTURAL GA (SHT 1)-->STRUCTURAL-->ENGINEERING-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-17 18:00 | 2020-06-16 17:40 | 2020-08-02 | 2020-08-17 18:00 |  |  | 2020-02-21 15:37 | 2020-08-17 22:47 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-GA-0014 |  | 2020-02-13 11:42 | 7012-155-PVC-B-051 |  |  |  | A |  |  |  | 7.4045 | 0.003644 | 0.95 | Plan & Actual | Date |  | 0 | 0 | 0 | 351.15 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3656 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-17 18:00 | 2020-05-06 18:00 |  | 10 |  |  |  | 2020-05-05 17:40 | 2020-06-10 18:00 |  | 30 |  |  |  | 2020-05-12 17:40 | 2020-06-13 18:00 |  | 35 |  |  |  | 2020-05-18 23:59 | 2020-06-20 18:00 |  | 65 | 2020-08-13 19:57 |  |  | 2020-05-25 17:40 | 2020-07-11 18:00 |  | 80 | 2020-08-17 22:37 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-16 17:40 | 2020-07-25 18:00 |  | 100 | 2020-08-17 22:48 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 152 |  |  |  |  | 101164
1291 | Task(Task)-->E (Engineering) | PIPE CONVEYOR FOR PC 2A/B : STRUCTURAL GA (SHT 2) |  | 1.11.1.3 | PIPE CONVEYOR FOR PC 2A/B : STRUCTURAL GA (SHT 2)-->STRUCTURAL-->ENGINEERING-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-17 18:00 | 2020-06-16 17:40 | 2020-08-21 09:00 | 2020-09-09 18:00 |  |  | 2020-02-21 15:37 | 2020-09-10 23:14 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-GA-0015 |  | 2020-02-13 11:42 | 7012-155-PVC-B-052 |  |  |  | A |  |  |  | 7.4045 | 0.003644 | 0.95 | Plan & Actual | Date |  | 0 | 0 | 0 | 351.15 | 0 | 70.3 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3657 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-17 18:00 | 2020-05-06 18:00 |  | 10 |  |  |  | 2020-05-05 17:40 | 2020-06-10 18:00 |  | 30 |  |  |  | 2020-05-12 17:40 | 2020-06-13 18:00 |  | 35 |  |  |  | 2020-05-18 23:59 | 2020-06-20 18:00 |  | 65 | 2020-08-21 21:30 |  |  | 2020-05-25 17:40 | 2020-07-11 18:00 |  | 80 | 2020-09-10 22:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-16 17:40 | 2020-07-25 18:00 |  | 100 | 2020-09-10 23:15 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 153 |  |  |  |  | 101165
1292 | Task(Task)-->E (Engineering) | PIPE CONVEYOR FOR PC 2A/B : STRUCTURAL GA (SHT 3) |  | 1.11.1.3 | PIPE CONVEYOR FOR PC 2A/B : STRUCTURAL GA (SHT 3)-->STRUCTURAL-->ENGINEERING-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-17 18:00 | 2020-06-16 17:40 | 2020-08-21 09:00 | 2020-09-09 18:00 |  |  | 2020-02-21 15:37 | 2020-09-10 23:14 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-GA-0016 |  | 2020-02-13 11:42 | 7012-155-PVC-B-053 |  |  |  | A |  |  |  | 7.4045 | 0.003644 | 0.95 | Plan & Actual | Date |  | 0 | 0 | 0 | 351.15 | 0 | 84 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3658 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-17 18:00 | 2020-05-06 18:00 |  | 10 |  |  |  | 2020-05-05 17:40 | 2020-06-10 18:00 |  | 30 |  |  |  | 2020-05-12 17:40 | 2020-06-13 18:00 |  | 35 |  |  |  | 2020-05-18 23:59 | 2020-06-20 18:00 |  | 65 | 2020-08-21 21:30 |  |  | 2020-05-25 17:40 | 2020-07-11 18:00 |  | 80 | 2020-09-10 22:38 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-16 17:40 | 2020-07-25 18:00 |  | 100 | 2020-09-10 23:15 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 154 |  |  |  |  | 101166
1293 | Task(Task)-->E (Engineering) | PIPE CONVEYOR FOR PC 2A/B : STRUCTURAL GA (SHT 4) |  | 1.11.1.3 | PIPE CONVEYOR FOR PC 2A/B : STRUCTURAL GA (SHT 4)-->STRUCTURAL-->ENGINEERING-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-17 18:00 | 2020-06-16 17:40 | 2020-08-21 09:00 | 2020-09-09 18:00 |  |  | 2020-02-21 15:37 | 2020-09-10 23:14 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-GA-0017 |  | 2020-02-13 11:42 | 7012-155-PVC-B-054 |  |  |  | A |  |  |  | 7.4045 | 0.003644 | 0.95 | Plan & Actual | Date |  | 0 | 0 | 0 | 351.15 | 0 | 127.3 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3659 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-17 18:00 | 2020-05-06 18:00 |  | 10 |  |  |  | 2020-05-05 17:40 | 2020-06-10 18:00 |  | 30 |  |  |  | 2020-05-12 17:40 | 2020-06-13 18:00 |  | 35 |  |  |  | 2020-05-18 23:59 | 2020-06-20 18:00 |  | 65 | 2020-08-21 21:30 |  |  | 2020-05-25 17:40 | 2020-07-11 18:00 |  | 80 | 2020-09-10 22:39 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-16 17:40 | 2020-07-25 18:00 |  | 100 | 2020-09-10 23:15 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 155 |  |  |  |  | 101167
1294 | Task(Task)-->E (Engineering) | PIPE CONVEYOR FOR PC 2A/B : STRUCTURAL GA (SHT 5) |  | 1.11.1.3 | PIPE CONVEYOR FOR PC 2A/B : STRUCTURAL GA (SHT 5)-->STRUCTURAL-->ENGINEERING-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-17 18:00 | 2020-06-16 17:40 | 2020-10-16 09:00 | 2020-11-15 23:59 |  |  | 2020-02-21 15:37 | 2020-11-03 22:48 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-GA-0018 |  | 2020-02-13 11:42 | 7012-155-PVC-B-055 |  |  |  | A |  |  |  | 7.4045 | 0.003644 | 0.95 | Plan & Actual | Date |  | 0 | 0 | 0 | 351.15 | 0 | 184 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3660 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-17 18:00 | 2020-05-06 18:00 |  | 10 |  |  |  | 2020-05-05 17:40 | 2020-06-10 18:00 |  | 30 |  |  |  | 2020-05-12 17:40 | 2020-06-13 18:00 |  | 35 |  |  |  | 2020-05-18 23:59 | 2020-06-20 18:00 |  | 65 | 2020-10-16 22:35 |  |  | 2020-05-25 17:40 | 2020-07-11 18:00 |  | 80 | 2020-11-03 22:34 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-16 17:40 | 2020-07-25 18:00 |  | 100 | 2020-11-03 22:48 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 156 |  |  |  |  | 101168
1295 | Task(Task)-->E (Engineering) | ARCHITECTURAL GA OF PIPE CONVEYOR FOR PC 2A/B |  | 1.11.1.3 | ARCHITECTURAL GA OF PIPE CONVEYOR FOR PC 2A/B-->STRUCTURAL-->ENGINEERING-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-06 18:00 | 2020-09-04 17:40 | 2020-07-06 18:00 | 2020-09-13 23:59 |  |  | 2020-02-21 15:39 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-AR-0007 |  | 2020-02-13 11:43 | 7012-155-PVC-C-113 |  |  |  | I |  |  |  | 0.85737 | 0.000422 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 40.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3651 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-07-06 18:00 | 2020-07-06 18:00 |  | 10 |  |  |  | 2020-07-24 17:40 | 2020-07-30 18:00 |  | 30 |  |  |  | 2020-07-31 17:40 | 2020-08-02 23:59 |  | 35 |  |  |  | 2020-08-06 23:59 | 2020-08-09 23:59 |  | 65 |  |  |  | 2020-08-13 17:40 | 2020-08-30 23:59 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-09-04 17:40 | 2020-09-13 23:59 |  | 100 | [122 empty] | Chetan Khodke | [5 empty] | A - Architecture | [16 empty] | 214 |  |  |  |  | 101224
1296 | Task(Task)-->E (Engineering) | PIPE CONVEYOR FOR PC 2A/B : DESIGN CALCULATION OF SUPER STRUCTURE |  | 1.11.1.3 | PIPE CONVEYOR FOR PC 2A/B : DESIGN CALCULATION OF SUPER STRUCTURE-->STRUCTURAL-->ENGINEERING-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-05 17:40 | 2020-06-16 17:40 | 2020-10-13 09:00 | 2020-10-27 18:00 |  |  | 2020-02-21 15:38 | 2020-11-03 22:48 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0042 |  | 2020-02-13 12:42 | 7012-155-PVC-U-049 |  |  |  | A |  |  |  | 54.7155 | 0.026928 | 7.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3653 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-05-22 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-05-05 17:40 | 2020-07-10 18:00 |  | 30 |  |  |  | 2020-05-12 17:40 | 2020-07-13 18:00 |  | 35 |  |  |  | 2020-05-18 23:59 | 2020-07-20 18:00 |  | 65 | 2020-10-16 22:35 |  |  | 2020-05-25 17:40 | 2020-08-10 18:00 |  | 80 | 2020-11-03 22:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-16 17:40 | 2020-08-24 18:00 |  | 100 | 2020-11-03 22:48 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 150 |  |  |  |  | 101464
1297 | Task(Task)-->E (Engineering) | PIPE CONVEYOR FOR PC 2A/B : DESIGN CALCULATION OF SUB STRUCTURE |  | 1.11.1.3 | PIPE CONVEYOR FOR PC 2A/B : DESIGN CALCULATION OF SUB STRUCTURE-->STRUCTURAL-->ENGINEERING-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-17 18:00 | 2020-07-21 17:40 | 2020-08-02 | 2020-08-17 18:00 |  |  | 2020-02-21 15:38 | 2020-10-27 19:17 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0045 |  | 2020-02-13 12:42 | 7012-155-PVC-U-050 |  |  |  | A |  |  |  | 7.4045 | 0.003644 | 0.95 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3656 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-17 18:00 | 2020-05-06 18:00 |  | 10 |  |  |  | 2020-06-09 17:40 | 2020-06-10 18:00 |  | 30 |  |  |  | 2020-06-16 17:40 | 2020-06-13 18:00 |  | 35 |  |  |  | 2020-06-22 23:59 | 2020-06-20 18:00 |  | 65 | 2020-10-13 22:05 |  |  | 2020-06-29 17:40 | 2020-07-11 18:00 |  | 80 | 2020-10-27 19:08 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-07-21 17:40 | 2020-07-25 18:00 |  | 100 | 2020-10-27 19:17 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 151 |  |  |  |  | 101465
1298 | Task(Task)-->E (Engineering) | ELECTRICAL | 1.11.1.4 | 1.11.1 | ELECTRICAL-->ENGINEERING-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-09 18:00 | 2020-06-29 17:40 | 2020-05-12 18:00 | 2020-06-24 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 | [15 empty] | 10.4558 | 0.015863 | 1.56 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3661 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036105
1299 | Task(Task)-->E (Engineering) | LIGHTING LAYOUT PLAN WITH POWER DISTRIBUTION ARRANGEMENT, SECTIONAL VIEW, BOM OF PIPE CONVEYOR 2A/B |  | 1.11.1.4 | LIGHTING LAYOUT PLAN WITH POWER DISTRIBUTION ARRANGEMENT, SECTIONAL VIEW, BOM OF PIPE CONVEYOR 2A/B-->ELECTRICAL-->ENGINEERING-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-09 18:00 | 2020-06-29 17:40 | 2020-05-12 18:00 | 2020-06-24 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5078 |  | 2020-02-13 11:45 | 7012-155-PVE-G-040 |  |  |  | A |  |  |  | 100 | 0.015863 | 1.56 | Plan & Actual | Date |  | 0 | 0 | 0 | 580.17 | 0 | 24.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3663 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-05-09 18:00 | 2020-05-12 18:00 |  | 10 | 2020-05-12 23:31 |  |  | 2020-05-18 17:40 | 2020-05-19 18:00 |  | 30 |  |  |  | 2020-05-25 17:40 | 2020-05-26 18:00 |  | 35 |  |  |  | 2020-05-30 23:59 | 2020-06-02 18:00 |  | 65 | 2020-06-10 11:31 |  |  | 2020-06-05 17:40 | 2020-06-23 18:00 |  | 80 | 2020-08-03 10:00 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-29 17:40 | 2020-06-23 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 275 |  |  |  |  | 101286
1300 | Task(Task)-->P (Procurement) | PROCUREMENT | 1.11.2 | 1.11 | PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-11-07 09:00 | 2021-03-31 18:00 | 2019-11-08 09:00 | 2022-02-22 18:00 |  |  | 2019-11-08 17:07 |  |  |  | 72.5637 | 29.657 | [15 empty] | 74.1058 | 21.2208 | 2086.93 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3666 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018826
1301 | Task(Task)-->P (Procurement) | PURCHASE REQUISITION | 1.11.2.1 | 1.11.2 | PURCHASE REQUISITION-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-11-07 09:00 | 2020-05-19 18:00 | 2019-11-08 09:00 | 2020-07-19 23:59 |  |  | 2019-11-08 17:07 |  |  |  | 100 | 99.5684 | [15 empty] | 4.9949 | 1.06 | 104.24 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3667 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018827
1302 | Task(Task)-->P (Procurement) | Pulley |  | 1.11.2.1 | Pulley-->PURCHASE REQUISITION-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-03 09:00 | 2020-03-03 18:00 | 2020-04-26 | 2020-04-26 23:59 |  |  | 2020-04-26 10:57 | 2020-04-26 10:57 |  |  | 100 | 100 | [15 empty] | 3.1751 | 0.033654 | 3.31 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3668 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018828
1303 | Task(Task)-->P (Procurement) | Idler |  | 1.11.2.1 | Idler-->PURCHASE REQUISITION-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-19 09:00 | 2019-11-19 18:00 | 2020-03-21 09:00 | 2020-03-21 18:00 |  |  | 2020-03-21 10:57 | 2020-03-21 10:57 |  |  | 100 | 100 | [15 empty] | 17.2374 | 0.18271 | 17.97 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3669 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018829
1304 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.11.2.1 | Plummer Block-->PURCHASE REQUISITION-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-17 | 2020-05-17 23:59 | 2020-04-26 | 2020-04-26 23:59 |  |  | 2020-04-26 10:57 | 2020-04-26 10:57 |  |  | 100 | 100 | [15 empty] | 0.25899 | 0.002745 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3670 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018830
1305 | Task(Task)-->P (Procurement) | Bearing |  | 1.11.2.1 | Bearing-->PURCHASE REQUISITION-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-17 | 2020-05-17 23:59 | 2020-04-26 | 2020-04-26 23:59 |  |  | 2020-04-26 10:57 | 2020-04-26 10:57 |  |  | 100 | 100 | [15 empty] | 0.57554 | 0.0061 | 0.6 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3671 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018831
1306 | Task(Task)-->P (Procurement) | Belting |  | 1.11.2.1 | Belting-->PURCHASE REQUISITION-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-07 09:00 | 2019-11-07 18:00 | 2020-02-21 09:00 | 2020-02-21 18:00 |  |  | 2020-02-21 15:59 | 2020-02-21 15:59 |  |  | 100 | 100 | [15 empty] | 32.2878 | 0.34224 | 33.66 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3672 | 1 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018832
1307 | Task(Task)-->P (Procurement) | Scrapper |  | 1.11.2.1 | Scrapper-->PURCHASE REQUISITION-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-17 | 2019-11-17 23:59 | 2020-03-11 09:00 | 2020-03-11 18:00 |  |  | 2020-03-11 10:57 | 2020-03-11 10:57 |  |  | 100 | 100 | [15 empty] | 0.019185 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3673 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018833
1308 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.11.2.1 | Technological Structure-->PURCHASE REQUISITION-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-10 09:00 | 2020-03-10 18:00 | 2020-03-11 09:00 | 2020-03-11 18:00 |  |  | 2020-03-11 12:41 | 2020-03-11 12:41 |  |  | 100 | 100 | [15 empty] | 1.2182 | 0.012913 | 1.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3674 | 0 | 4 | High | [7 empty] | 0 | 0 | [246 empty] | 1018834
1309 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.11.2.1 | Takeup Component-->PURCHASE REQUISITION-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-19 09:00 | 2020-05-19 18:00 | 2020-06-08 09:00 | 2020-06-08 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.43165 | 0.004575 | 0.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3675 | 1 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018835
1310 | Task(Task)-->P (Procurement) | Gear Box |  | 1.11.2.1 | Gear Box-->PURCHASE REQUISITION-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-13 09:00 | 2019-11-13 18:00 | 2020-02-21 09:00 | 2020-02-21 18:00 |  |  | 2020-02-21 10:57 | 2020-02-21 10:57 |  |  | 100 | 100 | [15 empty] | 1.6403 | 0.017386 | 1.71 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3676 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018836
1311 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.11.2.1 | Geared Coupling-->PURCHASE REQUISITION-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-21 09:00 | 2019-11-21 18:00 | 2020-04-27 09:00 | 2020-04-27 18:00 |  |  | 2020-04-27 10:41 | 2020-04-27 10:41 |  |  | 100 | 100 | [15 empty] | 0.35492 | 0.003762 | 0.37 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3677 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018837
1312 | Task(Task)-->P (Procurement) | Brake |  | 1.11.2.1 | Brake-->PURCHASE REQUISITION-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-18 09:00 | 2019-12-18 18:00 | 2020-05-01 09:00 | 2020-05-01 18:00 |  |  | 2020-04-23 11:33 | 2020-04-23 11:33 |  |  | 100 | 100 | [15 empty] | 0.11511 | 0.00122 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3678 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018838
1313 | Task(Task)-->P (Procurement) | Maintenance Trolley |  | 1.11.2.1 | Maintenance Trolley-->PURCHASE REQUISITION-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-30 09:00 | 2019-11-30 18:00 | 2020-07-19 | 2020-07-19 23:59 |  |  | 2020-07-28 11:45 | 2020-07-28 11:45 |  |  | 100 | 100 | [15 empty] | 0.29736 | 0.003152 | 0.31 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3679 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018839
1314 | Task(Task)-->P (Procurement) | Building Structure |  | 1.11.2.1 | Building Structure-->PURCHASE REQUISITION-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-20 09:00 | 2020-03-20 18:00 | 2020-04-06 09:00 | 2020-04-06 18:00 |  |  | 2020-04-06 17:30 | 2020-05-06 17:30 |  |  | 100 | 100 | [15 empty] | 35.6067 | 0.37742 | 37.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3680 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018840
1315 | Task(Task)-->P (Procurement) | 6.6KV HT VFD with Motors |  | 1.11.2.1 | 6.6KV HT VFD with Motors-->PURCHASE REQUISITION-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-30 09:00 | 2019-12-30 18:00 | 2020-01-24 09:00 | 2020-01-24 18:00 |  |  | 2019-11-21 10:57 | 2019-11-21 10:57 |  |  | 100 | 100 | [15 empty] | 6.0144 | 0.06375 | 6.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3681 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018841
1316 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.11.2.1 | LIGHT & LIGHT FIXTURES-->PURCHASE REQUISITION-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-10 09:00 | 2020-03-10 18:00 | 2020-03-16 09:00 | 2020-03-16 18:00 |  |  | 2020-03-16 10:57 | 2020-03-16 10:57 |  |  | 100 | 100 | [15 empty] | 0.25899 | 0.002745 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3682 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018842
1317 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.11.2.1 | LIGHTING POLES-->PURCHASE REQUISITION-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-27 09:00 | 2020-03-27 18:00 | 2020-04-30 09:00 | 2020-04-30 18:00 |  |  | 2020-04-30 10:57 | 2020-04-30 10:57 |  |  | 100 | 100 | [15 empty] | 0.11511 | 0.00122 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3683 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018843
1318 | Task(Task)-->P (Procurement) | WELDING DISTRIBUTION BOARD |  | 1.11.2.1 | WELDING DISTRIBUTION BOARD-->PURCHASE REQUISITION-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-14 09:00 | 2020-02-14 18:00 | 2019-11-08 09:00 | 2019-11-08 18:00 |  |  | 2019-11-08 17:07 | 2019-11-08 17:07 |  |  | 100 | 100 | [15 empty] | 0.35492 | 0.003762 | 0.37 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3684 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018844
1319 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.11.2.1 | CONVEYOR BELT PROTECTION SWITCHES-->PURCHASE REQUISITION-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-08 09:00 | 2020-01-08 18:00 | 2020-01-08 09:00 | 2020-01-08 18:00 |  |  | 2020-01-08 10:57 | 2020-01-08 10:57 |  |  | 100 | 100 | [15 empty] | 0.038369 | 0.000407 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3686 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018845
1320 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.11.2.1 | ZERO SPEED SWITCH-->PURCHASE REQUISITION-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-30 09:00 | 2019-12-30 18:00 | 2019-12-30 09:00 | 2019-12-30 18:00 |  |  | 2019-12-30 10:57 | 2019-12-30 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3687 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018846
1321 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.11.2.1 | CHUTE BLOCK SWITCH-->PURCHASE REQUISITION-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-03 09:00 | 2020-01-03 18:00 | 2020-01-03 09:00 | 2020-01-03 18:00 |  |  | 2020-01-03 10:57 | 2020-01-03 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3688 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018847
1322 | Task(Task)-->P (Procurement) | TECHNICAL CLEARANCE | 1.11.2.2 | 1.11.2 | TECHNICAL CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-11-08 09:00 | 2020-06-18 18:00 | 2019-11-08 09:00 | 2020-11-15 23:59 |  |  | 2019-11-09 17:08 |  |  |  | 100 | 99.271 | [15 empty] | 4.9949 | 1.06 | 104.24 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3689 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018848
1323 | Task(Task)-->P (Procurement) | Pulley |  | 1.11.2.2 | Pulley-->TECHNICAL CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-04 09:00 | 2020-03-04 18:00 | 2020-04-26 | 2020-04-26 23:59 |  |  | 2020-04-26 10:57 | 2020-04-26 10:57 |  |  | 100 | 100 | [15 empty] | 3.1751 | 0.033654 | 3.31 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3690 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018849
1324 | Task(Task)-->P (Procurement) | Idler |  | 1.11.2.2 | Idler-->TECHNICAL CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-20 09:00 | 2020-02-01 18:00 | 2020-03-21 09:00 | 2020-05-16 18:00 |  |  | 2020-03-23 15:49 | 2020-05-16 15:49 |  |  | 100 | 100 | [15 empty] | 17.2374 | 0.18271 | 17.97 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3691 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018850
1325 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.11.2.2 | Plummer Block-->TECHNICAL CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-18 09:00 | 2020-06-01 18:00 | 2020-04-26 | 2020-04-26 23:59 |  |  | 2020-04-26 10:57 | 2020-04-26 10:57 |  |  | 100 | 100 | [15 empty] | 0.25899 | 0.002745 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3692 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018851
1326 | Task(Task)-->P (Procurement) | Bearing |  | 1.11.2.2 | Bearing-->TECHNICAL CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-18 09:00 | 2020-06-16 18:00 | 2020-04-26 | 2020-04-26 23:59 |  |  | 2020-04-26 10:57 | 2020-04-26 10:57 |  |  | 100 | 100 | [15 empty] | 0.57554 | 0.0061 | 0.6 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3693 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018852
1327 | Task(Task)-->P (Procurement) | Belting |  | 1.11.2.2 | Belting-->TECHNICAL CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-08 09:00 | 2020-03-27 18:00 | 2020-02-21 09:00 | 2020-05-16 18:00 |  |  | 2020-05-16 10:57 | 2020-05-16 10:57 |  |  | 100 | 100 | [15 empty] | 32.2878 | 0.34224 | 33.66 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3694 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018853
1328 | Task(Task)-->P (Procurement) | Scrapper |  | 1.11.2.2 | Scrapper-->TECHNICAL CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-18 09:00 | 2020-03-16 18:00 | 2020-03-11 09:00 | 2020-03-26 18:00 |  |  | 2020-03-26 10:57 | 2020-03-26 10:57 |  |  | 100 | 100 | [15 empty] | 0.019185 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3695 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018854
1329 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.11.2.2 | Technological Structure-->TECHNICAL CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-11 09:00 | 2020-03-20 18:00 | 2020-03-11 09:00 | 2020-03-17 18:00 |  |  | 2020-03-12 12:43 | 2020-03-17 12:43 |  |  | 100 | 100 | [15 empty] | 1.2182 | 0.012913 | 1.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3696 | 0 | 4 | High | [7 empty] | 0 | 0 | [246 empty] | 1018855
1330 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.11.2.2 | Takeup Component-->TECHNICAL CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-20 09:00 | 2020-06-18 18:00 | 2020-06-08 09:00 | 2020-08-13 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.43165 | 0.004575 | 0.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3697 | 1 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018856
1331 | Task(Task)-->P (Procurement) | Gear Box |  | 1.11.2.2 | Gear Box-->TECHNICAL CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-14 09:00 | 2020-05-21 18:00 | 2020-02-21 09:00 | 2020-05-29 18:00 |  |  | 2020-02-22 11:19 | 2020-05-29 10:57 |  |  | 100 | 100 | [15 empty] | 1.6403 | 0.017386 | 1.71 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3698 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018857
1332 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.11.2.2 | Geared Coupling-->TECHNICAL CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-22 09:00 | 2020-03-19 18:00 | 2020-04-27 09:00 | 2020-05-30 18:00 |  |  | 2020-05-30 10:46 | 2020-05-30 10:46 |  |  | 100 | 100 | [15 empty] | 0.35492 | 0.003762 | 0.37 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3699 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018858
1333 | Task(Task)-->P (Procurement) | Brake |  | 1.11.2.2 | Brake-->TECHNICAL CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-19 09:00 | 2020-04-05 23:59 | 2020-05-01 09:00 | 2020-06-15 18:00 |  |  | 2020-04-24 11:34 | 2020-06-15 10:57 |  |  | 100 | 100 | [15 empty] | 0.11511 | 0.00122 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3700 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018859
1334 | Task(Task)-->P (Procurement) | Maintenance Trolley |  | 1.11.2.2 | Maintenance Trolley-->TECHNICAL CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-12-01 | 2019-12-18 18:00 | 2020-07-19 | 2020-11-15 23:59 | [6 empty] | 100 | 0 | [15 empty] | 0.29736 | 0.003152 | 0.31 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3701 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018860
1335 | Task(Task)-->P (Procurement) | Building Structure |  | 1.11.2.2 | Building Structure-->TECHNICAL CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-21 09:00 | 2020-03-27 18:00 | 2020-04-06 09:00 | 2020-04-13 18:00 |  |  | 2020-04-07 17:31 | 2020-04-13 17:31 |  |  | 100 | 100 | [15 empty] | 35.6067 | 0.37742 | 37.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3702 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018861
1336 | Task(Task)-->P (Procurement) | 6.6KV HT VFD with Motors |  | 1.11.2.2 | 6.6KV HT VFD with Motors-->TECHNICAL CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-31 09:00 | 2020-01-29 18:00 | 2020-01-24 09:00 | 2020-04-16 18:00 |  |  | 2020-02-26 10:57 | 2020-02-26 10:57 |  |  | 100 | 100 | [15 empty] | 6.0144 | 0.06375 | 6.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3703 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018862
1337 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.11.2.2 | LIGHT & LIGHT FIXTURES-->TECHNICAL CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-11 09:00 | 2020-03-25 18:00 | 2020-03-16 09:00 | 2020-06-02 18:00 |  |  | 2020-06-02 10:57 | 2020-06-02 10:57 |  |  | 100 | 100 | [15 empty] | 0.25899 | 0.002745 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3704 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018863
1338 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.11.2.2 | LIGHTING POLES-->TECHNICAL CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-28 09:00 | 2020-05-11 18:00 | 2020-04-30 09:00 | 2020-06-03 18:00 |  |  | 2020-06-03 10:57 | 2020-06-03 10:57 |  |  | 100 | 100 | [15 empty] | 0.11511 | 0.00122 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3705 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018864
1339 | Task(Task)-->P (Procurement) | WELDING DISTRIBUTION BOARD |  | 1.11.2.2 | WELDING DISTRIBUTION BOARD-->TECHNICAL CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-15 09:00 | 2020-02-28 18:00 | 2019-11-08 09:00 | 2020-02-13 18:00 |  |  | 2019-11-09 17:08 | 2020-02-13 17:08 |  |  | 100 | 100 | [15 empty] | 0.35492 | 0.003762 | 0.37 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3706 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018865
1340 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.11.2.2 | CONVEYOR BELT PROTECTION SWITCHES-->TECHNICAL CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-09 09:00 | 2020-01-22 18:00 | 2020-01-08 09:00 | 2020-03-10 18:00 |  |  | 2020-03-10 10:57 | 2020-03-10 10:57 |  |  | 100 | 100 | [15 empty] | 0.038369 | 0.000407 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3708 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018866
1341 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.11.2.2 | ZERO SPEED SWITCH-->TECHNICAL CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-31 09:00 | 2020-01-14 18:00 | 2019-12-30 09:00 | 2020-03-07 18:00 |  |  | 2020-03-07 10:57 | 2020-03-07 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3709 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018867
1342 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.11.2.2 | CHUTE BLOCK SWITCH-->TECHNICAL CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-04 09:00 | 2020-01-18 18:00 | 2020-01-03 09:00 | 2020-01-16 18:00 |  |  | 2020-01-16 10:57 | 2020-01-16 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3710 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018868
1343 | Task(Task)-->P (Procurement) | ORDERING | 1.11.2.3 | 1.11.2 | ORDERING-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-12-19 09:00 | 2020-07-18 18:00 | 2020-01-16 09:00 | 2020-12-05 18:00 |  |  | 2020-02-01 10:57 |  |  |  | 100 | 95.4724 | [15 empty] | 9.9898 | 2.1199 | 208.48 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3711 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018869
1344 | Task(Task)-->P (Procurement) | Pulley |  | 1.11.2.3 | Pulley-->ORDERING-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-05 09:00 | 2020-04-03 18:00 | 2020-04-26 | 2020-07-16 18:00 | [6 empty] | 100 | 0 | [15 empty] | 3.1799 | 0.06741 | 6.63 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3712 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018870
1345 | Task(Task)-->P (Procurement) | Idler |  | 1.11.2.3 | Idler-->ORDERING-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-02 | 2020-03-02 18:00 | 2020-05-16 09:00 | 2020-08-22 18:00 |  |  | 2020-05-16 16:19 | 2020-08-22 16:19 |  |  | 100 | 100 | [15 empty] | 17.2374 | 0.36542 | 35.94 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3713 | 1 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018871
1346 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.11.2.3 | Plummer Block-->ORDERING-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-06-02 09:00 | 2020-07-01 18:00 | 2020-04-26 | 2020-07-07 18:00 |  |  | 2020-04-27 09:32 | 2020-07-07 09:32 |  |  | 100 | 100 | [15 empty] | 0.25899 | 0.00549 | 0.54 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3714 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018872
1347 | Task(Task)-->P (Procurement) | Bearing |  | 1.11.2.3 | Bearing-->ORDERING-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-17 09:00 | 2020-07-16 18:00 | 2020-04-26 | 2020-08-22 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.57554 | 0.012201 | 1.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3715 | 1 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018873
1348 | Task(Task)-->P (Procurement) | Belting |  | 1.11.2.3 | Belting-->ORDERING-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-28 09:00 | 2020-05-11 18:00 | 2020-05-16 09:00 | 2020-09-04 18:00 |  |  | 2020-05-16 16:24 | 2020-09-04 16:24 |  |  | 100 | 100 | [15 empty] | 32.2878 | 0.68447 | 67.32 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3716 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018874
1349 | Task(Task)-->P (Procurement) | Scrapper |  | 1.11.2.3 | Scrapper-->ORDERING-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-17 09:00 | 2020-04-15 18:00 | 2020-03-26 09:00 | 2020-05-30 18:00 |  |  | 2020-05-30 10:57 | 2020-05-30 10:57 |  |  | 100 | 100 | [15 empty] | 0.019185 | 0.000407 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3717 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018875
1350 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.11.2.3 | Technological Structure-->ORDERING-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-21 09:00 | 2020-04-19 23:59 | 2020-03-17 09:00 | 2020-07-06 18:00 |  |  | 2020-03-18 12:44 | 2020-07-06 12:44 |  |  | 100 | 100 | [15 empty] | 1.2134 | 0.025724 | 2.53 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3718 | 0 | 4 | High | [7 empty] | 0 | 0 | [246 empty] | 1018876
1351 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.11.2.3 | Takeup Component-->ORDERING-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-19 09:00 | 2020-07-18 18:00 | 2020-08-13 09:00 | 2020-11-30 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.43645 | 0.009252 | 0.91 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3719 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018877
1352 | Task(Task)-->P (Procurement) | Gear Box |  | 1.11.2.3 | Gear Box-->ORDERING-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-22 09:00 | 2020-06-20 18:00 | 2020-05-29 09:00 | 2020-06-23 18:00 |  |  | 2020-05-30 11:21 | 2020-06-23 16:51 |  |  | 100 | 100 | [15 empty] | 1.6355 | 0.034671 | 3.41 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3720 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018878
1353 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.11.2.3 | Geared Coupling-->ORDERING-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-20 09:00 | 2020-04-18 18:00 | 2020-05-30 09:00 | 2020-06-16 18:00 |  |  | 2020-06-01 11:11 | 2020-06-16 16:05 |  |  | 100 | 100 | [15 empty] | 0.35492 | 0.007524 | 0.74 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3721 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018879
1354 | Task(Task)-->P (Procurement) | Brake |  | 1.11.2.3 | Brake-->ORDERING-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-06 09:00 | 2020-05-05 18:00 | 2020-06-15 09:00 | 2020-07-03 18:00 |  |  | 2020-06-16 11:40 | 2020-07-03 11:40 |  |  | 100 | 100 | [15 empty] | 0.11031 | 0.002339 | 0.23 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3722 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018880
1355 | Task(Task)-->P (Procurement) | Maintenance Trolley |  | 1.11.2.3 | Maintenance Trolley-->ORDERING-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-12-19 09:00 | 2020-01-07 18:00 | 2020-11-16 09:00 | 2020-12-05 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.30216 | 0.006406 | 0.63 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3723 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018881
1356 | Task(Task)-->P (Procurement) | Building Structure |  | 1.11.2.3 | Building Structure-->ORDERING-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-28 09:00 | 2020-04-26 23:59 | 2020-04-13 09:00 | 2020-05-31 23:59 |  |  | 2020-05-31 18:49 | 2020-05-31 18:49 |  |  | 100 | 100 | [15 empty] | 35.6019 | 0.75473 | 74.23 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3724 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018882
1357 | Task(Task)-->P (Procurement) | 6.6KV HT VFD with Motors |  | 1.11.2.3 | 6.6KV HT VFD with Motors-->ORDERING-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-30 09:00 | 2020-02-28 18:00 | 2020-04-16 09:00 | 2020-07-18 18:00 |  |  | 2020-04-29 10:57 | 2020-04-29 10:57 |  |  | 100 | 100 | [15 empty] | 6.0192 | 0.1276 | 12.55 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3725 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018883
1358 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.11.2.3 | LIGHT & LIGHT FIXTURES-->ORDERING-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-26 09:00 | 2020-04-10 18:00 | 2020-06-02 09:00 | 2020-07-31 18:00 |  |  | 2020-06-03 15:51 | 2020-06-29 15:51 |  |  | 100 | 100 | [15 empty] | 0.2542 | 0.005389 | 0.53 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3726 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018884
1359 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.11.2.3 | LIGHTING POLES-->ORDERING-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-12 09:00 | 2020-06-25 18:00 | 2020-06-03 09:00 | 2020-06-24 18:00 |  |  | 2020-06-15 10:57 | 2020-06-15 10:57 |  |  | 100 | 100 | [15 empty] | 0.11511 | 0.00244 | 0.24 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3727 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018885
1360 | Task(Task)-->P (Procurement) | WELDING DISTRIBUTION BOARD |  | 1.11.2.3 | WELDING DISTRIBUTION BOARD-->ORDERING-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-29 09:00 | 2020-03-14 18:00 | 2020-02-13 09:00 | 2020-06-17 18:00 |  |  | 2020-02-29 08:00 | 2020-03-24 16:05 |  |  | 100 | 100 | [15 empty] | 0.35971 | 0.007626 | 0.75 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3728 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018886
1361 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.11.2.3 | CONVEYOR BELT PROTECTION SWITCHES-->ORDERING-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-23 09:00 | 2020-02-05 18:00 | 2020-03-10 09:00 | 2020-08-17 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.033573 | 0.000712 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3730 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018887
1362 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.11.2.3 | ZERO SPEED SWITCH-->ORDERING-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-15 09:00 | 2020-02-01 18:00 | 2020-03-07 09:00 | 2020-08-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3731 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018888
1363 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.11.2.3 | CHUTE BLOCK SWITCH-->ORDERING-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-19 | 2020-01-31 18:00 | 2020-01-16 09:00 | 2020-02-01 18:00 |  |  | 2020-02-01 10:57 | 2020-02-01 10:57 |  |  | 100 | 100 | [15 empty] | 0.0047962 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3732 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018889
1364 | Task(Task)-->P (Procurement) | ITP APPROVAL | 1.11.2.4 | 1.11.2 | ITP APPROVAL-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-01-08 09:00 | 2020-08-27 18:00 | 2020-05-01 09:00 | 2021-01-14 18:00 |  |  | 2020-05-01 10:26 |  |  |  | 100 | 20.2059 | [15 empty] | 5.0951 | 1.0812 | 106.33 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3733 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018890
1365 | Task(Task)-->P (Procurement) | Pulley |  | 1.11.2.4 | Pulley-->ITP APPROVAL-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-04 09:00 | 2020-05-13 18:00 | 2020-07-16 09:00 | 2020-07-16 18:00 | [6 empty] | 100 | 0 | [15 empty] | 3.1127 | 0.033654 | 3.31 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3734 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018891
1366 | Task(Task)-->P (Procurement) | Idler |  | 1.11.2.4 | Idler-->ITP APPROVAL-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-03 09:00 | 2020-04-11 18:00 | 2020-08-22 09:00 | 2020-10-22 18:00 |  |  | 2020-08-22 16:23 |  |  |  | 100 | 10 | [15 empty] | 16.8986 | 0.18271 | 17.97 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3735 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018892
1367 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.11.2.4 | Plummer Block-->ITP APPROVAL-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-02 09:00 | 2020-08-10 18:00 | 2020-07-07 09:00 | 2020-08-13 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.2539 | 0.002745 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3736 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018893
1368 | Task(Task)-->P (Procurement) | Bearing |  | 1.11.2.4 | Bearing-->ITP APPROVAL-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-17 09:00 | 2020-08-25 18:00 | 2020-05-18 09:00 | 2020-05-25 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.56423 | 0.006101 | 0.6 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3737 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018894
1369 | Task(Task)-->P (Procurement) | Belting |  | 1.11.2.4 | Belting-->ITP APPROVAL-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-12 09:00 | 2020-06-20 18:00 | 2020-09-04 09:00 | 2020-11-10 18:00 |  |  | 2020-09-04 16:30 |  |  |  | 100 | 50 | [15 empty] | 31.6532 | 0.34224 | 33.66 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3738 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018895
1370 | Task(Task)-->P (Procurement) | Scrapper |  | 1.11.2.4 | Scrapper-->ITP APPROVAL-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-16 09:00 | 2020-05-25 18:00 | 2020-05-30 09:00 | 2020-06-25 18:00 |  |  | 2020-05-30 16:32 | 2020-06-25 16:32 |  |  | 100 | 100 | [15 empty] | 0.018808 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3739 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018896
1371 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.11.2.4 | Technological Structure-->ITP APPROVAL-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-20 09:00 | 2020-05-29 18:00 | 2020-07-06 09:00 | 2020-07-16 18:00 | [6 empty] | 100 | 0 | [15 empty] | 1.1943 | 0.012913 | 1.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3740 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018897
1372 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.11.2.4 | Takeup Component-->ITP APPROVAL-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-19 | 2020-08-27 18:00 | 2020-08-13 09:00 | 2020-11-15 23:59 | [6 empty] | 100 | 0 | [15 empty] | 0.42317 | 0.004575 | 0.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3741 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018898
1373 | Task(Task)-->P (Procurement) | Gear Box |  | 1.11.2.4 | Gear Box-->ITP APPROVAL-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-06-21 | 2020-07-30 18:00 | 2020-06-23 09:00 | 2020-06-23 18:00 |  |  | 2020-06-22 16:57 | 2020-06-22 16:57 |  |  | 100 | 100 | [15 empty] | 1.608 | 0.017386 | 1.71 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3742 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018899
1374 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.11.2.4 | Geared Coupling-->ITP APPROVAL-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-19 | 2020-05-28 18:00 | 2020-06-16 09:00 | 2020-06-18 18:00 |  |  | 2020-06-16 17:31 | 2020-06-18 17:31 |  |  | 100 | 100 | [15 empty] | 0.34794 | 0.003762 | 0.37 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3743 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018900
1375 | Task(Task)-->P (Procurement) | Brake |  | 1.11.2.4 | Brake-->ITP APPROVAL-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-06 09:00 | 2020-06-14 23:59 | 2020-07-03 09:00 | 2020-10-27 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.11285 | 0.00122 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3744 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018901
1376 | Task(Task)-->P (Procurement) | Maintenance Trolley |  | 1.11.2.4 | Maintenance Trolley-->ITP APPROVAL-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-08 09:00 | 2020-02-16 23:59 | 2020-12-06 | 2021-01-14 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.29152 | 0.003152 | 0.31 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3745 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018902
1377 | Task(Task)-->P (Procurement) | Building Structure |  | 1.11.2.4 | Building Structure-->ITP APPROVAL-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-27 09:00 | 2020-05-03 23:59 | 2020-05-31 | 2020-08-04 18:00 |  |  | 2020-06-25 19:04 |  |  |  | 100 | 0 | [15 empty] | 34.9069 | 0.37742 | 37.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3746 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018903
1378 | Task(Task)-->P (Procurement) | 6.6KV HT VFD with Motors |  | 1.11.2.4 | 6.6KV HT VFD with Motors-->ITP APPROVAL-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-29 09:00 | 2020-04-08 18:00 | 2020-08-01 09:00 | 2020-09-09 18:00 | [6 empty] | 100 | 0 | [15 empty] | 7.8616 | 0.085 | 8.36 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3747 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018904
1379 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.11.2.4 | LIGHT & LIGHT FIXTURES-->ITP APPROVAL-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-11 09:00 | 2020-05-20 18:00 | 2020-07-28 09:00 | 2020-09-08 18:00 |  |  | 2020-07-08 17:23 | 2020-09-08 17:23 |  |  | 100 | 100 | [15 empty] | 0.2539 | 0.002745 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3748 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018905
1380 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.11.2.4 | LIGHTING POLES-->ITP APPROVAL-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-06-26 09:00 | 2020-08-04 18:00 | 2020-06-23 09:00 | 2020-09-08 18:00 |  |  | 2020-06-23 17:44 | 2020-09-08 17:05 |  |  | 100 | 100 | [15 empty] | 0.11285 | 0.00122 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3749 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018906
1381 | Task(Task)-->P (Procurement) | WELDING DISTRIBUTION BOARD |  | 1.11.2.4 | WELDING DISTRIBUTION BOARD-->ITP APPROVAL-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-15 | 2020-04-23 18:00 | 2020-05-01 09:00 | 2020-05-19 18:00 |  |  | 2020-05-01 10:26 | 2020-05-19 10:26 |  |  | 100 | 100 | [15 empty] | 0.34794 | 0.003762 | 0.37 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3750 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018907
1382 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.11.2.4 | CONVEYOR BELT PROTECTION SWITCHES-->ITP APPROVAL-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-06 09:00 | 2020-03-16 18:00 | 2020-09-24 09:00 | 2020-11-30 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.037615 | 0.000407 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3752 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018908
1383 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.11.2.4 | ZERO SPEED SWITCH-->ITP APPROVAL-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-02 | 2020-03-12 18:00 | 2020-08-02 | 2020-09-10 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3753 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018909
1384 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.11.2.4 | CHUTE BLOCK SWITCH-->ITP APPROVAL-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-01 09:00 | 2020-03-11 18:00 | 2020-07-02 09:00 | 2020-08-04 18:00 |  |  | 2020-07-17 16:57 | 2020-08-04 16:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3754 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018910
1385 | Task(Task)-->P (Procurement) | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE | 1.11.2.5 | 1.11.2 | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-01-08 09:00 | 2020-09-01 18:00 | 2020-02-01 09:00 | 2021-02-13 18:00 |  |  | 2020-02-11 21:30 |  |  |  | 100 | 60.6881 | [15 empty] | 14.9852 | 3.18 | 312.73 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3755 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018911
1386 | Task(Task)-->P (Procurement) | Pulley |  | 1.11.2.5 | Pulley-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-04 09:00 | 2020-06-02 18:00 | 2020-07-16 09:00 | 2020-07-16 18:00 | [6 empty] | 100 | 0 | [15 empty] | 3.1785 | 0.10107 | 9.94 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3756 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018912
1387 | Task(Task)-->P (Procurement) | Idler |  | 1.11.2.5 | Idler-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-03 09:00 | 2020-05-01 18:00 | 2020-08-22 09:00 | 2020-11-15 23:59 | [6 empty] | 100 | 0 | [15 empty] | 17.2385 | 0.54818 | 53.91 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3757 | 1 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018913
1388 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.11.2.5 | Plummer Block-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-02 09:00 | 2020-08-30 23:59 | 2020-07-07 09:00 | 2020-09-28 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.25581 | 0.008135 | 0.8 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3758 | 1 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018914
1389 | Task(Task)-->P (Procurement) | Bearing |  | 1.11.2.5 | Bearing-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-17 09:00 | 2020-07-17 18:00 | 2020-07-18 09:00 | 2020-08-22 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.57558 | 0.018303 | 1.8 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3759 | 1 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018915
1390 | Task(Task)-->P (Procurement) | Belting |  | 1.11.2.5 | Belting-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-12 09:00 | 2020-07-20 18:00 | 2020-09-04 09:00 | 2020-11-15 23:59 |  |  | 2020-09-04 16:36 |  |  |  | 100 | 50 | [15 empty] | 32.2898 | 1.0268 | 100.98 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3760 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018916
1391 | Task(Task)-->P (Procurement) | Scrapper |  | 1.11.2.5 | Scrapper-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-16 09:00 | 2020-06-14 23:59 | 2020-05-30 09:00 | 2020-07-30 18:00 |  |  | 2020-05-30 16:34 | 2020-07-30 16:34 |  |  | 100 | 100 | [15 empty] | 0.019186 | 0.00061 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3761 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018917
1392 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.11.2.5 | Technological Structure-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-20 09:00 | 2020-08-17 18:00 | 2020-07-06 09:00 | 2020-07-06 18:00 |  |  | 2020-07-06 12:45 | 2020-07-06 12:45 |  |  | 100 | 100 | [15 empty] | 1.2151 | 0.03864 | 3.8 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3762 | 0 | 4 | High | [7 empty] | 0 | 0 | [246 empty] | 1018918
1393 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.11.2.5 | Takeup Component-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-19 | 2020-09-01 18:00 | 2020-12-01 09:00 | 2021-01-14 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.43488 | 0.013829 | 1.36 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3763 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018919
1394 | Task(Task)-->P (Procurement) | Gear Box |  | 1.11.2.5 | Gear Box-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-21 | 2020-08-19 18:00 | 2020-06-23 09:00 | 2020-11-16 18:00 |  |  | 2020-06-23 16:57 |  |  |  | 100 | 50 | [15 empty] | 1.6372 | 0.052063 | 5.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3764 | 1 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018920
1395 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.11.2.5 | Geared Coupling-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-19 | 2020-06-17 18:00 | 2020-06-16 09:00 | 2020-09-02 18:00 |  |  | 2020-06-16 17:31 | 2020-09-02 17:31 |  |  | 100 | 100 | [15 empty] | 0.35494 | 0.011287 | 1.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3765 | 1 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018921
1396 | Task(Task)-->P (Procurement) | Brake |  | 1.11.2.5 | Brake-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-06 09:00 | 2020-07-04 18:00 | 2020-07-03 09:00 | 2020-10-12 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.10872 | 0.003457 | 0.34 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3766 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018922
1397 | Task(Task)-->P (Procurement) | Maintenance Trolley |  | 1.11.2.5 | Maintenance Trolley-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-08 09:00 | 2020-03-17 18:00 | 2020-12-06 | 2021-02-13 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.30058 | 0.009558 | 0.94 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3767 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018923
1398 | Task(Task)-->P (Procurement) | Building Structure |  | 1.11.2.5 | Building Structure-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-25 09:00 | 2020-05-01 18:00 | 2020-05-31 | 2020-06-22 18:00 |  |  | 2020-05-31 18:54 | 2020-05-31 18:54 |  |  | 100 | 100 | [15 empty] | 35.6058 | 1.1323 | 111.35 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3768 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018924
1399 | Task(Task)-->P (Procurement) | 6.6KV HT VFD with Motors |  | 1.11.2.5 | 6.6KV HT VFD with Motors-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-29 09:00 | 2020-05-13 18:00 | 2020-08-08 09:00 | 2020-11-10 18:00 |  |  | 2020-07-28 11:51 | 2020-09-23 15:24 |  |  | 100 | 100 | [15 empty] | 6.018 | 0.19137 | 18.82 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3769 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018925
1400 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.11.2.5 | LIGHT & LIGHT FIXTURES-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-11 09:00 | 2020-05-25 18:00 | 2020-07-10 09:00 | 2020-11-16 18:00 |  |  | 2020-07-14 10:44 |  |  |  | 100 | 0 | [15 empty] | 0.25581 | 0.008135 | 0.8 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3770 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018926
1401 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.11.2.5 | LIGHTING POLES-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-06-26 09:00 | 2020-08-09 23:59 | 2020-05-30 09:00 | 2020-08-08 18:00 |  |  | 2020-06-18 17:15 | 2020-08-07 15:00 |  |  | 100 | 100 | [15 empty] | 0.11512 | 0.003661 | 0.36 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3771 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018927
1402 | Task(Task)-->P (Procurement) | WELDING DISTRIBUTION BOARD |  | 1.11.2.5 | WELDING DISTRIBUTION BOARD-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-15 | 2020-04-28 18:00 | 2020-04-25 09:00 | 2020-07-17 18:00 |  |  | 2020-04-25 10:24 | 2020-07-17 10:24 |  |  | 100 | 100 | [15 empty] | 0.35814 | 0.011389 | 1.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3772 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018928
1403 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.11.2.5 | CONVEYOR BELT PROTECTION SWITCHES-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-06 09:00 | 2020-03-21 18:00 | 2020-08-11 09:00 | 2020-09-19 18:00 |  |  | 2020-08-11 13:12 | 2020-09-19 12:58 |  |  | 100 | 100 | [15 empty] | 0.035174 | 0.001119 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3774 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018929
1404 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.11.2.5 | ZERO SPEED SWITCH-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-02 | 2020-03-17 18:00 | 2020-08-09 | 2020-10-29 18:00 |  |  | 2020-08-09 13:17 | 2020-10-29 12:59 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3775 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018930
1405 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.11.2.5 | CHUTE BLOCK SWITCH-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-01 09:00 | 2020-03-16 18:00 | 2020-02-01 09:00 | 2020-07-15 18:00 |  |  | 2020-02-11 21:30 | 2020-07-15 21:31 |  |  | 100 | 100 | [15 empty] | 0.0031976 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3776 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018931
1406 | Task(Task)-->P (Procurement) | MANUFACTURING & RECEIPT AT SITE (MRN) | 1.11.2.6 | 1.11.2 | MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-17 09:00 | 2021-03-31 18:00 | 2020-06-22 09:00 | 2022-02-22 18:00 |  |  | 2020-07-15 21:39 |  |  |  | 54.227 | 0.10648 | [15 empty] | 59.94 | 12.7197 | 1250.9 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3777 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018932
1407 | Task(Task)-->P (Procurement) | Pulley |  | 1.11.2.6 | Pulley-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-03 09:00 | 2021-03-31 18:00 | 2020-07-16 09:00 | 2021-03-31 18:00 | [6 empty] | 53.3113 | 0 | [15 empty] | 3.1777 | 0.4042 | 39.75 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3778 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018933
1408 | Task(Task)-->P (Procurement) | Idler |  | 1.11.2.6 | Idler-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-02 09:00 | 2021-03-28 23:59 | 2020-11-16 09:00 | 2021-10-12 18:00 | [6 empty] | 58.3082 | 0 | [15 empty] | 17.2381 | 2.1926 | 215.63 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3779 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018934
1409 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.11.2.6 | Plummer Block-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-31 09:00 | 2021-02-01 18:00 | 2020-09-28 09:00 | 2021-03-15 18:00 | [6 empty] | 46.4516 | 0 | [15 empty] | 0.25742 | 0.032743 | 3.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3780 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018935
1410 | Task(Task)-->P (Procurement) | Bearing |  | 1.11.2.6 | Bearing-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-26 09:00 | 2021-01-22 18:00 | 2020-08-22 09:00 | 2021-03-31 18:00 | [6 empty] | 51.3333 | 0 | [15 empty] | 0.57559 | 0.073214 | 7.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3781 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018936
1411 | Task(Task)-->P (Procurement) | Belting |  | 1.11.2.6 | Belting-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-21 09:00 | 2021-03-31 18:00 | 2020-11-16 09:00 | 2021-07-27 18:00 | [6 empty] | 44.4882 | 0 | [15 empty] | 32.2898 | 4.1072 | 403.91 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3782 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018937
1412 | Task(Task)-->P (Procurement) | Scrapper |  | 1.11.2.6 | Scrapper-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-15 09:00 | 2020-12-11 18:00 | 2020-07-30 09:00 | 2020-12-31 18:00 | [6 empty] | 82.7778 | 0 | [15 empty] | 0.017587 | 0.002237 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3783 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018938
1413 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.11.2.6 | Technological Structure-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-19 09:00 | 2021-03-15 18:00 | 2020-07-06 09:00 | 2021-01-31 23:59 | [6 empty] | 53.7037 | 0 | [15 empty] | 1.2151 | 0.15456 | 15.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3784 | 0 | 4 | High | [7 empty] | 0 | 0 | [246 empty] | 1018939
1414 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.11.2.6 | Takeup Component-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-09-02 09:00 | 2021-01-29 18:00 | 2021-01-15 09:00 | 2021-06-13 23:59 | [6 empty] | 46.6667 | 0 | [15 empty] | 0.43569 | 0.055419 | 5.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3785 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018940
1415 | Task(Task)-->P (Procurement) | Gear Box |  | 1.11.2.6 | Gear Box-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-20 09:00 | 2021-02-20 18:00 | 2020-11-17 09:00 | 2021-05-20 18:00 | [6 empty] | 44.8649 | 0 | [15 empty] | 1.6372 | 0.20825 | 20.48 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3786 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018941
1416 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.11.2.6 | Geared Coupling-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-18 09:00 | 2020-12-15 18:00 | 2020-09-02 09:00 | 2021-02-09 18:00 |  |  | 2020-09-02 17:44 |  |  |  | 80.663 | 30 | [15 empty] | 0.35495 | 0.045148 | 4.44 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3787 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018942
1417 | Task(Task)-->P (Procurement) | Brake |  | 1.11.2.6 | Brake-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-05 | 2021-02-10 18:00 | 2020-10-12 09:00 | 2021-02-10 18:00 | [6 empty] | 58.371 | 0 | [15 empty] | 0.11032 | 0.014033 | 1.38 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3788 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018943
1418 | Task(Task)-->P (Procurement) | Maintenance Trolley |  | 1.11.2.6 | Maintenance Trolley-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-18 09:00 | 2021-03-26 18:00 | 2021-02-14 | 2022-02-22 18:00 | [6 empty] | 63.6364 | 0 | [15 empty] | 0.29979 | 0.038132 | 3.75 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3789 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018944
1419 | Task(Task)-->P (Procurement) | Building Structure |  | 1.11.2.6 | Building Structure-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-04 09:00 | 2021-03-19 18:00 | 2020-06-22 09:00 | 2021-03-31 18:00 | [6 empty] | 59.6875 | 0 | [15 empty] | 35.6058 | 4.529 | 445.39 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3790 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018945
1420 | Task(Task)-->P (Procurement) | 6.6KV HT VFD with Motors |  | 1.11.2.6 | 6.6KV HT VFD with Motors-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-14 09:00 | 2021-03-09 18:00 | 2020-11-11 09:00 | 2021-09-06 18:00 | [6 empty] | 60.3333 | 0 | [15 empty] | 6.0181 | 0.76549 | 75.28 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3791 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018946
1421 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.11.2.6 | LIGHT & LIGHT FIXTURES-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-26 09:00 | 2021-02-18 18:00 | 2020-11-17 09:00 | 2021-08-12 18:00 | [6 empty] | 62.8253 | 0 | [15 empty] | 0.25502 | 0.032438 | 3.19 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3792 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018947
1422 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.11.2.6 | LIGHTING POLES-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-10 09:00 | 2020-11-07 18:00 | 2020-09-09 09:00 | 2020-12-07 18:00 |  |  | 2020-08-07 15:03 |  |  |  | 100 | 0 | [15 empty] | 0.11592 | 0.014744 | 1.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3793 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018948
1423 | Task(Task)-->P (Procurement) | WELDING DISTRIBUTION BOARD |  | 1.11.2.6 | WELDING DISTRIBUTION BOARD-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-29 09:00 | 2020-09-26 18:00 | 2020-07-18 09:00 | 2020-12-15 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.35894 | 0.045657 | 4.49 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3794 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018949
1424 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.11.2.6 | CONVEYOR BELT PROTECTION SWITCHES-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-22 | 2020-08-05 18:00 | 2020-12-01 09:00 | 2021-04-16 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.033576 | 0.004271 | 0.42 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3796 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018950
1425 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.11.2.6 | ZERO SPEED SWITCH-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-18 09:00 | 2020-07-27 18:00 | 2020-10-30 09:00 | 2021-03-10 18:00 |  |  | 2020-10-29 13:03 |  |  |  | 100 | 0 | [15 empty] | 0.00079943 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3797 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018951
1426 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.11.2.6 | CHUTE BLOCK SWITCH-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-17 09:00 | 2020-07-31 18:00 | 2020-07-02 09:00 | 2020-11-15 23:59 |  |  | 2020-07-15 21:39 |  |  |  | 100 | 0 | [15 empty] | 0.0023983 | 0.000305 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3798 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018952
1427 | Task(Task)-->C (Construction) | CONSTRUCTION | 1.11.3 | 1.11 | CONSTRUCTION-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-22 | 2021-09-13 18:00 | 2020-08-26 09:00 | 2022-05-06 18:00 | [6 empty] | 28.9602 | 0.00506 | [15 empty] | 25.3644 | 7.2633 | 714.3 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3799 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018953
1428 | Task(Task)-->C (Construction) | CIVIL | 1.11.3.1 | 1.11.3 | CIVIL-->CONSTRUCTION-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-22 | 2021-05-26 18:00 | 2020-08-26 09:00 | 2021-09-10 18:00 | [6 empty] | 66.411 | 0.02056 | [15 empty] | 24.6199 | 1.7882 | 175.86 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3800 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018954
1429 | Task(Task)-->C (Construction) | AVAILABILITY OF FRONT BY NTPC |  | 1.11.3.1 | AVAILABILITY OF FRONT BY NTPC-->CIVIL-->CONSTRUCTION-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-06 09:00 | 2020-07-06 18:00 | 2020-08-26 09:00 | 2020-08-26 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | Weekly | Cumulative | 0 | No | No | 3801 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018955
1430 | Task(Task)-->C (Construction) | APPROACH IN PIPE CONVEYOR CORRIDOR |  | 1.11.3.1 | APPROACH IN PIPE CONVEYOR CORRIDOR-->CIVIL-->CONSTRUCTION-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-07 09:00 | 2021-05-02 23:59 | 2020-08-27 09:00 | 2021-06-22 18:00 | [6 empty] | 42.3333 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5610 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018956
1431 | Task(Task)-->C (Construction) | EXCAVATION |  | 1.11.3.1 | EXCAVATION-->CIVIL-->CONSTRUCTION-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-13 09:00 | 2021-05-08 18:00 | 2020-10-28 09:00 | 2021-08-23 18:00 | [6 empty] | 40.3333 | 0 | [15 empty] | 11.1339 | 0.1991 | 19.58 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 73381 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | Weekly | Cumulative | 0 | No | No | 3802 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | Excavation | [23 empty] | 1018957
1432 | Task(Task)-->C (Construction) | PCC |  | 1.11.3.1 | PCC-->CIVIL-->CONSTRUCTION-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-22 | 2021-05-11 18:00 | 2020-10-31 09:00 | 2021-08-26 18:00 | [6 empty] | 550.2012 | 0.36969 | [15 empty] | 5.5612 | 0.099447 | 9.78 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 1082 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | Weekly | Cumulative | 0 | No | No | 3803 | 0 | 4 | Low | ADMINISTRATOR | [6 empty] | 0 | 0 | [222 empty] | PCC | [23 empty] | 1018958
1433 | Task(Task)-->C (Construction) | RAFT OF FOUNDATIONS |  | 1.11.3.1 | RAFT OF FOUNDATIONS-->CIVIL-->CONSTRUCTION-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-17 09:00 | 2021-05-12 18:00 | 2020-11-01 | 2021-08-27 18:00 | [6 empty] | 39 | 0 | [15 empty] | 58.3077 | 1.0427 | 102.54 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 3865 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3804 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018959
1434 | Task(Task)-->C (Construction) | PEDESTALS |  | 1.11.3.1 | PEDESTALS-->CIVIL-->CONSTRUCTION-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-31 09:00 | 2021-05-26 18:00 | 2020-11-15 | 2021-09-10 18:00 | [6 empty] | 34.3333 | 0 | [15 empty] | 24.9972 | 0.447 | 43.96 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 1657 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3805 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018960
1435 | Task(Task)-->C (Construction) | STRUCTURAL WORKS | 1.11.3.2 | 1.11.3 | STRUCTURAL WORKS-->CONSTRUCTION-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-28 09:00 | 2021-06-23 18:00 | 2020-12-13 | 2021-10-08 18:00 | [6 empty] | 25 | 0 | [15 empty] | 47.5304 | 3.4523 | 339.51 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3806 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018961
1436 | Task(Task)-->C (Construction) | ERECTION OF STRUCTURAL STEEL |  | 1.11.3.2 | ERECTION OF STRUCTURAL STEEL-->STRUCTURAL WORKS-->CONSTRUCTION-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-28 09:00 | 2021-06-23 18:00 | 2020-12-13 | 2021-10-08 18:00 | [6 empty] | 25 | 0 | [15 empty] | 100 | 3.4523 | 339.51 | Plan & Actual | Quantity | Metric Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 5250 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3807 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018962
1437 | Task(Task)-->C (Construction) | MECHANICAL EQUIPMENT WORKS | 1.11.3.3 | 1.11.3 | MECHANICAL EQUIPMENT WORKS-->CONSTRUCTION-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-09-17 09:00 | 2021-07-13 18:00 | 2021-02-14 | 2021-12-10 18:00 | [6 empty] | 11.0008 | 0 | [15 empty] | 6.6107 | 0.48015 | 47.22 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5469 | 0 | 3 | High | [7 empty] | 0 | 0 | [246 empty] | 1018963
1438 | Task(Task)-->C (Construction) | ERECTION OF TECHNOLOGICAL STR. & IDLERS |  | 1.11.3.3 | ERECTION OF TECHNOLOGICAL STR. & IDLERS-->MECHANICAL EQUIPMENT WORKS-->CONSTRUCTION-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-09-17 09:00 | 2021-07-13 18:00 | 2021-02-14 | 2021-12-10 18:00 | [6 empty] | 18.3333 | 0 | [15 empty] | 60.0042 | 0.28811 | 28.34 | Plan & Actual | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3808 | 0 | 4 | High | [7 empty] | 0 | 0 | [246 empty] | 1018964
1439 | Task(Task)-->C (Construction) | ERECTION OF PULLEYS WITH FRAME |  | 1.11.3.3 | ERECTION OF PULLEYS WITH FRAME-->MECHANICAL EQUIPMENT WORKS-->CONSTRUCTION-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-04-01 09:00 | 2021-05-30 23:59 | 2021-08-16 09:00 | 2021-10-14 18:00 | [6 empty] | 0 | 0 | [15 empty] | 10.3536 | 0.049713 | 4.89 | Plan & Actual | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5433 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018965
1440 | Task(Task)-->C (Construction) | ERECTION OF DRIVES (MOTOR, GEAR BOX, COUPLING) |  | 1.11.3.3 | ERECTION OF DRIVES (MOTOR, GEAR BOX, COUPLING)-->MECHANICAL EQUIPMENT WORKS-->CONSTRUCTION-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-03-10 09:00 | 2021-05-08 18:00 | 2021-09-07 09:00 | 2021-11-05 18:00 | [6 empty] | 0 | 0 | [15 empty] | 11.751 | 0.056423 | 5.55 | Plan & Actual | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5434 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018966
1441 | Task(Task)-->C (Construction) | ERECTION OF TAKE-UP COMPONENTS |  | 1.11.3.3 | ERECTION OF TAKE-UP COMPONENTS-->MECHANICAL EQUIPMENT WORKS-->CONSTRUCTION-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-01-30 09:00 | 2021-03-30 18:00 | 2021-06-14 09:00 | 2021-08-12 18:00 | [6 empty] | 0 | 0 | [15 empty] | 17.8912 | 0.085905 | 8.45 | Plan & Actual | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5435 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018967
1442 | Task(Task)-->C (Construction) | BELT LAYING & JOINTING WORK |  | 1.11.3 | BELT LAYING & JOINTING WORK-->CONSTRUCTION-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-05-03 09:00 | 2021-08-30 18:00 | 2021-09-30 09:00 | 2022-01-27 18:00 | [6 empty] | 0 | 0 | [15 empty] | 9.2104 | 0.66898 | 65.79 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 22600 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3809 | 0 | 3 | High | [7 empty] | 0 | 0 | [246 empty] | 1018968
1443 | Task(Task)-->C (Construction) | MAINTENANCE TROLLEY |  | 1.11.3 | MAINTENANCE TROLLEY-->CONSTRUCTION-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-06-24 09:00 | 2021-07-07 18:00 | 2022-02-23 09:00 | 2022-03-08 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0.046199 | 0.003356 | 0.33 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5472 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018969
1444 | Task(Task)-->C (Construction) | ELECTRICAL & INSTRUMENTATION | 1.11.3.6 | 1.11.3 | ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-05-23 | 2021-08-30 18:00 | 2021-09-07 09:00 | 2022-04-22 18:00 | [6 empty] | 0 | 0 | [15 empty] | 11.7668 | 0.85466 | 84.05 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3810 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018970
1445 | Task(Task)-->C (Construction) | CABLE TRAY |  | 1.11.3.6 | CABLE TRAY-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-06-03 09:00 | 2021-07-07 18:00 | 2021-09-18 09:00 | 2021-10-22 18:00 | [6 empty] | 0 | 0 | [15 empty] | 21.9564 | 0.18765 | 18.45 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 43200 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3811 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018971
1446 | Task(Task)-->C (Construction) | POWER CABLE |  | 1.11.3.6 | POWER CABLE-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-07-08 09:00 | 2021-08-04 18:00 | 2021-10-23 09:00 | 2021-11-19 18:00 | [6 empty] | 0 | 0 | [15 empty] | 20.6593 | 0.17657 | 17.36 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 122676 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3812 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018972
1447 | Task(Task)-->C (Construction) | CONTROL CABLE |  | 1.11.3.6 | CONTROL CABLE-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-07-26 09:00 | 2021-08-04 18:00 | 2021-11-10 09:00 | 2021-11-19 18:00 | [6 empty] | 0 | 0 | [15 empty] | 4.8792 | 0.0417 | 4.1 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 29000 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3813 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018973
1448 | Task(Task)-->C (Construction) | EARTHING |  | 1.11.3.6 | EARTHING-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-06-05 09:00 | 2021-07-07 18:00 | 2021-09-20 09:00 | 2021-10-22 18:00 | [6 empty] | 0 | 0 | [15 empty] | 8.7588 | 0.074857 | 7.36 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 33000 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3814 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018974
1449 | Task(Task)-->C (Construction) | EARTH PIT |  | 1.11.3.6 | EARTH PIT-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-05-23 | 2021-05-26 18:00 | 2021-09-07 09:00 | 2021-09-10 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5324 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018975
1450 | Task(Task)-->C (Construction) | LIGHTING |  | 1.11.3.6 | LIGHTING-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-05-23 | 2021-07-07 18:00 | 2021-09-07 09:00 | 2021-10-22 18:00 | [6 empty] | 0 | 0 | [15 empty] | 41.8184 | 0.3574 | 35.14 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5325 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018976
1451 | Task(Task)-->C (Construction) | FIELD INTRUMENTS |  | 1.11.3.6 | FIELD INTRUMENTS-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-08-03 09:00 | 2021-08-05 18:00 | 2021-11-18 09:00 | 2021-11-20 18:00 | [6 empty] | 0 | 0 | [15 empty] | 1.5352 | 0.01312 | 1.29 | Plan & Actual | Quantity | Lot | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5326 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018977
1452 | Task(Task)-->C (Construction) | MOTOR TERMINATION |  | 1.11.3.6 | MOTOR TERMINATION-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-08-02 09:00 | 2021-08-05 18:00 | 2021-11-17 09:00 | 2021-11-20 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0.39272 | 0.003356 | 0.33 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5327 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018978
1453 | Task(Task)-->C (Construction) | NO LOAD RUN OF MOTOR |  | 1.11.3.6 | NO LOAD RUN OF MOTOR-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-08-27 09:00 | 2021-08-30 18:00 | 2022-04-19 09:00 | 2022-04-22 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5473 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018979
1454 | Task(Task)-->C (Construction) | NO LOAD COMMISSIONING & SYSTEM READYNESS FOR LOAD & TRIAL OPERATION |  | 1.11.3 | NO LOAD COMMISSIONING & SYSTEM READYNESS FOR LOAD & TRIAL OPERATION-->CONSTRUCTION-->PIPE CONVEYOR PC 2A & PC 2B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-08-31 09:00 | 2021-09-13 18:00 | 2022-04-23 09:00 | 2022-05-06 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0.2156 | 0.015659 | 1.54 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5328 | 0 | 3 | High | [7 empty] | 0 | 0 | [246 empty] | 1018980
1455 | Task(Task)-->E (Engineering) | TROUGH CONVEYOR SY 3A & SY 3B | 1.12 | 1 | TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-09-27 09:00 | 2021-09-08 18:00 | 2019-12-30 09:00 | 2022-04-06 18:00 |  |  | 2019-12-30 10:57 |  |  |  | 85.7276 | 25.5498 | [15 empty] | 0.82924 | 0.82924 | 81.55 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3815 | 0 | 1 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018981
1456 | Task(Task)-->E (Engineering) | ENGINEERING | 1.12.1 | 1.12 | ENGINEERING-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-12-17 18:00 | 2020-06-29 17:40 | 2020-01-28 18:00 | 2020-09-03 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 81.2646 | [15 empty] | 1.9742 | 0.016371 | 1.61 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3816 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018982
1457 | Task(Task)-->E (Engineering) | MECHANICAL | 1.12.1.1 | 1.12.1 | MECHANICAL-->ENGINEERING-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-12-17 18:00 | 2020-02-06 17:40 | 2020-01-28 18:00 | 2020-04-19 23:59 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 80 | [15 empty] | 33.5404 | 0.005491 | 0.54 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3817 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036106
1458 | Task(Task)-->E (Engineering) | G.A & MARKING OF CONV. SY-1A / 1B |  | 1.12.1.1 | G.A & MARKING OF CONV. SY-1A / 1B-->MECHANICAL-->ENGINEERING-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-12-17 18:00 | 2020-02-06 17:40 | 2020-01-28 18:00 | 2020-04-19 23:59 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-0021 |  | 2020-02-13 10:26 | 7012-155-PVM-B-021 |  |  |  | A |  |  |  | 100 | 0.005491 | 0.54 | Plan & Actual | Date |  | 0 | 0 | 0 | 200 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3818 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-12-17 18:00 | 2020-01-28 18:00 |  | 10 | 2020-01-28 23:31 |  |  | 2019-12-30 17:40 | 2020-02-12 18:00 |  | 30 | 2020-02-12 23:31 |  |  | 2020-01-04 17:40 | 2020-02-14 18:00 |  | 35 | 2020-02-14 23:31 |  |  | 2020-01-10 23:59 | 2020-02-21 18:00 |  | 65 | 2020-02-21 23:31 |  |  | 2020-01-16 17:40 | 2020-04-05 23:59 |  | 80 | 2020-04-05 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-02-06 17:40 | 2020-04-19 23:59 |  | 100 | [122 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 21 |  |  |  |  | 101035
1459 | Task(Task)-->E (Engineering) | CIVIL | 1.12.1.2 | 1.12.1 | CIVIL-->ENGINEERING-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-02-23 23:59 | 2020-05-25 17:40 | 2020-05-05 18:00 | 2020-09-03 18:00 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 87.2716 | [15 empty] | 17.3913 | 0.002847 | 0.28 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3841 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036107
1460 | Task(Task)-->E (Engineering) | CONV. SY-1A / 1B : NUM & RC DETAILS OF FDN |  | 1.12.1.2 | CONV. SY-1A / 1B : NUM & RC DETAILS OF FDN-->CIVIL-->ENGINEERING-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-24 18:00 | 2020-05-25 17:40 | 2020-08-12 09:00 | 2020-09-01 18:00 |  |  | 2020-02-21 15:37 | 2020-09-02 00:38 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-NR-0024 |  | 2020-02-13 11:42 | 7012-155-PVC-C-073 |  |  |  | A |  |  |  | 36.3636 | 0.001035 | 0.16 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 4.31 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3842 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-24 18:00 | 2020-05-05 18:00 |  | 10 |  |  |  | 2020-04-13 17:40 | 2020-06-24 18:00 |  | 30 |  |  |  | 2020-04-18 17:40 | 2020-06-27 18:00 |  | 35 | 2020-08-12 17:50 |  |  | 2020-04-24 23:59 | 2020-07-04 18:00 |  | 65 | 2020-08-13 19:57 |  |  | 2020-05-01 17:40 | 2020-07-25 18:00 |  | 80 | 2020-09-01 23:28 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-25 17:40 | 2020-08-08 18:00 |  | 100 | 2020-09-02 00:39 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 174 |  |  |  |  | 101184
1461 | Task(Task)-->E (Engineering) | CONV. SY-1A / 1B : DESIGN CALCULATION OF SUPER STRUCTURE |  | 1.12.1.2 | CONV. SY-1A / 1B : DESIGN CALCULATION OF SUPER STRUCTURE-->CIVIL-->ENGINEERING-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-23 23:59 | 2020-04-23 17:40 | 2020-08-07 09:00 | 2020-09-01 18:00 |  |  | 2020-02-21 15:38 | 2020-09-02 00:38 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0020B |  | 2020-02-13 12:42 | 7012-155-PVC-U-070 |  |  |  | A |  |  |  | 27.2727 | 0.000776 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3843 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-23 23:59 | 2020-04-05 23:59 |  | 10 | 2020-04-05 23:31 |  |  | 2020-03-12 17:40 | 2020-05-25 18:00 |  | 30 |  |  |  | 2020-03-19 17:40 | 2020-05-28 18:00 |  | 35 |  |  |  | 2020-03-25 23:59 | 2020-06-04 18:00 |  | 65 | 2020-08-13 19:58 |  |  | 2020-04-01 17:40 | 2020-06-25 18:00 |  | 80 | 2020-09-01 23:27 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-23 17:40 | 2020-07-09 18:00 |  | 100 | 2020-09-02 00:39 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 171 |  |  |  |  | 101466
1462 | Task(Task)-->E (Engineering) | CONV. SY-1A / 1B : DESIGN CALCULATION OF SUB STRUCTURE |  | 1.12.1.2 | CONV. SY-1A / 1B : DESIGN CALCULATION OF SUB STRUCTURE-->CIVIL-->ENGINEERING-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-24 18:00 | 2020-05-25 17:40 | 2020-05-05 18:00 | 2020-09-03 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0021B |  | 2020-02-13 12:42 | 7012-155-PVC-U-071 |  |  |  | A |  |  |  | 36.3636 | 0.001035 | 0.16 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3844 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-24 18:00 | 2020-05-05 18:00 |  | 10 | 2020-05-05 23:31 |  |  | 2020-04-13 17:40 | 2020-06-24 18:00 |  | 30 |  |  |  | 2020-04-18 17:40 | 2020-06-27 18:00 |  | 35 |  |  |  | 2020-04-24 23:59 | 2020-07-04 18:00 |  | 65 | 2020-08-13 19:58 |  |  | 2020-05-01 17:40 | 2020-07-25 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-25 17:40 | 2020-08-08 18:00 |  | 100 | [122 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 172 |  |  |  |  | 101467
1463 | Task(Task)-->E (Engineering) | STRUCTURAL | 1.12.1.3 | 1.12.1 | STRUCTURAL-->ENGINEERING-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-23 23:59 | 2020-04-23 17:40 | 2020-04-05 23:59 | 2020-09-01 18:00 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 80 | [15 empty] | 7.4534 | 0.00122 | 0.12 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3845 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036108
1464 | Task(Task)-->E (Engineering) | CONV. SY-1A / 1B : STRUCTURAL GA |  | 1.12.1.3 | CONV. SY-1A / 1B : STRUCTURAL GA-->STRUCTURAL-->ENGINEERING-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-23 23:59 | 2020-04-23 17:40 | 2020-04-05 23:59 | 2020-09-01 18:00 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-GA-0022 |  | 2020-02-13 11:42 | 7012-155-PVC-B-072 |  |  |  | A |  |  |  | 100 | 0.00122 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 43.49 | 0 | 47.17 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3846 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-23 23:59 | 2020-04-05 23:59 |  | 10 | 2020-04-05 23:31 |  |  | 2020-03-12 17:40 | 2020-05-25 18:00 |  | 30 |  |  |  | 2020-03-19 17:40 | 2020-05-28 18:00 |  | 35 | 2020-07-31 22:52 |  |  | 2020-03-25 23:59 | 2020-06-04 18:00 |  | 65 | 2020-08-13 19:57 |  |  | 2020-04-01 17:40 | 2020-06-25 18:00 |  | 80 | 2020-09-01 23:30 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-23 17:40 | 2020-07-09 18:00 |  | 100 | [122 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 173 |  |  |  |  | 101183
1465 | Task(Task)-->E (Engineering) | ELECTRICAL | 1.12.1.4 | 1.12.1 | ELECTRICAL-->ENGINEERING-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-09 18:00 | 2020-06-29 17:40 | 2020-04-28 09:00 | 2020-06-21 23:59 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 | [15 empty] | 41.6149 | 0.006813 | 0.67 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3849 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036109
1466 | Task(Task)-->E (Engineering) | LIGHTING LAYOUT PLAN WITH POWER DISTRIBUTION ARRANGEMENT, SECTIONAL VIEW, BOM OFCONV. SY-1A / 1B |  | 1.12.1.4 | LIGHTING LAYOUT PLAN WITH POWER DISTRIBUTION ARRANGEMENT, SECTIONAL VIEW, BOM OFCONV. SY-1A / 1B-->ELECTRICAL-->ENGINEERING-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-09 18:00 | 2020-06-29 17:40 | 2020-04-28 09:00 | 2020-06-21 23:59 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5082 |  | 2020-02-13 11:45 | 7012-155-PVE-G-044 |  |  |  | A |  |  |  | 100 | 0.006813 | 0.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 248.42 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3850 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-05-09 18:00 | 2020-05-10 23:59 |  | 10 | 2020-04-20 23:31 |  |  | 2020-05-18 17:40 | 2020-05-17 23:59 |  | 30 | 2020-04-25 23:31 |  |  | 2020-05-25 17:40 | 2020-05-24 23:59 |  | 35 | 2020-04-25 23:31 |  |  | 2020-05-30 23:59 | 2020-05-31 23:59 |  | 65 | 2020-04-28 23:31 |  |  | 2020-06-05 17:40 | 2020-06-21 23:59 |  | 80 | 2020-05-11 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-29 17:40 | 2020-06-21 23:59 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 279 |  |  |  |  | 101290
1467 | Task(Task)-->P (Procurement) | PROCUREMENT | 1.12.2 | 1.12 | PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-09-27 09:00 | 2021-02-13 18:00 | 2019-12-30 09:00 | 2021-06-13 23:59 |  |  | 2019-12-30 10:57 |  |  |  | 96.4977 | 29.3251 | [15 empty] | 81.6554 | 0.67712 | 66.59 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3851 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018987
1468 | Task(Task)-->P (Procurement) | PURCHASE REQUISITION | 1.12.2.1 | 1.12.2 | PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-09-27 09:00 | 2020-05-19 18:00 | 2019-12-30 09:00 | 2020-05-29 18:00 |  |  | 2019-12-30 10:57 |  |  |  | 100 | 100 | [15 empty] | 5.0008 | 0.033861 | 3.33 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3852 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018988
1469 | Task(Task)-->P (Procurement) | Pulley |  | 1.12.2.1 | Pulley-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-09-27 09:00 | 2019-09-27 18:00 | 2020-02-05 09:00 | 2020-02-05 18:00 |  |  | 2020-02-05 16:16 | 2020-02-05 16:16 |  |  | 100 | 100 | [15 empty] | 15.015 | 0.005084 | 0.5 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3853 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018989
1470 | Task(Task)-->P (Procurement) | Idler |  | 1.12.2.1 | Idler-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-19 09:00 | 2019-12-19 18:00 | 2020-02-13 09:00 | 2020-02-13 18:00 |  |  | 2020-02-13 15:44 | 2020-02-13 15:44 |  |  | 100 | 100 | [15 empty] | 5.1051 | 0.001729 | 0.17 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3854 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018990
1471 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.12.2.1 | Plummer Block-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-17 | 2020-05-17 23:59 | 2020-02-10 09:00 | 2020-02-10 18:00 |  |  | 2020-02-10 09:26 | 2020-02-10 09:26 |  |  | 100 | 100 | [15 empty] | 1.2012 | 0.000407 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3855 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018991
1472 | Task(Task)-->P (Procurement) | Bearing |  | 1.12.2.1 | Bearing-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-17 | 2020-05-17 23:59 | 2020-02-10 09:00 | 2020-02-10 18:00 |  |  | 2020-02-10 09:36 | 2020-02-10 09:36 |  |  | 100 | 100 | [15 empty] | 1.8018 | 0.00061 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3856 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018992
1473 | Task(Task)-->P (Procurement) | Belting |  | 1.12.2.1 | Belting-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-07 09:00 | 2019-11-07 18:00 | 2020-01-20 09:00 | 2020-01-20 18:00 |  |  | 2020-01-20 15:54 | 2020-01-20 15:54 |  |  | 100 | 100 | [15 empty] | 6.006 | 0.002034 | 0.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3857 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018993
1474 | Task(Task)-->P (Procurement) | Scrapper |  | 1.12.2.1 | Scrapper-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-17 | 2019-11-17 23:59 | 2020-03-11 09:00 | 2020-03-11 18:00 |  |  | 2020-03-11 10:57 | 2020-03-11 10:57 |  |  | 100 | 100 | [15 empty] | 0.6006 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3858 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018994
1475 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.12.2.1 | Technological Structure-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-10 09:00 | 2020-03-10 18:00 | 2020-03-11 09:00 | 2020-03-11 18:00 |  |  | 2020-03-11 12:41 | 2020-03-11 12:41 |  |  | 100 | 100 | [15 empty] | 5.7057 | 0.001932 | 0.19 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3859 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018995
1476 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.12.2.1 | Takeup Component-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-19 09:00 | 2020-05-19 18:00 | 2020-04-16 09:00 | 2020-04-16 18:00 |  |  | 2020-04-16 10:57 | 2020-04-16 10:57 |  |  | 100 | 100 | [15 empty] | 0.3003 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3860 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018996
1477 | Task(Task)-->P (Procurement) | Gear Box |  | 1.12.2.1 | Gear Box-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-13 09:00 | 2019-11-13 18:00 | 2020-01-20 09:00 | 2020-01-20 18:00 |  |  | 2020-01-20 11:17 | 2020-01-20 11:17 |  |  | 100 | 100 | [15 empty] | 3.003 | 0.001017 | 0.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3861 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018997
1478 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.12.2.1 | Geared Coupling-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-21 09:00 | 2019-11-21 18:00 | 2020-01-22 09:00 | 2020-01-22 18:00 |  |  | 2020-01-22 10:41 | 2020-01-22 10:41 |  |  | 100 | 100 | [15 empty] | 0.3003 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3862 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018998
1479 | Task(Task)-->P (Procurement) | Fluid Coupling |  | 1.12.2.1 | Fluid Coupling-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-25 09:00 | 2019-11-25 18:00 | 2020-01-22 09:00 | 2020-01-22 18:00 |  |  | 2020-01-22 09:54 | 2020-01-22 09:54 |  |  | 100 | 100 | [15 empty] | 3.003 | 0.001017 | 0.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3863 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1018999
1480 | Task(Task)-->P (Procurement) | Brake |  | 1.12.2.1 | Brake-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-18 09:00 | 2019-12-18 18:00 | 2020-04-04 09:00 | 2020-04-04 18:00 |  |  | 2020-04-04 11:33 | 2020-04-04 11:33 |  |  | 100 | 100 | [15 empty] | 0.3003 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3864 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019000
1481 | Task(Task)-->P (Procurement) | Building Structure |  | 1.12.2.1 | Building Structure-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-15 09:00 | 2020-04-15 18:00 | 2020-05-29 09:00 | 2020-05-29 18:00 |  |  | 2020-05-31 18:44 | 2020-05-31 18:44 |  |  | 100 | 100 | [15 empty] | 36.3363 | 0.012304 | 1.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3865 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019001
1482 | Task(Task)-->P (Procurement) | HT AC MOTORS |  | 1.12.2.1 | HT AC MOTORS-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-07 09:00 | 2020-01-07 18:00 | 2020-01-17 09:00 | 2020-01-17 18:00 |  |  | 2020-01-17 10:57 | 2020-01-17 10:57 |  |  | 100 | 100 | [15 empty] | 8.7087 | 0.002949 | 0.29 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3866 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019002
1483 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.12.2.1 | LIGHT & LIGHT FIXTURES-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-10 09:00 | 2020-03-10 18:00 | 2020-03-16 09:00 | 2020-03-16 18:00 |  |  | 2020-03-16 10:57 | 2020-03-16 10:57 |  |  | 100 | 100 | [15 empty] | 8.1081 | 0.002745 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3867 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019003
1484 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.12.2.1 | LIGHTING POLES-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-27 09:00 | 2020-03-27 18:00 | 2020-04-30 09:00 | 2020-04-30 18:00 |  |  | 2020-04-30 10:57 | 2020-04-30 10:57 |  |  | 100 | 100 | [15 empty] | 3.6036 | 0.00122 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3868 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019004
1485 | Task(Task)-->P (Procurement) | LPBS |  | 1.12.2.1 | LPBS-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-20 09:00 | 2020-03-20 18:00 | 2020-04-14 09:00 | 2020-04-14 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3869 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019005
1486 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.12.2.1 | CONVEYOR BELT PROTECTION SWITCHES-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-08 09:00 | 2020-01-08 18:00 | 2020-01-08 09:00 | 2020-01-08 18:00 |  |  | 2020-01-08 10:57 | 2020-01-08 10:57 |  |  | 100 | 100 | [15 empty] | 0.9009 | 0.000305 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3871 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019006
1487 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.12.2.1 | ZERO SPEED SWITCH-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-30 09:00 | 2019-12-30 18:00 | 2019-12-30 09:00 | 2019-12-30 18:00 |  |  | 2019-12-30 10:57 | 2019-12-30 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3872 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019007
1488 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.12.2.1 | CHUTE BLOCK SWITCH-->PURCHASE REQUISITION-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-03 09:00 | 2020-01-03 18:00 | 2020-01-03 09:00 | 2020-01-03 18:00 |  |  | 2020-01-03 10:57 | 2020-01-03 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3873 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019008
1489 | Task(Task)-->P (Procurement) | TECHNICAL CLEARANCE | 1.12.2.2 | 1.12.2 | TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-09-28 09:00 | 2020-06-18 18:00 | 2019-12-30 09:00 | 2020-06-12 18:00 |  |  | 2020-01-16 10:57 |  |  |  | 100 | 100 | [15 empty] | 5.0008 | 0.033861 | 3.33 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3874 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019009
1490 | Task(Task)-->P (Procurement) | Pulley |  | 1.12.2.2 | Pulley-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-09-28 09:00 | 2020-01-04 18:00 | 2020-02-05 09:00 | 2020-02-10 18:00 |  |  | 2020-02-06 16:19 | 2020-02-10 16:19 |  |  | 100 | 100 | [15 empty] | 15.015 | 0.005084 | 0.5 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3875 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019010
1491 | Task(Task)-->P (Procurement) | Idler |  | 1.12.2.2 | Idler-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-20 09:00 | 2020-02-01 18:00 | 2020-02-13 09:00 | 2020-03-26 18:00 |  |  | 2020-02-14 10:57 | 2020-03-26 10:57 |  |  | 100 | 100 | [15 empty] | 5.1051 | 0.001729 | 0.17 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3876 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019011
1492 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.12.2.2 | Plummer Block-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-18 09:00 | 2020-06-01 18:00 | 2020-02-10 09:00 | 2020-02-10 18:00 |  |  | 2020-02-10 09:28 | 2020-02-10 09:28 |  |  | 100 | 100 | [15 empty] | 1.2012 | 0.000407 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3877 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019012
1493 | Task(Task)-->P (Procurement) | Bearing |  | 1.12.2.2 | Bearing-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-18 09:00 | 2020-06-16 18:00 | 2020-02-10 09:00 | 2020-02-10 18:00 |  |  | 2020-02-10 09:37 | 2020-02-10 09:37 |  |  | 100 | 100 | [15 empty] | 1.8018 | 0.00061 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3878 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019013
1494 | Task(Task)-->P (Procurement) | Belting |  | 1.12.2.2 | Belting-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-08 09:00 | 2020-01-06 18:00 | 2020-01-20 09:00 | 2020-05-16 18:00 |  |  | 2020-05-16 10:57 | 2020-05-16 10:57 |  |  | 100 | 100 | [15 empty] | 6.006 | 0.002034 | 0.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3879 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019014
1495 | Task(Task)-->P (Procurement) | Scrapper |  | 1.12.2.2 | Scrapper-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-18 09:00 | 2020-03-16 18:00 | 2020-03-11 09:00 | 2020-03-26 18:00 |  |  | 2020-03-26 10:57 | 2020-03-26 10:57 |  |  | 100 | 100 | [15 empty] | 0.6006 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3880 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019015
1496 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.12.2.2 | Technological Structure-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-11 09:00 | 2020-03-20 18:00 | 2020-03-11 09:00 | 2020-03-17 18:00 |  |  | 2020-03-12 12:43 | 2020-03-17 12:43 |  |  | 100 | 100 | [15 empty] | 5.7057 | 0.001932 | 0.19 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3881 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019016
1497 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.12.2.2 | Takeup Component-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-20 09:00 | 2020-06-18 18:00 | 2020-04-16 09:00 | 2020-04-16 18:00 |  |  | 2020-04-16 10:57 | 2020-04-16 10:57 |  |  | 100 | 100 | [15 empty] | 0.3003 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3882 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019017
1498 | Task(Task)-->P (Procurement) | Gear Box |  | 1.12.2.2 | Gear Box-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-14 09:00 | 2020-02-26 18:00 | 2020-01-20 09:00 | 2020-03-20 18:00 |  |  | 2020-01-22 11:19 | 2020-03-20 11:19 |  |  | 100 | 100 | [15 empty] | 3.003 | 0.001017 | 0.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3883 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019018
1499 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.12.2.2 | Geared Coupling-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-22 09:00 | 2020-03-19 18:00 | 2020-01-22 09:00 | 2020-04-13 18:00 |  |  | 2020-04-13 10:46 | 2020-04-13 10:46 |  |  | 100 | 100 | [15 empty] | 0.3003 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3884 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019019
1500 | Task(Task)-->P (Procurement) | Fluid Coupling |  | 1.12.2.2 | Fluid Coupling-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-26 09:00 | 2020-03-01 23:59 | 2020-01-22 09:00 | 2020-04-13 18:00 |  |  | 2020-01-23 09:54 | 2020-04-13 09:54 |  |  | 100 | 100 | [15 empty] | 3.003 | 0.001017 | 0.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3885 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019020
1501 | Task(Task)-->P (Procurement) | Brake |  | 1.12.2.2 | Brake-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-19 09:00 | 2020-03-09 18:00 | 2020-04-04 09:00 | 2020-04-22 18:00 |  |  | 2020-04-05 11:34 | 2020-04-22 11:34 |  |  | 100 | 100 | [15 empty] | 0.3003 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3886 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019021
1502 | Task(Task)-->P (Procurement) | Building Structure |  | 1.12.2.2 | Building Structure-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-16 09:00 | 2020-04-22 18:00 | 2020-05-29 09:00 | 2020-05-29 18:00 |  |  | 2020-05-29 17:31 | 2020-05-29 17:31 |  |  | 100 | 100 | [15 empty] | 36.3363 | 0.012304 | 1.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3887 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019022
1503 | Task(Task)-->P (Procurement) | HT AC MOTORS |  | 1.12.2.2 | HT AC MOTORS-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-08 09:00 | 2020-01-29 18:00 | 2020-01-17 09:00 | 2020-04-11 18:00 |  |  | 2020-04-11 10:57 | 2020-04-11 10:57 |  |  | 100 | 100 | [15 empty] | 8.7087 | 0.002949 | 0.29 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3888 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019023
1504 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.12.2.2 | LIGHT & LIGHT FIXTURES-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-11 09:00 | 2020-03-25 18:00 | 2020-03-16 09:00 | 2020-06-02 18:00 |  |  | 2020-06-02 10:57 | 2020-06-02 10:57 |  |  | 100 | 100 | [15 empty] | 8.1081 | 0.002745 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3889 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019024
1505 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.12.2.2 | LIGHTING POLES-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-28 09:00 | 2020-05-11 18:00 | 2020-04-30 09:00 | 2020-06-03 18:00 |  |  | 2020-06-03 10:57 | 2020-06-03 10:57 |  |  | 100 | 100 | [15 empty] | 3.6036 | 0.00122 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3890 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019025
1506 | Task(Task)-->P (Procurement) | LPBS |  | 1.12.2.2 | LPBS-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-21 09:00 | 2020-04-04 18:00 | 2020-04-14 09:00 | 2020-06-12 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3891 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019026
1507 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.12.2.2 | CONVEYOR BELT PROTECTION SWITCHES-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-09 09:00 | 2020-01-22 18:00 | 2020-01-08 09:00 | 2020-03-10 18:00 |  |  | 2020-03-10 10:57 | 2020-03-10 10:57 |  |  | 100 | 100 | [15 empty] | 0.9009 | 0.000305 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3893 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019027
1508 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.12.2.2 | ZERO SPEED SWITCH-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-31 09:00 | 2020-01-14 18:00 | 2019-12-30 09:00 | 2020-03-07 18:00 |  |  | 2020-03-07 10:57 | 2020-03-07 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3894 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019028
1509 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.12.2.2 | CHUTE BLOCK SWITCH-->TECHNICAL CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-04 09:00 | 2020-01-18 18:00 | 2020-01-03 09:00 | 2020-01-16 18:00 |  |  | 2020-01-16 10:57 | 2020-01-16 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3895 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019029
1510 | Task(Task)-->P (Procurement) | ORDERING | 1.12.2.3 | 1.12.2 | ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-01-05 | 2020-07-18 18:00 | 2020-01-16 09:00 | 2020-09-04 18:00 |  |  | 2020-01-05 08:00 |  |  |  | 100 | 98.6489 | [15 empty] | 10.0015 | 0.067722 | 6.66 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3896 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019030
1511 | Task(Task)-->P (Procurement) | Pulley |  | 1.12.2.3 | Pulley-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-05 | 2020-02-03 18:00 | 2020-02-10 09:00 | 2020-03-21 18:00 |  |  | 2020-01-05 08:00 | 2020-03-21 16:05 |  |  | 100 | 100 | [15 empty] | 15.015 | 0.010168 | 1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3897 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019031
1512 | Task(Task)-->P (Procurement) | Idler |  | 1.12.2.3 | Idler-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-02 | 2020-03-02 18:00 | 2020-03-26 09:00 | 2020-04-30 18:00 |  |  | 2020-02-02 08:00 | 2020-04-29 16:05 |  |  | 100 | 100 | [15 empty] | 5.1051 | 0.003457 | 0.34 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3898 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019032
1513 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.12.2.3 | Plummer Block-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-06-02 09:00 | 2020-07-01 18:00 | 2020-02-10 09:00 | 2020-03-24 18:00 |  |  | 2020-02-11 09:32 | 2020-03-24 09:32 |  |  | 100 | 100 | [15 empty] | 1.0511 | 0.000712 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3899 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019033
1514 | Task(Task)-->P (Procurement) | Bearing |  | 1.12.2.3 | Bearing-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-06-17 09:00 | 2020-07-16 18:00 | 2020-02-10 09:00 | 2020-03-24 18:00 |  |  | 2020-02-11 09:40 | 2020-03-24 09:40 |  |  | 100 | 100 | [15 empty] | 1.952 | 0.001322 | 0.13 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3900 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019034
1515 | Task(Task)-->P (Procurement) | Belting |  | 1.12.2.3 | Belting-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-07 09:00 | 2020-02-20 18:00 | 2020-05-16 09:00 | 2020-09-04 18:00 |  |  | 2020-05-16 16:24 | 2020-09-04 16:24 |  |  | 100 | 100 | [15 empty] | 5.8559 | 0.003966 | 0.39 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3901 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019035
1516 | Task(Task)-->P (Procurement) | Scrapper |  | 1.12.2.3 | Scrapper-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-17 09:00 | 2020-04-15 18:00 | 2020-03-26 09:00 | 2020-05-30 18:00 |  |  | 2020-05-30 10:57 | 2020-05-30 10:57 |  |  | 100 | 100 | [15 empty] | 0.6006 | 0.000407 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3902 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019036
1517 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.12.2.3 | Technological Structure-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-21 09:00 | 2020-04-19 23:59 | 2020-03-17 09:00 | 2020-07-06 18:00 |  |  | 2020-03-18 12:44 | 2020-07-06 12:44 |  |  | 100 | 100 | [15 empty] | 5.7057 | 0.003864 | 0.38 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3903 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019037
1518 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.12.2.3 | Takeup Component-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-19 09:00 | 2020-07-18 18:00 | 2020-04-16 09:00 | 2020-08-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.3003 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3904 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019038
1519 | Task(Task)-->P (Procurement) | Gear Box |  | 1.12.2.3 | Gear Box-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-27 09:00 | 2020-03-27 18:00 | 2020-03-20 09:00 | 2020-04-30 18:00 |  |  | 2020-03-21 11:21 | 2020-04-30 11:21 |  |  | 100 | 100 | [15 empty] | 3.003 | 0.002034 | 0.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3905 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019039
1520 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.12.2.3 | Geared Coupling-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-20 09:00 | 2020-04-18 18:00 | 2020-04-13 09:00 | 2020-04-30 18:00 |  |  | 2020-04-14 11:11 | 2020-04-30 11:11 |  |  | 100 | 100 | [15 empty] | 0.45045 | 0.000305 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3906 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019040
1521 | Task(Task)-->P (Procurement) | Fluid Coupling |  | 1.12.2.3 | Fluid Coupling-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-02 09:00 | 2020-03-31 18:00 | 2020-04-13 09:00 | 2020-05-18 18:00 |  |  | 2020-04-14 09:54 | 2020-05-18 16:05 |  |  | 100 | 100 | [15 empty] | 3.1532 | 0.002135 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3907 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019041
1522 | Task(Task)-->P (Procurement) | Brake |  | 1.12.2.3 | Brake-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-10 09:00 | 2020-04-08 18:00 | 2020-04-22 09:00 | 2020-05-18 18:00 |  |  | 2020-04-23 11:37 | 2020-05-18 16:05 |  |  | 100 | 100 | [15 empty] | 0.3003 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3908 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019042
1523 | Task(Task)-->P (Procurement) | Building Structure |  | 1.12.2.3 | Building Structure-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-23 09:00 | 2020-05-22 18:00 | 2020-05-29 09:00 | 2020-05-31 23:59 |  |  | 2020-05-31 18:49 | 2020-05-31 18:49 |  |  | 100 | 100 | [15 empty] | 36.1862 | 0.024506 | 2.41 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3909 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019043
1524 | Task(Task)-->P (Procurement) | HT AC MOTORS |  | 1.12.2.3 | HT AC MOTORS-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-30 09:00 | 2020-02-20 18:00 | 2020-04-11 09:00 | 2020-06-25 18:00 |  |  | 2020-04-13 09:41 | 2020-06-25 09:41 |  |  | 100 | 100 | [15 empty] | 8.7087 | 0.005898 | 0.58 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3910 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019044
1525 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.12.2.3 | LIGHT & LIGHT FIXTURES-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-26 09:00 | 2020-04-10 18:00 | 2020-06-02 09:00 | 2020-07-31 18:00 |  |  | 2020-06-03 15:51 | 2020-06-29 15:51 |  |  | 100 | 100 | [15 empty] | 7.958 | 0.005389 | 0.53 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3911 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019045
1526 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.12.2.3 | LIGHTING POLES-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-12 09:00 | 2020-06-25 18:00 | 2020-06-03 09:00 | 2020-06-24 18:00 |  |  | 2020-06-15 10:57 | 2020-06-15 10:57 |  |  | 100 | 100 | [15 empty] | 3.6036 | 0.00244 | 0.24 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3912 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019046
1527 | Task(Task)-->P (Procurement) | LPBS |  | 1.12.2.3 | LPBS-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-05 | 2020-04-20 18:00 | 2020-06-12 09:00 | 2020-08-19 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.15015 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3913 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019047
1528 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.12.2.3 | CONVEYOR BELT PROTECTION SWITCHES-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-23 09:00 | 2020-02-05 18:00 | 2020-03-10 09:00 | 2020-08-17 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.9009 | 0.00061 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3915 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019048
1529 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.12.2.3 | ZERO SPEED SWITCH-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-15 09:00 | 2020-01-31 18:00 | 2020-03-07 09:00 | 2020-08-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3916 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019049
1530 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.12.2.3 | CHUTE BLOCK SWITCH-->ORDERING-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-19 | 2020-01-31 18:00 | 2020-01-16 09:00 | 2020-02-01 18:00 |  |  | 2020-02-01 10:57 | 2020-02-01 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3917 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019050
1531 | Task(Task)-->P (Procurement) | ITP APPROVAL | 1.12.2.4 | 1.12.2 | ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-02-01 09:00 | 2020-08-25 18:00 | 2020-03-21 09:00 | 2020-11-30 18:00 |  |  | 2020-04-13 16:22 |  |  |  | 100 | 26.7261 | [15 empty] | 5.0008 | 0.033861 | 3.33 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3918 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019051
1532 | Task(Task)-->P (Procurement) | Pulley |  | 1.12.2.4 | Pulley-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-04 09:00 | 2020-03-14 18:00 | 2020-03-21 09:00 | 2020-05-11 18:00 | [6 empty] | 100 | 0 | [15 empty] | 15.015 | 0.005084 | 0.5 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3919 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019052
1533 | Task(Task)-->P (Procurement) | Idler |  | 1.12.2.4 | Idler-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-03 09:00 | 2020-04-11 18:00 | 2020-04-30 09:00 | 2020-05-19 18:00 |  |  | 2020-04-13 16:22 | 2020-05-19 16:22 |  |  | 100 | 100 | [15 empty] | 5.1051 | 0.001729 | 0.17 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3920 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019053
1534 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.12.2.4 | Plummer Block-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-02 09:00 | 2020-08-10 18:00 | 2020-03-24 09:00 | 2020-08-13 18:00 | [6 empty] | 100 | 0 | [15 empty] | 1.2012 | 0.000407 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3921 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019054
1535 | Task(Task)-->P (Procurement) | Bearing |  | 1.12.2.4 | Bearing-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-17 09:00 | 2020-08-25 18:00 | 2020-03-24 09:00 | 2020-03-29 23:59 | [6 empty] | 100 | 0 | [15 empty] | 1.8018 | 0.00061 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3922 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019055
1536 | Task(Task)-->P (Procurement) | Belting |  | 1.12.2.4 | Belting-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-21 09:00 | 2020-03-31 18:00 | 2020-09-04 09:00 | 2020-09-30 18:00 |  |  | 2020-09-04 16:30 | 2020-09-30 17:07 |  |  | 100 | 100 | [15 empty] | 6.006 | 0.002034 | 0.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3923 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019056
1537 | Task(Task)-->P (Procurement) | Scrapper |  | 1.12.2.4 | Scrapper-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-16 09:00 | 2020-05-25 18:00 | 2020-05-30 09:00 | 2020-06-25 18:00 |  |  | 2020-05-30 16:32 | 2020-06-25 16:32 |  |  | 100 | 100 | [15 empty] | 0.6006 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3924 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019057
1538 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.12.2.4 | Technological Structure-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-20 09:00 | 2020-05-29 18:00 | 2020-07-06 09:00 | 2020-07-16 18:00 | [6 empty] | 100 | 0 | [15 empty] | 5.7057 | 0.001932 | 0.19 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3925 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019058
1539 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.12.2.4 | Takeup Component-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-19 | 2020-08-17 18:00 | 2020-06-25 09:00 | 2020-06-25 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.3003 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3926 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019059
1540 | Task(Task)-->P (Procurement) | Gear Box |  | 1.12.2.4 | Gear Box-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-28 09:00 | 2020-05-06 18:00 | 2020-04-30 09:00 | 2020-06-22 18:00 |  |  | 2020-04-30 16:54 | 2020-06-22 16:54 |  |  | 100 | 100 | [15 empty] | 3.003 | 0.001017 | 0.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3927 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019060
1541 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.12.2.4 | Geared Coupling-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-19 | 2020-05-28 18:00 | 2020-04-30 09:00 | 2020-06-18 18:00 |  |  | 2020-04-30 01:54 | 2020-06-18 17:31 |  |  | 100 | 100 | [15 empty] | 0.3003 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3928 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019061
1542 | Task(Task)-->P (Procurement) | Fluid Coupling |  | 1.12.2.4 | Fluid Coupling-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-01 09:00 | 2020-05-10 23:59 | 2020-05-18 09:00 | 2020-08-18 18:00 | [6 empty] | 100 | 0 | [15 empty] | 3.003 | 0.001017 | 0.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3929 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019062
1543 | Task(Task)-->P (Procurement) | Brake |  | 1.12.2.4 | Brake-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-09 09:00 | 2020-05-18 18:00 | 2020-05-18 09:00 | 2020-10-14 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.3003 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3930 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019063
1544 | Task(Task)-->P (Procurement) | Building Structure |  | 1.12.2.4 | Building Structure-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-23 09:00 | 2020-05-29 18:00 | 2020-05-31 | 2020-08-04 18:00 |  |  | 2020-06-25 19:04 |  |  |  | 100 | 0 | [15 empty] | 36.3363 | 0.012304 | 1.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3931 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019064
1545 | Task(Task)-->P (Procurement) | HT AC MOTORS |  | 1.12.2.4 | HT AC MOTORS-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-21 09:00 | 2020-03-31 18:00 | 2020-09-11 09:00 | 2020-11-10 18:00 |  |  | 2020-09-11 15:20 |  |  |  | 100 | 0 | [15 empty] | 8.7087 | 0.002949 | 0.29 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3932 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019065
1546 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.12.2.4 | LIGHT & LIGHT FIXTURES-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-11 09:00 | 2020-05-20 18:00 | 2020-07-28 09:00 | 2020-09-08 18:00 |  |  | 2020-07-08 17:23 | 2020-09-08 17:23 |  |  | 100 | 100 | [15 empty] | 8.1081 | 0.002745 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3933 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019066
1547 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.12.2.4 | LIGHTING POLES-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-06-26 09:00 | 2020-08-04 18:00 | 2020-06-23 09:00 | 2020-09-08 18:00 |  |  | 2020-06-23 17:45 | 2020-09-08 17:05 |  |  | 100 | 100 | [15 empty] | 3.6036 | 0.00122 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3934 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019067
1548 | Task(Task)-->P (Procurement) | LPBS |  | 1.12.2.4 | LPBS-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-21 09:00 | 2020-05-30 18:00 | 2020-07-29 09:00 | 2020-08-21 18:00 |  |  | 2020-07-29 15:00 | 2020-08-22 12:54 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3935 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019068
1549 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.12.2.4 | CONVEYOR BELT PROTECTION SWITCHES-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-06 09:00 | 2020-03-16 18:00 | 2020-09-24 09:00 | 2020-11-30 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.9009 | 0.000305 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3937 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019069
1550 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.12.2.4 | ZERO SPEED SWITCH-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-01 09:00 | 2020-03-11 18:00 | 2020-08-02 | 2020-09-10 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3938 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019070
1551 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.12.2.4 | CHUTE BLOCK SWITCH-->ITP APPROVAL-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-01 09:00 | 2020-03-11 18:00 | 2020-07-02 09:00 | 2020-08-04 18:00 |  |  | 2020-07-17 16:57 | 2020-08-04 16:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3939 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019071
1552 | Task(Task)-->P (Procurement) | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE | 1.12.2.5 | 1.12.2 | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-02-01 09:00 | 2020-09-16 18:00 | 2020-02-01 09:00 | 2020-11-22 23:59 |  |  | 2020-02-11 21:28 |  |  |  | 100 | 49.1485 | [15 empty] | 15.0023 | 0.10158 | 9.99 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3940 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019072
1553 | Task(Task)-->P (Procurement) | Pulley |  | 1.12.2.5 | Pulley-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-04 09:00 | 2020-03-29 23:59 | 2020-03-21 09:00 | 2020-03-25 18:00 |  |  | 2020-03-22 18:03 | 2020-03-25 18:03 |  |  | 100 | 100 | [15 empty] | 15 | 0.015237 | 1.5 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3941 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019073
1554 | Task(Task)-->P (Procurement) | Idler |  | 1.12.2.5 | Idler-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-03 09:00 | 2020-05-01 18:00 | 2020-04-30 09:00 | 2020-06-25 18:00 |  |  | 2020-06-25 14:53 | 2020-06-25 14:53 |  |  | 100 | 100 | [15 empty] | 5.2 | 0.005282 | 0.52 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3942 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019074
1555 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.12.2.5 | Plummer Block-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-07-02 09:00 | 2020-08-30 23:59 | 2020-03-24 09:00 | 2020-06-29 18:00 |  |  | 2020-05-14 14:59 | 2020-06-29 14:59 |  |  | 100 | 100 | [15 empty] | 1.1 | 0.001117 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3943 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019075
1556 | Task(Task)-->P (Procurement) | Bearing |  | 1.12.2.5 | Bearing-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-07-17 09:00 | 2020-07-17 18:00 | 2020-03-24 09:00 | 2020-03-24 18:00 |  |  | 2020-03-24 10:05 | 2020-03-24 10:05 |  |  | 100 | 100 | [15 empty] | 1.9 | 0.00193 | 0.19 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3944 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019076
1557 | Task(Task)-->P (Procurement) | Belting |  | 1.12.2.5 | Belting-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-21 09:00 | 2020-04-20 18:00 | 2020-09-04 09:00 | 2020-11-15 23:59 |  |  | 2020-09-04 16:36 |  |  |  | 100 | 50 | [15 empty] | 5.9 | 0.005993 | 0.59 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3945 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019077
1558 | Task(Task)-->P (Procurement) | Scrapper |  | 1.12.2.5 | Scrapper-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-16 09:00 | 2020-06-14 23:59 | 2020-05-30 09:00 | 2020-07-30 18:00 |  |  | 2020-05-30 16:34 | 2020-07-30 16:34 |  |  | 100 | 100 | [15 empty] | 0.6 | 0.000609 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3946 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019078
1559 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.12.2.5 | Technological Structure-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-20 09:00 | 2020-09-16 18:00 | 2020-07-06 09:00 | 2020-07-06 18:00 |  |  | 2020-07-06 12:45 | 2020-07-06 12:45 |  |  | 100 | 100 | [15 empty] | 5.7 | 0.00579 | 0.57 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3947 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019079
1560 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.12.2.5 | Takeup Component-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-19 | 2020-08-27 18:00 | 2020-08-04 09:00 | 2020-08-04 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.3 | 0.000305 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3948 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019080
1561 | Task(Task)-->P (Procurement) | Gear Box |  | 1.12.2.5 | Gear Box-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-28 09:00 | 2020-05-26 18:00 | 2020-04-30 09:00 | 2020-07-01 18:00 |  |  | 2020-04-30 15:33 | 2020-07-01 15:33 |  |  | 100 | 100 | [15 empty] | 3 | 0.003047 | 0.3 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3949 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019081
1562 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.12.2.5 | Geared Coupling-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-19 | 2020-06-17 18:00 | 2020-04-30 09:00 | 2020-07-30 18:00 |  |  | 2020-04-30 15:31 | 2020-07-06 15:31 |  |  | 100 | 100 | [15 empty] | 0.4 | 0.000406 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3950 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019082
1563 | Task(Task)-->P (Procurement) | Fluid Coupling |  | 1.12.2.5 | Fluid Coupling-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-01 09:00 | 2020-05-30 18:00 | 2020-05-18 09:00 | 2020-08-21 18:00 | [6 empty] | 100 | 0 | [15 empty] | 3.1 | 0.003149 | 0.31 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3951 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019083
1564 | Task(Task)-->P (Procurement) | Brake |  | 1.12.2.5 | Brake-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-09 09:00 | 2020-06-07 23:59 | 2020-05-18 09:00 | 2020-08-13 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.3 | 0.000305 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3952 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019084
1565 | Task(Task)-->P (Procurement) | Building Structure |  | 1.12.2.5 | Building Structure-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-30 09:00 | 2020-05-06 18:00 | 2020-11-16 09:00 | 2020-11-22 23:59 | [6 empty] | 100 | 0 | [15 empty] | 36.2 | 0.036773 | 3.62 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3953 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019085
1566 | Task(Task)-->P (Procurement) | HT AC MOTORS |  | 1.12.2.5 | HT AC MOTORS-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-21 09:00 | 2020-05-05 18:00 | 2020-07-18 09:00 | 2020-09-28 18:00 |  |  | 2020-07-18 09:04 | 2020-09-28 10:23 |  |  | 100 | 100 | [15 empty] | 8.7 | 0.008838 | 0.87 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3954 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019086
1567 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.12.2.5 | LIGHT & LIGHT FIXTURES-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-11 09:00 | 2020-05-25 18:00 | 2020-07-10 09:00 | 2020-11-16 18:00 |  |  | 2020-07-14 10:44 |  |  |  | 100 | 0 | [15 empty] | 8 | 0.008127 | 0.8 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3955 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019087
1568 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.12.2.5 | LIGHTING POLES-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-06-26 09:00 | 2020-08-09 23:59 | 2020-05-30 09:00 | 2020-08-08 18:00 |  |  | 2020-06-18 17:16 | 2020-08-07 15:00 |  |  | 100 | 100 | [15 empty] | 3.6 | 0.003657 | 0.36 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3956 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019088
1569 | Task(Task)-->P (Procurement) | LPBS |  | 1.12.2.5 | LPBS-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-21 09:00 | 2020-06-04 18:00 | 2020-07-25 09:00 | 2020-08-22 18:00 |  |  | 2020-07-24 18:45 | 2020-08-22 12:58 |  |  | 100 | 100 | [15 empty] | 0.1 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3957 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019089
1570 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.12.2.5 | CONVEYOR BELT PROTECTION SWITCHES-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-06 09:00 | 2020-03-21 18:00 | 2020-08-11 09:00 | 2020-09-19 18:00 |  |  | 2020-08-11 13:12 | 2020-09-19 12:58 |  |  | 100 | 100 | [15 empty] | 0.9 | 0.000914 | 0.09 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3959 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019090
1571 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.12.2.5 | ZERO SPEED SWITCH-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-01 09:00 | 2020-03-16 18:00 | 2020-08-09 | 2020-10-29 18:00 |  |  | 2020-08-09 13:17 | 2020-10-29 12:59 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3960 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019091
1572 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.12.2.5 | CHUTE BLOCK SWITCH-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-01 09:00 | 2020-03-16 18:00 | 2020-02-01 09:00 | 2020-07-15 18:00 |  |  | 2020-02-11 21:28 | 2020-07-15 21:28 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3961 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019092
1573 | Task(Task)-->P (Procurement) | MANUFACTURING & RECEIPT AT SITE (MRN) | 1.12.2.6 | 1.12.2 | MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-17 09:00 | 2021-02-13 18:00 | 2020-03-24 09:00 | 2021-06-13 23:59 |  |  | 2020-03-25 18:05 |  |  |  | 94.1622 | 1.2456 | [15 empty] | 59.994 | 0.40623 | 39.95 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3962 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019093
1574 | Task(Task)-->P (Procurement) | Pulley |  | 1.12.2.6 | Pulley-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-30 09:00 | 2020-11-20 18:00 | 2020-03-25 09:00 | 2020-12-01 18:00 |  |  | 2020-03-25 18:05 |  |  |  | 95.7627 | 0 | [15 empty] | 15.0325 | 0.061067 | 6.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3963 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019094
1575 | Task(Task)-->P (Procurement) | Idler |  | 1.12.2.6 | Idler-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-02 09:00 | 2020-11-13 18:00 | 2020-06-25 09:00 | 2020-12-31 18:00 | [6 empty] | 98.4694 | 0 | [15 empty] | 5.1526 | 0.020931 | 2.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3964 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019095
1576 | Task(Task)-->P (Procurement) | Plummer Block |  | 1.12.2.6 | Plummer Block-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-31 09:00 | 2020-12-23 18:00 | 2020-06-29 09:00 | 2020-12-31 18:00 | [6 empty] | 62.6087 | 0 | [15 empty] | 1.1006 | 0.004471 | 0.44 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3965 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019096
1577 | Task(Task)-->P (Procurement) | Bearing |  | 1.12.2.6 | Bearing-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-26 09:00 | 2020-12-23 18:00 | 2020-03-24 09:00 | 2020-09-09 18:00 | [6 empty] | 64.1667 | 0 | [15 empty] | 1.8759 | 0.007621 | 0.75 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3966 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019097
1578 | Task(Task)-->P (Procurement) | Belting |  | 1.12.2.6 | Belting-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-21 09:00 | 2020-11-16 18:00 | 2020-11-16 09:00 | 2021-06-13 23:59 | [6 empty] | 97.1429 | 0 | [15 empty] | 5.8779 | 0.023878 | 2.35 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3967 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019098
1579 | Task(Task)-->P (Procurement) | Scrapper |  | 1.12.2.6 | Scrapper-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-15 09:00 | 2020-12-11 18:00 | 2020-07-30 09:00 | 2020-12-31 18:00 | [6 empty] | 82.7778 | 0 | [15 empty] | 0.55028 | 0.002235 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3968 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019099
1580 | Task(Task)-->P (Procurement) | Technological Structure |  | 1.12.2.6 | Technological Structure-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-19 09:00 | 2021-02-13 18:00 | 2020-07-06 09:00 | 2021-01-31 23:59 | [6 empty] | 60.4167 | 0 | [15 empty] | 5.6778 | 0.023065 | 2.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3969 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019100
1581 | Task(Task)-->P (Procurement) | Takeup Component |  | 1.12.2.6 | Takeup Component-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-28 09:00 | 2020-12-25 18:00 | 2020-08-04 09:00 | 2020-12-25 18:00 | [6 empty] | 62.5 | 0 | [15 empty] | 0.32516 | 0.001321 | 0.13 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3970 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019101
1582 | Task(Task)-->P (Procurement) | Gear Box |  | 1.12.2.6 | Gear Box-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-27 09:00 | 2020-12-22 18:00 | 2020-07-01 09:00 | 2020-12-31 18:00 |  |  | 2020-07-01 17:25 |  |  |  | 80 | 30 | [15 empty] | 3.0265 | 0.012295 | 1.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3971 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019102
1583 | Task(Task)-->P (Procurement) | Geared Coupling |  | 1.12.2.6 | Geared Coupling-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-18 09:00 | 2020-12-15 18:00 | 2020-07-30 09:00 | 2020-11-30 18:00 |  |  | 2020-07-30 17:44 |  |  |  | 80.663 | 90 | [15 empty] | 0.37519 | 0.001524 | 0.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3972 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019103
1584 | Task(Task)-->P (Procurement) | Fluid Coupling |  | 1.12.2.6 | Fluid Coupling-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-31 | 2020-12-26 18:00 | 2020-08-21 09:00 | 2021-01-31 23:59 | [6 empty] | 78.0952 | 0 | [15 empty] | 3.1266 | 0.012701 | 1.25 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3973 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019104
1585 | Task(Task)-->P (Procurement) | Brake |  | 1.12.2.6 | Brake-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-08 09:00 | 2020-12-04 18:00 | 2020-08-13 09:00 | 2020-11-30 18:00 | [6 empty] | 86.6667 | 0 | [15 empty] | 0.32516 | 0.001321 | 0.13 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3974 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019105
1586 | Task(Task)-->P (Procurement) | Building Structure |  | 1.12.2.6 | Building Structure-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-30 09:00 | 2020-09-30 18:00 | 2020-11-23 09:00 | 2021-03-26 18:00 | [6 empty] | 100 | 0 | [15 empty] | 36.1681 | 0.14693 | 14.46 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3975 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019106
1587 | Task(Task)-->P (Procurement) | HT AC MOTORS |  | 1.12.2.6 | HT AC MOTORS-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-06 09:00 | 2020-09-30 18:00 | 2020-11-11 09:00 | 2021-04-07 18:00 |  |  | 2020-09-28 10:24 |  |  |  | 100 | 0 | [15 empty] | 8.7044 | 0.03536 | 3.48 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3976 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019107
1588 | Task(Task)-->P (Procurement) | LIGHT & LIGHT FIXTURES |  | 1.12.2.6 | LIGHT & LIGHT FIXTURES-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-26 09:00 | 2020-10-21 18:00 | 2020-11-17 09:00 | 2021-04-14 18:00 | [6 empty] | 100 | 0 | [15 empty] | 7.979 | 0.032413 | 3.19 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3977 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019108
1589 | Task(Task)-->P (Procurement) | LIGHTING POLES |  | 1.12.2.6 | LIGHTING POLES-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-10 09:00 | 2020-11-07 18:00 | 2020-09-09 09:00 | 2020-12-07 18:00 |  |  | 2020-08-07 15:03 |  |  |  | 100 | 0 | [15 empty] | 3.6268 | 0.014733 | 1.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3978 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019109
1590 | Task(Task)-->P (Procurement) | LPBS |  | 1.12.2.6 | LPBS-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-05 09:00 | 2020-09-16 18:00 | 2020-08-23 | 2020-12-04 18:00 |  |  | 2020-08-22 13:01 |  |  |  | 100 | 0 | [15 empty] | 0.10005 | 0.000406 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3979 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019110
1591 | Task(Task)-->P (Procurement) | CONVEYOR BELT PROTECTION SWITCHES |  | 1.12.2.6 | CONVEYOR BELT PROTECTION SWITCHES-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-22 | 2020-08-05 18:00 | 2020-12-01 09:00 | 2021-04-16 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.90045 | 0.003658 | 0.36 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3981 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019111
1592 | Task(Task)-->P (Procurement) | ZERO SPEED SWITCH |  | 1.12.2.6 | ZERO SPEED SWITCH-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-17 09:00 | 2020-07-27 18:00 | 2020-10-30 09:00 | 2021-03-11 18:00 |  |  | 2020-10-29 13:03 |  |  |  | 100 | 0 | [15 empty] | 0.025013 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3982 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019112
1593 | Task(Task)-->P (Procurement) | CHUTE BLOCK SWITCH |  | 1.12.2.6 | CHUTE BLOCK SWITCH-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-17 09:00 | 2020-07-31 18:00 | 2020-07-02 09:00 | 2020-11-15 23:59 |  |  | 2020-07-15 21:40 |  |  |  | 100 | 0 | [15 empty] | 0.050025 | 0.000203 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3983 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019113
1594 | Task(Task)-->C (Construction) | CONSTRUCTION | 1.12.3 | 1.12 | CONSTRUCTION-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-08 09:00 | 2021-09-08 18:00 | 2020-08-26 09:00 | 2022-04-06 18:00 | [6 empty] | 30.2852 | 0 | [15 empty] | 16.3703 | 0.13575 | 13.35 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3984 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019114
1595 | Task(Task)-->C (Construction) | CIVIL WORKS | 1.12.3.1 | 1.12.3 | CIVIL WORKS-->CONSTRUCTION-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-08 09:00 | 2020-09-11 18:00 | 2020-08-26 09:00 | 2020-12-30 18:00 | [6 empty] | 100 | 0 | [15 empty] | 9.9551 | 0.013514 | 1.33 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5477 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019115
1596 | Task(Task)-->C (Construction) | AVAILABILITY OF FRONT BY NTPC |  | 1.12.3.1 | AVAILABILITY OF FRONT BY NTPC-->CIVIL WORKS-->CONSTRUCTION-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-08 09:00 | 2020-05-08 18:00 | 2020-08-26 09:00 | 2020-08-26 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5476 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019116
1597 | Task(Task)-->C (Construction) | CIVIL |  | 1.12.3.1 | CIVIL-->CIVIL WORKS-->CONSTRUCTION-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-15 09:00 | 2020-09-11 18:00 | 2020-09-02 09:00 | 2020-12-30 18:00 | [6 empty] | 100 | 0 | [15 empty] | 100 | 0.013514 | 1.33 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3985 | 0 | 4 | Low | ADMINISTRATOR | [6 empty] | 0 | 0 | [246 empty] | 1019117
1598 | Task(Task)-->C (Construction) | MECHANICAL | 1.12.3.2 | 1.12.3 | MECHANICAL-->CONSTRUCTION-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-10-01 09:00 | 2021-05-14 18:00 | 2021-03-27 09:00 | 2021-08-23 18:00 | [6 empty] | 35.5046 | 0 | [15 empty] | 57.2605 | 0.077731 | 7.65 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3986 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019118
1599 | Task(Task)-->C (Construction) | ERECTION OF STRUCTURAL STEEL |  | 1.12.3.2 | ERECTION OF STRUCTURAL STEEL-->MECHANICAL-->CONSTRUCTION-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-10-01 09:00 | 2020-11-29 23:59 | 2021-03-27 09:00 | 2021-05-25 18:00 | [6 empty] | 68.3333 | 0 | [15 empty] | 51.9582 | 0.040388 | 3.98 | Plan & Actual | Quantity | Metric Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3987 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019119
1600 | Task(Task)-->C (Construction) | ERECTION OF SY 3A |  | 1.12.3.2 | ERECTION OF SY 3A-->MECHANICAL-->CONSTRUCTION-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-02-14 | 2021-03-30 18:00 | 2021-05-26 09:00 | 2021-07-09 18:00 | [6 empty] | 0 | 0 | [15 empty] | 24.0209 | 0.018672 | 1.84 | Plan & Actual | Quantity | Metric Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3988 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019120
1601 | Task(Task)-->C (Construction) | ERECTION OF SY 3B |  | 1.12.3.2 | ERECTION OF SY 3B-->MECHANICAL-->CONSTRUCTION-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-03-31 09:00 | 2021-05-14 18:00 | 2021-07-10 09:00 | 2021-08-23 18:00 | [6 empty] | 0 | 0 | [15 empty] | 24.0209 | 0.018672 | 1.84 | Plan & Actual | Quantity | Metric Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5436 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019121
1602 | Task(Task)-->C (Construction) | BELT LAYING & JOINTING WORK |  | 1.12.3 | BELT LAYING & JOINTING WORK-->CONSTRUCTION-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-05-15 09:00 | 2021-06-14 18:00 | 2021-08-24 09:00 | 2021-09-23 18:00 | [6 empty] | 0 | 0 | [15 empty] | 3.8922 | 0.005284 | 0.52 | Plan & Actual | Quantity | Meter | 0 | 0 | 0 | 0 | 0 | 0 | 332 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3989 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019122
1603 | Task(Task)-->C (Construction) | ELECTRICAL & INSTRUMENTATION | 1.12.3.4 | 1.12.3 | ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-09-10 09:00 | 2021-08-25 18:00 | 2020-12-29 09:00 | 2022-03-23 18:00 | [6 empty] | 0 | 0 | [15 empty] | 17.3653 | 0.023573 | 2.32 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5266 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019123
1604 | Task(Task)-->C (Construction) | CABLE TRAY |  | 1.12.3.4 | CABLE TRAY-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-11-30 09:00 | 2020-12-02 18:00 | 2021-05-26 09:00 | 2021-05-28 18:00 | [6 empty] | 0 | 0 | [15 empty] | 9.0909 | 0.002143 | 0.21 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3990 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019124
1605 | Task(Task)-->C (Construction) | POWER CABLE |  | 1.12.3.4 | POWER CABLE-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-05-15 09:00 | 2021-05-19 18:00 | 2021-08-24 09:00 | 2021-08-28 18:00 | [6 empty] | 0 | 0 | [15 empty] | 31.1688 | 0.007347 | 0.72 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 5080 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5267 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019125
1606 | Task(Task)-->C (Construction) | CONTROL CABLE |  | 1.12.3.4 | CONTROL CABLE-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-05-19 09:00 | 2021-05-19 18:00 | 2021-10-26 09:00 | 2021-10-26 18:00 | [6 empty] | 0 | 0 | [15 empty] | 2.5974 | 0.000612 | 0.06 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 456 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3991 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019126
1607 | Task(Task)-->C (Construction) | EARTHING |  | 1.12.3.4 | EARTHING-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-02-09 09:00 | 2021-02-11 18:00 | 2021-05-26 09:00 | 2021-05-28 18:00 | [6 empty] | 0 | 0 | [15 empty] | 3.4632 | 0.000816 | 0.08 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 369 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5329 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019127
1608 | Task(Task)-->C (Construction) | EARTH PIT |  | 1.12.3.4 | EARTH PIT-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-09-10 09:00 | 2020-09-11 18:00 | 2020-12-29 09:00 | 2020-12-30 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5330 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019128
1609 | Task(Task)-->C (Construction) | LIGHTING |  | 1.12.3.4 | LIGHTING-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-11-30 09:00 | 2020-12-04 18:00 | 2021-05-26 09:00 | 2021-05-30 23:59 | [6 empty] | 0 | 0 | [15 empty] | 16.8831 | 0.00398 | 0.39 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5331 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019129
1610 | Task(Task)-->C (Construction) | FIELD INTRUMENTS |  | 1.12.3.4 | FIELD INTRUMENTS-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-05-18 09:00 | 2021-05-20 18:00 | 2021-10-25 09:00 | 2021-10-27 18:00 | [6 empty] | 0 | 0 | [15 empty] | 36.7965 | 0.008674 | 0.85 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5332 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019130
1611 | Task(Task)-->C (Construction) | MOTOR TERMINATION |  | 1.12.3.4 | MOTOR TERMINATION-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-05-19 09:00 | 2021-05-20 18:00 | 2021-08-28 09:00 | 2021-08-29 23:59 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5333 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019131
1612 | Task(Task)-->C (Construction) | NO LOAD RUN OF MOTOR |  | 1.12.3.4 | NO LOAD RUN OF MOTOR-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-08-22 | 2021-08-25 18:00 | 2022-03-20 | 2022-03-23 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5478 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019132
1613 | Task(Task)-->C (Construction) | NO LOAD COMMISSIONING & SYSTEM READYNESS FOR LOAD & TRIAL OPERATION |  | 1.12.3 | NO LOAD COMMISSIONING & SYSTEM READYNESS FOR LOAD & TRIAL OPERATION-->CONSTRUCTION-->TROUGH CONVEYOR SY 3A & SY 3B-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-08-26 09:00 | 2021-09-08 18:00 | 2022-03-24 09:00 | 2022-04-06 18:00 | [6 empty] | 0 | 0 | [15 empty] | 11.5269 | 0.015648 | 1.54 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5334 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019133
1614 | Task(Task)-->E (Engineering) | SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER | 1.13 | 1 | SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-11-12 09:00 | 2021-08-21 18:00 | 2019-11-02 09:00 | 2022-04-13 18:00 |  |  | 2019-11-02 10:57 |  |  |  | 68.0392 | 14.3065 | [15 empty] | 3.5168 | 3.5168 | 345.85 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3992 | 0 | 1 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019134
1615 | Task(Task)-->E (Engineering) | ENGINEERING | 1.13.1 | 1.13 | ENGINEERING-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-12-18 18:00 | 2020-07-02 17:40 | 2020-01-13 18:00 | 2020-11-15 23:59 |  |  | 2020-02-21 14:31 |  |  |  | 100 | 72.6329 | [15 empty] | 2.4461 | 0.086025 | 8.46 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3993 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019135
1616 | Task(Task)-->E (Engineering) | CIVIL | 1.13.1.1 | 1.13.1 | CIVIL-->ENGINEERING-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-03-04 18:00 | 2020-07-02 17:40 | 2020-03-31 18:00 | 2020-11-04 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 92.8786 | [15 empty] | 48.7334 | 0.041923 | 4.04 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No | 3994 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036113
1617 | Task(Task)-->E (Engineering) | SUBSTATION-1 CUM CONTROL ROOM (SS-KDTP-1) : DESIGN CALCULATION |  | 1.13.1.1 | SUBSTATION-1 CUM CONTROL ROOM (SS-KDTP-1) : DESIGN CALCULATION-->CIVIL-->ENGINEERING-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-23 17:40 | 2020-05-04 17:40 | 2020-05-02 09:00 | 2020-05-29 18:00 |  |  | 2020-03-23 17:40 | 2020-06-04 14:29 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0025 |  | 2020-02-13 11:42 | 7012-155-PVC-U-086 |  |  |  | A |  |  |  | 47.8908 | 0.020077 | 1.93 | Plan & Actual | Date |  | 0 | 0 | 0 | 717.2 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3999 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-04 18:00 | 2020-03-31 18:00 |  | 10 | 2020-03-31 23:31 |  |  | 2020-03-23 17:40 | 2020-04-25 18:00 |  | 30 | 2020-04-25 23:31 |  |  | 2020-03-30 17:40 | 2020-04-28 18:00 |  | 35 | 2020-04-28 23:31 |  |  | 2020-04-04 23:59 | 2020-05-05 18:00 |  | 65 | 2020-05-02 23:31 |  |  | 2020-04-10 17:40 | 2020-05-26 18:00 |  | 80 | 2020-05-22 23:31 | [5 empty] | 80 | 2020-05-29 23:06 | [5 empty] | 80 | 2020-05-29 22:57 | [5 empty] | 80 | 2020-06-04 14:26 | [5 empty] | 80 | 2020-06-04 14:26 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-04 17:40 | 2020-06-09 18:00 |  | 100 | 2020-06-04 14:30 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 187 |  |  |  |  | 101197
1618 | Task(Task)-->E (Engineering) | SUBSTATION-1 CUM CONTROL ROOM (SS-KDTP-1) : NUM & RC DETAILS (SHT 1) |  | 1.13.1.1 | SUBSTATION-1 CUM CONTROL ROOM (SS-KDTP-1) : NUM & RC DETAILS (SHT 1)-->CIVIL-->ENGINEERING-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-23 17:40 | 2020-05-04 17:40 | 2020-05-02 09:00 | 2020-05-29 18:00 |  |  | 2020-03-23 17:40 | 2020-06-02 21:04 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-NR-0034 |  | 2020-02-13 11:42 | 7012-155-PVC-C-087 |  |  |  | A |  |  |  | 15.8809 | 0.006658 | 0.64 | Plan & Actual | Date |  | 0 | 0 | 0 | 239.46 | 0 | 28.4 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3995 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-04 18:00 | 2020-03-31 18:00 |  | 10 | 2020-03-31 23:31 |  |  | 2020-03-23 17:40 | 2020-04-25 18:00 |  | 30 | 2020-04-25 23:31 |  |  | 2020-03-30 17:40 | 2020-04-28 18:00 |  | 35 | 2020-04-28 23:31 |  |  | 2020-04-04 23:59 | 2020-05-05 18:00 |  | 65 | 2020-05-02 23:31 |  |  | 2020-04-10 17:40 | 2020-05-26 18:00 |  | 80 | 2020-05-22 23:31 | [5 empty] | 80 | 2020-05-29 23:05 | [5 empty] | 80 | 2020-05-29 22:59 | [5 empty] | 80 | 2020-06-02 20:50 | [5 empty] | 80 | 2020-06-02 20:50 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-04 17:40 | 2020-06-09 18:00 |  | 100 | 2020-06-02 21:05 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 188 |  |  |  |  | 101198
1619 | Task(Task)-->E (Engineering) | SUBSTATION-1 CUM CONTROL ROOM (SS-KDTP-1) : NUM & RC DETAILS (SHT 2) |  | 1.13.1.1 | SUBSTATION-1 CUM CONTROL ROOM (SS-KDTP-1) : NUM & RC DETAILS (SHT 2)-->CIVIL-->ENGINEERING-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-04 18:00 | 2020-05-04 17:40 | 2020-07-08 09:00 | 2020-07-22 18:00 |  |  | 2020-02-21 15:38 | 2020-07-22 23:11 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-NR-0035 |  | 2020-02-13 11:43 | 7012-155-PVC-C-088 |  |  |  | A |  |  |  | 15.8809 | 0.006658 | 0.64 | Plan & Actual | Date |  | 0 | 0 | 0 | 239.46 | 0 | 10.05 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3996 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-04 18:00 | 2020-03-31 18:00 |  | 10 | 2020-04-26 23:31 |  |  | 2020-03-23 17:40 | 2020-04-25 18:00 |  | 30 | 2020-05-19 23:31 |  |  | 2020-03-30 17:40 | 2020-04-28 18:00 |  | 35 | 2020-05-27 12:13 |  |  | 2020-04-04 23:59 | 2020-05-05 18:00 |  | 65 | 2020-07-22 23:02 |  |  | 2020-04-10 17:40 | 2020-05-26 18:00 |  | 80 | 2020-07-22 23:09 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-04 17:40 | 2020-06-09 18:00 |  | 100 | 2020-07-22 23:12 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 189 |  |  |  |  | 101199
1620 | Task(Task)-->E (Engineering) | SUBSTATION-1 CUM CONTROL ROOM (SS-KDTP-1) : NUM & RC DETAILS (SHT 3) |  | 1.13.1.1 | SUBSTATION-1 CUM CONTROL ROOM (SS-KDTP-1) : NUM & RC DETAILS (SHT 3)-->CIVIL-->ENGINEERING-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-04 18:00 | 2020-05-04 17:40 | 2020-03-31 18:00 | 2020-11-04 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-NR-0036 |  | 2020-02-13 11:43 | 7012-155-PVC-C-089 |  |  |  | A |  |  |  | 15.8809 | 0.006658 | 0.64 | Plan & Actual | Date |  | 0 | 0 | 0 | 239.46 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3997 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-04 18:00 | 2020-03-31 18:00 |  | 10 |  |  |  | 2020-03-23 17:40 | 2020-04-25 18:00 |  | 30 |  |  |  | 2020-03-30 17:40 | 2020-04-28 18:00 |  | 35 | 2020-10-01 16:44 |  |  | 2020-04-04 23:59 | 2020-05-05 18:00 |  | 65 | 2020-10-01 17:16 |  |  | 2020-04-10 17:40 | 2020-05-26 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-04 17:40 | 2020-06-09 18:00 |  | 100 | [122 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 190 |  |  |  |  | 101200
1621 | Task(Task)-->E (Engineering) | ARCHITECTURAL GA OF SUBSTATION-1 CUM CONTROL ROOM (SS-KDTP-1) |  | 1.13.1.1 | ARCHITECTURAL GA OF SUBSTATION-1 CUM CONTROL ROOM (SS-KDTP-1)-->CIVIL-->ENGINEERING-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-03 23:59 | 2020-07-02 17:40 | 2020-05-15 18:00 | 2020-09-28 18:00 |  |  | 2020-02-21 15:39 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-AR-0011 |  | 2020-02-13 11:43 | 7012-155-PVC-C-117 |  |  |  | A |  |  |  | 4.4665 | 0.001872 | 0.18 | Plan & Actual | Date |  | 0 | 0 | 0 | 68.01 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 3998 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-05-03 23:59 | 2020-05-15 18:00 |  | 10 |  |  |  | 2020-05-21 17:40 | 2020-06-09 18:00 |  | 30 | 2020-08-28 09:01 |  |  | 2020-05-28 17:40 | 2020-06-12 18:00 |  | 35 | 2020-09-03 12:48 |  |  | 2020-06-03 23:59 | 2020-06-19 18:00 |  | 65 | 2020-09-03 16:24 |  |  | 2020-06-09 17:40 | 2020-07-10 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-07-02 17:40 | 2020-07-24 18:00 |  | 100 | [122 empty] | Chetan Khodke | [5 empty] | A - Architecture | [16 empty] | 218 |  |  |  |  | 101228
1622 | Task(Task)-->E (Engineering) | ELECTRICAL | 1.13.1.2 | 1.13.1 | ELECTRICAL-->ENGINEERING-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-12-18 18:00 | 2020-05-16 17:40 | 2020-01-13 18:00 | 2020-11-15 23:59 |  |  | 2020-02-21 14:31 |  |  |  | 100 | 53.3875 | [15 empty] | 51.2666 | 0.044102 | 4.25 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No | 4000 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036114
1623 | Task(Task)-->E (Engineering) | GA & CROSS SECTIONAL, FLOOR PLAN FOR 6.6 kV HT SWITCHGEAR FOR CHP |  | 1.13.1.2 | GA & CROSS SECTIONAL, FLOOR PLAN FOR 6.6 kV HT SWITCHGEAR FOR CHP-->ELECTRICAL-->ENGINEERING-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-28 18:00 | 2020-04-13 17:40 | 2020-05-21 18:00 | 2020-09-01 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-123 |  | 2020-02-13 11:45 | 7012-155-PVE-B-068 |  |  |  | A |  |  |  | 1.3921 | 0.000614 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4007 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-28 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-02 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-03-07 17:40 | 2020-06-04 18:00 |  | 35 |  |  |  | 2020-03-13 23:59 | 2020-06-04 18:00 |  | 65 | 2020-09-23 14:45 |  |  | 2020-03-20 17:40 | 2020-06-25 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-13 17:40 | 2020-06-25 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 303 |  |  |  |  | 101314
1624 | Task(Task)-->E (Engineering) | SINGLE LINE DIAGRAM FOR 6.6 kV HT SWITCHGEAR FOR CHP |  | 1.13.1.2 | SINGLE LINE DIAGRAM FOR 6.6 kV HT SWITCHGEAR FOR CHP-->ELECTRICAL-->ENGINEERING-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-29 18:00 | 2020-04-13 17:40 | 2020-05-21 18:00 | 2020-09-22 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-126 |  | 2020-02-13 11:45 | 7012-155-PVE-P-071 |  |  |  | A |  |  |  | 1.3921 | 0.000614 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4028 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-29 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-02 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-03-07 17:40 | 2020-06-03 18:00 |  | 35 |  |  |  | 2020-03-13 23:59 | 2020-06-03 18:00 |  | 65 | 2020-09-23 14:49 |  |  | 2020-03-20 17:40 | 2020-06-24 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-13 17:40 | 2020-06-24 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 306 |  |  |  |  | 101317
1625 | Task(Task)-->E (Engineering) | SCHEME DIAGRAM FOR TIE INCOMER WITH LINE PT (TYPE-DE-IC) |  | 1.13.1.2 | SCHEME DIAGRAM FOR TIE INCOMER WITH LINE PT (TYPE-DE-IC)-->ELECTRICAL-->ENGINEERING-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-28 18:00 | 2020-04-13 17:40 | 2020-05-21 18:00 | 2020-09-17 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-127 |  | 2020-02-13 11:45 | 7012-155-PVE-L-072 |  |  |  | A |  |  |  | 1.3921 | 0.000614 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4016 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-28 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-02 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-03-07 17:40 | 2020-06-04 18:00 |  | 35 |  |  |  | 2020-03-13 23:59 | 2020-06-04 18:00 |  | 65 | 2020-09-23 16:58 |  |  | 2020-03-20 17:40 | 2020-06-25 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-13 17:40 | 2020-06-25 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 307 |  |  |  |  | 101318
1626 | Task(Task)-->E (Engineering) | SCHEME DIAGRAM FOR AUXILIARY INCOMER FEEDER WITH LINE PT (TYPE-DC) |  | 1.13.1.2 | SCHEME DIAGRAM FOR AUXILIARY INCOMER FEEDER WITH LINE PT (TYPE-DC)-->ELECTRICAL-->ENGINEERING-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-27 18:00 | 2020-04-13 17:40 | 2020-05-21 18:00 | 2020-09-17 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-128 |  | 2020-02-13 11:45 | 7012-155-PVE-L-073 |  |  |  | A |  |  |  | 1.3921 | 0.000614 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4017 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-27 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-02 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-03-07 17:40 | 2020-06-05 18:00 |  | 35 |  |  |  | 2020-03-13 23:59 | 2020-06-05 18:00 |  | 65 | 2020-09-23 17:35 |  |  | 2020-03-20 17:40 | 2020-06-26 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-13 17:40 | 2020-06-26 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 308 |  |  |  |  | 101319
1627 | Task(Task)-->E (Engineering) | SCHEME DIAGRAM FOR BUS COUPLER FEEDER (TYPE-DD) |  | 1.13.1.2 | SCHEME DIAGRAM FOR BUS COUPLER FEEDER (TYPE-DD)-->ELECTRICAL-->ENGINEERING-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-29 18:00 | 2020-04-13 17:40 | 2020-05-21 18:00 | 2020-09-17 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-129 |  | 2020-02-13 11:45 | 7012-155-PVE-L-074 |  |  |  | A |  |  |  | 1.3921 | 0.000614 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4018 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-29 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-02 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-03-07 17:40 | 2020-06-03 18:00 |  | 35 |  |  |  | 2020-03-13 23:59 | 2020-06-03 18:00 |  | 65 | 2020-09-23 17:35 |  |  | 2020-03-20 17:40 | 2020-06-24 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-13 17:40 | 2020-06-24 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 309 |  |  |  |  | 101320
1628 | Task(Task)-->E (Engineering) | SCHEME DIAGRAM FOR BUS PT FEEDER (TYPE-G) |  | 1.13.1.2 | SCHEME DIAGRAM FOR BUS PT FEEDER (TYPE-G)-->ELECTRICAL-->ENGINEERING-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-28 18:00 | 2020-04-13 17:40 | 2020-05-21 18:00 | 2020-09-17 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-130 |  | 2020-02-13 11:45 | 7012-155-PVE-L-075 |  |  |  | A |  |  |  | 1.3921 | 0.000614 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4019 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-28 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-02 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-03-07 17:40 | 2020-06-04 18:00 |  | 35 |  |  |  | 2020-03-13 23:59 | 2020-06-04 18:00 |  | 65 | 2020-09-23 17:36 |  |  | 2020-03-20 17:40 | 2020-06-25 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-13 17:40 | 2020-06-25 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 310 |  |  |  |  | 101321
1629 | Task(Task)-->E (Engineering) | SCHEME DIAGRAM FOR TRANSFORMER FEEDER WITHOUT DIFFERENTIAL (OIL TYPE) (TYPE-DB) |  | 1.13.1.2 | SCHEME DIAGRAM FOR TRANSFORMER FEEDER WITHOUT DIFFERENTIAL (OIL TYPE) (TYPE-DB)-->ELECTRICAL-->ENGINEERING-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-27 18:00 | 2020-04-13 17:40 | 2020-05-21 18:00 | 2020-09-17 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-131 |  | 2020-02-13 11:45 | 7012-155-PVE-L-076 |  |  |  | A |  |  |  | 1.3921 | 0.000614 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4020 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-27 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-02 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-03-07 17:40 | 2020-06-05 18:00 |  | 35 |  |  |  | 2020-03-13 23:59 | 2020-06-05 18:00 |  | 65 | 2020-09-23 17:37 |  |  | 2020-03-20 17:40 | 2020-06-26 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-13 17:40 | 2020-06-26 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 311 |  |  |  |  | 101322
1630 | Task(Task)-->E (Engineering) | SCHEME DIAGRAM FOR TRANSFORMER FEEDER WITH DIFFERENTIAL (OIL TYPE) (TYPE-DBF) |  | 1.13.1.2 | SCHEME DIAGRAM FOR TRANSFORMER FEEDER WITH DIFFERENTIAL (OIL TYPE) (TYPE-DBF)-->ELECTRICAL-->ENGINEERING-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-26 18:00 | 2020-04-13 17:40 | 2020-05-21 18:00 | 2020-09-17 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-132 |  | 2020-02-13 11:45 | 7012-155-PVE-L-077 |  |  |  | A |  |  |  | 1.3921 | 0.000614 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4021 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-26 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-02 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-03-07 17:40 | 2020-06-06 18:00 |  | 35 |  |  |  | 2020-03-13 23:59 | 2020-06-06 18:00 |  | 65 | 2020-09-23 17:38 |  |  | 2020-03-20 17:40 | 2020-06-27 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-13 17:40 | 2020-06-27 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 312 |  |  |  |  | 101323
1631 | Task(Task)-->E (Engineering) | SCHEME DIAGRAM FOR MOTOR FEEDER WITHOUT DIFFERENTIAL (TYPE-CC) |  | 1.13.1.2 | SCHEME DIAGRAM FOR MOTOR FEEDER WITHOUT DIFFERENTIAL (TYPE-CC)-->ELECTRICAL-->ENGINEERING-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-01 23:59 | 2020-04-13 17:40 | 2020-05-21 18:00 | 2020-09-18 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-133 |  | 2020-02-13 11:45 | 7012-155-PVE-L-078 |  |  |  | A |  |  |  | 1.3921 | 0.000614 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4022 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-01 23:59 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-02 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-03-07 17:40 | 2020-06-02 18:00 |  | 35 |  |  |  | 2020-03-13 23:59 | 2020-06-02 18:00 |  | 65 | 2020-09-23 17:39 |  |  | 2020-03-20 17:40 | 2020-06-23 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-13 17:40 | 2020-06-23 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 313 |  |  |  |  | 101324
1632 | Task(Task)-->E (Engineering) | SCHEME DIAGRAM FOR TIE OUTGOING FEEDER (TYPE-DE) |  | 1.13.1.2 | SCHEME DIAGRAM FOR TIE OUTGOING FEEDER (TYPE-DE)-->ELECTRICAL-->ENGINEERING-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-29 18:00 | 2020-04-13 17:40 | 2020-05-21 18:00 | 2020-09-18 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-134 |  | 2020-02-13 11:45 | 7012-155-PVE-L-079 |  |  |  | A |  |  |  | 1.3921 | 0.000614 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4023 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-29 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-02 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-03-07 17:40 | 2020-06-03 18:00 |  | 35 |  |  |  | 2020-03-13 23:59 | 2020-06-03 18:00 |  | 65 | 2020-09-23 17:40 |  |  | 2020-03-20 17:40 | 2020-06-24 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-13 17:40 | 2020-06-24 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 314 |  |  |  |  | 101325
1633 | Task(Task)-->E (Engineering) | SCHEME DIAGRAM FOR CAPACITOR FEEDER |  | 1.13.1.2 | SCHEME DIAGRAM FOR CAPACITOR FEEDER-->ELECTRICAL-->ENGINEERING-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-28 18:00 | 2020-04-13 17:40 | 2020-05-21 18:00 | 2020-09-18 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-135 |  | 2020-02-13 11:45 | 7012-155-PVE-L-080 |  |  |  | A |  |  |  | 1.3921 | 0.000614 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4024 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-28 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-02 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-03-07 17:40 | 2020-06-04 18:00 |  | 35 |  |  |  | 2020-03-13 23:59 | 2020-06-04 18:00 |  | 65 | 2020-09-23 17:44 |  |  | 2020-03-20 17:40 | 2020-06-25 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-13 17:40 | 2020-06-25 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 315 |  |  |  |  | 101326
1634 | Task(Task)-->E (Engineering) | SCHEME DIAGRAM FOR AUXILIARY PANEL |  | 1.13.1.2 | SCHEME DIAGRAM FOR AUXILIARY PANEL-->ELECTRICAL-->ENGINEERING-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-26 18:00 | 2020-04-13 17:40 | 2020-05-21 18:00 | 2020-09-18 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-137 |  | 2020-02-13 11:45 | 7012-155-PVE-L-082 |  |  |  | A |  |  |  | 1.3921 | 0.000614 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4025 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-26 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-02 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-03-07 17:40 | 2020-06-06 18:00 |  | 35 |  |  |  | 2020-03-13 23:59 | 2020-06-06 18:00 |  | 65 | 2020-09-23 17:46 |  |  | 2020-03-20 17:40 | 2020-06-27 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-13 17:40 | 2020-06-27 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 317 |  |  |  |  | 101328
1635 | Task(Task)-->E (Engineering) | SCHEME DIAGRAM FOR EARTHING TRUCK |  | 1.13.1.2 | SCHEME DIAGRAM FOR EARTHING TRUCK-->ELECTRICAL-->ENGINEERING-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-28 18:00 | 2020-04-13 17:40 | 2020-05-21 18:00 | 2020-09-18 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-138 |  | 2020-02-13 11:46 | 7012-155-PVE-L-083 |  |  |  | A |  |  |  | 1.3921 | 0.000614 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4026 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-28 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-02 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-03-07 17:40 | 2020-06-04 18:00 |  | 35 |  |  |  | 2020-03-13 23:59 | 2020-06-04 18:00 |  | 65 | 2020-09-23 17:52 |  |  | 2020-03-20 17:40 | 2020-06-25 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-13 17:40 | 2020-06-25 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 318 |  |  |  |  | 101329
1636 | Task(Task)-->E (Engineering) | OIL TYPE POWER TRANSFORMER - GA DRAWINGS |  | 1.13.1.2 | OIL TYPE POWER TRANSFORMER - GA DRAWINGS-->ELECTRICAL-->ENGINEERING-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-23 18:00 | 2020-05-06 17:40 | 2020-05-21 18:00 | 2020-07-28 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-139 |  | 2020-02-13 11:46 | 7012-155-PVE-B-084 |  |  |  | A |  |  |  | 2.5522 | 0.001126 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4008 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-23 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-25 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-04-01 17:40 | 2020-06-05 18:00 |  | 35 |  |  |  | 2020-04-07 23:59 | 2020-06-05 18:00 |  | 65 | 2020-07-20 11:44 |  |  | 2020-04-14 17:40 | 2020-06-26 18:00 |  | 80 | 2020-08-03 10:04 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-06 17:40 | 2020-06-26 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 319 |  |  |  |  | 101330
1637 | Task(Task)-->E (Engineering) | OIL TYPE POWER TRANSFORMER - RATING AND DIAGRAM PLATE |  | 1.13.1.2 | OIL TYPE POWER TRANSFORMER - RATING AND DIAGRAM PLATE-->ELECTRICAL-->ENGINEERING-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-25 17:40 | 2020-05-06 17:40 | 2020-05-21 18:00 | 2020-07-28 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-140 |  | 2020-02-13 11:46 | 7012-155-PVE-W-085 |  |  |  | A |  |  |  | 2.5522 | 0.001126 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4029 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-25 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-25 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-04-01 17:40 | 2020-06-03 18:00 |  | 35 |  |  |  | 2020-04-07 23:59 | 2020-06-03 18:00 |  | 65 | 2020-07-20 11:45 |  |  | 2020-04-14 17:40 | 2020-06-24 18:00 |  | 80 | 2020-07-28 17:55 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-06 17:40 | 2020-06-24 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 320 |  |  |  |  | 101331
1638 | Task(Task)-->E (Engineering) | OIL TYPE POWER TRANSFORMER - GA OF H.V. CABLE BOX |  | 1.13.1.2 | OIL TYPE POWER TRANSFORMER - GA OF H.V. CABLE BOX-->ELECTRICAL-->ENGINEERING-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-23 18:00 | 2020-05-06 17:40 | 2020-05-21 18:00 | 2020-07-28 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-141 |  | 2020-02-13 11:46 | 7012-155-PVE-B-086 |  |  |  | A |  |  |  | 0.46404 | 0.000205 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 8.17 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4009 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-23 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-25 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-04-01 17:40 | 2020-06-05 18:00 |  | 35 |  |  |  | 2020-04-07 23:59 | 2020-06-05 18:00 |  | 65 | 2020-07-20 11:46 |  |  | 2020-04-14 17:40 | 2020-06-26 18:00 |  | 80 | 2020-08-03 10:04 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-06 17:40 | 2020-06-26 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 321 |  |  |  |  | 101332
1639 | Task(Task)-->E (Engineering) | OIL TYPE POWER TRANSFORMER - GA OF L.V. CABLE BOX |  | 1.13.1.2 | OIL TYPE POWER TRANSFORMER - GA OF L.V. CABLE BOX-->ELECTRICAL-->ENGINEERING-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-25 17:40 | 2020-05-06 17:40 | 2020-05-21 18:00 | 2020-07-28 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-142 |  | 2020-02-13 11:46 | 7012-155-PVE-B-087 |  |  |  | A |  |  |  | 0.46404 | 0.000205 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 8.17 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4010 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-26 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-25 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-04-01 17:40 | 2020-06-02 18:00 |  | 35 |  |  |  | 2020-04-07 23:59 | 2020-06-02 18:00 |  | 65 | 2020-07-20 11:46 |  |  | 2020-04-14 17:40 | 2020-06-23 18:00 |  | 80 | 2020-08-03 10:03 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-06 17:40 | 2020-06-23 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 322 |  |  |  |  | 101333
1640 | Task(Task)-->E (Engineering) | OIL TYPE POWER TRANSFORMER - GA & SCHEMATIC OF MARSHALLING BOX |  | 1.13.1.2 | OIL TYPE POWER TRANSFORMER - GA & SCHEMATIC OF MARSHALLING BOX-->ELECTRICAL-->ENGINEERING-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-23 18:00 | 2020-05-06 17:40 | 2020-05-21 18:00 | 2020-07-28 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-143 |  | 2020-02-13 11:46 | 7012-155-PVE-B-088 |  |  |  | A |  |  |  | 1.3921 | 0.000614 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4011 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-23 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-25 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-04-01 17:40 | 2020-06-05 18:00 |  | 35 |  |  |  | 2020-04-07 23:59 | 2020-06-05 18:00 |  | 65 | 2020-07-20 11:47 |  |  | 2020-04-14 17:40 | 2020-06-26 18:00 |  | 80 | 2020-08-03 10:03 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-06 17:40 | 2020-06-26 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 323 |  |  |  |  | 101334
1641 | Task(Task)-->E (Engineering) | OIL TYPE POWER TRANSFORMER - MANDATORY SPARES LIST |  | 1.13.1.2 | OIL TYPE POWER TRANSFORMER - MANDATORY SPARES LIST-->ELECTRICAL-->ENGINEERING-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-25 17:40 | 2020-05-06 17:40 | 2020-05-21 18:00 | 2020-11-15 23:59 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-144 |  | 2020-02-13 11:46 | 7012-155-PVE-W-089 |  |  |  | A |  |  |  | 1.3921 | 0.000614 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4030 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-25 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-25 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-04-01 17:40 | 2020-06-03 18:00 |  | 35 |  |  |  | 2020-04-07 23:59 | 2020-06-03 18:00 |  | 65 |  |  |  | 2020-04-14 17:40 | 2020-06-24 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-06 17:40 | 2020-06-24 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 324 |  |  |  |  | 101335
1642 | Task(Task)-->E (Engineering) | OIL TYPE POWER TRANSFORMER - DATASHEET |  | 1.13.1.2 | OIL TYPE POWER TRANSFORMER - DATASHEET-->ELECTRICAL-->ENGINEERING-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-24 18:00 | 2020-05-06 17:40 | 2020-05-21 18:00 | 2020-07-20 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-145 |  | 2020-02-13 11:46 | 7012-155-PVE-Y-090 |  |  |  | A |  |  |  | 1.3921 | 0.000614 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4034 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-24 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-25 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-04-01 17:40 | 2020-06-04 18:00 |  | 35 |  |  |  | 2020-04-07 23:59 | 2020-06-04 18:00 |  | 65 | 2020-09-23 17:53 |  |  | 2020-04-14 17:40 | 2020-06-25 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-06 17:40 | 2020-06-25 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 325 |  |  |  |  | 101336
1643 | Task(Task)-->E (Engineering) | OIL TYPE DISTRIBUTION TRANSFORMER - GA DRAWINGS |  | 1.13.1.2 | OIL TYPE DISTRIBUTION TRANSFORMER - GA DRAWINGS-->ELECTRICAL-->ENGINEERING-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-23 18:00 | 2020-05-06 17:40 | 2020-05-21 18:00 | 2020-08-06 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-146 |  | 2020-02-13 11:46 | 7012-155-PVE-B-091 |  |  |  | A |  |  |  | 1.3921 | 0.000614 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4012 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-23 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-25 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-04-01 17:40 | 2020-06-05 18:00 |  | 35 |  |  |  | 2020-04-07 23:59 | 2020-06-05 18:00 |  | 65 | 2020-09-23 17:54 |  |  | 2020-04-14 17:40 | 2020-06-26 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-06 17:40 | 2020-06-26 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 326 |  |  |  |  | 101337
1644 | Task(Task)-->E (Engineering) | OIL TYPE DISTRIBUTION TRANSFORMER - RATING AND DIAGRAM PLATE |  | 1.13.1.2 | OIL TYPE DISTRIBUTION TRANSFORMER - RATING AND DIAGRAM PLATE-->ELECTRICAL-->ENGINEERING-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-25 17:40 | 2020-05-06 17:40 | 2020-05-21 18:00 | 2020-08-07 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-147 |  | 2020-02-13 11:46 | 7012-155-PVE-W-092 |  |  |  | A |  |  |  | 0.46404 | 0.000205 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 8.17 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4031 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-26 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-25 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-04-01 17:40 | 2020-06-02 18:00 |  | 35 |  |  |  | 2020-04-07 23:59 | 2020-06-02 18:00 |  | 65 |  |  |  | 2020-04-14 17:40 | 2020-06-23 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-06 17:40 | 2020-06-23 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 327 |  |  |  |  | 101338
1645 | Task(Task)-->E (Engineering) | OIL TYPE DISTRIBUTION TRANSFORMER - GA OF H.V. CABLE BOX |  | 1.13.1.2 | OIL TYPE DISTRIBUTION TRANSFORMER - GA OF H.V. CABLE BOX-->ELECTRICAL-->ENGINEERING-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-25 17:40 | 2020-05-06 17:40 | 2020-05-21 18:00 | 2020-08-07 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-148 |  | 2020-02-13 11:46 | 7012-155-PVE-B-093 |  |  |  | A |  |  |  | 0.46404 | 0.000205 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 8.17 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4013 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-27 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-25 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-04-01 17:40 | 2020-06-01 18:00 |  | 35 |  |  |  | 2020-04-07 23:59 | 2020-06-01 18:00 |  | 65 |  |  |  | 2020-04-14 17:40 | 2020-06-22 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-06 17:40 | 2020-06-22 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 328 |  |  |  |  | 101339
1646 | Task(Task)-->E (Engineering) | OIL TYPE DISTRIBUTION TRANSFORMER - GA OF L.V. BUS DUCT |  | 1.13.1.2 | OIL TYPE DISTRIBUTION TRANSFORMER - GA OF L.V. BUS DUCT-->ELECTRICAL-->ENGINEERING-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-25 17:40 | 2020-05-06 17:40 | 2020-05-21 18:00 | 2020-08-07 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-149 |  | 2020-02-13 11:46 | 7012-155-PVE-B-094 |  |  |  | A |  |  |  | 0.46404 | 0.000205 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 8.17 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4014 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-25 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-25 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-04-01 17:40 | 2020-06-03 18:00 |  | 35 |  |  |  | 2020-04-07 23:59 | 2020-06-03 18:00 |  | 65 |  |  |  | 2020-04-14 17:40 | 2020-06-24 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-06 17:40 | 2020-06-24 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 329 |  |  |  |  | 101340
1647 | Task(Task)-->E (Engineering) | OIL TYPE DISTRIBUTION TRANSFORMER - GA & SCHEMATIC OF MARSHALLING BOX |  | 1.13.1.2 | OIL TYPE DISTRIBUTION TRANSFORMER - GA & SCHEMATIC OF MARSHALLING BOX-->ELECTRICAL-->ENGINEERING-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-24 18:00 | 2020-05-06 17:40 | 2020-05-21 18:00 | 2020-08-12 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-150 |  | 2020-02-13 11:46 | 7012-155-PVE-B-095 |  |  |  | A |  |  |  | 1.3921 | 0.000614 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4015 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-24 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-25 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-04-01 17:40 | 2020-06-04 18:00 |  | 35 |  |  |  | 2020-04-07 23:59 | 2020-06-04 18:00 |  | 65 |  |  |  | 2020-04-14 17:40 | 2020-06-25 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-06 17:40 | 2020-06-25 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 330 |  |  |  |  | 101341
1648 | Task(Task)-->E (Engineering) | OIL TYPE DISTRIBUTION TRANSFORMER - MANDATORY SPARES LIST |  | 1.13.1.2 | OIL TYPE DISTRIBUTION TRANSFORMER - MANDATORY SPARES LIST-->ELECTRICAL-->ENGINEERING-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-24 18:00 | 2020-05-06 17:40 | 2020-05-21 18:00 | 2020-08-21 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-151 |  | 2020-02-13 11:46 | 7012-155-PVE-W-096 |  |  |  | A |  |  |  | 1.3921 | 0.000614 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4032 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-24 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-25 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-04-01 17:40 | 2020-06-04 18:00 |  | 35 |  |  |  | 2020-04-07 23:59 | 2020-06-04 18:00 |  | 65 |  |  |  | 2020-04-14 17:40 | 2020-06-25 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-06 17:40 | 2020-06-25 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 331 |  |  |  |  | 101342
1649 | Task(Task)-->E (Engineering) | OIL TYPE DISTRIBUTION TRANSFORMER - DATASHEET |  | 1.13.1.2 | OIL TYPE DISTRIBUTION TRANSFORMER - DATASHEET-->ELECTRICAL-->ENGINEERING-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-23 18:00 | 2020-05-06 17:40 | 2020-05-21 18:00 | 2020-08-12 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-152 |  | 2020-02-13 11:46 | 7012-155-PVE-Y-097 |  |  |  | A |  |  |  | 1.3921 | 0.000614 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4035 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-23 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-25 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-04-01 17:40 | 2020-06-05 18:00 |  | 35 |  |  |  | 2020-04-07 23:59 | 2020-06-05 18:00 |  | 65 |  |  |  | 2020-04-14 17:40 | 2020-06-26 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-06 17:40 | 2020-06-26 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 332 |  |  |  |  | 101343
1650 | Task(Task)-->E (Engineering) | GAD, WIRING DIAGRAM, DATA SHEET & BOM OF 415V LV VFD FOR CHP. |  | 1.13.1.2 | GAD, WIRING DIAGRAM, DATA SHEET & BOM OF 415V LV VFD FOR CHP.-->ELECTRICAL-->ENGINEERING-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-04 17:40 | 2020-05-16 17:40 | 2020-05-21 18:00 | 2020-07-12 23:59 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-154 |  | 2020-02-13 11:46 | 7012-155-PVE-W-099 |  |  |  | A |  |  |  | 5.1044 | 0.002251 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 82.54 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4005 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-05 23:59 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-04-04 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-04-10 17:40 | 2020-06-02 18:00 |  | 35 |  |  |  | 2020-04-17 23:59 | 2020-06-02 18:00 |  | 65 | 2020-08-03 10:44 |  |  | 2020-04-23 17:40 | 2020-06-23 18:00 |  | 80 | 2020-08-03 10:45 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-16 17:40 | 2020-06-23 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 334 |  |  |  |  | 101345
1651 | Task(Task)-->E (Engineering) | DATASHEET & TYPICAL SCHEME DIAGRAM OF 415V LT PMCC FOR CHP |  | 1.13.1.2 | DATASHEET & TYPICAL SCHEME DIAGRAM OF 415V LT PMCC FOR CHP-->ELECTRICAL-->ENGINEERING-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-11 18:00 | 2020-04-23 17:40 | 2020-05-21 18:00 | 2020-09-22 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-158 |  | 2020-02-13 11:46 | 7012-155-PVE-L-103 |  |  |  | A |  |  |  | 12.993 | 0.00573 | 0.56 | Plan & Actual | Date |  | 0 | 0 | 0 | 207.15 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4027 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-11 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-12 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-03-19 17:40 | 2020-06-04 18:00 |  | 35 |  |  |  | 2020-03-25 23:59 | 2020-06-04 18:00 |  | 65 |  |  |  | 2020-04-01 17:40 | 2020-06-25 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-23 17:40 | 2020-06-25 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 338 |  |  |  |  | 101349
1652 | Task(Task)-->E (Engineering) | GA, DATA SHEETS, BOM & LAYOUT OF 415V LT (NSPBD) BUSDUCT |  | 1.13.1.2 | GA, DATA SHEETS, BOM & LAYOUT OF 415V LT (NSPBD) BUSDUCT-->ELECTRICAL-->ENGINEERING-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-20 17:40 | 2020-05-01 17:40 | 2020-05-21 18:00 | 2020-11-15 23:59 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-159 |  | 2020-02-13 11:46 | 7012-155-PVE-W-104 |  |  |  | A |  |  |  | 5.1044 | 0.002251 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 82.54 | 0 | 39 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4033 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-23 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-20 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-03-26 17:40 | 2020-05-31 23:59 |  | 35 |  |  |  | 2020-04-02 23:59 | 2020-05-31 23:59 |  | 65 |  |  |  | 2020-04-08 17:40 | 2020-06-21 23:59 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-01 17:40 | 2020-06-21 23:59 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 339 |  |  |  |  | 101350
1653 | Task(Task)-->E (Engineering) | SUBSTATION-1 (SS-1) NEAR KDTP-1 EQUIPMENT, CABLE ROUTING,EARTHING & LIGHTNING LAYOUT WITH PLAN & SECTIONAL VIEW & BOM. |  | 1.13.1.2 | SUBSTATION-1 (SS-1) NEAR KDTP-1 EQUIPMENT, CABLE ROUTING,EARTHING & LIGHTNING LAYOUT WITH PLAN & SECTIONAL VIEW & BOM.-->ELECTRICAL-->ENGINEERING-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-12-18 18:00 | 2020-02-12 17:40 | 2020-01-13 18:00 | 2020-05-06 18:00 |  |  | 2020-02-21 14:31 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5060 |  | 2020-02-13 11:44 | 7012-155-PVE-F-022 |  |  |  | A |  |  |  | 15.5452 | 0.006856 | 0.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 248.42 | 0 | 23.3 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4001 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-12-18 18:00 | 2020-01-13 18:00 |  | 10 | 2020-01-13 23:31 |  |  | 2020-01-03 17:40 | 2020-02-24 18:00 |  | 30 | 2020-02-24 23:31 |  |  | 2020-01-09 17:40 | 2020-03-09 18:00 |  | 35 | 2020-03-09 23:31 |  |  | 2020-01-15 23:59 | 2020-03-16 18:00 |  | 65 | 2020-03-16 23:31 |  |  | 2020-01-21 17:40 | 2020-04-06 18:00 |  | 80 | 2020-04-15 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-02-12 17:40 | 2020-05-06 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 257 |  |  |  |  | 101268
1654 | Task(Task)-->E (Engineering) | LIGHTING LAYOUT PLAN WITH POWER DISTRIBUTION ARRANGEMENT, SECTIONAL VIEW, BOM OF SS-1 |  | 1.13.1.2 | LIGHTING LAYOUT PLAN WITH POWER DISTRIBUTION ARRANGEMENT, SECTIONAL VIEW, BOM OF SS-1-->ELECTRICAL-->ENGINEERING-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-10 18:00 | 2020-03-31 17:40 | 2020-05-15 09:00 | 2020-07-11 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5071 |  | 2020-02-13 11:44 | 7012-155-PVE-G-033 |  |  |  | A |  |  |  | 15.5452 | 0.006856 | 0.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 248.42 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4002 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-10 18:00 | 2020-05-30 18:00 |  | 10 | 2020-05-10 23:31 |  |  | 2020-02-18 17:40 | 2020-06-06 18:00 |  | 30 | 2020-05-12 23:31 |  |  | 2020-02-25 17:40 | 2020-06-13 18:00 |  | 35 | 2020-05-12 23:31 |  |  | 2020-03-02 23:59 | 2020-06-20 18:00 |  | 65 | 2020-05-15 23:31 |  |  | 2020-03-07 17:40 | 2020-07-11 18:00 |  | 80 | 2020-05-22 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-31 17:40 | 2020-07-11 18:00 |  | 100 | 2020-05-22 23:31 | [121 empty] | Varun Parihari | [22 empty] | 268 |  |  |  |  | 101279
1655 | Task(Task)-->E (Engineering) | GA & CROSS SECTIONAL, FLOOR PLAN FOR 33 kV HT SWITCHGEAR FOR CHP |  | 1.13.1.2 | GA & CROSS SECTIONAL, FLOOR PLAN FOR 33 kV HT SWITCHGEAR FOR CHP-->ELECTRICAL-->ENGINEERING-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-28 18:00 | 2020-04-13 17:40 | 2020-05-21 18:00 | 2020-09-18 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-121 |  | 2020-02-13 11:45 | 7012-155-PVE-B-066 |  |  |  | A |  |  |  | 1.3921 | 0.000614 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4003 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-28 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-02 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-03-07 17:40 | 2020-06-04 18:00 |  | 35 |  |  |  | 2020-03-13 23:59 | 2020-06-04 18:00 |  | 65 | 2020-09-23 14:43 |  |  | 2020-03-20 17:40 | 2020-06-25 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-13 17:40 | 2020-06-25 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 301 |  |  |  |  | 101312
1656 | Task(Task)-->E (Engineering) | SINGLE LINE DIAGRAM FOR 33 kV HT SWITCHGEAR FOR CHP |  | 1.13.1.2 | SINGLE LINE DIAGRAM FOR 33 kV HT SWITCHGEAR FOR CHP-->ELECTRICAL-->ENGINEERING-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-27 18:00 | 2020-04-13 17:40 | 2020-05-21 18:00 | 2020-09-22 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-124 |  | 2020-02-13 11:45 | 7012-155-PVE-P-069 |  |  |  | A |  |  |  | 1.3921 | 0.000614 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4004 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-27 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-02 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-03-07 17:40 | 2020-06-05 18:00 |  | 35 |  |  |  | 2020-03-13 23:59 | 2020-06-05 18:00 |  | 65 | 2020-09-23 14:47 |  |  | 2020-03-20 17:40 | 2020-06-26 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-13 17:40 | 2020-06-26 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 304 |  |  |  |  | 101315
1657 | Task(Task)-->E (Engineering) | GA, SLD & BOM FOR 415V LT CHP PMCC-1 |  | 1.13.1.2 | GA, SLD & BOM FOR 415V LT CHP PMCC-1-->ELECTRICAL-->ENGINEERING-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-12 17:40 | 2020-04-23 17:40 | 2020-05-21 18:00 | 2020-09-22 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-155 |  | 2020-02-13 11:46 | 7012-155-PVE-W-100 |  |  |  | A |  |  |  | 7.6566 | 0.003377 | 0.33 | Plan & Actual | Date |  | 0 | 0 | 0 | 124.21 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4006 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-12 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-12 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-03-19 17:40 | 2020-06-03 18:00 |  | 35 |  |  |  | 2020-03-25 23:59 | 2020-06-03 18:00 |  | 65 |  |  |  | 2020-04-01 17:40 | 2020-06-24 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-23 17:40 | 2020-06-24 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 335 |  |  |  |  | 101346
1658 | Task(Task)-->P (Procurement) | PROCUREMENT | 1.13.2 | 1.13 | PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-11-12 09:00 | 2021-03-31 18:00 | 2019-11-02 09:00 | 2021-11-24 18:00 |  |  | 2019-11-02 10:57 |  |  |  | 83.6939 | 20.9158 | [15 empty] | 58.6757 | 2.0635 | 202.93 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4036 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019138
1659 | Task(Task)-->P (Procurement) | PURCHASE REQUISITION | 1.13.2.1 | 1.13.2 | PURCHASE REQUISITION-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-11-12 09:00 | 2020-05-26 18:00 | 2019-11-02 09:00 | 2020-04-18 18:00 |  |  | 2019-11-02 10:57 |  |  |  | 100 | 84.2681 | [15 empty] | 5.0015 | 0.10321 | 10.15 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4037 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019139
1660 | Task(Task)-->P (Procurement) | 33/6.9KV HT TRANSFORMER (ONAN TYPE) |  | 1.13.2.1 | 33/6.9KV HT TRANSFORMER (ONAN TYPE)-->PURCHASE REQUISITION-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-28 09:00 | 2019-11-28 18:00 | 2020-01-17 09:00 | 2020-01-17 18:00 |  |  | 2020-01-22 10:57 | 2020-01-22 10:57 |  |  | 100 | 100 | [15 empty] | 10.0295 | 0.010351 | 1.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4038 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019140
1661 | Task(Task)-->P (Procurement) | HT SWITCHGEAR (33KV & 6.6KV) |  | 1.13.2.1 | HT SWITCHGEAR (33KV & 6.6KV)-->PURCHASE REQUISITION-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-13 09:00 | 2019-11-13 18:00 | 2019-11-02 09:00 | 2019-11-02 18:00 |  |  | 2019-11-02 10:57 | 2019-11-02 10:57 |  |  | 100 | 100 | [15 empty] | 31.2684 | 0.032271 | 3.18 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4039 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019141
1662 | Task(Task)-->P (Procurement) | 6.6KV HT VFD with Motors |  | 1.13.2.1 | 6.6KV HT VFD with Motors-->PURCHASE REQUISITION-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-30 09:00 | 2019-12-30 18:00 | 2020-01-24 09:00 | 2020-01-24 18:00 |  |  | 2019-11-21 10:57 | 2019-11-21 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4040 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019142
1663 | Task(Task)-->P (Procurement) | 415V LT VFD |  | 1.13.2.1 | 415V LT VFD-->PURCHASE REQUISITION-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-18 09:00 | 2019-12-18 18:00 | 2019-11-21 09:00 | 2019-11-21 18:00 |  |  | 2019-11-21 10:57 | 2019-11-21 10:57 |  |  | 100 | 100 | [15 empty] | 4.6214 | 0.00477 | 0.47 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4041 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019143
1664 | Task(Task)-->P (Procurement) | 6.6KV HT APFC PANEL |  | 1.13.2.1 | 6.6KV HT APFC PANEL-->PURCHASE REQUISITION-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-24 09:00 | 2020-01-24 18:00 | 2020-02-13 09:00 | 2020-02-13 18:00 |  |  | 2020-02-13 10:57 | 2020-02-13 10:57 |  |  | 100 | 100 | [15 empty] | 1.1799 | 0.001218 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4042 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019144
1665 | Task(Task)-->P (Procurement) | 6.6KV/0.433V LT TRANSFORMER |  | 1.13.2.1 | 6.6KV/0.433V LT TRANSFORMER-->PURCHASE REQUISITION-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-25 09:00 | 2019-11-25 18:00 | 2020-01-22 09:00 | 2020-01-22 18:00 |  |  | 2020-01-22 15:37 | 2020-01-22 15:37 |  |  | 100 | 100 | [15 empty] | 10.0295 | 0.010351 | 1.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4043 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019145
1666 | Task(Task)-->P (Procurement) | LT BUSDUCT |  | 1.13.2.1 | LT BUSDUCT-->PURCHASE REQUISITION-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-02 09:00 | 2019-12-02 18:00 | 2019-12-11 09:00 | 2019-12-11 18:00 |  |  | 2019-12-11 10:57 | 2019-12-11 10:57 |  |  | 100 | 100 | [15 empty] | 1.5733 | 0.001624 | 0.16 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4044 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019146
1667 | Task(Task)-->P (Procurement) | 415V MCC |  | 1.13.2.1 | 415V MCC-->PURCHASE REQUISITION-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-11-28 09:00 | 2019-11-28 18:00 | 2019-11-14 09:00 | 2019-11-14 18:00 | [6 empty] | 100 | 0 | [15 empty] | 10.1278 | 0.010452 | 1.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4045 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019147
1668 | Task(Task)-->P (Procurement) | 110V DC BATTERY & BATTERY CHARGER SYSTEM |  | 1.13.2.1 | 110V DC BATTERY & BATTERY CHARGER SYSTEM-->PURCHASE REQUISITION-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-13 09:00 | 2020-01-13 18:00 | 2020-01-13 09:00 | 2020-01-13 18:00 |  |  | 2020-01-13 10:57 | 2020-01-13 10:57 |  |  | 100 | 100 | [15 empty] | 3.3432 | 0.00345 | 0.34 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4046 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019148
1669 | Task(Task)-->P (Procurement) | 6.6KV NEUTRAL GROUNDING RESISTOR |  | 1.13.2.1 | 6.6KV NEUTRAL GROUNDING RESISTOR-->PURCHASE REQUISITION-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-12 09:00 | 2019-12-12 18:00 | 2019-12-12 09:00 | 2019-12-12 18:00 |  |  | 2019-12-12 15:20 | 2019-12-12 15:21 |  |  | 100 | 100 | [15 empty] | 0.29499 | 0.000304 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4047 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019149
1670 | Task(Task)-->P (Procurement) | PLC SYSTEM |  | 1.13.2.1 | PLC SYSTEM-->PURCHASE REQUISITION-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-12 09:00 | 2019-11-12 18:00 | 2019-11-12 09:00 | 2019-11-12 18:00 |  |  | 2019-11-12 10:57 | 2019-11-12 10:57 |  |  | 100 | 100 | [15 empty] | 7.9646 | 0.00822 | 0.81 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4048 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019150
1671 | Task(Task)-->P (Procurement) | UPS SYSTEM |  | 1.13.2.1 | UPS SYSTEM-->PURCHASE REQUISITION-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-08 09:00 | 2020-01-08 18:00 | 2020-02-19 09:00 | 2020-02-19 18:00 |  |  | 2020-02-19 10:57 | 2020-02-19 10:57 |  |  | 100 | 100 | [15 empty] | 1.4749 | 0.001522 | 0.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4049 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019151
1672 | Task(Task)-->P (Procurement) | 24V DC BATTERY AND BATTERY CHARGER SYSTEM |  | 1.13.2.1 | 24V DC BATTERY AND BATTERY CHARGER SYSTEM-->PURCHASE REQUISITION-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-27 09:00 | 2020-01-27 18:00 | 2020-02-26 09:00 | 2020-02-26 18:00 |  |  | 2020-02-26 10:57 | 2020-02-26 10:57 |  |  | 100 | 100 | [15 empty] | 0.6883 | 0.00071 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4050 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019152
1673 | Task(Task)-->P (Procurement) | FDA SYSTEM |  | 1.13.2.1 | FDA SYSTEM-->PURCHASE REQUISITION-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-14 09:00 | 2020-02-14 18:00 | 2020-02-17 09:00 | 2020-02-17 18:00 |  |  | 2020-02-17 10:57 | 2020-02-17 10:57 |  |  | 100 | 100 | [15 empty] | 4.8181 | 0.004973 | 0.49 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4051 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019153
1674 | Task(Task)-->P (Procurement) | SCADA |  | 1.13.2.1 | SCADA-->PURCHASE REQUISITION-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-10 09:00 | 2019-12-10 18:00 | 2019-12-21 09:00 | 2019-12-21 18:00 |  |  | 2019-12-21 10:57 | 2019-12-21 10:57 |  |  | 100 | 100 | [15 empty] | 2.2616 | 0.002334 | 0.23 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4052 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019154
1675 | Task(Task)-->P (Procurement) | RUBBER MATS |  | 1.13.2.1 | RUBBER MATS-->PURCHASE REQUISITION-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-26 09:00 | 2020-05-26 18:00 | 2020-04-18 09:00 | 2020-04-18 18:00 |  |  | 2020-04-18 10:57 | 2020-04-18 10:57 |  |  | 100 | 100 | [15 empty] | 0.098328 | 0.000101 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4055 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019155
1676 | Task(Task)-->P (Procurement) | MAIN LIGHTING DISTRIBUTION BOARD |  | 1.13.2.1 | MAIN LIGHTING DISTRIBUTION BOARD-->PURCHASE REQUISITION-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-04 09:00 | 2020-02-04 18:00 | 2020-04-02 09:00 | 2020-04-02 18:00 |  |  | 2020-04-02 17:08 | 2020-04-02 17:08 |  |  | 100 | 100 | [15 empty] | 0.49164 | 0.000507 | 0.05 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4056 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019156
1677 | Task(Task)-->P (Procurement) | LIGHTING PANELS |  | 1.13.2.1 | LIGHTING PANELS-->PURCHASE REQUISITION-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-28 09:00 | 2020-02-28 18:00 | 2020-04-02 09:00 | 2020-04-02 18:00 | [6 empty] | 100 | 0 | [15 empty] | 5.6047 | 0.005784 | 0.57 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4057 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019157
1678 | Task(Task)-->P (Procurement) | DCDB & DC FUSE BOARD |  | 1.13.2.1 | DCDB & DC FUSE BOARD-->PURCHASE REQUISITION-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-28 09:00 | 2020-01-28 18:00 | 2020-04-02 09:00 | 2020-04-02 18:00 |  |  | 2020-04-02 16:53 | 2020-04-02 16:53 |  |  | 100 | 100 | [15 empty] | 2.0649 | 0.002131 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4058 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019158
1679 | Task(Task)-->P (Procurement) | UPS DB,ACDB,MCBDB & AFB |  | 1.13.2.1 | UPS DB,ACDB,MCBDB & AFB-->PURCHASE REQUISITION-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-18 09:00 | 2020-03-18 18:00 | 2020-04-02 09:00 | 2020-04-02 18:00 |  |  | 2020-04-02 17:01 | 2020-04-02 17:01 |  |  | 100 | 100 | [15 empty] | 2.0649 | 0.002131 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4059 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019159
1680 | Task(Task)-->P (Procurement) | TECHNICAL CLEARANCE | 1.13.2.2 | 1.13.2 | TECHNICAL CLEARANCE-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-11-13 09:00 | 2020-06-20 18:00 | 2019-11-02 09:00 | 2020-07-10 18:00 |  |  | 2019-11-04 14:46 |  |  |  | 100 | 83.5801 | [15 empty] | 5.0015 | 0.10321 | 10.15 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4060 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019160
1681 | Task(Task)-->P (Procurement) | 33/6.9KV HT TRANSFORMER (ONAN TYPE) |  | 1.13.2.2 | 33/6.9KV HT TRANSFORMER (ONAN TYPE)-->TECHNICAL CLEARANCE-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-29 09:00 | 2019-12-22 23:59 | 2020-01-17 09:00 | 2020-02-17 18:00 |  |  | 2020-03-16 10:57 | 2020-03-16 10:57 |  |  | 100 | 100 | [15 empty] | 10.0295 | 0.010351 | 1.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4061 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019161
1682 | Task(Task)-->P (Procurement) | HT SWITCHGEAR (33KV & 6.6KV) |  | 1.13.2.2 | HT SWITCHGEAR (33KV & 6.6KV)-->TECHNICAL CLEARANCE-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-14 09:00 | 2019-12-13 18:00 | 2019-11-02 09:00 | 2020-03-10 18:00 |  |  | 2019-11-04 14:46 | 2020-03-10 14:46 |  |  | 100 | 100 | [15 empty] | 31.2684 | 0.032271 | 3.18 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4062 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019162
1683 | Task(Task)-->P (Procurement) | 6.6KV HT VFD with Motors |  | 1.13.2.2 | 6.6KV HT VFD with Motors-->TECHNICAL CLEARANCE-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-31 09:00 | 2020-01-29 18:00 | 2020-01-24 09:00 | 2020-04-16 18:00 |  |  | 2020-02-26 10:57 | 2020-02-26 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4063 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019163
1684 | Task(Task)-->P (Procurement) | 415V LT VFD |  | 1.13.2.2 | 415V LT VFD-->TECHNICAL CLEARANCE-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-19 09:00 | 2020-01-17 18:00 | 2019-11-21 09:00 | 2020-02-26 18:00 |  |  | 2020-02-26 10:57 | 2020-02-26 10:57 |  |  | 100 | 100 | [15 empty] | 4.6214 | 0.00477 | 0.47 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4064 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019164
1685 | Task(Task)-->P (Procurement) | 6.6KV HT APFC PANEL |  | 1.13.2.2 | 6.6KV HT APFC PANEL-->TECHNICAL CLEARANCE-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-25 09:00 | 2020-02-16 23:59 | 2020-02-13 09:00 | 2020-04-28 18:00 |  |  | 2020-04-28 10:57 | 2020-04-28 10:57 |  |  | 100 | 100 | [15 empty] | 1.1799 | 0.001218 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4065 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019165
1686 | Task(Task)-->P (Procurement) | 6.6KV/0.433V LT TRANSFORMER |  | 1.13.2.2 | 6.6KV/0.433V LT TRANSFORMER-->TECHNICAL CLEARANCE-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-26 09:00 | 2019-12-20 18:00 | 2020-01-22 09:00 | 2020-03-16 18:00 |  |  | 2020-01-23 15:38 | 2020-03-16 15:38 |  |  | 100 | 100 | [15 empty] | 10.0295 | 0.010351 | 1.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4066 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019166
1687 | Task(Task)-->P (Procurement) | LT BUSDUCT |  | 1.13.2.2 | LT BUSDUCT-->TECHNICAL CLEARANCE-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-03 09:00 | 2020-01-03 18:00 | 2019-12-11 09:00 | 2020-03-10 18:00 |  |  | 2020-03-10 10:57 | 2020-03-10 10:57 |  |  | 100 | 100 | [15 empty] | 1.5733 | 0.001624 | 0.16 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4067 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019167
1688 | Task(Task)-->P (Procurement) | 415V MCC |  | 1.13.2.2 | 415V MCC-->TECHNICAL CLEARANCE-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-11-29 09:00 | 2020-01-11 18:00 | 2019-11-14 09:00 | 2020-03-11 18:00 | [6 empty] | 100 | 0 | [15 empty] | 10.1278 | 0.010452 | 1.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4068 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019168
1689 | Task(Task)-->P (Procurement) | 110V DC BATTERY & BATTERY CHARGER SYSTEM |  | 1.13.2.2 | 110V DC BATTERY & BATTERY CHARGER SYSTEM-->TECHNICAL CLEARANCE-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-14 09:00 | 2020-02-03 18:00 | 2020-01-13 09:00 | 2020-06-04 18:00 |  |  | 2020-01-14 17:10 | 2020-06-04 17:10 |  |  | 100 | 100 | [15 empty] | 3.3432 | 0.00345 | 0.34 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4069 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019169
1690 | Task(Task)-->P (Procurement) | 6.6KV NEUTRAL GROUNDING RESISTOR |  | 1.13.2.2 | 6.6KV NEUTRAL GROUNDING RESISTOR-->TECHNICAL CLEARANCE-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-13 09:00 | 2019-12-31 18:00 | 2019-12-12 09:00 | 2020-01-21 18:00 |  |  | 2019-12-13 15:22 | 2020-01-21 15:23 |  |  | 100 | 100 | [15 empty] | 0.29499 | 0.000304 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4070 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019170
1691 | Task(Task)-->P (Procurement) | PLC SYSTEM |  | 1.13.2.2 | PLC SYSTEM-->TECHNICAL CLEARANCE-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-13 09:00 | 2019-12-04 18:00 | 2019-11-12 09:00 | 2020-03-16 18:00 |  |  | 2020-03-16 10:57 | 2020-03-16 10:57 |  |  | 100 | 100 | [15 empty] | 7.9646 | 0.00822 | 0.81 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4071 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019171
1692 | Task(Task)-->P (Procurement) | UPS SYSTEM |  | 1.13.2.2 | UPS SYSTEM-->TECHNICAL CLEARANCE-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-09 09:00 | 2020-01-28 18:00 | 2020-02-19 09:00 | 2020-06-06 18:00 |  |  | 2020-06-06 10:57 | 2020-06-06 10:57 |  |  | 100 | 100 | [15 empty] | 1.4749 | 0.001522 | 0.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4072 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019172
1693 | Task(Task)-->P (Procurement) | 24V DC BATTERY AND BATTERY CHARGER SYSTEM |  | 1.13.2.2 | 24V DC BATTERY AND BATTERY CHARGER SYSTEM-->TECHNICAL CLEARANCE-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-28 09:00 | 2020-02-07 18:00 | 2020-02-26 09:00 | 2020-07-10 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.6883 | 0.00071 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4073 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019173
1694 | Task(Task)-->P (Procurement) | FDA SYSTEM |  | 1.13.2.2 | FDA SYSTEM-->TECHNICAL CLEARANCE-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-15 09:00 | 2020-03-12 18:00 | 2020-02-17 09:00 | 2020-06-10 18:00 |  |  | 2020-06-10 10:57 | 2020-06-10 10:57 |  |  | 100 | 100 | [15 empty] | 4.8181 | 0.004973 | 0.49 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4074 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019174
1695 | Task(Task)-->P (Procurement) | SCADA |  | 1.13.2.2 | SCADA-->TECHNICAL CLEARANCE-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-11 09:00 | 2020-01-15 18:00 | 2019-12-21 09:00 | 2020-03-16 18:00 |  |  | 2020-03-16 10:57 | 2020-03-16 10:57 |  |  | 100 | 100 | [15 empty] | 2.2616 | 0.002334 | 0.23 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4075 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019175
1696 | Task(Task)-->P (Procurement) | RUBBER MATS |  | 1.13.2.2 | RUBBER MATS-->TECHNICAL CLEARANCE-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-27 09:00 | 2020-06-20 18:00 | 2020-04-18 09:00 | 2020-04-20 18:00 |  |  | 2020-04-20 10:57 | 2020-04-20 10:57 |  |  | 100 | 100 | [15 empty] | 0.098328 | 0.000101 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4078 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019176
1697 | Task(Task)-->P (Procurement) | MAIN LIGHTING DISTRIBUTION BOARD |  | 1.13.2.2 | MAIN LIGHTING DISTRIBUTION BOARD-->TECHNICAL CLEARANCE-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-05 09:00 | 2020-04-02 18:00 | 2020-04-02 09:00 | 2020-07-01 18:00 |  |  | 2020-04-03 17:08 | 2020-07-01 17:08 |  |  | 100 | 100 | [15 empty] | 0.49164 | 0.000507 | 0.05 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4079 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019177
1698 | Task(Task)-->P (Procurement) | LIGHTING PANELS |  | 1.13.2.2 | LIGHTING PANELS-->TECHNICAL CLEARANCE-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-29 09:00 | 2020-05-11 18:00 | 2020-04-02 09:00 | 2020-07-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 5.6047 | 0.005784 | 0.57 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4080 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019178
1699 | Task(Task)-->P (Procurement) | DCDB & DC FUSE BOARD |  | 1.13.2.2 | DCDB & DC FUSE BOARD-->TECHNICAL CLEARANCE-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-29 09:00 | 2020-04-02 18:00 | 2020-04-02 09:00 | 2020-07-01 18:00 |  |  | 2020-04-03 16:59 | 2020-07-01 16:59 |  |  | 100 | 100 | [15 empty] | 2.0649 | 0.002131 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4081 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019179
1700 | Task(Task)-->P (Procurement) | UPS DB,ACDB,MCBDB & AFB |  | 1.13.2.2 | UPS DB,ACDB,MCBDB & AFB-->TECHNICAL CLEARANCE-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-19 09:00 | 2020-04-02 18:00 | 2020-04-02 09:00 | 2020-07-01 18:00 |  |  | 2020-04-03 17:03 | 2020-07-01 17:03 |  |  | 100 | 100 | [15 empty] | 2.0649 | 0.002131 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4082 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019180
1701 | Task(Task)-->P (Procurement) | ORDERING | 1.13.2.3 | 1.13.2 | ORDERING-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-12-05 09:00 | 2020-06-25 18:00 | 2020-01-21 09:00 | 2020-08-13 18:00 |  |  | 2020-03-11 14:48 |  |  |  | 100 | 77.3063 | [15 empty] | 9.998 | 0.20631 | 20.29 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4083 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019181
1702 | Task(Task)-->P (Procurement) | 33/6.9KV HT TRANSFORMER (ONAN TYPE) |  | 1.13.2.3 | 33/6.9KV HT TRANSFORMER (ONAN TYPE)-->ORDERING-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-23 09:00 | 2020-01-15 18:00 | 2020-02-17 09:00 | 2020-06-24 18:00 |  |  | 2020-07-16 22:27 | 2020-07-16 22:27 |  |  | 100 | 100 | [15 empty] | 10.0148 | 0.020661 | 2.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4084 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019182
1703 | Task(Task)-->P (Procurement) | HT SWITCHGEAR (33KV & 6.6KV) |  | 1.13.2.3 | HT SWITCHGEAR (33KV & 6.6KV)-->ORDERING-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-14 09:00 | 2020-01-13 18:00 | 2020-03-10 09:00 | 2020-07-18 18:00 |  |  | 2020-03-11 14:48 | 2020-07-04 14:48 |  |  | 100 | 100 | [15 empty] | 31.3764 | 0.064732 | 6.36 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4085 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019183
1704 | Task(Task)-->P (Procurement) | 6.6KV HT VFD with Motors |  | 1.13.2.3 | 6.6KV HT VFD with Motors-->ORDERING-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-30 09:00 | 2020-02-28 18:00 | 2020-04-16 09:00 | 2020-07-18 18:00 |  |  | 2020-04-29 10:57 | 2020-04-29 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4086 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019184
1705 | Task(Task)-->P (Procurement) | 415V LT VFD |  | 1.13.2.3 | 415V LT VFD-->ORDERING-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-18 09:00 | 2020-02-17 18:00 | 2020-02-26 09:00 | 2020-06-10 18:00 |  |  | 2020-04-29 10:57 | 2020-06-10 09:39 |  |  | 100 | 100 | [15 empty] | 4.6374 | 0.009567 | 0.94 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4087 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019185
1706 | Task(Task)-->P (Procurement) | 6.6KV HT APFC PANEL |  | 1.13.2.3 | 6.6KV HT APFC PANEL-->ORDERING-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-17 09:00 | 2020-03-10 18:00 | 2020-04-28 09:00 | 2020-07-28 18:00 |  |  | 2020-05-04 15:15 | 2020-07-10 15:15 |  |  | 100 | 100 | [15 empty] | 1.184 | 0.002443 | 0.24 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4088 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019186
1707 | Task(Task)-->P (Procurement) | 6.6KV/0.433V LT TRANSFORMER |  | 1.13.2.3 | 6.6KV/0.433V LT TRANSFORMER-->ORDERING-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-21 09:00 | 2020-01-15 18:00 | 2020-03-16 09:00 | 2020-06-23 18:00 |  |  | 2020-06-23 10:14 | 2020-06-23 10:14 |  |  | 100 | 100 | [15 empty] | 10.1135 | 0.020865 | 2.05 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4089 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019187
1708 | Task(Task)-->P (Procurement) | LT BUSDUCT |  | 1.13.2.3 | LT BUSDUCT-->ORDERING-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-04 09:00 | 2020-02-04 18:00 | 2020-03-10 09:00 | 2020-06-11 18:00 |  |  | 2020-04-27 10:57 | 2020-04-27 10:57 |  |  | 100 | 100 | [15 empty] | 1.5294 | 0.003155 | 0.31 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4090 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019188
1709 | Task(Task)-->P (Procurement) | 415V MCC |  | 1.13.2.3 | 415V MCC-->ORDERING-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-12 | 2020-02-25 18:00 | 2020-03-11 09:00 | 2020-07-04 18:00 | [6 empty] | 100 | 0 | [15 empty] | 10.2121 | 0.021068 | 2.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4091 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019189
1710 | Task(Task)-->P (Procurement) | 110V DC BATTERY & BATTERY CHARGER SYSTEM |  | 1.13.2.3 | 110V DC BATTERY & BATTERY CHARGER SYSTEM-->ORDERING-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-04 09:00 | 2020-02-24 18:00 | 2020-06-04 09:00 | 2020-07-18 18:00 |  |  | 2020-06-05 17:10 | 2020-07-06 17:10 |  |  | 100 | 100 | [15 empty] | 3.3054 | 0.006819 | 0.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4092 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019190
1711 | Task(Task)-->P (Procurement) | 6.6KV NEUTRAL GROUNDING RESISTOR |  | 1.13.2.3 | 6.6KV NEUTRAL GROUNDING RESISTOR-->ORDERING-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-01 09:00 | 2020-01-20 18:00 | 2020-01-21 09:00 | 2020-03-19 18:00 |  |  | 2020-03-19 10:19 | 2020-03-19 10:19 |  |  | 100 | 100 | [15 empty] | 0.296 | 0.000611 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4093 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019191
1712 | Task(Task)-->P (Procurement) | PLC SYSTEM |  | 1.13.2.3 | PLC SYSTEM-->ORDERING-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-05 09:00 | 2019-12-27 18:00 | 2020-03-16 09:00 | 2020-07-07 18:00 |  |  | 2020-03-17 17:20 | 2020-06-04 17:20 |  |  | 100 | 100 | [15 empty] | 7.9921 | 0.016488 | 1.62 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4094 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019192
1713 | Task(Task)-->P (Procurement) | UPS SYSTEM |  | 1.13.2.3 | UPS SYSTEM-->ORDERING-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-29 09:00 | 2020-02-18 18:00 | 2020-06-06 09:00 | 2020-07-31 18:00 | [6 empty] | 100 | 0 | [15 empty] | 1.4307 | 0.002952 | 0.29 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4095 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019193
1714 | Task(Task)-->P (Procurement) | 24V DC BATTERY AND BATTERY CHARGER SYSTEM |  | 1.13.2.3 | 24V DC BATTERY AND BATTERY CHARGER SYSTEM-->ORDERING-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-08 09:00 | 2020-02-19 18:00 | 2020-07-10 09:00 | 2020-08-07 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.69068 | 0.001425 | 0.14 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4096 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019194
1715 | Task(Task)-->P (Procurement) | FDA SYSTEM |  | 1.13.2.3 | FDA SYSTEM-->ORDERING-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-13 09:00 | 2020-04-08 18:00 | 2020-06-10 09:00 | 2020-08-06 18:00 | [6 empty] | 100 | 0 | [15 empty] | 4.7854 | 0.009873 | 0.97 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4097 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019195
1716 | Task(Task)-->P (Procurement) | SCADA |  | 1.13.2.3 | SCADA-->ORDERING-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-16 09:00 | 2020-02-20 18:00 | 2020-03-16 09:00 | 2020-06-24 18:00 |  |  | 2020-06-24 10:20 | 2020-06-24 10:20 |  |  | 100 | 100 | [15 empty] | 2.22 | 0.00458 | 0.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4098 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019196
1717 | Task(Task)-->P (Procurement) | RUBBER MATS |  | 1.13.2.3 | RUBBER MATS-->ORDERING-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2020-06-21 | 2020-06-25 18:00 | 2020-04-20 09:00 | 2020-06-06 18:00 |  |  | 2020-04-25 10:57 | 2020-04-25 10:57 |  |  | 100 | 100 | [15 empty] | 0.098668 | 0.000204 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4101 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019197
1718 | Task(Task)-->P (Procurement) | MAIN LIGHTING DISTRIBUTION BOARD |  | 1.13.2.3 | MAIN LIGHTING DISTRIBUTION BOARD-->ORDERING-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-03 09:00 | 2020-04-18 18:00 | 2020-07-01 09:00 | 2020-08-13 18:00 |  |  | 2020-07-02 17:08 | 2020-07-07 17:08 |  |  | 100 | 100 | [15 empty] | 0.49334 | 0.001018 | 0.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4102 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019198
1719 | Task(Task)-->P (Procurement) | LIGHTING PANELS |  | 1.13.2.3 | LIGHTING PANELS-->ORDERING-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-12 09:00 | 2020-06-25 18:00 | 2020-07-01 09:00 | 2020-08-13 18:00 | [6 empty] | 100 | 0 | [15 empty] | 5.5747 | 0.011501 | 1.13 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4103 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019199
1720 | Task(Task)-->P (Procurement) | DCDB & DC FUSE BOARD |  | 1.13.2.3 | DCDB & DC FUSE BOARD-->ORDERING-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-03 09:00 | 2020-04-18 18:00 | 2020-07-01 09:00 | 2020-08-13 18:00 |  |  | 2020-07-02 17:00 | 2020-07-07 17:00 |  |  | 100 | 100 | [15 empty] | 2.0227 | 0.004173 | 0.41 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4104 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019200
1721 | Task(Task)-->P (Procurement) | UPS DB,ACDB,MCBDB & AFB |  | 1.13.2.3 | UPS DB,ACDB,MCBDB & AFB-->ORDERING-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-03 09:00 | 2020-04-18 18:00 | 2020-07-01 09:00 | 2020-08-13 18:00 |  |  | 2020-07-02 17:05 | 2020-07-07 17:05 |  |  | 100 | 100 | [15 empty] | 2.0227 | 0.004173 | 0.41 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4105 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019201
1722 | Task(Task)-->P (Procurement) | ITP APPROVAL | 1.13.2.4 | 1.13.2 | ITP APPROVAL-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-12-28 09:00 | 2020-08-04 18:00 | 2020-06-05 09:00 | 2020-11-30 18:00 |  |  | 2020-06-05 08:53 |  |  |  | 100 | 12.8803 | [15 empty] | 5.0015 | 0.10321 | 10.15 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4106 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019202
1723 | Task(Task)-->P (Procurement) | 33/6.9KV HT TRANSFORMER (ONAN TYPE) |  | 1.13.2.4 | 33/6.9KV HT TRANSFORMER (ONAN TYPE)-->ITP APPROVAL-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-16 09:00 | 2020-02-24 18:00 | 2020-07-03 09:00 | 2020-07-15 18:00 |  |  | 2020-07-03 08:44 | 2020-07-15 08:45 |  |  | 100 | 100 | [15 empty] | 10.0295 | 0.010351 | 1.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4107 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019203
1724 | Task(Task)-->P (Procurement) | HT SWITCHGEAR (33KV & 6.6KV) |  | 1.13.2.4 | HT SWITCHGEAR (33KV & 6.6KV)-->ITP APPROVAL-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-14 09:00 | 2020-02-22 18:00 | 2020-08-06 09:00 | 2020-11-20 18:00 |  |  | 2020-07-13 10:49 |  |  |  | 100 | 0 | [15 empty] | 31.2684 | 0.032271 | 3.18 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4108 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019204
1725 | Task(Task)-->P (Procurement) | 6.6KV HT VFD with Motors |  | 1.13.2.4 | 6.6KV HT VFD with Motors-->ITP APPROVAL-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-29 09:00 | 2020-04-08 18:00 | 2020-08-01 09:00 | 2020-09-09 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4109 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019205
1726 | Task(Task)-->P (Procurement) | 415V LT VFD |  | 1.13.2.4 | 415V LT VFD-->ITP APPROVAL-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-18 09:00 | 2020-03-28 18:00 | 2020-09-14 09:00 | 2020-10-14 18:00 |  |  | 2020-09-02 17:03 |  |  |  | 100 | 0 | [15 empty] | 4.6214 | 0.00477 | 0.47 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4110 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019206
1727 | Task(Task)-->P (Procurement) | 6.6KV HT APFC PANEL |  | 1.13.2.4 | 6.6KV HT APFC PANEL-->ITP APPROVAL-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-11 09:00 | 2020-04-19 23:59 | 2020-08-01 09:00 | 2020-09-09 18:00 | [6 empty] | 100 | 0 | [15 empty] | 1.1799 | 0.001218 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4111 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019207
1728 | Task(Task)-->P (Procurement) | 6.6KV/0.433V LT TRANSFORMER |  | 1.13.2.4 | 6.6KV/0.433V LT TRANSFORMER-->ITP APPROVAL-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-16 09:00 | 2020-02-24 18:00 | 2020-08-05 09:00 | 2020-11-10 18:00 | [6 empty] | 100 | 0 | [15 empty] | 10.0295 | 0.010351 | 1.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4112 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019208
1729 | Task(Task)-->P (Procurement) | LT BUSDUCT |  | 1.13.2.4 | LT BUSDUCT-->ITP APPROVAL-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-05 09:00 | 2020-03-15 23:59 | 2020-09-21 09:00 | 2020-10-14 18:00 |  |  | 2020-09-21 17:35 |  |  |  | 100 | 0 | [15 empty] | 1.5733 | 0.001624 | 0.16 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4113 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019209
1730 | Task(Task)-->P (Procurement) | 415V MCC |  | 1.13.2.4 | 415V MCC-->ITP APPROVAL-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-26 09:00 | 2020-04-05 23:59 | 2020-08-01 09:00 | 2020-09-09 18:00 | [6 empty] | 100 | 0 | [15 empty] | 10.1278 | 0.010452 | 1.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4114 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019210
1731 | Task(Task)-->P (Procurement) | 110V DC BATTERY & BATTERY CHARGER SYSTEM |  | 1.13.2.4 | 110V DC BATTERY & BATTERY CHARGER SYSTEM-->ITP APPROVAL-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-25 09:00 | 2020-04-04 18:00 | 2020-07-07 09:00 | 2020-11-15 23:59 |  |  | 2020-07-07 10:31 |  |  |  | 100 | 0 | [15 empty] | 3.3432 | 0.00345 | 0.34 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4115 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019211
1732 | Task(Task)-->P (Procurement) | 6.6KV NEUTRAL GROUNDING RESISTOR |  | 1.13.2.4 | 6.6KV NEUTRAL GROUNDING RESISTOR-->ITP APPROVAL-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-21 09:00 | 2020-02-29 18:00 | 2020-06-05 09:00 | 2020-07-15 18:00 |  |  | 2020-06-05 08:53 | 2020-07-15 08:53 |  |  | 100 | 100 | [15 empty] | 0.29499 | 0.000304 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4116 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019212
1733 | Task(Task)-->P (Procurement) | PLC SYSTEM |  | 1.13.2.4 | PLC SYSTEM-->ITP APPROVAL-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-12-28 09:00 | 2020-02-05 18:00 | 2020-08-27 09:00 | 2020-10-22 18:00 |  |  | 2020-08-27 17:07 |  |  |  | 100 | 0 | [15 empty] | 7.9646 | 0.00822 | 0.81 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4117 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019213
1734 | Task(Task)-->P (Procurement) | UPS SYSTEM |  | 1.13.2.4 | UPS SYSTEM-->ITP APPROVAL-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-19 09:00 | 2020-03-29 23:59 | 2020-09-01 09:00 | 2020-09-25 18:00 | [6 empty] | 100 | 0 | [15 empty] | 1.4749 | 0.001522 | 0.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4118 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019214
1735 | Task(Task)-->P (Procurement) | 24V DC BATTERY AND BATTERY CHARGER SYSTEM |  | 1.13.2.4 | 24V DC BATTERY AND BATTERY CHARGER SYSTEM-->ITP APPROVAL-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-20 09:00 | 2020-03-30 18:00 | 2020-08-08 09:00 | 2020-11-30 18:00 |  |  | 2020-08-06 16:17 |  |  |  | 100 | 0 | [15 empty] | 0.6883 | 0.00071 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4119 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019215
1736 | Task(Task)-->P (Procurement) | FDA SYSTEM |  | 1.13.2.4 | FDA SYSTEM-->ITP APPROVAL-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-09 09:00 | 2020-05-18 18:00 | 2020-08-21 09:00 | 2020-11-30 18:00 | [6 empty] | 100 | 0 | [15 empty] | 4.8181 | 0.004973 | 0.49 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4120 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019216
1737 | Task(Task)-->P (Procurement) | SCADA |  | 1.13.2.4 | SCADA-->ITP APPROVAL-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-21 09:00 | 2020-03-31 18:00 | 2020-09-17 09:00 | 2020-11-15 23:59 | [6 empty] | 100 | 0 | [15 empty] | 2.2616 | 0.002334 | 0.23 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4121 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019217
1738 | Task(Task)-->P (Procurement) | RUBBER MATS |  | 1.13.2.4 | RUBBER MATS-->ITP APPROVAL-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-26 09:00 | 2020-08-04 18:00 | 2020-08-10 09:00 | 2020-08-10 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.098328 | 0.000101 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4124 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019218
1739 | Task(Task)-->P (Procurement) | MAIN LIGHTING DISTRIBUTION BOARD |  | 1.13.2.4 | MAIN LIGHTING DISTRIBUTION BOARD-->ITP APPROVAL-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-19 | 2020-05-28 18:00 | 2020-07-28 09:00 | 2020-10-14 18:00 |  |  | 2020-07-28 17:50 | 2020-10-14 15:09 |  |  | 100 | 100 | [15 empty] | 0.49164 | 0.000507 | 0.05 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4125 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019219
1740 | Task(Task)-->P (Procurement) | LIGHTING PANELS |  | 1.13.2.4 | LIGHTING PANELS-->ITP APPROVAL-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-26 09:00 | 2020-08-04 18:00 | 2020-07-28 09:00 | 2020-10-14 18:00 |  |  | 2020-07-28 17:39 |  |  |  | 100 | 0 | [15 empty] | 5.6047 | 0.005784 | 0.57 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4126 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019220
1741 | Task(Task)-->P (Procurement) | DCDB & DC FUSE BOARD |  | 1.13.2.4 | DCDB & DC FUSE BOARD-->ITP APPROVAL-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-19 | 2020-05-28 18:00 | 2020-07-28 09:00 | 2020-10-14 18:00 |  |  | 2020-07-28 14:24 | 2020-10-14 15:11 |  |  | 100 | 100 | [15 empty] | 2.0649 | 0.002131 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4127 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019221
1742 | Task(Task)-->P (Procurement) | UPS DB,ACDB,MCBDB & AFB |  | 1.13.2.4 | UPS DB,ACDB,MCBDB & AFB-->ITP APPROVAL-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-19 | 2020-05-28 18:00 | 2020-07-28 09:00 | 2020-10-14 18:00 |  |  | 2020-07-28 17:48 |  |  |  | 100 | 0 | [15 empty] | 2.0649 | 0.002131 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4128 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019222
1743 | Task(Task)-->P (Procurement) | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE | 1.13.2.5 | 1.13.2 | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-12-28 09:00 | 2020-08-09 23:59 | 2020-03-19 09:00 | 2020-11-30 18:00 |  |  | 2020-03-20 15:24 |  |  |  | 100 | 27.6518 | [15 empty] | 14.9995 | 0.30951 | 30.44 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4129 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019223
1744 | Task(Task)-->P (Procurement) | 33/6.9KV HT TRANSFORMER (ONAN TYPE) |  | 1.13.2.5 | 33/6.9KV HT TRANSFORMER (ONAN TYPE)-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-16 09:00 | 2020-03-15 23:59 | 2020-06-30 09:00 | 2020-09-22 18:00 |  |  | 2020-06-30 17:44 | 2020-09-22 12:23 |  |  | 100 | 100 | [15 empty] | 10.0164 | 0.031002 | 3.05 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4130 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019224
1745 | Task(Task)-->P (Procurement) | HT SWITCHGEAR (33KV & 6.6KV) |  | 1.13.2.5 | HT SWITCHGEAR (33KV & 6.6KV)-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-14 09:00 | 2020-03-28 18:00 | 2020-07-30 09:00 | 2020-10-31 18:00 |  |  | 2020-07-30 10:50 |  |  |  | 100 | 0 | [15 empty] | 31.3629 | 0.097072 | 9.55 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4131 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019225
1746 | Task(Task)-->P (Procurement) | 6.6KV HT VFD with Motors |  | 1.13.2.5 | 6.6KV HT VFD with Motors-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-29 09:00 | 2020-05-13 18:00 | 2020-08-08 09:00 | 2020-11-10 18:00 |  |  | 2020-07-28 11:51 | 2020-09-23 15:24 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4132 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019226
1747 | Task(Task)-->P (Procurement) | 415V LT VFD |  | 1.13.2.5 | 415V LT VFD-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-18 09:00 | 2020-05-02 18:00 | 2020-06-16 09:00 | 2020-09-23 18:00 |  |  | 2020-06-16 10:34 | 2020-09-22 17:02 |  |  | 100 | 100 | [15 empty] | 4.5977 | 0.01423 | 1.4 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4133 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019227
1748 | Task(Task)-->P (Procurement) | 6.6KV HT APFC PANEL |  | 1.13.2.5 | 6.6KV HT APFC PANEL-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-11 09:00 | 2020-04-24 18:00 | 2020-07-22 09:00 | 2020-11-10 18:00 |  |  | 2020-07-22 08:56 |  |  |  | 100 | 0 | [15 empty] | 1.1823 | 0.003659 | 0.36 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4134 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019228
1749 | Task(Task)-->P (Procurement) | 6.6KV/0.433V LT TRANSFORMER |  | 1.13.2.5 | 6.6KV/0.433V LT TRANSFORMER-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-16 09:00 | 2020-03-15 23:59 | 2020-07-20 09:00 | 2020-09-17 18:00 |  |  | 2020-07-20 09:00 | 2020-09-17 12:32 |  |  | 100 | 100 | [15 empty] | 10.0821 | 0.031205 | 3.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4135 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019229
1750 | Task(Task)-->P (Procurement) | LT BUSDUCT |  | 1.13.2.5 | LT BUSDUCT-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-05 09:00 | 2020-03-20 18:00 | 2020-06-12 09:00 | 2020-07-26 23:59 |  |  | 2020-09-16 17:36 |  |  |  | 100 | 0 | [15 empty] | 1.5435 | 0.004777 | 0.47 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4136 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019230
1751 | Task(Task)-->P (Procurement) | 415V MCC |  | 1.13.2.5 | 415V MCC-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-26 09:00 | 2020-05-10 23:59 | 2020-08-17 09:00 | 2020-11-10 18:00 |  |  | 2020-08-17 14:17 |  |  |  | 100 | 0 | [15 empty] | 10.1806 | 0.03151 | 3.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4137 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019231
1752 | Task(Task)-->P (Procurement) | 110V DC BATTERY & BATTERY CHARGER SYSTEM |  | 1.13.2.5 | 110V DC BATTERY & BATTERY CHARGER SYSTEM-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-25 09:00 | 2020-04-19 23:59 | 2020-07-07 09:00 | 2020-10-29 18:00 |  |  | 2020-07-07 10:31 |  |  |  | 100 | 0 | [15 empty] | 3.3169 | 0.010266 | 1.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4138 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019232
1753 | Task(Task)-->P (Procurement) | 6.6KV NEUTRAL GROUNDING RESISTOR |  | 1.13.2.5 | 6.6KV NEUTRAL GROUNDING RESISTOR-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-21 09:00 | 2020-03-05 18:00 | 2020-03-19 09:00 | 2020-06-04 18:00 |  |  | 2020-03-20 15:24 | 2020-06-04 15:24 |  |  | 100 | 100 | [15 empty] | 0.29557 | 0.000915 | 0.09 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4139 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019233
1754 | Task(Task)-->P (Procurement) | PLC SYSTEM |  | 1.13.2.5 | PLC SYSTEM-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-12-28 09:00 | 2020-03-11 18:00 | 2020-07-29 09:00 | 2020-11-16 18:00 |  |  | 2020-07-29 17:09 |  |  |  | 100 | 0 | [15 empty] | 7.9803 | 0.0247 | 2.43 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4140 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019234
1755 | Task(Task)-->P (Procurement) | UPS SYSTEM |  | 1.13.2.5 | UPS SYSTEM-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-19 09:00 | 2020-04-03 18:00 | 2020-08-01 09:00 | 2020-09-14 18:00 |  |  | 2020-08-31 12:21 |  |  |  | 100 | 0 | [15 empty] | 1.445 | 0.004472 | 0.44 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4141 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019235
1756 | Task(Task)-->P (Procurement) | 24V DC BATTERY AND BATTERY CHARGER SYSTEM |  | 1.13.2.5 | 24V DC BATTERY AND BATTERY CHARGER SYSTEM-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-20 09:00 | 2020-04-14 18:00 | 2020-08-06 09:00 | 2020-10-30 18:00 |  |  | 2020-08-06 16:16 |  |  |  | 100 | 0 | [15 empty] | 0.68966 | 0.002135 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4142 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019236
1757 | Task(Task)-->P (Procurement) | FDA SYSTEM |  | 1.13.2.5 | FDA SYSTEM-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-09 09:00 | 2020-06-22 18:00 | 2020-08-13 09:00 | 2020-11-30 18:00 | [6 empty] | 100 | 0 | [15 empty] | 4.7947 | 0.01484 | 1.46 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4143 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019237
1758 | Task(Task)-->P (Procurement) | SCADA |  | 1.13.2.5 | SCADA-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-21 09:00 | 2020-05-05 18:00 | 2020-08-15 09:00 | 2020-11-30 18:00 |  |  | 2020-07-06 17:05 |  |  |  | 100 | 0 | [15 empty] | 2.2332 | 0.006912 | 0.68 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4144 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019238
1759 | Task(Task)-->P (Procurement) | RUBBER MATS |  | 1.13.2.5 | RUBBER MATS-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2020-06-26 09:00 | 2020-07-16 18:00 | 2020-06-30 09:00 | 2020-07-23 18:00 |  |  | 2020-06-11 21:15 | 2020-07-03 21:15 |  |  | 100 | 100 | [15 empty] | 0.098522 | 0.000305 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4147 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019239
1760 | Task(Task)-->P (Procurement) | MAIN LIGHTING DISTRIBUTION BOARD |  | 1.13.2.5 | MAIN LIGHTING DISTRIBUTION BOARD-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-19 | 2020-06-02 18:00 | 2020-07-28 09:00 | 2020-11-10 18:00 |  |  | 2020-07-28 17:30 | 2020-10-31 10:06 |  |  | 100 | 100 | [15 empty] | 0.52545 | 0.001626 | 0.16 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4148 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019240
1761 | Task(Task)-->P (Procurement) | LIGHTING PANELS |  | 1.13.2.5 | LIGHTING PANELS-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-26 09:00 | 2020-08-09 23:59 | 2020-07-28 09:00 | 2020-11-10 18:00 |  |  | 2020-07-28 17:40 |  |  |  | 100 | 0 | [15 empty] | 5.5829 | 0.01728 | 1.7 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4149 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019241
1762 | Task(Task)-->P (Procurement) | DCDB & DC FUSE BOARD |  | 1.13.2.5 | DCDB & DC FUSE BOARD-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-19 | 2020-06-02 18:00 | 2020-07-28 09:00 | 2020-11-10 18:00 |  |  | 2020-07-28 14:22 |  |  |  | 100 | 0 | [15 empty] | 2.0361 | 0.006302 | 0.62 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4150 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019242
1763 | Task(Task)-->P (Procurement) | UPS DB,ACDB,MCBDB & AFB |  | 1.13.2.5 | UPS DB,ACDB,MCBDB & AFB-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-19 | 2020-06-02 18:00 | 2020-07-28 09:00 | 2020-11-10 18:00 |  |  | 2020-07-28 17:47 | 2020-09-28 17:47 |  |  | 100 | 100 | [15 empty] | 2.0361 | 0.006302 | 0.62 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4151 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019243
1764 | Task(Task)-->P (Procurement) | MANUFACTURING & RECEIPT AT SITE (MRN) | 1.13.2.6 | 1.13.2 | MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-06 09:00 | 2021-03-31 18:00 | 2020-07-16 09:00 | 2021-11-24 18:00 |  |  | 2020-09-18 12:33 |  |  |  | 72.8222 | 0 | [15 empty] | 59.998 | 1.2381 | 121.76 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4152 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019244
1765 | Task(Task)-->P (Procurement) | 33/6.9KV HT TRANSFORMER (ONAN TYPE) |  | 1.13.2.6 | 33/6.9KV HT TRANSFORMER (ONAN TYPE)-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-16 09:00 | 2021-03-22 18:00 | 2020-09-23 09:00 | 2021-09-29 18:00 |  |  | 2020-09-23 09:26 |  |  |  | 64.5161 | 0 | [15 empty] | 10.0074 | 0.1239 | 12.18 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4153 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019245
1766 | Task(Task)-->P (Procurement) | HT SWITCHGEAR (33KV & 6.6KV) |  | 1.13.2.6 | HT SWITCHGEAR (33KV & 6.6KV)-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-29 | 2021-03-22 18:00 | 2020-11-21 09:00 | 2021-11-14 23:59 | [6 empty] | 63.2312 | 0 | [15 empty] | 31.3696 | 0.38837 | 38.18 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4154 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019246
1767 | Task(Task)-->P (Procurement) | 6.6KV HT VFD with Motors |  | 1.13.2.6 | 6.6KV HT VFD with Motors-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-14 09:00 | 2021-03-09 18:00 | 2020-11-11 09:00 | 2021-09-06 18:00 | [6 empty] | 60.3333 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4155 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019247
1768 | Task(Task)-->P (Procurement) | 415V LT VFD |  | 1.13.2.6 | 415V LT VFD-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-03 | 2020-10-28 18:00 | 2020-10-15 09:00 | 2021-04-11 23:59 |  |  | 2020-09-23 09:02 |  |  |  | 100 | 0 | [15 empty] | 4.6093 | 0.057066 | 5.61 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4156 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019248
1769 | Task(Task)-->P (Procurement) | 6.6KV HT APFC PANEL |  | 1.13.2.6 | 6.6KV HT APFC PANEL-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-25 09:00 | 2020-11-04 18:00 | 2020-11-11 09:00 | 2021-05-23 23:59 | [6 empty] | 100 | 0 | [15 empty] | 1.1914 | 0.01475 | 1.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4157 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019249
1770 | Task(Task)-->P (Procurement) | 6.6KV/0.433V LT TRANSFORMER |  | 1.13.2.6 | 6.6KV/0.433V LT TRANSFORMER-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-16 09:00 | 2021-03-29 18:00 | 2020-11-11 09:00 | 2021-11-24 18:00 |  |  | 2020-09-18 12:33 |  |  |  | 63.3245 | 0 | [15 empty] | 10.0978 | 0.12501 | 12.29 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4158 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019250
1771 | Task(Task)-->P (Procurement) | LT BUSDUCT |  | 1.13.2.6 | LT BUSDUCT-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-21 09:00 | 2020-08-13 18:00 | 2020-10-15 09:00 | 2021-03-09 18:00 | [6 empty] | 100 | 0 | [15 empty] | 1.5364 | 0.019022 | 1.87 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4159 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019251
1772 | Task(Task)-->P (Procurement) | 415V MCC |  | 1.13.2.6 | 415V MCC-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-11 09:00 | 2021-03-31 18:00 | 2020-11-11 09:00 | 2021-10-01 18:00 | [6 empty] | 56.6154 | 0 | [15 empty] | 10.1964 | 0.12624 | 12.41 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4160 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019252
1773 | Task(Task)-->P (Procurement) | 110V DC BATTERY & BATTERY CHARGER SYSTEM |  | 1.13.2.6 | 110V DC BATTERY & BATTERY CHARGER SYSTEM-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-20 09:00 | 2020-11-03 18:00 | 2020-11-16 09:00 | 2021-06-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 3.3111 | 0.040994 | 4.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4161 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019253
1774 | Task(Task)-->P (Procurement) | 6.6KV NEUTRAL GROUNDING RESISTOR |  | 1.13.2.6 | 6.6KV NEUTRAL GROUNDING RESISTOR-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-06 09:00 | 2020-09-02 18:00 | 2020-07-16 09:00 | 2021-01-12 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.304 | 0.003764 | 0.37 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4162 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019254
1775 | Task(Task)-->P (Procurement) | PLC SYSTEM |  | 1.13.2.6 | PLC SYSTEM-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-12 09:00 | 2021-01-20 18:00 | 2020-11-17 09:00 | 2021-09-27 18:00 | [6 empty] | 77.4603 | 0 | [15 empty] | 7.9944 | 0.098975 | 9.73 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4163 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019255
1776 | Task(Task)-->P (Procurement) | UPS SYSTEM |  | 1.13.2.6 | UPS SYSTEM-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-04 09:00 | 2020-11-03 18:00 | 2020-09-26 09:00 | 2021-04-27 18:00 | [6 empty] | 100 | 0 | [15 empty] | 1.4378 | 0.017801 | 1.75 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4164 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019256
1777 | Task(Task)-->P (Procurement) | 24V DC BATTERY AND BATTERY CHARGER SYSTEM |  | 1.13.2.6 | 24V DC BATTERY AND BATTERY CHARGER SYSTEM-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-15 09:00 | 2020-10-18 23:59 | 2020-12-01 09:00 | 2021-06-05 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.69838 | 0.008646 | 0.85 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4165 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019257
1778 | Task(Task)-->P (Procurement) | FDA SYSTEM |  | 1.13.2.6 | FDA SYSTEM-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-23 09:00 | 2020-12-25 18:00 | 2020-12-01 09:00 | 2021-06-04 18:00 | [6 empty] | 75.8064 | 0 | [15 empty] | 4.7819 | 0.059202 | 5.82 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4166 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019258
1779 | Task(Task)-->P (Procurement) | SCADA |  | 1.13.2.6 | SCADA-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-06 09:00 | 2021-02-17 18:00 | 2020-12-01 09:00 | 2021-09-14 18:00 | [6 empty] | 65.625 | 0 | [15 empty] | 2.2184 | 0.027465 | 2.7 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4167 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019259
1780 | Task(Task)-->P (Procurement) | RUBBER MATS |  | 1.13.2.6 | RUBBER MATS-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-05 09:00 | 2021-01-16 18:00 | 2020-08-11 09:00 | 2021-01-22 18:00 | [6 empty] | 59.3939 | 0 | [15 empty] | 0.098595 | 0.001221 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4170 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019260
1781 | Task(Task)-->P (Procurement) | MAIN LIGHTING DISTRIBUTION BOARD |  | 1.13.2.6 | MAIN LIGHTING DISTRIBUTION BOARD-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-03 09:00 | 2020-09-16 18:00 | 2020-11-11 09:00 | 2021-02-24 18:00 |  |  | 2020-10-31 14:08 |  |  |  | 100 | 0 | [15 empty] | 0.50941 | 0.006307 | 0.62 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4171 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019261
1782 | Task(Task)-->P (Procurement) | LIGHTING PANELS |  | 1.13.2.6 | LIGHTING PANELS-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-10 09:00 | 2020-09-10 18:00 | 2020-11-11 09:00 | 2020-12-12 18:00 | [6 empty] | 100 | 0 | [15 empty] | 5.5788 | 0.069069 | 6.79 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4172 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019262
1783 | Task(Task)-->P (Procurement) | DCDB & DC FUSE BOARD |  | 1.13.2.6 | DCDB & DC FUSE BOARD-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-03 09:00 | 2020-08-10 18:00 | 2020-11-11 09:00 | 2021-01-18 18:00 | [6 empty] | 100 | 0 | [15 empty] | 2.0294 | 0.025125 | 2.47 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4173 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019263
1784 | Task(Task)-->P (Procurement) | UPS DB,ACDB,MCBDB & AFB |  | 1.13.2.6 | UPS DB,ACDB,MCBDB & AFB-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-03 09:00 | 2020-11-28 18:00 | 2020-11-11 09:00 | 2021-05-08 18:00 |  |  | 2020-09-29 09:00 |  |  |  | 89.9441 | 0 | [15 empty] | 2.0294 | 0.025125 | 2.47 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4174 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019264
1785 | Task(Task)-->C (Construction) | CONSTRUCTION | 1.13.3 | 1.13 | CONSTRUCTION-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-18 09:00 | 2021-08-21 18:00 | 2020-06-05 09:00 | 2022-04-13 18:00 |  |  | 2020-06-05 10:27 |  |  |  | 42.4019 | 0.66179 | [15 empty] | 38.8781 | 1.3673 | 134.46 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4175 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019265
1786 | Task(Task)-->C (Construction) | CIVIL | 1.13.3.1 | 1.13.3 | CIVIL-->CONSTRUCTION-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-18 09:00 | 2021-07-30 18:00 | 2020-06-05 09:00 | 2021-12-29 18:00 |  |  | 2020-06-05 10:27 |  |  |  | 50.6382 | 0.79034 | [15 empty] | 83.7349 | 1.1449 | 112.59 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4176 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019266
1787 | Task(Task)-->C (Construction) | AVAILABILITY OF FRONT BY NTPC |  | 1.13.3.1 | AVAILABILITY OF FRONT BY NTPC-->CIVIL-->CONSTRUCTION-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-18 09:00 | 2020-04-18 18:00 | 2020-06-05 09:00 | 2020-12-15 18:00 |  |  | 2020-06-05 10:27 |  |  |  | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4177 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019267
1788 | Task(Task)-->C (Construction) | EXCAVATION |  | 1.13.3.1 | EXCAVATION-->CIVIL-->CONSTRUCTION-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-25 09:00 | 2020-05-19 18:00 | 2020-06-05 09:00 | 2021-01-15 18:00 |  |  | 2020-06-05 10:28 |  |  |  | 100 | 41.2715 | [15 empty] | 1.7586 | 0.020134 | 1.98 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 7424 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4178 | 0 | 4 | Low | Niharendu Kamle,Santosh Anand | [6 empty] | 0 | 0 | [222 empty] | Excavation | [23 empty] | 1019268
1789 | Task(Task)-->C (Construction) | PCC |  | 1.13.3.1 | PCC-->CIVIL-->CONSTRUCTION-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-16 09:00 | 2020-06-09 18:00 | 2020-06-27 09:00 | 2021-01-22 18:00 |  |  | 2020-06-27 10:29 |  |  |  | 100 | 9.1954 | [15 empty] | 0.70166 | 0.008033 | 0.79 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 87 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4179 | 0 | 4 | Low | Niharendu Kamle,Santosh Anand | [6 empty] | 0 | 0 | [222 empty] | PCC | [23 empty] | 1019269
1790 | Task(Task)-->C (Construction) | RAFT |  | 1.13.3.1 | RAFT-->CIVIL-->CONSTRUCTION-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-23 09:00 | 2020-07-01 18:00 | 2020-10-22 09:00 | 2021-02-13 18:00 | [6 empty] | 100 | 0 | [15 empty] | 13.4293 | 0.15375 | 15.12 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 570 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4180 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019270
1791 | Task(Task)-->C (Construction) | PLINTH BEAM |  | 1.13.3.1 | PLINTH BEAM-->CIVIL-->CONSTRUCTION-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-17 09:00 | 2020-08-15 18:00 | 2020-11-16 09:00 | 2021-03-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 2.3537 | 0.026946 | 2.65 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4181 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019271
1792 | Task(Task)-->C (Construction) | PULL PIT & GRADE SLAB OF GROUND FLOOR |  | 1.13.3.1 | PULL PIT & GRADE SLAB OF GROUND FLOOR-->CIVIL-->CONSTRUCTION-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-17 09:00 | 2020-08-30 23:59 | 2020-12-16 09:00 | 2021-01-29 18:00 | [6 empty] | 100 | 0 | [15 empty] | 16.3158 | 0.18679 | 18.37 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 981 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5498 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019272
1793 | Task(Task)-->C (Construction) | RCC COLUMN & SLAB FOR 1ST FLOOR |  | 1.13.3.1 | RCC COLUMN & SLAB FOR 1ST FLOOR-->CIVIL-->CONSTRUCTION-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-16 | 2020-09-29 18:00 | 2021-01-15 09:00 | 2021-02-28 23:59 | [6 empty] | 100 | 0 | [15 empty] | 8.2512 | 0.094465 | 9.29 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5486 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019273
1794 | Task(Task)-->C (Construction) | RCC COLUMN & SLAB FOR 2ND (ROOF) FLOOR |  | 1.13.3.1 | RCC COLUMN & SLAB FOR 2ND (ROOF) FLOOR-->CIVIL-->CONSTRUCTION-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-10-07 09:00 | 2020-12-05 18:00 | 2021-03-08 09:00 | 2021-05-06 18:00 | [6 empty] | 58.3333 | 0 | [15 empty] | 8.2512 | 0.094465 | 9.29 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5487 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019274
1795 | Task(Task)-->C (Construction) | RCC COLUMN & SLAB OF MUMTY & FOUNDATION OF FAN/ AC ETC |  | 1.13.3.1 | RCC COLUMN & SLAB OF MUMTY & FOUNDATION OF FAN/ AC ETC-->CIVIL-->CONSTRUCTION-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-12-06 | 2021-01-04 18:00 | 2021-05-07 09:00 | 2021-06-05 18:00 | [6 empty] | 0 | 0 | [15 empty] | 1.1813 | 0.013524 | 1.33 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5504 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019275
1796 | Task(Task)-->C (Construction) | BRICK WORK OF GROUND FLOOR |  | 1.13.3.1 | BRICK WORK OF GROUND FLOOR-->CIVIL-->CONSTRUCTION-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-10-28 09:00 | 2020-12-16 18:00 | 2021-03-29 09:00 | 2021-05-17 18:00 | [6 empty] | 28 | 0 | [15 empty] | 4.2011 | 0.048097 | 4.73 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4185 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019276
1797 | Task(Task)-->C (Construction) | PLASTERING OF GROUND FLOOR (IN SIDE) & HANDING OVER FOR ELECTRICAL WORKS |  | 1.13.3.1 | PLASTERING OF GROUND FLOOR (IN SIDE) & HANDING OVER FOR ELECTRICAL WORKS-->CIVIL-->CONSTRUCTION-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-11-07 09:00 | 2020-12-26 18:00 | 2021-04-08 09:00 | 2021-05-27 18:00 | [6 empty] | 8 | 0 | [15 empty] | 1.652 | 0.018913 | 1.86 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 3358 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4186 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019277
1798 | Task(Task)-->C (Construction) | BRICK WORK OF 1ST FLOOR |  | 1.13.3.1 | BRICK WORK OF 1ST FLOOR-->CIVIL-->CONSTRUCTION-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-01-03 | 2021-03-03 18:00 | 2021-06-04 09:00 | 2021-08-02 18:00 | [6 empty] | 0 | 0 | [15 empty] | 4.2011 | 0.048097 | 4.73 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5490 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019278
1799 | Task(Task)-->C (Construction) | PLASTERING OF 1ST FLOOR (IN SIDE) |  | 1.13.3.1 | PLASTERING OF 1ST FLOOR (IN SIDE)-->CIVIL-->CONSTRUCTION-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-01-27 09:00 | 2021-03-17 18:00 | 2021-06-28 09:00 | 2021-08-16 18:00 | [6 empty] | 0 | 0 | [15 empty] | 1.652 | 0.018913 | 1.86 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 3358 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5489 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019279
1800 | Task(Task)-->C (Construction) | PAINTING OF CEILING OF ROOF SLAB (GRID 2 to 3) & HANDING OVER FOR ELECTRICAL WORKS |  | 1.13.3.1 | PAINTING OF CEILING OF ROOF SLAB (GRID 2 to 3) & HANDING OVER FOR ELECTRICAL WORKS-->CIVIL-->CONSTRUCTION-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-03-08 09:00 | 2021-03-27 18:00 | 2021-08-07 09:00 | 2021-08-26 18:00 | [6 empty] | 0 | 0 | [15 empty] | 1.501 | 0.017185 | 1.69 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 3358 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5492 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019280
1801 | Task(Task)-->C (Construction) | INSIDE PAINTING & FALSE CEILING (GRID 1 TO 2) & HANDING OVER FOR ELECTRICAL WORKS |  | 1.13.3.1 | INSIDE PAINTING & FALSE CEILING (GRID 1 TO 2) & HANDING OVER FOR ELECTRICAL WORKS-->CIVIL-->CONSTRUCTION-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-03-18 09:00 | 2021-04-16 18:00 | 2021-08-17 09:00 | 2021-09-15 18:00 | [6 empty] | 0 | 0 | [15 empty] | 14.0687 | 0.16107 | 15.84 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 3358 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5495 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019281
1802 | Task(Task)-->C (Construction) | TRANSFORMER FOUNDATION, TRENCH, BRICK WORK & PLASTERING ETC & HANDING OVER TO ELECTRICAL |  | 1.13.3.1 | TRANSFORMER FOUNDATION, TRENCH, BRICK WORK & PLASTERING ETC & HANDING OVER TO ELECTRICAL-->CIVIL-->CONSTRUCTION-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-16 | 2020-12-13 23:59 | 2021-03-02 09:00 | 2021-06-29 18:00 | [6 empty] | 72.5 | 0 | [15 empty] | 2.3537 | 0.026946 | 2.65 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5497 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019282
1803 | Task(Task)-->C (Construction) | BALANCE BRICK WORK |  | 1.13.3.1 | BALANCE BRICK WORK-->CIVIL-->CONSTRUCTION-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-03-18 09:00 | 2021-04-16 18:00 | 2021-08-17 09:00 | 2021-09-15 18:00 | [6 empty] | 0 | 0 | [15 empty] | 1.1902 | 0.013626 | 1.34 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5501 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019283
1804 | Task(Task)-->C (Construction) | OUTSIDE PLASTERING |  | 1.13.3.1 | OUTSIDE PLASTERING-->CIVIL-->CONSTRUCTION-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-04-17 09:00 | 2021-06-15 18:00 | 2021-09-16 09:00 | 2021-11-14 23:59 | [6 empty] | 0 | 0 | [15 empty] | 3.304 | 0.037827 | 3.72 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 6715 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5493 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019284
1805 | Task(Task)-->C (Construction) | DOOR , WINDOW, MONORAIL DOOR & ROLLING SHUTTER |  | 1.13.3.1 | DOOR , WINDOW, MONORAIL DOOR & ROLLING SHUTTER-->CIVIL-->CONSTRUCTION-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-05-17 09:00 | 2021-06-23 18:00 | 2021-10-16 09:00 | 2021-11-22 18:00 | [6 empty] | 0 | 0 | [15 empty] | 3.0465 | 0.034878 | 3.43 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4187 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019285
1806 | Task(Task)-->C (Construction) | BALANCE PAINTING |  | 1.13.3.1 | BALANCE PAINTING-->CIVIL-->CONSTRUCTION-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-06-16 09:00 | 2021-07-30 18:00 | 2021-11-15 09:00 | 2021-12-29 18:00 | [6 empty] | 0 | 0 | [15 empty] | 3.0109 | 0.034471 | 3.39 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 6715 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5496 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019286
1807 | Task(Task)-->C (Construction) | ROOF WATER PROFING & RWDC PIPE |  | 1.13.3.1 | ROOF WATER PROFING & RWDC PIPE-->CIVIL-->CONSTRUCTION-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-02-02 09:00 | 2021-03-04 18:00 | 2021-07-04 | 2021-08-03 18:00 | [6 empty] | 0 | 0 | [15 empty] | 5.5245 | 0.063248 | 6.22 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 1296 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4189 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019287
1808 | Task(Task)-->C (Construction) | GARLAND DRAIN & PLINTH PROTECTION |  | 1.13.3.1 | GARLAND DRAIN & PLINTH PROTECTION-->CIVIL-->CONSTRUCTION-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-06-16 09:00 | 2021-07-30 18:00 | 2021-11-15 09:00 | 2021-12-29 18:00 | [6 empty] | 0 | 0 | [15 empty] | 2.0517 | 0.023489 | 2.31 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4190 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019288
1809 | Task(Task)-->C (Construction) | ELECTRICAL & INSTRUMENTATION | 1.13.3.2 | 1.13.3 | ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-12-27 | 2021-08-06 18:00 | 2021-05-28 09:00 | 2022-02-01 18:00 | [6 empty] | 0 | 0 | [15 empty] | 11.3565 | 0.15527 | 15.27 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5252 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019289
1810 | Task(Task)-->C (Construction) | TRANSFORMERS |  | 1.13.3.2 | TRANSFORMERS-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-03-23 09:00 | 2021-04-12 18:00 | 2021-09-30 09:00 | 2021-10-20 18:00 | [6 empty] | 0 | 0 | [15 empty] | 15.1376 | 0.023504 | 2.31 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4194 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019290
1811 | Task(Task)-->C (Construction) | HT PANEL |  | 1.13.3.2 | HT PANEL-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-03-28 | 2021-04-16 18:00 | 2021-11-15 09:00 | 2021-12-04 18:00 | [6 empty] | 0 | 0 | [15 empty] | 8.0603 | 0.012515 | 1.23 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5253 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019291
1812 | Task(Task)-->C (Construction) | HT VFD |  | 1.13.3.2 | HT VFD-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-04-17 09:00 | 2021-04-17 18:00 | 2021-12-05 | 2021-12-05 23:59 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4195 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019292
1813 | Task(Task)-->C (Construction) | HT APFC |  | 1.13.3.2 | HT APFC-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-04-18 | 2021-04-18 23:59 | 2021-12-06 09:00 | 2021-12-06 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5335 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019293
1814 | Task(Task)-->C (Construction) | LT PANEL |  | 1.13.3.2 | LT PANEL-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-03-30 09:00 | 2021-04-23 18:00 | 2021-11-25 09:00 | 2021-12-19 23:59 | [6 empty] | 0 | 0 | [15 empty] | 2.2936 | 0.003561 | 0.35 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5336 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019294
1815 | Task(Task)-->C (Construction) | LT VFD |  | 1.13.3.2 | LT VFD-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-04-18 | 2021-04-21 18:00 | 2021-12-06 09:00 | 2021-12-09 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5337 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019295
1816 | Task(Task)-->C (Construction) | BATTERY, BATTERY CHARGER & UPS |  | 1.13.3.2 | BATTERY, BATTERY CHARGER & UPS-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-07-31 09:00 | 2021-08-06 18:00 | 2021-12-30 09:00 | 2022-01-05 18:00 | [6 empty] | 0 | 0 | [15 empty] | 1.0485 | 0.001628 | 0.16 | Plan & Actual | Quantity | Set | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5509 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019296
1817 | Task(Task)-->C (Construction) | PLC PANEL & SCADA |  | 1.13.3.2 | PLC PANEL & SCADA-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-04-17 09:00 | 2021-04-23 18:00 | 2021-09-28 09:00 | 2021-10-04 18:00 | [6 empty] | 0 | 0 | [15 empty] | 28.7025 | 0.044567 | 4.38 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5507 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019297
1818 | Task(Task)-->C (Construction) | CABLE TRAY |  | 1.13.3.2 | CABLE TRAY-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-12-27 | 2021-01-05 18:00 | 2021-05-28 09:00 | 2021-06-06 23:59 | [6 empty] | 0 | 0 | [15 empty] | 5.5701 | 0.008649 | 0.85 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5338 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019298
1819 | Task(Task)-->C (Construction) | POWER CABLE |  | 1.13.3.2 | POWER CABLE-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-04-24 09:00 | 2021-05-13 18:00 | 2021-12-20 09:00 | 2022-01-08 18:00 | [6 empty] | 0 | 0 | [15 empty] | 12.7785 | 0.019841 | 1.95 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 13795 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5339 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019299
1820 | Task(Task)-->C (Construction) | CONTROL CABLE |  | 1.13.3.2 | CONTROL CABLE-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-04-24 09:00 | 2021-04-29 18:00 | 2021-12-20 09:00 | 2021-12-25 18:00 | [6 empty] | 0 | 0 | [15 empty] | 11.1402 | 0.017298 | 1.7 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5340 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019300
1821 | Task(Task)-->C (Construction) | EARTHING |  | 1.13.3.2 | EARTHING-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-04-30 09:00 | 2021-05-13 18:00 | 2021-12-26 | 2022-01-08 18:00 | [6 empty] | 0 | 0 | [15 empty] | 2.0315 | 0.003154 | 0.31 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 1410 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5341 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019301
1822 | Task(Task)-->C (Construction) | EARTH PIT |  | 1.13.3.2 | EARTH PIT-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-07-24 09:00 | 2021-07-30 18:00 | 2021-12-23 09:00 | 2021-12-29 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5342 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019302
1823 | Task(Task)-->C (Construction) | LIGHTING |  | 1.13.3.2 | LIGHTING-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-03-18 09:00 | 2021-05-01 18:00 | 2021-08-17 09:00 | 2021-09-30 18:00 | [6 empty] | 0 | 0 | [15 empty] | 13.2372 | 0.020554 | 2.02 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 207 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5343 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019303
1824 | Task(Task)-->C (Construction) | NON-MOTOR TERMINATION |  | 1.13.3.2 | NON-MOTOR TERMINATION-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-05-14 09:00 | 2021-06-06 23:59 | 2022-01-09 | 2022-02-01 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 237 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5346 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019304
1825 | Task(Task)-->C (Construction) | TESTING & CHARGING FOR LOAD & TRIAL OPERATION | 1.13.3.3 | 1.13.3 | TESTING & CHARGING FOR LOAD & TRIAL OPERATION-->CONSTRUCTION-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-05-19 09:00 | 2021-08-21 18:00 | 2022-01-09 | 2022-04-13 18:00 | [6 empty] | 0 | 0 | [15 empty] | 4.9085 | 0.067112 | 6.6 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5347 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019305
1826 | Task(Task)-->C (Construction) | TRANSFORMERS (33KV/6.6KV) |  | 1.13.3.3 | TRANSFORMERS (33KV/6.6KV)-->TESTING & CHARGING FOR LOAD & TRIAL OPERATION-->CONSTRUCTION-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-06-08 09:00 | 2021-06-17 18:00 | 2022-01-29 09:00 | 2022-02-07 18:00 | [6 empty] | 0 | 0 | [15 empty] | 7.5758 | 0.005084 | 0.5 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5512 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019306
1827 | Task(Task)-->C (Construction) | TRANSFORMERS (6.6KV/415V) |  | 1.13.3.3 | TRANSFORMERS (6.6KV/415V)-->TESTING & CHARGING FOR LOAD & TRIAL OPERATION-->CONSTRUCTION-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-07-08 09:00 | 2021-07-27 18:00 | 2022-02-28 09:00 | 2022-03-19 18:00 | [6 empty] | 0 | 0 | [15 empty] | 15 | 0.010067 | 0.99 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5590 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019307
1828 | Task(Task)-->C (Construction) | 33KV SWITCH BOARD |  | 1.13.3.3 | 33KV SWITCH BOARD-->TESTING & CHARGING FOR LOAD & TRIAL OPERATION-->CONSTRUCTION-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-05-19 09:00 | 2021-06-07 18:00 | 2022-01-09 | 2022-01-28 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5348 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019308
1829 | Task(Task)-->C (Construction) | 6.6. KV SWITCH BOARD |  | 1.13.3.3 | 6.6. KV SWITCH BOARD-->TESTING & CHARGING FOR LOAD & TRIAL OPERATION-->CONSTRUCTION-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-06-18 09:00 | 2021-07-07 18:00 | 2022-02-08 09:00 | 2022-02-27 23:59 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5349 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019309
1830 | Task(Task)-->C (Construction) | PMCC-1A (LT SWITCH BOARD) |  | 1.13.3.3 | PMCC-1A (LT SWITCH BOARD)-->TESTING & CHARGING FOR LOAD & TRIAL OPERATION-->CONSTRUCTION-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-07-28 09:00 | 2021-08-16 18:00 | 2022-03-20 | 2022-04-08 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5350 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019310
1831 | Task(Task)-->C (Construction) | PMCC-1B (LT SWITCH BOARD) |  | 1.13.3.3 | PMCC-1B (LT SWITCH BOARD)-->TESTING & CHARGING FOR LOAD & TRIAL OPERATION-->CONSTRUCTION-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-08-02 09:00 | 2021-08-21 18:00 | 2022-03-25 09:00 | 2022-04-13 18:00 | [6 empty] | 0 | 0 | [15 empty] | 23.3333 | 0.015659 | 1.54 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5351 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019311
1832 | Task(Task)-->C (Construction) | BATTERY, BATTERY CHARGER & UPS |  | 1.13.3.3 | BATTERY, BATTERY CHARGER & UPS-->TESTING & CHARGING FOR LOAD & TRIAL OPERATION-->CONSTRUCTION-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-08-07 09:00 | 2021-08-13 18:00 | 2022-01-09 | 2022-01-15 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Set | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5510 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019312
1833 | Task(Task)-->C (Construction) | PLC SYSTEM |  | 1.13.3.3 | PLC SYSTEM-->TESTING & CHARGING FOR LOAD & TRIAL OPERATION-->CONSTRUCTION-->SUB STATION-1 & CHP CONTROL ROOM NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-08-14 09:00 | 2021-08-20 18:00 | 2022-01-16 | 2022-01-22 18:00 | [6 empty] | 0 | 0 | [15 empty] | 54.0909 | 0.036301 | 3.57 | Plan & Actual | Quantity | Set | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5511 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019313
1834 | Task(Task)-->E (Engineering) | SUB STATION-2 NEAR KDTP-2 | 1.14 | 1 | SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-11-12 09:00 | 2021-08-26 18:00 | 2019-11-02 09:00 | 2022-04-18 18:00 |  |  | 2019-11-02 10:57 |  |  |  | 68.5161 | 11.9775 | [15 empty] | 2.7123 | 2.7123 | 266.74 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4196 | 0 | 1 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019314
1835 | Task(Task)-->E (Engineering) | ENGINEERING | 1.14.1 | 1.14 | ENGINEERING-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-01-06 18:00 | 2020-07-21 17:40 | 2020-03-04 18:00 | 2020-11-15 23:59 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 84.976 | [15 empty] | 1.7733 | 0.048097 | 4.73 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4197 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019315
1836 | Task(Task)-->E (Engineering) | CIVIL | 1.14.1.1 | 1.14.1 | CIVIL-->ENGINEERING-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-03-23 18:00 | 2020-07-21 17:40 | 2020-04-30 18:00 | 2020-11-04 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 94.4031 | [15 empty] | 66.88 | 0.032167 | 4.18 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No | 4198 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036115
1837 | Task(Task)-->E (Engineering) | SUBSTATION-2 (SS-KDTP-2) : DESIGN CALCULATION |  | 1.14.1.1 | SUBSTATION-2 (SS-KDTP-2) : DESIGN CALCULATION-->CIVIL-->ENGINEERING-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-23 18:00 | 2020-05-22 17:40 | 2020-06-29 09:00 | 2020-07-15 18:00 |  |  | 2020-02-21 15:38 | 2020-07-15 14:58 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0026 |  | 2020-02-13 11:43 | 7012-155-PVC-U-090 |  |  |  | A |  |  |  | 47.7327 | 0.015354 | 2 | Plan & Actual | Date |  | 0 | 0 | 0 | 742.18 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4203 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-23 18:00 | 2020-04-30 18:00 |  | 10 |  |  |  | 2020-04-10 17:40 | 2020-05-25 18:00 |  | 30 |  |  |  | 2020-04-17 17:40 | 2020-05-28 18:00 |  | 35 |  |  |  | 2020-04-23 23:59 | 2020-06-04 18:00 |  | 65 | 2020-07-15 14:51 |  |  | 2020-04-30 17:40 | 2020-06-25 18:00 |  | 80 | 2020-07-15 14:55 | [5 empty] | 80 | 2020-07-15 14:57 | [5 empty] | 80 | 2020-07-15 14:57 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-22 17:40 | 2020-07-09 18:00 |  | 100 | 2020-07-15 14:59 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 191 |  |  |  |  | 101201
1838 | Task(Task)-->E (Engineering) | SUBSTATION-2 (SS-KDTP-2) : NUM & RC DETAILS (SHT 1) |  | 1.14.1.1 | SUBSTATION-2 (SS-KDTP-2) : NUM & RC DETAILS (SHT 1)-->CIVIL-->ENGINEERING-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-23 18:00 | 2020-05-22 17:40 | 2020-06-29 09:00 | 2020-07-13 18:00 |  |  | 2020-02-21 15:38 | 2020-07-13 23:05 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-NR-0037 |  | 2020-02-13 11:43 | 7012-155-PVC-C-091 |  |  |  | A |  |  |  | 15.9905 | 0.005144 | 0.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 247.26 | 0 | 4.15 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4199 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-23 18:00 | 2020-04-30 18:00 |  | 10 |  |  |  | 2020-04-10 17:40 | 2020-05-25 18:00 |  | 30 |  |  |  | 2020-04-17 17:40 | 2020-05-28 18:00 |  | 35 | 2020-06-25 20:06 |  |  | 2020-04-23 23:59 | 2020-06-04 18:00 |  | 65 | 2020-07-13 22:48 |  |  | 2020-04-30 17:40 | 2020-06-25 18:00 |  | 80 | 2020-07-13 22:59 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-22 17:40 | 2020-07-09 18:00 |  | 100 | 2020-07-13 23:06 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 192 |  |  |  |  | 101202
1839 | Task(Task)-->E (Engineering) | SUBSTATION-2 (SS-KDTP-2) : NUM & RC DETAILS (SHT 2) |  | 1.14.1.1 | SUBSTATION-2 (SS-KDTP-2) : NUM & RC DETAILS (SHT 2)-->CIVIL-->ENGINEERING-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-23 18:00 | 2020-05-22 17:40 | 2020-06-29 09:00 | 2020-07-13 18:00 |  |  | 2020-02-21 15:38 | 2020-07-13 23:06 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-NR-0038 |  | 2020-02-13 11:43 | 7012-155-PVC-C-092 |  |  |  | A |  |  |  | 15.9905 | 0.005144 | 0.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 247.26 | 0 | 2.35 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4200 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-23 18:00 | 2020-04-30 18:00 |  | 10 |  |  |  | 2020-04-10 17:40 | 2020-05-25 18:00 |  | 30 |  |  |  | 2020-04-17 17:40 | 2020-05-28 18:00 |  | 35 | 2020-06-26 11:25 |  |  | 2020-04-23 23:59 | 2020-06-04 18:00 |  | 65 | 2020-07-13 22:49 |  |  | 2020-04-30 17:40 | 2020-06-25 18:00 |  | 80 | 2020-07-13 23:00 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-22 17:40 | 2020-07-09 18:00 |  | 100 | 2020-07-13 23:07 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 193 |  |  |  |  | 101203
1840 | Task(Task)-->E (Engineering) | SUBSTATION-2 (SS-KDTP-2) : NUM & RC DETAILS (SHT 3) |  | 1.14.1.1 | SUBSTATION-2 (SS-KDTP-2) : NUM & RC DETAILS (SHT 3)-->CIVIL-->ENGINEERING-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-23 18:00 | 2020-05-22 17:40 | 2020-04-30 18:00 | 2020-11-04 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-NR-0039 |  | 2020-02-13 11:43 | 7012-155-PVC-C-093 |  |  |  | A |  |  |  | 15.9905 | 0.005144 | 0.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 247.26 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4201 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-23 18:00 | 2020-04-30 18:00 |  | 10 |  |  |  | 2020-04-10 17:40 | 2020-05-25 18:00 |  | 30 |  |  |  | 2020-04-17 17:40 | 2020-05-28 18:00 |  | 35 | 2020-09-30 12:05 |  |  | 2020-04-23 23:59 | 2020-06-04 18:00 |  | 65 | 2020-09-30 21:54 |  |  | 2020-04-30 17:40 | 2020-06-25 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-22 17:40 | 2020-07-09 18:00 |  | 100 | [122 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 194 |  |  |  |  | 101204
1841 | Task(Task)-->E (Engineering) | ARCHITECTURAL GA OF SUBSTATION-2 (SS-KDTP-2) |  | 1.14.1.1 | ARCHITECTURAL GA OF SUBSTATION-2 (SS-KDTP-2)-->CIVIL-->ENGINEERING-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-22 18:00 | 2020-07-21 17:40 | 2020-07-31 09:00 | 2020-08-31 18:00 |  |  | 2020-02-21 15:39 | 2020-09-01 00:08 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-AR-0012 |  | 2020-02-13 11:43 | 7012-155-PVC-C-118 |  |  |  | A |  |  |  | 4.2959 | 0.001382 | 0.18 | Plan & Actual | Date |  | 0 | 0 | 0 | 68.01 | 0 | 4.1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4202 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-05-22 18:00 | 2020-06-14 23:59 |  | 10 |  |  |  | 2020-06-09 17:40 | 2020-07-09 18:00 |  | 30 |  |  |  | 2020-06-16 17:40 | 2020-07-12 23:59 |  | 35 | 2020-07-31 22:57 |  |  | 2020-06-22 23:59 | 2020-07-19 23:59 |  | 65 | 2020-08-13 19:58 |  |  | 2020-06-29 17:40 | 2020-08-09 23:59 |  | 80 | 2020-09-01 00:04 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-07-21 17:40 | 2020-08-23 23:59 |  | 100 | 2020-09-01 00:09 | [121 empty] | Chetan Khodke | [5 empty] | A - Architecture | [16 empty] | 219 |  |  |  |  | 101229
1842 | Task(Task)-->E (Engineering) | ELECTRICAL | 1.14.1.2 | 1.14.1 | ELECTRICAL-->ENGINEERING-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-06 18:00 | 2020-04-23 17:40 | 2020-03-04 18:00 | 2020-11-15 23:59 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 65.94 | [15 empty] | 33.12 | 0.01593 | 2.07 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No | 4204 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036116
1843 | Task(Task)-->E (Engineering) | GA & CROSS SECTIONAL, FLOOR PLAN FOR 33 kV HT CICO PANEL FOR CHP |  | 1.14.1.2 | GA & CROSS SECTIONAL, FLOOR PLAN FOR 33 kV HT CICO PANEL FOR CHP-->ELECTRICAL-->ENGINEERING-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-29 18:00 | 2020-04-13 17:40 | 2020-05-21 18:00 | 2020-11-15 23:59 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-122 |  | 2020-02-13 11:45 | 7012-155-PVE-B-067 |  |  |  | A |  |  |  | 2.8986 | 0.000462 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4237 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-29 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-02 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-03-07 17:40 | 2020-06-03 18:00 |  | 35 |  |  |  | 2020-03-13 23:59 | 2020-06-03 18:00 |  | 65 | 2020-09-23 14:44 |  |  | 2020-03-20 17:40 | 2020-06-24 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-13 17:40 | 2020-06-24 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 302 |  |  |  |  | 101313
1844 | Task(Task)-->E (Engineering) | SINGLE LINE DIAGRAM FOR 33 kV HT CICO PANEL FOR CHP |  | 1.14.1.2 | SINGLE LINE DIAGRAM FOR 33 kV HT CICO PANEL FOR CHP-->ELECTRICAL-->ENGINEERING-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-26 18:00 | 2020-04-13 17:40 | 2020-05-21 18:00 | 2020-09-22 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-125 |  | 2020-02-13 11:45 | 7012-155-PVE-P-070 |  |  |  | A |  |  |  | 2.8986 | 0.000462 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4239 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-26 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-02 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-03-07 17:40 | 2020-06-06 18:00 |  | 35 |  |  |  | 2020-03-13 23:59 | 2020-06-06 18:00 |  | 65 | 2020-09-23 14:48 |  |  | 2020-03-20 17:40 | 2020-06-27 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-13 17:40 | 2020-06-27 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 305 |  |  |  |  | 101316
1845 | Task(Task)-->E (Engineering) | SCHEME DIAGRAM FOR CICO FEEDER WITH LINE PT AND WITH DIFFERENTIAL (OIL TYPE) (TYPE-DBF1) |  | 1.14.1.2 | SCHEME DIAGRAM FOR CICO FEEDER WITH LINE PT AND WITH DIFFERENTIAL (OIL TYPE) (TYPE-DBF1)-->ELECTRICAL-->ENGINEERING-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-27 18:00 | 2020-04-13 17:40 | 2020-05-21 18:00 | 2020-09-18 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-136 |  | 2020-02-13 11:45 | 7012-155-PVE-L-081 |  |  |  | A |  |  |  | 2.8986 | 0.000462 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4238 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-27 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-02 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-03-07 17:40 | 2020-06-05 18:00 |  | 35 |  |  |  | 2020-03-13 23:59 | 2020-06-05 18:00 |  | 65 | 2020-09-23 17:45 |  |  | 2020-03-20 17:40 | 2020-06-26 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-13 17:40 | 2020-06-26 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 316 |  |  |  |  | 101327
1846 | Task(Task)-->E (Engineering) | SUBSTATION-2 (SS-2) NEAR KDTP-2 EQUIPMENT, CABLE ROUTING,EARTHING & LIGHTNING LAYOUT WITH PLAN & SECTIONAL VIEW & BOM. |  | 1.14.1.2 | SUBSTATION-2 (SS-2) NEAR KDTP-2 EQUIPMENT, CABLE ROUTING,EARTHING & LIGHTNING LAYOUT WITH PLAN & SECTIONAL VIEW & BOM.-->ELECTRICAL-->ENGINEERING-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-06 18:00 | 2020-03-03 17:40 | 2020-03-04 18:00 | 2020-05-19 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5061 |  | 2020-02-13 11:44 | 7012-155-PVE-F-023 |  |  |  | A |  |  |  | 42.9952 | 0.006849 | 0.89 | Plan & Actual | Date |  | 0 | 0 | 0 | 331.35 | 0 | 51.18 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4205 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-06 18:00 | 2020-03-04 18:00 |  | 10 | 2020-03-04 23:31 |  |  | 2020-01-22 17:40 | 2020-04-01 18:00 |  | 30 | 2020-04-01 23:31 |  |  | 2020-01-28 17:40 | 2020-04-08 18:00 |  | 35 | 2020-04-08 23:31 |  |  | 2020-02-03 23:59 | 2020-04-15 18:00 |  | 65 | 2020-04-15 23:31 |  |  | 2020-02-10 17:40 | 2020-05-06 18:00 |  | 80 | 2020-04-28 23:31 | [5 empty] | 80 | 2020-07-07 14:38 | [5 empty] | 80 | 2020-07-07 14:38 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-03 17:40 | 2020-05-19 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 258 |  |  |  |  | 101269
1847 | Task(Task)-->E (Engineering) | LIGHTING LAYOUT PLAN WITH POWER DISTRIBUTION ARRANGEMENT, SECTIONAL VIEW, BOM OF SS-2 |  | 1.14.1.2 | LIGHTING LAYOUT PLAN WITH POWER DISTRIBUTION ARRANGEMENT, SECTIONAL VIEW, BOM OF SS-2-->ELECTRICAL-->ENGINEERING-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-10 18:00 | 2020-04-07 17:40 | 2020-05-22 09:00 | 2020-07-13 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5072 |  | 2020-02-13 11:44 | 7012-155-PVE-G-034 |  |  |  | A |  |  |  | 32.3671 | 0.005156 | 0.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 248.42 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4206 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-10 18:00 | 2020-06-01 18:00 |  | 10 | 2020-05-15 23:31 |  |  | 2020-02-26 17:40 | 2020-06-08 18:00 |  | 30 | 2020-05-20 23:31 |  |  | 2020-03-03 17:40 | 2020-06-15 18:00 |  | 35 | 2020-05-20 23:31 |  |  | 2020-03-09 23:59 | 2020-06-22 18:00 |  | 65 | 2020-05-22 23:31 |  |  | 2020-03-16 17:40 | 2020-07-13 18:00 |  | 80 | 2020-06-01 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-07 17:40 | 2020-07-13 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 269 |  |  |  |  | 101280
1848 | Task(Task)-->E (Engineering) | GA, SLD & BOM FOR 415V LT CHP PMCC-2 |  | 1.14.1.2 | GA, SLD & BOM FOR 415V LT CHP PMCC-2-->ELECTRICAL-->ENGINEERING-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-12 17:40 | 2020-04-23 17:40 | 2020-05-21 18:00 | 2020-09-22 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-156 |  | 2020-02-13 11:46 | 7012-155-PVE-W-101 |  |  |  | A |  |  |  | 15.942 | 0.00254 | 0.33 | Plan & Actual | Date |  | 0 | 0 | 0 | 124.21 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4236 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-14 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-12 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-03-19 17:40 | 2020-06-01 18:00 |  | 35 |  |  |  | 2020-03-25 23:59 | 2020-06-01 18:00 |  | 65 |  |  |  | 2020-04-01 17:40 | 2020-06-22 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-23 17:40 | 2020-06-22 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 336 |  |  |  |  | 101347
1849 | Task(Task)-->P (Procurement) | PROCUREMENT | 1.14.2 | 1.14 | PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-11-12 09:00 | 2021-03-31 18:00 | 2019-11-02 09:00 | 2021-11-24 18:00 |  |  | 2019-11-02 10:57 |  |  |  | 84.4532 | 19.263 | [15 empty] | 54.3563 | 1.4743 | 144.99 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4240 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019318
1850 | Task(Task)-->P (Procurement) | PURCHASE REQUISITION | 1.14.2.1 | 1.14.2 | PURCHASE REQUISITION-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-11-12 09:00 | 2020-06-25 18:00 | 2019-11-02 09:00 | 2020-04-18 18:00 |  |  | 2019-11-02 10:57 |  |  |  | 100 | 78.0225 | [15 empty] | 5.0003 | 0.073721 | 7.25 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4241 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019319
1851 | Task(Task)-->P (Procurement) | 33/6.9KV HT TRANSFORMER (ONAN TYPE) |  | 1.14.2.1 | 33/6.9KV HT TRANSFORMER (ONAN TYPE)-->PURCHASE REQUISITION-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-28 09:00 | 2019-11-28 18:00 | 2020-01-17 09:00 | 2020-01-17 18:00 |  |  | 2020-01-22 10:57 | 2020-01-22 10:57 |  |  | 100 | 100 | [15 empty] | 14.011 | 0.010329 | 1.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4242 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019320
1852 | Task(Task)-->P (Procurement) | HT SWITCHGEAR (33KV & 6.6KV) |  | 1.14.2.1 | HT SWITCHGEAR (33KV & 6.6KV)-->PURCHASE REQUISITION-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-13 09:00 | 2019-11-13 18:00 | 2019-11-02 09:00 | 2019-11-02 18:00 |  |  | 2019-11-02 10:57 | 2019-11-02 10:57 |  |  | 100 | 100 | [15 empty] | 18.544 | 0.013671 | 1.35 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4243 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019321
1853 | Task(Task)-->P (Procurement) | 6.6KV HT VFD with Motors |  | 1.14.2.1 | 6.6KV HT VFD with Motors-->PURCHASE REQUISITION-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-30 09:00 | 2019-12-30 18:00 | 2020-01-24 09:00 | 2020-01-24 18:00 |  |  | 2019-11-21 10:57 | 2019-11-21 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4244 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019322
1854 | Task(Task)-->P (Procurement) | 6.6KV HT APFC PANEL |  | 1.14.2.1 | 6.6KV HT APFC PANEL-->PURCHASE REQUISITION-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-24 09:00 | 2020-01-24 18:00 | 2020-02-13 09:00 | 2020-02-13 18:00 |  |  | 2020-02-13 10:57 | 2020-02-13 10:57 |  |  | 100 | 100 | [15 empty] | 1.6484 | 0.001215 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4245 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019323
1855 | Task(Task)-->P (Procurement) | 6.6KV/0.433V LT TRANSFORMER |  | 1.14.2.1 | 6.6KV/0.433V LT TRANSFORMER-->PURCHASE REQUISITION-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-25 09:00 | 2019-11-25 18:00 | 2020-01-22 09:00 | 2020-01-22 18:00 |  |  | 2020-01-22 15:37 | 2020-01-22 15:37 |  |  | 100 | 100 | [15 empty] | 7.0055 | 0.005165 | 0.51 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4246 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019324
1856 | Task(Task)-->P (Procurement) | LT BUSDUCT |  | 1.14.2.1 | LT BUSDUCT-->PURCHASE REQUISITION-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-02 09:00 | 2019-12-02 18:00 | 2019-12-11 09:00 | 2019-12-11 18:00 |  |  | 2019-12-11 15:44 | 2019-12-11 15:44 |  |  | 100 | 100 | [15 empty] | 2.1978 | 0.00162 | 0.16 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4247 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019325
1857 | Task(Task)-->P (Procurement) | 415V MCC |  | 1.14.2.1 | 415V MCC-->PURCHASE REQUISITION-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-11-28 09:00 | 2019-11-28 18:00 | 2019-11-14 09:00 | 2019-11-14 18:00 | [6 empty] | 100 | 0 | [15 empty] | 14.1484 | 0.01043 | 1.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4248 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019326
1858 | Task(Task)-->P (Procurement) | 110V DC BATTERY & BATTERY CHARGER SYSTEM |  | 1.14.2.1 | 110V DC BATTERY & BATTERY CHARGER SYSTEM-->PURCHASE REQUISITION-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-13 09:00 | 2020-01-13 18:00 | 2020-01-13 09:00 | 2020-01-13 18:00 |  |  | 2020-01-13 10:57 | 2020-01-13 10:57 |  |  | 100 | 100 | [15 empty] | 4.6703 | 0.003443 | 0.34 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4249 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019327
1859 | Task(Task)-->P (Procurement) | 6.6KV NEUTRAL GROUNDING RESISTOR |  | 1.14.2.1 | 6.6KV NEUTRAL GROUNDING RESISTOR-->PURCHASE REQUISITION-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-12 09:00 | 2019-12-12 18:00 | 2019-12-12 09:00 | 2019-12-12 18:00 |  |  | 2019-12-12 15:21 | 2019-12-12 15:21 |  |  | 100 | 100 | [15 empty] | 0.41209 | 0.000304 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4250 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019328
1860 | Task(Task)-->P (Procurement) | PLC SYSTEM |  | 1.14.2.1 | PLC SYSTEM-->PURCHASE REQUISITION-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-12 09:00 | 2019-11-12 18:00 | 2019-11-12 09:00 | 2019-11-12 18:00 |  |  | 2019-11-12 10:57 | 2019-11-12 10:57 |  |  | 100 | 100 | [15 empty] | 10.0275 | 0.007392 | 0.73 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4251 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019329
1861 | Task(Task)-->P (Procurement) | UPS SYSTEM |  | 1.14.2.1 | UPS SYSTEM-->PURCHASE REQUISITION-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-08 09:00 | 2020-01-08 18:00 | 2020-02-19 09:00 | 2020-02-19 18:00 |  |  | 2020-02-19 10:57 | 2020-02-19 10:57 |  |  | 100 | 100 | [15 empty] | 2.0604 | 0.001519 | 0.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4252 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019330
1862 | Task(Task)-->P (Procurement) | 24V DC BATTERY AND BATTERY CHARGER SYSTEM |  | 1.14.2.1 | 24V DC BATTERY AND BATTERY CHARGER SYSTEM-->PURCHASE REQUISITION-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-27 09:00 | 2020-01-27 18:00 | 2020-02-26 09:00 | 2020-02-26 18:00 |  |  | 2020-02-26 10:57 | 2020-02-26 10:57 |  |  | 100 | 100 | [15 empty] | 0.96154 | 0.000709 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4253 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019331
1863 | Task(Task)-->P (Procurement) | FDA SYSTEM |  | 1.14.2.1 | FDA SYSTEM-->PURCHASE REQUISITION-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-14 09:00 | 2020-02-14 18:00 | 2020-02-17 09:00 | 2020-02-17 18:00 |  |  | 2020-02-17 10:57 | 2020-02-17 10:57 |  |  | 100 | 100 | [15 empty] | 6.7308 | 0.004962 | 0.49 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4254 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019332
1864 | Task(Task)-->P (Procurement) | SCADA |  | 1.14.2.1 | SCADA-->PURCHASE REQUISITION-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-10 09:00 | 2019-12-10 18:00 | 2019-12-21 09:00 | 2019-12-21 18:00 |  |  | 2019-12-21 10:57 | 2019-12-21 10:57 |  |  | 100 | 100 | [15 empty] | 3.1593 | 0.002329 | 0.23 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4255 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019333
1865 | Task(Task)-->P (Procurement) | RUBBER MATS |  | 1.14.2.1 | RUBBER MATS-->PURCHASE REQUISITION-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-06-25 09:00 | 2020-06-25 18:00 | 2020-04-18 09:00 | 2020-04-18 18:00 |  |  | 2020-04-18 10:57 | 2020-04-18 10:57 |  |  | 100 | 100 | [15 empty] | 0.13736 | 0.000101 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4258 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019334
1866 | Task(Task)-->P (Procurement) | MAIN LIGHTING DISTRIBUTION BOARD |  | 1.14.2.1 | MAIN LIGHTING DISTRIBUTION BOARD-->PURCHASE REQUISITION-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-04 09:00 | 2020-02-04 18:00 | 2020-04-02 09:00 | 2020-04-02 18:00 |  |  | 2020-04-02 17:08 | 2020-04-02 17:08 |  |  | 100 | 100 | [15 empty] | 0.68681 | 0.000506 | 0.05 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4259 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019335
1867 | Task(Task)-->P (Procurement) | LIGHTING PANELS |  | 1.14.2.1 | LIGHTING PANELS-->PURCHASE REQUISITION-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-28 09:00 | 2020-02-28 18:00 | 2020-04-02 09:00 | 2020-04-02 18:00 | [6 empty] | 100 | 0 | [15 empty] | 7.8297 | 0.005772 | 0.57 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4260 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019336
1868 | Task(Task)-->P (Procurement) | DCDB & DC FUSE BOARD |  | 1.14.2.1 | DCDB & DC FUSE BOARD-->PURCHASE REQUISITION-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-28 09:00 | 2020-01-28 18:00 | 2020-04-02 09:00 | 2020-04-02 18:00 |  |  | 2020-04-02 16:53 | 2020-04-02 16:53 |  |  | 100 | 100 | [15 empty] | 2.8846 | 0.002127 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4261 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019337
1869 | Task(Task)-->P (Procurement) | UPS DB,ACDB,MCBDB & AFB |  | 1.14.2.1 | UPS DB,ACDB,MCBDB & AFB-->PURCHASE REQUISITION-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-18 09:00 | 2020-03-18 18:00 | 2020-04-02 09:00 | 2020-04-02 18:00 |  |  | 2020-04-02 17:02 | 2020-04-02 17:02 |  |  | 100 | 100 | [15 empty] | 2.8846 | 0.002127 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4262 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019338
1870 | Task(Task)-->P (Procurement) | TECHNICAL CLEARANCE | 1.14.2.2 | 1.14.2 | TECHNICAL CLEARANCE-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-11-13 09:00 | 2020-07-20 18:00 | 2019-11-02 09:00 | 2020-07-10 18:00 |  |  | 2019-11-04 14:47 |  |  |  | 100 | 77.0608 | [15 empty] | 5.0003 | 0.073721 | 7.25 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4263 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019339
1871 | Task(Task)-->P (Procurement) | 33/6.9KV HT TRANSFORMER (ONAN TYPE) |  | 1.14.2.2 | 33/6.9KV HT TRANSFORMER (ONAN TYPE)-->TECHNICAL CLEARANCE-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-29 09:00 | 2019-12-22 23:59 | 2020-01-17 09:00 | 2020-02-17 18:00 |  |  | 2020-03-16 10:57 | 2020-03-16 10:57 |  |  | 100 | 100 | [15 empty] | 14.011 | 0.010329 | 1.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4264 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019340
1872 | Task(Task)-->P (Procurement) | HT SWITCHGEAR (33KV & 6.6KV) |  | 1.14.2.2 | HT SWITCHGEAR (33KV & 6.6KV)-->TECHNICAL CLEARANCE-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-14 09:00 | 2019-12-13 18:00 | 2019-11-02 09:00 | 2020-03-10 18:00 |  |  | 2019-11-04 14:47 | 2020-03-10 14:47 |  |  | 100 | 100 | [15 empty] | 18.544 | 0.013671 | 1.35 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4265 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019341
1873 | Task(Task)-->P (Procurement) | 6.6KV HT VFD with Motors |  | 1.14.2.2 | 6.6KV HT VFD with Motors-->TECHNICAL CLEARANCE-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-31 09:00 | 2020-01-29 18:00 | 2020-01-24 09:00 | 2020-04-16 18:00 |  |  | 2020-02-26 10:57 | 2020-02-26 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4266 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019342
1874 | Task(Task)-->P (Procurement) | 6.6KV HT APFC PANEL |  | 1.14.2.2 | 6.6KV HT APFC PANEL-->TECHNICAL CLEARANCE-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-25 09:00 | 2020-02-16 23:59 | 2020-02-13 09:00 | 2020-04-28 18:00 |  |  | 2020-04-28 10:57 | 2020-04-28 10:57 |  |  | 100 | 100 | [15 empty] | 1.6484 | 0.001215 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4267 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019343
1875 | Task(Task)-->P (Procurement) | 6.6KV/0.433V LT TRANSFORMER |  | 1.14.2.2 | 6.6KV/0.433V LT TRANSFORMER-->TECHNICAL CLEARANCE-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-26 09:00 | 2019-12-20 18:00 | 2020-01-22 09:00 | 2020-03-16 18:00 |  |  | 2020-01-23 15:38 | 2020-03-16 15:38 |  |  | 100 | 100 | [15 empty] | 7.0055 | 0.005165 | 0.51 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4268 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019344
1876 | Task(Task)-->P (Procurement) | LT BUSDUCT |  | 1.14.2.2 | LT BUSDUCT-->TECHNICAL CLEARANCE-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-03 09:00 | 2020-01-03 18:00 | 2019-12-11 09:00 | 2020-03-10 18:00 |  |  | 2019-12-12 15:45 | 2020-03-10 15:45 |  |  | 100 | 100 | [15 empty] | 2.1978 | 0.00162 | 0.16 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4269 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019345
1877 | Task(Task)-->P (Procurement) | 415V MCC |  | 1.14.2.2 | 415V MCC-->TECHNICAL CLEARANCE-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-11-29 09:00 | 2020-01-11 18:00 | 2019-11-14 09:00 | 2020-03-11 18:00 | [6 empty] | 100 | 0 | [15 empty] | 14.1484 | 0.01043 | 1.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4270 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019346
1878 | Task(Task)-->P (Procurement) | 110V DC BATTERY & BATTERY CHARGER SYSTEM |  | 1.14.2.2 | 110V DC BATTERY & BATTERY CHARGER SYSTEM-->TECHNICAL CLEARANCE-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-14 09:00 | 2020-02-03 18:00 | 2020-01-13 09:00 | 2020-06-04 18:00 |  |  | 2020-01-14 17:10 | 2020-06-04 17:10 |  |  | 100 | 100 | [15 empty] | 4.6703 | 0.003443 | 0.34 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4271 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019347
1879 | Task(Task)-->P (Procurement) | 6.6KV NEUTRAL GROUNDING RESISTOR |  | 1.14.2.2 | 6.6KV NEUTRAL GROUNDING RESISTOR-->TECHNICAL CLEARANCE-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-13 09:00 | 2019-12-31 18:00 | 2019-12-12 09:00 | 2020-01-21 18:00 |  |  | 2019-12-13 15:23 | 2020-01-21 15:23 |  |  | 100 | 100 | [15 empty] | 0.41209 | 0.000304 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4272 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019348
1880 | Task(Task)-->P (Procurement) | PLC SYSTEM |  | 1.14.2.2 | PLC SYSTEM-->TECHNICAL CLEARANCE-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-13 09:00 | 2019-12-04 18:00 | 2019-11-12 09:00 | 2020-03-16 18:00 |  |  | 2020-03-16 10:57 | 2020-03-16 10:57 |  |  | 100 | 100 | [15 empty] | 10.0275 | 0.007392 | 0.73 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4273 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019349
1881 | Task(Task)-->P (Procurement) | UPS SYSTEM |  | 1.14.2.2 | UPS SYSTEM-->TECHNICAL CLEARANCE-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-09 09:00 | 2020-01-28 18:00 | 2020-02-19 09:00 | 2020-06-06 18:00 |  |  | 2020-06-06 10:57 | 2020-06-06 10:57 |  |  | 100 | 100 | [15 empty] | 2.0604 | 0.001519 | 0.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4274 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019350
1882 | Task(Task)-->P (Procurement) | 24V DC BATTERY AND BATTERY CHARGER SYSTEM |  | 1.14.2.2 | 24V DC BATTERY AND BATTERY CHARGER SYSTEM-->TECHNICAL CLEARANCE-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-28 09:00 | 2020-02-07 18:00 | 2020-02-26 09:00 | 2020-07-10 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.96154 | 0.000709 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4275 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019351
1883 | Task(Task)-->P (Procurement) | FDA SYSTEM |  | 1.14.2.2 | FDA SYSTEM-->TECHNICAL CLEARANCE-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-15 09:00 | 2020-03-12 18:00 | 2020-02-17 09:00 | 2020-06-10 18:00 |  |  | 2020-06-10 10:57 | 2020-06-10 10:57 |  |  | 100 | 100 | [15 empty] | 6.7308 | 0.004962 | 0.49 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4276 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019352
1884 | Task(Task)-->P (Procurement) | SCADA |  | 1.14.2.2 | SCADA-->TECHNICAL CLEARANCE-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-11 09:00 | 2020-01-15 18:00 | 2019-12-21 09:00 | 2020-03-16 18:00 |  |  | 2020-03-16 10:57 | 2020-03-16 10:57 |  |  | 100 | 100 | [15 empty] | 3.1593 | 0.002329 | 0.23 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4277 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019353
1885 | Task(Task)-->P (Procurement) | RUBBER MATS |  | 1.14.2.2 | RUBBER MATS-->TECHNICAL CLEARANCE-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-06-26 09:00 | 2020-07-20 18:00 | 2020-04-18 09:00 | 2020-04-20 18:00 |  |  | 2020-04-20 10:57 | 2020-04-20 10:57 |  |  | 100 | 100 | [15 empty] | 0.13736 | 0.000101 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4280 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019354
1886 | Task(Task)-->P (Procurement) | MAIN LIGHTING DISTRIBUTION BOARD |  | 1.14.2.2 | MAIN LIGHTING DISTRIBUTION BOARD-->TECHNICAL CLEARANCE-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-05 09:00 | 2020-04-02 18:00 | 2020-04-02 09:00 | 2020-07-01 18:00 |  |  | 2020-04-03 17:08 | 2020-07-01 17:08 |  |  | 100 | 100 | [15 empty] | 0.68681 | 0.000506 | 0.05 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4281 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019355
1887 | Task(Task)-->P (Procurement) | LIGHTING PANELS |  | 1.14.2.2 | LIGHTING PANELS-->TECHNICAL CLEARANCE-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-29 09:00 | 2020-05-11 18:00 | 2020-04-02 09:00 | 2020-07-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 7.8297 | 0.005772 | 0.57 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4282 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019356
1888 | Task(Task)-->P (Procurement) | DCDB & DC FUSE BOARD |  | 1.14.2.2 | DCDB & DC FUSE BOARD-->TECHNICAL CLEARANCE-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-29 09:00 | 2020-04-02 18:00 | 2020-04-02 09:00 | 2020-07-01 18:00 |  |  | 2020-04-03 16:59 | 2020-07-01 16:59 |  |  | 100 | 100 | [15 empty] | 2.8846 | 0.002127 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4283 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019357
1889 | Task(Task)-->P (Procurement) | UPS DB,ACDB,MCBDB & AFB |  | 1.14.2.2 | UPS DB,ACDB,MCBDB & AFB-->TECHNICAL CLEARANCE-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-19 09:00 | 2020-04-02 18:00 | 2020-04-02 09:00 | 2020-07-01 18:00 |  |  | 2020-04-03 17:03 | 2020-07-01 17:03 |  |  | 100 | 100 | [15 empty] | 2.8846 | 0.002127 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4284 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019358
1890 | Task(Task)-->P (Procurement) | ORDERING | 1.14.2.3 | 1.14.2 | ORDERING-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-12-05 09:00 | 2020-07-25 18:00 | 2020-01-21 09:00 | 2020-08-13 18:00 |  |  | 2020-01-04 08:00 |  |  |  | 100 | 68.232 | [15 empty] | 10.0007 | 0.14744 | 14.5 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4285 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019359
1891 | Task(Task)-->P (Procurement) | 33/6.9KV HT TRANSFORMER (ONAN TYPE) |  | 1.14.2.3 | 33/6.9KV HT TRANSFORMER (ONAN TYPE)-->ORDERING-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-23 09:00 | 2020-01-15 18:00 | 2020-02-17 09:00 | 2020-06-24 18:00 |  |  | 2020-07-16 22:28 | 2020-07-16 22:28 |  |  | 100 | 100 | [15 empty] | 14.0193 | 0.020671 | 2.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4286 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019360
1892 | Task(Task)-->P (Procurement) | HT SWITCHGEAR (33KV & 6.6KV) |  | 1.14.2.3 | HT SWITCHGEAR (33KV & 6.6KV)-->ORDERING-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-14 09:00 | 2020-01-13 18:00 | 2020-03-10 09:00 | 2020-07-18 18:00 |  |  | 2020-03-11 14:48 | 2020-07-04 14:48 |  |  | 100 | 100 | [15 empty] | 18.6464 | 0.027493 | 2.7 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4287 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019361
1893 | Task(Task)-->P (Procurement) | 6.6KV HT VFD with Motors |  | 1.14.2.3 | 6.6KV HT VFD with Motors-->ORDERING-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-30 09:00 | 2020-02-28 18:00 | 2020-04-16 09:00 | 2020-07-18 18:00 |  |  | 2020-04-29 10:57 | 2020-04-29 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4288 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019362
1894 | Task(Task)-->P (Procurement) | 6.6KV HT APFC PANEL |  | 1.14.2.3 | 6.6KV HT APFC PANEL-->ORDERING-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-17 09:00 | 2020-03-10 18:00 | 2020-04-28 09:00 | 2020-07-28 18:00 |  |  | 2020-05-04 15:17 | 2020-07-10 15:17 |  |  | 100 | 100 | [15 empty] | 1.6575 | 0.002444 | 0.24 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4289 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019363
1895 | Task(Task)-->P (Procurement) | 6.6KV/0.433V LT TRANSFORMER |  | 1.14.2.3 | 6.6KV/0.433V LT TRANSFORMER-->ORDERING-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-21 09:00 | 2020-01-15 18:00 | 2020-03-16 09:00 | 2020-06-23 18:00 |  |  | 2020-06-23 10:14 | 2020-06-23 10:14 |  |  | 100 | 100 | [15 empty] | 7.0442 | 0.010386 | 1.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4290 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019364
1896 | Task(Task)-->P (Procurement) | LT BUSDUCT |  | 1.14.2.3 | LT BUSDUCT-->ORDERING-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-04 09:00 | 2020-02-04 18:00 | 2020-03-10 09:00 | 2020-06-11 18:00 |  |  | 2020-01-04 08:00 | 2020-04-27 15:46 |  |  | 100 | 100 | [15 empty] | 2.1409 | 0.003157 | 0.31 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4291 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019365
1897 | Task(Task)-->P (Procurement) | 415V MCC |  | 1.14.2.3 | 415V MCC-->ORDERING-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-12 | 2020-02-25 18:00 | 2020-03-11 09:00 | 2020-07-04 18:00 | [6 empty] | 100 | 0 | [15 empty] | 14.2956 | 0.021078 | 2.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4292 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019366
1898 | Task(Task)-->P (Procurement) | 110V DC BATTERY & BATTERY CHARGER SYSTEM |  | 1.14.2.3 | 110V DC BATTERY & BATTERY CHARGER SYSTEM-->ORDERING-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-04 09:00 | 2020-02-24 18:00 | 2020-06-04 09:00 | 2020-07-18 18:00 |  |  | 2020-06-05 17:10 | 2020-07-06 17:10 |  |  | 100 | 100 | [15 empty] | 4.6271 | 0.006822 | 0.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4293 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019367
1899 | Task(Task)-->P (Procurement) | 6.6KV NEUTRAL GROUNDING RESISTOR |  | 1.14.2.3 | 6.6KV NEUTRAL GROUNDING RESISTOR-->ORDERING-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-01 09:00 | 2020-01-20 18:00 | 2020-01-21 09:00 | 2020-03-19 18:00 |  |  | 2020-03-19 10:20 | 2020-03-19 10:20 |  |  | 100 | 100 | [15 empty] | 0.41436 | 0.000611 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4294 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019368
1900 | Task(Task)-->P (Procurement) | PLC SYSTEM |  | 1.14.2.3 | PLC SYSTEM-->ORDERING-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-05 09:00 | 2019-12-27 18:00 | 2020-03-16 09:00 | 2020-07-07 18:00 |  |  | 2020-03-16 17:20 | 2020-06-04 17:20 |  |  | 100 | 100 | [15 empty] | 10.0829 | 0.014866 | 1.46 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4295 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019369
1901 | Task(Task)-->P (Procurement) | UPS SYSTEM |  | 1.14.2.3 | UPS SYSTEM-->ORDERING-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-29 09:00 | 2020-02-18 18:00 | 2020-06-06 09:00 | 2020-07-31 18:00 | [6 empty] | 100 | 0 | [15 empty] | 2.0028 | 0.002953 | 0.29 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4296 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019370
1902 | Task(Task)-->P (Procurement) | 24V DC BATTERY AND BATTERY CHARGER SYSTEM |  | 1.14.2.3 | 24V DC BATTERY AND BATTERY CHARGER SYSTEM-->ORDERING-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-08 09:00 | 2020-02-19 18:00 | 2020-07-10 09:00 | 2020-08-07 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.96685 | 0.001426 | 0.14 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4297 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019371
1903 | Task(Task)-->P (Procurement) | FDA SYSTEM |  | 1.14.2.3 | FDA SYSTEM-->ORDERING-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-13 09:00 | 2020-04-08 18:00 | 2020-06-10 09:00 | 2020-08-06 18:00 | [6 empty] | 100 | 0 | [15 empty] | 6.6989 | 0.009877 | 0.97 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4298 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019372
1904 | Task(Task)-->P (Procurement) | SCADA |  | 1.14.2.3 | SCADA-->ORDERING-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-16 09:00 | 2020-02-20 18:00 | 2020-03-16 09:00 | 2020-06-24 18:00 |  |  | 2020-06-24 10:20 | 2020-06-24 10:20 |  |  | 100 | 100 | [15 empty] | 3.1077 | 0.004582 | 0.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4299 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019373
1905 | Task(Task)-->P (Procurement) | RUBBER MATS |  | 1.14.2.3 | RUBBER MATS-->ORDERING-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-07-21 09:00 | 2020-07-25 18:00 | 2020-04-20 09:00 | 2020-06-06 18:00 |  |  | 2020-04-25 10:57 | 2020-04-25 10:57 |  |  | 100 | 100 | [15 empty] | 0.13812 | 0.000204 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4302 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019374
1906 | Task(Task)-->P (Procurement) | MAIN LIGHTING DISTRIBUTION BOARD |  | 1.14.2.3 | MAIN LIGHTING DISTRIBUTION BOARD-->ORDERING-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-03 09:00 | 2020-04-18 18:00 | 2020-07-01 09:00 | 2020-08-13 18:00 |  |  | 2020-07-02 17:08 | 2020-07-07 17:08 |  |  | 100 | 100 | [15 empty] | 0.69061 | 0.001018 | 0.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4303 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019375
1907 | Task(Task)-->P (Procurement) | LIGHTING PANELS |  | 1.14.2.3 | LIGHTING PANELS-->ORDERING-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-12 09:00 | 2020-06-25 18:00 | 2020-07-01 09:00 | 2020-08-13 18:00 | [6 empty] | 100 | 0 | [15 empty] | 7.8039 | 0.011506 | 1.13 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4304 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019376
1908 | Task(Task)-->P (Procurement) | DCDB & DC FUSE BOARD |  | 1.14.2.3 | DCDB & DC FUSE BOARD-->ORDERING-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-03 09:00 | 2020-04-18 18:00 | 2020-07-01 09:00 | 2020-08-13 18:00 |  |  | 2020-07-02 17:00 | 2020-07-07 17:00 |  |  | 100 | 100 | [15 empty] | 2.8315 | 0.004175 | 0.41 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4305 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019377
1909 | Task(Task)-->P (Procurement) | UPS DB,ACDB,MCBDB & AFB |  | 1.14.2.3 | UPS DB,ACDB,MCBDB & AFB-->ORDERING-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-03 09:00 | 2020-04-18 18:00 | 2020-07-01 09:00 | 2020-08-13 18:00 |  |  | 2020-07-02 17:05 | 2020-07-07 17:05 |  |  | 100 | 100 | [15 empty] | 2.8315 | 0.004175 | 0.41 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4306 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019378
1910 | Task(Task)-->P (Procurement) | ITP APPROVAL | 1.14.2.4 | 1.14.2 | ITP APPROVAL-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-12-28 09:00 | 2020-09-03 18:00 | 2020-06-05 09:00 | 2020-11-30 18:00 |  |  | 2020-06-05 08:52 |  |  |  | 100 | 17.9949 | [15 empty] | 5.0003 | 0.073721 | 7.25 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4307 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019379
1911 | Task(Task)-->P (Procurement) | 33/6.9KV HT TRANSFORMER (ONAN TYPE) |  | 1.14.2.4 | 33/6.9KV HT TRANSFORMER (ONAN TYPE)-->ITP APPROVAL-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-16 09:00 | 2020-02-24 18:00 | 2020-07-03 09:00 | 2020-07-15 18:00 |  |  | 2020-07-03 08:46 | 2020-07-15 08:46 |  |  | 100 | 100 | [15 empty] | 14.011 | 0.010329 | 1.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4308 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019380
1912 | Task(Task)-->P (Procurement) | HT SWITCHGEAR (33KV & 6.6KV) |  | 1.14.2.4 | HT SWITCHGEAR (33KV & 6.6KV)-->ITP APPROVAL-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-14 09:00 | 2020-02-22 18:00 | 2020-08-06 09:00 | 2020-11-20 18:00 |  |  | 2020-07-13 10:49 |  |  |  | 100 | 0 | [15 empty] | 18.544 | 0.013671 | 1.35 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4309 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019381
1913 | Task(Task)-->P (Procurement) | 6.6KV HT VFD with Motors |  | 1.14.2.4 | 6.6KV HT VFD with Motors-->ITP APPROVAL-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-29 09:00 | 2020-04-08 18:00 | 2020-08-01 09:00 | 2020-09-09 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4310 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019382
1914 | Task(Task)-->P (Procurement) | 6.6KV HT APFC PANEL |  | 1.14.2.4 | 6.6KV HT APFC PANEL-->ITP APPROVAL-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-11 09:00 | 2020-04-19 23:59 | 2020-08-01 09:00 | 2020-09-09 18:00 | [6 empty] | 100 | 0 | [15 empty] | 1.6484 | 0.001215 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4311 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019383
1915 | Task(Task)-->P (Procurement) | 6.6KV/0.433V LT TRANSFORMER |  | 1.14.2.4 | 6.6KV/0.433V LT TRANSFORMER-->ITP APPROVAL-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-16 09:00 | 2020-02-24 18:00 | 2020-08-05 09:00 | 2020-11-10 18:00 | [6 empty] | 100 | 0 | [15 empty] | 7.0055 | 0.005165 | 0.51 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4312 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019384
1916 | Task(Task)-->P (Procurement) | LT BUSDUCT |  | 1.14.2.4 | LT BUSDUCT-->ITP APPROVAL-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-05 09:00 | 2020-03-15 23:59 | 2020-09-21 09:00 | 2020-10-14 18:00 |  |  | 2020-09-21 17:35 |  |  |  | 100 | 0 | [15 empty] | 2.1978 | 0.00162 | 0.16 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4313 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019385
1917 | Task(Task)-->P (Procurement) | 415V MCC |  | 1.14.2.4 | 415V MCC-->ITP APPROVAL-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-26 09:00 | 2020-04-05 23:59 | 2020-08-01 09:00 | 2020-09-09 18:00 | [6 empty] | 100 | 0 | [15 empty] | 14.1484 | 0.01043 | 1.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4314 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019386
1918 | Task(Task)-->P (Procurement) | 110V DC BATTERY & BATTERY CHARGER SYSTEM |  | 1.14.2.4 | 110V DC BATTERY & BATTERY CHARGER SYSTEM-->ITP APPROVAL-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-25 09:00 | 2020-04-04 18:00 | 2020-07-07 09:00 | 2020-11-15 23:59 |  |  | 2020-07-07 10:31 |  |  |  | 100 | 0 | [15 empty] | 4.6703 | 0.003443 | 0.34 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4315 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019387
1919 | Task(Task)-->P (Procurement) | 6.6KV NEUTRAL GROUNDING RESISTOR |  | 1.14.2.4 | 6.6KV NEUTRAL GROUNDING RESISTOR-->ITP APPROVAL-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-21 09:00 | 2020-02-29 18:00 | 2020-06-05 09:00 | 2020-07-15 18:00 |  |  | 2020-06-05 08:52 | 2020-07-15 08:52 |  |  | 100 | 100 | [15 empty] | 0.41209 | 0.000304 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4316 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019388
1920 | Task(Task)-->P (Procurement) | PLC SYSTEM |  | 1.14.2.4 | PLC SYSTEM-->ITP APPROVAL-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-12-28 09:00 | 2020-02-05 18:00 | 2020-08-27 09:00 | 2020-10-22 18:00 |  |  | 2020-08-27 17:08 |  |  |  | 100 | 0 | [15 empty] | 10.0275 | 0.007392 | 0.73 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4317 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019389
1921 | Task(Task)-->P (Procurement) | UPS SYSTEM |  | 1.14.2.4 | UPS SYSTEM-->ITP APPROVAL-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-19 09:00 | 2020-03-29 23:59 | 2020-09-01 09:00 | 2020-09-25 18:00 | [6 empty] | 100 | 0 | [15 empty] | 2.0604 | 0.001519 | 0.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4318 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019390
1922 | Task(Task)-->P (Procurement) | 24V DC BATTERY AND BATTERY CHARGER SYSTEM |  | 1.14.2.4 | 24V DC BATTERY AND BATTERY CHARGER SYSTEM-->ITP APPROVAL-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-20 09:00 | 2020-03-30 18:00 | 2020-08-08 09:00 | 2020-11-30 18:00 |  |  | 2020-08-06 16:17 |  |  |  | 100 | 0 | [15 empty] | 0.96154 | 0.000709 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4319 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019391
1923 | Task(Task)-->P (Procurement) | FDA SYSTEM |  | 1.14.2.4 | FDA SYSTEM-->ITP APPROVAL-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-09 09:00 | 2020-05-18 18:00 | 2020-08-21 09:00 | 2020-11-30 18:00 | [6 empty] | 100 | 0 | [15 empty] | 6.7308 | 0.004962 | 0.49 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4320 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019392
1924 | Task(Task)-->P (Procurement) | SCADA |  | 1.14.2.4 | SCADA-->ITP APPROVAL-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-21 09:00 | 2020-03-31 18:00 | 2020-09-17 09:00 | 2020-11-15 23:59 | [6 empty] | 100 | 0 | [15 empty] | 3.1593 | 0.002329 | 0.23 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4321 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019393
1925 | Task(Task)-->P (Procurement) | RUBBER MATS |  | 1.14.2.4 | RUBBER MATS-->ITP APPROVAL-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-26 | 2020-09-03 18:00 | 2020-08-10 09:00 | 2020-08-10 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.13736 | 0.000101 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4324 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019394
1926 | Task(Task)-->P (Procurement) | MAIN LIGHTING DISTRIBUTION BOARD |  | 1.14.2.4 | MAIN LIGHTING DISTRIBUTION BOARD-->ITP APPROVAL-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-19 | 2020-05-28 18:00 | 2020-07-28 09:00 | 2020-10-14 18:00 |  |  | 2020-07-28 17:50 | 2020-10-14 15:09 |  |  | 100 | 100 | [15 empty] | 0.68681 | 0.000506 | 0.05 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4325 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019395
1927 | Task(Task)-->P (Procurement) | LIGHTING PANELS |  | 1.14.2.4 | LIGHTING PANELS-->ITP APPROVAL-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-26 09:00 | 2020-08-04 18:00 | 2020-07-28 09:00 | 2020-10-14 18:00 |  |  | 2020-07-28 17:39 |  |  |  | 100 | 0 | [15 empty] | 7.8297 | 0.005772 | 0.57 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4326 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019396
1928 | Task(Task)-->P (Procurement) | DCDB & DC FUSE BOARD |  | 1.14.2.4 | DCDB & DC FUSE BOARD-->ITP APPROVAL-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-19 | 2020-05-28 18:00 | 2020-07-28 09:00 | 2020-10-14 18:00 |  |  | 2020-07-28 14:24 | 2020-10-14 15:11 |  |  | 100 | 100 | [15 empty] | 2.8846 | 0.002127 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4327 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019397
1929 | Task(Task)-->P (Procurement) | UPS DB,ACDB,MCBDB & AFB |  | 1.14.2.4 | UPS DB,ACDB,MCBDB & AFB-->ITP APPROVAL-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-19 | 2020-05-28 18:00 | 2020-07-28 09:00 | 2020-10-14 18:00 |  |  | 2020-07-28 17:48 |  |  |  | 100 | 0 | [15 empty] | 2.8846 | 0.002127 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4328 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019398
1930 | Task(Task)-->P (Procurement) | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE | 1.14.2.5 | 1.14.2 | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-12-28 09:00 | 2020-08-15 18:00 | 2020-03-19 09:00 | 2020-11-30 18:00 |  |  | 2020-03-20 15:25 |  |  |  | 100 | 25.2301 | [15 empty] | 15.001 | 0.22116 | 21.75 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4329 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019399
1931 | Task(Task)-->P (Procurement) | 33/6.9KV HT TRANSFORMER (ONAN TYPE) |  | 1.14.2.5 | 33/6.9KV HT TRANSFORMER (ONAN TYPE)-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-16 09:00 | 2020-03-15 23:59 | 2020-06-30 09:00 | 2020-09-22 18:00 |  |  | 2020-06-30 08:48 | 2020-09-22 12:23 |  |  | 100 | 100 | [15 empty] | 14.0165 | 0.031 | 3.05 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4330 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019400
1932 | Task(Task)-->P (Procurement) | HT SWITCHGEAR (33KV & 6.6KV) |  | 1.14.2.5 | HT SWITCHGEAR (33KV & 6.6KV)-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-14 09:00 | 2020-03-28 18:00 | 2020-07-30 09:00 | 2020-10-31 18:00 |  |  | 2020-07-30 10:50 |  |  |  | 100 | 0 | [15 empty] | 18.5662 | 0.041062 | 4.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4331 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019401
1933 | Task(Task)-->P (Procurement) | 6.6KV HT VFD with Motors |  | 1.14.2.5 | 6.6KV HT VFD with Motors-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-29 09:00 | 2020-05-13 18:00 | 2020-08-08 09:00 | 2020-11-10 18:00 |  |  | 2020-07-28 11:51 | 2020-09-23 15:24 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4332 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019402
1934 | Task(Task)-->P (Procurement) | 6.6KV HT APFC PANEL |  | 1.14.2.5 | 6.6KV HT APFC PANEL-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-11 09:00 | 2020-04-24 18:00 | 2020-07-22 09:00 | 2020-11-10 18:00 |  |  | 2020-07-22 08:56 |  |  |  | 100 | 0 | [15 empty] | 1.6544 | 0.003659 | 0.36 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4333 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019403
1935 | Task(Task)-->P (Procurement) | 6.6KV/0.433V LT TRANSFORMER |  | 1.14.2.5 | 6.6KV/0.433V LT TRANSFORMER-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-16 09:00 | 2020-03-15 23:59 | 2020-07-20 09:00 | 2020-09-17 18:00 |  |  | 2020-07-20 09:00 | 2020-09-17 12:32 |  |  | 100 | 100 | [15 empty] | 7.0772 | 0.015652 | 1.54 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4334 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019404
1936 | Task(Task)-->P (Procurement) | LT BUSDUCT |  | 1.14.2.5 | LT BUSDUCT-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-05 09:00 | 2020-03-20 18:00 | 2020-06-12 09:00 | 2020-07-26 23:59 |  |  | 2020-09-16 17:36 |  |  |  | 100 | 0 | [15 empty] | 2.1599 | 0.004777 | 0.47 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4335 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019405
1937 | Task(Task)-->P (Procurement) | 415V MCC |  | 1.14.2.5 | 415V MCC-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-26 09:00 | 2020-05-10 23:59 | 2020-08-17 09:00 | 2020-11-10 18:00 |  |  | 2020-08-17 14:17 |  |  |  | 100 | 0 | [15 empty] | 14.2463 | 0.031508 | 3.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4336 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019406
1938 | Task(Task)-->P (Procurement) | 110V DC BATTERY & BATTERY CHARGER SYSTEM |  | 1.14.2.5 | 110V DC BATTERY & BATTERY CHARGER SYSTEM-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-25 09:00 | 2020-04-19 23:59 | 2020-07-07 09:00 | 2020-10-29 18:00 |  |  | 2020-07-07 10:31 |  |  |  | 100 | 0 | [15 empty] | 4.6415 | 0.010265 | 1.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4337 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019407
1939 | Task(Task)-->P (Procurement) | 6.6KV NEUTRAL GROUNDING RESISTOR |  | 1.14.2.5 | 6.6KV NEUTRAL GROUNDING RESISTOR-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-21 09:00 | 2020-03-05 18:00 | 2020-03-19 09:00 | 2020-06-04 18:00 |  |  | 2020-03-20 15:25 | 2020-06-04 15:25 |  |  | 100 | 100 | [15 empty] | 0.4136 | 0.000915 | 0.09 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4338 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019408
1940 | Task(Task)-->P (Procurement) | PLC SYSTEM |  | 1.14.2.5 | PLC SYSTEM-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-12-28 09:00 | 2020-03-11 18:00 | 2020-07-29 09:00 | 2020-11-16 18:00 |  |  | 2020-07-29 17:09 |  |  |  | 100 | 0 | [15 empty] | 10.0184 | 0.022157 | 2.18 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4339 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019409
1941 | Task(Task)-->P (Procurement) | UPS SYSTEM |  | 1.14.2.5 | UPS SYSTEM-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-19 09:00 | 2020-04-03 18:00 | 2020-08-01 09:00 | 2020-09-14 18:00 |  |  | 2020-08-31 12:21 |  |  |  | 100 | 0 | [15 empty] | 2.0221 | 0.004472 | 0.44 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4340 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019410
1942 | Task(Task)-->P (Procurement) | 24V DC BATTERY AND BATTERY CHARGER SYSTEM |  | 1.14.2.5 | 24V DC BATTERY AND BATTERY CHARGER SYSTEM-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-20 09:00 | 2020-04-14 18:00 | 2020-08-06 09:00 | 2020-10-30 18:00 |  |  | 2020-08-06 16:16 |  |  |  | 100 | 0 | [15 empty] | 0.96507 | 0.002134 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4341 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019411
1943 | Task(Task)-->P (Procurement) | FDA SYSTEM |  | 1.14.2.5 | FDA SYSTEM-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-09 09:00 | 2020-06-22 18:00 | 2020-08-13 09:00 | 2020-11-30 18:00 | [6 empty] | 100 | 0 | [15 empty] | 6.7096 | 0.014839 | 1.46 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4342 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019412
1944 | Task(Task)-->P (Procurement) | SCADA |  | 1.14.2.5 | SCADA-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-21 09:00 | 2020-05-05 18:00 | 2020-08-15 09:00 | 2020-11-30 18:00 |  |  | 2020-07-06 17:05 |  |  |  | 100 | 0 | [15 empty] | 3.125 | 0.006911 | 0.68 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4343 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019413
1945 | Task(Task)-->P (Procurement) | RUBBER MATS |  | 1.14.2.5 | RUBBER MATS-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-07-26 | 2020-08-15 18:00 | 2020-06-30 09:00 | 2020-07-23 18:00 |  |  | 2020-06-11 21:16 | 2020-07-03 21:16 |  |  | 100 | 100 | [15 empty] | 0.13787 | 0.000305 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4346 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019414
1946 | Task(Task)-->P (Procurement) | MAIN LIGHTING DISTRIBUTION BOARD |  | 1.14.2.5 | MAIN LIGHTING DISTRIBUTION BOARD-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-19 | 2020-06-02 18:00 | 2020-07-28 09:00 | 2020-11-10 18:00 |  |  | 2020-07-28 17:30 | 2020-10-31 10:07 |  |  | 100 | 100 | [15 empty] | 0.73529 | 0.001626 | 0.16 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4347 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019415
1947 | Task(Task)-->P (Procurement) | LIGHTING PANELS |  | 1.14.2.5 | LIGHTING PANELS-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-26 09:00 | 2020-08-09 23:59 | 2020-07-28 09:00 | 2020-11-10 18:00 |  |  | 2020-07-28 17:40 |  |  |  | 100 | 0 | [15 empty] | 7.8125 | 0.017278 | 1.7 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4348 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019416
1948 | Task(Task)-->P (Procurement) | DCDB & DC FUSE BOARD |  | 1.14.2.5 | DCDB & DC FUSE BOARD-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-19 | 2020-06-02 18:00 | 2020-07-28 09:00 | 2020-11-10 18:00 |  |  | 2020-07-28 14:23 |  |  |  | 100 | 0 | [15 empty] | 2.8493 | 0.006302 | 0.62 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4349 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019417
1949 | Task(Task)-->P (Procurement) | UPS DB,ACDB,MCBDB & AFB |  | 1.14.2.5 | UPS DB,ACDB,MCBDB & AFB-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-19 | 2020-06-02 18:00 | 2020-07-28 09:00 | 2020-11-10 18:00 |  |  | 2020-07-28 17:47 | 2020-09-28 17:47 |  |  | 100 | 100 | [15 empty] | 2.8493 | 0.006302 | 0.62 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4350 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019418
1950 | Task(Task)-->P (Procurement) | MANUFACTURING & RECEIPT AT SITE (MRN) | 1.14.2.6 | 1.14.2 | MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-06 09:00 | 2021-03-31 18:00 | 2020-07-16 09:00 | 2021-11-24 18:00 |  |  | 2020-09-18 12:33 |  |  |  | 74.0875 | 0 | [15 empty] | 59.9972 | 0.88455 | 86.99 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4351 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019419
1951 | Task(Task)-->P (Procurement) | 33/6.9KV HT TRANSFORMER (ONAN TYPE) |  | 1.14.2.6 | 33/6.9KV HT TRANSFORMER (ONAN TYPE)-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-16 09:00 | 2021-03-22 18:00 | 2020-09-23 09:00 | 2021-09-29 18:00 |  |  | 2020-09-23 09:25 |  |  |  | 64.5161 | 0 | [15 empty] | 14.0064 | 0.1239 | 12.18 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4352 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019420
1952 | Task(Task)-->P (Procurement) | HT SWITCHGEAR (33KV & 6.6KV) |  | 1.14.2.6 | HT SWITCHGEAR (33KV & 6.6KV)-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-29 | 2021-03-22 18:00 | 2020-11-21 09:00 | 2021-11-14 23:59 | [6 empty] | 63.2312 | 0 | [15 empty] | 18.6063 | 0.16458 | 16.18 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4353 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019421
1953 | Task(Task)-->P (Procurement) | 6.6KV HT VFD with Motors |  | 1.14.2.6 | 6.6KV HT VFD with Motors-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-14 09:00 | 2021-03-09 18:00 | 2020-11-11 09:00 | 2021-09-06 18:00 | [6 empty] | 60.3333 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4354 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019422
1954 | Task(Task)-->P (Procurement) | 6.6KV HT APFC PANEL |  | 1.14.2.6 | 6.6KV HT APFC PANEL-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-25 09:00 | 2020-11-04 18:00 | 2020-11-11 09:00 | 2021-05-23 23:59 | [6 empty] | 100 | 0 | [15 empty] | 1.6674 | 0.014749 | 1.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4355 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019423
1955 | Task(Task)-->P (Procurement) | 6.6KV/0.433V LT TRANSFORMER |  | 1.14.2.6 | 6.6KV/0.433V LT TRANSFORMER-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-16 09:00 | 2021-03-29 18:00 | 2020-11-11 09:00 | 2021-11-24 18:00 |  |  | 2020-09-18 12:33 |  |  |  | 63.3245 | 0 | [15 empty] | 7.0722 | 0.062558 | 6.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4356 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019424
1956 | Task(Task)-->P (Procurement) | LT BUSDUCT |  | 1.14.2.6 | LT BUSDUCT-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-21 09:00 | 2020-08-13 18:00 | 2020-10-15 09:00 | 2021-03-09 18:00 | [6 empty] | 100 | 0 | [15 empty] | 2.1504 | 0.019022 | 1.87 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4357 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019425
1957 | Task(Task)-->P (Procurement) | 415V MCC |  | 1.14.2.6 | 415V MCC-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-11 09:00 | 2021-03-31 18:00 | 2020-11-11 09:00 | 2021-10-01 18:00 | [6 empty] | 56.6154 | 0 | [15 empty] | 14.2709 | 0.12623 | 12.41 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4358 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019426
1958 | Task(Task)-->P (Procurement) | 110V DC BATTERY & BATTERY CHARGER SYSTEM |  | 1.14.2.6 | 110V DC BATTERY & BATTERY CHARGER SYSTEM-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-20 09:00 | 2020-11-03 18:00 | 2020-11-16 09:00 | 2021-06-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 4.6343 | 0.040993 | 4.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4359 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019427
1959 | Task(Task)-->P (Procurement) | 6.6KV NEUTRAL GROUNDING RESISTOR |  | 1.14.2.6 | 6.6KV NEUTRAL GROUNDING RESISTOR-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-06 09:00 | 2020-09-02 18:00 | 2020-07-16 09:00 | 2021-01-12 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.42548 | 0.003764 | 0.37 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4360 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019428
1960 | Task(Task)-->P (Procurement) | PLC SYSTEM |  | 1.14.2.6 | PLC SYSTEM-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-12 09:00 | 2021-01-20 18:00 | 2020-11-17 09:00 | 2021-09-27 18:00 | [6 empty] | 77.4603 | 0 | [15 empty] | 10.0391 | 0.088801 | 8.73 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4361 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019429
1961 | Task(Task)-->P (Procurement) | UPS SYSTEM |  | 1.14.2.6 | UPS SYSTEM-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-04 09:00 | 2020-11-03 18:00 | 2020-09-26 09:00 | 2021-04-27 18:00 | [6 empty] | 100 | 0 | [15 empty] | 2.0124 | 0.017801 | 1.75 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4362 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019430
1962 | Task(Task)-->P (Procurement) | 24V DC BATTERY AND BATTERY CHARGER SYSTEM |  | 1.14.2.6 | 24V DC BATTERY AND BATTERY CHARGER SYSTEM-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-15 09:00 | 2020-10-18 23:59 | 2020-12-01 09:00 | 2021-06-05 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.97746 | 0.008646 | 0.85 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4363 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019431
1963 | Task(Task)-->P (Procurement) | FDA SYSTEM |  | 1.14.2.6 | FDA SYSTEM-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-23 09:00 | 2020-12-25 18:00 | 2020-12-01 09:00 | 2021-06-04 18:00 | [6 empty] | 75.8064 | 0 | [15 empty] | 6.6927 | 0.059201 | 5.82 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4364 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019432
1964 | Task(Task)-->P (Procurement) | SCADA |  | 1.14.2.6 | SCADA-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-06 09:00 | 2021-02-17 18:00 | 2020-12-01 09:00 | 2021-09-14 18:00 | [6 empty] | 65.625 | 0 | [15 empty] | 3.1049 | 0.027464 | 2.7 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4365 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019433
1965 | Task(Task)-->P (Procurement) | RUBBER MATS |  | 1.14.2.6 | RUBBER MATS-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-09-04 09:00 | 2021-02-15 18:00 | 2020-08-11 09:00 | 2021-01-22 18:00 | [6 empty] | 41.2121 | 0 | [15 empty] | 0.13799 | 0.001221 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4368 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019434
1966 | Task(Task)-->P (Procurement) | MAIN LIGHTING DISTRIBUTION BOARD |  | 1.14.2.6 | MAIN LIGHTING DISTRIBUTION BOARD-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-03 09:00 | 2020-09-16 18:00 | 2020-11-11 09:00 | 2021-02-24 18:00 |  |  | 2020-10-31 14:08 |  |  |  | 100 | 0 | [15 empty] | 0.71297 | 0.006307 | 0.62 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4369 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019435
1967 | Task(Task)-->P (Procurement) | LIGHTING PANELS |  | 1.14.2.6 | LIGHTING PANELS-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-10 09:00 | 2020-09-10 18:00 | 2020-11-11 09:00 | 2020-12-12 18:00 | [6 empty] | 100 | 0 | [15 empty] | 7.8082 | 0.069068 | 6.79 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4370 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019436
1968 | Task(Task)-->P (Procurement) | DCDB & DC FUSE BOARD |  | 1.14.2.6 | DCDB & DC FUSE BOARD-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-03 09:00 | 2020-08-10 18:00 | 2020-11-11 09:00 | 2021-01-18 18:00 | [6 empty] | 100 | 0 | [15 empty] | 2.8404 | 0.025125 | 2.47 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4371 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019437
1969 | Task(Task)-->P (Procurement) | UPS DB,ACDB,MCBDB & AFB |  | 1.14.2.6 | UPS DB,ACDB,MCBDB & AFB-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-03 09:00 | 2020-11-28 18:00 | 2020-11-11 09:00 | 2021-05-08 18:00 |  |  | 2020-09-29 09:00 |  |  |  | 89.9441 | 0 | [15 empty] | 2.8404 | 0.025125 | 2.47 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4372 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019438
1970 | Task(Task)-->C (Construction) | CONSTRUCTION | 1.14.3 | 1.14 | CONSTRUCTION-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-07 09:00 | 2021-08-26 18:00 | 2020-08-01 09:00 | 2022-04-18 18:00 | [6 empty] | 47.4972 | 0 | [15 empty] | 43.8704 | 1.1899 | 117.02 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4373 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019439
1971 | Task(Task)-->C (Construction) | CIVIL | 1.14.3.1 | 1.14.3 | CIVIL-->CONSTRUCTION-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-07 09:00 | 2021-08-04 18:00 | 2020-08-01 09:00 | 2022-01-26 18:00 | [6 empty] | 52.1547 | 0 | [15 empty] | 91.0699 | 1.0837 | 106.57 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4374 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019440
1972 | Task(Task)-->C (Construction) | AVAILABILITY OF FRONT BY NTPC |  | 1.14.3.1 | AVAILABILITY OF FRONT BY NTPC-->CIVIL-->CONSTRUCTION-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-07 09:00 | 2020-05-07 18:00 | 2020-08-01 09:00 | 2020-08-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4375 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019441
1973 | Task(Task)-->C (Construction) | EXCAVATION |  | 1.14.3.1 | EXCAVATION-->CIVIL-->CONSTRUCTION-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-14 09:00 | 2020-06-02 18:00 | 2020-11-05 09:00 | 2021-01-28 18:00 | [6 empty] | 100 | 0 | [15 empty] | 1.6232 | 0.01759 | 1.73 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 6500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4376 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | Excavation | [23 empty] | 1019442
1974 | Task(Task)-->C (Construction) | PCC |  | 1.14.3.1 | PCC-->CIVIL-->CONSTRUCTION-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-21 09:00 | 2020-06-09 18:00 | 2020-11-12 09:00 | 2020-12-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.76938 | 0.008337 | 0.82 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 91 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4377 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | PCC | [23 empty] | 1019443
1975 | Task(Task)-->C (Construction) | RAFT |  | 1.14.3.1 | RAFT-->CIVIL-->CONSTRUCTION-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-28 09:00 | 2020-07-01 18:00 | 2020-11-19 09:00 | 2020-12-23 18:00 | [6 empty] | 100 | 0 | [15 empty] | 15.4813 | 0.16776 | 16.5 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 622 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4378 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019444
1976 | Task(Task)-->C (Construction) | PLINTH BEAM |  | 1.14.3.1 | PLINTH BEAM-->CIVIL-->CONSTRUCTION-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-22 09:00 | 2020-08-10 18:00 | 2020-12-14 09:00 | 2021-02-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 2.4864 | 0.026944 | 2.65 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4379 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019445
1977 | Task(Task)-->C (Construction) | PULL PIT & GRADE SLAB FOR GROUND FLOOR |  | 1.14.3.1 | PULL PIT & GRADE SLAB FOR GROUND FLOOR-->CIVIL-->CONSTRUCTION-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-22 09:00 | 2020-08-30 23:59 | 2021-01-13 09:00 | 2021-02-21 23:59 | [6 empty] | 100 | 0 | [15 empty] | 15.5282 | 0.16827 | 16.55 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 884 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5514 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019446
1978 | Task(Task)-->C (Construction) | COLUMN AND SLAB OF 1ST FLOOR |  | 1.14.3.1 | COLUMN AND SLAB OF 1ST FLOOR-->CIVIL-->CONSTRUCTION-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-21 09:00 | 2020-10-04 23:59 | 2021-02-12 09:00 | 2021-03-28 23:59 | [6 empty] | 100 | 0 | [15 empty] | 8.7165 | 0.094456 | 9.29 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5516 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019447
1979 | Task(Task)-->C (Construction) | COLUMN AND ROOF SLAB (2ND FLOOR) |  | 1.14.3.1 | COLUMN AND ROOF SLAB (2ND FLOOR)-->CIVIL-->CONSTRUCTION-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-10-12 09:00 | 2020-12-10 18:00 | 2021-04-05 09:00 | 2021-06-03 18:00 | [6 empty] | 50 | 0 | [15 empty] | 8.7165 | 0.094456 | 9.29 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4382 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019448
1980 | Task(Task)-->C (Construction) | RCC COLUMN & SLAB OF MUMTY & FOUNDATION OF FAN/ AC ETC |  | 1.14.3.1 | RCC COLUMN & SLAB OF MUMTY & FOUNDATION OF FAN/ AC ETC-->CIVIL-->CONSTRUCTION-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-12-11 09:00 | 2021-01-09 18:00 | 2021-06-04 09:00 | 2021-07-03 18:00 | [6 empty] | 0 | 0 | [15 empty] | 1.2479 | 0.013523 | 1.33 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5517 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019449
1981 | Task(Task)-->C (Construction) | BRICK WORK OF GROUND FLOOR |  | 1.14.3.1 | BRICK WORK OF GROUND FLOOR-->CIVIL-->CONSTRUCTION-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-11-02 09:00 | 2020-12-21 18:00 | 2021-04-26 09:00 | 2021-06-14 18:00 | [6 empty] | 18 | 0 | [15 empty] | 4.438 | 0.048092 | 4.73 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5518 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019450
1982 | Task(Task)-->C (Construction) | PLASTERING OF GROUND FLOOR (IN SIDE) & HANDING OVER FOR ELECTRICAL WORKS |  | 1.14.3.1 | PLASTERING OF GROUND FLOOR (IN SIDE) & HANDING OVER FOR ELECTRICAL WORKS-->CIVIL-->CONSTRUCTION-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-11-12 09:00 | 2020-12-31 18:00 | 2021-05-06 09:00 | 2021-06-24 18:00 | [6 empty] | 0 | 0 | [15 empty] | 1.9234 | 0.020843 | 2.05 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 3698 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5519 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019451
1983 | Task(Task)-->C (Construction) | BRICK WORK OF 1ST FLOOR |  | 1.14.3.1 | BRICK WORK OF 1ST FLOOR-->CIVIL-->CONSTRUCTION-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-01-08 09:00 | 2021-03-08 18:00 | 2021-07-02 09:00 | 2021-08-30 18:00 | [6 empty] | 0 | 0 | [15 empty] | 4.438 | 0.048092 | 4.73 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5520 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019452
1984 | Task(Task)-->C (Construction) | PLASTERING OF 1ST FLOOR (IN SIDE) |  | 1.14.3.1 | PLASTERING OF 1ST FLOOR (IN SIDE)-->CIVIL-->CONSTRUCTION-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-02-01 09:00 | 2021-03-22 18:00 | 2021-07-26 09:00 | 2021-09-13 18:00 | [6 empty] | 0 | 0 | [15 empty] | 1.9234 | 0.020843 | 2.05 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 3698 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5521 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019453
1985 | Task(Task)-->C (Construction) | PAINTING OF CEILING OF ROOF SLAB (GRID 2 to 3) & HANDING OVER FOR ELECTRICAL WORKS |  | 1.14.3.1 | PAINTING OF CEILING OF ROOF SLAB (GRID 2 to 3) & HANDING OVER FOR ELECTRICAL WORKS-->CIVIL-->CONSTRUCTION-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-03-13 09:00 | 2021-04-01 18:00 | 2021-09-04 09:00 | 2021-09-23 18:00 | [6 empty] | 0 | 0 | [15 empty] | 1.7546 | 0.019013 | 1.87 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 3698 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5522 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019454
1986 | Task(Task)-->C (Construction) | INSIDE PAINTING & FALSE CEILING (GRID 1 TO 2) & HANDING OVER FOR ELECTRICAL WORKS |  | 1.14.3.1 | INSIDE PAINTING & FALSE CEILING (GRID 1 TO 2) & HANDING OVER FOR ELECTRICAL WORKS-->CIVIL-->CONSTRUCTION-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-03-23 09:00 | 2021-04-21 18:00 | 2021-09-14 09:00 | 2021-10-13 18:00 | [6 empty] | 0 | 0 | [15 empty] | 6.5115 | 0.070562 | 6.94 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 3698 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5523 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019455
1987 | Task(Task)-->C (Construction) | TRANSFORMER FOUNDATION, TRENCH, BRICK WORK & PLASTERING ETC & HANDING OVER TO ELECTRICAL |  | 1.14.3.1 | TRANSFORMER FOUNDATION, TRENCH, BRICK WORK & PLASTERING ETC & HANDING OVER TO ELECTRICAL-->CIVIL-->CONSTRUCTION-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-11 09:00 | 2020-11-08 23:59 | 2021-02-02 09:00 | 2021-05-02 23:59 | [6 empty] | 100 | 0 | [15 empty] | 2.3926 | 0.025927 | 2.55 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5524 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019456
1988 | Task(Task)-->C (Construction) | BALANCE BRICK WORK |  | 1.14.3.1 | BALANCE BRICK WORK-->CIVIL-->CONSTRUCTION-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-03-23 09:00 | 2021-04-21 18:00 | 2021-09-14 09:00 | 2021-10-13 18:00 | [6 empty] | 0 | 0 | [15 empty] | 3.481 | 0.037721 | 3.71 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 235 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5525 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019457
1989 | Task(Task)-->C (Construction) | OUTSIDE PLASTERING |  | 1.14.3.1 | OUTSIDE PLASTERING-->CIVIL-->CONSTRUCTION-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-04-22 09:00 | 2021-06-20 23:59 | 2021-10-14 09:00 | 2021-12-12 23:59 | [6 empty] | 0 | 0 | [15 empty] | 3.8469 | 0.041687 | 4.1 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 7395 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5526 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019458
1990 | Task(Task)-->C (Construction) | DOOR , WINDOW, MONORAIL DOOR & ROLLING SHUTTER |  | 1.14.3.1 | DOOR , WINDOW, MONORAIL DOOR & ROLLING SHUTTER-->CIVIL-->CONSTRUCTION-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-05-22 09:00 | 2021-06-28 18:00 | 2021-11-13 09:00 | 2021-12-20 18:00 | [6 empty] | 0 | 0 | [15 empty] | 3.2182 | 0.034875 | 3.43 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5527 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019459
1991 | Task(Task)-->C (Construction) | BALANCE PAINTING |  | 1.14.3.1 | BALANCE PAINTING-->CIVIL-->CONSTRUCTION-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-06-21 09:00 | 2021-08-04 18:00 | 2021-12-13 09:00 | 2022-01-26 18:00 | [6 empty] | 0 | 0 | [15 empty] | 3.4997 | 0.037925 | 3.73 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 7395 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5528 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019460
1992 | Task(Task)-->C (Construction) | ROOF WATER PROFING & RWDC PIPE |  | 1.14.3.1 | ROOF WATER PROFING & RWDC PIPE-->CIVIL-->CONSTRUCTION-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-02-07 | 2021-03-09 18:00 | 2021-08-01 | 2021-08-31 18:00 | [6 empty] | 0 | 0 | [15 empty] | 5.836 | 0.063242 | 6.22 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 1296 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5529 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019461
1993 | Task(Task)-->C (Construction) | GARLAND DRAIN & PLINTH PROTECTION |  | 1.14.3.1 | GARLAND DRAIN & PLINTH PROTECTION-->CIVIL-->CONSTRUCTION-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-06-21 09:00 | 2021-08-04 18:00 | 2021-12-13 09:00 | 2022-01-26 18:00 | [6 empty] | 0 | 0 | [15 empty] | 2.1674 | 0.023487 | 2.31 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5530 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019462
1994 | Task(Task)-->C (Construction) | ELECTRICAL & INSTRUMENTATION | 1.14.3.2 | 1.14.3 | ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-01-01 09:00 | 2021-08-04 18:00 | 2021-06-25 09:00 | 2022-01-26 18:00 | [6 empty] | 0 | 0 | [15 empty] | 6.7681 | 0.080534 | 7.92 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5254 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019463
1995 | Task(Task)-->C (Construction) | TRANSFORMERS |  | 1.14.3.2 | TRANSFORMERS-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-03-23 09:00 | 2021-04-05 18:00 | 2021-09-30 09:00 | 2021-10-13 18:00 | [6 empty] | 0 | 0 | [15 empty] | 19.4444 | 0.015659 | 1.54 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4392 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019464
1996 | Task(Task)-->C (Construction) | HT PANEL |  | 1.14.3.2 | HT PANEL-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-04-02 09:00 | 2021-04-16 18:00 | 2021-11-15 09:00 | 2021-11-29 18:00 | [6 empty] | 0 | 0 | [15 empty] | 8.5859 | 0.006915 | 0.68 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5255 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019465
1997 | Task(Task)-->C (Construction) | HT VFD |  | 1.14.3.2 | HT VFD-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-04-22 09:00 | 2021-04-23 18:00 | 2021-11-30 09:00 | 2021-12-01 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4393 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019466
1998 | Task(Task)-->C (Construction) | HT APFC |  | 1.14.3.2 | HT APFC-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-04-24 09:00 | 2021-04-24 18:00 | 2021-12-02 09:00 | 2021-12-02 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5352 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019467
1999 | Task(Task)-->C (Construction) | LT PANEL |  | 1.14.3.2 | LT PANEL-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-04-02 09:00 | 2021-04-21 18:00 | 2021-11-25 09:00 | 2021-12-14 18:00 | [6 empty] | 0 | 0 | [15 empty] | 2.5253 | 0.002034 | 0.2 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5353 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019468
2000 | Task(Task)-->C (Construction) | BATTERY, BATTERY CHARGER & UPS |  | 1.14.3.2 | BATTERY, BATTERY CHARGER & UPS-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-01-01 09:00 | 2021-01-07 18:00 | 2021-06-25 09:00 | 2021-07-01 18:00 | [6 empty] | 0 | 0 | [15 empty] | 2.0202 | 0.001627 | 0.16 | Plan & Actual | Quantity | Set | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5552 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019469
2001 | Task(Task)-->C (Construction) | CABLE TRAY |  | 1.14.3.2 | CABLE TRAY-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-01-01 09:00 | 2021-01-10 23:59 | 2021-06-25 09:00 | 2021-07-04 23:59 | [6 empty] | 0 | 0 | [15 empty] | 8.0808 | 0.006508 | 0.64 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5354 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019470
2002 | Task(Task)-->C (Construction) | POWRE CABLE |  | 1.14.3.2 | POWRE CABLE-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-04-25 | 2021-05-09 23:59 | 2021-12-15 09:00 | 2021-12-29 18:00 | [6 empty] | 0 | 0 | [15 empty] | 15.5303 | 0.012507 | 1.23 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 8710 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5355 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019471
2003 | Task(Task)-->C (Construction) | CONTROL CABLE |  | 1.14.3.2 | CONTROL CABLE-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-05-05 09:00 | 2021-05-09 23:59 | 2021-12-25 09:00 | 2021-12-29 18:00 | [6 empty] | 0 | 0 | [15 empty] | 16.0354 | 0.012914 | 1.27 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 9000 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5356 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019472
2004 | Task(Task)-->C (Construction) | EARTHING |  | 1.14.3.2 | EARTHING-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-05-03 09:00 | 2021-05-09 23:59 | 2021-12-23 09:00 | 2021-12-29 18:00 | [6 empty] | 0 | 0 | [15 empty] | 3.9141 | 0.003152 | 0.31 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 1377 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5357 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019473
2005 | Task(Task)-->C (Construction) | EARTH PIT |  | 1.14.3.2 | EARTH PIT-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-07-22 09:00 | 2021-08-04 18:00 | 2022-01-13 09:00 | 2022-01-26 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5358 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019474
2006 | Task(Task)-->C (Construction) | LIGHTING |  | 1.14.3.2 | LIGHTING-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-04-02 09:00 | 2021-04-08 18:00 | 2021-09-24 09:00 | 2021-09-30 18:00 | [6 empty] | 0 | 0 | [15 empty] | 23.8636 | 0.019218 | 1.89 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 194 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5359 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019475
2007 | Task(Task)-->C (Construction) | NON-MOTOR TERMINATION |  | 1.14.3.2 | NON-MOTOR TERMINATION-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-05-10 09:00 | 2021-05-11 18:00 | 2021-12-30 09:00 | 2021-12-31 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 183 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5362 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019476
2008 | Task(Task)-->C (Construction) | TESTING & CHARGING FOR LOAD & TRIAL OPERATION | 1.14.3.3 | 1.14.3 | TESTING & CHARGING FOR LOAD & TRIAL OPERATION-->CONSTRUCTION-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-05-10 09:00 | 2021-08-26 18:00 | 2021-12-30 09:00 | 2022-04-18 18:00 | [6 empty] | 0 | 0 | [15 empty] | 2.162 | 0.025726 | 2.53 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5363 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019477
2009 | Task(Task)-->C (Construction) | TRANSFORMERS (33KV/6.6KV) |  | 1.14.3.3 | TRANSFORMERS (33KV/6.6KV)-->TESTING & CHARGING FOR LOAD & TRIAL OPERATION-->CONSTRUCTION-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-06-28 09:00 | 2021-07-07 18:00 | 2022-02-18 09:00 | 2022-02-27 23:59 | [6 empty] | 0 | 0 | [15 empty] | 19.685 | 0.005064 | 0.5 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5591 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019478
2010 | Task(Task)-->C (Construction) | TRANSFORMERS (6.6KV/415V) |  | 1.14.3.3 | TRANSFORMERS (6.6KV/415V)-->TESTING & CHARGING FOR LOAD & TRIAL OPERATION-->CONSTRUCTION-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-07-28 09:00 | 2021-08-06 18:00 | 2022-03-20 | 2022-03-29 18:00 | [6 empty] | 0 | 0 | [15 empty] | 19.685 | 0.005064 | 0.5 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5592 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019479
2011 | Task(Task)-->C (Construction) | 33KV SWBD |  | 1.14.3.3 | 33KV SWBD-->TESTING & CHARGING FOR LOAD & TRIAL OPERATION-->CONSTRUCTION-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-06-08 09:00 | 2021-06-27 23:59 | 2022-01-29 09:00 | 2022-02-17 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5364 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019480
2012 | Task(Task)-->C (Construction) | 6.6. KV SWBD |  | 1.14.3.3 | 6.6. KV SWBD-->TESTING & CHARGING FOR LOAD & TRIAL OPERATION-->CONSTRUCTION-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-07-08 09:00 | 2021-07-27 18:00 | 2022-02-28 09:00 | 2022-03-19 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5365 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019481
2013 | Task(Task)-->C (Construction) | PMCC-2 |  | 1.14.3.3 | PMCC-2-->TESTING & CHARGING FOR LOAD & TRIAL OPERATION-->CONSTRUCTION-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-08-07 09:00 | 2021-08-26 18:00 | 2022-03-30 09:00 | 2022-04-18 18:00 | [6 empty] | 0 | 0 | [15 empty] | 60.6299 | 0.015598 | 1.54 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5366 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019482
2014 | Task(Task)-->C (Construction) | BATTERY, BATTERY CHARGER & UPS |  | 1.14.3.3 | BATTERY, BATTERY CHARGER & UPS-->TESTING & CHARGING FOR LOAD & TRIAL OPERATION-->CONSTRUCTION-->SUB STATION-2 NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-05-10 09:00 | 2021-05-16 23:59 | 2021-12-30 09:00 | 2022-01-05 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Set | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5556 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019483
2015 | Task(Task)-->E (Engineering) | SUB STATION-3 NEAR KDTP-3 | 1.15 | 1 | SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-11-12 09:00 | 2021-08-29 23:59 | 2019-11-02 09:00 | 2022-03-19 18:00 |  |  | 2019-11-02 10:57 |  |  |  | 67.4962 | 13.7205 | [15 empty] | 2.7774 | 2.7774 | 273.14 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4394 | 0 | 1 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019484
2016 | Task(Task)-->E (Engineering) | ENGINEERING | 1.15.1 | 1.15 | ENGINEERING-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-01-31 18:00 | 2020-08-15 17:40 | 2020-04-02 18:00 | 2020-11-04 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 84.6406 | [15 empty] | 4.1299 | 0.1147 | 11.28 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4395 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019485
2017 | Task(Task)-->E (Engineering) | CIVIL | 1.15.1.1 | 1.15.1 | CIVIL-->ENGINEERING-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-04-17 18:00 | 2020-08-15 17:40 | 2020-05-13 18:00 | 2020-11-04 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 92.8987 | [15 empty] | 71.2329 | 0.081707 | 4.16 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No | 4396 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036117
2018 | Task(Task)-->E (Engineering) | SUBSTATION-3 (SS-KDTP-3) : DESIGN CALCULATION |  | 1.15.1.1 | SUBSTATION-3 (SS-KDTP-3) : DESIGN CALCULATION-->CIVIL-->ENGINEERING-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-17 18:00 | 2020-06-16 17:40 | 2020-07-10 09:00 | 2020-07-30 18:00 |  |  | 2020-02-21 15:38 | 2020-07-30 20:23 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0027 |  | 2020-02-13 11:43 | 7012-155-PVC-U-094 |  |  |  | A |  |  |  | 47.8261 | 0.039077 | 1.98 | Plan & Actual | Date |  | 0 | 0 | 0 | 737.42 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4401 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-17 18:00 | 2020-05-13 18:00 |  | 10 |  |  |  | 2020-05-05 17:40 | 2020-06-07 23:59 |  | 30 |  |  |  | 2020-05-12 17:40 | 2020-06-10 18:00 |  | 35 |  |  |  | 2020-05-18 23:59 | 2020-06-17 18:00 |  | 65 | 2020-07-30 19:29 |  |  | 2020-05-25 17:40 | 2020-07-08 18:00 |  | 80 | 2020-07-30 20:20 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-16 17:40 | 2020-07-22 18:00 |  | 100 | 2020-07-30 20:23 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 195 |  |  |  |  | 101205
2019 | Task(Task)-->E (Engineering) | SUBSTATION-3 (SS-KDTP-3) : NUM & RC DETAILS (SHT 1) |  | 1.15.1.1 | SUBSTATION-3 (SS-KDTP-3) : NUM & RC DETAILS (SHT 1)-->CIVIL-->ENGINEERING-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-17 18:00 | 2020-06-16 17:40 | 2020-07-10 09:00 | 2020-07-30 18:00 |  |  | 2020-02-21 15:38 | 2020-07-30 20:24 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-NR-0040 |  | 2020-02-13 11:43 | 7012-155-PVC-C-095 |  |  |  | A |  |  |  | 15.942 | 0.013026 | 0.66 | Plan & Actual | Date |  | 0 | 0 | 0 | 245.42 | 0 | 2.15 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4397 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-17 18:00 | 2020-05-13 18:00 |  | 10 |  |  |  | 2020-05-05 17:40 | 2020-06-07 23:59 |  | 30 |  |  |  | 2020-05-12 17:40 | 2020-06-10 18:00 |  | 35 | 2020-07-11 06:31 |  |  | 2020-05-18 23:59 | 2020-06-17 18:00 |  | 65 | 2020-07-30 19:30 |  |  | 2020-05-25 17:40 | 2020-07-08 18:00 |  | 80 | 2020-07-30 19:38 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-16 17:40 | 2020-07-22 18:00 |  | 100 | 2020-07-30 20:24 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 196 |  |  |  |  | 101206
2020 | Task(Task)-->E (Engineering) | SUBSTATION-3 (SS-KDTP-3) : NUM & RC DETAILS (SHT 2) |  | 1.15.1.1 | SUBSTATION-3 (SS-KDTP-3) : NUM & RC DETAILS (SHT 2)-->CIVIL-->ENGINEERING-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-17 18:00 | 2020-06-16 17:40 | 2020-07-10 09:00 | 2020-07-30 18:00 |  |  | 2020-02-21 15:38 | 2020-07-30 20:25 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-NR-0041 |  | 2020-02-13 11:43 | 7012-155-PVC-C-096 |  |  |  | A |  |  |  | 15.942 | 0.013026 | 0.66 | Plan & Actual | Date |  | 0 | 0 | 0 | 245.42 | 0 | 2.1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4398 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-17 18:00 | 2020-05-13 18:00 |  | 10 |  |  |  | 2020-05-05 17:40 | 2020-06-07 23:59 |  | 30 |  |  |  | 2020-05-12 17:40 | 2020-06-10 18:00 |  | 35 | 2020-07-10 13:29 |  |  | 2020-05-18 23:59 | 2020-06-17 18:00 |  | 65 | 2020-07-11 08:03 |  |  | 2020-05-25 17:40 | 2020-07-08 18:00 |  | 80 | 2020-07-30 19:34 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-16 17:40 | 2020-07-22 18:00 |  | 100 | 2020-07-11 08:03 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 197 |  |  |  |  | 101207
2021 | Task(Task)-->E (Engineering) | SUBSTATION-3 (SS-KDTP-3) : NUM & RC DETAILS (SHT 3) |  | 1.15.1.1 | SUBSTATION-3 (SS-KDTP-3) : NUM & RC DETAILS (SHT 3)-->CIVIL-->ENGINEERING-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-17 18:00 | 2020-06-16 17:40 | 2020-05-13 18:00 | 2020-11-04 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-NR-0042 |  | 2020-02-13 11:43 | 7012-155-PVC-C-097 |  |  |  | A |  |  |  | 15.942 | 0.013026 | 0.66 | Plan & Actual | Date |  | 0 | 0 | 0 | 245.42 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4399 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-17 18:00 | 2020-05-13 18:00 |  | 10 |  |  |  | 2020-05-05 17:40 | 2020-06-07 23:59 |  | 30 |  |  |  | 2020-05-12 17:40 | 2020-06-10 18:00 |  | 35 | 2020-09-30 12:07 |  |  | 2020-05-18 23:59 | 2020-06-17 18:00 |  | 65 | 2020-09-30 21:53 |  |  | 2020-05-25 17:40 | 2020-07-08 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-16 17:40 | 2020-07-22 18:00 |  | 100 | [122 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 198 |  |  |  |  | 101208
2022 | Task(Task)-->E (Engineering) | ARCHITECTURAL GA OF SUBSTATION-3 (SS-KDTP-3) |  | 1.15.1.1 | ARCHITECTURAL GA OF SUBSTATION-3 (SS-KDTP-3)-->CIVIL-->ENGINEERING-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-16 18:00 | 2020-08-15 17:40 | 2020-06-27 18:00 | 2020-10-01 18:00 |  |  | 2020-02-21 15:39 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-AR-0013 |  | 2020-02-13 11:43 | 7012-155-PVC-C-119 |  |  |  | A |  |  |  | 4.3478 | 0.003552 | 0.18 | Plan & Actual | Date |  | 0 | 0 | 0 | 68.01 | 0 | 74 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4400 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-06-16 18:00 | 2020-06-27 18:00 |  | 10 |  |  |  | 2020-07-04 17:40 | 2020-07-22 18:00 |  | 30 |  |  |  | 2020-07-10 17:40 | 2020-07-25 18:00 |  | 35 | 2020-09-14 13:24 |  |  | 2020-07-17 23:59 | 2020-08-01 18:00 |  | 65 | 2020-09-14 13:47 |  |  | 2020-07-23 17:40 | 2020-08-22 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-08-15 17:40 | 2020-09-05 18:00 |  | 100 | [122 empty] | Chetan Khodke | [5 empty] | A - Architecture | [16 empty] | 220 |  |  |  |  | 101230
2023 | Task(Task)-->E (Engineering) | ELECTRICAL | 1.15.1.2 | 1.15.1 | ELECTRICAL-->ENGINEERING-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-31 18:00 | 2020-04-23 17:40 | 2020-04-02 18:00 | 2020-09-22 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 64.192 | [15 empty] | 28.7671 | 0.032997 | 1.68 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No | 4402 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036118
2024 | Task(Task)-->E (Engineering) | SUBSTATION-3 (SS-3) NEAR KDTP-3 EQUIPMENT, CABLE ROUTING,EARTHING & LIGHTNING LAYOUT WITH PLAN & SECTIONAL VIEW & BOM. |  | 1.15.1.2 | SUBSTATION-3 (SS-3) NEAR KDTP-3 EQUIPMENT, CABLE ROUTING,EARTHING & LIGHTNING LAYOUT WITH PLAN & SECTIONAL VIEW & BOM.-->ELECTRICAL-->ENGINEERING-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-31 18:00 | 2020-03-27 17:40 | 2020-04-02 18:00 | 2020-05-22 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5062 |  | 2020-02-13 11:44 | 7012-155-PVE-F-024 |  |  |  | A |  |  |  | 40.1198 | 0.013238 | 0.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 248.42 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4403 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-31 18:00 | 2020-04-02 18:00 |  | 10 | 2020-04-02 23:31 |  |  | 2020-02-15 17:40 | 2020-04-16 18:00 |  | 30 | 2020-04-15 23:31 |  |  | 2020-02-21 17:40 | 2020-04-23 18:00 |  | 35 | 2020-04-21 23:31 |  |  | 2020-02-28 23:59 | 2020-04-30 18:00 |  | 65 | 2020-04-21 23:31 |  |  | 2020-03-05 17:40 | 2020-05-21 18:00 |  | 80 | 2020-05-01 23:31 | [5 empty] | 80 | 2020-08-27 18:50 | [5 empty] | 80 | 2020-08-27 18:50 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-27 17:40 | 2020-05-22 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 259 |  |  |  |  | 101270
2025 | Task(Task)-->E (Engineering) | LIGHTING LAYOUT PLAN WITH POWER DISTRIBUTION ARRANGEMENT, SECTIONAL VIEW, BOM OF SS-3 |  | 1.15.1.2 | LIGHTING LAYOUT PLAN WITH POWER DISTRIBUTION ARRANGEMENT, SECTIONAL VIEW, BOM OF SS-3-->ELECTRICAL-->ENGINEERING-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-24 18:00 | 2020-04-14 17:40 | 2020-05-30 09:00 | 2020-07-15 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5073 |  | 2020-02-13 11:44 | 7012-155-PVE-G-035 |  |  |  | A |  |  |  | 40.1198 | 0.013238 | 0.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 248.42 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4404 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-24 18:00 | 2020-06-03 18:00 |  | 10 | 2020-05-25 23:31 |  |  | 2020-03-03 17:40 | 2020-06-10 18:00 |  | 30 | 2020-05-25 23:31 |  |  | 2020-03-09 17:40 | 2020-06-17 18:00 |  | 35 | 2020-05-25 23:31 |  |  | 2020-03-16 23:59 | 2020-06-24 18:00 |  | 65 | 2020-05-30 23:31 |  |  | 2020-03-21 17:40 | 2020-07-15 18:00 |  | 80 | 2020-06-17 13:15 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-14 17:40 | 2020-07-15 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 270 |  |  |  |  | 101281
2026 | Task(Task)-->E (Engineering) | GA, SLD & BOM FOR 415V LT CHP PMCC-3 |  | 1.15.1.2 | GA, SLD & BOM FOR 415V LT CHP PMCC-3-->ELECTRICAL-->ENGINEERING-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-12 17:40 | 2020-04-23 17:40 | 2020-05-21 18:00 | 2020-09-22 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-157 |  | 2020-02-13 11:46 | 7012-155-PVE-W-102 |  |  |  | A |  |  |  | 19.7605 | 0.00652 | 0.33 | Plan & Actual | Date |  | 0 | 0 | 0 | 124.21 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4434 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-12 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-12 17:40 | 2020-05-28 18:00 |  | 30 |  |  |  | 2020-03-19 17:40 | 2020-06-03 18:00 |  | 35 |  |  |  | 2020-03-25 23:59 | 2020-06-03 18:00 |  | 65 |  |  |  | 2020-04-01 17:40 | 2020-06-24 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-23 17:40 | 2020-06-24 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 337 |  |  |  |  | 101348
2027 | Task(Task)-->P (Procurement) | PROCUREMENT | 1.15.2 | 1.15 | PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-11-12 09:00 | 2021-03-31 18:00 | 2019-11-02 09:00 | 2021-11-24 18:00 |  |  | 2019-11-02 10:57 |  |  |  | 84.4543 | 19.2616 | [15 empty] | 53.0846 | 1.4744 | 144.99 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4438 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019488
2028 | Task(Task)-->P (Procurement) | PURCHASE REQUISITION | 1.15.2.1 | 1.15.2 | PURCHASE REQUISITION-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-11-12 09:00 | 2020-06-25 18:00 | 2019-11-02 09:00 | 2020-04-18 18:00 |  |  | 2019-11-02 10:57 |  |  |  | 100 | 78.022 | [15 empty] | 5 | 0.073719 | 7.25 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4439 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019489
2029 | Task(Task)-->P (Procurement) | 33/6.9KV HT TRANSFORMER (ONAN TYPE) |  | 1.15.2.1 | 33/6.9KV HT TRANSFORMER (ONAN TYPE)-->PURCHASE REQUISITION-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-28 09:00 | 2019-11-28 18:00 | 2020-01-17 09:00 | 2020-01-17 18:00 |  |  | 2020-01-22 10:57 | 2020-01-22 10:57 |  |  | 100 | 100 | [15 empty] | 14.011 | 0.010329 | 1.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4440 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019490
2030 | Task(Task)-->P (Procurement) | HT SWITCHGEAR (33KV & 6.6KV) |  | 1.15.2.1 | HT SWITCHGEAR (33KV & 6.6KV)-->PURCHASE REQUISITION-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-13 09:00 | 2019-11-13 18:00 | 2019-11-02 09:00 | 2019-11-02 18:00 |  |  | 2019-11-02 10:57 | 2019-11-02 10:57 |  |  | 100 | 100 | [15 empty] | 18.544 | 0.01367 | 1.35 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4441 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019491
2031 | Task(Task)-->P (Procurement) | 6.6KV HT VFD with Motors |  | 1.15.2.1 | 6.6KV HT VFD with Motors-->PURCHASE REQUISITION-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-30 09:00 | 2019-12-30 18:00 | 2020-01-24 09:00 | 2020-01-24 18:00 |  |  | 2019-11-21 10:57 | 2019-11-21 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4442 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019492
2032 | Task(Task)-->P (Procurement) | 6.6KV HT APFC PANEL |  | 1.15.2.1 | 6.6KV HT APFC PANEL-->PURCHASE REQUISITION-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-24 09:00 | 2020-01-24 18:00 | 2020-02-13 09:00 | 2020-02-13 18:00 |  |  | 2020-02-13 10:57 | 2020-02-13 10:57 |  |  | 100 | 100 | [15 empty] | 1.6484 | 0.001215 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4443 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019493
2033 | Task(Task)-->P (Procurement) | 6.6KV/0.433V LT TRANSFORMER |  | 1.15.2.1 | 6.6KV/0.433V LT TRANSFORMER-->PURCHASE REQUISITION-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-25 09:00 | 2019-11-25 18:00 | 2020-01-22 09:00 | 2020-01-22 18:00 |  |  | 2020-01-22 15:37 | 2020-01-22 15:37 |  |  | 100 | 100 | [15 empty] | 7.0055 | 0.005164 | 0.51 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4444 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019494
2034 | Task(Task)-->P (Procurement) | LT BUSDUCT |  | 1.15.2.1 | LT BUSDUCT-->PURCHASE REQUISITION-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-02 09:00 | 2019-12-02 18:00 | 2019-12-11 09:00 | 2019-12-11 18:00 |  |  | 2019-12-11 15:44 | 2019-12-11 15:44 |  |  | 100 | 100 | [15 empty] | 2.1978 | 0.00162 | 0.16 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4445 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019495
2035 | Task(Task)-->P (Procurement) | 415V MCC |  | 1.15.2.1 | 415V MCC-->PURCHASE REQUISITION-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-11-28 09:00 | 2019-11-28 18:00 | 2019-11-14 09:00 | 2019-11-14 18:00 | [6 empty] | 100 | 0 | [15 empty] | 14.1484 | 0.01043 | 1.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4446 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019496
2036 | Task(Task)-->P (Procurement) | 110V DC BATTERY & BATTERY CHARGER SYSTEM |  | 1.15.2.1 | 110V DC BATTERY & BATTERY CHARGER SYSTEM-->PURCHASE REQUISITION-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-13 09:00 | 2020-01-13 18:00 | 2020-01-13 09:00 | 2020-01-13 18:00 |  |  | 2020-01-13 10:57 | 2020-01-13 10:57 |  |  | 100 | 100 | [15 empty] | 4.6703 | 0.003443 | 0.34 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4447 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019497
2037 | Task(Task)-->P (Procurement) | 6.6KV NEUTRAL GROUNDING RESISTOR |  | 1.15.2.1 | 6.6KV NEUTRAL GROUNDING RESISTOR-->PURCHASE REQUISITION-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-12 09:00 | 2019-12-12 18:00 | 2019-12-12 09:00 | 2019-12-12 18:00 |  |  | 2019-12-12 15:21 | 2019-12-12 15:22 |  |  | 100 | 100 | [15 empty] | 0.41209 | 0.000304 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4448 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019498
2038 | Task(Task)-->P (Procurement) | PLC SYSTEM |  | 1.15.2.1 | PLC SYSTEM-->PURCHASE REQUISITION-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-12 09:00 | 2019-11-12 18:00 | 2019-11-12 09:00 | 2019-11-12 18:00 |  |  | 2019-11-12 10:57 | 2019-11-12 10:57 |  |  | 100 | 100 | [15 empty] | 10.0275 | 0.007392 | 0.73 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4449 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019499
2039 | Task(Task)-->P (Procurement) | UPS SYSTEM |  | 1.15.2.1 | UPS SYSTEM-->PURCHASE REQUISITION-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-08 09:00 | 2020-01-08 18:00 | 2020-02-19 09:00 | 2020-02-19 18:00 |  |  | 2020-02-19 10:57 | 2020-02-19 10:57 |  |  | 100 | 100 | [15 empty] | 2.0604 | 0.001519 | 0.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4450 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019500
2040 | Task(Task)-->P (Procurement) | 24V DC BATTERY AND BATTERY CHARGER SYSTEM |  | 1.15.2.1 | 24V DC BATTERY AND BATTERY CHARGER SYSTEM-->PURCHASE REQUISITION-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-27 09:00 | 2020-01-27 18:00 | 2020-02-26 09:00 | 2020-02-26 18:00 |  |  | 2020-02-26 10:57 | 2020-02-26 10:57 |  |  | 100 | 100 | [15 empty] | 0.96154 | 0.000709 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4451 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019501
2041 | Task(Task)-->P (Procurement) | FDA SYSTEM |  | 1.15.2.1 | FDA SYSTEM-->PURCHASE REQUISITION-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-14 09:00 | 2020-02-14 18:00 | 2020-02-17 09:00 | 2020-02-17 18:00 |  |  | 2020-02-17 10:57 | 2020-02-17 10:57 |  |  | 100 | 100 | [15 empty] | 6.7308 | 0.004962 | 0.49 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4452 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019502
2042 | Task(Task)-->P (Procurement) | SCADA |  | 1.15.2.1 | SCADA-->PURCHASE REQUISITION-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-10 09:00 | 2019-12-10 18:00 | 2019-12-21 09:00 | 2019-12-21 18:00 |  |  | 2019-12-21 10:57 | 2019-12-21 10:57 |  |  | 100 | 100 | [15 empty] | 3.1593 | 0.002329 | 0.23 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4453 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019503
2043 | Task(Task)-->P (Procurement) | RUBBER MATS |  | 1.15.2.1 | RUBBER MATS-->PURCHASE REQUISITION-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2020-06-25 09:00 | 2020-06-25 18:00 | 2020-04-18 09:00 | 2020-04-18 18:00 |  |  | 2020-04-18 10:57 | 2020-04-18 10:57 |  |  | 100 | 100 | [15 empty] | 0.13736 | 0.000101 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4456 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019504
2044 | Task(Task)-->P (Procurement) | MAIN LIGHTING DISTRIBUTION BOARD |  | 1.15.2.1 | MAIN LIGHTING DISTRIBUTION BOARD-->PURCHASE REQUISITION-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-04 09:00 | 2020-02-04 18:00 | 2020-04-02 09:00 | 2020-04-02 18:00 |  |  | 2020-04-02 17:08 | 2020-04-02 17:08 |  |  | 100 | 100 | [15 empty] | 0.68681 | 0.000506 | 0.05 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4457 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019505
2045 | Task(Task)-->P (Procurement) | LIGHTING PANELS |  | 1.15.2.1 | LIGHTING PANELS-->PURCHASE REQUISITION-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-28 09:00 | 2020-02-28 18:00 | 2020-04-02 09:00 | 2020-04-02 18:00 | [6 empty] | 100 | 0 | [15 empty] | 7.8297 | 0.005772 | 0.57 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4458 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019506
2046 | Task(Task)-->P (Procurement) | DCDB & DC FUSE BOARD |  | 1.15.2.1 | DCDB & DC FUSE BOARD-->PURCHASE REQUISITION-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-28 09:00 | 2020-01-28 18:00 | 2020-04-02 09:00 | 2020-04-02 18:00 |  |  | 2020-04-02 16:54 | 2020-04-02 16:54 |  |  | 100 | 100 | [15 empty] | 2.8846 | 0.002127 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4459 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019507
2047 | Task(Task)-->P (Procurement) | UPS DB,ACDB,MCBDB & AFB |  | 1.15.2.1 | UPS DB,ACDB,MCBDB & AFB-->PURCHASE REQUISITION-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-18 09:00 | 2020-03-18 18:00 | 2020-04-02 09:00 | 2020-04-02 18:00 |  |  | 2020-04-02 17:02 | 2020-04-02 17:02 |  |  | 100 | 100 | [15 empty] | 2.8846 | 0.002127 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4460 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019508
2048 | Task(Task)-->P (Procurement) | TECHNICAL CLEARANCE | 1.15.2.2 | 1.15.2 | TECHNICAL CLEARANCE-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-11-13 09:00 | 2020-07-20 18:00 | 2019-11-02 09:00 | 2020-07-10 18:00 |  |  | 2019-11-04 14:47 |  |  |  | 100 | 77.0602 | [15 empty] | 5 | 0.073719 | 7.25 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4461 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019509
2049 | Task(Task)-->P (Procurement) | 33/6.9KV HT TRANSFORMER (ONAN TYPE) |  | 1.15.2.2 | 33/6.9KV HT TRANSFORMER (ONAN TYPE)-->TECHNICAL CLEARANCE-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-29 09:00 | 2019-12-22 23:59 | 2020-01-17 09:00 | 2020-02-17 18:00 |  |  | 2020-03-16 10:57 | 2020-03-16 10:57 |  |  | 100 | 100 | [15 empty] | 14.011 | 0.010329 | 1.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4462 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019510
2050 | Task(Task)-->P (Procurement) | HT SWITCHGEAR (33KV & 6.6KV) |  | 1.15.2.2 | HT SWITCHGEAR (33KV & 6.6KV)-->TECHNICAL CLEARANCE-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-14 09:00 | 2019-12-13 18:00 | 2019-11-02 09:00 | 2020-03-10 18:00 |  |  | 2019-11-04 14:47 | 2020-03-10 14:47 |  |  | 100 | 100 | [15 empty] | 18.544 | 0.01367 | 1.35 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4463 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019511
2051 | Task(Task)-->P (Procurement) | 6.6KV HT VFD with Motors |  | 1.15.2.2 | 6.6KV HT VFD with Motors-->TECHNICAL CLEARANCE-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-31 09:00 | 2020-01-29 18:00 | 2020-01-24 09:00 | 2020-04-16 18:00 |  |  | 2020-02-26 10:57 | 2020-02-26 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4464 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019512
2052 | Task(Task)-->P (Procurement) | 6.6KV HT APFC PANEL |  | 1.15.2.2 | 6.6KV HT APFC PANEL-->TECHNICAL CLEARANCE-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-25 09:00 | 2020-02-16 23:59 | 2020-02-13 09:00 | 2020-04-28 18:00 |  |  | 2020-04-28 10:57 | 2020-04-28 10:57 |  |  | 100 | 100 | [15 empty] | 1.6484 | 0.001215 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4465 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019513
2053 | Task(Task)-->P (Procurement) | 6.6KV/0.433V LT TRANSFORMER |  | 1.15.2.2 | 6.6KV/0.433V LT TRANSFORMER-->TECHNICAL CLEARANCE-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-26 09:00 | 2019-12-20 18:00 | 2020-01-22 09:00 | 2020-03-16 18:00 |  |  | 2020-01-23 15:39 | 2020-03-16 15:39 |  |  | 100 | 100 | [15 empty] | 7.0055 | 0.005164 | 0.51 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4466 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019514
2054 | Task(Task)-->P (Procurement) | LT BUSDUCT |  | 1.15.2.2 | LT BUSDUCT-->TECHNICAL CLEARANCE-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-03 09:00 | 2020-01-03 18:00 | 2019-12-11 09:00 | 2020-03-10 18:00 |  |  | 2019-12-12 15:46 | 2020-03-10 15:46 |  |  | 100 | 100 | [15 empty] | 2.1978 | 0.00162 | 0.16 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4467 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019515
2055 | Task(Task)-->P (Procurement) | 415V MCC |  | 1.15.2.2 | 415V MCC-->TECHNICAL CLEARANCE-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-11-29 09:00 | 2020-01-11 18:00 | 2019-11-14 09:00 | 2020-03-11 18:00 | [6 empty] | 100 | 0 | [15 empty] | 14.1484 | 0.01043 | 1.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4468 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019516
2056 | Task(Task)-->P (Procurement) | 110V DC BATTERY & BATTERY CHARGER SYSTEM |  | 1.15.2.2 | 110V DC BATTERY & BATTERY CHARGER SYSTEM-->TECHNICAL CLEARANCE-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-14 09:00 | 2020-02-03 18:00 | 2020-01-13 09:00 | 2020-06-04 18:00 |  |  | 2020-01-14 17:10 | 2020-06-04 17:10 |  |  | 100 | 100 | [15 empty] | 4.6703 | 0.003443 | 0.34 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4469 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019517
2057 | Task(Task)-->P (Procurement) | 6.6KV NEUTRAL GROUNDING RESISTOR |  | 1.15.2.2 | 6.6KV NEUTRAL GROUNDING RESISTOR-->TECHNICAL CLEARANCE-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-13 09:00 | 2019-12-31 18:00 | 2019-12-12 09:00 | 2020-01-21 18:00 |  |  | 2019-12-13 15:23 | 2020-01-21 15:24 |  |  | 100 | 100 | [15 empty] | 0.41209 | 0.000304 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4470 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019518
2058 | Task(Task)-->P (Procurement) | PLC SYSTEM |  | 1.15.2.2 | PLC SYSTEM-->TECHNICAL CLEARANCE-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-13 09:00 | 2019-12-04 18:00 | 2019-11-12 09:00 | 2020-03-16 18:00 |  |  | 2020-03-16 10:57 | 2020-03-16 10:57 |  |  | 100 | 100 | [15 empty] | 10.0275 | 0.007392 | 0.73 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4471 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019519
2059 | Task(Task)-->P (Procurement) | UPS SYSTEM |  | 1.15.2.2 | UPS SYSTEM-->TECHNICAL CLEARANCE-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-09 09:00 | 2020-01-28 18:00 | 2020-02-19 09:00 | 2020-06-06 18:00 |  |  | 2020-06-06 10:57 | 2020-06-06 10:57 |  |  | 100 | 100 | [15 empty] | 2.0604 | 0.001519 | 0.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4472 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019520
2060 | Task(Task)-->P (Procurement) | 24V DC BATTERY AND BATTERY CHARGER SYSTEM |  | 1.15.2.2 | 24V DC BATTERY AND BATTERY CHARGER SYSTEM-->TECHNICAL CLEARANCE-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-28 09:00 | 2020-02-07 18:00 | 2020-02-26 09:00 | 2020-07-10 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.96154 | 0.000709 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4473 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019521
2061 | Task(Task)-->P (Procurement) | FDA SYSTEM |  | 1.15.2.2 | FDA SYSTEM-->TECHNICAL CLEARANCE-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-15 09:00 | 2020-03-12 18:00 | 2020-02-17 09:00 | 2020-06-10 18:00 |  |  | 2020-06-10 10:57 | 2020-06-10 10:57 |  |  | 100 | 100 | [15 empty] | 6.7308 | 0.004962 | 0.49 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4474 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019522
2062 | Task(Task)-->P (Procurement) | SCADA |  | 1.15.2.2 | SCADA-->TECHNICAL CLEARANCE-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-11 09:00 | 2020-01-15 18:00 | 2019-12-21 09:00 | 2020-03-16 18:00 |  |  | 2020-03-16 10:57 | 2020-03-16 10:57 |  |  | 100 | 100 | [15 empty] | 3.1593 | 0.002329 | 0.23 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4475 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019523
2063 | Task(Task)-->P (Procurement) | RUBBER MATS |  | 1.15.2.2 | RUBBER MATS-->TECHNICAL CLEARANCE-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2020-06-26 09:00 | 2020-07-20 18:00 | 2020-04-18 09:00 | 2020-04-20 18:00 |  |  | 2020-04-20 10:57 | 2020-04-20 10:57 |  |  | 100 | 100 | [15 empty] | 0.13736 | 0.000101 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4478 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019524
2064 | Task(Task)-->P (Procurement) | MAIN LIGHTING DISTRIBUTION BOARD |  | 1.15.2.2 | MAIN LIGHTING DISTRIBUTION BOARD-->TECHNICAL CLEARANCE-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-05 09:00 | 2020-04-02 18:00 | 2020-04-02 09:00 | 2020-07-01 18:00 |  |  | 2020-04-03 17:08 | 2020-07-01 17:08 |  |  | 100 | 100 | [15 empty] | 0.68681 | 0.000506 | 0.05 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4479 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019525
2065 | Task(Task)-->P (Procurement) | LIGHTING PANELS |  | 1.15.2.2 | LIGHTING PANELS-->TECHNICAL CLEARANCE-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-29 09:00 | 2020-05-11 18:00 | 2020-04-02 09:00 | 2020-07-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 7.8297 | 0.005772 | 0.57 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4480 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019526
2066 | Task(Task)-->P (Procurement) | DCDB & DC FUSE BOARD |  | 1.15.2.2 | DCDB & DC FUSE BOARD-->TECHNICAL CLEARANCE-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-29 09:00 | 2020-04-02 18:00 | 2020-04-02 09:00 | 2020-07-01 18:00 |  |  | 2020-04-03 16:59 | 2020-07-01 16:59 |  |  | 100 | 100 | [15 empty] | 2.8846 | 0.002127 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4481 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019527
2067 | Task(Task)-->P (Procurement) | UPS DB,ACDB,MCBDB & AFB |  | 1.15.2.2 | UPS DB,ACDB,MCBDB & AFB-->TECHNICAL CLEARANCE-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-19 09:00 | 2020-04-02 18:00 | 2020-04-02 09:00 | 2020-07-01 18:00 |  |  | 2020-04-03 17:03 | 2020-07-01 17:03 |  |  | 100 | 100 | [15 empty] | 2.8846 | 0.002127 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4482 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019528
2068 | Task(Task)-->P (Procurement) | ORDERING | 1.15.2.3 | 1.15.2 | ORDERING-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-12-05 09:00 | 2020-07-25 18:00 | 2020-01-21 09:00 | 2020-08-13 18:00 |  |  | 2020-01-04 08:00 |  |  |  | 100 | 68.2318 | [15 empty] | 10 | 0.14744 | 14.5 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4483 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019529
2069 | Task(Task)-->P (Procurement) | 33/6.9KV HT TRANSFORMER (ONAN TYPE) |  | 1.15.2.3 | 33/6.9KV HT TRANSFORMER (ONAN TYPE)-->ORDERING-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-23 09:00 | 2020-01-15 18:00 | 2020-02-17 09:00 | 2020-06-24 18:00 |  |  | 2020-07-16 22:28 | 2020-07-16 22:28 |  |  | 100 | 100 | [15 empty] | 14.0193 | 0.02067 | 2.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4484 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019530
2070 | Task(Task)-->P (Procurement) | HT SWITCHGEAR (33KV & 6.6KV) |  | 1.15.2.3 | HT SWITCHGEAR (33KV & 6.6KV)-->ORDERING-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-14 09:00 | 2020-01-13 18:00 | 2020-03-10 09:00 | 2020-07-18 18:00 |  |  | 2020-03-11 14:49 | 2020-07-04 14:49 |  |  | 100 | 100 | [15 empty] | 18.6464 | 0.027492 | 2.7 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4485 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019531
2071 | Task(Task)-->P (Procurement) | 6.6KV HT VFD with Motors |  | 1.15.2.3 | 6.6KV HT VFD with Motors-->ORDERING-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-30 09:00 | 2020-02-28 18:00 | 2020-04-16 09:00 | 2020-07-18 18:00 |  |  | 2020-04-29 10:57 | 2020-04-29 10:57 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4486 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019532
2072 | Task(Task)-->P (Procurement) | 6.6KV HT APFC PANEL |  | 1.15.2.3 | 6.6KV HT APFC PANEL-->ORDERING-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-17 09:00 | 2020-03-10 18:00 | 2020-04-28 09:00 | 2020-07-28 18:00 |  |  | 2020-05-04 15:17 | 2020-07-10 15:17 |  |  | 100 | 100 | [15 empty] | 1.6575 | 0.002444 | 0.24 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4487 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019533
2073 | Task(Task)-->P (Procurement) | 6.6KV/0.433V LT TRANSFORMER |  | 1.15.2.3 | 6.6KV/0.433V LT TRANSFORMER-->ORDERING-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-21 09:00 | 2020-01-15 18:00 | 2020-03-16 09:00 | 2020-06-23 18:00 |  |  | 2020-06-23 10:14 | 2020-06-23 10:14 |  |  | 100 | 100 | [15 empty] | 7.0442 | 0.010386 | 1.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4488 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019534
2074 | Task(Task)-->P (Procurement) | LT BUSDUCT |  | 1.15.2.3 | LT BUSDUCT-->ORDERING-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-04 09:00 | 2020-02-04 18:00 | 2020-03-10 09:00 | 2020-06-11 18:00 |  |  | 2020-01-04 08:00 | 2020-04-27 15:47 |  |  | 100 | 100 | [15 empty] | 2.1409 | 0.003156 | 0.31 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4489 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019535
2075 | Task(Task)-->P (Procurement) | 415V MCC |  | 1.15.2.3 | 415V MCC-->ORDERING-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-12 | 2020-02-25 18:00 | 2020-03-11 09:00 | 2020-07-04 18:00 | [6 empty] | 100 | 0 | [15 empty] | 14.2956 | 0.021077 | 2.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4490 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019536
2076 | Task(Task)-->P (Procurement) | 110V DC BATTERY & BATTERY CHARGER SYSTEM |  | 1.15.2.3 | 110V DC BATTERY & BATTERY CHARGER SYSTEM-->ORDERING-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-04 09:00 | 2020-02-24 18:00 | 2020-06-04 09:00 | 2020-07-18 18:00 |  |  | 2020-06-05 17:10 | 2020-07-06 17:10 |  |  | 100 | 100 | [15 empty] | 4.6271 | 0.006822 | 0.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4491 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019537
2077 | Task(Task)-->P (Procurement) | 6.6KV NEUTRAL GROUNDING RESISTOR |  | 1.15.2.3 | 6.6KV NEUTRAL GROUNDING RESISTOR-->ORDERING-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-01 09:00 | 2020-01-20 18:00 | 2020-01-21 09:00 | 2020-03-19 18:00 |  |  | 2020-03-19 10:20 | 2020-03-19 10:21 |  |  | 100 | 100 | [15 empty] | 0.41436 | 0.000611 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4492 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019538
2078 | Task(Task)-->P (Procurement) | PLC SYSTEM |  | 1.15.2.3 | PLC SYSTEM-->ORDERING-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-05 09:00 | 2019-12-27 18:00 | 2020-03-16 09:00 | 2020-07-07 18:00 |  |  | 2020-03-16 17:20 | 2020-06-04 17:21 |  |  | 100 | 100 | [15 empty] | 10.0829 | 0.014866 | 1.46 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4493 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019539
2079 | Task(Task)-->P (Procurement) | UPS SYSTEM |  | 1.15.2.3 | UPS SYSTEM-->ORDERING-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-29 09:00 | 2020-02-18 18:00 | 2020-06-06 09:00 | 2020-07-31 18:00 | [6 empty] | 100 | 0 | [15 empty] | 2.0028 | 0.002953 | 0.29 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4494 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019540
2080 | Task(Task)-->P (Procurement) | 24V DC BAT TERY AND BATTERY CHARGER SYSTEM |  | 1.15.2.3 | 24V DC BAT TERY AND BATTERY CHARGER SYSTEM-->ORDERING-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-08 09:00 | 2020-02-19 18:00 | 2020-07-10 09:00 | 2020-08-07 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.96685 | 0.001426 | 0.14 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4495 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019541
2081 | Task(Task)-->P (Procurement) | FDA SYSTEM |  | 1.15.2.3 | FDA SYSTEM-->ORDERING-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-13 09:00 | 2020-04-08 18:00 | 2020-06-10 09:00 | 2020-08-06 18:00 | [6 empty] | 100 | 0 | [15 empty] | 6.6989 | 0.009877 | 0.97 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4496 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019542
2082 | Task(Task)-->P (Procurement) | SCADA |  | 1.15.2.3 | SCADA-->ORDERING-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-16 09:00 | 2020-02-20 18:00 | 2020-03-16 09:00 | 2020-06-24 18:00 |  |  | 2020-06-24 10:20 | 2020-06-24 10:20 |  |  | 100 | 100 | [15 empty] | 3.1077 | 0.004582 | 0.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4497 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019543
2083 | Task(Task)-->P (Procurement) | RUBBER MATS |  | 1.15.2.3 | RUBBER MATS-->ORDERING-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2020-07-21 09:00 | 2020-07-25 18:00 | 2020-04-20 09:00 | 2020-06-06 18:00 |  |  | 2020-04-25 10:57 | 2020-04-25 10:57 |  |  | 100 | 100 | [15 empty] | 0.13812 | 0.000204 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4500 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019544
2084 | Task(Task)-->P (Procurement) | MAIN LIGHTING DISTRIBUTION BOARD |  | 1.15.2.3 | MAIN LIGHTING DISTRIBUTION BOARD-->ORDERING-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-03 09:00 | 2020-04-18 18:00 | 2020-07-01 09:00 | 2020-08-13 18:00 |  |  | 2020-07-02 17:08 | 2020-07-07 17:08 |  |  | 100 | 100 | [15 empty] | 0.69061 | 0.001018 | 0.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4501 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019545
2085 | Task(Task)-->P (Procurement) | LIGHTING PANELS |  | 1.15.2.3 | LIGHTING PANELS-->ORDERING-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-12 09:00 | 2020-06-25 18:00 | 2020-07-01 09:00 | 2020-08-13 18:00 | [6 empty] | 100 | 0 | [15 empty] | 7.8039 | 0.011506 | 1.13 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4502 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019546
2086 | Task(Task)-->P (Procurement) | DCDB & DC FUSE BOARD |  | 1.15.2.3 | DCDB & DC FUSE BOARD-->ORDERING-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-03 09:00 | 2020-04-18 18:00 | 2020-07-01 09:00 | 2020-08-13 18:00 |  |  | 2020-07-02 17:00 | 2020-07-07 17:00 |  |  | 100 | 100 | [15 empty] | 2.8315 | 0.004175 | 0.41 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4503 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019547
2087 | Task(Task)-->P (Procurement) | UPS DB,ACDB,MCBDB & AFB |  | 1.15.2.3 | UPS DB,ACDB,MCBDB & AFB-->ORDERING-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-03 09:00 | 2020-04-18 18:00 | 2020-07-01 09:00 | 2020-08-13 18:00 |  |  | 2020-07-02 17:05 | 2020-07-07 17:05 |  |  | 100 | 100 | [15 empty] | 2.8315 | 0.004175 | 0.41 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4504 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019548
2088 | Task(Task)-->P (Procurement) | ITP APPROVAL | 1.15.2.4 | 1.15.2 | ITP APPROVAL-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-12-28 09:00 | 2020-09-03 18:00 | 2020-06-05 09:00 | 2020-11-30 18:00 |  |  | 2020-06-05 08:54 |  |  |  | 100 | 17.9954 | [15 empty] | 5 | 0.073719 | 7.25 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4505 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019549
2089 | Task(Task)-->P (Procurement) | 33/6.9KV HT TRANSFORMER (ONAN TYPE) |  | 1.15.2.4 | 33/6.9KV HT TRANSFORMER (ONAN TYPE)-->ITP APPROVAL-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-16 09:00 | 2020-02-24 18:00 | 2020-07-03 09:00 | 2020-07-15 18:00 |  |  | 2020-07-03 08:47 | 2020-07-15 08:47 |  |  | 100 | 100 | [15 empty] | 14.011 | 0.010329 | 1.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4506 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019550
2090 | Task(Task)-->P (Procurement) | HT SWITCHGEAR (33KV & 6.6KV) |  | 1.15.2.4 | HT SWITCHGEAR (33KV & 6.6KV)-->ITP APPROVAL-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-14 09:00 | 2020-02-22 18:00 | 2020-08-06 09:00 | 2020-11-20 18:00 |  |  | 2020-07-13 10:49 |  |  |  | 100 | 0 | [15 empty] | 18.544 | 0.01367 | 1.35 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4507 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019551
2091 | Task(Task)-->P (Procurement) | 6.6KV HT VFD with Motors |  | 1.15.2.4 | 6.6KV HT VFD with Motors-->ITP APPROVAL-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-29 09:00 | 2020-04-08 18:00 | 2020-08-01 09:00 | 2020-09-09 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4508 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019552
2092 | Task(Task)-->P (Procurement) | 6.6KV HT APFC PANEL |  | 1.15.2.4 | 6.6KV HT APFC PANEL-->ITP APPROVAL-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-11 09:00 | 2020-04-19 23:59 | 2020-08-01 09:00 | 2020-09-09 18:00 | [6 empty] | 100 | 0 | [15 empty] | 1.6484 | 0.001215 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4509 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019553
2093 | Task(Task)-->P (Procurement) | 6.6KV/0.433V LT TRANSFORMER |  | 1.15.2.4 | 6.6KV/0.433V LT TRANSFORMER-->ITP APPROVAL-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-16 09:00 | 2020-02-24 18:00 | 2020-08-05 09:00 | 2020-11-10 18:00 | [6 empty] | 100 | 0 | [15 empty] | 7.0055 | 0.005164 | 0.51 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4510 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019554
2094 | Task(Task)-->P (Procurement) | LT BUSDUCT |  | 1.15.2.4 | LT BUSDUCT-->ITP APPROVAL-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-05 09:00 | 2020-03-15 23:59 | 2020-09-21 09:00 | 2020-10-14 18:00 |  |  | 2020-09-21 17:35 |  |  |  | 100 | 0 | [15 empty] | 2.1978 | 0.00162 | 0.16 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4511 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019555
2095 | Task(Task)-->P (Procurement) | 415V MCC |  | 1.15.2.4 | 415V MCC-->ITP APPROVAL-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-26 09:00 | 2020-04-05 23:59 | 2020-08-01 09:00 | 2020-09-09 18:00 | [6 empty] | 100 | 0 | [15 empty] | 14.1484 | 0.01043 | 1.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4512 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019556
2096 | Task(Task)-->P (Procurement) | 110V DC BATTERY & BATTERY CHARGER SYSTEM |  | 1.15.2.4 | 110V DC BATTERY & BATTERY CHARGER SYSTEM-->ITP APPROVAL-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-25 09:00 | 2020-04-04 18:00 | 2020-07-07 09:00 | 2020-11-15 23:59 |  |  | 2020-07-07 10:31 |  |  |  | 100 | 0 | [15 empty] | 4.6703 | 0.003443 | 0.34 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4513 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019557
2097 | Task(Task)-->P (Procurement) | 6.6KV NEUTRAL GROUNDING RESISTOR |  | 1.15.2.4 | 6.6KV NEUTRAL GROUNDING RESISTOR-->ITP APPROVAL-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-21 09:00 | 2020-02-29 18:00 | 2020-06-05 09:00 | 2020-07-15 18:00 |  |  | 2020-06-05 08:54 | 2020-07-15 08:54 |  |  | 100 | 100 | [15 empty] | 0.41209 | 0.000304 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4514 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019558
2098 | Task(Task)-->P (Procurement) | PLC SYSTEM |  | 1.15.2.4 | PLC SYSTEM-->ITP APPROVAL-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-12-28 09:00 | 2020-02-05 18:00 | 2020-08-27 09:00 | 2020-10-22 18:00 |  |  | 2020-08-27 17:08 |  |  |  | 100 | 0 | [15 empty] | 10.0275 | 0.007392 | 0.73 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4515 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019559
2099 | Task(Task)-->P (Procurement) | UPS SYSTEM |  | 1.15.2.4 | UPS SYSTEM-->ITP APPROVAL-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-19 09:00 | 2020-03-29 23:59 | 2020-09-01 09:00 | 2020-09-25 18:00 | [6 empty] | 100 | 0 | [15 empty] | 2.0604 | 0.001519 | 0.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4516 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019560
2100 | Task(Task)-->P (Procurement) | 24V DC BATTERY AND BATTERY CHARGER SYSTEM |  | 1.15.2.4 | 24V DC BATTERY AND BATTERY CHARGER SYSTEM-->ITP APPROVAL-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-20 09:00 | 2020-03-30 18:00 | 2020-08-08 09:00 | 2020-11-30 18:00 |  |  | 2020-08-06 16:18 |  |  |  | 100 | 0 | [15 empty] | 0.96154 | 0.000709 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4517 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019561
2101 | Task(Task)-->P (Procurement) | FDA SYSTEM |  | 1.15.2.4 | FDA SYSTEM-->ITP APPROVAL-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-09 09:00 | 2020-05-18 18:00 | 2020-08-21 09:00 | 2020-11-30 18:00 | [6 empty] | 100 | 0 | [15 empty] | 6.7308 | 0.004962 | 0.49 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4518 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019562
2102 | Task(Task)-->P (Procurement) | SCADA |  | 1.15.2.4 | SCADA-->ITP APPROVAL-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-21 09:00 | 2020-03-31 18:00 | 2020-09-17 09:00 | 2020-11-15 23:59 | [6 empty] | 100 | 0 | [15 empty] | 3.1593 | 0.002329 | 0.23 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4519 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019563
2103 | Task(Task)-->P (Procurement) | RUBBER MATS |  | 1.15.2.4 | RUBBER MATS-->ITP APPROVAL-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-26 | 2020-09-03 18:00 | 2020-08-10 09:00 | 2020-08-10 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.13736 | 0.000101 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4522 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019564
2104 | Task(Task)-->P (Procurement) | MAIN LIGHTING DISTRIBUTION BOARD |  | 1.15.2.4 | MAIN LIGHTING DISTRIBUTION BOARD-->ITP APPROVAL-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-19 | 2020-05-28 18:00 | 2020-07-28 09:00 | 2020-10-14 18:00 |  |  | 2020-07-28 17:50 | 2020-10-14 15:09 |  |  | 100 | 100 | [15 empty] | 0.68681 | 0.000506 | 0.05 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4523 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019565
2105 | Task(Task)-->P (Procurement) | LIGHTING PANELS |  | 1.15.2.4 | LIGHTING PANELS-->ITP APPROVAL-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-26 09:00 | 2020-08-04 18:00 | 2020-07-28 09:00 | 2020-10-14 18:00 |  |  | 2020-07-28 17:39 |  |  |  | 100 | 0 | [15 empty] | 7.8297 | 0.005772 | 0.57 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4524 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019566
2106 | Task(Task)-->P (Procurement) | DCDB & DC FUSE BOARD |  | 1.15.2.4 | DCDB & DC FUSE BOARD-->ITP APPROVAL-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-19 | 2020-05-28 18:00 | 2020-07-28 09:00 | 2020-10-14 18:00 |  |  | 2020-07-28 14:24 | 2020-10-14 15:11 |  |  | 100 | 100 | [15 empty] | 2.8846 | 0.002127 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4525 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019567
2107 | Task(Task)-->P (Procurement) | UPS DB,ACDB,MCBDB & AFB |  | 1.15.2.4 | UPS DB,ACDB,MCBDB & AFB-->ITP APPROVAL-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-19 | 2020-05-28 18:00 | 2020-07-28 09:00 | 2020-10-14 18:00 |  |  | 2020-07-28 17:49 |  |  |  | 100 | 0 | [15 empty] | 2.8846 | 0.002127 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4526 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019568
2108 | Task(Task)-->P (Procurement) | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE | 1.15.2.5 | 1.15.2 | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-12-28 09:00 | 2020-08-15 18:00 | 2020-03-19 09:00 | 2020-11-30 18:00 |  |  | 2020-03-20 15:25 |  |  |  | 100 | 25.23 | [15 empty] | 15 | 0.22116 | 21.75 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4527 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019569
2109 | Task(Task)-->P (Procurement) | 33/6.9KV HT TRANSFORMER (ONAN TYPE) |  | 1.15.2.5 | 33/6.9KV HT TRANSFORMER (ONAN TYPE)-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-16 09:00 | 2020-03-15 23:59 | 2020-06-30 09:00 | 2020-09-22 18:00 |  |  | 2020-06-30 08:49 | 2020-09-22 12:23 |  |  | 100 | 100 | [15 empty] | 14.0165 | 0.030999 | 3.05 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4528 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019570
2110 | Task(Task)-->P (Procurement) | HT SWITCHGEAR (33KV & 6.6KV) |  | 1.15.2.5 | HT SWITCHGEAR (33KV & 6.6KV)-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-14 09:00 | 2020-03-28 18:00 | 2020-07-30 09:00 | 2020-10-31 18:00 |  |  | 2020-07-30 10:51 |  |  |  | 100 | 0 | [15 empty] | 18.5662 | 0.04106 | 4.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4529 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019571
2111 | Task(Task)-->P (Procurement) | 6.6KV HT VFD with Motors |  | 1.15.2.5 | 6.6KV HT VFD with Motors-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-29 09:00 | 2020-05-13 18:00 | 2020-08-08 09:00 | 2020-11-10 18:00 |  |  | 2020-07-28 11:51 | 2020-09-23 15:24 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4530 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019572
2112 | Task(Task)-->P (Procurement) | 6.6KV HT APFC PANEL |  | 1.15.2.5 | 6.6KV HT APFC PANEL-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-11 09:00 | 2020-04-24 18:00 | 2020-07-22 09:00 | 2020-11-10 18:00 |  |  | 2020-07-22 08:57 |  |  |  | 100 | 0 | [15 empty] | 1.6544 | 0.003659 | 0.36 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4531 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019573
2113 | Task(Task)-->P (Procurement) | 6.6KV/0.433V LT TRANSFORMER |  | 1.15.2.5 | 6.6KV/0.433V LT TRANSFORMER-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-16 09:00 | 2020-03-15 23:59 | 2020-07-20 09:00 | 2020-09-17 18:00 |  |  | 2020-07-20 09:00 | 2020-09-17 12:32 |  |  | 100 | 100 | [15 empty] | 7.0772 | 0.015652 | 1.54 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4532 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019574
2114 | Task(Task)-->P (Procurement) | LT BUSDUCT |  | 1.15.2.5 | LT BUSDUCT-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-05 09:00 | 2020-03-20 18:00 | 2020-06-12 09:00 | 2020-07-26 23:59 |  |  | 2020-09-16 17:36 |  |  |  | 100 | 0 | [15 empty] | 2.1599 | 0.004777 | 0.47 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4533 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019575
2115 | Task(Task)-->P (Procurement) | 415V MCC |  | 1.15.2.5 | 415V MCC-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-26 09:00 | 2020-05-10 23:59 | 2020-08-17 09:00 | 2020-11-10 18:00 |  |  | 2020-08-17 14:15 |  |  |  | 100 | 0 | [15 empty] | 14.2463 | 0.031507 | 3.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4534 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019576
2116 | Task(Task)-->P (Procurement) | 110V DC BATTERY & BATTERY CHARGER SYSTEM |  | 1.15.2.5 | 110V DC BATTERY & BATTERY CHARGER SYSTEM-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-25 09:00 | 2020-04-19 23:59 | 2020-07-07 09:00 | 2020-10-29 18:00 |  |  | 2020-07-07 10:31 |  |  |  | 100 | 0 | [15 empty] | 4.6415 | 0.010265 | 1.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4535 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019577
2117 | Task(Task)-->P (Procurement) | 6.6KV NEUTRAL GROUNDING RESISTOR |  | 1.15.2.5 | 6.6KV NEUTRAL GROUNDING RESISTOR-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-21 09:00 | 2020-03-05 18:00 | 2020-03-19 09:00 | 2020-06-04 18:00 |  |  | 2020-03-20 15:25 | 2020-06-04 15:25 |  |  | 100 | 100 | [15 empty] | 0.4136 | 0.000915 | 0.09 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4536 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019578
2118 | Task(Task)-->P (Procurement) | PLC SYSTEM |  | 1.15.2.5 | PLC SYSTEM-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-12-28 09:00 | 2020-03-11 18:00 | 2020-07-29 09:00 | 2020-11-16 18:00 |  |  | 2020-07-29 17:09 |  |  |  | 100 | 0 | [15 empty] | 10.0184 | 0.022156 | 2.18 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4537 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019579
2119 | Task(Task)-->P (Procurement) | UPS SYSTEM |  | 1.15.2.5 | UPS SYSTEM-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-19 09:00 | 2020-04-03 18:00 | 2020-08-01 09:00 | 2020-09-14 18:00 |  |  | 2020-08-31 12:21 |  |  |  | 100 | 0 | [15 empty] | 2.0221 | 0.004472 | 0.44 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4538 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019580
2120 | Task(Task)-->P (Procurement) | 24V DC BATTERY AND BATTERY CHARGER SYSTEM |  | 1.15.2.5 | 24V DC BATTERY AND BATTERY CHARGER SYSTEM-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-20 09:00 | 2020-04-14 18:00 | 2020-08-06 09:00 | 2020-10-30 18:00 |  |  | 2020-08-06 16:16 |  |  |  | 100 | 0 | [15 empty] | 0.96507 | 0.002134 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4539 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019581
2121 | Task(Task)-->P (Procurement) | FDA SYSTEM |  | 1.15.2.5 | FDA SYSTEM-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-09 09:00 | 2020-06-22 18:00 | 2020-08-13 09:00 | 2020-11-30 18:00 | [6 empty] | 100 | 0 | [15 empty] | 6.7096 | 0.014839 | 1.46 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4540 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019582
2122 | Task(Task)-->P (Procurement) | SCADA |  | 1.15.2.5 | SCADA-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-21 09:00 | 2020-05-05 18:00 | 2020-08-15 09:00 | 2020-11-30 18:00 |  |  | 2020-07-06 17:05 |  |  |  | 100 | 0 | [15 empty] | 3.125 | 0.006911 | 0.68 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4541 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019583
2123 | Task(Task)-->P (Procurement) | RUBBER MATS |  | 1.15.2.5 | RUBBER MATS-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2020-07-26 | 2020-08-15 18:00 | 2020-06-30 09:00 | 2020-07-23 18:00 |  |  | 2020-06-11 21:17 | 2020-07-03 21:17 |  |  | 100 | 100 | [15 empty] | 0.13787 | 0.000305 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4544 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019584
2124 | Task(Task)-->P (Procurement) | MAIN LIGHTING DISTRIBUTION BOARD |  | 1.15.2.5 | MAIN LIGHTING DISTRIBUTION BOARD-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-19 | 2020-06-02 18:00 | 2020-07-28 09:00 | 2020-11-10 18:00 |  |  | 2020-07-28 17:31 | 2020-10-31 10:07 |  |  | 100 | 100 | [15 empty] | 0.73529 | 0.001626 | 0.16 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4545 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019585
2125 | Task(Task)-->P (Procurement) | LIGHTING PANELS |  | 1.15.2.5 | LIGHTING PANELS-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-26 09:00 | 2020-08-09 23:59 | 2020-07-28 09:00 | 2020-11-10 18:00 |  |  | 2020-07-28 17:40 |  |  |  | 100 | 0 | [15 empty] | 7.8125 | 0.017278 | 1.7 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4546 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019586
2126 | Task(Task)-->P (Procurement) | DCDB & DC FUSE BOARD |  | 1.15.2.5 | DCDB & DC FUSE BOARD-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-19 | 2020-06-02 18:00 | 2020-07-28 09:00 | 2020-11-10 18:00 |  |  | 2020-07-28 14:23 |  |  |  | 100 | 0 | [15 empty] | 2.8493 | 0.006301 | 0.62 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4547 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019587
2127 | Task(Task)-->P (Procurement) | UPS DB,ACDB,MCBDB & AFB |  | 1.15.2.5 | UPS DB,ACDB,MCBDB & AFB-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-19 | 2020-06-02 18:00 | 2020-07-28 09:00 | 2020-11-10 18:00 |  |  | 2020-07-28 17:47 | 2020-09-28 17:47 |  |  | 100 | 100 | [15 empty] | 2.8493 | 0.006301 | 0.62 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4548 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019588
2128 | Task(Task)-->P (Procurement) | MANUFACTURING & RECEIPT AT SITE (MRN) | 1.15.2.6 | 1.15.2 | MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-06 09:00 | 2021-03-31 18:00 | 2020-07-16 09:00 | 2021-11-24 18:00 |  |  | 2020-06-04 11:32 |  |  |  | 74.0904 | 0 | [15 empty] | 60 | 0.88463 | 87 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4549 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019589
2129 | Task(Task)-->P (Procurement) | 33/6.9KV HT TRANSFORMER (ONAN TYPE) |  | 1.15.2.6 | 33/6.9KV HT TRANSFORMER (ONAN TYPE)-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-16 09:00 | 2021-03-22 18:00 | 2020-09-23 09:00 | 2021-09-29 18:00 |  |  | 2020-09-23 09:25 |  |  |  | 64.5161 | 0 | [15 empty] | 14.0048 | 0.12389 | 12.18 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4550 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019590
2130 | Task(Task)-->P (Procurement) | HT SWITCHGEAR (33KV & 6.6KV) |  | 1.15.2.6 | HT SWITCHGEAR (33KV & 6.6KV)-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-29 | 2021-03-22 18:00 | 2020-11-21 09:00 | 2021-11-14 23:59 | [6 empty] | 63.2312 | 0 | [15 empty] | 18.6041 | 0.16458 | 16.18 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4551 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019591
2131 | Task(Task)-->P (Procurement) | 6.6KV HT VFD with Motors |  | 1.15.2.6 | 6.6KV HT VFD with Motors-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-14 09:00 | 2021-03-09 18:00 | 2020-11-11 09:00 | 2021-09-06 18:00 | [6 empty] | 60.3333 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4552 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019592
2132 | Task(Task)-->P (Procurement) | 6.6KV HT APFC PANEL |  | 1.15.2.6 | 6.6KV HT APFC PANEL-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-25 09:00 | 2020-11-04 18:00 | 2020-11-11 09:00 | 2021-05-23 23:59 | [6 empty] | 100 | 0 | [15 empty] | 1.6672 | 0.014749 | 1.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4553 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019593
2133 | Task(Task)-->P (Procurement) | 6.6KV/0.433V LT TRANSFORMER |  | 1.15.2.6 | 6.6KV/0.433V LT TRANSFORMER-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-16 09:00 | 2021-03-29 18:00 | 2020-11-11 09:00 | 2021-11-24 18:00 |  |  | 2020-09-18 12:33 |  |  |  | 63.3245 | 0 | [15 empty] | 7.0714 | 0.062556 | 6.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4554 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019594
2134 | Task(Task)-->P (Procurement) | LT BUSDUCT |  | 1.15.2.6 | LT BUSDUCT-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-21 09:00 | 2020-08-13 18:00 | 2020-10-15 09:00 | 2021-03-09 18:00 | [6 empty] | 100 | 0 | [15 empty] | 2.1502 | 0.019021 | 1.87 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4555 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019595
2135 | Task(Task)-->P (Procurement) | 415V MCC |  | 1.15.2.6 | 415V MCC-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-11 09:00 | 2021-03-31 18:00 | 2020-11-11 09:00 | 2021-10-01 18:00 | [6 empty] | 56.6154 | 0 | [15 empty] | 14.2693 | 0.12623 | 12.41 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4556 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019596
2136 | Task(Task)-->P (Procurement) | 110V DC BATTERY & BATTERY CHARGER SYSTEM |  | 1.15.2.6 | 110V DC BATTERY & BATTERY CHARGER SYSTEM-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-20 09:00 | 2020-11-03 18:00 | 2020-11-16 09:00 | 2021-06-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 4.6453 | 0.041093 | 4.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4557 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019597
2137 | Task(Task)-->P (Procurement) | 6.6KV NEUTRAL GROUNDING RESISTOR |  | 1.15.2.6 | 6.6KV NEUTRAL GROUNDING RESISTOR-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-06 09:00 | 2020-09-02 18:00 | 2020-07-16 09:00 | 2021-01-12 18:00 |  |  | 2020-06-04 11:32 |  |  |  | 100 | 0 | [15 empty] | 0.42543 | 0.003764 | 0.37 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4558 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019598
2138 | Task(Task)-->P (Procurement) | PLC SYSTEM |  | 1.15.2.6 | PLC SYSTEM-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-12 09:00 | 2021-01-20 18:00 | 2020-11-17 09:00 | 2021-09-27 18:00 | [6 empty] | 77.4603 | 0 | [15 empty] | 10.0379 | 0.088798 | 8.73 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4559 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019599
2139 | Task(Task)-->P (Procurement) | UPS SYSTEM |  | 1.15.2.6 | UPS SYSTEM-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-04 09:00 | 2020-11-03 18:00 | 2020-09-26 09:00 | 2021-04-27 18:00 | [6 empty] | 100 | 0 | [15 empty] | 2.0122 | 0.0178 | 1.75 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4560 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019600
2140 | Task(Task)-->P (Procurement) | 24V DC BATTERY AND BATTERY CHARGER SYSTEM |  | 1.15.2.6 | 24V DC BATTERY AND BATTERY CHARGER SYSTEM-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-15 09:00 | 2020-10-18 23:59 | 2020-12-01 09:00 | 2021-06-05 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.97735 | 0.008646 | 0.85 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4561 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019601
2141 | Task(Task)-->P (Procurement) | FDA SYSTEM |  | 1.15.2.6 | FDA SYSTEM-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-23 09:00 | 2020-12-25 18:00 | 2020-12-01 09:00 | 2021-06-04 18:00 | [6 empty] | 75.8064 | 0 | [15 empty] | 6.692 | 0.059199 | 5.82 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4562 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019602
2142 | Task(Task)-->P (Procurement) | SCADA |  | 1.15.2.6 | SCADA-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-06 09:00 | 2021-02-17 18:00 | 2020-12-01 09:00 | 2021-09-14 18:00 | [6 empty] | 65.625 | 0 | [15 empty] | 3.1045 | 0.027463 | 2.7 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4563 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019603
2143 | Task(Task)-->P (Procurement) | RUBBER MATS |  | 1.15.2.6 | RUBBER MATS-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-09-04 09:00 | 2021-02-15 18:00 | 2020-08-11 09:00 | 2021-01-22 18:00 | [6 empty] | 41.2121 | 0 | [15 empty] | 0.13798 | 0.001221 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4566 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019604
2144 | Task(Task)-->P (Procurement) | MAIN LIGHTING DISTRIBUTION BOARD |  | 1.15.2.6 | MAIN LIGHTING DISTRIBUTION BOARD-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-03 09:00 | 2020-09-16 18:00 | 2020-11-11 09:00 | 2021-02-24 18:00 |  |  | 2020-10-31 14:08 |  |  |  | 100 | 0 | [15 empty] | 0.71289 | 0.006306 | 0.62 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4567 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019605
2145 | Task(Task)-->P (Procurement) | LIGHTING PANELS |  | 1.15.2.6 | LIGHTING PANELS-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-10 09:00 | 2020-09-10 18:00 | 2020-11-11 09:00 | 2020-12-12 18:00 | [6 empty] | 100 | 0 | [15 empty] | 7.8073 | 0.069065 | 6.79 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4568 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019606
2146 | Task(Task)-->P (Procurement) | DCDB & DC FUSE BOARD |  | 1.15.2.6 | DCDB & DC FUSE BOARD-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-03 09:00 | 2020-08-10 18:00 | 2020-11-11 09:00 | 2021-01-18 18:00 | [6 empty] | 100 | 0 | [15 empty] | 2.8401 | 0.025124 | 2.47 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4569 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019607
2147 | Task(Task)-->P (Procurement) | UPS DB,ACDB,MCBDB & AFB |  | 1.15.2.6 | UPS DB,ACDB,MCBDB & AFB-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-03 09:00 | 2020-11-28 18:00 | 2020-11-11 09:00 | 2021-05-08 18:00 |  |  | 2020-09-29 09:00 |  |  |  | 89.9441 | 0 | [15 empty] | 2.8401 | 0.025124 | 2.47 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4570 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019608
2148 | Task(Task)-->C (Construction) | CONSTRUCTION | 1.15.3 | 1.15 | CONSTRUCTION-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-01 09:00 | 2021-08-29 23:59 | 2020-08-01 09:00 | 2022-03-19 18:00 | [6 empty] | 43.3187 | 0 | [15 empty] | 42.7855 | 1.1883 | 116.86 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4571 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019609
2149 | Task(Task)-->C (Construction) | CIVIL | 1.15.3.1 | 1.15.3 | CIVIL-->CONSTRUCTION-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-01 09:00 | 2021-08-29 23:59 | 2020-08-01 09:00 | 2022-01-26 18:00 | [6 empty] | 47.3061 | 0 | [15 empty] | 91.5711 | 1.0882 | 107.01 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4572 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019610
2150 | Task(Task)-->C (Construction) | AVAILABILITY OF FRONT BY NTPC |  | 1.15.3.1 | AVAILABILITY OF FRONT BY NTPC-->CIVIL-->CONSTRUCTION-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-01 09:00 | 2020-06-01 18:00 | 2020-08-01 09:00 | 2020-08-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4573 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019611
2151 | Task(Task)-->C (Construction) | EXCAVATION |  | 1.15.3.1 | EXCAVATION-->CIVIL-->CONSTRUCTION-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-08 09:00 | 2020-06-27 18:00 | 2020-11-05 09:00 | 2021-01-28 18:00 | [6 empty] | 100 | 0 | [15 empty] | 1.6165 | 0.01759 | 1.73 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 6500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5531 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | Excavation | [23 empty] | 1019612
2152 | Task(Task)-->C (Construction) | PCC |  | 1.15.3.1 | PCC-->CIVIL-->CONSTRUCTION-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-15 09:00 | 2020-07-04 18:00 | 2020-11-12 09:00 | 2020-12-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.75687 | 0.008236 | 0.81 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5532 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | PCC | [23 empty] | 1019613
2153 | Task(Task)-->C (Construction) | RAFT |  | 1.15.3.1 | RAFT-->CIVIL-->CONSTRUCTION-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-22 09:00 | 2020-07-26 23:59 | 2020-11-19 09:00 | 2020-12-23 18:00 | [6 empty] | 100 | 0 | [15 empty] | 15.1467 | 0.16482 | 16.21 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 611 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5533 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019614
2154 | Task(Task)-->C (Construction) | PLINTH BEAM |  | 1.15.3.1 | PLINTH BEAM-->CIVIL-->CONSTRUCTION-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-17 09:00 | 2020-09-04 18:00 | 2020-12-14 09:00 | 2021-02-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 2.4762 | 0.026945 | 2.65 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5534 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019615
2155 | Task(Task)-->C (Construction) | PULL PIT & GRADE SLAB FOR GROUND FLOOR |  | 1.15.3.1 | PULL PIT & GRADE SLAB FOR GROUND FLOOR-->CIVIL-->CONSTRUCTION-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-16 | 2020-09-24 18:00 | 2021-01-13 09:00 | 2021-02-21 23:59 | [6 empty] | 100 | 0 | [15 empty] | 16.0624 | 0.17479 | 17.19 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 918 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5535 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019616
2156 | Task(Task)-->C (Construction) | COLUMN AND SLAB OF 1ST FLOOR |  | 1.15.3.1 | COLUMN AND SLAB OF 1ST FLOOR-->CIVIL-->CONSTRUCTION-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-09-15 09:00 | 2020-10-29 18:00 | 2021-02-12 09:00 | 2021-03-28 23:59 | [6 empty] | 100 | 0 | [15 empty] | 8.6806 | 0.09446 | 9.29 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5536 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019617
2157 | Task(Task)-->C (Construction) | COLUMN AND ROOF SLAB (2ND FLOOR) |  | 1.15.3.1 | COLUMN AND ROOF SLAB (2ND FLOOR)-->CIVIL-->CONSTRUCTION-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-11-06 09:00 | 2021-01-04 18:00 | 2021-04-05 09:00 | 2021-06-03 18:00 | [6 empty] | 8.3333 | 0 | [15 empty] | 8.6806 | 0.09446 | 9.29 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5537 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019618
2158 | Task(Task)-->C (Construction) | RCC COLUMN & SLAB OF MUMTY & FOUNDATION OF FAN/ AC ETC |  | 1.15.3.1 | RCC COLUMN & SLAB OF MUMTY & FOUNDATION OF FAN/ AC ETC-->CIVIL-->CONSTRUCTION-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-01-05 09:00 | 2021-02-03 18:00 | 2021-06-04 09:00 | 2021-07-03 18:00 | [6 empty] | 0 | 0 | [15 empty] | 1.2428 | 0.013523 | 1.33 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5538 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019619
2159 | Task(Task)-->C (Construction) | BRICK WORK OF GROUND FLOOR |  | 1.15.3.1 | BRICK WORK OF GROUND FLOOR-->CIVIL-->CONSTRUCTION-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-11-27 09:00 | 2021-01-15 18:00 | 2021-04-26 09:00 | 2021-06-14 18:00 | [6 empty] | 0 | 0 | [15 empty] | 4.4197 | 0.048094 | 4.73 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5539 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019620
2160 | Task(Task)-->C (Construction) | PLASTERING OF GROUND FLOOR (IN SIDE) & HANDING OVER FOR ELECTRICAL WORKS |  | 1.15.3.1 | PLASTERING OF GROUND FLOOR (IN SIDE) & HANDING OVER FOR ELECTRICAL WORKS-->CIVIL-->CONSTRUCTION-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-12-07 09:00 | 2021-01-25 18:00 | 2021-05-06 09:00 | 2021-06-24 18:00 | [6 empty] | 0 | 0 | [15 empty] | 1.9155 | 0.020844 | 2.05 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 3698 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5540 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019621
2161 | Task(Task)-->C (Construction) | BRICK WORK OF 1ST FLOOR |  | 1.15.3.1 | BRICK WORK OF 1ST FLOOR-->CIVIL-->CONSTRUCTION-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-02-02 09:00 | 2021-04-02 18:00 | 2021-07-02 09:00 | 2021-08-30 18:00 | [6 empty] | 0 | 0 | [15 empty] | 4.4197 | 0.048094 | 4.73 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5541 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019622
2162 | Task(Task)-->C (Construction) | PLASTERING OF 1ST FLOOR (IN SIDE) |  | 1.15.3.1 | PLASTERING OF 1ST FLOOR (IN SIDE)-->CIVIL-->CONSTRUCTION-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-02-26 09:00 | 2021-04-16 18:00 | 2021-07-26 09:00 | 2021-09-13 18:00 | [6 empty] | 0 | 0 | [15 empty] | 1.9155 | 0.020844 | 2.05 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 3698 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5542 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019623
2163 | Task(Task)-->C (Construction) | PAINTING OF CEILING OF ROOF SLAB (NON-AC) & HANDING OVER FOR ELECTRICAL WORKS |  | 1.15.3.1 | PAINTING OF CEILING OF ROOF SLAB (NON-AC) & HANDING OVER FOR ELECTRICAL WORKS-->CIVIL-->CONSTRUCTION-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-04-07 09:00 | 2021-04-26 18:00 | 2021-09-04 09:00 | 2021-09-23 18:00 | [6 empty] | 0 | 0 | [15 empty] | 1.7473 | 0.019014 | 1.87 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 3698 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5543 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019624
2164 | Task(Task)-->C (Construction) | INSIDE PAINTING & FALSE CEILING (AC) & HANDING OVER FOR ELECTRICAL WORKS |  | 1.15.3.1 | INSIDE PAINTING & FALSE CEILING (AC) & HANDING OVER FOR ELECTRICAL WORKS-->CIVIL-->CONSTRUCTION-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-04-17 09:00 | 2021-05-16 23:59 | 2021-09-14 09:00 | 2021-10-13 18:00 | [6 empty] | 0 | 0 | [15 empty] | 6.4848 | 0.070565 | 6.94 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 3698 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5544 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019625
2165 | Task(Task)-->C (Construction) | TRANSFORMER FOUNDATION, TRENCH, BRICK WORK & PLASTERING ETC & HANDING OVER TO ELECTRICAL |  | 1.15.3.1 | TRANSFORMER FOUNDATION, TRENCH, BRICK WORK & PLASTERING ETC & HANDING OVER TO ELECTRICAL-->CIVIL-->CONSTRUCTION-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-09-05 09:00 | 2020-12-03 18:00 | 2021-02-02 09:00 | 2021-05-02 23:59 | [6 empty] | 74.4444 | 0 | [15 empty] | 2.4762 | 0.026945 | 2.65 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5545 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019626
2166 | Task(Task)-->C (Construction) | BALANCE BRICK WORK |  | 1.15.3.1 | BALANCE BRICK WORK-->CIVIL-->CONSTRUCTION-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-04-17 09:00 | 2021-05-16 23:59 | 2021-09-14 09:00 | 2021-10-13 18:00 | [6 empty] | 0 | 0 | [15 empty] | 3.4666 | 0.037723 | 3.71 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 235 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5546 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019627
2167 | Task(Task)-->C (Construction) | OUTSIDE PLASTERING |  | 1.15.3.1 | OUTSIDE PLASTERING-->CIVIL-->CONSTRUCTION-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-05-17 09:00 | 2021-07-15 18:00 | 2021-10-14 09:00 | 2021-12-12 23:59 | [6 empty] | 0 | 0 | [15 empty] | 3.8311 | 0.041688 | 4.1 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 7395 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5547 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019628
2168 | Task(Task)-->C (Construction) | DOOR , WINDOW, MONORAIL DOOR & ROLLING SHUTTER |  | 1.15.3.1 | DOOR , WINDOW, MONORAIL DOOR & ROLLING SHUTTER-->CIVIL-->CONSTRUCTION-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-06-16 09:00 | 2021-07-23 18:00 | 2021-11-13 09:00 | 2021-12-20 18:00 | [6 empty] | 0 | 0 | [15 empty] | 3.205 | 0.034876 | 3.43 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5548 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019629
2169 | Task(Task)-->C (Construction) | BALANCE PAINTING |  | 1.15.3.1 | BALANCE PAINTING-->CIVIL-->CONSTRUCTION-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-07-16 09:00 | 2021-08-29 23:59 | 2021-12-13 09:00 | 2022-01-26 18:00 | [6 empty] | 0 | 0 | [15 empty] | 3.4853 | 0.037926 | 3.73 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 7395 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5549 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019630
2170 | Task(Task)-->C (Construction) | ROOF WATER PROFING & RWDC PIPE |  | 1.15.3.1 | ROOF WATER PROFING & RWDC PIPE-->CIVIL-->CONSTRUCTION-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-03-04 09:00 | 2021-04-03 18:00 | 2021-08-01 | 2021-08-31 18:00 | [6 empty] | 0 | 0 | [15 empty] | 5.812 | 0.063244 | 6.22 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 1296 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5550 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019631
2171 | Task(Task)-->C (Construction) | GARLAND DRAIN & PLINTH PROTECTION |  | 1.15.3.1 | GARLAND DRAIN & PLINTH PROTECTION-->CIVIL-->CONSTRUCTION-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-07-16 09:00 | 2021-08-29 23:59 | 2021-12-13 09:00 | 2022-01-26 18:00 | [6 empty] | 0 | 0 | [15 empty] | 2.1585 | 0.023488 | 2.31 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5551 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019632
2172 | Task(Task)-->C (Construction) | ELECTRICAL & INSTRUMENTATION | 1.15.3.2 | 1.15.3 | ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-12-04 09:00 | 2021-08-29 23:59 | 2021-05-03 09:00 | 2022-01-26 18:00 | [6 empty] | 0 | 0 | [15 empty] | 6.2639 | 0.074436 | 7.32 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5256 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019633
2173 | Task(Task)-->C (Construction) | TRANSFORMERS |  | 1.15.3.2 | TRANSFORMERS-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-12-04 09:00 | 2020-12-24 18:00 | 2021-05-03 09:00 | 2021-05-23 23:59 | [6 empty] | 0 | 0 | [15 empty] | 21.0095 | 0.015639 | 1.54 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4592 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019634
2174 | Task(Task)-->C (Construction) | HT PANEL |  | 1.15.3.2 | HT PANEL-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-04-27 09:00 | 2021-05-11 18:00 | 2021-11-15 09:00 | 2021-11-29 18:00 | [6 empty] | 0 | 0 | [15 empty] | 8.5948 | 0.006398 | 0.63 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5257 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019635
2175 | Task(Task)-->C (Construction) | HT VFD |  | 1.15.3.2 | HT VFD-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-05-17 09:00 | 2021-05-18 18:00 | 2021-10-14 09:00 | 2021-10-15 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4593 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019636
2176 | Task(Task)-->C (Construction) | HT APFC |  | 1.15.3.2 | HT APFC-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-05-17 09:00 | 2021-05-17 18:00 | 2021-10-14 09:00 | 2021-10-14 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5367 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019637
2177 | Task(Task)-->C (Construction) | LT PANEL |  | 1.15.3.2 | LT PANEL-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-04-27 09:00 | 2021-05-16 23:59 | 2021-11-25 09:00 | 2021-12-14 18:00 | [6 empty] | 0 | 0 | [15 empty] | 2.3192 | 0.001726 | 0.17 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5368 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019638
2178 | Task(Task)-->C (Construction) | BATTERY, BATTERY CHARGER & UPS |  | 1.15.3.2 | BATTERY, BATTERY CHARGER & UPS-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-01-26 09:00 | 2021-02-01 18:00 | 2021-06-25 09:00 | 2021-07-01 18:00 | [6 empty] | 0 | 0 | [15 empty] | 2.1828 | 0.001625 | 0.16 | Plan & Actual | Quantity | Set | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5559 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019639
2179 | Task(Task)-->C (Construction) | CABLE TRAY |  | 1.15.3.2 | CABLE TRAY-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-01-26 09:00 | 2021-02-04 18:00 | 2021-06-25 09:00 | 2021-07-04 23:59 | [6 empty] | 0 | 0 | [15 empty] | 8.7312 | 0.006499 | 0.64 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5369 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019640
2180 | Task(Task)-->C (Construction) | POWER CABLE |  | 1.15.3.2 | POWER CABLE-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-05-19 09:00 | 2021-06-02 18:00 | 2021-12-15 09:00 | 2021-12-29 18:00 | [6 empty] | 0 | 0 | [15 empty] | 15.9618 | 0.011881 | 1.17 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 8300 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5370 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019641
2181 | Task(Task)-->C (Construction) | CONTROL CABLE |  | 1.15.3.2 | CONTROL CABLE-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-05-29 09:00 | 2021-06-02 18:00 | 2021-12-25 09:00 | 2021-12-29 18:00 | [6 empty] | 0 | 0 | [15 empty] | 12.9604 | 0.009647 | 0.95 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 6700 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5371 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019642
2182 | Task(Task)-->C (Construction) | EARTHING |  | 1.15.3.2 | EARTHING-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-05-27 09:00 | 2021-06-02 18:00 | 2021-12-23 09:00 | 2021-12-29 18:00 | [6 empty] | 0 | 0 | [15 empty] | 4.2292 | 0.003148 | 0.31 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 1377 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5372 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019643
2183 | Task(Task)-->C (Construction) | EARTH PIT |  | 1.15.3.2 | EARTH PIT-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-08-16 09:00 | 2021-08-29 23:59 | 2022-01-13 09:00 | 2022-01-26 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5373 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019644
2184 | Task(Task)-->C (Construction) | LIGHTING |  | 1.15.3.2 | LIGHTING-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-05-01 09:00 | 2021-05-07 18:00 | 2021-09-28 09:00 | 2021-10-04 18:00 | [6 empty] | 0 | 0 | [15 empty] | 24.0109 | 0.017873 | 1.76 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5374 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019645
2185 | Task(Task)-->C (Construction) | NON-MOTOR TERMINATION |  | 1.15.3.2 | NON-MOTOR TERMINATION-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-06-03 09:00 | 2021-06-04 18:00 | 2021-12-30 09:00 | 2021-12-31 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 148 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5377 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019646
2186 | Task(Task)-->C (Construction) | TESTING & CHARGING FOR LOAD & TRIAL OPERATION | 1.15.3.3 | 1.15.3 | TESTING & CHARGING FOR LOAD & TRIAL OPERATION-->CONSTRUCTION-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-06-03 09:00 | 2021-08-21 18:00 | 2021-12-30 09:00 | 2022-03-19 18:00 | [6 empty] | 0 | 0 | [15 empty] | 2.165 | 0.025727 | 2.53 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5378 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019647
2187 | Task(Task)-->C (Construction) | TRANSFORMERS (33KV/6.6KV) |  | 1.15.3.3 | TRANSFORMERS (33KV/6.6KV)-->TESTING & CHARGING FOR LOAD & TRIAL OPERATION-->CONSTRUCTION-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-06-23 09:00 | 2021-07-02 18:00 | 2022-01-19 09:00 | 2022-01-28 18:00 | [6 empty] | 0 | 0 | [15 empty] | 19.685 | 0.005064 | 0.5 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5593 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019648
2188 | Task(Task)-->C (Construction) | TRANSFORMERS (6.6KV/415V) |  | 1.15.3.3 | TRANSFORMERS (6.6KV/415V)-->TESTING & CHARGING FOR LOAD & TRIAL OPERATION-->CONSTRUCTION-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-07-23 09:00 | 2021-08-01 23:59 | 2022-02-18 09:00 | 2022-02-27 23:59 | [6 empty] | 0 | 0 | [15 empty] | 19.685 | 0.005064 | 0.5 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5594 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019649
2189 | Task(Task)-->C (Construction) | 33 KV SWBD |  | 1.15.3.3 | 33 KV SWBD-->TESTING & CHARGING FOR LOAD & TRIAL OPERATION-->CONSTRUCTION-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-06-03 09:00 | 2021-06-22 18:00 | 2021-12-30 09:00 | 2022-01-18 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5379 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019650
2190 | Task(Task)-->C (Construction) | 6.6. KV SWBD |  | 1.15.3.3 | 6.6. KV SWBD-->TESTING & CHARGING FOR LOAD & TRIAL OPERATION-->CONSTRUCTION-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-07-03 09:00 | 2021-07-22 18:00 | 2022-01-29 09:00 | 2022-02-17 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5595 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019651
2191 | Task(Task)-->C (Construction) | PMCC-3 |  | 1.15.3.3 | PMCC-3-->TESTING & CHARGING FOR LOAD & TRIAL OPERATION-->CONSTRUCTION-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-08-02 09:00 | 2021-08-21 18:00 | 2022-02-28 09:00 | 2022-03-19 18:00 | [6 empty] | 0 | 0 | [15 empty] | 60.6299 | 0.015598 | 1.54 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5380 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019652
2192 | Task(Task)-->C (Construction) | BATTERY, BATTERY CHARGER & UPS |  | 1.15.3.3 | BATTERY, BATTERY CHARGER & UPS-->TESTING & CHARGING FOR LOAD & TRIAL OPERATION-->CONSTRUCTION-->SUB STATION-3 NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-06-03 09:00 | 2021-06-09 18:00 | 2021-12-30 09:00 | 2022-01-05 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Set | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5560 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019653
2193 | Task(Task)-->E (Engineering) | PUMP HOUSE -A NEAR DUMP HOPPER | 1.16 | 1 | PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-12-17 09:00 | 2021-09-07 18:00 | 2020-01-13 09:00 | 2022-04-30 18:00 |  |  | 2020-01-13 10:57 |  |  |  | 67.5504 | 17.0277 | [15 empty] | 0.6035 | 0.6035 | 59.35 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4594 | 0 | 1 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019654
2194 | Task(Task)-->E (Engineering) | ENGINEERING | 1.16.1 | 1.16 | ENGINEERING-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-01-22 18:00 | 2020-08-21 17:40 | 2020-05-04 18:00 | 2020-10-05 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 78.4645 | [15 empty] | 18.6889 | 0.11279 | 11.09 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4595 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019655
2195 | Task(Task)-->E (Engineering) | MECHANICAL | 1.16.1.1 | 1.16.1 | MECHANICAL-->ENGINEERING-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-22 18:00 | 2020-06-11 17:40 | 2020-05-16 18:00 | 2020-09-01 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 76.0489 | [15 empty] | 50.3686 | 0.056809 | 2.05 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4596 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036119
2196 | Task(Task)-->E (Engineering) | G.A AND SCHEDULE OF ELECTRIC HOIST |  | 1.16.1.1 | G.A AND SCHEDULE OF ELECTRIC HOIST-->MECHANICAL-->ENGINEERING-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-19 23:59 | 2020-06-11 17:40 | 2020-06-30 18:00 | 2020-09-01 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1034 |  | 2020-02-13 10:27 | 7012-155-PVM-B-134 |  |  |  | A |  |  |  | 31.7073 | 0.018013 | 0.65 | Plan & Actual | Date |  | 0 | 0 | 0 | 240 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4598 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-19 23:59 | 2020-06-30 18:00 |  | 10 |  |  |  | 2020-05-01 17:40 | 2020-07-15 18:00 |  | 30 |  |  |  | 2020-05-07 17:40 | 2020-07-18 18:00 |  | 35 |  |  |  | 2020-05-14 23:59 | 2020-07-25 18:00 |  | 65 | 2020-08-19 11:04 |  |  | 2020-05-20 17:40 | 2020-08-15 18:00 |  | 80 | 2020-09-02 16:06 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-11 17:40 | 2020-08-15 18:00 |  | 100 | [122 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 64 |  |  |  |  | 101078
2197 | Task(Task)-->E (Engineering) | G.A AND SCHEDULE OF MANUAL HOIST |  | 1.16.1.1 | G.A AND SCHEDULE OF MANUAL HOIST-->MECHANICAL-->ENGINEERING-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-19 23:59 | 2020-06-11 17:40 | 2020-06-30 18:00 | 2020-09-01 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1035 |  | 2020-02-13 10:27 | 7012-155-PVM-B-135 |  |  |  | A |  |  |  | 41.9512 | 0.023832 | 0.86 | Plan & Actual | Date |  | 0 | 0 | 0 | 320 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4599 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-19 23:59 | 2020-06-30 18:00 |  | 10 |  |  |  | 2020-05-01 17:40 | 2020-07-15 18:00 |  | 30 |  |  |  | 2020-05-07 17:40 | 2020-07-18 18:00 |  | 35 |  |  |  | 2020-05-14 23:59 | 2020-07-25 18:00 |  | 65 | 2020-08-14 23:27 |  |  | 2020-05-20 17:40 | 2020-08-15 18:00 |  | 80 | 2020-09-02 16:08 | [5 empty] | 80 | 2020-09-02 16:56 | [5 empty] | 80 | 2020-09-02 16:56 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-11 17:40 | 2020-08-15 18:00 |  | 100 | [122 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 65 |  |  |  |  | 101079
2198 | Task(Task)-->E (Engineering) | PUMP HOUSE -A ARRANGEMENT ( PUMP HOUSE A) ALONG WITH PIPING LAYOUT & MS WATER TANK |  | 1.16.1.1 | PUMP HOUSE -A ARRANGEMENT ( PUMP HOUSE A) ALONG WITH PIPING LAYOUT & MS WATER TANK-->MECHANICAL-->ENGINEERING-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-22 18:00 | 2020-03-25 17:40 | 2020-05-16 18:00 | 2020-07-15 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-DS-GA-6008 |  | 2020-02-13 11:40 | 7012-155-PVM-B-038 |  |  |  | A |  |  |  | 26.3415 | 0.014964 | 0.54 | Plan & Actual | Date |  | 0 | 0 | 0 | 200 | 0 | 11.45 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4597 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-22 18:00 | 2020-05-16 18:00 |  | 10 |  |  |  | 2020-02-13 17:40 | 2020-06-06 18:00 |  | 30 |  |  |  | 2020-02-19 17:40 | 2020-06-13 18:00 |  | 35 | 2020-06-30 13:09 |  |  | 2020-02-26 23:59 | 2020-06-20 18:00 |  | 65 | 2020-08-22 12:47 |  |  | 2020-03-03 17:40 | 2020-07-11 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-25 17:40 | 2020-07-11 18:00 |  | 100 | [122 empty] | Ram Prasad Roy | [5 empty] | U - Water Media & Utility System | [16 empty] | 83 |  |  |  |  | 101097
2199 | Task(Task)-->E (Engineering) | CIVIL | 1.16.1.2 | 1.16.1 | CIVIL-->ENGINEERING-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-04-15 18:00 | 2020-08-13 17:40 | 2020-06-20 18:00 | 2020-10-05 18:00 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 83.8464 | [15 empty] | 22.3587 | 0.025218 | 0.91 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4600 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036120
2200 | Task(Task)-->E (Engineering) | Pump House-A : DESIGN CALCULATION |  | 1.16.1.2 | Pump House-A : DESIGN CALCULATION-->CIVIL-->ENGINEERING-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-15 18:00 | 2020-06-15 17:40 | 2020-07-24 09:00 | 2020-08-07 18:00 |  |  | 2020-02-21 15:37 | 2020-08-07 23:19 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0022 |  | 2020-02-13 11:42 | 7012-155-PVC-U-074 |  |  |  | A |  |  |  | 40.6593 | 0.010253 | 0.37 | Plan & Actual | Date |  | 0 | 0 | 0 | 136.02 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4605 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-15 18:00 | 2020-06-20 18:00 |  | 10 |  |  |  | 2020-05-04 17:40 | 2020-07-15 18:00 |  | 30 |  |  |  | 2020-05-11 17:40 | 2020-07-18 18:00 |  | 35 |  |  |  | 2020-05-16 23:59 | 2020-07-25 18:00 |  | 65 | 2020-08-07 23:08 |  |  | 2020-05-22 17:40 | 2020-08-15 18:00 |  | 80 | 2020-08-07 23:16 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-15 17:40 | 2020-08-29 18:00 |  | 100 | 2020-08-07 23:19 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 175 |  |  |  |  | 101185
2201 | Task(Task)-->E (Engineering) | Pump House-A : NUM & RC DETAILS (SHT 1) |  | 1.16.1.2 | Pump House-A : NUM & RC DETAILS (SHT 1)-->CIVIL-->ENGINEERING-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-15 18:00 | 2020-06-15 17:40 | 2020-06-20 18:00 | 2020-08-29 18:00 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-NR-0025 |  | 2020-02-13 11:42 | 7012-155-PVC-C-075 |  |  |  | A |  |  |  | 13.1868 | 0.003325 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 45.03 | 0 | 5.15 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4601 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-15 18:00 | 2020-06-20 18:00 |  | 10 |  |  |  | 2020-05-04 17:40 | 2020-07-15 18:00 |  | 30 |  |  |  | 2020-05-11 17:40 | 2020-07-18 18:00 |  | 35 | 2020-07-20 18:56 |  |  | 2020-05-16 23:59 | 2020-07-25 18:00 |  | 65 | 2020-08-07 23:10 |  |  | 2020-05-22 17:40 | 2020-08-15 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-15 17:40 | 2020-08-29 18:00 |  | 100 | [122 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 176 |  |  |  |  | 101186
2202 | Task(Task)-->E (Engineering) | Pump House-A : NUM & RC DETAILS (SHT 2) |  | 1.16.1.2 | Pump House-A : NUM & RC DETAILS (SHT 2)-->CIVIL-->ENGINEERING-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-15 18:00 | 2020-06-15 17:40 | 2020-07-24 09:00 | 2020-08-07 18:00 |  |  | 2020-02-21 15:37 | 2020-08-07 23:19 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-NR-0026 |  | 2020-02-13 11:42 | 7012-155-PVC-C-076 |  |  |  | A |  |  |  | 13.1868 | 0.003325 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 45.03 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4602 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-15 18:00 | 2020-06-20 18:00 |  | 10 |  |  |  | 2020-05-04 17:40 | 2020-07-15 18:00 |  | 30 |  |  |  | 2020-05-11 17:40 | 2020-07-18 18:00 |  | 35 |  |  |  | 2020-05-16 23:59 | 2020-07-25 18:00 |  | 65 | 2020-08-07 23:11 |  |  | 2020-05-22 17:40 | 2020-08-15 18:00 |  | 80 | 2020-08-07 23:17 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-15 17:40 | 2020-08-29 18:00 |  | 100 | 2020-08-07 23:20 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 177 |  |  |  |  | 101187
2203 | Task(Task)-->E (Engineering) | Pump House-A : NUM & RC DETAILS (SHT 3) |  | 1.16.1.2 | Pump House-A : NUM & RC DETAILS (SHT 3)-->CIVIL-->ENGINEERING-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-15 18:00 | 2020-06-15 17:40 | 2020-06-20 18:00 | 2020-08-29 18:00 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-NR-0027 |  | 2020-02-13 11:42 | 7012-155-PVC-C-077 |  |  |  | A |  |  |  | 13.1868 | 0.003325 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 45.03 | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4603 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-15 18:00 | 2020-06-20 18:00 |  | 10 |  |  |  | 2020-05-04 17:40 | 2020-07-15 18:00 |  | 30 |  |  |  | 2020-05-11 17:40 | 2020-07-18 18:00 |  | 35 | 2020-11-05 17:42 |  |  | 2020-05-16 23:59 | 2020-07-25 18:00 |  | 65 | 2020-11-05 17:45 |  |  | 2020-05-22 17:40 | 2020-08-15 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-15 17:40 | 2020-08-29 18:00 |  | 100 | [122 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 178 |  |  |  |  | 101188
2204 | Task(Task)-->E (Engineering) | ARCHITECTURAL GA OF PUMP HOUSE A |  | 1.16.1.2 | ARCHITECTURAL GA OF PUMP HOUSE A-->CIVIL-->ENGINEERING-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-14 23:59 | 2020-08-13 17:40 | 2020-07-27 18:00 | 2020-10-05 18:00 |  |  | 2020-02-21 15:39 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-AR-0008 |  | 2020-02-13 11:43 | 7012-155-PVC-C-114 |  |  |  | A |  |  |  | 19.7802 | 0.004988 | 0.18 | Plan & Actual | Date |  | 0 | 0 | 0 | 68.01 | 0 | 54 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4604 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-06-14 23:59 | 2020-07-27 18:00 |  | 10 |  |  |  | 2020-07-02 17:40 | 2020-08-21 18:00 |  | 30 |  |  |  | 2020-07-08 17:40 | 2020-08-24 18:00 |  | 35 | 2020-09-03 17:09 |  |  | 2020-07-15 23:59 | 2020-08-31 18:00 |  | 65 | 2020-09-06 16:08 |  |  | 2020-07-21 17:40 | 2020-09-21 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-08-13 17:40 | 2020-10-05 18:00 |  | 100 | [122 empty] | Chetan Khodke | [5 empty] | A - Architecture | [16 empty] | 215 |  |  |  |  | 101225
2205 | Task(Task)-->E (Engineering) | ELECTRICAL | 1.16.1.3 | 1.16.1 | ELECTRICAL-->ENGINEERING-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-06 18:00 | 2020-08-21 17:40 | 2020-05-04 18:00 | 2020-08-21 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 78.5136 | [15 empty] | 27.2727 | 0.03076 | 1.11 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4606 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036121
2206 | Task(Task)-->E (Engineering) | GA, DATA SHEET, WIRING DIAGRAM & BOM OF ELECTRIC HOIST FOR CHP. |  | 1.16.1.3 | GA, DATA SHEET, WIRING DIAGRAM & BOM OF ELECTRIC HOIST FOR CHP.-->ELECTRICAL-->ENGINEERING-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-10 17:40 | 2020-08-21 17:40 | 2020-07-11 18:00 | 2020-08-21 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-407 |  | 2020-02-13 11:47 | 7012-155-PVE-W-143 |  |  |  | A |  |  |  | 9.9099 | 0.003048 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4609 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-07-11 18:00 | 2020-07-11 18:00 |  | 10 |  |  |  | 2020-07-10 17:40 | 2020-07-18 18:00 |  | 30 |  |  |  | 2020-07-17 17:40 | 2020-07-23 18:00 |  | 35 |  |  |  | 2020-07-23 23:59 | 2020-07-23 18:00 |  | 65 | 2020-10-07 15:52 |  |  | 2020-07-30 17:40 | 2020-08-13 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-08-21 17:40 | 2020-08-13 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 378 |  |  |  |  | 101389
2207 | Task(Task)-->E (Engineering) | EQUIPMENT, CABLE ROUTING, EARTHING & LIGHTNING LAYOUT WITH PLAN, SECTIONAL VIEWS & BOM OF PUMP HOUSE-A NEAR KDTP-1 |  | 1.16.1.3 | EQUIPMENT, CABLE ROUTING, EARTHING & LIGHTNING LAYOUT WITH PLAN, SECTIONAL VIEWS & BOM OF PUMP HOUSE-A NEAR KDTP-1-->ELECTRICAL-->ENGINEERING-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-06 18:00 | 2020-05-26 17:40 | 2020-05-04 18:00 | 2020-07-02 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5057 |  | 2020-02-13 11:44 | 7012-155-PVE-F-019 |  |  |  | A |  |  |  | 60.3604 | 0.018567 | 0.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 248.42 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4607 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-06 18:00 | 2020-05-04 18:00 |  | 10 |  |  |  | 2020-04-14 17:40 | 2020-05-18 18:00 |  | 30 | 2020-06-09 11:11 |  |  | 2020-04-20 17:40 | 2020-05-25 18:00 |  | 35 | 2020-07-01 19:14 |  |  | 2020-04-27 23:59 | 2020-06-01 18:00 |  | 65 | 2020-07-28 15:41 |  |  | 2020-05-02 17:40 | 2020-06-22 18:00 |  | 80 | 2020-07-28 17:47 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-26 17:40 | 2020-06-22 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 254 |  |  |  |  | 101265
2208 | Task(Task)-->E (Engineering) | LIGHTING LAYOUT PLAN WITH POWER DISTRIBUTION ARRANGEMENT, SECTIONAL VIEW, BOM OF PUMP HOUSE-A |  | 1.16.1.3 | LIGHTING LAYOUT PLAN WITH POWER DISTRIBUTION ARRANGEMENT, SECTIONAL VIEW, BOM OF PUMP HOUSE-A-->ELECTRICAL-->ENGINEERING-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-17 18:00 | 2020-06-06 17:40 | 2020-05-12 18:00 | 2020-07-06 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5068 |  | 2020-02-13 11:44 | 7012-155-PVE-G-030 |  |  |  | A |  |  |  | 29.7297 | 0.009145 | 0.33 | Plan & Actual | Date |  | 0 | 0 | 0 | 124.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4608 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-17 18:00 | 2020-05-12 18:00 |  | 10 |  |  |  | 2020-04-27 17:40 | 2020-05-19 18:00 |  | 30 |  |  |  | 2020-05-02 17:40 | 2020-05-26 18:00 |  | 35 |  |  |  | 2020-05-08 23:59 | 2020-06-02 18:00 |  | 65 | 2020-08-03 12:06 |  |  | 2020-05-15 17:40 | 2020-06-23 18:00 |  | 80 | 2020-08-03 13:29 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-06 17:40 | 2020-06-23 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 265 |  |  |  |  | 101276
2209 | Task(Task)-->P (Procurement) | PROCUREMENT | 1.16.2 | 1.16 | PROCUREMENT-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-12-17 09:00 | 2020-10-27 18:00 | 2020-01-13 09:00 | 2021-06-11 18:00 |  |  | 2020-01-13 10:57 |  |  |  | 100 | 24.9558 | [15 empty] | 9.4708 | 0.057156 | 5.62 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4610 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019659
2210 | Task(Task)-->P (Procurement) | PURCHASE REQUISITION | 1.16.2.1 | 1.16.2 | PURCHASE REQUISITION-->PROCUREMENT-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-12-17 09:00 | 2020-03-20 18:00 | 2020-01-13 09:00 | 2020-05-29 18:00 |  |  | 2020-01-13 10:57 |  |  |  | 100 | 96.4248 | [15 empty] | 4.9911 | 0.002853 | 0.28 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4611 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019660
2211 | Task(Task)-->P (Procurement) | Building Structure |  | 1.16.2.1 | Building Structure-->PURCHASE REQUISITION-->PROCUREMENT-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-18 09:00 | 2020-03-18 18:00 | 2020-05-29 09:00 | 2020-05-29 18:00 |  |  | 2020-05-31 17:35 | 2020-05-31 17:35 |  |  | 100 | 100 | [15 empty] | 71.4286 | 0.002038 | 0.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4612 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019661
2212 | Task(Task)-->P (Procurement) | LPBS |  | 1.16.2.1 | LPBS-->PURCHASE REQUISITION-->PROCUREMENT-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-20 09:00 | 2020-03-20 18:00 | 2020-04-14 09:00 | 2020-04-14 18:00 | [6 empty] | 100 | 0 | [15 empty] | 3.5714 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4613 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019662
2213 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR UTILITY SYSTEM |  | 1.16.2.1 | LT AC MOTORS FOR UTILITY SYSTEM-->PURCHASE REQUISITION-->PROCUREMENT-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-17 09:00 | 2019-12-17 18:00 | 2020-01-13 09:00 | 2020-01-13 18:00 |  |  | 2020-01-13 10:57 | 2020-01-13 10:57 |  |  | 100 | 100 | [15 empty] | 25 | 0.000713 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4614 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019663
2214 | Task(Task)-->P (Procurement) | TECHNICAL CLEARANCE | 1.16.2.2 | 1.16.2 | TECHNICAL CLEARANCE-->PROCUREMENT-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-12-18 09:00 | 2020-04-04 18:00 | 2020-01-13 09:00 | 2020-06-12 18:00 |  |  | 2020-04-11 10:57 |  |  |  | 100 | 96.4248 | [15 empty] | 4.9911 | 0.002853 | 0.28 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4615 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019664
2215 | Task(Task)-->P (Procurement) | Building Structure |  | 1.16.2.2 | Building Structure-->TECHNICAL CLEARANCE-->PROCUREMENT-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-19 09:00 | 2020-03-25 18:00 | 2020-05-29 09:00 | 2020-05-29 18:00 |  |  | 2020-05-29 17:31 | 2020-05-29 17:31 |  |  | 100 | 100 | [15 empty] | 71.4286 | 0.002038 | 0.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4616 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019665
2216 | Task(Task)-->P (Procurement) | LPBS |  | 1.16.2.2 | LPBS-->TECHNICAL CLEARANCE-->PROCUREMENT-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-21 09:00 | 2020-04-04 18:00 | 2020-04-14 09:00 | 2020-06-12 18:00 | [6 empty] | 100 | 0 | [15 empty] | 3.5714 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4617 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019666
2217 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR UTILITY SYSTEM |  | 1.16.2.2 | LT AC MOTORS FOR UTILITY SYSTEM-->TECHNICAL CLEARANCE-->PROCUREMENT-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-18 09:00 | 2020-01-01 18:00 | 2020-01-13 09:00 | 2020-04-11 18:00 |  |  | 2020-04-11 10:57 | 2020-04-11 10:57 |  |  | 100 | 100 | [15 empty] | 25 | 0.000713 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4618 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019667
2218 | Task(Task)-->P (Procurement) | ORDERING | 1.16.2.3 | 1.16.2 | ORDERING-->PROCUREMENT-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-01-02 09:00 | 2020-04-24 18:00 | 2020-04-11 09:00 | 2020-08-19 18:00 |  |  | 2020-04-12 15:47 |  |  |  | 100 | 96.4242 | [15 empty] | 9.9822 | 0.005705 | 0.56 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4619 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019668
2219 | Task(Task)-->P (Procurement) | Building Structure |  | 1.16.2.3 | Building Structure-->ORDERING-->PROCUREMENT-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-26 09:00 | 2020-04-24 18:00 | 2020-05-29 09:00 | 2020-05-31 23:59 |  |  | 2020-05-31 17:38 | 2020-05-31 17:39 |  |  | 100 | 100 | [15 empty] | 71.4286 | 0.004075 | 0.4 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4620 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019669
2220 | Task(Task)-->P (Procurement) | LPBS |  | 1.16.2.3 | LPBS-->ORDERING-->PROCUREMENT-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-05 | 2020-04-20 18:00 | 2020-06-12 09:00 | 2020-08-19 18:00 | [6 empty] | 100 | 0 | [15 empty] | 3.5714 | 0.000204 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4621 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019670
2221 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR UTILITY SYSTEM |  | 1.16.2.3 | LT AC MOTORS FOR UTILITY SYSTEM-->ORDERING-->PROCUREMENT-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-02 09:00 | 2020-01-16 18:00 | 2020-04-11 09:00 | 2020-07-20 18:00 |  |  | 2020-04-12 15:47 | 2020-06-20 15:47 |  |  | 100 | 100 | [15 empty] | 25 | 0.001426 | 0.14 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4622 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019671
2222 | Task(Task)-->P (Procurement) | ITP APPROVAL | 1.16.2.4 | 1.16.2 | ITP APPROVAL-->PROCUREMENT-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-01-17 09:00 | 2020-05-30 18:00 | 2020-05-31 | 2020-10-14 18:00 |  |  | 2020-07-29 15:02 |  |  |  | 100 | 28.5664 | [15 empty] | 4.9911 | 0.002853 | 0.28 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4623 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019672
2223 | Task(Task)-->P (Procurement) | Building Structure |  | 1.16.2.4 | Building Structure-->ITP APPROVAL-->PROCUREMENT-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-25 09:00 | 2020-05-01 18:00 | 2020-05-31 | 2020-08-04 18:00 | [6 empty] | 100 | 0 | [15 empty] | 71.4286 | 0.002038 | 0.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4624 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019673
2224 | Task(Task)-->P (Procurement) | LPBS |  | 1.16.2.4 | LPBS-->ITP APPROVAL-->PROCUREMENT-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-21 09:00 | 2020-05-30 18:00 | 2020-07-29 09:00 | 2020-08-21 18:00 |  |  | 2020-07-29 15:02 | 2020-08-22 12:54 |  |  | 100 | 100 | [15 empty] | 3.5714 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4625 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019674
2225 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR UTILITY SYSTEM |  | 1.16.2.4 | LT AC MOTORS FOR UTILITY SYSTEM-->ITP APPROVAL-->PROCUREMENT-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-17 09:00 | 2020-02-25 18:00 | 2020-09-08 09:00 | 2020-10-14 18:00 |  |  | 2020-09-08 15:16 | 2020-10-14 15:16 |  |  | 100 | 100 | [15 empty] | 25 | 0.000713 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4626 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019675
2226 | Task(Task)-->P (Procurement) | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE | 1.16.2.5 | 1.16.2 | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-01-17 09:00 | 2020-06-04 18:00 | 2020-05-31 | 2020-09-29 18:00 |  |  | 2020-07-07 10:15 |  |  |  | 100 | 28.5781 | [15 empty] | 14.9733 | 0.008558 | 0.84 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4627 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019676
2227 | Task(Task)-->P (Procurement) | Building Structure |  | 1.16.2.5 | Building Structure-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-17 09:00 | 2020-04-23 18:00 | 2020-05-31 | 2020-09-09 18:00 | [6 empty] | 100 | 0 | [15 empty] | 71.4286 | 0.006113 | 0.6 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4628 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019677
2228 | Task(Task)-->P (Procurement) | LPBS |  | 1.16.2.5 | LPBS-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-21 09:00 | 2020-06-04 18:00 | 2020-07-25 09:00 | 2020-08-22 18:00 |  |  | 2020-07-24 18:45 | 2020-08-22 12:58 |  |  | 100 | 100 | [15 empty] | 3.5714 | 0.000306 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4629 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019678
2229 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR UTILITY SYSTEM |  | 1.16.2.5 | LT AC MOTORS FOR UTILITY SYSTEM-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-17 09:00 | 2020-03-01 23:59 | 2020-07-07 09:00 | 2020-09-29 18:00 |  |  | 2020-07-07 10:15 | 2020-09-29 14:40 |  |  | 100 | 100 | [15 empty] | 25 | 0.00214 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4630 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019679
2230 | Task(Task)-->P (Procurement) | MANUFACTURING & RECEIPT AT SITE (MRN) | 1.16.2.6 | 1.16.2 | MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-02 09:00 | 2020-10-27 18:00 | 2020-08-23 | 2021-06-11 18:00 |  |  | 2020-08-22 13:01 |  |  |  | 100 | 0 | [15 empty] | 60.0713 | 0.034334 | 3.37 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4631 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019680
2231 | Task(Task)-->P (Procurement) | Water tanks |  | 1.16.2.6 | Water tanks-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-02 09:00 | 2020-07-30 18:00 | 2020-09-09 09:00 | 2021-04-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 70.6231 | 0.024248 | 2.38 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4632 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019681
2232 | Task(Task)-->P (Procurement) | LPBS |  | 1.16.2.6 | LPBS-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-05 09:00 | 2020-09-16 18:00 | 2020-08-23 | 2020-12-04 18:00 |  |  | 2020-08-22 13:01 |  |  |  | 100 | 0 | [15 empty] | 3.8576 | 0.001324 | 0.13 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4633 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019682
2233 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR UTILITY SYSTEM |  | 1.16.2.6 | LT AC MOTORS FOR UTILITY SYSTEM-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-02 09:00 | 2020-10-27 18:00 | 2020-10-15 09:00 | 2021-06-11 18:00 |  |  | 2020-09-29 16:44 |  |  |  | 100 | 0 | [15 empty] | 25.5193 | 0.008762 | 0.86 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4634 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019683
2234 | Task(Task)-->C (Construction) | CONSTRUCTION | 1.16.3 | 1.16 | CONSTRUCTION-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-30 09:00 | 2021-09-07 18:00 | 2020-08-01 09:00 | 2022-04-30 18:00 | [6 empty] | 54.831 | 0 | [15 empty] | 71.8402 | 0.43355 | 42.63 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4635 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019684
2235 | Task(Task)-->C (Construction) | CIVIL | 1.16.3.1 | 1.16.3 | CIVIL-->CONSTRUCTION-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-30 09:00 | 2021-02-19 18:00 | 2020-08-01 09:00 | 2021-05-26 18:00 | [6 empty] | 72.322 | 0 | [15 empty] | 75.8152 | 0.3287 | 32.32 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4636 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019685
2236 | Task(Task)-->C (Construction) | AVAILABILITY OF FRONT BY NTPC |  | 1.16.3.1 | AVAILABILITY OF FRONT BY NTPC-->CIVIL-->CONSTRUCTION-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-30 09:00 | 2020-05-30 18:00 | 2020-08-01 09:00 | 2020-08-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4637 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019686
2237 | Task(Task)-->C (Construction) | EXCAVATION |  | 1.16.3.1 | EXCAVATION-->CIVIL-->CONSTRUCTION-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-06 09:00 | 2020-06-19 18:00 | 2020-08-22 09:00 | 2020-09-04 18:00 | [6 empty] | 100 | 0 | [15 empty] | 2.63 | 0.008645 | 0.85 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 3203 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4638 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | Excavation | [23 empty] | 1019687
2238 | Task(Task)-->C (Construction) | PCC |  | 1.16.3.1 | PCC-->CIVIL-->CONSTRUCTION-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-20 09:00 | 2020-06-29 18:00 | 2020-09-24 09:00 | 2020-10-03 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.95916 | 0.003153 | 0.31 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4639 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | PCC | [23 empty] | 1019688
2239 | Task(Task)-->C (Construction) | RAFT |  | 1.16.3.1 | RAFT-->CIVIL-->CONSTRUCTION-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-30 09:00 | 2020-07-24 18:00 | 2020-10-04 | 2020-10-28 18:00 | [6 empty] | 100 | 0 | [15 empty] | 6.9926 | 0.022985 | 2.26 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4640 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019689
2240 | Task(Task)-->C (Construction) | PLINTH BEAM |  | 1.16.3.1 | PLINTH BEAM-->CIVIL-->CONSTRUCTION-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-27 09:00 | 2020-08-06 18:00 | 2020-10-31 09:00 | 2020-11-10 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.8354 | 0.002746 | 0.27 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4641 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019690
2241 | Task(Task)-->C (Construction) | PUMP FOUNDATION & TRENCH |  | 1.16.3.1 | PUMP FOUNDATION & TRENCH-->CIVIL-->CONSTRUCTION-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-01 09:00 | 2020-08-16 23:59 | 2020-11-05 09:00 | 2020-11-20 18:00 | [6 empty] | 100 | 0 | [15 empty] | 1.2376 | 0.004068 | 0.4 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4642 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019691
2242 | Task(Task)-->C (Construction) | GRADE SLAB |  | 1.16.3.1 | GRADE SLAB-->CIVIL-->CONSTRUCTION-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-14 09:00 | 2020-09-13 23:59 | 2020-11-18 09:00 | 2020-12-18 18:00 | [6 empty] | 100 | 0 | [15 empty] | 40.3775 | 0.13272 | 13.05 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 697 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4643 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019692
2243 | Task(Task)-->C (Construction) | COLUMN AND ROOF SLAB |  | 1.16.3.1 | COLUMN AND ROOF SLAB-->CIVIL-->CONSTRUCTION-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-09-01 09:00 | 2020-10-13 18:00 | 2020-12-06 | 2021-01-17 23:59 | [6 empty] | 100 | 0 | [15 empty] | 2.2896 | 0.007526 | 0.74 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4644 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019693
2244 | Task(Task)-->C (Construction) | WATER TANK FOUNDATION |  | 1.16.3.1 | WATER TANK FOUNDATION-->CIVIL-->CONSTRUCTION-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-20 09:00 | 2020-11-02 18:00 | 2020-09-05 09:00 | 2021-01-18 18:00 | [6 empty] | 100 | 0 | [15 empty] | 14.604 | 0.048003 | 4.72 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 178 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4645 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019694
2245 | Task(Task)-->C (Construction) | BRICK WORK |  | 1.16.3.1 | BRICK WORK-->CIVIL-->CONSTRUCTION-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-10-14 09:00 | 2020-11-13 18:00 | 2021-01-18 09:00 | 2021-02-17 18:00 | [6 empty] | 90.3226 | 0 | [15 empty] | 2.4752 | 0.008136 | 0.8 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4646 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019695
2246 | Task(Task)-->C (Construction) | PLASTER |  | 1.16.3.1 | PLASTER-->CIVIL-->CONSTRUCTION-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-11-04 09:00 | 2020-12-04 18:00 | 2021-02-08 09:00 | 2021-03-10 18:00 | [6 empty] | 22.5806 | 0 | [15 empty] | 0.71163 | 0.002339 | 0.23 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 410 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4647 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019696
2247 | Task(Task)-->C (Construction) | DOOR , WINDOW, MONORAIL DOOR & ROLLING SHUTTER |  | 1.16.3.1 | DOOR , WINDOW, MONORAIL DOOR & ROLLING SHUTTER-->CIVIL-->CONSTRUCTION-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-11-28 09:00 | 2020-12-20 23:59 | 2021-03-04 09:00 | 2021-03-26 18:00 | [6 empty] | 0 | 0 | [15 empty] | 10.6126 | 0.034884 | 3.43 | Plan & Actual | Quantity | Lot | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4648 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019697
2248 | Task(Task)-->C (Construction) | FLOORING |  | 1.16.3.1 | FLOORING-->CIVIL-->CONSTRUCTION-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-11-28 09:00 | 2020-12-25 18:00 | 2021-03-04 09:00 | 2021-03-31 18:00 | [6 empty] | 0 | 0 | [15 empty] | 6.0644 | 0.019934 | 1.96 | Plan & Actual | Quantity | Lot | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4649 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019698
2249 | Task(Task)-->C (Construction) | ROOF WATER PROFING & RWDC PIPE |  | 1.16.3.1 | ROOF WATER PROFING & RWDC PIPE-->CIVIL-->CONSTRUCTION-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-11-11 09:00 | 2020-12-11 18:00 | 2021-02-15 09:00 | 2021-03-17 18:00 | [6 empty] | 0 | 0 | [15 empty] | 2.5371 | 0.00834 | 0.82 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 171 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4650 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019699
2250 | Task(Task)-->C (Construction) | GARLAND DRAIN & PLINTH PROTECTION |  | 1.16.3.1 | GARLAND DRAIN & PLINTH PROTECTION-->CIVIL-->CONSTRUCTION-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-11-28 09:00 | 2021-01-09 18:00 | 2021-03-04 09:00 | 2021-04-15 18:00 | [6 empty] | 0 | 0 | [15 empty] | 7.1473 | 0.023493 | 2.31 | Plan & Actual | Quantity | Lot | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4651 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019700
2251 | Task(Task)-->C (Construction) | PAINTING |  | 1.16.3.1 | PAINTING-->CIVIL-->CONSTRUCTION-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-12-21 09:00 | 2021-02-19 18:00 | 2021-03-27 09:00 | 2021-05-26 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0.52599 | 0.001729 | 0.17 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 342 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4652 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019701
2252 | Task(Task)-->C (Construction) | MECHANICAL | 1.16.3.2 | 1.16.3 | MECHANICAL-->CONSTRUCTION-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-12-01 09:00 | 2021-06-08 18:00 | 2021-03-18 09:00 | 2021-06-06 23:59 | [6 empty] | 0 | 0 | [15 empty] | 13.6289 | 0.059089 | 5.81 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4653 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019702
2253 | Task(Task)-->C (Construction) | WATER TANKS |  | 1.16.3.2 | WATER TANKS-->MECHANICAL-->CONSTRUCTION-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-12-01 09:00 | 2021-01-29 18:00 | 2021-04-02 09:00 | 2021-05-31 18:00 | [6 empty] | 0 | 0 | [15 empty] | 90.8778 | 0.053699 | 5.28 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4654 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019703
2254 | Task(Task)-->C (Construction) | ERECTION OF MONORAIL & HOISTS |  | 1.16.3.2 | ERECTION OF MONORAIL & HOISTS-->MECHANICAL-->CONSTRUCTION-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-03-20 09:00 | 2021-04-09 18:00 | 2021-03-18 09:00 | 2021-04-07 18:00 | [6 empty] | 0 | 0 | [15 empty] | 4.475 | 0.002644 | 0.26 | Plan & Actual | Quantity | Set | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5480 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019704
2255 | Task(Task)-->C (Construction) | ERECTION OF PUMPS |  | 1.16.3.2 | ERECTION OF PUMPS-->MECHANICAL-->CONSTRUCTION-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-04-10 09:00 | 2021-06-08 18:00 | 2021-04-08 09:00 | 2021-06-06 23:59 | [6 empty] | 0 | 0 | [15 empty] | 4.6472 | 0.002746 | 0.27 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4655 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019705
2256 | Task(Task)-->C (Construction) | ELECTRICAL & INSTRUMENTATION | 1.16.3.3 | 1.16.3 | ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-12-05 09:00 | 2021-08-28 18:00 | 2021-03-11 09:00 | 2022-04-20 18:00 | [6 empty] | 0 | 0 | [15 empty] | 6.9435 | 0.030104 | 2.96 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5259 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019706
2257 | Task(Task)-->C (Construction) | CABLE TRAY |  | 1.16.3.3 | CABLE TRAY-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-12-05 09:00 | 2020-12-06 23:59 | 2021-03-11 09:00 | 2021-03-12 18:00 | [6 empty] | 0 | 0 | [15 empty] | 7.1186 | 0.002143 | 0.21 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4656 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019707
2258 | Task(Task)-->C (Construction) | POWER CABLE |  | 1.16.3.3 | POWER CABLE-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-06-09 09:00 | 2021-06-15 18:00 | 2021-07-25 | 2021-07-31 18:00 | [6 empty] | 0 | 0 | [15 empty] | 10.5085 | 0.003163 | 0.31 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 2220 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5258 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019708
2259 | Task(Task)-->C (Construction) | CONTROL CABLE |  | 1.16.3.3 | CONTROL CABLE-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-06-13 | 2021-06-15 18:00 | 2021-10-26 09:00 | 2021-10-28 18:00 | [6 empty] | 0 | 0 | [15 empty] | 16.9492 | 0.005102 | 0.5 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4657 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019709
2260 | Task(Task)-->C (Construction) | EARTHING |  | 1.16.3.3 | EARTHING-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-06-13 | 2021-06-15 18:00 | 2021-07-29 09:00 | 2021-07-31 18:00 | [6 empty] | 0 | 0 | [15 empty] | 2.7119 | 0.000816 | 0.08 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 377 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5381 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019710
2261 | Task(Task)-->C (Construction) | EARTH PIT |  | 1.16.3.3 | EARTH PIT-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-01-07 09:00 | 2021-01-09 18:00 | 2021-04-13 09:00 | 2021-04-15 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5382 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019711
2262 | Task(Task)-->C (Construction) | LIGHTING |  | 1.16.3.3 | LIGHTING-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-12-05 09:00 | 2020-12-11 18:00 | 2021-03-11 09:00 | 2021-03-17 18:00 | [6 empty] | 0 | 0 | [15 empty] | 10.5085 | 0.003163 | 0.31 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5383 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019712
2263 | Task(Task)-->C (Construction) | FIELD INTRUMENTS |  | 1.16.3.3 | FIELD INTRUMENTS-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-06-12 09:00 | 2021-06-16 18:00 | 2021-10-25 09:00 | 2021-10-29 18:00 | [6 empty] | 0 | 0 | [15 empty] | 52.2034 | 0.015715 | 1.54 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5384 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019713
2264 | Task(Task)-->C (Construction) | MOTOR TERMINATION |  | 1.16.3.3 | MOTOR TERMINATION-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-06-16 09:00 | 2021-06-19 18:00 | 2021-10-26 09:00 | 2021-10-29 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5385 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019714
2265 | Task(Task)-->C (Construction) | NO LOAD RUN OF MOTOR |  | 1.16.3.3 | NO LOAD RUN OF MOTOR-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-08-22 | 2021-08-28 18:00 | 2022-04-14 09:00 | 2022-04-20 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5481 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019715
2266 | Task(Task)-->C (Construction) | NO LOAD COMMISSIONING & SYSTEM READYNESS FOR LOAD & TRIAL OPERATION |  | 1.16.3 | NO LOAD COMMISSIONING & SYSTEM READYNESS FOR LOAD & TRIAL OPERATION-->CONSTRUCTION-->PUMP HOUSE -A NEAR DUMP HOPPER-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-08-29 | 2021-09-07 18:00 | 2022-04-21 09:00 | 2022-04-30 18:00 | [6 empty] | 0 | 0 | [15 empty] | 3.6125 | 0.015662 | 1.54 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5386 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019716
2267 | Task(Task)-->E (Engineering) | PUMP HOUSE -B NEAR KDTP-2 | 1.17 | 1 | PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-12-17 09:00 | 2021-09-13 18:00 | 2020-01-13 09:00 | 2022-05-06 18:00 |  |  | 2020-01-13 10:57 |  |  |  | 57.3555 | 10.8922 | [15 empty] | 0.36789 | 0.3679 | 36.18 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4658 | 0 | 1 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019717
2268 | Task(Task)-->E (Engineering) | ENGINEERING | 1.17.1 | 1.17 | ENGINEERING-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-01-22 18:00 | 2020-08-14 17:40 | 2020-05-06 18:00 | 2020-10-05 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 79.8206 | [15 empty] | 8.7894 | 0.032336 | 3.18 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4659 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019718
2269 | Task(Task)-->E (Engineering) | MECHANICAL | 1.17.1.1 | 1.17.1 | MECHANICAL-->ENGINEERING-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-22 18:00 | 2020-03-25 17:40 | 2020-05-22 18:00 | 2020-07-17 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 65 | [15 empty] | 24.2152 | 0.00783 | 0.54 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4660 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036122
2270 | Task(Task)-->E (Engineering) | PUMP HOUSE -2 ARRANGEMENT ( PUMP HOUSE B) ALONG WITH PIPING LAYOUT & MS WATER TANK |  | 1.17.1.1 | PUMP HOUSE -2 ARRANGEMENT ( PUMP HOUSE B) ALONG WITH PIPING LAYOUT & MS WATER TANK-->MECHANICAL-->ENGINEERING-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-22 18:00 | 2020-03-25 17:40 | 2020-05-22 18:00 | 2020-07-17 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-DS-GA-6009 |  | 2020-02-13 11:40 | 7012-155-PVM-B-039 |  |  |  | A |  |  |  | 100 | 0.00783 | 0.54 | Plan & Actual | Date |  | 0 | 0 | 0 | 200 | 0 | 11.1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4661 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-22 18:00 | 2020-05-22 18:00 |  | 10 |  |  |  | 2020-02-13 17:40 | 2020-06-12 18:00 |  | 30 |  |  |  | 2020-02-19 17:40 | 2020-06-19 18:00 |  | 35 | 2020-06-19 09:46 |  |  | 2020-02-26 23:59 | 2020-06-26 18:00 |  | 65 | 2020-06-19 17:16 |  |  | 2020-03-03 17:40 | 2020-07-17 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-25 17:40 | 2020-07-17 18:00 |  | 100 | [122 empty] | Ram Prasad Roy | [5 empty] | U - Water Media & Utility System | [16 empty] | 84 |  |  |  |  | 101098
2271 | Task(Task)-->E (Engineering) | CIVIL | 1.17.1.2 | 1.17.1 | CIVIL-->ENGINEERING-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-04-16 18:00 | 2020-08-14 17:40 | 2020-06-26 18:00 | 2020-10-05 18:00 |  |  | 2020-02-21 15:37 |  |  |  | 100 | 88.4615 | [15 empty] | 40.8072 | 0.013195 | 0.91 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4664 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036123
2272 | Task(Task)-->E (Engineering) | Pump House-B : DESIGN CALCULATION |  | 1.17.1.2 | Pump House-B : DESIGN CALCULATION-->CIVIL-->ENGINEERING-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-16 18:00 | 2020-06-15 17:40 | 2020-07-28 09:00 | 2020-08-17 18:00 |  |  | 2020-02-21 15:37 | 2020-08-17 22:44 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0023 |  | 2020-02-13 11:42 | 7012-155-PVC-U-078 |  |  |  | A |  |  |  | 40.6593 | 0.005365 | 0.37 | Plan & Actual | Date |  | 0 | 0 | 0 | 136.02 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4669 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-16 18:00 | 2020-06-26 18:00 |  | 10 |  |  |  | 2020-05-05 17:40 | 2020-07-21 18:00 |  | 30 |  |  |  | 2020-05-12 17:40 | 2020-07-24 18:00 |  | 35 |  |  |  | 2020-05-17 23:59 | 2020-07-31 18:00 |  | 65 | 2020-08-13 19:56 |  |  | 2020-05-22 17:40 | 2020-08-21 18:00 |  | 80 | 2020-08-17 22:40 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-15 17:40 | 2020-09-04 18:00 |  | 100 | 2020-08-17 22:45 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 179 |  |  |  |  | 101189
2273 | Task(Task)-->E (Engineering) | Pump House-B : NUM & RC DETAILS (SHT 1) |  | 1.17.1.2 | Pump House-B : NUM & RC DETAILS (SHT 1)-->CIVIL-->ENGINEERING-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-16 18:00 | 2020-06-15 17:40 | 2020-07-28 09:00 | 2020-08-17 18:00 |  |  | 2020-02-21 15:37 | 2020-08-17 22:44 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-NR-0028 |  | 2020-02-13 11:42 | 7012-155-PVC-C-079 |  |  |  | A |  |  |  | 13.1868 | 0.00174 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 45.03 | 0 | 5.1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4665 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-16 18:00 | 2020-06-26 18:00 |  | 10 |  |  |  | 2020-05-05 17:40 | 2020-07-21 18:00 |  | 30 |  |  |  | 2020-05-12 17:40 | 2020-07-24 18:00 |  | 35 | 2020-07-26 10:51 |  |  | 2020-05-17 23:59 | 2020-07-31 18:00 |  | 65 | 2020-08-13 19:56 |  |  | 2020-05-22 17:40 | 2020-08-21 18:00 |  | 80 | 2020-08-17 22:39 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-15 17:40 | 2020-09-04 18:00 |  | 100 | 2020-08-17 22:45 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 180 |  |  |  |  | 101190
2274 | Task(Task)-->E (Engineering) | Pump House-B : NUM & RC DETAILS (SHT 2) |  | 1.17.1.2 | Pump House-B : NUM & RC DETAILS (SHT 2)-->CIVIL-->ENGINEERING-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-16 18:00 | 2020-06-15 17:40 | 2020-07-28 09:00 | 2020-08-17 18:00 |  |  | 2020-02-21 15:37 | 2020-08-17 22:44 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-NR-0029 |  | 2020-02-13 11:42 | 7012-155-PVC-C-080 |  |  |  | A |  |  |  | 13.1868 | 0.00174 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 45.03 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4666 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-16 18:00 | 2020-06-26 18:00 |  | 10 |  |  |  | 2020-05-05 17:40 | 2020-07-21 18:00 |  | 30 |  |  |  | 2020-05-12 17:40 | 2020-07-24 18:00 |  | 35 |  |  |  | 2020-05-17 23:59 | 2020-07-31 18:00 |  | 65 | 2020-08-13 19:56 |  |  | 2020-05-22 17:40 | 2020-08-21 18:00 |  | 80 | 2020-08-17 22:36 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-15 17:40 | 2020-09-04 18:00 |  | 100 | 2020-08-17 22:45 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 181 |  |  |  |  | 101191
2275 | Task(Task)-->E (Engineering) | Pump House-B : NUM & RC DETAILS (SHT 3) |  | 1.17.1.2 | Pump House-B : NUM & RC DETAILS (SHT 3)-->CIVIL-->ENGINEERING-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-16 18:00 | 2020-06-15 17:40 | 2020-06-26 18:00 | 2020-09-04 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-NR-0030 |  | 2020-02-13 11:42 | 7012-155-PVC-C-081 |  |  |  | A |  |  |  | 13.1868 | 0.00174 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 45.03 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4667 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-16 18:00 | 2020-06-26 18:00 |  | 10 |  |  |  | 2020-05-05 17:40 | 2020-07-21 18:00 |  | 30 |  |  |  | 2020-05-12 17:40 | 2020-07-24 18:00 |  | 35 | 2020-11-09 18:50 |  |  | 2020-05-17 23:59 | 2020-07-31 18:00 |  | 65 | 2020-11-09 21:02 |  |  | 2020-05-22 17:40 | 2020-08-21 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-15 17:40 | 2020-09-04 18:00 |  | 100 | [122 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 182 |  |  |  |  | 101192
2276 | Task(Task)-->E (Engineering) | ARCHITECTURAL GA OF PUMP HOUSE B |  | 1.17.1.2 | ARCHITECTURAL GA OF PUMP HOUSE B-->CIVIL-->ENGINEERING-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-15 18:00 | 2020-08-14 17:40 | 2020-07-27 18:00 | 2020-10-05 18:00 |  |  | 2020-02-21 15:39 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-AR-0009 |  | 2020-02-13 11:43 | 7012-155-PVC-C-115 |  |  |  | A |  |  |  | 19.7802 | 0.00261 | 0.18 | Plan & Actual | Date |  | 0 | 0 | 0 | 68.01 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4668 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-06-15 18:00 | 2020-07-27 18:00 |  | 10 |  |  |  | 2020-07-03 17:40 | 2020-08-21 18:00 |  | 30 |  |  |  | 2020-07-09 17:40 | 2020-08-24 18:00 |  | 35 | 2020-09-14 12:35 |  |  | 2020-07-16 23:59 | 2020-08-31 18:00 |  | 65 | 2020-09-14 20:16 |  |  | 2020-07-22 17:40 | 2020-09-21 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-08-14 17:40 | 2020-10-05 18:00 |  | 100 | [122 empty] | Chetan Khodke | [5 empty] | A - Architecture | [16 empty] | 216 |  |  |  |  | 101226
2277 | Task(Task)-->E (Engineering) | ELECTRICAL | 1.17.1.3 | 1.17.1 | ELECTRICAL-->ENGINEERING-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-23 18:00 | 2020-06-19 17:40 | 2020-05-06 18:00 | 2020-07-06 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 | [15 empty] | 34.9776 | 0.01131 | 0.78 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4670 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036124
2278 | Task(Task)-->E (Engineering) | EQUIPMENT, CABLE ROUTING, EARTHING & LIGHTNING LAYOUT WITH PLAN, SECTIONAL VIEWS & BOM OF PUMP HOUSE-B NEAR KDTP-2 |  | 1.17.1.3 | EQUIPMENT, CABLE ROUTING, EARTHING & LIGHTNING LAYOUT WITH PLAN, SECTIONAL VIEWS & BOM OF PUMP HOUSE-B NEAR KDTP-2-->ELECTRICAL-->ENGINEERING-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-23 18:00 | 2020-06-11 17:40 | 2020-05-06 18:00 | 2020-07-01 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5058 |  | 2020-02-13 11:44 | 7012-155-PVE-F-020 |  |  |  | A |  |  |  | 57.6923 | 0.006525 | 0.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 165.48 | 0 | 33.47 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4671 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-23 18:00 | 2020-05-06 18:00 |  | 10 |  |  |  | 2020-05-01 17:40 | 2020-05-20 18:00 |  | 30 | 2020-06-19 10:07 |  |  | 2020-05-07 17:40 | 2020-05-27 18:00 |  | 35 | 2020-06-23 14:41 |  |  | 2020-05-14 23:59 | 2020-06-03 18:00 |  | 65 | 2020-08-03 11:20 |  |  | 2020-05-20 17:40 | 2020-06-24 18:00 |  | 80 | 2020-08-03 11:27 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-11 17:40 | 2020-06-24 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 255 |  |  |  |  | 101266
2279 | Task(Task)-->E (Engineering) | LIGHTING LAYOUT PLAN WITH POWER DISTRIBUTION ARRANGEMENT, SECTIONAL VIEW, BOM OF PUMP HOUSE-B |  | 1.17.1.3 | LIGHTING LAYOUT PLAN WITH POWER DISTRIBUTION ARRANGEMENT, SECTIONAL VIEW, BOM OF PUMP HOUSE-B-->ELECTRICAL-->ENGINEERING-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-30 18:00 | 2020-06-19 17:40 | 2020-05-20 18:00 | 2020-07-06 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5069 |  | 2020-02-13 11:44 | 7012-155-PVE-G-031 |  |  |  | A |  |  |  | 42.3077 | 0.004785 | 0.33 | Plan & Actual | Date |  | 0 | 0 | 0 | 124.21 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4672 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-30 18:00 | 2020-05-20 18:00 |  | 10 |  |  |  | 2020-05-08 17:40 | 2020-05-27 18:00 |  | 30 | 2020-07-20 12:23 |  |  | 2020-05-15 17:40 | 2020-06-03 18:00 |  | 35 |  |  |  | 2020-05-21 23:59 | 2020-06-10 18:00 |  | 65 | 2020-07-20 12:36 |  |  | 2020-05-28 17:40 | 2020-07-01 18:00 |  | 80 | 2020-07-28 17:53 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-19 17:40 | 2020-07-01 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 266 |  |  |  |  | 101277
2280 | Task(Task)-->P (Procurement) | PROCUREMENT | 1.17.2 | 1.17 | PROCUREMENT-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-12-17 09:00 | 2020-10-27 18:00 | 2020-01-13 09:00 | 2021-06-11 18:00 |  |  | 2020-01-13 10:57 |  |  |  | 100 | 24.9549 | [15 empty] | 15.5334 | 0.057147 | 5.62 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4674 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019722
2281 | Task(Task)-->P (Procurement) | PURCHASE REQUISITION | 1.17.2.1 | 1.17.2 | PURCHASE REQUISITION-->PROCUREMENT-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-12-17 09:00 | 2020-03-20 18:00 | 2020-01-13 09:00 | 2020-05-29 18:00 |  |  | 2020-01-13 10:57 |  |  |  | 100 | 96.4236 | [15 empty] | 4.9911 | 0.002852 | 0.28 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4675 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019723
2282 | Task(Task)-->P (Procurement) | Building Structure |  | 1.17.2.1 | Building Structure-->PURCHASE REQUISITION-->PROCUREMENT-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-18 09:00 | 2020-03-18 18:00 | 2020-05-29 09:00 | 2020-05-29 18:00 |  |  | 2020-05-31 17:35 | 2020-05-31 17:35 |  |  | 100 | 100 | [15 empty] | 71.4286 | 0.002037 | 0.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4676 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019724
2283 | Task(Task)-->P (Procurement) | LPBS |  | 1.17.2.1 | LPBS-->PURCHASE REQUISITION-->PROCUREMENT-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-20 09:00 | 2020-03-20 18:00 | 2020-04-14 09:00 | 2020-04-14 18:00 | [6 empty] | 100 | 0 | [15 empty] | 3.5714 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4677 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019725
2284 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR UTILITY SYSTEM |  | 1.17.2.1 | LT AC MOTORS FOR UTILITY SYSTEM-->PURCHASE REQUISITION-->PROCUREMENT-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-17 09:00 | 2019-12-17 18:00 | 2020-01-13 09:00 | 2020-01-13 18:00 |  |  | 2020-01-13 10:57 | 2020-01-13 10:57 |  |  | 100 | 100 | [15 empty] | 25 | 0.000713 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4678 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019726
2285 | Task(Task)-->P (Procurement) | TECHNICAL CLEARANCE | 1.17.2.2 | 1.17.2 | TECHNICAL CLEARANCE-->PROCUREMENT-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-12-18 09:00 | 2020-04-04 18:00 | 2020-01-13 09:00 | 2020-06-12 18:00 |  |  | 2020-04-11 10:57 |  |  |  | 100 | 96.4236 | [15 empty] | 4.9911 | 0.002852 | 0.28 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4679 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019727
2286 | Task(Task)-->P (Procurement) | Building Structure |  | 1.17.2.2 | Building Structure-->TECHNICAL CLEARANCE-->PROCUREMENT-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-19 09:00 | 2020-03-25 18:00 | 2020-05-29 09:00 | 2020-05-29 18:00 |  |  | 2020-05-29 17:31 | 2020-05-29 17:31 |  |  | 100 | 100 | [15 empty] | 71.4286 | 0.002037 | 0.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4680 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019728
2287 | Task(Task)-->P (Procurement) | LPBS |  | 1.17.2.2 | LPBS-->TECHNICAL CLEARANCE-->PROCUREMENT-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-21 09:00 | 2020-04-04 18:00 | 2020-04-14 09:00 | 2020-06-12 18:00 | [6 empty] | 100 | 0 | [15 empty] | 3.5714 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4681 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019729
2288 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR UTILITY SYSTEM |  | 1.17.2.2 | LT AC MOTORS FOR UTILITY SYSTEM-->TECHNICAL CLEARANCE-->PROCUREMENT-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-18 09:00 | 2020-01-01 18:00 | 2020-01-13 09:00 | 2020-04-11 18:00 |  |  | 2020-04-11 10:57 | 2020-04-11 10:57 |  |  | 100 | 100 | [15 empty] | 25 | 0.000713 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4682 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019730
2289 | Task(Task)-->P (Procurement) | ORDERING | 1.17.2.3 | 1.17.2 | ORDERING-->PROCUREMENT-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-01-02 09:00 | 2020-04-24 18:00 | 2020-04-11 09:00 | 2020-08-19 18:00 |  |  | 2020-04-12 15:47 |  |  |  | 100 | 96.4242 | [15 empty] | 9.9822 | 0.005705 | 0.56 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4683 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019731
2290 | Task(Task)-->P (Procurement) | Building Structure |  | 1.17.2.3 | Building Structure-->ORDERING-->PROCUREMENT-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-26 09:00 | 2020-04-24 18:00 | 2020-05-29 09:00 | 2020-05-31 23:59 |  |  | 2020-05-31 17:39 | 2020-05-31 17:39 |  |  | 100 | 100 | [15 empty] | 71.4286 | 0.004075 | 0.4 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4684 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019732
2291 | Task(Task)-->P (Procurement) | LPBS |  | 1.17.2.3 | LPBS-->ORDERING-->PROCUREMENT-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-05 | 2020-04-20 18:00 | 2020-06-12 09:00 | 2020-08-19 18:00 | [6 empty] | 100 | 0 | [15 empty] | 3.5714 | 0.000204 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4685 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019733
2292 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR UTILITY SYSTEM |  | 1.17.2.3 | LT AC MOTORS FOR UTILITY SYSTEM-->ORDERING-->PROCUREMENT-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-02 09:00 | 2020-01-16 18:00 | 2020-04-11 09:00 | 2020-07-20 18:00 |  |  | 2020-04-12 15:47 | 2020-06-20 15:47 |  |  | 100 | 100 | [15 empty] | 25 | 0.001426 | 0.14 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4686 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019734
2293 | Task(Task)-->P (Procurement) | ITP APPROVAL | 1.17.2.4 | 1.17.2 | ITP APPROVAL-->PROCUREMENT-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-01-17 09:00 | 2020-05-30 18:00 | 2020-05-31 | 2020-10-14 18:00 |  |  | 2020-07-29 15:03 |  |  |  | 100 | 28.5764 | [15 empty] | 4.9911 | 0.002852 | 0.28 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4687 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019735
2294 | Task(Task)-->P (Procurement) | Building Structure |  | 1.17.2.4 | Building Structure-->ITP APPROVAL-->PROCUREMENT-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-25 09:00 | 2020-05-01 18:00 | 2020-05-31 | 2020-08-04 18:00 | [6 empty] | 100 | 0 | [15 empty] | 71.4286 | 0.002037 | 0.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4688 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019736
2295 | Task(Task)-->P (Procurement) | LPBS |  | 1.17.2.4 | LPBS-->ITP APPROVAL-->PROCUREMENT-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-21 09:00 | 2020-05-30 18:00 | 2020-07-29 09:00 | 2020-08-21 18:00 |  |  | 2020-07-29 15:03 | 2020-08-22 12:55 |  |  | 100 | 100 | [15 empty] | 3.5714 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4689 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019737
2296 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR UTILITY SYSTEM |  | 1.17.2.4 | LT AC MOTORS FOR UTILITY SYSTEM-->ITP APPROVAL-->PROCUREMENT-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-17 09:00 | 2020-02-25 18:00 | 2020-09-08 09:00 | 2020-10-14 18:00 |  |  | 2020-09-08 15:17 | 2020-10-14 15:17 |  |  | 100 | 100 | [15 empty] | 25 | 0.000713 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4690 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019738
2297 | Task(Task)-->P (Procurement) | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE | 1.17.2.5 | 1.17.2 | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-01-17 09:00 | 2020-06-04 18:00 | 2020-05-31 | 2020-09-29 18:00 |  |  | 2020-07-07 10:15 |  |  |  | 100 | 28.5731 | [15 empty] | 14.9733 | 0.008557 | 0.84 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4691 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019739
2298 | Task(Task)-->P (Procurement) | Building Structure |  | 1.17.2.5 | Building Structure-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-17 09:00 | 2020-04-23 18:00 | 2020-05-31 | 2020-09-09 18:00 | [6 empty] | 100 | 0 | [15 empty] | 71.4286 | 0.006112 | 0.6 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4692 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019740
2299 | Task(Task)-->P (Procurement) | LPBS |  | 1.17.2.5 | LPBS-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-21 09:00 | 2020-06-04 18:00 | 2020-07-25 09:00 | 2020-08-22 18:00 |  |  | 2020-07-24 18:41 | 2020-08-22 12:58 |  |  | 100 | 100 | [15 empty] | 3.5714 | 0.000306 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4693 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019741
2300 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR UTILITY SYSTEM |  | 1.17.2.5 | LT AC MOTORS FOR UTILITY SYSTEM-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-17 09:00 | 2020-03-01 23:59 | 2020-07-07 09:00 | 2020-09-29 18:00 |  |  | 2020-07-07 10:15 | 2020-09-29 14:41 |  |  | 100 | 100 | [15 empty] | 25 | 0.002139 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4694 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019742
2301 | Task(Task)-->P (Procurement) | MANUFACTURING & RECEIPT AT SITE (MRN) | 1.17.2.6 | 1.17.2 | MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-02 09:00 | 2020-10-27 18:00 | 2020-08-23 | 2021-06-11 18:00 |  |  | 2020-08-22 13:01 |  |  |  | 100 | 0 | [15 empty] | 60.0713 | 0.034329 | 3.37 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4695 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019743
2302 | Task(Task)-->P (Procurement) | WATER TANK |  | 1.17.2.6 | WATER TANK-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-02 09:00 | 2020-07-30 18:00 | 2020-09-09 09:00 | 2021-04-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 70.6231 | 0.024244 | 2.38 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4696 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019744
2303 | Task(Task)-->P (Procurement) | LPBS |  | 1.17.2.6 | LPBS-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-05 09:00 | 2020-09-16 18:00 | 2020-08-23 | 2020-12-04 18:00 |  |  | 2020-08-22 13:01 |  |  |  | 100 | 0 | [15 empty] | 3.8576 | 0.001324 | 0.13 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4697 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019745
2304 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR UTILITY SYSTEM |  | 1.17.2.6 | LT AC MOTORS FOR UTILITY SYSTEM-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-02 09:00 | 2020-10-27 18:00 | 2020-10-15 09:00 | 2021-06-11 18:00 |  |  | 2020-09-29 16:44 |  |  |  | 100 | 0 | [15 empty] | 25.5193 | 0.008761 | 0.86 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4698 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019746
2305 | Task(Task)-->C (Construction) | CONSTRUCTION | 1.17.3 | 1.17 | CONSTRUCTION-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-31 | 2021-09-13 18:00 | 2020-08-11 09:00 | 2022-05-06 18:00 | [6 empty] | 43.6494 | 0 | [15 empty] | 75.6772 | 0.27841 | 27.38 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4699 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019747
2306 | Task(Task)-->C (Construction) | CIVIL | 1.17.3.1 | 1.17.3 | CIVIL-->CONSTRUCTION-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-31 | 2021-01-23 18:00 | 2020-08-11 09:00 | 2021-04-30 18:00 | [6 empty] | 68.3136 | 0 | [15 empty] | 60.2264 | 0.16768 | 16.49 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4700 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019748
2307 | Task(Task)-->C (Construction) | AVAILABILITY OF FRONT BY NTPC |  | 1.17.3.1 | AVAILABILITY OF FRONT BY NTPC-->CIVIL-->CONSTRUCTION-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-31 | 2020-05-31 23:59 | 2020-08-11 09:00 | 2020-08-11 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4701 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019749
2308 | Task(Task)-->C (Construction) | EXCAVATION |  | 1.17.3.1 | EXCAVATION-->CIVIL-->CONSTRUCTION-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-07 | 2020-06-18 18:00 | 2020-08-22 09:00 | 2020-09-02 18:00 | [6 empty] | 100 | 0 | [15 empty] | 2.7273 | 0.004573 | 0.45 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 1670 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4702 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | Excavation | [23 empty] | 1019750
2309 | Task(Task)-->C (Construction) | PCC |  | 1.17.3.1 | PCC-->CIVIL-->CONSTRUCTION-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-19 09:00 | 2020-06-27 18:00 | 2020-09-24 09:00 | 2020-10-02 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.54545 | 0.000915 | 0.09 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4703 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | PCC | [23 empty] | 1019751
2310 | Task(Task)-->C (Construction) | RAFT |  | 1.17.3.1 | RAFT-->CIVIL-->CONSTRUCTION-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-28 | 2020-07-21 18:00 | 2020-10-03 09:00 | 2020-10-26 18:00 | [6 empty] | 100 | 0 | [15 empty] | 8.0606 | 0.013516 | 1.33 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4704 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019752
2311 | Task(Task)-->C (Construction) | PLINTH BEAM |  | 1.17.3.1 | PLINTH BEAM-->CIVIL-->CONSTRUCTION-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-30 09:00 | 2020-07-10 18:00 | 2020-10-05 09:00 | 2020-10-15 18:00 | [6 empty] | 100 | 0 | [15 empty] | 1.6364 | 0.002744 | 0.27 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4705 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019753
2312 | Task(Task)-->C (Construction) | PUMP FOUNDATION & TRENCH |  | 1.17.3.1 | PUMP FOUNDATION & TRENCH-->CIVIL-->CONSTRUCTION-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-05 | 2020-07-20 18:00 | 2020-10-10 09:00 | 2020-10-25 23:59 | [6 empty] | 100 | 0 | [15 empty] | 2.4242 | 0.004065 | 0.4 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4706 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019754
2313 | Task(Task)-->C (Construction) | GRADE SLAB |  | 1.17.3.1 | GRADE SLAB-->CIVIL-->CONSTRUCTION-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-18 09:00 | 2020-08-17 18:00 | 2020-10-23 09:00 | 2020-11-22 23:59 | [6 empty] | 100 | 0 | [15 empty] | 16.2424 | 0.027235 | 2.68 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 143 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4707 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019755
2314 | Task(Task)-->C (Construction) | COLUMN AND ROOF SLAB |  | 1.17.3.1 | COLUMN AND ROOF SLAB-->CIVIL-->CONSTRUCTION-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-05 09:00 | 2020-09-16 18:00 | 2020-11-10 09:00 | 2020-12-22 18:00 | [6 empty] | 100 | 0 | [15 empty] | 4 | 0.006707 | 0.66 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4708 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019756
2315 | Task(Task)-->C (Construction) | WATER TANK FOUNDATION |  | 1.17.3.1 | WATER TANK FOUNDATION-->CIVIL-->CONSTRUCTION-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-19 09:00 | 2020-10-11 23:59 | 2020-09-03 09:00 | 2020-12-26 18:00 | [6 empty] | 100 | 0 | [15 empty] | 6.4242 | 0.010772 | 1.06 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4709 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019757
2316 | Task(Task)-->C (Construction) | BRICK WORK |  | 1.17.3.1 | BRICK WORK-->CIVIL-->CONSTRUCTION-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-09-17 09:00 | 2020-10-17 18:00 | 2020-12-23 09:00 | 2021-01-22 18:00 | [6 empty] | 100 | 0 | [15 empty] | 4.4848 | 0.00752 | 0.74 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4710 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019758
2317 | Task(Task)-->C (Construction) | PLASTER |  | 1.17.3.1 | PLASTER-->CIVIL-->CONSTRUCTION-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-10-08 09:00 | 2020-11-07 18:00 | 2021-01-13 09:00 | 2021-02-12 18:00 | [6 empty] | 100 | 0 | [15 empty] | 1.2727 | 0.002134 | 0.21 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 378 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4711 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019759
2318 | Task(Task)-->C (Construction) | DOOR , WINDOW, MONORAIL DOOR & ROLLING SHUTTER |  | 1.17.3.1 | DOOR , WINDOW, MONORAIL DOOR & ROLLING SHUTTER-->CIVIL-->CONSTRUCTION-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-11-01 | 2020-11-23 18:00 | 2021-02-06 09:00 | 2021-02-28 23:59 | [6 empty] | 43.4783 | 0 | [15 empty] | 20.7879 | 0.034857 | 3.43 | Plan & Actual | Quantity | Lot | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4712 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019760
2319 | Task(Task)-->C (Construction) | FLOORING |  | 1.17.3.1 | FLOORING-->CIVIL-->CONSTRUCTION-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-11-01 | 2020-11-28 18:00 | 2021-02-06 09:00 | 2021-03-05 18:00 | [6 empty] | 35.7143 | 0 | [15 empty] | 11.8788 | 0.019918 | 1.96 | Plan & Actual | Quantity | Lot | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4713 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019761
2320 | Task(Task)-->C (Construction) | ROOF WATER PROFING & RWDC PIPE |  | 1.17.3.1 | ROOF WATER PROFING & RWDC PIPE-->CIVIL-->CONSTRUCTION-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-10-15 09:00 | 2020-11-14 18:00 | 2021-01-20 09:00 | 2021-02-19 18:00 | [6 empty] | 87.0968 | 0 | [15 empty] | 4.5455 | 0.007622 | 0.75 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 156 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4714 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019762
2321 | Task(Task)-->C (Construction) | GARLAND DRAIN & PLINTH PROTECTION |  | 1.17.3.1 | GARLAND DRAIN & PLINTH PROTECTION-->CIVIL-->CONSTRUCTION-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-11-01 | 2020-12-13 23:59 | 2021-02-06 09:00 | 2021-03-20 18:00 | [6 empty] | 23.2558 | 0 | [15 empty] | 14 | 0.023475 | 2.31 | Plan & Actual | Quantity | Lot | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4715 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019763
2322 | Task(Task)-->C (Construction) | PAINTING |  | 1.17.3.1 | PAINTING-->CIVIL-->CONSTRUCTION-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-11-24 09:00 | 2021-01-23 18:00 | 2021-03-01 09:00 | 2021-04-30 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0.9697 | 0.001626 | 0.16 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 313 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4716 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019764
2323 | Task(Task)-->C (Construction) | MECHANICAL | 1.17.3.2 | 1.17.3 | MECHANICAL-->CONSTRUCTION-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-11-09 09:00 | 2021-06-08 18:00 | 2021-02-20 09:00 | 2021-05-11 18:00 | [6 empty] | 6.0586 | 0 | [15 empty] | 21.2199 | 0.059079 | 5.81 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4717 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019765
2324 | Task(Task)-->C (Construction) | WATER TANKS |  | 1.17.3.2 | WATER TANKS-->MECHANICAL-->CONSTRUCTION-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-11-09 09:00 | 2020-12-08 18:00 | 2021-04-02 09:00 | 2021-05-01 18:00 | [6 empty] | 6.6667 | 0 | [15 empty] | 90.8778 | 0.05369 | 5.28 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4718 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019766
2325 | Task(Task)-->C (Construction) | ERECTION OF MONORAIL & HOISTS |  | 1.17.3.2 | ERECTION OF MONORAIL & HOISTS-->MECHANICAL-->CONSTRUCTION-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-03-20 09:00 | 2021-04-09 18:00 | 2021-02-20 09:00 | 2021-03-12 18:00 | [6 empty] | 0 | 0 | [15 empty] | 4.475 | 0.002644 | 0.26 | Plan & Actual | Quantity | Set | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5482 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019767
2326 | Task(Task)-->C (Construction) | ERECTION OF PUMPS |  | 1.17.3.2 | ERECTION OF PUMPS-->MECHANICAL-->CONSTRUCTION-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-04-10 09:00 | 2021-06-08 18:00 | 2021-03-13 09:00 | 2021-05-11 18:00 | [6 empty] | 0 | 0 | [15 empty] | 4.6472 | 0.002745 | 0.27 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4719 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019768
2327 | Task(Task)-->C (Construction) | ELECTRICAL & INSTRUMENTATION | 1.17.3.3 | 1.17.3 | ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-11-08 | 2021-09-03 18:00 | 2021-02-13 09:00 | 2022-04-26 18:00 | [6 empty] | 9.4426 | 0 | [15 empty] | 12.9291 | 0.035996 | 3.54 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5260 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019769
2328 | Task(Task)-->C (Construction) | CABLE TRAY |  | 1.17.3.3 | CABLE TRAY-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-11-08 | 2020-11-09 18:00 | 2021-02-13 09:00 | 2021-02-14 23:59 | [6 empty] | 100 | 0 | [15 empty] | 5.9322 | 0.002135 | 0.21 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4720 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019770
2329 | Task(Task)-->C (Construction) | POWER CABLE |  | 1.17.3.3 | POWER CABLE-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-06-05 09:00 | 2021-06-11 18:00 | 2021-07-25 | 2021-07-31 18:00 | [6 empty] | 0 | 0 | [15 empty] | 16.1017 | 0.005796 | 0.57 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5261 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019771
2330 | Task(Task)-->C (Construction) | CONTROL CABLE |  | 1.17.3.3 | CONTROL CABLE-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-06-09 09:00 | 2021-06-11 18:00 | 2021-10-26 09:00 | 2021-10-28 18:00 | [6 empty] | 0 | 0 | [15 empty] | 22.0339 | 0.007931 | 0.78 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 5505 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4721 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019772
2331 | Task(Task)-->C (Construction) | EARTHING |  | 1.17.3.3 | EARTHING-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-06-09 09:00 | 2021-06-11 18:00 | 2021-07-29 09:00 | 2021-07-31 18:00 | [6 empty] | 0 | 0 | [15 empty] | 2.2599 | 0.000813 | 0.08 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 377 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5387 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019773
2332 | Task(Task)-->C (Construction) | EARTH PIT |  | 1.17.3.3 | EARTH PIT-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-12-11 09:00 | 2020-12-13 23:59 | 2021-03-18 09:00 | 2021-03-20 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5388 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019774
2333 | Task(Task)-->C (Construction) | LIGHTING |  | 1.17.3.3 | LIGHTING-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-11-08 | 2020-11-14 18:00 | 2021-02-13 09:00 | 2021-02-19 18:00 | [6 empty] | 42.8571 | 0 | [15 empty] | 8.1921 | 0.002949 | 0.29 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5389 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019775
2334 | Task(Task)-->C (Construction) | FIELD INTRUMENTS |  | 1.17.3.3 | FIELD INTRUMENTS-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-06-08 09:00 | 2021-06-12 18:00 | 2021-10-25 09:00 | 2021-10-29 18:00 | [6 empty] | 0 | 0 | [15 empty] | 45.4802 | 0.016371 | 1.61 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5390 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019776
2335 | Task(Task)-->C (Construction) | MOTOR TERMINATION |  | 1.17.3.3 | MOTOR TERMINATION-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-06-09 09:00 | 2021-06-12 18:00 | 2022-01-02 | 2022-01-05 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5391 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019777
2336 | Task(Task)-->C (Construction) | NO LOAD RUN OF MOTOR |  | 1.17.3.3 | NO LOAD RUN OF MOTOR-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-08-27 09:00 | 2021-09-03 18:00 | 2022-04-19 09:00 | 2022-04-26 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5483 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019778
2337 | Task(Task)-->C (Construction) | NO LOAD COMMISSIONING & SYSTEM READYNESS FOR LOAD & TRIAL OPERATION |  | 1.17.3 | NO LOAD COMMISSIONING & SYSTEM READYNESS FOR LOAD & TRIAL OPERATION-->CONSTRUCTION-->PUMP HOUSE -B NEAR KDTP-2-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-09-04 09:00 | 2021-09-13 18:00 | 2022-04-27 09:00 | 2022-05-06 18:00 | [6 empty] | 0 | 0 | [15 empty] | 5.6245 | 0.015659 | 1.54 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5392 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019779
2338 | Task(Task)-->E (Engineering) | PUMP HOUSE -C NEAR KDTP-3 | 1.18 | 1 | PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-12-17 09:00 | 2021-09-04 18:00 | 2020-01-13 09:00 | 2022-04-02 18:00 |  |  | 2020-01-13 10:57 |  |  |  | 47.0581 | 9.2905 | [15 empty] | 0.35803 | 0.35803 | 35.21 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4722 | 0 | 1 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019780
2339 | Task(Task)-->E (Engineering) | ENGINEERING | 1.18.1 | 1.18 | ENGINEERING-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-01-22 18:00 | 2020-08-13 17:40 | 2020-05-09 18:00 | 2020-10-05 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 79.8212 | [15 empty] | 6.6477 | 0.023801 | 2.34 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4723 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019781
2340 | Task(Task)-->E (Engineering) | MECHANICAL | 1.18.1.1 | 1.18.1 | MECHANICAL-->ENGINEERING-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-22 18:00 | 2020-03-25 17:40 | 2020-05-26 18:00 | 2020-07-21 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 65 | [15 empty] | 24.2152 | 0.005763 | 0.54 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4724 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036125
2341 | Task(Task)-->E (Engineering) | PUMP HOUSE -C ARRANGEMENT ( PUMP HOUSE C) ALONG WITH PIPING LAYOUT & MS WATER TANK |  | 1.18.1.1 | PUMP HOUSE -C ARRANGEMENT ( PUMP HOUSE C) ALONG WITH PIPING LAYOUT & MS WATER TANK-->MECHANICAL-->ENGINEERING-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-22 18:00 | 2020-03-25 17:40 | 2020-05-26 18:00 | 2020-07-21 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-DS-GA-6010 |  | 2020-02-13 11:40 | 7012-155-PVM-B-040 |  |  |  | A |  |  |  | 100 | 0.005763 | 0.54 | Plan & Actual | Date |  | 0 | 0 | 0 | 200 | 0 | 10.4 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4725 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-22 18:00 | 2020-05-26 18:00 |  | 10 |  |  |  | 2020-02-13 17:40 | 2020-06-16 18:00 |  | 30 |  |  |  | 2020-02-19 17:40 | 2020-06-23 18:00 |  | 35 | 2020-06-19 09:47 |  |  | 2020-02-26 23:59 | 2020-06-30 18:00 |  | 65 | 2020-06-19 17:16 |  |  | 2020-03-03 17:40 | 2020-07-21 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-25 17:40 | 2020-07-21 18:00 |  | 100 | [122 empty] | Ram Prasad Roy | [5 empty] | U - Water Media & Utility System | [16 empty] | 85 |  |  |  |  | 101099
2342 | Task(Task)-->E (Engineering) | CIVIL | 1.18.1.2 | 1.18.1 | CIVIL-->ENGINEERING-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-04-15 18:00 | 2020-08-13 17:40 | 2020-06-30 18:00 | 2020-10-05 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 88.4619 | [15 empty] | 40.8072 | 0.009713 | 0.91 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4728 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036126
2343 | Task(Task)-->E (Engineering) | Pump House-C : DESIGN CALCULATION |  | 1.18.1.2 | Pump House-C : DESIGN CALCULATION-->CIVIL-->ENGINEERING-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-15 18:00 | 2020-06-15 17:40 | 2020-07-31 09:00 | 2020-08-17 18:00 |  |  | 2020-02-21 15:38 | 2020-08-17 22:45 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0024 |  | 2020-02-13 11:42 | 7012-155-PVC-U-082 |  |  |  | A |  |  |  | 40.6593 | 0.003949 | 0.37 | Plan & Actual | Date |  | 0 | 0 | 0 | 136.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4733 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-15 18:00 | 2020-06-30 18:00 |  | 10 |  |  |  | 2020-05-04 17:40 | 2020-07-25 18:00 |  | 30 |  |  |  | 2020-05-11 17:40 | 2020-07-28 18:00 |  | 35 |  |  |  | 2020-05-16 23:59 | 2020-08-04 18:00 |  | 65 | 2020-08-13 19:58 |  |  | 2020-05-22 17:40 | 2020-08-25 18:00 |  | 80 | 2020-08-17 22:40 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-15 17:40 | 2020-09-08 18:00 |  | 100 | 2020-08-17 22:46 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 183 |  |  |  |  | 101193
2344 | Task(Task)-->E (Engineering) | Pump House-C : NUM & RC DETAILS (SHT 1) |  | 1.18.1.2 | Pump House-C : NUM & RC DETAILS (SHT 1)-->CIVIL-->ENGINEERING-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-15 18:00 | 2020-06-15 17:40 | 2020-07-31 09:00 | 2020-08-17 18:00 |  |  | 2020-02-21 15:38 | 2020-08-17 22:45 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-NR-0031 |  | 2020-02-13 11:42 | 7012-155-PVC-C-083 |  |  |  | A |  |  |  | 13.1868 | 0.001281 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 45.03 | 0 | 12.15 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4729 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-15 18:00 | 2020-06-30 18:00 |  | 10 |  |  |  | 2020-05-04 17:40 | 2020-07-25 18:00 |  | 30 |  |  |  | 2020-05-11 17:40 | 2020-07-28 18:00 |  | 35 | 2020-07-29 11:24 |  |  | 2020-05-16 23:59 | 2020-08-04 18:00 |  | 65 | 2020-08-13 19:58 |  |  | 2020-05-22 17:40 | 2020-08-25 18:00 |  | 80 | 2020-08-17 22:35 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-15 17:40 | 2020-09-08 18:00 |  | 100 | 2020-08-17 22:46 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 184 |  |  |  |  | 101194
2345 | Task(Task)-->E (Engineering) | Pump House-C : NUM & RC DETAILS (SHT 2) |  | 1.18.1.2 | Pump House-C : NUM & RC DETAILS (SHT 2)-->CIVIL-->ENGINEERING-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-15 18:00 | 2020-06-15 17:40 | 2020-07-31 09:00 | 2020-08-17 18:00 |  |  | 2020-02-21 15:38 | 2020-08-17 22:45 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-NR-0032 |  | 2020-02-13 11:42 | 7012-155-PVC-C-084 |  |  |  | A |  |  |  | 13.1868 | 0.001281 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 45.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4730 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-15 18:00 | 2020-06-30 18:00 |  | 10 |  |  |  | 2020-05-04 17:40 | 2020-07-25 18:00 |  | 30 |  |  |  | 2020-05-11 17:40 | 2020-07-28 18:00 |  | 35 |  |  |  | 2020-05-16 23:59 | 2020-08-04 18:00 |  | 65 | 2020-08-13 19:58 |  |  | 2020-05-22 17:40 | 2020-08-25 18:00 |  | 80 | 2020-08-17 22:41 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-15 17:40 | 2020-09-08 18:00 |  | 100 | 2020-08-17 22:46 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 185 |  |  |  |  | 101195
2346 | Task(Task)-->E (Engineering) | Pump House-C : NUM & RC DETAILS (SHT 3) |  | 1.18.1.2 | Pump House-C : NUM & RC DETAILS (SHT 3)-->CIVIL-->ENGINEERING-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-15 18:00 | 2020-06-15 17:40 | 2020-06-30 18:00 | 2020-09-08 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-NR-0033 |  | 2020-02-13 11:42 | 7012-155-PVC-C-085 |  |  |  | A |  |  |  | 13.1868 | 0.001281 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 45.03 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4731 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-15 18:00 | 2020-06-30 18:00 |  | 10 |  |  |  | 2020-05-04 17:40 | 2020-07-25 18:00 |  | 30 |  |  |  | 2020-05-11 17:40 | 2020-07-28 18:00 |  | 35 | 2020-11-09 18:52 |  |  | 2020-05-16 23:59 | 2020-08-04 18:00 |  | 65 | 2020-11-09 21:02 |  |  | 2020-05-22 17:40 | 2020-08-25 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-15 17:40 | 2020-09-08 18:00 |  | 100 | [122 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 186 |  |  |  |  | 101196
2347 | Task(Task)-->E (Engineering) | ARCHITECTURAL GA OF PUMP HOUSE C |  | 1.18.1.2 | ARCHITECTURAL GA OF PUMP HOUSE C-->CIVIL-->ENGINEERING-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-14 23:59 | 2020-08-13 17:40 | 2020-07-27 18:00 | 2020-10-05 18:00 |  |  | 2020-02-21 15:39 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-AR-0010 |  | 2020-02-13 11:43 | 7012-155-PVC-C-116 |  |  |  | A |  |  |  | 19.7802 | 0.001921 | 0.18 | Plan & Actual | Date |  | 0 | 0 | 0 | 68.01 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4732 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-06-14 23:59 | 2020-07-27 18:00 |  | 10 |  |  |  | 2020-07-02 17:40 | 2020-08-21 18:00 |  | 30 |  |  |  | 2020-07-08 17:40 | 2020-08-24 18:00 |  | 35 | 2020-09-15 12:24 |  |  | 2020-07-15 23:59 | 2020-08-31 18:00 |  | 65 | 2020-09-15 15:54 |  |  | 2020-07-21 17:40 | 2020-09-21 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-08-13 17:40 | 2020-10-05 18:00 |  | 100 | [122 empty] | Chetan Khodke | [5 empty] | A - Architecture | [16 empty] | 217 |  |  |  |  | 101227
2348 | Task(Task)-->E (Engineering) | ELECTRICAL | 1.18.1.3 | 1.18.1 | ELECTRICAL-->ENGINEERING-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-30 18:00 | 2020-06-29 17:40 | 2020-05-09 18:00 | 2020-07-07 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 | [15 empty] | 34.9776 | 0.008325 | 0.78 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4734 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036127
2349 | Task(Task)-->E (Engineering) | EQUIPMENT, CABLE ROUTING, EARTHING & LIGHTNING LAYOUT WITH PLAN, SECTIONAL VIEWS & BOM OF PUMP HOUSE-C NEAR KDTP-3 |  | 1.18.1.3 | EQUIPMENT, CABLE ROUTING, EARTHING & LIGHTNING LAYOUT WITH PLAN, SECTIONAL VIEWS & BOM OF PUMP HOUSE-C NEAR KDTP-3-->ELECTRICAL-->ENGINEERING-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-30 18:00 | 2020-06-19 17:40 | 2020-05-09 18:00 | 2020-07-02 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5059 |  | 2020-02-13 11:44 | 7012-155-PVE-F-021 |  |  |  | A |  |  |  | 57.6923 | 0.004803 | 0.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 165.48 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4735 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-30 18:00 | 2020-05-09 18:00 |  | 10 |  |  |  | 2020-05-08 17:40 | 2020-05-23 18:00 |  | 30 | 2020-06-20 14:06 |  |  | 2020-05-15 17:40 | 2020-05-30 18:00 |  | 35 | 2020-06-24 13:47 |  |  | 2020-05-21 23:59 | 2020-06-06 18:00 |  | 65 | 2020-08-03 11:20 |  |  | 2020-05-28 17:40 | 2020-06-27 18:00 |  | 80 | 2020-08-03 11:26 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-19 17:40 | 2020-06-27 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 256 |  |  |  |  | 101267
2350 | Task(Task)-->E (Engineering) | LIGHTING LAYOUT PLAN WITH POWER DISTRIBUTION ARRANGEMENT, SECTIONAL VIEW, BOM OF PUMP HOUSE-C |  | 1.18.1.3 | LIGHTING LAYOUT PLAN WITH POWER DISTRIBUTION ARRANGEMENT, SECTIONAL VIEW, BOM OF PUMP HOUSE-C-->ELECTRICAL-->ENGINEERING-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-09 18:00 | 2020-06-29 17:40 | 2020-05-26 18:00 | 2020-07-07 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5070 |  | 2020-02-13 11:44 | 7012-155-PVE-G-032 |  |  |  | A |  |  |  | 42.3077 | 0.003522 | 0.33 | Plan & Actual | Date |  | 0 | 0 | 0 | 124.21 | 0 | 8.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4736 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-05-09 18:00 | 2020-05-26 18:00 |  | 10 |  |  |  | 2020-05-18 17:40 | 2020-06-02 18:00 |  | 30 | 2020-07-20 12:26 |  |  | 2020-05-25 17:40 | 2020-06-09 18:00 |  | 35 |  |  |  | 2020-05-30 23:59 | 2020-06-16 18:00 |  | 65 | 2020-07-20 12:38 |  |  | 2020-06-05 17:40 | 2020-07-07 18:00 |  | 80 | 2020-07-28 17:53 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-29 17:40 | 2020-07-07 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 267 |  |  |  |  | 101278
2351 | Task(Task)-->P (Procurement) | PROCUREMENT | 1.18.2 | 1.18 | PROCUREMENT-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-12-17 09:00 | 2020-10-27 18:00 | 2020-01-13 09:00 | 2021-06-11 18:00 |  |  | 2020-01-13 10:57 |  |  |  | 100 | 24.9545 | [15 empty] | 15.9659 | 0.057163 | 5.62 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4738 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019785
2352 | Task(Task)-->P (Procurement) | PURCHASE REQUISITION | 1.18.2.1 | 1.18.2 | PURCHASE REQUISITION-->PROCUREMENT-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-12-17 09:00 | 2020-06-06 18:00 | 2020-01-13 09:00 | 2020-05-29 18:00 |  |  | 2020-01-13 10:57 |  |  |  | 100 | 96.4248 | [15 empty] | 4.9911 | 0.002853 | 0.28 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4739 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019786
2353 | Task(Task)-->P (Procurement) | Building Structure |  | 1.18.2.1 | Building Structure-->PURCHASE REQUISITION-->PROCUREMENT-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2020-06-06 09:00 | 2020-06-06 18:00 | 2020-05-29 09:00 | 2020-05-29 18:00 |  |  | 2020-05-31 17:36 | 2020-05-31 17:36 |  |  | 100 | 100 | [15 empty] | 71.4286 | 0.002038 | 0.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4740 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019787
2354 | Task(Task)-->P (Procurement) | LPBS |  | 1.18.2.1 | LPBS-->PURCHASE REQUISITION-->PROCUREMENT-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-20 09:00 | 2020-03-20 18:00 | 2020-04-14 09:00 | 2020-04-14 18:00 | [6 empty] | 100 | 0 | [15 empty] | 3.5714 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4741 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019788
2355 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR UTILITY SYSTEM |  | 1.18.2.1 | LT AC MOTORS FOR UTILITY SYSTEM-->PURCHASE REQUISITION-->PROCUREMENT-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-17 09:00 | 2019-12-17 18:00 | 2020-01-13 09:00 | 2020-01-13 18:00 |  |  | 2020-01-13 10:57 | 2020-01-13 10:57 |  |  | 100 | 100 | [15 empty] | 25 | 0.000713 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4742 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019789
2356 | Task(Task)-->P (Procurement) | TECHNICAL CLEARANCE | 1.18.2.2 | 1.18.2 | TECHNICAL CLEARANCE-->PROCUREMENT-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-12-18 09:00 | 2020-06-13 18:00 | 2020-01-13 09:00 | 2020-06-12 18:00 |  |  | 2020-04-11 10:57 |  |  |  | 100 | 96.4248 | [15 empty] | 4.9911 | 0.002853 | 0.28 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4743 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019790
2357 | Task(Task)-->P (Procurement) | Building Structure |  | 1.18.2.2 | Building Structure-->TECHNICAL CLEARANCE-->PROCUREMENT-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2020-06-07 | 2020-06-13 18:00 | 2020-05-29 09:00 | 2020-05-29 18:00 |  |  | 2020-05-29 17:31 | 2020-05-29 17:31 |  |  | 100 | 100 | [15 empty] | 71.4286 | 0.002038 | 0.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4744 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019791
2358 | Task(Task)-->P (Procurement) | LPBS |  | 1.18.2.2 | LPBS-->TECHNICAL CLEARANCE-->PROCUREMENT-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-21 09:00 | 2020-04-04 18:00 | 2020-04-14 09:00 | 2020-06-12 18:00 | [6 empty] | 100 | 0 | [15 empty] | 3.5714 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4745 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019792
2359 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR UTILITY SYSTEM |  | 1.18.2.2 | LT AC MOTORS FOR UTILITY SYSTEM-->TECHNICAL CLEARANCE-->PROCUREMENT-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-18 09:00 | 2020-01-01 18:00 | 2020-01-13 09:00 | 2020-04-11 18:00 |  |  | 2020-04-11 10:57 | 2020-04-11 10:57 |  |  | 100 | 100 | [15 empty] | 25 | 0.000713 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4746 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019793
2360 | Task(Task)-->P (Procurement) | ORDERING | 1.18.2.3 | 1.18.2 | ORDERING-->PROCUREMENT-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-01-02 09:00 | 2020-07-13 18:00 | 2020-04-11 09:00 | 2020-08-19 18:00 |  |  | 2020-04-12 15:47 |  |  |  | 100 | 96.4254 | [15 empty] | 9.9822 | 0.005706 | 0.56 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4747 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019794
2361 | Task(Task)-->P (Procurement) | Building Structure |  | 1.18.2.3 | Building Structure-->ORDERING-->PROCUREMENT-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2020-06-14 | 2020-07-13 18:00 | 2020-05-29 09:00 | 2020-05-31 23:59 |  |  | 2020-05-31 17:39 | 2020-05-31 17:39 |  |  | 100 | 100 | [15 empty] | 71.4286 | 0.004076 | 0.4 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4748 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019795
2362 | Task(Task)-->P (Procurement) | LPBS |  | 1.18.2.3 | LPBS-->ORDERING-->PROCUREMENT-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-05 | 2020-04-20 18:00 | 2020-06-12 09:00 | 2020-08-19 18:00 | [6 empty] | 100 | 0 | [15 empty] | 3.5714 | 0.000204 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4749 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019796
2363 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR UTILITY SYSTEM |  | 1.18.2.3 | LT AC MOTORS FOR UTILITY SYSTEM-->ORDERING-->PROCUREMENT-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-02 09:00 | 2020-01-16 18:00 | 2020-04-11 09:00 | 2020-07-20 18:00 |  |  | 2020-04-12 15:47 | 2020-06-20 15:47 |  |  | 100 | 100 | [15 empty] | 25 | 0.001427 | 0.14 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4750 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019797
2364 | Task(Task)-->P (Procurement) | ITP APPROVAL | 1.18.2.4 | 1.18.2 | ITP APPROVAL-->PROCUREMENT-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-01-17 09:00 | 2020-07-20 18:00 | 2020-05-31 | 2020-10-14 18:00 |  |  | 2020-07-29 15:04 |  |  |  | 100 | 28.5664 | [15 empty] | 4.9911 | 0.002853 | 0.28 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4751 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019798
2365 | Task(Task)-->P (Procurement) | Building Structure |  | 1.18.2.4 | Building Structure-->ITP APPROVAL-->PROCUREMENT-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-14 09:00 | 2020-07-20 18:00 | 2020-05-31 | 2020-08-04 18:00 | [6 empty] | 100 | 0 | [15 empty] | 71.4286 | 0.002038 | 0.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4752 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019799
2366 | Task(Task)-->P (Procurement) | LPBS |  | 1.18.2.4 | LPBS-->ITP APPROVAL-->PROCUREMENT-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-21 09:00 | 2020-05-30 18:00 | 2020-07-29 09:00 | 2020-08-21 18:00 |  |  | 2020-07-29 15:04 | 2020-08-22 12:55 |  |  | 100 | 100 | [15 empty] | 3.5714 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4753 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019800
2367 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR UTILITY SYSTEM |  | 1.18.2.4 | LT AC MOTORS FOR UTILITY SYSTEM-->ITP APPROVAL-->PROCUREMENT-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-17 09:00 | 2020-02-25 18:00 | 2020-09-08 09:00 | 2020-10-14 18:00 |  |  | 2020-09-08 15:17 | 2020-10-14 15:17 |  |  | 100 | 100 | [15 empty] | 25 | 0.000713 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4754 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019801
2368 | Task(Task)-->P (Procurement) | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE | 1.18.2.5 | 1.18.2 | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-01-17 09:00 | 2020-07-12 23:59 | 2020-05-31 | 2020-09-29 18:00 |  |  | 2020-07-07 10:15 |  |  |  | 100 | 28.5748 | [15 empty] | 14.9733 | 0.008559 | 0.84 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4755 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019802
2369 | Task(Task)-->P (Procurement) | Building Structure |  | 1.18.2.5 | Building Structure-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-06 09:00 | 2020-07-12 23:59 | 2020-05-31 | 2020-09-09 18:00 | [6 empty] | 100 | 0 | [15 empty] | 71.4286 | 0.006114 | 0.6 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4756 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019803
2370 | Task(Task)-->P (Procurement) | LPBS |  | 1.18.2.5 | LPBS-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-21 09:00 | 2020-06-04 18:00 | 2020-07-25 09:00 | 2020-08-22 18:00 |  |  | 2020-07-24 18:40 | 2020-08-22 12:59 |  |  | 100 | 100 | [15 empty] | 3.5714 | 0.000306 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4757 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019804
2371 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR UTILITY SYSTEM |  | 1.18.2.5 | LT AC MOTORS FOR UTILITY SYSTEM-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-17 09:00 | 2020-03-01 23:59 | 2020-07-07 09:00 | 2020-09-29 18:00 |  |  | 2020-07-07 10:15 | 2020-09-29 14:41 |  |  | 100 | 100 | [15 empty] | 25 | 0.00214 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4758 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019805
2372 | Task(Task)-->P (Procurement) | MANUFACTURING & RECEIPT AT SITE (MRN) | 1.18.2.6 | 1.18.2 | MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-02 09:00 | 2020-10-27 18:00 | 2020-08-23 | 2021-06-11 18:00 |  |  | 2020-08-22 13:01 |  |  |  | 100 | 0 | [15 empty] | 60.0713 | 0.034339 | 3.37 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4759 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019806
2373 | Task(Task)-->P (Procurement) | WATER TANK |  | 1.18.2.6 | WATER TANK-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-21 09:00 | 2020-10-18 23:59 | 2020-09-09 09:00 | 2021-04-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 70.6231 | 0.024251 | 2.38 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4760 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019807
2374 | Task(Task)-->P (Procurement) | LPBS |  | 1.18.2.6 | LPBS-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-05 09:00 | 2020-09-16 18:00 | 2020-08-23 | 2020-12-04 18:00 |  |  | 2020-08-22 13:01 |  |  |  | 100 | 0 | [15 empty] | 3.8576 | 0.001325 | 0.13 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4761 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019808
2375 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR UTILITY SYSTEM |  | 1.18.2.6 | LT AC MOTORS FOR UTILITY SYSTEM-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-02 09:00 | 2020-10-27 18:00 | 2020-10-15 09:00 | 2021-06-11 18:00 |  |  | 2020-09-29 16:43 |  |  |  | 100 | 0 | [15 empty] | 25.5193 | 0.008763 | 0.86 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4762 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019809
2376 | Task(Task)-->C (Construction) | CONSTRUCTION | 1.18.3 | 1.18 | CONSTRUCTION-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-30 09:00 | 2021-09-04 18:00 | 2020-08-11 09:00 | 2022-04-02 18:00 | [6 empty] | 31.5876 | 0 | [15 empty] | 77.3864 | 0.27707 | 27.24 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4763 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019810
2377 | Task(Task)-->C (Construction) | CIVIL | 1.18.3.1 | 1.18.3 | CIVIL-->CONSTRUCTION-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-30 09:00 | 2021-02-09 18:00 | 2020-08-11 09:00 | 2021-05-18 18:00 | [6 empty] | 48.304 | 0 | [15 empty] | 61.3803 | 0.17006 | 16.72 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4764 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019811
2378 | Task(Task)-->C (Construction) | AVAILABILITY OF FRONT BY NTPC |  | 1.18.3.1 | AVAILABILITY OF FRONT BY NTPC-->CIVIL-->CONSTRUCTION-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-30 09:00 | 2020-05-30 18:00 | 2020-08-11 09:00 | 2020-08-11 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4765 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019812
2379 | Task(Task)-->C (Construction) | EXCAVATION |  | 1.18.3.1 | EXCAVATION-->CIVIL-->CONSTRUCTION-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-06 09:00 | 2020-06-17 18:00 | 2020-08-26 09:00 | 2020-09-06 23:59 | [6 empty] | 100 | 0 | [15 empty] | 2.7496 | 0.004676 | 0.46 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 1713 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4766 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | Excavation | [23 empty] | 1019813
2380 | Task(Task)-->C (Construction) | PCC |  | 1.18.3.1 | PCC-->CIVIL-->CONSTRUCTION-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-18 09:00 | 2020-06-26 18:00 | 2020-09-24 09:00 | 2020-10-02 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.53796 | 0.000915 | 0.09 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4767 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | PCC | [23 empty] | 1019814
2381 | Task(Task)-->C (Construction) | RAFT |  | 1.18.3.1 | RAFT-->CIVIL-->CONSTRUCTION-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-27 09:00 | 2020-07-20 18:00 | 2020-10-03 09:00 | 2020-10-26 18:00 | [6 empty] | 100 | 0 | [15 empty] | 8.2487 | 0.014028 | 1.38 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4768 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019815
2382 | Task(Task)-->C (Construction) | PLINTH BEAM |  | 1.18.3.1 | PLINTH BEAM-->CIVIL-->CONSTRUCTION-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-23 09:00 | 2020-08-02 23:59 | 2020-10-29 09:00 | 2020-11-08 23:59 | [6 empty] | 100 | 0 | [15 empty] | 1.6139 | 0.002745 | 0.27 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4769 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019816
2383 | Task(Task)-->C (Construction) | PUMP FOUNDATION & TRENCH |  | 1.18.3.1 | PUMP FOUNDATION & TRENCH-->CIVIL-->CONSTRUCTION-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-28 09:00 | 2020-08-12 18:00 | 2020-11-03 09:00 | 2020-11-18 18:00 | [6 empty] | 100 | 0 | [15 empty] | 2.3909 | 0.004066 | 0.4 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4770 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019817
2384 | Task(Task)-->C (Construction) | GRADE SLAB |  | 1.18.3.1 | GRADE SLAB-->CIVIL-->CONSTRUCTION-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-10 09:00 | 2020-09-09 18:00 | 2020-11-16 09:00 | 2020-12-16 18:00 | [6 empty] | 100 | 0 | [15 empty] | 16.5571 | 0.028158 | 2.77 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 148 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4771 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019818
2385 | Task(Task)-->C (Construction) | COLUMN AND ROOF SLAB |  | 1.18.3.1 | COLUMN AND ROOF SLAB-->CIVIL-->CONSTRUCTION-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-28 09:00 | 2020-10-09 18:00 | 2020-12-04 09:00 | 2021-01-15 18:00 | [6 empty] | 100 | 0 | [15 empty] | 3.945 | 0.006709 | 0.66 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4772 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019819
2386 | Task(Task)-->C (Construction) | WATER TANK FOUNDATION |  | 1.18.3.1 | WATER TANK FOUNDATION-->CIVIL-->CONSTRUCTION-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-18 09:00 | 2020-10-10 18:00 | 2020-09-07 09:00 | 2020-12-30 18:00 | [6 empty] | 100 | 0 | [15 empty] | 6.3359 | 0.010775 | 1.06 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4773 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019820
2387 | Task(Task)-->C (Construction) | BRICK WORK |  | 1.18.3.1 | BRICK WORK-->CIVIL-->CONSTRUCTION-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-10-10 09:00 | 2020-11-09 18:00 | 2021-01-16 09:00 | 2021-02-15 18:00 | [6 empty] | 100 | 0 | [15 empty] | 4.6025 | 0.007827 | 0.77 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4774 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019821
2388 | Task(Task)-->C (Construction) | PLASTER |  | 1.18.3.1 | PLASTER-->CIVIL-->CONSTRUCTION-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-10-25 | 2020-11-24 18:00 | 2021-01-31 | 2021-03-02 18:00 | [6 empty] | 54.8387 | 0 | [15 empty] | 1.315 | 0.002236 | 0.22 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 394 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4775 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019822
2389 | Task(Task)-->C (Construction) | DOOR , WINDOW, MONORAIL DOOR & ROLLING SHUTTER |  | 1.18.3.1 | DOOR , WINDOW, MONORAIL DOOR & ROLLING SHUTTER-->CIVIL-->CONSTRUCTION-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-11-18 09:00 | 2020-12-10 18:00 | 2021-02-24 09:00 | 2021-03-18 18:00 | [6 empty] | 0 | 0 | [15 empty] | 20.5021 | 0.034867 | 3.43 | Plan & Actual | Quantity | Lot | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4776 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019823
2390 | Task(Task)-->C (Construction) | FLOORING |  | 1.18.3.1 | FLOORING-->CIVIL-->CONSTRUCTION-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-11-18 09:00 | 2020-12-15 18:00 | 2021-02-24 09:00 | 2021-03-23 18:00 | [6 empty] | 0 | 0 | [15 empty] | 11.7155 | 0.019924 | 1.96 | Plan & Actual | Quantity | Lot | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4777 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019824
2391 | Task(Task)-->C (Construction) | ROOF WATER PROFING & RWDC PIPE |  | 1.18.3.1 | ROOF WATER PROFING & RWDC PIPE-->CIVIL-->CONSTRUCTION-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-11-07 09:00 | 2020-12-07 18:00 | 2021-02-13 09:00 | 2021-03-15 18:00 | [6 empty] | 12.9032 | 0 | [15 empty] | 4.6623 | 0.007929 | 0.78 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 163 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4778 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019825
2392 | Task(Task)-->C (Construction) | GARLAND DRAIN & PLINTH PROTECTION |  | 1.18.3.1 | GARLAND DRAIN & PLINTH PROTECTION-->CIVIL-->CONSTRUCTION-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-11-18 09:00 | 2020-12-30 18:00 | 2021-02-24 09:00 | 2021-04-07 18:00 | [6 empty] | 0 | 0 | [15 empty] | 13.8075 | 0.023482 | 2.31 | Plan & Actual | Quantity | Lot | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4779 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019826
2393 | Task(Task)-->C (Construction) | PAINTING |  | 1.18.3.1 | PAINTING-->CIVIL-->CONSTRUCTION-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-12-11 09:00 | 2021-02-09 18:00 | 2021-03-19 09:00 | 2021-05-18 18:00 | [6 empty] | 0 | 0 | [15 empty] | 1.0161 | 0.001728 | 0.17 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 327 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4780 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019827
2394 | Task(Task)-->C (Construction) | MECHANICAL | 1.18.3.2 | 1.18.3 | MECHANICAL-->CONSTRUCTION-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-11-08 | 2021-05-09 23:59 | 2021-03-10 09:00 | 2021-05-01 18:00 | [6 empty] | 9.0877 | 0 | [15 empty] | 21.3289 | 0.059095 | 5.81 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4781 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019828
2395 | Task(Task)-->C (Construction) | WATER TANKS |  | 1.18.3.2 | WATER TANKS-->MECHANICAL-->CONSTRUCTION-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-11-08 | 2020-12-07 18:00 | 2021-04-02 09:00 | 2021-05-01 18:00 | [6 empty] | 10 | 0 | [15 empty] | 90.8778 | 0.053704 | 5.28 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4782 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019829
2396 | Task(Task)-->C (Construction) | ERECTION OF MONORAIL & HOISTS |  | 1.18.3.2 | ERECTION OF MONORAIL & HOISTS-->MECHANICAL-->CONSTRUCTION-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-03-20 09:00 | 2021-04-09 18:00 | 2021-03-10 09:00 | 2021-03-30 18:00 | [6 empty] | 0 | 0 | [15 empty] | 4.475 | 0.002645 | 0.26 | Plan & Actual | Quantity | Set | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5484 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019830
2397 | Task(Task)-->C (Construction) | ERECTION OF PUMPS |  | 1.18.3.2 | ERECTION OF PUMPS-->MECHANICAL-->CONSTRUCTION-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-04-10 09:00 | 2021-05-09 23:59 | 2021-03-31 09:00 | 2021-04-29 18:00 | [6 empty] | 0 | 0 | [15 empty] | 4.6472 | 0.002746 | 0.27 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4783 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019831
2398 | Task(Task)-->C (Construction) | ELECTRICAL & INSTRUMENTATION | 1.18.3.3 | 1.18.3 | ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-11-25 09:00 | 2021-08-25 18:00 | 2021-03-03 09:00 | 2022-03-23 18:00 | [6 empty] | 0 | 0 | [15 empty] | 11.6373 | 0.032243 | 3.17 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5262 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019832
2399 | Task(Task)-->C (Construction) | CABLE TRAY |  | 1.18.3.3 | CABLE TRAY-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-11-25 09:00 | 2020-11-26 18:00 | 2021-03-03 09:00 | 2021-03-04 18:00 | [6 empty] | 0 | 0 | [15 empty] | 6.6456 | 0.002143 | 0.21 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4784 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019833
2400 | Task(Task)-->C (Construction) | POWER CABLE |  | 1.18.3.3 | POWER CABLE-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-05-04 09:00 | 2021-05-10 18:00 | 2021-07-25 | 2021-07-31 18:00 | [6 empty] | 0 | 0 | [15 empty] | 18.3544 | 0.005918 | 0.58 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 4080 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5263 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019834
2401 | Task(Task)-->C (Construction) | CONTROL CABLE |  | 1.18.3.3 | CONTROL CABLE-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-05-08 09:00 | 2021-05-10 18:00 | 2021-10-26 09:00 | 2021-10-28 18:00 | [6 empty] | 0 | 0 | [15 empty] | 13.2911 | 0.004285 | 0.42 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4785 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019835
2402 | Task(Task)-->C (Construction) | EARTHING |  | 1.18.3.3 | EARTHING-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-05-08 09:00 | 2021-05-10 18:00 | 2021-07-29 09:00 | 2021-07-31 18:00 | [6 empty] | 0 | 0 | [15 empty] | 2.5316 | 0.000816 | 0.08 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 377 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5393 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019836
2403 | Task(Task)-->C (Construction) | EARTH PIT |  | 1.18.3.3 | EARTH PIT-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-12-28 09:00 | 2020-12-30 18:00 | 2021-04-05 09:00 | 2021-04-07 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5394 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019837
2404 | Task(Task)-->C (Construction) | LIGHTING |  | 1.18.3.3 | LIGHTING-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-12-02 09:00 | 2020-12-08 18:00 | 2021-03-10 09:00 | 2021-03-16 18:00 | [6 empty] | 0 | 0 | [15 empty] | 9.1772 | 0.002959 | 0.29 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5395 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019838
2405 | Task(Task)-->C (Construction) | FIELD INTRUMENTS |  | 1.18.3.3 | FIELD INTRUMENTS-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-05-07 09:00 | 2021-05-11 18:00 | 2021-10-25 09:00 | 2021-10-29 18:00 | [6 empty] | 0 | 0 | [15 empty] | 50 | 0.016122 | 1.58 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5396 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019839
2406 | Task(Task)-->C (Construction) | MOTOR TERMINATION |  | 1.18.3.3 | MOTOR TERMINATION-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-05-19 09:00 | 2021-05-22 18:00 | 2022-01-02 | 2022-01-05 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5397 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019840
2407 | Task(Task)-->C (Construction) | NO LOAD RUN OF MOTOR |  | 1.18.3.3 | NO LOAD RUN OF MOTOR-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-08-22 | 2021-08-25 18:00 | 2022-03-20 | 2022-03-23 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5485 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019841
2408 | Task(Task)-->C (Construction) | NO LOAD COMMISSIONING & SYSTEM READYNESS FOR LOAD & TRIAL OPERATION |  | 1.18.3 | NO LOAD COMMISSIONING & SYSTEM READYNESS FOR LOAD & TRIAL OPERATION-->CONSTRUCTION-->PUMP HOUSE -C NEAR KDTP-3-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-08-26 09:00 | 2021-09-04 18:00 | 2022-03-24 09:00 | 2022-04-02 18:00 | [6 empty] | 0 | 0 | [15 empty] | 5.6535 | 0.015664 | 1.54 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5398 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019842
2409 | Task(Task)-->E (Engineering) | CABLE GALLERY & CABLE TRENCH | 1.19 | 1 | CABLE GALLERY & CABLE TRENCH-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-01-28 09:00 | 2021-05-28 18:00 | 2020-03-16 09:00 | 2021-11-25 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 74.0273 | 12.7537 | [15 empty] | 1.3856 | 1.3856 | 136.26 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4786 | 0 | 1 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019843
2410 | Task(Task)-->E (Engineering) | ENGINEERING | 1.19.1 | 1.19 | ENGINEERING-->CABLE GALLERY & CABLE TRENCH-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-03-18 18:00 | 2020-06-10 17:40 | 2020-05-14 18:00 | 2020-09-10 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 81.8726 | [15 empty] | 0.79254 | 0.010981 | 1.08 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4787 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019844
2411 | Task(Task)-->E (Engineering) | CIVIL | 1.19.1.1 | 1.19.1 | CIVIL-->ENGINEERING-->CABLE GALLERY & CABLE TRENCH-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-18 18:00 | 2020-06-10 17:40 | 2020-08-26 09:00 | 2020-09-08 18:00 |  |  | 2020-02-21 15:38 | 2020-09-10 23:14 |  |  | 100 | 100 | [15 empty] | 73.1481 | 0.008032 | 0.79 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4788 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036128
2412 | Task(Task)-->E (Engineering) | CABLE GALLERY & SUPPORTING TRESTLES : DESIGN CALCULATION OF SUB STRUCTURE |  | 1.19.1.1 | CABLE GALLERY & SUPPORTING TRESTLES : DESIGN CALCULATION OF SUB STRUCTURE-->CIVIL-->ENGINEERING-->CABLE GALLERY & CABLE TRENCH-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-12 23:59 | 2020-06-10 17:40 | 2020-08-31 09:00 | 2020-09-08 18:00 |  |  | 2020-02-21 15:38 | 2020-09-10 23:14 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0028 |  | 2020-02-13 11:43 | 7012-155-PVC-U-098 |  |  |  | A |  |  |  | 31.6456 | 0.002542 | 0.25 | Plan & Actual | Date |  | 0 | 0 | 0 | 92.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4790 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-12 23:59 | 2020-06-13 18:00 |  | 10 |  |  |  | 2020-04-30 17:40 | 2020-07-23 18:00 |  | 30 |  |  |  | 2020-05-06 17:40 | 2020-07-26 23:59 |  | 35 |  |  |  | 2020-05-13 23:59 | 2020-08-02 23:59 |  | 65 | 2020-08-31 23:46 |  |  | 2020-05-19 17:40 | 2020-08-23 23:59 |  | 80 | 2020-09-10 22:56 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-10 17:40 | 2020-09-06 23:59 |  | 100 | 2020-09-10 23:15 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 199 |  |  |  |  | 101209
2413 | Task(Task)-->E (Engineering) | CABLE GALLERY & SUPPORTING TRESTLES: NUM & RC DETAILS |  | 1.19.1.1 | CABLE GALLERY & SUPPORTING TRESTLES: NUM & RC DETAILS-->CIVIL-->ENGINEERING-->CABLE GALLERY & CABLE TRENCH-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-12 23:59 | 2020-06-10 17:40 | 2020-08-31 09:00 | 2020-09-08 18:00 |  |  | 2020-02-21 15:38 | 2020-09-10 23:14 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-NR-0043 |  | 2020-02-13 11:43 | 7012-155-PVC-C-099 |  |  |  | A |  |  |  | 31.6456 | 0.002542 | 0.25 | Plan & Actual | Date |  | 0 | 0 | 0 | 92.1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4789 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-12 23:59 | 2020-06-13 18:00 |  | 10 |  |  |  | 2020-04-30 17:40 | 2020-07-23 18:00 |  | 30 |  |  |  | 2020-05-06 17:40 | 2020-07-26 23:59 |  | 35 | 2020-09-02 17:18 |  |  | 2020-05-13 23:59 | 2020-08-02 23:59 |  | 65 | 2020-09-02 20:31 |  |  | 2020-05-19 17:40 | 2020-08-23 23:59 |  | 80 | 2020-09-10 22:55 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-10 17:40 | 2020-09-06 23:59 |  | 100 | 2020-09-10 23:15 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 200 |  |  |  |  | 101210
2414 | Task(Task)-->E (Engineering) | CABLE GALLERY & SUPPORTING TRESTLES : DESIGN CALCULATION OF SUPER STRUCTURE |  | 1.19.1.1 | CABLE GALLERY & SUPPORTING TRESTLES : DESIGN CALCULATION OF SUPER STRUCTURE-->CIVIL-->ENGINEERING-->CABLE GALLERY & CABLE TRENCH-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-18 18:00 | 2020-05-18 17:40 | 2020-08-26 09:00 | 2020-09-08 18:00 |  |  | 2020-02-21 15:38 | 2020-09-10 23:14 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0029 |  | 2020-02-13 11:43 | 7012-155-PVC-U-100 |  |  |  | A |  |  |  | 36.7089 | 0.002948 | 0.29 | Plan & Actual | Date |  | 0 | 0 | 0 | 108.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4791 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-18 18:00 | 2020-05-14 18:00 |  | 10 |  |  |  | 2020-04-06 17:40 | 2020-06-23 18:00 |  | 30 |  |  |  | 2020-04-13 17:40 | 2020-06-26 18:00 |  | 35 |  |  |  | 2020-04-18 23:59 | 2020-07-03 18:00 |  | 65 | 2020-08-26 21:13 |  |  | 2020-04-24 17:40 | 2020-07-24 18:00 |  | 80 | 2020-09-10 22:58 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-18 17:40 | 2020-08-07 18:00 |  | 100 | 2020-09-10 23:15 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 201 |  |  |  |  | 101211
2415 | Task(Task)-->E (Engineering) | STRUCTURAL | 1.19.1.2 | 1.19.1 | STRUCTURAL-->ENGINEERING-->CABLE GALLERY & CABLE TRENCH-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-18 18:00 | 2020-05-18 17:40 | 2020-05-14 18:00 | 2020-09-10 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 32.5 | [15 empty] | 26.8519 | 0.002949 | 0.29 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4792 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036129
2416 | Task(Task)-->E (Engineering) | CABLE GALLERY & SUPPORTING TRESTLES : STRUCTURAL GA (SHT 1) |  | 1.19.1.2 | CABLE GALLERY & SUPPORTING TRESTLES : STRUCTURAL GA (SHT 1)-->STRUCTURAL-->ENGINEERING-->CABLE GALLERY & CABLE TRENCH-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-18 18:00 | 2020-05-18 17:40 | 2020-05-14 18:00 | 2020-09-10 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-GA-0023 |  | 2020-02-13 11:43 | 7012-155-PVC-B-101 |  |  |  | A |  |  |  | 50 | 0.001475 | 0.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 54.29 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4793 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-18 18:00 | 2020-05-14 18:00 |  | 10 |  |  |  | 2020-04-06 17:40 | 2020-06-23 18:00 |  | 30 | 2020-08-20 17:46 |  |  | 2020-04-13 17:40 | 2020-06-26 18:00 |  | 35 |  |  |  | 2020-04-18 23:59 | 2020-07-03 18:00 |  | 65 | 2020-08-26 21:12 |  |  | 2020-04-24 17:40 | 2020-07-24 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-18 17:40 | 2020-08-07 18:00 |  | 100 | [122 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 202 |  |  |  |  | 101212
2417 | Task(Task)-->E (Engineering) | CABLE GALLERY & SUPPORTING TRESTLES : STRUCTURAL GA (SHT 2) |  | 1.19.1.2 | CABLE GALLERY & SUPPORTING TRESTLES : STRUCTURAL GA (SHT 2)-->STRUCTURAL-->ENGINEERING-->CABLE GALLERY & CABLE TRENCH-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-18 18:00 | 2020-05-18 17:40 | 2020-05-14 18:00 | 2020-08-21 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-GA-0024 |  | 2020-02-13 11:43 | 7012-155-PVC-B-102 |  |  |  | A |  |  |  | 50 | 0.001475 | 0.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 54.29 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4794 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-18 18:00 | 2020-05-14 18:00 |  | 10 |  |  |  | 2020-04-06 17:40 | 2020-06-23 18:00 |  | 30 |  |  |  | 2020-04-13 17:40 | 2020-06-26 18:00 |  | 35 |  |  |  | 2020-04-18 23:59 | 2020-07-03 18:00 |  | 65 |  |  |  | 2020-04-24 17:40 | 2020-07-24 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-18 17:40 | 2020-08-07 18:00 |  | 100 | [122 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 203 |  |  |  |  | 101213
2418 | Task(Task)-->P (Procurement) | PROCUREMENT | 1.19.2 | 1.19 | PROCUREMENT-->CABLE GALLERY & CABLE TRENCH-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-01-28 09:00 | 2020-11-30 18:00 | 2020-03-16 09:00 | 2021-04-01 18:00 |  |  | 2020-03-16 16:04 |  |  |  | 96.1827 | 26.3124 | [15 empty] | 46.0043 | 0.63741 | 62.69 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4796 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019847
2419 | Task(Task)-->P (Procurement) | PURCHASE REQUISITION | 1.19.2.1 | 1.19.2 | PURCHASE REQUISITION-->PROCUREMENT-->CABLE GALLERY & CABLE TRENCH-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-28 09:00 | 2020-04-18 18:00 | 2020-03-16 09:00 | 2020-05-29 18:00 |  |  | 2020-03-16 16:04 | 2020-05-31 18:44 |  |  | 100 | 100 | [15 empty] | 4.9944 | 0.031835 | 3.13 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4797 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019848
2420 | Task(Task)-->P (Procurement) | Building Structure |  | 1.19.2.1 | Building Structure-->PURCHASE REQUISITION-->PROCUREMENT-->CABLE GALLERY & CABLE TRENCH-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-18 09:00 | 2020-04-18 18:00 | 2020-05-29 09:00 | 2020-05-29 18:00 |  |  | 2020-05-31 18:44 | 2020-05-31 18:44 |  |  | 100 | 100 | [15 empty] | 57.8275 | 0.018409 | 1.81 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4798 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019849
2421 | Task(Task)-->P (Procurement) | CABLE TRAY & ACCESSORIES |  | 1.19.2.1 | CABLE TRAY & ACCESSORIES-->PURCHASE REQUISITION-->PROCUREMENT-->CABLE GALLERY & CABLE TRENCH-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-28 09:00 | 2020-01-28 18:00 | 2020-03-16 09:00 | 2020-03-16 18:00 |  |  | 2020-03-16 16:04 | 2020-03-16 16:04 |  |  | 100 | 100 | [15 empty] | 42.1725 | 0.013426 | 1.32 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4799 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019850
2422 | Task(Task)-->P (Procurement) | TECHNICAL CLEARANCE | 1.19.2.2 | 1.19.2 | TECHNICAL CLEARANCE-->PROCUREMENT-->CABLE GALLERY & CABLE TRENCH-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-29 09:00 | 2020-04-25 18:00 | 2020-03-16 09:00 | 2020-05-29 18:00 |  |  | 2020-03-17 16:05 | 2020-05-29 17:31 |  |  | 100 | 100 | [15 empty] | 4.9944 | 0.031835 | 3.13 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4800 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019851
2423 | Task(Task)-->P (Procurement) | Building Structure |  | 1.19.2.2 | Building Structure-->TECHNICAL CLEARANCE-->PROCUREMENT-->CABLE GALLERY & CABLE TRENCH-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-19 | 2020-04-25 18:00 | 2020-05-29 09:00 | 2020-05-29 18:00 |  |  | 2020-05-29 17:31 | 2020-05-29 17:31 |  |  | 100 | 100 | [15 empty] | 57.8275 | 0.018409 | 1.81 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4801 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019852
2424 | Task(Task)-->P (Procurement) | CABLE TRAY & ACCESSORIES |  | 1.19.2.2 | CABLE TRAY & ACCESSORIES-->TECHNICAL CLEARANCE-->PROCUREMENT-->CABLE GALLERY & CABLE TRENCH-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-29 09:00 | 2020-02-06 18:00 | 2020-03-16 09:00 | 2020-05-04 18:00 |  |  | 2020-03-17 16:05 | 2020-05-04 16:05 |  |  | 100 | 100 | [15 empty] | 42.1725 | 0.013426 | 1.32 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4802 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019853
2425 | Task(Task)-->P (Procurement) | ORDERING | 1.19.2.3 | 1.19.2 | ORDERING-->PROCUREMENT-->CABLE GALLERY & CABLE TRENCH-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-07 09:00 | 2020-05-25 18:00 | 2020-05-04 09:00 | 2020-08-07 18:00 |  |  | 2020-05-05 16:06 | 2020-07-06 16:06 |  |  | 100 | 100 | [15 empty] | 10.0048 | 0.063772 | 6.27 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4803 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019854
2426 | Task(Task)-->P (Procurement) | Building Structure |  | 1.19.2.3 | Building Structure-->ORDERING-->PROCUREMENT-->CABLE GALLERY & CABLE TRENCH-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-26 | 2020-05-25 18:00 | 2020-05-29 09:00 | 2020-05-31 23:59 |  |  | 2020-05-31 18:49 | 2020-05-31 18:49 |  |  | 100 | 100 | [15 empty] | 57.8947 | 0.036921 | 3.63 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4804 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019855
2427 | Task(Task)-->P (Procurement) | CABLE TRAY & ACCESSORIES |  | 1.19.2.3 | CABLE TRAY & ACCESSORIES-->ORDERING-->PROCUREMENT-->CABLE GALLERY & CABLE TRENCH-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-07 09:00 | 2020-02-15 18:00 | 2020-05-04 09:00 | 2020-08-07 18:00 |  |  | 2020-05-05 16:06 | 2020-07-06 16:06 |  |  | 100 | 100 | [15 empty] | 42.1053 | 0.026851 | 2.64 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4805 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019856
2428 | Task(Task)-->P (Procurement) | ITP APPROVAL | 1.19.2.4 | 1.19.2 | ITP APPROVAL-->PROCUREMENT-->CABLE GALLERY & CABLE TRENCH-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-16 | 2020-06-01 18:00 | 2020-05-30 09:00 | 2020-08-04 18:00 |  |  | 2020-06-25 19:04 |  |  |  | 100 | 0 | [15 empty] | 4.9944 | 0.031835 | 3.13 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4806 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019857
2429 | Task(Task)-->P (Procurement) | Building Structure |  | 1.19.2.4 | Building Structure-->ITP APPROVAL-->PROCUREMENT-->CABLE GALLERY & CABLE TRENCH-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-26 09:00 | 2020-06-01 18:00 | 2020-05-31 | 2020-08-04 18:00 |  |  | 2020-06-25 19:04 |  |  |  | 100 | 0 | [15 empty] | 57.8275 | 0.018409 | 1.81 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4807 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019858
2430 | Task(Task)-->P (Procurement) | CABLE TRAY & ACCESSORIES |  | 1.19.2.4 | CABLE TRAY & ACCESSORIES-->ITP APPROVAL-->PROCUREMENT-->CABLE GALLERY & CABLE TRENCH-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-16 | 2020-03-26 18:00 | 2020-05-30 09:00 | 2020-07-28 18:00 | [6 empty] | 100 | 0 | [15 empty] | 42.1725 | 0.013426 | 1.32 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4808 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019859
2431 | Task(Task)-->P (Procurement) | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE | 1.19.2.5 | 1.19.2 | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->CABLE GALLERY & CABLE TRENCH-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-02-16 | 2020-05-30 18:00 | 2020-05-30 09:00 | 2020-09-09 18:00 |  |  | 2020-07-06 10:19 |  |  |  | 100 | 42.1277 | [15 empty] | 14.9992 | 0.095607 | 9.4 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4809 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019860
2432 | Task(Task)-->P (Procurement) | Building Structure |  | 1.19.2.5 | Building Structure-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->CABLE GALLERY & CABLE TRENCH-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-24 | 2020-05-30 18:00 | 2020-05-31 | 2020-09-09 18:00 | [6 empty] | 100 | 0 | [15 empty] | 57.8723 | 0.05533 | 5.44 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4810 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019861
2433 | Task(Task)-->P (Procurement) | CABLE TRAY & ACCESSORIES |  | 1.19.2.5 | CABLE TRAY & ACCESSORIES-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->CABLE GALLERY & CABLE TRENCH-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-16 | 2020-03-31 18:00 | 2020-05-30 09:00 | 2020-08-08 18:00 |  |  | 2020-07-06 10:19 | 2020-08-08 13:46 |  |  | 100 | 100 | [15 empty] | 42.1277 | 0.040277 | 3.96 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4811 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019862
2434 | Task(Task)-->P (Procurement) | MANUFACTURING & RECEIPT AT SITE (MRN) | 1.19.2.6 | 1.19.2 | MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->CABLE GALLERY & CABLE TRENCH-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-01 09:00 | 2020-11-30 18:00 | 2020-08-09 | 2021-04-01 18:00 |  |  | 2020-08-09 13:53 |  |  |  | 93.6392 | 0 | [15 empty] | 60.0128 | 0.38253 | 37.61 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4812 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019863
2435 | Task(Task)-->P (Procurement) | Building Structure |  | 1.19.2.6 | Building Structure-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->CABLE GALLERY & CABLE TRENCH-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-02 09:00 | 2020-11-30 18:00 | 2020-09-09 09:00 | 2021-04-01 18:00 | [6 empty] | 89.011 | 0 | [15 empty] | 57.8835 | 0.22142 | 21.77 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4813 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019864
2436 | Task(Task)-->P (Procurement) | CABLE TRAY & ACCESSORIES |  | 1.19.2.6 | CABLE TRAY & ACCESSORIES-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->CABLE GALLERY & CABLE TRENCH-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-01 09:00 | 2020-08-10 18:00 | 2020-08-09 | 2020-12-19 18:00 |  |  | 2020-08-09 13:53 |  |  |  | 100 | 0 | [15 empty] | 42.1165 | 0.16111 | 15.84 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4814 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019865
2437 | Task(Task)-->C (Construction) | CONSTRUCTION | 1.19.3 | 1.19 | CONSTRUCTION-->CABLE GALLERY & CABLE TRENCH-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-27 09:00 | 2021-05-28 18:00 | 2020-09-02 09:00 | 2021-11-25 18:00 | [6 empty] | 54.4828 | 0 | [15 empty] | 53.2032 | 0.73716 | 72.5 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4815 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019866
2438 | Task(Task)-->C (Construction) | CIVIL | 1.19.3.1 | 1.19.3 | CIVIL-->CONSTRUCTION-->CABLE GALLERY & CABLE TRENCH-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-27 09:00 | 2020-11-02 18:00 | 2020-09-02 09:00 | 2021-02-08 18:00 | [6 empty] | 100 | 0 | [15 empty] | 54.4828 | 0.40163 | 39.5 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4816 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019867
2439 | Task(Task)-->C (Construction) | AVAILABILITY OF FRONT BY NTPC |  | 1.19.3.1 | AVAILABILITY OF FRONT BY NTPC-->CIVIL-->CONSTRUCTION-->CABLE GALLERY & CABLE TRENCH-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-27 09:00 | 2020-05-27 18:00 | 2020-09-02 09:00 | 2020-09-02 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4817 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019868
2440 | Task(Task)-->C (Construction) | EXCAVATION |  | 1.19.3.1 | EXCAVATION-->CIVIL-->CONSTRUCTION-->CABLE GALLERY & CABLE TRENCH-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-03 09:00 | 2020-07-28 18:00 | 2020-09-09 09:00 | 2020-11-03 18:00 | [6 empty] | 100 | 0 | [15 empty] | 6.7612 | 0.027155 | 2.67 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 9990 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4818 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | Excavation | [23 empty] | 1019869
2441 | Task(Task)-->C (Construction) | PCC |  | 1.19.3.1 | PCC-->CIVIL-->CONSTRUCTION-->CABLE GALLERY & CABLE TRENCH-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-18 09:00 | 2020-08-04 18:00 | 2020-09-24 09:00 | 2020-11-10 18:00 | [6 empty] | 100 | 0 | [15 empty] | 2.0765 | 0.00834 | 0.82 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 91 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4819 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | PCC | [23 empty] | 1019870
2442 | Task(Task)-->C (Construction) | CABLE GALLARY TRESTLE FOUNDATION |  | 1.19.3.1 | CABLE GALLARY TRESTLE FOUNDATION-->CIVIL-->CONSTRUCTION-->CABLE GALLERY & CABLE TRENCH-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-03 09:00 | 2020-08-19 18:00 | 2020-10-09 09:00 | 2020-11-25 18:00 | [6 empty] | 100 | 0 | [15 empty] | 8.0527 | 0.032342 | 3.18 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4820 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019871
2443 | Task(Task)-->C (Construction) | CABLE GALLARY TRESTLE PEDESTAL |  | 1.19.3.1 | CABLE GALLARY TRESTLE PEDESTAL-->CIVIL-->CONSTRUCTION-->CABLE GALLERY & CABLE TRENCH-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-28 09:00 | 2020-09-18 18:00 | 2020-11-03 09:00 | 2020-12-25 18:00 | [6 empty] | 100 | 0 | [15 empty] | 4.7607 | 0.01912 | 1.88 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 71 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4821 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019872
2444 | Task(Task)-->C (Construction) | CABLE TRENCH FOUNDATION, WALL & RCC COVER |  | 1.19.3.1 | CABLE TRENCH FOUNDATION, WALL & RCC COVER-->CIVIL-->CONSTRUCTION-->CABLE GALLERY & CABLE TRENCH-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-28 09:00 | 2020-10-03 18:00 | 2020-11-03 09:00 | 2021-01-09 18:00 | [6 empty] | 100 | 0 | [15 empty] | 16.7891 | 0.067429 | 6.63 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4822 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019873
2445 | Task(Task)-->C (Construction) | PIPE CULVERT & PULPIT |  | 1.19.3.1 | PIPE CULVERT & PULPIT-->CIVIL-->CONSTRUCTION-->CABLE GALLERY & CABLE TRENCH-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-28 09:00 | 2020-10-03 18:00 | 2020-11-03 09:00 | 2021-01-09 18:00 | [6 empty] | 100 | 0 | [15 empty] | 5.3684 | 0.021561 | 2.12 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4823 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019874
2446 | Task(Task)-->C (Construction) | BACK FILLING |  | 1.19.3.1 | BACK FILLING-->CIVIL-->CONSTRUCTION-->CABLE GALLERY & CABLE TRENCH-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-27 09:00 | 2020-11-02 18:00 | 2020-12-03 09:00 | 2021-02-08 18:00 | [6 empty] | 100 | 0 | [15 empty] | 56.1914 | 0.22568 | 22.19 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 8319 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4824 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019875
2447 | Task(Task)-->C (Construction) | STRUCTURAL | 1.19.3.2 | 1.19.3 | STRUCTURAL-->CONSTRUCTION-->CABLE GALLERY & CABLE TRENCH-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-12-01 09:00 | 2021-04-29 18:00 | 2021-04-02 09:00 | 2021-08-29 23:59 | [6 empty] | 0 | 0 | [15 empty] | 31.131 | 0.22948 | 22.57 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5264 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019876
2448 | Task(Task)-->C (Construction) | STRUCTURAL WORK |  | 1.19.3.2 | STRUCTURAL WORK-->STRUCTURAL-->CONSTRUCTION-->CABLE GALLERY & CABLE TRENCH-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-12-01 09:00 | 2021-04-29 18:00 | 2021-04-02 09:00 | 2021-08-29 23:59 | [6 empty] | 0 | 0 | [15 empty] | 100 | 0.22948 | 22.57 | Plan & Actual | Quantity | Metric Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 349 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4825 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019877
2449 | Task(Task)-->C (Construction) | ELECTRICAL | 1.19.3.3 | 1.19.3 | ELECTRICAL-->CONSTRUCTION-->CABLE GALLERY & CABLE TRENCH-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-04-15 09:00 | 2021-05-28 18:00 | 2021-08-15 | 2021-11-25 18:00 | [6 empty] | 0 | 0 | [15 empty] | 14.3862 | 0.10605 | 10.43 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5265 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019878
2450 | Task(Task)-->C (Construction) | CABLE TRAY |  | 1.19.3.3 | CABLE TRAY-->ELECTRICAL-->CONSTRUCTION-->CABLE GALLERY & CABLE TRENCH-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-04-15 09:00 | 2021-04-27 18:00 | 2021-08-15 | 2021-08-27 18:00 | [6 empty] | 0 | 0 | [15 empty] | 13.3269 | 0.014133 | 1.39 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 3250 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4826 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019879
2451 | Task(Task)-->C (Construction) | CABLE LAYING |  | 1.19.3.3 | CABLE LAYING-->ELECTRICAL-->CONSTRUCTION-->CABLE GALLERY & CABLE TRENCH-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-04-28 09:00 | 2021-05-18 18:00 | 2021-10-26 09:00 | 2021-11-15 18:00 | [6 empty] | 0 | 0 | [15 empty] | 28.9549 | 0.030706 | 3.02 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 21355 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5399 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019880
2452 | Task(Task)-->C (Construction) | EARTHING |  | 1.19.3.3 | EARTHING-->ELECTRICAL-->CONSTRUCTION-->CABLE GALLERY & CABLE TRENCH-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-04-20 09:00 | 2021-05-12 18:00 | 2021-08-20 09:00 | 2021-09-11 18:00 | [6 empty] | 0 | 0 | [15 empty] | 50.5273 | 0.053584 | 5.27 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 23600 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5400 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019881
2453 | Task(Task)-->C (Construction) | LIGHTING |  | 1.19.3.3 | LIGHTING-->ELECTRICAL-->CONSTRUCTION-->CABLE GALLERY & CABLE TRENCH-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-05-19 09:00 | 2021-05-28 18:00 | 2021-11-16 09:00 | 2021-11-25 18:00 | [6 empty] | 0 | 0 | [15 empty] | 7.1908 | 0.007626 | 0.75 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 77 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5401 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019882
2454 | Task(Task)-->E (Engineering) | TRANSMISSION LINE | 1.20 | 1 | TRANSMISSION LINE-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-09-27 09:00 | 2021-05-18 18:00 | 2019-09-27 09:00 | 2022-01-01 18:00 |  |  | 2019-09-27 10:57 |  |  |  | 90.6222 | 11.6967 | [15 empty] | 2.8466 | 2.8466 | 279.94 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4827 | 0 | 1 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019883
2455 | Task(Task)-->E (Engineering) | ENGINEERING | 1.20.1 | 1.20 | ENGINEERING-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-11-18 18:00 | 2020-06-12 17:40 | 2019-10-18 18:00 | 2020-11-15 23:59 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 17.1725 | [15 empty] | 0.63585 | 0.0181 | 1.78 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4828 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019884
2456 | Task(Task)-->E (Engineering) | CIVIL | 1.20.1.1 | 1.20.1 | CIVIL-->ENGINEERING-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-12-31 18:00 | 2020-06-12 17:40 | 2019-10-18 18:00 | 2020-08-21 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 7.2727 | [15 empty] | 38.764 | 0.007016 | 0.69 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4829 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036130
2457 | Task(Task)-->E (Engineering) | Gantry Tower : Design calculation for Sub Structure |  | 1.20.1.1 | Gantry Tower : Design calculation for Sub Structure-->CIVIL-->ENGINEERING-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-14 18:00 | 2020-06-12 17:40 | 2020-06-15 18:00 | 2020-08-21 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0041 |  | 2020-02-13 11:44 | 7012-155-PVC-U-134 |  |  |  | A |  |  |  | 9.0909 | 0.000638 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 22.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4833 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-14 18:00 | 2020-06-15 18:00 |  | 10 |  |  |  | 2020-05-02 17:40 | 2020-07-06 18:00 |  | 30 |  |  |  | 2020-05-08 17:40 | 2020-07-09 18:00 |  | 35 |  |  |  | 2020-05-15 23:59 | 2020-07-16 18:00 |  | 65 |  |  |  | 2020-05-21 17:40 | 2020-08-06 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-12 17:40 | 2020-08-06 18:00 |  | 100 | [122 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 234 |  |  |  |  | 101244
2458 | Task(Task)-->E (Engineering) | Gantry Tower : NUM & RC DETAILS (SHT 1) |  | 1.20.1.1 | Gantry Tower : NUM & RC DETAILS (SHT 1)-->CIVIL-->ENGINEERING-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-14 18:00 | 2020-06-12 17:40 | 2020-06-15 18:00 | 2020-08-21 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-NR-0049 |  | 2020-02-13 11:44 | 7012-155-PVC-C-135 |  |  |  | A |  |  |  | 9.0909 | 0.000638 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 22.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4832 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-14 18:00 | 2020-06-15 18:00 |  | 10 |  |  |  | 2020-05-02 17:40 | 2020-07-06 18:00 |  | 30 |  |  |  | 2020-05-08 17:40 | 2020-07-09 18:00 |  | 35 |  |  |  | 2020-05-15 23:59 | 2020-07-16 18:00 |  | 65 |  |  |  | 2020-05-21 17:40 | 2020-08-06 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-12 17:40 | 2020-08-06 18:00 |  | 100 | [122 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 235 |  |  |  |  | 101245
2459 | Task(Task)-->E (Engineering) | Route Survey Report (for 33kV D/C transmission line route). |  | 1.20.1.1 | Route Survey Report (for 33kV D/C transmission line route).-->CIVIL-->ENGINEERING-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-12-31 18:00 | 2020-02-29 17:40 | 2019-10-18 18:00 | 2019-12-27 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0036 |  | 2020-02-13 11:43 | 7012-155-PVC-U-126 |  |  |  | A |  |  |  | 9.0909 | 0.000638 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 22.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4830 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-12-31 18:00 | 2019-10-18 18:00 |  | 10 | 2019-10-18 23:31 |  |  | 2020-01-20 17:40 | 2019-11-12 18:00 |  | 30 | 2019-11-12 23:31 |  |  | 2020-01-25 17:40 | 2019-11-15 18:00 |  | 35 | 2019-11-15 23:31 |  |  | 2020-01-31 23:59 | 2019-11-22 18:00 |  | 65 | 2019-11-22 23:31 |  |  | 2020-02-06 17:40 | 2019-12-27 18:00 |  | 80 | 2019-12-27 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-02-29 17:40 | 2019-12-27 18:00 |  | 100 | [122 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 226 |  |  |  |  | 101236
2460 | Task(Task)-->E (Engineering) | Geotechnical Investigation Report (for 33kV D/C transmission line route). |  | 1.20.1.1 | Geotechnical Investigation Report (for 33kV D/C transmission line route).-->CIVIL-->ENGINEERING-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-28 18:00 | 2020-03-27 17:40 | 2020-06-15 18:00 | 2020-08-21 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0037 |  | 2020-02-13 11:43 | 7012-155-PVC-U-127 |  |  |  | A |  |  |  | 18.1818 | 0.001276 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 45.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4831 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-28 18:00 | 2020-06-15 18:00 |  | 10 |  |  |  | 2020-02-15 17:40 | 2020-07-06 18:00 |  | 30 |  |  |  | 2020-02-21 17:40 | 2020-07-09 18:00 |  | 35 |  |  |  | 2020-02-28 23:59 | 2020-07-16 18:00 |  | 65 |  |  |  | 2020-03-05 17:40 | 2020-08-06 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-27 17:40 | 2020-08-06 18:00 |  | 100 | [122 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 227 |  |  |  |  | 101237
2461 | Task(Task)-->E (Engineering) | 220kV Monopole Tower : Design calculation for Sub Structure |  | 1.20.1.1 | 220kV Monopole Tower : Design calculation for Sub Structure-->CIVIL-->ENGINEERING-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-26 18:00 | 2020-05-25 17:40 | 2020-06-15 18:00 | 2020-08-21 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0038 |  | 2020-02-13 11:43 | 7012-155-PVC-U-128 |  |  |  | A |  |  |  | 9.0909 | 0.000638 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 22.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4837 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-26 18:00 | 2020-06-15 18:00 |  | 10 |  |  |  | 2020-04-14 17:40 | 2020-07-06 18:00 |  | 30 |  |  |  | 2020-04-20 17:40 | 2020-07-09 18:00 |  | 35 |  |  |  | 2020-04-26 23:59 | 2020-07-16 18:00 |  | 65 |  |  |  | 2020-05-01 17:40 | 2020-08-06 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-25 17:40 | 2020-08-06 18:00 |  | 100 | [122 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 228 |  |  |  |  | 101238
2462 | Task(Task)-->E (Engineering) | 220kV Monopole Tower : NUM & RC DETAILS (SHT 1) |  | 1.20.1.1 | 220kV Monopole Tower : NUM & RC DETAILS (SHT 1)-->CIVIL-->ENGINEERING-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-26 18:00 | 2020-05-25 17:40 | 2020-06-15 18:00 | 2020-08-21 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-NR-0046 |  | 2020-02-13 11:43 | 7012-155-PVC-C-129 |  |  |  | A |  |  |  | 9.0909 | 0.000638 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 22.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4834 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-26 18:00 | 2020-06-15 18:00 |  | 10 |  |  |  | 2020-04-14 17:40 | 2020-07-06 18:00 |  | 30 |  |  |  | 2020-04-20 17:40 | 2020-07-09 18:00 |  | 35 |  |  |  | 2020-04-26 23:59 | 2020-07-16 18:00 |  | 65 |  |  |  | 2020-05-01 17:40 | 2020-08-06 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-25 17:40 | 2020-08-06 18:00 |  | 100 | [122 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 229 |  |  |  |  | 101239
2463 | Task(Task)-->E (Engineering) | 33 kV Isolator : Design calculation for Sub Structure |  | 1.20.1.1 | 33 kV Isolator : Design calculation for Sub Structure-->CIVIL-->ENGINEERING-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-02 18:00 | 2020-06-01 17:40 | 2020-06-15 18:00 | 2020-08-21 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0039 |  | 2020-02-13 11:43 | 7012-155-PVC-U-130 |  |  |  | A |  |  |  | 9.0909 | 0.000638 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 22.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4838 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-02 18:00 | 2020-06-15 18:00 |  | 10 |  |  |  | 2020-04-21 17:40 | 2020-07-06 18:00 |  | 30 |  |  |  | 2020-04-28 17:40 | 2020-07-09 18:00 |  | 35 |  |  |  | 2020-05-03 23:59 | 2020-07-16 18:00 |  | 65 |  |  |  | 2020-05-08 17:40 | 2020-08-06 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-01 17:40 | 2020-08-06 18:00 |  | 100 | [122 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 230 |  |  |  |  | 101240
2464 | Task(Task)-->E (Engineering) | 33 kV Isolator : NUM & RC DETAILS (SHT 1) |  | 1.20.1.1 | 33 kV Isolator : NUM & RC DETAILS (SHT 1)-->CIVIL-->ENGINEERING-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-02 18:00 | 2020-06-01 17:40 | 2020-06-15 18:00 | 2020-08-21 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-NR-0047 |  | 2020-02-13 11:44 | 7012-155-PVC-C-131 |  |  |  | A |  |  |  | 9.0909 | 0.000638 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 22.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4835 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-02 18:00 | 2020-06-15 18:00 |  | 10 |  |  |  | 2020-04-21 17:40 | 2020-07-06 18:00 |  | 30 |  |  |  | 2020-04-28 17:40 | 2020-07-09 18:00 |  | 35 |  |  |  | 2020-05-03 23:59 | 2020-07-16 18:00 |  | 65 |  |  |  | 2020-05-08 17:40 | 2020-08-06 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-01 17:40 | 2020-08-06 18:00 |  | 100 | [122 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 231 |  |  |  |  | 101241
2465 | Task(Task)-->E (Engineering) | 33 kV LA : Design calculation for Sub Structure |  | 1.20.1.1 | 33 kV LA : Design calculation for Sub Structure-->CIVIL-->ENGINEERING-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-02 18:00 | 2020-06-01 17:40 | 2020-06-15 18:00 | 2020-08-21 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0040 |  | 2020-02-13 11:44 | 7012-155-PVC-U-132 |  |  |  | A |  |  |  | 9.0909 | 0.000638 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 22.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4839 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-02 18:00 | 2020-06-15 18:00 |  | 10 |  |  |  | 2020-04-21 17:40 | 2020-07-06 18:00 |  | 30 |  |  |  | 2020-04-28 17:40 | 2020-07-09 18:00 |  | 35 |  |  |  | 2020-05-03 23:59 | 2020-07-16 18:00 |  | 65 |  |  |  | 2020-05-08 17:40 | 2020-08-06 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-01 17:40 | 2020-08-06 18:00 |  | 100 | [122 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 232 |  |  |  |  | 101242
2466 | Task(Task)-->E (Engineering) | 33 kV LA : NUM & RC DETAILS (SHT 1) |  | 1.20.1.1 | 33 kV LA : NUM & RC DETAILS (SHT 1)-->CIVIL-->ENGINEERING-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-02 18:00 | 2020-06-01 17:40 | 2020-06-15 18:00 | 2020-08-21 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-NR-0048 |  | 2020-02-13 11:44 | 7012-155-PVC-C-133 |  |  |  | A |  |  |  | 9.0909 | 0.000638 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 22.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4836 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-02 18:00 | 2020-06-15 18:00 |  | 10 |  |  |  | 2020-04-21 17:40 | 2020-07-06 18:00 |  | 30 |  |  |  | 2020-04-28 17:40 | 2020-07-09 18:00 |  | 35 |  |  |  | 2020-05-03 23:59 | 2020-07-16 18:00 |  | 65 |  |  |  | 2020-05-08 17:40 | 2020-08-06 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-01 17:40 | 2020-08-06 18:00 |  | 100 | [122 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 233 |  |  |  |  | 101243
2467 | Task(Task)-->E (Engineering) | ELECTRICAL | 1.20.1.2 | 1.20.1 | ELECTRICAL-->ENGINEERING-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-11-18 18:00 | 2020-05-15 17:40 | 2019-11-13 18:00 | 2020-11-15 23:59 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 23.4389 | [15 empty] | 61.236 | 0.011084 | 1.09 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4841 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036131
2468 | Task(Task)-->E (Engineering) | 6.6kV HT APFC CAPACITOR SIZING CALCULATION FOR CHP |  | 1.20.1.2 | 6.6kV HT APFC CAPACITOR SIZING CALCULATION FOR CHP-->ELECTRICAL-->ENGINEERING-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-11-18 18:00 | 2020-01-06 17:40 | 2019-11-25 18:00 | 2020-04-30 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DC-5011 |  | 2020-02-13 11:44 | 7012-155-PVE-U-011 |  |  |  | A |  |  |  | 18.0328 | 0.001999 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 82.54 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4843 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-11-18 18:00 | 2019-11-25 18:00 |  | 10 | 2019-11-25 23:31 |  |  | 2019-11-28 17:40 | 2019-12-10 18:00 |  | 30 | 2019-12-10 23:31 |  |  | 2019-12-04 17:40 | 2019-12-10 18:00 |  | 35 | 2019-12-10 23:31 |  |  | 2019-12-10 23:59 | 2019-12-13 18:00 |  | 65 | 2019-12-13 23:31 |  |  | 2019-12-16 17:40 | 2019-12-27 18:00 |  | 80 | 2019-12-27 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-01-06 17:40 | 2020-04-30 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 246 |  |  |  |  | 101257
2469 | Task(Task)-->E (Engineering) | TRANSMISSION LINE ROUTE & 220kV MONOPOLE TOWER SPOTTING PROFILE FOR 33KV D/C TRANSMISSION LINE |  | 1.20.1.2 | TRANSMISSION LINE ROUTE & 220kV MONOPOLE TOWER SPOTTING PROFILE FOR 33KV D/C TRANSMISSION LINE-->ELECTRICAL-->ENGINEERING-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-26 18:00 | 2020-05-15 17:40 | 2019-11-13 18:00 | 2020-04-05 23:59 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-100 |  | 2020-02-13 11:45 | 7012-155-PVE-V-045 |  |  |  | A |  |  |  | 9.0164 | 0.000999 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 38.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4845 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-26 18:00 | 2019-11-13 18:00 |  | 10 | 2019-11-13 23:31 |  |  | 2020-04-03 17:40 | 2019-11-20 18:00 |  | 30 | 2019-11-20 23:31 |  |  | 2020-04-09 17:40 | 2019-11-27 18:00 |  | 35 | 2019-11-27 23:31 |  |  | 2020-04-16 23:59 | 2019-12-04 18:00 |  | 65 | 2019-12-04 23:31 |  |  | 2020-04-22 17:40 | 2019-12-10 18:00 |  | 80 | 2019-12-10 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-15 17:40 | 2020-04-05 23:59 |  | 100 | 2020-05-11 23:31 | [121 empty] | Varun Parihari | [22 empty] | 280 |  |  |  |  | 101291
2470 | Task(Task)-->E (Engineering) | 33KV EQUIPMENT SUPPORT STRUCTURE-ISOLATOR |  | 1.20.1.2 | 33KV EQUIPMENT SUPPORT STRUCTURE-ISOLATOR-->ELECTRICAL-->ENGINEERING-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-24 18:00 | 2020-05-15 17:40 | 2020-06-05 18:00 | 2020-08-21 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-101 |  | 2020-02-13 11:45 | 7012-155-PVE-V-046 |  |  |  | A |  |  |  | 4.918 | 0.000545 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4846 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-24 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-04-03 17:40 | 2020-07-20 18:00 |  | 30 |  |  |  | 2020-04-09 17:40 | 2020-07-27 18:00 |  | 35 |  |  |  | 2020-04-16 23:59 | 2020-07-27 18:00 |  | 65 |  |  |  | 2020-04-22 17:40 | 2020-08-17 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-15 17:40 | 2020-08-17 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 281 |  |  |  |  | 101292
2471 | Task(Task)-->E (Engineering) | 33KV EQUIPMENT SUPPORT STRUCTURE-LA |  | 1.20.1.2 | 33KV EQUIPMENT SUPPORT STRUCTURE-LA-->ELECTRICAL-->ENGINEERING-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-24 18:00 | 2020-05-15 17:40 | 2020-06-05 18:00 | 2020-08-21 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-102 |  | 2020-02-13 11:45 | 7012-155-PVE-V-047 |  |  |  | A |  |  |  | 4.918 | 0.000545 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4847 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-24 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-04-03 17:40 | 2020-07-20 18:00 |  | 30 |  |  |  | 2020-04-09 17:40 | 2020-07-27 18:00 |  | 35 |  |  |  | 2020-04-16 23:59 | 2020-07-27 18:00 |  | 65 |  |  |  | 2020-04-22 17:40 | 2020-08-17 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-15 17:40 | 2020-08-17 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 282 |  |  |  |  | 101293
2472 | Task(Task)-->E (Engineering) | 33KV EQUIPMENT SUPPORT STRUCTURE-BPI |  | 1.20.1.2 | 33KV EQUIPMENT SUPPORT STRUCTURE-BPI-->ELECTRICAL-->ENGINEERING-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-24 18:00 | 2020-05-15 17:40 | 2020-06-05 18:00 | 2020-08-21 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-103 |  | 2020-02-13 11:45 | 7012-155-PVE-V-048 |  |  |  | A |  |  |  | 4.918 | 0.000545 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4848 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-24 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-04-03 17:40 | 2020-07-20 18:00 |  | 30 |  |  |  | 2020-04-09 17:40 | 2020-07-27 18:00 |  | 35 |  |  |  | 2020-04-16 23:59 | 2020-07-27 18:00 |  | 65 |  |  |  | 2020-04-22 17:40 | 2020-08-17 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-15 17:40 | 2020-08-17 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 283 |  |  |  |  | 101294
2473 | Task(Task)-->E (Engineering) | 33KV EQPT. PROTO CORRECTED SUPPORT STRUCTURE-ISOLATOR |  | 1.20.1.2 | 33KV EQPT. PROTO CORRECTED SUPPORT STRUCTURE-ISOLATOR-->ELECTRICAL-->ENGINEERING-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-24 18:00 | 2020-05-15 17:40 | 2020-06-05 18:00 | 2020-08-21 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-104 |  | 2020-02-13 11:45 | 7012-155-PVE-V-049 |  |  |  | A |  |  |  | 4.918 | 0.000545 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4849 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-24 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-04-03 17:40 | 2020-07-20 18:00 |  | 30 |  |  |  | 2020-04-09 17:40 | 2020-07-27 18:00 |  | 35 |  |  |  | 2020-04-16 23:59 | 2020-07-27 18:00 |  | 65 |  |  |  | 2020-04-22 17:40 | 2020-08-17 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-15 17:40 | 2020-08-17 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 284 |  |  |  |  | 101295
2474 | Task(Task)-->E (Engineering) | 33KV EQPT. PROTO CORRECTED SUPPORT STRUCTURE-LA |  | 1.20.1.2 | 33KV EQPT. PROTO CORRECTED SUPPORT STRUCTURE-LA-->ELECTRICAL-->ENGINEERING-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-24 18:00 | 2020-05-15 17:40 | 2020-06-05 18:00 | 2020-08-21 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-105 |  | 2020-02-13 11:45 | 7012-155-PVE-V-050 |  |  |  | A |  |  |  | 4.918 | 0.000545 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4850 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-24 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-04-03 17:40 | 2020-07-20 18:00 |  | 30 |  |  |  | 2020-04-09 17:40 | 2020-07-27 18:00 |  | 35 |  |  |  | 2020-04-16 23:59 | 2020-07-27 18:00 |  | 65 |  |  |  | 2020-04-22 17:40 | 2020-08-17 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-15 17:40 | 2020-08-17 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 285 |  |  |  |  | 101296
2475 | Task(Task)-->E (Engineering) | 33KV EQPT. PROTO CORRECTED SUPPORT STRUCTURE-BPI |  | 1.20.1.2 | 33KV EQPT. PROTO CORRECTED SUPPORT STRUCTURE-BPI-->ELECTRICAL-->ENGINEERING-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-24 18:00 | 2020-05-15 17:40 | 2020-06-05 18:00 | 2020-08-21 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-106 |  | 2020-02-13 11:45 | 7012-155-PVE-V-051 |  |  |  | A |  |  |  | 4.918 | 0.000545 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4851 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-24 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-04-03 17:40 | 2020-07-20 18:00 |  | 30 |  |  |  | 2020-04-09 17:40 | 2020-07-27 18:00 |  | 35 |  |  |  | 2020-04-16 23:59 | 2020-07-27 18:00 |  | 65 |  |  |  | 2020-04-22 17:40 | 2020-08-17 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-15 17:40 | 2020-08-17 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 286 |  |  |  |  | 101297
2476 | Task(Task)-->E (Engineering) | 33KV ISOLATOR -DRAWINGS |  | 1.20.1.2 | 33KV ISOLATOR -DRAWINGS-->ELECTRICAL-->ENGINEERING-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-24 18:00 | 2020-05-15 17:40 | 2020-06-05 18:00 | 2020-08-21 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-107 |  | 2020-02-13 11:45 | 7012-155-PVE-W-052 |  |  |  | A |  |  |  | 4.918 | 0.000545 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4852 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-24 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-04-03 17:40 | 2020-07-20 18:00 |  | 30 |  |  |  | 2020-04-09 17:40 | 2020-07-27 18:00 |  | 35 |  |  |  | 2020-04-16 23:59 | 2020-07-27 18:00 |  | 65 |  |  |  | 2020-04-22 17:40 | 2020-08-17 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-15 17:40 | 2020-08-17 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 287 |  |  |  |  | 101298
2477 | Task(Task)-->E (Engineering) | 33KV LA -DRAWINGS |  | 1.20.1.2 | 33KV LA -DRAWINGS-->ELECTRICAL-->ENGINEERING-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-24 18:00 | 2020-05-15 17:40 | 2020-06-05 18:00 | 2020-08-21 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-108 |  | 2020-02-13 11:45 | 7012-155-PVE-W-053 |  |  |  | A |  |  |  | 4.918 | 0.000545 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4853 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-24 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-04-03 17:40 | 2020-07-20 18:00 |  | 30 |  |  |  | 2020-04-09 17:40 | 2020-07-27 18:00 |  | 35 |  |  |  | 2020-04-16 23:59 | 2020-07-27 18:00 |  | 65 |  |  |  | 2020-04-22 17:40 | 2020-08-17 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-15 17:40 | 2020-08-17 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 288 |  |  |  |  | 101299
2478 | Task(Task)-->E (Engineering) | 33KV STRING HARDWARE -GA, PART DRAWINGS |  | 1.20.1.2 | 33KV STRING HARDWARE -GA, PART DRAWINGS-->ELECTRICAL-->ENGINEERING-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-24 18:00 | 2020-05-15 17:40 | 2020-06-05 18:00 | 2020-08-21 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-109 |  | 2020-02-13 11:45 | 7012-155-PVE-W-054 |  |  |  | A |  |  |  | 4.918 | 0.000545 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4854 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-24 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-04-03 17:40 | 2020-07-20 18:00 |  | 30 |  |  |  | 2020-04-09 17:40 | 2020-07-27 18:00 |  | 35 |  |  |  | 2020-04-16 23:59 | 2020-07-27 18:00 |  | 65 |  |  |  | 2020-04-22 17:40 | 2020-08-17 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-15 17:40 | 2020-08-17 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 289 |  |  |  |  | 101300
2479 | Task(Task)-->E (Engineering) | 33KV CLAMPS & CONNECTORS- DRAWINGS & DATA SHEET |  | 1.20.1.2 | 33KV CLAMPS & CONNECTORS- DRAWINGS & DATA SHEET-->ELECTRICAL-->ENGINEERING-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-24 18:00 | 2020-05-15 17:40 | 2020-06-05 18:00 | 2020-08-21 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-110 |  | 2020-02-13 11:45 | 7012-155-PVE-W-055 |  |  |  | A |  |  |  | 1.6393 | 0.000182 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 8.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4855 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-24 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-04-03 17:40 | 2020-07-20 18:00 |  | 30 |  |  |  | 2020-04-09 17:40 | 2020-07-27 18:00 |  | 35 |  |  |  | 2020-04-16 23:59 | 2020-07-27 18:00 |  | 65 |  |  |  | 2020-04-22 17:40 | 2020-08-17 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-15 17:40 | 2020-08-17 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 290 |  |  |  |  | 101301
2480 | Task(Task)-->E (Engineering) | 33kV D/C TRANSMISSION LINE ERECTION KEY DIAGRAM |  | 1.20.1.2 | 33kV D/C TRANSMISSION LINE ERECTION KEY DIAGRAM-->ELECTRICAL-->ENGINEERING-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-24 18:00 | 2020-05-15 17:40 | 2020-06-05 18:00 | 2020-08-21 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-111 |  | 2020-02-13 11:45 | 7012-155-PVE-E-056 |  |  |  | A |  |  |  | 4.918 | 0.000545 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4842 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-24 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-04-03 17:40 | 2020-07-20 18:00 |  | 30 |  |  |  | 2020-04-09 17:40 | 2020-07-27 18:00 |  | 35 |  |  |  | 2020-04-16 23:59 | 2020-07-27 18:00 |  | 65 |  |  |  | 2020-04-22 17:40 | 2020-08-17 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-15 17:40 | 2020-08-17 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 291 |  |  |  |  | 101302
2481 | Task(Task)-->E (Engineering) | 33KV D/C TRANSMISSION LINE- ACSR ZEBRA CONDUCTOR- DRAWINGS & DATA SHEET |  | 1.20.1.2 | 33KV D/C TRANSMISSION LINE- ACSR ZEBRA CONDUCTOR- DRAWINGS & DATA SHEET-->ELECTRICAL-->ENGINEERING-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-24 18:00 | 2020-05-15 17:40 | 2020-06-05 18:00 | 2020-08-21 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-112 |  | 2020-02-13 11:45 | 7012-155-PVE-Y-057 |  |  |  | A |  |  |  | 1.6393 | 0.000182 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 8.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4860 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-24 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-04-03 17:40 | 2020-07-20 18:00 |  | 30 |  |  |  | 2020-04-09 17:40 | 2020-07-27 18:00 |  | 35 |  |  |  | 2020-04-16 23:59 | 2020-07-27 18:00 |  | 65 |  |  |  | 2020-04-22 17:40 | 2020-08-17 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-15 17:40 | 2020-08-17 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 292 |  |  |  |  | 101303
2482 | Task(Task)-->E (Engineering) | TRANSMISSION LINE- 33KV INSULATOR- DRAWINGS & DATA SHEET |  | 1.20.1.2 | TRANSMISSION LINE- 33KV INSULATOR- DRAWINGS & DATA SHEET-->ELECTRICAL-->ENGINEERING-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-24 18:00 | 2020-05-15 17:40 | 2020-06-05 18:00 | 2020-08-21 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-113 |  | 2020-02-13 11:45 | 7012-155-PVE-Y-058 |  |  |  | A |  |  |  | 1.6393 | 0.000182 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 8.17 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4861 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-24 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-04-03 17:40 | 2020-07-20 18:00 |  | 30 |  |  |  | 2020-04-09 17:40 | 2020-07-27 18:00 |  | 35 |  |  |  | 2020-04-16 23:59 | 2020-07-27 18:00 |  | 65 |  |  |  | 2020-04-22 17:40 | 2020-08-17 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-15 17:40 | 2020-08-17 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 293 |  |  |  |  | 101304
2483 | Task(Task)-->E (Engineering) | TRANSMISSION LINE- PLACEMENT CHART OF VIBRATION DAMPERS |  | 1.20.1.2 | TRANSMISSION LINE- PLACEMENT CHART OF VIBRATION DAMPERS-->ELECTRICAL-->ENGINEERING-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-24 18:00 | 2020-05-15 17:40 | 2020-06-05 18:00 | 2020-08-21 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-114 |  | 2020-02-13 11:45 | 7012-155-PVE-W-059 |  |  |  | A |  |  |  | 1.6393 | 0.000182 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 8.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4862 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-24 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-04-03 17:40 | 2020-07-20 18:00 |  | 30 |  |  |  | 2020-04-09 17:40 | 2020-07-27 18:00 |  | 35 |  |  |  | 2020-04-16 23:59 | 2020-07-27 18:00 |  | 65 |  |  |  | 2020-04-22 17:40 | 2020-08-17 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-15 17:40 | 2020-08-17 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 294 |  |  |  |  | 101305
2484 | Task(Task)-->E (Engineering) | TRANSMISSION LINE- EARTHING DETAILS |  | 1.20.1.2 | TRANSMISSION LINE- EARTHING DETAILS-->ELECTRICAL-->ENGINEERING-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-24 18:00 | 2020-05-15 17:40 | 2020-06-05 18:00 | 2020-11-03 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-115 |  | 2020-02-13 11:45 | 7012-155-PVE-W-060 |  |  |  | A |  |  |  | 1.6393 | 0.000182 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 8.17 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4863 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-24 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-04-03 17:40 | 2020-07-20 18:00 |  | 30 |  |  |  | 2020-04-09 17:40 | 2020-07-27 18:00 |  | 35 |  |  |  | 2020-04-16 23:59 | 2020-07-27 18:00 |  | 65 |  |  |  | 2020-04-22 17:40 | 2020-08-17 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-15 17:40 | 2020-08-17 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 295 |  |  |  |  | 101306
2485 | Task(Task)-->E (Engineering) | D/C TRANSMISSION LINE- BILL OF MATERIALS |  | 1.20.1.2 | D/C TRANSMISSION LINE- BILL OF MATERIALS-->ELECTRICAL-->ENGINEERING-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-24 18:00 | 2020-05-15 17:40 | 2020-06-05 18:00 | 2020-11-15 23:59 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-116 |  | 2020-02-13 11:45 | 7012-155-PVE-W-061 |  |  |  | A |  |  |  | 1.6393 | 0.000182 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 8.17 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4864 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-24 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-04-03 17:40 | 2020-07-20 18:00 |  | 30 |  |  |  | 2020-04-09 17:40 | 2020-07-27 18:00 |  | 35 |  |  |  | 2020-04-16 23:59 | 2020-07-27 18:00 |  | 65 |  |  |  | 2020-04-22 17:40 | 2020-08-17 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-15 17:40 | 2020-08-17 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 296 |  |  |  |  | 101307
2486 | Task(Task)-->E (Engineering) | 33 KV D/C TRANSMISSION LINE- 220kV MONO POLE TOWER TYPE- DB- TYPE TESTED/ PROTO CORRECTED STRUCTAL DRAWING |  | 1.20.1.2 | 33 KV D/C TRANSMISSION LINE- 220kV MONO POLE TOWER TYPE- DB- TYPE TESTED/ PROTO CORRECTED STRUCTAL DRAWING-->ELECTRICAL-->ENGINEERING-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-24 18:00 | 2020-05-15 17:40 | 2020-06-05 18:00 | 2020-08-21 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-118 |  | 2020-02-13 11:45 | 7012-155-PVE-W-063 |  |  |  | A |  |  |  | 1.6393 | 0.000182 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 8.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4856 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-24 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-04-03 17:40 | 2020-07-20 18:00 |  | 30 |  |  |  | 2020-04-09 17:40 | 2020-07-27 18:00 |  | 35 |  |  |  | 2020-04-16 23:59 | 2020-07-27 18:00 |  | 65 |  |  |  | 2020-04-22 17:40 | 2020-08-17 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-15 17:40 | 2020-08-17 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 298 |  |  |  |  | 101309
2487 | Task(Task)-->E (Engineering) | 33 KV D/C TRANSMISSION LINE- 220kV MONO POLE TOWER TYPE- DD- TYPE TESTED/ PROTO CORRECTED STRUCTAL DRAWING |  | 1.20.1.2 | 33 KV D/C TRANSMISSION LINE- 220kV MONO POLE TOWER TYPE- DD- TYPE TESTED/ PROTO CORRECTED STRUCTAL DRAWING-->ELECTRICAL-->ENGINEERING-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-24 18:00 | 2020-05-15 17:40 | 2020-06-05 18:00 | 2020-08-21 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-119 |  | 2020-02-13 11:45 | 7012-155-PVE-W-064 |  |  |  | A |  |  |  | 1.6393 | 0.000182 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 8.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4857 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-24 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-04-03 17:40 | 2020-07-20 18:00 |  | 30 |  |  |  | 2020-04-09 17:40 | 2020-07-27 18:00 |  | 35 |  |  |  | 2020-04-16 23:59 | 2020-07-27 18:00 |  | 65 |  |  |  | 2020-04-22 17:40 | 2020-08-17 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-15 17:40 | 2020-08-17 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 299 |  |  |  |  | 101310
2488 | Task(Task)-->E (Engineering) | 33 KV D/C TRANSMISSION LINE- 220kV MONO POLE TOWER TYPE- DE- TYPE TESTED/ PROTO CORRECTED STRUCTAL DRAWING |  | 1.20.1.2 | 33 KV D/C TRANSMISSION LINE- 220kV MONO POLE TOWER TYPE- DE- TYPE TESTED/ PROTO CORRECTED STRUCTAL DRAWING-->ELECTRICAL-->ENGINEERING-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-24 18:00 | 2020-05-15 17:40 | 2020-06-05 18:00 | 2020-08-21 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-120 |  | 2020-02-13 11:45 | 7012-155-PVE-W-065 |  |  |  | A |  |  |  | 1.6393 | 0.000182 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 8.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4858 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-24 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-04-03 17:40 | 2020-07-20 18:00 |  | 30 |  |  |  | 2020-04-09 17:40 | 2020-07-27 18:00 |  | 35 |  |  |  | 2020-04-16 23:59 | 2020-07-27 18:00 |  | 65 |  |  |  | 2020-04-22 17:40 | 2020-08-17 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-15 17:40 | 2020-08-17 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 300 |  |  |  |  | 101311
2489 | Task(Task)-->E (Engineering) | 33 KV D/C TRANSMISSION LINE- SAG TENSION CALCULATION & CLEARANCE CHECK DIAGRAM |  | 1.20.1.2 | 33 KV D/C TRANSMISSION LINE- SAG TENSION CALCULATION & CLEARANCE CHECK DIAGRAM-->ELECTRICAL-->ENGINEERING-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-24 18:00 | 2020-05-15 17:40 | 2020-06-05 18:00 | 2020-09-18 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-117 |  | 2020-02-13 11:45 | 7012-155-PVE-U-062 |  |  |  | A |  |  |  | 9.0164 | 0.000999 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4844 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-24 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-04-03 17:40 | 2020-07-20 18:00 |  | 30 |  |  |  | 2020-04-09 17:40 | 2020-07-27 18:00 |  | 35 |  |  |  | 2020-04-16 23:59 | 2020-07-27 18:00 |  | 65 |  |  |  | 2020-04-22 17:40 | 2020-08-17 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-15 17:40 | 2020-08-17 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 297 |  |  |  |  | 101308
2490 | Task(Task)-->P (Procurement) | PROCUREMENT | 1.20.2 | 1.20 | PROCUREMENT-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-09-27 09:00 | 2020-11-13 18:00 | 2019-09-27 09:00 | 2021-08-20 18:00 |  |  | 2019-09-27 10:57 |  |  |  | 99.313 | 20.0012 | [15 empty] | 57.9338 | 1.6491 | 162.18 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4865 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019887
2491 | Task(Task)-->P (Procurement) | PURCHASE REQUISITION | 1.20.2.1 | 1.20.2 | PURCHASE REQUISITION-->PROCUREMENT-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Completed | No | No | 2019-09-27 09:00 | 2019-09-27 18:00 | 2019-09-27 09:00 | 2019-09-27 18:00 |  |  | 2019-09-27 10:57 | 2019-09-27 10:57 |  |  | 100 | 100 | [15 empty] | 5.0003 | 0.082461 | 8.11 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4866 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019888
2492 | Task(Task)-->P (Procurement) | 33KV OVERHEAD TRANSMISSION LINE |  | 1.20.2.1 | 33KV OVERHEAD TRANSMISSION LINE-->PURCHASE REQUISITION-->PROCUREMENT-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Completed | No | No | 2019-09-27 09:00 | 2019-09-27 18:00 | 2019-09-27 09:00 | 2019-09-27 18:00 |  |  | 2019-09-27 10:57 | 2019-09-27 10:57 |  |  | 100 | 100 | [15 empty] | 100 | 0.082461 | 8.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4867 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019889
2493 | Task(Task)-->P (Procurement) | TECHNICAL CLEARANCE | 1.20.2.2 | 1.20.2 | TECHNICAL CLEARANCE-->PROCUREMENT-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Completed | No | No | 2019-09-28 09:00 | 2019-11-15 18:00 | 2019-09-27 09:00 | 2020-03-10 18:00 |  |  | 2020-03-10 10:57 | 2020-03-10 10:57 |  |  | 100 | 100 | [15 empty] | 5.0003 | 0.082461 | 8.11 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4868 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019890
2494 | Task(Task)-->P (Procurement) | 33KV OVERHEAD TRANSMISSION LINE |  | 1.20.2.2 | 33KV OVERHEAD TRANSMISSION LINE-->TECHNICAL CLEARANCE-->PROCUREMENT-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Completed | No | No | 2019-09-28 09:00 | 2019-11-15 18:00 | 2019-09-27 09:00 | 2020-03-10 18:00 |  |  | 2020-03-10 10:57 | 2020-03-10 10:57 |  |  | 100 | 100 | [15 empty] | 100 | 0.082461 | 8.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4869 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019891
2495 | Task(Task)-->P (Procurement) | ORDERING | 1.20.2.3 | 1.20.2 | ORDERING-->PROCUREMENT-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-16 09:00 | 2019-12-27 18:00 | 2020-03-10 09:00 | 2020-08-01 18:00 |  |  | 2020-03-11 17:28 | 2020-07-07 17:28 |  |  | 100 | 100 | [15 empty] | 10.0006 | 0.16492 | 16.22 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4870 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019892
2496 | Task(Task)-->P (Procurement) | 33KV OVERHEAD TRANSMISSION LINE |  | 1.20.2.3 | 33KV OVERHEAD TRANSMISSION LINE-->ORDERING-->PROCUREMENT-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-16 09:00 | 2019-12-27 18:00 | 2020-03-10 09:00 | 2020-08-01 18:00 |  |  | 2020-03-11 17:28 | 2020-07-07 17:28 |  |  | 100 | 100 | [15 empty] | 100 | 0.16492 | 16.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4871 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019893
2497 | Task(Task)-->P (Procurement) | ITP APPROVAL | 1.20.2.4 | 1.20.2 | ITP APPROVAL-->PROCUREMENT-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-12-28 09:00 | 2020-02-05 18:00 | 2020-07-16 09:00 | 2020-12-01 18:00 |  |  | 2020-07-16 10:54 |  |  |  | 100 | 0 | [15 empty] | 5.0003 | 0.082461 | 8.11 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4872 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019894
2498 | Task(Task)-->P (Procurement) | 33KV OVERHEAD TRANSMISSION LINE |  | 1.20.2.4 | 33KV OVERHEAD TRANSMISSION LINE-->ITP APPROVAL-->PROCUREMENT-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-12-28 09:00 | 2020-02-05 18:00 | 2020-07-16 09:00 | 2020-12-01 18:00 |  |  | 2020-07-16 10:54 |  |  |  | 100 | 0 | [15 empty] | 100 | 0.082461 | 8.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4873 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019895
2499 | Task(Task)-->P (Procurement) | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE | 1.20.2.5 | 1.20.2 | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-12-28 09:00 | 2020-02-25 18:00 | 2020-07-20 09:00 | 2020-12-01 18:00 |  |  | 2020-07-20 10:53 |  |  |  | 100 | 0 | [15 empty] | 15.0009 | 0.24738 | 24.33 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4874 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019896
2500 | Task(Task)-->P (Procurement) | 33KV OVERHEAD TRANSMISSION LINE |  | 1.20.2.5 | 33KV OVERHEAD TRANSMISSION LINE-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-12-28 09:00 | 2020-02-25 18:00 | 2020-07-20 09:00 | 2020-12-01 18:00 |  |  | 2020-07-20 10:53 |  |  |  | 100 | 0 | [15 empty] | 100 | 0.24738 | 24.33 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4875 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019897
2501 | Task(Task)-->P (Procurement) | MANUFACTURING & RECEIPT AT SITE (MRN) | 1.20.2.6 | 1.20.2 | MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-26 09:00 | 2020-11-13 18:00 | 2020-12-02 09:00 | 2021-08-20 18:00 | [6 empty] | 98.855 | 0 | [15 empty] | 59.9975 | 0.98943 | 97.31 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4876 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019898
2502 | Task(Task)-->P (Procurement) | 33KV OVERHEAD TRANSMISSION LINE |  | 1.20.2.6 | 33KV OVERHEAD TRANSMISSION LINE-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-26 09:00 | 2020-11-13 18:00 | 2020-12-02 09:00 | 2021-08-20 18:00 | [6 empty] | 98.855 | 0 | [15 empty] | 100 | 0.98943 | 97.31 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4877 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019899
2503 | Task(Task)-->C (Construction) | CONSTRUCTION | 1.20.3 | 1.20 | CONSTRUCTION-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-10 | 2021-05-18 18:00 | 2020-08-15 09:00 | 2022-01-01 18:00 | [6 empty] | 78.3255 | 0 | [15 empty] | 41.4303 | 1.1793 | 115.98 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4878 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019900
2504 | Task(Task)-->C (Construction) | CIVIL | 1.20.3.1 | 1.20.3 | CIVIL-->CONSTRUCTION-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-10 | 2021-01-04 18:00 | 2020-08-15 09:00 | 2021-04-15 18:00 | [6 empty] | 97.7635 | 0 | [15 empty] | 80.1173 | 0.94485 | 92.92 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4879 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019901
2505 | Task(Task)-->C (Construction) | AVAILABILITY OF FRONT BY NTPC |  | 1.20.3.1 | AVAILABILITY OF FRONT BY NTPC-->CIVIL-->CONSTRUCTION-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-10 | 2020-05-10 23:59 | 2020-08-15 09:00 | 2020-08-15 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4880 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019902
2506 | Task(Task)-->C (Construction) | GEO TECHNICAL INVESTIGATION WORK |  | 1.20.3.1 | GEO TECHNICAL INVESTIGATION WORK-->CIVIL-->CONSTRUCTION-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-11 09:00 | 2020-07-09 18:00 | 2020-08-16 | 2020-10-14 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5275 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019903
2507 | Task(Task)-->C (Construction) | EXCAVATION |  | 1.20.3.1 | EXCAVATION-->CIVIL-->CONSTRUCTION-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-05 09:00 | 2020-10-09 18:00 | 2020-08-22 09:00 | 2020-12-26 18:00 | [6 empty] | 100 | 0 | [15 empty] | 7.232 | 0.068332 | 6.72 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 25202 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4881 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | Excavation | [23 empty] | 1019904
2508 | Task(Task)-->C (Construction) | PCC |  | 1.20.3.1 | PCC-->CIVIL-->CONSTRUCTION-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-15 09:00 | 2020-10-16 18:00 | 2020-09-24 09:00 | 2021-01-25 18:00 | [6 empty] | 100 | 0 | [15 empty] | 2.6797 | 0.025319 | 2.49 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 275 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4882 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | PCC | [23 empty] | 1019905
2509 | Task(Task)-->C (Construction) | MONOPOLE FOUNDATION - RCC (21 FOUNDATIONS) |  | 1.20.3.1 | MONOPOLE FOUNDATION - RCC (21 FOUNDATIONS)-->CIVIL-->CONSTRUCTION-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-22 09:00 | 2020-11-10 18:00 | 2020-10-01 09:00 | 2021-02-19 18:00 | [6 empty] | 100 | 0 | [15 empty] | 79.2617 | 0.74891 | 73.65 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4883 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019906
2510 | Task(Task)-->C (Construction) | MONOPOLE PEDESTAL |  | 1.20.3.1 | MONOPOLE PEDESTAL-->CIVIL-->CONSTRUCTION-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-29 09:00 | 2020-12-05 18:00 | 2020-10-08 09:00 | 2021-03-16 18:00 | [6 empty] | 84.375 | 0 | [15 empty] | 7.9208 | 0.07484 | 7.36 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4884 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019907
2511 | Task(Task)-->C (Construction) | BACK FILLING |  | 1.20.3.1 | BACK FILLING-->CIVIL-->CONSTRUCTION-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-29 09:00 | 2021-01-04 18:00 | 2020-11-07 09:00 | 2021-04-15 18:00 | [6 empty] | 65.625 | 0 | [15 empty] | 2.9057 | 0.027455 | 2.7 | Plan & Actual | Quantity | Cubic Meter | 0 | 0 | 0 | 0 | 0 | 0 | 22452 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4885 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019908
2512 | Task(Task)-->C (Construction) | ELECTRICAL & INSTRUMENTATION | 1.20.3.2 | 1.20.3 | ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-01-05 09:00 | 2021-04-18 23:59 | 2021-04-16 09:00 | 2021-12-02 18:00 | [6 empty] | 0 | 0 | [15 empty] | 18.5549 | 0.21882 | 21.52 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4886 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019909
2513 | Task(Task)-->C (Construction) | CABLE TRAY |  | 1.20.3.2 | CABLE TRAY-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-01-05 09:00 | 2021-01-18 18:00 | 2021-04-16 09:00 | 2021-04-29 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0.41783 | 0.000914 | 0.09 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4887 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019910
2514 | Task(Task)-->C (Construction) | CABLE LAYING |  | 1.20.3.2 | CABLE LAYING-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-02-04 09:00 | 2021-02-17 18:00 | 2021-10-26 09:00 | 2021-11-08 18:00 | [6 empty] | 0 | 0 | [15 empty] | 4.5961 | 0.010057 | 0.99 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 7000 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4888 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019911
2515 | Task(Task)-->C (Construction) | EARTHING |  | 1.20.3.2 | EARTHING-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-02-09 09:00 | 2021-02-22 18:00 | 2021-10-26 09:00 | 2021-11-08 18:00 | [6 empty] | 0 | 0 | [15 empty] | 8.3101 | 0.018185 | 1.79 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5251 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019912
2516 | Task(Task)-->C (Construction) | EARTH PIT |  | 1.20.3.2 | EARTH PIT-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-02-09 09:00 | 2021-02-22 18:00 | 2021-10-26 09:00 | 2021-11-08 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4889 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019913
2517 | Task(Task)-->C (Construction) | LIGHTING |  | 1.20.3.2 | LIGHTING-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-02-23 09:00 | 2021-03-08 18:00 | 2021-11-09 09:00 | 2021-11-22 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0.7428 | 0.001625 | 0.16 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5402 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019914
2518 | Task(Task)-->C (Construction) | ERECTION OF MONOPOLES |  | 1.20.3.2 | ERECTION OF MONOPOLES-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-01-05 09:00 | 2021-03-05 18:00 | 2021-08-21 09:00 | 2021-10-19 18:00 | [6 empty] | 0 | 0 | [15 empty] | 59.2386 | 0.12963 | 12.76 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5403 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019915
2519 | Task(Task)-->C (Construction) | STRINGING OF CONDUCTOR |  | 1.20.3.2 | STRINGING OF CONDUCTOR-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-02-04 09:00 | 2021-04-04 23:59 | 2021-09-20 09:00 | 2021-11-18 18:00 | [6 empty] | 0 | 0 | [15 empty] | 26.6945 | 0.058414 | 5.75 | Plan & Actual | Quantity | RM | 0 | 0 | 0 | 0 | 0 | 0 | 28000 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5404 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019916
2520 | Task(Task)-->C (Construction) | GANTRY WORK AT SUB-STATION |  | 1.20.3.2 | GANTRY WORK AT SUB-STATION-->ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-02-18 09:00 | 2021-04-18 23:59 | 2021-10-04 09:00 | 2021-12-02 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5561 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019917
2521 | Task(Task)-->C (Construction) | TESTING & CHARGING FOR LOAD & TRIAL OPERATION |  | 1.20.3 | TESTING & CHARGING FOR LOAD & TRIAL OPERATION-->CONSTRUCTION-->TRANSMISSION LINE-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-04-19 09:00 | 2021-05-18 18:00 | 2021-12-03 09:00 | 2022-01-01 18:00 | [6 empty] | 0 | 0 | [15 empty] | 1.3278 | 0.015659 | 1.54 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5405 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019918
2522 | Task(Task)-->E (Engineering) | UTILITY- VENTILATION & AIR CONDITIONING | 1.21 | 1 | UTILITY- VENTILATION & AIR CONDITIONING-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-09-27 09:00 | 2021-09-09 18:00 | 2019-09-27 09:00 | 2022-05-02 18:00 |  |  | 2019-09-27 10:57 |  |  |  | 57.2933 | 18.8223 | [15 empty] | 0.92136 | 0.92136 | 90.61 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4890 | 0 | 1 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019919
2523 | Task(Task)-->E (Engineering) | ENGINEERING | 1.21.1 | 1.21 | ENGINEERING-->UTILITY- VENTILATION & AIR CONDITIONING-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-07 18:00 | 2020-06-11 17:40 | 2020-05-16 18:00 | 2020-10-05 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 70.6512 | [15 empty] | 2.3731 | 0.021865 | 2.15 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4891 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019920
2524 | Task(Task)-->E (Engineering) | MECHANICAL | 1.21.1.1 | 1.21.1 | MECHANICAL-->ENGINEERING-->UTILITY- VENTILATION & AIR CONDITIONING-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-07 18:00 | 2020-06-11 17:40 | 2020-05-16 18:00 | 2020-10-05 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 70.6512 | [15 empty] | 100 | 0.021865 | 2.15 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4892 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036132
2525 | Task(Task)-->E (Engineering) | DESIGN BASIS REPORT FOR DRY TYPE PRESSURISATION VENTILATION SYSTEM |  | 1.21.1.1 | DESIGN BASIS REPORT FOR DRY TYPE PRESSURISATION VENTILATION SYSTEM-->MECHANICAL-->ENGINEERING-->UTILITY- VENTILATION & AIR CONDITIONING-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-07 18:00 | 2020-04-13 17:40 | 2020-05-16 18:00 | 2020-07-25 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-VS-DB-6002 |  | 2020-02-13 11:40 | 7012-155-PVM-L-032 |  |  |  | A |  |  |  | 31.1628 | 0.006814 | 0.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 250 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4894 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-07 18:00 | 2020-05-16 18:00 |  | 10 |  |  |  | 2020-03-02 17:40 | 2020-06-06 18:00 |  | 30 |  |  |  | 2020-03-07 17:40 | 2020-06-13 18:00 |  | 35 | 2020-06-25 10:27 |  |  | 2020-03-13 23:59 | 2020-06-20 18:00 |  | 65 | 2020-08-22 12:47 |  |  | 2020-03-20 17:40 | 2020-07-11 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-13 17:40 | 2020-07-25 18:00 |  | 100 | [122 empty] | Ram Prasad Roy | [5 empty] | U - Water Media & Utility System | [16 empty] | 77 |  |  |  |  | 101091
2526 | Task(Task)-->E (Engineering) | DESIGN BASIS FOR AIR CONDITIONING SYSTEM |  | 1.21.1.1 | DESIGN BASIS FOR AIR CONDITIONING SYSTEM-->MECHANICAL-->ENGINEERING-->UTILITY- VENTILATION & AIR CONDITIONING-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-21 18:00 | 2020-04-27 17:40 | 2020-05-18 18:00 | 2020-07-27 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-AC-DB-6003 |  | 2020-02-13 11:40 | 7012-155-PVM-L-033 |  |  |  | A |  |  |  | 31.1628 | 0.006814 | 0.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 250 | 0 | 2.15 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4896 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-21 18:00 | 2020-05-18 18:00 |  | 10 |  |  |  | 2020-03-16 17:40 | 2020-06-08 18:00 |  | 30 |  |  |  | 2020-03-21 17:40 | 2020-06-15 18:00 |  | 35 | 2020-07-04 14:25 |  |  | 2020-03-27 23:59 | 2020-06-22 18:00 |  | 65 | 2020-08-22 12:50 |  |  | 2020-04-03 17:40 | 2020-07-13 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-27 17:40 | 2020-07-27 18:00 |  | 100 | [122 empty] | Ram Prasad Roy | [5 empty] | U - Water Media & Utility System | [16 empty] | 78 |  |  |  |  | 101092
2527 | Task(Task)-->E (Engineering) | GA, CS, DATA SHEET & CURVE OF SUPPLY & EXHAUST FANS FOR VENTILATION SYSTEM |  | 1.21.1.1 | GA, CS, DATA SHEET & CURVE OF SUPPLY & EXHAUST FANS FOR VENTILATION SYSTEM-->MECHANICAL-->ENGINEERING-->UTILITY- VENTILATION & AIR CONDITIONING-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-19 18:00 | 2020-05-11 17:40 | 2020-08-20 18:00 | 2020-10-05 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-VS-GA-6201 |  | 2020-02-13 11:40 | 7012-155-PVM-B-152 |  |  |  | A |  |  |  | 25.1163 | 0.005492 | 0.54 | Plan & Actual | Date |  | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4893 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-19 18:00 | 2020-08-20 18:00 |  | 10 |  |  |  | 2020-03-31 17:40 | 2020-09-04 18:00 |  | 30 |  |  |  | 2020-04-06 17:40 | 2020-09-08 18:00 |  | 35 |  |  |  | 2020-04-11 23:59 | 2020-09-12 18:00 |  | 65 | 2020-08-22 12:42 |  |  | 2020-04-17 17:40 | 2020-10-03 18:00 |  | 80 | 2020-09-09 10:31 | [5 empty] | 80 | 2020-09-17 12:06 | [5 empty] | 80 | 2020-09-17 12:06 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-11 17:40 | 2020-10-03 18:00 |  | 100 | [122 empty] | Ram Prasad Roy | [5 empty] | U - Water Media & Utility System | [16 empty] | 92 |  |  |  |  | 101106
2528 | Task(Task)-->E (Engineering) | DATA SHEET & GA DRG OF AIR CONDITIONERS |  | 1.21.1.1 | DATA SHEET & GA DRG OF AIR CONDITIONERS-->MECHANICAL-->ENGINEERING-->UTILITY- VENTILATION & AIR CONDITIONING-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-15 18:00 | 2020-06-11 17:40 | 2020-08-10 18:00 | 2020-10-05 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-AC-GA-6401 |  | 2020-02-13 11:40 | 7012-155-PVM-B-160 |  |  |  | A |  |  |  | 12.5581 | 0.002746 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4895 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-15 18:00 | 2020-08-10 18:00 |  | 10 |  |  |  | 2020-05-01 17:40 | 2020-08-25 18:00 |  | 30 |  |  |  | 2020-05-07 17:40 | 2020-09-01 18:00 |  | 35 |  |  |  | 2020-05-14 23:59 | 2020-09-08 18:00 |  | 65 | 2020-08-22 12:45 |  |  | 2020-05-20 17:40 | 2020-09-29 18:00 |  | 80 | 2020-09-10 17:23 | [5 empty] | 80 | 2020-09-28 10:18 | [5 empty] | 80 | 2020-09-28 10:18 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-11 17:40 | 2020-09-29 18:00 |  | 100 | [122 empty] | Ram Prasad Roy | [5 empty] | U - Water Media & Utility System | [16 empty] | 100 |  |  |  |  | 101114
2529 | Task(Task)-->E (Engineering) | ELECTRICAL | 1.21.1.2 | 1.21.1 | ELECTRICAL-->ENGINEERING-->UTILITY- VENTILATION & AIR CONDITIONING-->NTPC's CHP KERENDARI | Unscheduled | No | No | [10 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4898 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036133
2530 | Task(Task)-->P (Procurement) | PROCUREMENT | 1.21.2 | 1.21 | PROCUREMENT-->UTILITY- VENTILATION & AIR CONDITIONING-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-09-27 09:00 | 2021-03-15 18:00 | 2019-09-27 09:00 | 2021-06-29 18:00 |  |  | 2019-09-27 10:57 |  |  |  | 64.0465 | 19.9948 | [15 empty] | 85.7506 | 0.79007 | 77.69 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4899 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019923
2531 | Task(Task)-->P (Procurement) | PURCHASE REQUISITION | 1.21.2.1 | 1.21.2 | PURCHASE REQUISITION-->PROCUREMENT-->UTILITY- VENTILATION & AIR CONDITIONING-->NTPC's CHP KERENDARI | Completed | No | No | 2019-09-27 09:00 | 2019-09-27 18:00 | 2019-09-27 09:00 | 2019-09-27 18:00 |  |  | 2019-09-27 10:57 | 2019-09-27 10:57 |  |  | 100 | 100 | [15 empty] | 4.9955 | 0.039468 | 3.88 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4900 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019924
2532 | Task(Task)-->P (Procurement) | Ventilation System |  | 1.21.2.1 | Ventilation System-->PURCHASE REQUISITION-->PROCUREMENT-->UTILITY- VENTILATION & AIR CONDITIONING-->NTPC's CHP KERENDARI | Completed | No | No | 2019-09-27 09:00 | 2019-09-27 18:00 | 2019-09-27 09:00 | 2019-09-27 18:00 |  |  | 2019-09-27 10:57 | 2019-09-27 10:57 |  |  | 100 | 100 | [15 empty] | 19.0231 | 0.007508 | 0.74 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4901 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019925
2533 | Task(Task)-->P (Procurement) | AC System |  | 1.21.2.1 | AC System-->PURCHASE REQUISITION-->PROCUREMENT-->UTILITY- VENTILATION & AIR CONDITIONING-->NTPC's CHP KERENDARI | Completed | No | No | 2019-09-27 09:00 | 2019-09-27 18:00 | 2019-09-27 09:00 | 2019-09-27 18:00 |  |  | 2019-09-27 10:57 | 2019-09-27 10:57 |  |  | 100 | 100 | [15 empty] | 80.9769 | 0.03196 | 3.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4902 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019926
2534 | Task(Task)-->P (Procurement) | TECHNICAL CLEARANCE | 1.21.2.2 | 1.21.2 | TECHNICAL CLEARANCE-->PROCUREMENT-->UTILITY- VENTILATION & AIR CONDITIONING-->NTPC's CHP KERENDARI | Completed | No | No | 2019-09-28 09:00 | 2020-04-04 18:00 | 2019-09-27 09:00 | 2020-04-10 18:00 |  |  | 2020-04-09 10:57 | 2020-04-10 10:57 |  |  | 100 | 100 | [15 empty] | 4.9955 | 0.039468 | 3.88 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4903 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019927
2535 | Task(Task)-->P (Procurement) | Ventilation System |  | 1.21.2.2 | Ventilation System-->TECHNICAL CLEARANCE-->PROCUREMENT-->UTILITY- VENTILATION & AIR CONDITIONING-->NTPC's CHP KERENDARI | Completed | No | No | 2019-09-28 09:00 | 2020-02-26 18:00 | 2019-09-27 09:00 | 2020-04-10 18:00 |  |  | 2020-04-10 10:57 | 2020-04-10 10:57 |  |  | 100 | 100 | [15 empty] | 19.0231 | 0.007508 | 0.74 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4904 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019928
2536 | Task(Task)-->P (Procurement) | AC System |  | 1.21.2.2 | AC System-->TECHNICAL CLEARANCE-->PROCUREMENT-->UTILITY- VENTILATION & AIR CONDITIONING-->NTPC's CHP KERENDARI | Completed | No | No | 2019-09-28 09:00 | 2020-04-04 18:00 | 2019-09-27 09:00 | 2020-04-09 18:00 |  |  | 2020-04-09 10:57 | 2020-04-09 10:57 |  |  | 100 | 100 | [15 empty] | 80.9769 | 0.03196 | 3.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4905 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019929
2537 | Task(Task)-->P (Procurement) | ORDERING | 1.21.2.3 | 1.21.2 | ORDERING-->PROCUREMENT-->UTILITY- VENTILATION & AIR CONDITIONING-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-27 09:00 | 2020-04-29 18:00 | 2020-04-09 09:00 | 2020-06-11 18:00 |  |  | 2020-06-11 10:57 | 2020-06-11 10:57 |  |  | 100 | 100 | [15 empty] | 10.0039 | 0.079038 | 7.77 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4906 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019930
2538 | Task(Task)-->P (Procurement) | Ventilation System |  | 1.21.2.3 | Ventilation System-->ORDERING-->PROCUREMENT-->UTILITY- VENTILATION & AIR CONDITIONING-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-27 09:00 | 2020-03-27 18:00 | 2020-04-10 09:00 | 2020-06-11 18:00 |  |  | 2020-06-11 10:57 | 2020-06-11 10:57 |  |  | 100 | 100 | [15 empty] | 18.9189 | 0.014953 | 1.47 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4907 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019931
2539 | Task(Task)-->P (Procurement) | AC System |  | 1.21.2.3 | AC System-->ORDERING-->PROCUREMENT-->UTILITY- VENTILATION & AIR CONDITIONING-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-05 | 2020-04-29 18:00 | 2020-04-09 09:00 | 2020-06-11 18:00 |  |  | 2020-06-11 10:57 | 2020-06-11 10:57 |  |  | 100 | 100 | [15 empty] | 81.0811 | 0.064085 | 6.3 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4908 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019932
2540 | Task(Task)-->P (Procurement) | ITP APPROVAL | 1.21.2.4 | 1.21.2 | ITP APPROVAL-->PROCUREMENT-->UTILITY- VENTILATION & AIR CONDITIONING-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-28 09:00 | 2020-06-28 23:59 | 2020-06-11 09:00 | 2020-12-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 4.9955 | 0.039468 | 3.88 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4909 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019933
2541 | Task(Task)-->P (Procurement) | Ventilation System |  | 1.21.2.4 | Ventilation System-->ITP APPROVAL-->PROCUREMENT-->UTILITY- VENTILATION & AIR CONDITIONING-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-28 09:00 | 2020-05-26 18:00 | 2020-06-11 09:00 | 2020-12-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 19.0231 | 0.007508 | 0.74 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4910 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019934
2542 | Task(Task)-->P (Procurement) | AC System |  | 1.21.2.4 | AC System-->ITP APPROVAL-->PROCUREMENT-->UTILITY- VENTILATION & AIR CONDITIONING-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-30 09:00 | 2020-06-28 23:59 | 2020-06-11 09:00 | 2020-12-01 18:00 | [6 empty] | 100 | 0 | [15 empty] | 80.9769 | 0.03196 | 3.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4911 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019935
2543 | Task(Task)-->P (Procurement) | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE | 1.21.2.5 | 1.21.2 | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->UTILITY- VENTILATION & AIR CONDITIONING-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-28 09:00 | 2020-09-26 18:00 | 2020-06-11 09:00 | 2020-10-12 18:00 | [6 empty] | 100 | 0 | [15 empty] | 14.9994 | 0.11851 | 11.65 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4912 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019936
2544 | Task(Task)-->P (Procurement) | Ventilation System |  | 1.21.2.5 | Ventilation System-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->UTILITY- VENTILATION & AIR CONDITIONING-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-28 09:00 | 2020-08-24 18:00 | 2020-06-11 09:00 | 2020-10-06 18:00 | [6 empty] | 100 | 0 | [15 empty] | 18.9537 | 0.022461 | 2.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4913 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019937
2545 | Task(Task)-->P (Procurement) | AC System |  | 1.21.2.5 | AC System-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->UTILITY- VENTILATION & AIR CONDITIONING-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-30 09:00 | 2020-09-26 18:00 | 2020-06-11 09:00 | 2020-10-12 18:00 | [6 empty] | 100 | 0 | [15 empty] | 81.0463 | 0.096045 | 9.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4914 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019938
2546 | Task(Task)-->P (Procurement) | MANUFACTURING & RECEIPT AT SITE (MRN) | 1.21.2.6 | 1.21.2 | MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->UTILITY- VENTILATION & AIR CONDITIONING-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-18 09:00 | 2021-03-15 18:00 | 2020-12-02 09:00 | 2021-06-29 18:00 | [6 empty] | 40.0878 | 0 | [15 empty] | 60.0103 | 0.47413 | 46.61 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4915 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019939
2547 | Task(Task)-->P (Procurement) | Ventilation System |  | 1.21.2.6 | Ventilation System-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->UTILITY- VENTILATION & AIR CONDITIONING-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-25 09:00 | 2021-03-15 18:00 | 2020-12-02 09:00 | 2021-06-22 18:00 | [6 empty] | 38.4237 | 0 | [15 empty] | 18.923 | 0.089719 | 8.82 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4916 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019940
2548 | Task(Task)-->P (Procurement) | AC System |  | 1.21.2.6 | AC System-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->UTILITY- VENTILATION & AIR CONDITIONING-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-18 09:00 | 2021-03-15 18:00 | 2020-12-02 09:00 | 2021-06-29 18:00 | [6 empty] | 40.4762 | 0 | [15 empty] | 81.077 | 0.38441 | 37.79 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4917 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019941
2549 | Task(Task)-->C (Construction) | CONSTRUCTION | 1.21.3 | 1.21 | CONSTRUCTION-->UTILITY- VENTILATION & AIR CONDITIONING-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-03-16 09:00 | 2021-09-09 18:00 | 2021-06-23 09:00 | 2022-05-02 18:00 | [6 empty] | 0 | 0 | [15 empty] | 11.8764 | 0.10942 | 10.76 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4918 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019942
2550 | Task(Task)-->C (Construction) | MECHANICAL | 1.21.3.1 | 1.21.3 | MECHANICAL-->CONSTRUCTION-->UTILITY- VENTILATION & AIR CONDITIONING-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-03-16 09:00 | 2021-06-30 18:00 | 2021-06-23 09:00 | 2021-11-27 18:00 | [6 empty] | 0 | 0 | [15 empty] | 57.1031 | 0.062485 | 6.15 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4924 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019943
2551 | Task(Task)-->C (Construction) | ERECTION OF VENTILATION DUCT FOR SS-1 |  | 1.21.3.1 | ERECTION OF VENTILATION DUCT FOR SS-1-->MECHANICAL-->CONSTRUCTION-->UTILITY- VENTILATION & AIR CONDITIONING-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-04-17 09:00 | 2021-06-15 18:00 | 2021-09-16 09:00 | 2021-11-14 23:59 | [6 empty] | 0 | 0 | [15 empty] | 18.9233 | 0.011824 | 1.16 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5270 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019944
2552 | Task(Task)-->C (Construction) | ERECTION OF FANS (SUPPLY) FOR SS-1 |  | 1.21.3.1 | ERECTION OF FANS (SUPPLY) FOR SS-1-->MECHANICAL-->CONSTRUCTION-->UTILITY- VENTILATION & AIR CONDITIONING-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-03-16 09:00 | 2021-03-29 18:00 | 2021-06-23 09:00 | 2021-07-06 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0.97879 | 0.000612 | 0.06 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5440 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019945
2553 | Task(Task)-->C (Construction) | ERECTION OF FANS (EXHAUST) FOR SS-1 |  | 1.21.3.1 | ERECTION OF FANS (EXHAUST) FOR SS-1-->MECHANICAL-->CONSTRUCTION-->UTILITY- VENTILATION & AIR CONDITIONING-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-04-17 09:00 | 2021-04-30 18:00 | 2021-09-16 09:00 | 2021-09-29 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0.16313 | 0.000102 | 0.01 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5441 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019946
2554 | Task(Task)-->C (Construction) | ERECTION OF VENTILATION DUCT FOR SS-2 |  | 1.21.3.1 | ERECTION OF VENTILATION DUCT FOR SS-2-->MECHANICAL-->CONSTRUCTION-->UTILITY- VENTILATION & AIR CONDITIONING-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-04-22 09:00 | 2021-06-05 18:00 | 2021-10-14 09:00 | 2021-11-27 18:00 | [6 empty] | 0 | 0 | [15 empty] | 18.9233 | 0.011824 | 1.16 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5562 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019947
2555 | Task(Task)-->C (Construction) | ERECTION OF FANS (SUPPLY) FOR SS-2 |  | 1.21.3.1 | ERECTION OF FANS (SUPPLY) FOR SS-2-->MECHANICAL-->CONSTRUCTION-->UTILITY- VENTILATION & AIR CONDITIONING-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-03-16 09:00 | 2021-03-29 18:00 | 2021-07-04 | 2021-07-17 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0.97879 | 0.000612 | 0.06 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5563 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019948
2556 | Task(Task)-->C (Construction) | ERECTION OF FANS (EXHAUST) FOR SS-2 |  | 1.21.3.1 | ERECTION OF FANS (EXHAUST) FOR SS-2-->MECHANICAL-->CONSTRUCTION-->UTILITY- VENTILATION & AIR CONDITIONING-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-04-22 09:00 | 2021-05-01 18:00 | 2021-10-14 09:00 | 2021-10-23 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0.16313 | 0.000102 | 0.01 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5564 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019949
2557 | Task(Task)-->C (Construction) | ERECTION OF VENTILATION DUCT FOR SS-3 |  | 1.21.3.1 | ERECTION OF VENTILATION DUCT FOR SS-3-->MECHANICAL-->CONSTRUCTION-->UTILITY- VENTILATION & AIR CONDITIONING-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-05-17 09:00 | 2021-06-30 18:00 | 2021-10-14 09:00 | 2021-11-27 18:00 | [6 empty] | 0 | 0 | [15 empty] | 18.9233 | 0.011824 | 1.16 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5565 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019950
2558 | Task(Task)-->C (Construction) | ERECTION OF FANS (SUPPLY) FOR SS-3 |  | 1.21.3.1 | ERECTION OF FANS (SUPPLY) FOR SS-3-->MECHANICAL-->CONSTRUCTION-->UTILITY- VENTILATION & AIR CONDITIONING-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-03-16 09:00 | 2021-03-29 18:00 | 2021-07-04 | 2021-07-17 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0.97879 | 0.000612 | 0.06 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5566 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019951
2559 | Task(Task)-->C (Construction) | ERECTION OF FANS (EXHAUST) FOR SS-3 |  | 1.21.3.1 | ERECTION OF FANS (EXHAUST) FOR SS-3-->MECHANICAL-->CONSTRUCTION-->UTILITY- VENTILATION & AIR CONDITIONING-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-05-17 09:00 | 2021-05-26 18:00 | 2021-10-14 09:00 | 2021-10-23 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0.16313 | 0.000102 | 0.01 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5567 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019952
2560 | Task(Task)-->C (Construction) | INSTALLATION OF AC FOR SS-1 |  | 1.21.3.1 | INSTALLATION OF AC FOR SS-1-->MECHANICAL-->CONSTRUCTION-->UTILITY- VENTILATION & AIR CONDITIONING-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-03-16 09:00 | 2021-03-30 18:00 | 2021-06-30 09:00 | 2021-07-14 18:00 | [6 empty] | 0 | 0 | [15 empty] | 9.1354 | 0.005708 | 0.56 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5442 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | Installation | [23 empty] | 1019953
2561 | Task(Task)-->C (Construction) | INSTALLATION OF AC FOR SS-2 |  | 1.21.3.1 | INSTALLATION OF AC FOR SS-2-->MECHANICAL-->CONSTRUCTION-->UTILITY- VENTILATION & AIR CONDITIONING-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-03-16 09:00 | 2021-04-01 18:00 | 2021-07-04 | 2021-07-20 18:00 | [6 empty] | 0 | 0 | [15 empty] | 18.4339 | 0.011518 | 1.13 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5443 | 0 | 4 | Low | [7 empty] | 0 | 0 | [222 empty] | Installation | [23 empty] | 1019954
2562 | Task(Task)-->C (Construction) | INSTALATION OF AC FOR SS-3 |  | 1.21.3.1 | INSTALATION OF AC FOR SS-3-->MECHANICAL-->CONSTRUCTION-->UTILITY- VENTILATION & AIR CONDITIONING-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-03-16 09:00 | 2021-03-30 18:00 | 2021-07-04 | 2021-07-18 23:59 | [6 empty] | 0 | 0 | [15 empty] | 12.2349 | 0.007645 | 0.75 | Plan & Actual | Quantity | Numbers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5444 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019955
2563 | Task(Task)-->C (Construction) | ELECTRICAL WORKS | 1.21.3.2 | 1.21.3 | ELECTRICAL WORKS-->CONSTRUCTION-->UTILITY- VENTILATION & AIR CONDITIONING-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-05-01 09:00 | 2021-06-25 18:00 | 2021-09-30 09:00 | 2021-11-22 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5570 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019956
2564 | Task(Task)-->C (Construction) | ELECTRICAL & INSTRUMENTATION FOR SS-1 |  | 1.21.3.2 | ELECTRICAL & INSTRUMENTATION FOR SS-1-->ELECTRICAL WORKS-->CONSTRUCTION-->UTILITY- VENTILATION & AIR CONDITIONING-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-05-01 09:00 | 2021-05-30 23:59 | 2021-09-30 09:00 | 2021-10-29 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5271 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019957
2565 | Task(Task)-->C (Construction) | ELECTRICAL & INSTRUMENTATION FOR SS-2 |  | 1.21.3.2 | ELECTRICAL & INSTRUMENTATION FOR SS-2-->ELECTRICAL WORKS-->CONSTRUCTION-->UTILITY- VENTILATION & AIR CONDITIONING-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-05-02 | 2021-05-31 18:00 | 2021-10-24 | 2021-11-22 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5568 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019958
2566 | Task(Task)-->C (Construction) | ELECTRICAL & INSTRUMENTATION FOR SS-2 |  | 1.21.3.2 | ELECTRICAL & INSTRUMENTATION FOR SS-2-->ELECTRICAL WORKS-->CONSTRUCTION-->UTILITY- VENTILATION & AIR CONDITIONING-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-05-27 09:00 | 2021-06-25 18:00 | 2021-10-24 | 2021-11-22 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5569 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019959
2567 | Task(Task)-->C (Construction) | NO LOAD COMMISSIONING & SYSTEM READYNESS FOR TRIAL OPERATION | 1.21.3.3 | 1.21.3 | NO LOAD COMMISSIONING & SYSTEM READYNESS FOR TRIAL OPERATION-->CONSTRUCTION-->UTILITY- VENTILATION & AIR CONDITIONING-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-08-22 | 2021-09-09 18:00 | 2022-03-20 | 2022-05-02 18:00 | [6 empty] | 0 | 0 | [15 empty] | 42.8969 | 0.04694 | 4.62 |  | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5272 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019960
2568 | Task(Task)-->C (Construction) | SS-1 & CONTROL ROOM |  | 1.21.3.3 | SS-1 & CONTROL ROOM-->NO LOAD COMMISSIONING & SYSTEM READYNESS FOR TRIAL OPERATION-->CONSTRUCTION-->UTILITY- VENTILATION & AIR CONDITIONING-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-08-22 | 2021-09-04 18:00 | 2022-04-14 09:00 | 2022-04-27 18:00 | [6 empty] | 0 | 0 | [15 empty] | 33.3333 | 0.015647 | 1.54 | Plan & Actual | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5572 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019961
2569 | Task(Task)-->C (Construction) | SS-2 |  | 1.21.3.3 | SS-2-->NO LOAD COMMISSIONING & SYSTEM READYNESS FOR TRIAL OPERATION-->CONSTRUCTION-->UTILITY- VENTILATION & AIR CONDITIONING-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-08-27 09:00 | 2021-09-09 18:00 | 2022-04-19 09:00 | 2022-05-02 18:00 | [6 empty] | 0 | 0 | [15 empty] | 33.3333 | 0.015647 | 1.54 | Plan & Actual | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5573 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019962
2570 | Task(Task)-->C (Construction) | SS-3 |  | 1.21.3.3 | SS-3-->NO LOAD COMMISSIONING & SYSTEM READYNESS FOR TRIAL OPERATION-->CONSTRUCTION-->UTILITY- VENTILATION & AIR CONDITIONING-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-08-22 | 2021-09-04 18:00 | 2022-03-20 | 2022-04-02 18:00 | [6 empty] | 0 | 0 | [15 empty] | 33.3333 | 0.015647 | 1.54 | Plan & Actual | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5571 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019963
2571 | Task(Task)-->E (Engineering) | UTILITY- PWDS, SW, DW, MVWS & DS | 1.22 | 1 | UTILITY- PWDS, SW, DW, MVWS & DS-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-09-27 09:00 | 2021-07-14 18:00 | 2019-09-27 09:00 | 2021-12-07 18:00 |  |  | 2019-09-27 14:27 |  |  |  | 59.3766 | 30.1683 | [15 empty] | 0.35915 | 0.35915 | 35.32 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4927 | 0 | 1 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019964
2572 | Task(Task)-->E (Engineering) | ENGINEERING | 1.22.1 | 1.22 | ENGINEERING-->UTILITY- PWDS, SW, DW, MVWS & DS-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-12-16 18:00 | 2020-05-12 17:40 | 2020-05-10 23:59 | 2020-11-15 23:59 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 62.1131 | [15 empty] | 7.5573 | 0.027142 | 2.67 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4928 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019965
2573 | Task(Task)-->E (Engineering) | MECHANICAL | 1.22.1.1 | 1.22.1 | MECHANICAL-->ENGINEERING-->UTILITY- PWDS, SW, DW, MVWS & DS-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-12-16 18:00 | 2020-05-12 17:40 | 2020-05-10 23:59 | 2020-11-15 23:59 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 62.1131 | [15 empty] | 100 | 0.027142 | 2.67 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4929 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036134
2574 | Task(Task)-->E (Engineering) | DBR & SCHEMATIC DIAGRAM FOR DS,SW & PW SYSTEM |  | 1.22.1.1 | DBR & SCHEMATIC DIAGRAM FOR DS,SW & PW SYSTEM-->MECHANICAL-->ENGINEERING-->UTILITY- PWDS, SW, DW, MVWS & DS-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-12-21 18:00 | 2020-02-24 17:40 | 2020-05-10 23:59 | 2020-07-19 23:59 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-DS-DB-6001 |  | 2020-02-13 11:40 | 7012-155-PVM-L-031 |  |  |  | A |  |  |  | 25.283 | 0.006862 | 0.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 250 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4935 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-12-21 18:00 | 2020-05-10 23:59 |  | 10 |  |  |  | 2020-01-14 17:40 | 2020-05-31 23:59 |  | 30 |  |  |  | 2020-01-20 17:40 | 2020-06-07 23:59 |  | 35 |  |  |  | 2020-01-25 23:59 | 2020-06-14 23:59 |  | 65 | 2020-05-30 23:31 |  |  | 2020-01-31 17:40 | 2020-07-05 23:59 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-02-24 17:40 | 2020-07-19 23:59 |  | 100 | [122 empty] | Ram Prasad Roy | [5 empty] | U - Water Media & Utility System | [16 empty] | 76 |  |  |  |  | 101090
2575 | Task(Task)-->E (Engineering) | GENERAL LAYOUT PLAN SHOWING DS,SW & PW SYSTEM |  | 1.22.1.1 | GENERAL LAYOUT PLAN SHOWING DS,SW & PW SYSTEM-->MECHANICAL-->ENGINEERING-->UTILITY- PWDS, SW, DW, MVWS & DS-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-12-16 18:00 | 2020-02-17 17:40 | 2020-05-25 18:00 | 2020-10-14 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-DS-GA-6006 |  | 2020-02-13 11:40 | 7012-155-PVM-P-036 |  |  |  | A |  |  |  | 15.0943 | 0.004097 | 0.4 | Plan & Actual | Date |  | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4936 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-12-16 18:00 | 2020-05-25 18:00 |  | 10 |  |  |  | 2020-01-08 17:40 | 2020-06-15 18:00 |  | 30 |  |  |  | 2020-01-14 17:40 | 2020-06-22 18:00 |  | 35 |  |  |  | 2020-01-20 23:59 | 2020-06-29 18:00 |  | 65 | 2020-08-22 12:40 |  |  | 2020-01-25 17:40 | 2020-07-20 18:00 |  | 80 | 2020-09-10 17:18 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-02-17 17:40 | 2020-07-20 18:00 |  | 100 | [122 empty] | Ram Prasad Roy | [5 empty] | U - Water Media & Utility System | [16 empty] | 81 |  |  |  |  | 101095
2576 | Task(Task)-->E (Engineering) | GA, CS, DATA SHEET & CURVE OF PUMPS FOR PLAIN WATER DS, SW & PW SYSTEM |  | 1.22.1.1 | GA, CS, DATA SHEET & CURVE OF PUMPS FOR PLAIN WATER DS, SW & PW SYSTEM-->MECHANICAL-->ENGINEERING-->UTILITY- PWDS, SW, DW, MVWS & DS-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-24 18:00 | 2020-03-16 17:40 | 2020-07-20 18:00 | 2020-11-15 23:59 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-DS-GA-6100 |  | 2020-02-13 11:40 | 7012-155-PVM-B-146 |  |  |  | A |  |  |  | 20.3774 | 0.005531 | 0.54 | Plan & Actual | Date |  | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4930 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-24 18:00 | 2020-07-20 18:00 |  | 10 |  |  |  | 2020-02-03 17:40 | 2020-08-04 18:00 |  | 30 |  |  |  | 2020-02-10 17:40 | 2020-08-08 18:00 |  | 35 |  |  |  | 2020-02-15 23:59 | 2020-08-11 18:00 |  | 65 | 2020-09-12 14:30 |  |  | 2020-02-21 17:40 | 2020-09-01 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-16 17:40 | 2020-09-01 18:00 |  | 100 | [122 empty] | Ram Prasad Roy | [5 empty] | U - Water Media & Utility System | [16 empty] | 86 |  |  |  |  | 101100
2577 | Task(Task)-->E (Engineering) | DATA SHEET & GA DRG OF MANUAL VALVES FOR PLAIN WATER DS, SW & PW SYSTEM |  | 1.22.1.1 | DATA SHEET & GA DRG OF MANUAL VALVES FOR PLAIN WATER DS, SW & PW SYSTEM-->MECHANICAL-->ENGINEERING-->UTILITY- PWDS, SW, DW, MVWS & DS-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-05 17:40 | 2020-03-18 17:40 | 2020-08-05 18:00 | 2020-11-15 23:59 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-DS-GA-6101 |  | 2020-02-13 11:40 | 7012-155-PVM-B-147 |  |  |  | A |  |  |  | 10.1887 | 0.002765 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4931 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-07 18:00 | 2020-08-05 18:00 |  | 10 |  |  |  | 2020-02-05 17:40 | 2020-08-12 18:00 |  | 30 |  |  |  | 2020-02-12 17:40 | 2020-08-16 23:59 |  | 35 |  |  |  | 2020-02-18 23:59 | 2020-08-16 23:59 |  | 65 | 2020-09-12 14:30 |  |  | 2020-02-25 17:40 | 2020-09-06 23:59 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-18 17:40 | 2020-09-06 23:59 |  | 100 | [122 empty] | Ram Prasad Roy | [5 empty] | U - Water Media & Utility System | [16 empty] | 87 |  |  |  |  | 101101
2578 | Task(Task)-->E (Engineering) | DATA SHEET & GA DRG OF SPRAY NOZZLES & SPRAY HEADERS FOR PLAIN WATER DS SYSTEM |  | 1.22.1.1 | DATA SHEET & GA DRG OF SPRAY NOZZLES & SPRAY HEADERS FOR PLAIN WATER DS SYSTEM-->MECHANICAL-->ENGINEERING-->UTILITY- PWDS, SW, DW, MVWS & DS-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-07 17:40 | 2020-03-20 17:40 | 2020-07-15 18:00 | 2020-10-17 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-DS-GA-6102 |  | 2020-02-13 11:40 | 7012-155-PVM-B-148 |  |  |  | A |  |  |  | 4.9057 | 0.001331 | 0.13 | Plan & Actual | Date |  | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4932 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-09 23:59 | 2020-07-15 18:00 |  | 10 |  |  |  | 2020-02-07 17:40 | 2020-07-22 18:00 |  | 30 |  |  |  | 2020-02-14 17:40 | 2020-07-26 23:59 |  | 35 |  |  |  | 2020-02-20 23:59 | 2020-07-26 23:59 |  | 65 | 2020-09-16 10:02 |  |  | 2020-02-27 17:40 | 2020-08-16 23:59 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-20 17:40 | 2020-08-16 23:59 |  | 100 | [122 empty] | Ram Prasad Roy | [5 empty] | U - Water Media & Utility System | [16 empty] | 88 |  |  |  |  | 101102
2579 | Task(Task)-->E (Engineering) | DATA SHEET OF PIPES & PIPE FITTINGS FOR PLAIN WATER DS, SW & PW SYSTEM |  | 1.22.1.1 | DATA SHEET OF PIPES & PIPE FITTINGS FOR PLAIN WATER DS, SW & PW SYSTEM-->MECHANICAL-->ENGINEERING-->UTILITY- PWDS, SW, DW, MVWS & DS-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-11 17:40 | 2020-03-21 17:40 | 2020-08-20 18:00 | 2020-09-21 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-DS-GA-6103 |  | 2020-02-13 11:40 | 7012-155-PVM-Y-149 |  |  |  | A |  |  |  | 4.9057 | 0.001331 | 0.13 | Plan & Actual | Date |  | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4937 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-11 18:00 | 2020-08-20 18:00 |  | 10 |  |  |  | 2020-02-11 17:40 | 2020-08-27 18:00 |  | 30 |  |  |  | 2020-02-17 17:40 | 2020-08-31 18:00 |  | 35 |  |  |  | 2020-02-22 23:59 | 2020-08-31 18:00 |  | 65 | 2020-08-22 12:40 |  |  | 2020-02-28 17:40 | 2020-09-21 18:00 |  | 80 | 2020-09-10 17:21 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-21 17:40 | 2020-09-21 18:00 |  | 100 | [122 empty] | Ram Prasad Roy | [5 empty] | U - Water Media & Utility System | [16 empty] | 89 |  |  |  |  | 101103
2580 | Task(Task)-->E (Engineering) | DATA SHEET & GA DRG OF DUPLEX STRAINERS FOR PLAIN WATER DS, SW & PW SYSTEM |  | 1.22.1.1 | DATA SHEET & GA DRG OF DUPLEX STRAINERS FOR PLAIN WATER DS, SW & PW SYSTEM-->MECHANICAL-->ENGINEERING-->UTILITY- PWDS, SW, DW, MVWS & DS-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-12 17:40 | 2020-03-24 17:40 | 2020-08-12 18:00 | 2020-10-17 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-DS-GA-6104 |  | 2020-02-13 11:40 | 7012-155-PVM-B-150 |  |  |  | A |  |  |  | 10.1887 | 0.002765 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4933 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-14 18:00 | 2020-08-12 18:00 |  | 10 |  |  |  | 2020-02-12 17:40 | 2020-08-19 18:00 |  | 30 |  |  |  | 2020-02-18 17:40 | 2020-08-23 23:59 |  | 35 |  |  |  | 2020-02-25 23:59 | 2020-08-23 23:59 |  | 65 | 2020-09-17 12:25 |  |  | 2020-03-02 17:40 | 2020-09-13 23:59 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-24 17:40 | 2020-09-13 23:59 |  | 100 | [122 empty] | Ram Prasad Roy | [5 empty] | U - Water Media & Utility System | [16 empty] | 90 |  |  |  |  | 101104
2581 | Task(Task)-->E (Engineering) | DATA SHEET & GA DRG OF SOLENOID BOX ASSEMBLY FOR PLAIN WATER DS SYSTEM |  | 1.22.1.1 | DATA SHEET & GA DRG OF SOLENOID BOX ASSEMBLY FOR PLAIN WATER DS SYSTEM-->MECHANICAL-->ENGINEERING-->UTILITY- PWDS, SW, DW, MVWS & DS-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-12 18:00 | 2020-03-26 17:40 | 2020-07-15 18:00 | 2020-11-15 23:59 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-DS-GA-6105 |  | 2020-02-13 11:40 | 7012-155-PVM-B-151 |  |  |  | A |  |  |  | 4.9057 | 0.001331 | 0.13 | Plan & Actual | Date |  | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4934 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-12 18:00 | 2020-07-15 18:00 |  | 10 |  |  |  | 2020-02-14 17:40 | 2020-07-22 18:00 |  | 30 |  |  |  | 2020-02-20 17:40 | 2020-07-26 23:59 |  | 35 |  |  |  | 2020-02-27 23:59 | 2020-07-30 18:00 |  | 65 |  |  |  | 2020-03-04 17:40 | 2020-08-20 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-26 17:40 | 2020-08-20 18:00 |  | 100 | [122 empty] | Ram Prasad Roy | [5 empty] | U - Water Media & Utility System | [16 empty] | 91 |  |  |  |  | 101105
2582 | Task(Task)-->E (Engineering) | GA, DATA SHEET, TERMINAL BOX ARRANGEMET & CHARACTERISTICS CURVES OF LT MOTOR (UTILITY SYSTEM) |  | 1.22.1.1 | GA, DATA SHEET, TERMINAL BOX ARRANGEMET & CHARACTERISTICS CURVES OF LT MOTOR (UTILITY SYSTEM)-->MECHANICAL-->ENGINEERING-->UTILITY- PWDS, SW, DW, MVWS & DS-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-31 17:40 | 2020-05-12 17:40 | 2020-05-31 23:59 | 2020-09-29 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-163 |  | 2020-02-13 11:46 | 7012-155-PVE-W-108 |  |  |  | A |  |  |  | 4.1509 | 0.001127 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4938 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-02 18:00 | 2020-05-31 23:59 |  | 10 |  |  |  | 2020-03-31 17:40 | 2020-06-07 23:59 |  | 30 |  |  |  | 2020-04-06 17:40 | 2020-06-11 18:00 |  | 35 |  |  |  | 2020-04-13 23:59 | 2020-06-11 18:00 |  | 65 |  |  |  | 2020-04-18 17:40 | 2020-07-02 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-12 17:40 | 2020-07-02 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 343 |  |  |  |  | 101354
2583 | Task(Task)-->E (Engineering) | CIVIL | 1.22.1.2 | 1.22.1 | CIVIL-->ENGINEERING-->UTILITY- PWDS, SW, DW, MVWS & DS-->NTPC's CHP KERENDARI | Unscheduled | No | No | [10 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4939 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036135
2584 | Task(Task)-->E (Engineering) | ELECTRICAL | 1.22.1.3 | 1.22.1 | ELECTRICAL-->ENGINEERING-->UTILITY- PWDS, SW, DW, MVWS & DS-->NTPC's CHP KERENDARI | Unscheduled | No | No | [10 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4940 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036136
2585 | Task(Task)-->P (Procurement) | PROCUREMENT | 1.22.2 | 1.22 | PROCUREMENT-->UTILITY- PWDS, SW, DW, MVWS & DS-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-09-27 09:00 | 2021-03-15 18:00 | 2019-09-27 09:00 | 2021-06-11 18:00 |  |  | 2019-09-27 14:27 |  |  |  | 71.5705 | 35.1838 | [15 empty] | 72.4031 | 0.26004 | 25.58 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4941 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019969
2586 | Task(Task)-->P (Procurement) | PURCHASE REQUISITION | 1.22.2.1 | 1.22.2 | PURCHASE REQUISITION-->PROCUREMENT-->UTILITY- PWDS, SW, DW, MVWS & DS-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-09-27 09:00 | 2020-03-20 18:00 | 2019-09-27 09:00 | 2020-04-14 18:00 |  |  | 2019-09-27 14:27 |  |  |  | 100 | 99.2162 | [15 empty] | 5.0039 | 0.013012 | 1.28 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4942 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019970
2587 | Task(Task)-->P (Procurement) | DS System |  | 1.22.2.1 | DS System-->PURCHASE REQUISITION-->PROCUREMENT-->UTILITY- PWDS, SW, DW, MVWS & DS-->NTPC's CHP KERENDARI | Completed | No | No | 2019-09-27 09:00 | 2019-09-27 18:00 | 2019-09-27 09:00 | 2019-09-27 18:00 |  |  | 2019-09-27 14:27 | 2019-09-27 14:27 |  |  | 100 | 100 | [15 empty] | 93.75 | 0.012199 | 1.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4943 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019971
2588 | Task(Task)-->P (Procurement) | LPBS |  | 1.22.2.1 | LPBS-->PURCHASE REQUISITION-->PROCUREMENT-->UTILITY- PWDS, SW, DW, MVWS & DS-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-20 09:00 | 2020-03-20 18:00 | 2020-04-14 09:00 | 2020-04-14 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.78125 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4944 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019972
2589 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR UTILITY SYSTEM |  | 1.22.2.1 | LT AC MOTORS FOR UTILITY SYSTEM-->PURCHASE REQUISITION-->PROCUREMENT-->UTILITY- PWDS, SW, DW, MVWS & DS-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-16 09:00 | 2019-12-16 18:00 | 2020-01-13 09:00 | 2020-01-13 18:00 |  |  | 2020-01-13 10:57 | 2020-01-13 10:57 |  |  | 100 | 100 | [15 empty] | 5.4688 | 0.000712 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4945 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019973
2590 | Task(Task)-->P (Procurement) | TECHNICAL CLEARANCE | 1.22.2.2 | 1.22.2 | TECHNICAL CLEARANCE-->PROCUREMENT-->UTILITY- PWDS, SW, DW, MVWS & DS-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-09-28 09:00 | 2020-04-04 18:00 | 2019-09-27 09:00 | 2020-06-12 18:00 |  |  | 2019-09-28 14:28 |  |  |  | 100 | 99.2162 | [15 empty] | 5.0039 | 0.013012 | 1.28 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4946 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019974
2591 | Task(Task)-->P (Procurement) | DS System |  | 1.22.2.2 | DS System-->TECHNICAL CLEARANCE-->PROCUREMENT-->UTILITY- PWDS, SW, DW, MVWS & DS-->NTPC's CHP KERENDARI | Completed | No | No | 2019-09-28 09:00 | 2020-01-13 18:00 | 2019-09-27 09:00 | 2020-02-19 18:00 |  |  | 2019-09-28 14:28 | 2020-02-19 14:28 |  |  | 100 | 100 | [15 empty] | 93.75 | 0.012199 | 1.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4947 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019975
2592 | Task(Task)-->P (Procurement) | LPBS |  | 1.22.2.2 | LPBS-->TECHNICAL CLEARANCE-->PROCUREMENT-->UTILITY- PWDS, SW, DW, MVWS & DS-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-21 09:00 | 2020-04-04 18:00 | 2020-04-14 09:00 | 2020-06-12 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.78125 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4948 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019976
2593 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR UTILITY SYSTEM |  | 1.22.2.2 | LT AC MOTORS FOR UTILITY SYSTEM-->TECHNICAL CLEARANCE-->PROCUREMENT-->UTILITY- PWDS, SW, DW, MVWS & DS-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-17 09:00 | 2019-12-31 18:00 | 2020-01-13 09:00 | 2020-04-11 18:00 |  |  | 2020-04-11 10:57 | 2020-04-11 10:57 |  |  | 100 | 100 | [15 empty] | 5.4688 | 0.000712 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4949 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019977
2594 | Task(Task)-->P (Procurement) | ORDERING | 1.22.2.3 | 1.22.2 | ORDERING-->PROCUREMENT-->UTILITY- PWDS, SW, DW, MVWS & DS-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-01-01 09:00 | 2020-04-20 18:00 | 2020-02-19 09:00 | 2020-08-19 18:00 |  |  | 2020-02-20 14:29 |  |  |  | 100 | 100 | [15 empty] | 9.9296 | 0.025821 | 2.54 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4950 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019978
2595 | Task(Task)-->P (Procurement) | DS System |  | 1.22.2.3 | DS System-->ORDERING-->PROCUREMENT-->UTILITY- PWDS, SW, DW, MVWS & DS-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-14 09:00 | 2020-02-12 18:00 | 2020-02-19 09:00 | 2020-04-28 18:00 |  |  | 2020-02-20 14:29 | 2020-04-28 14:29 |  |  | 100 | 100 | [15 empty] | 94.4664 | 0.024392 | 2.39 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4951 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019979
2596 | Task(Task)-->P (Procurement) | LPBS |  | 1.22.2.3 | LPBS-->ORDERING-->PROCUREMENT-->UTILITY- PWDS, SW, DW, MVWS & DS-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-05 | 2020-04-20 18:00 | 2020-06-12 09:00 | 2020-08-19 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4952 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019980
2597 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR UTILITY SYSTEM |  | 1.22.2.3 | LT AC MOTORS FOR UTILITY SYSTEM-->ORDERING-->PROCUREMENT-->UTILITY- PWDS, SW, DW, MVWS & DS-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-01 09:00 | 2020-01-16 18:00 | 2020-04-11 09:00 | 2020-07-20 18:00 |  |  | 2020-04-12 15:47 | 2020-06-20 15:47 |  |  | 100 | 100 | [15 empty] | 5.5336 | 0.001429 | 0.14 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4953 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019981
2598 | Task(Task)-->P (Procurement) | ITP APPROVAL | 1.22.2.4 | 1.22.2 | ITP APPROVAL-->PROCUREMENT-->UTILITY- PWDS, SW, DW, MVWS & DS-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-01-17 09:00 | 2020-05-30 18:00 | 2020-04-28 09:00 | 2020-11-30 18:00 |  |  | 2020-07-29 15:06 |  |  |  | 100 | 6.2553 | [15 empty] | 5.0039 | 0.013012 | 1.28 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4954 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019982
2599 | Task(Task)-->P (Procurement) | DS System |  | 1.22.2.4 | DS System-->ITP APPROVAL-->PROCUREMENT-->UTILITY- PWDS, SW, DW, MVWS & DS-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-13 09:00 | 2020-03-23 18:00 | 2020-04-28 09:00 | 2020-11-30 18:00 | [6 empty] | 100 | 0 | [15 empty] | 93.75 | 0.012199 | 1.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4955 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019983
2600 | Task(Task)-->P (Procurement) | LPBS |  | 1.22.2.4 | LPBS-->ITP APPROVAL-->PROCUREMENT-->UTILITY- PWDS, SW, DW, MVWS & DS-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-21 09:00 | 2020-05-30 18:00 | 2020-07-29 09:00 | 2020-08-21 18:00 |  |  | 2020-07-29 15:06 | 2020-08-22 12:55 |  |  | 100 | 100 | [15 empty] | 0.78125 | 0.000102 | 0.01 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4956 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019984
2601 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR UTILITY SYSTEM |  | 1.22.2.4 | LT AC MOTORS FOR UTILITY SYSTEM-->ITP APPROVAL-->PROCUREMENT-->UTILITY- PWDS, SW, DW, MVWS & DS-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-17 09:00 | 2020-02-25 18:00 | 2020-09-08 09:00 | 2020-10-14 18:00 |  |  | 2020-09-08 15:17 | 2020-10-14 15:17 |  |  | 100 | 100 | [15 empty] | 5.4688 | 0.000712 | 0.07 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4957 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019985
2602 | Task(Task)-->P (Procurement) | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE | 1.22.2.5 | 1.22.2 | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->UTILITY- PWDS, SW, DW, MVWS & DS-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-17 09:00 | 2020-07-11 18:00 | 2020-04-28 09:00 | 2020-09-29 18:00 |  |  | 2020-04-29 14:33 | 2020-09-29 14:41 |  |  | 100 | 100 | [15 empty] | 15.0117 | 0.039036 | 3.84 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4958 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019986
2603 | Task(Task)-->P (Procurement) | DS System |  | 1.22.2.5 | DS System-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->UTILITY- PWDS, SW, DW, MVWS & DS-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-13 09:00 | 2020-07-11 18:00 | 2020-04-28 09:00 | 2020-06-25 18:00 |  |  | 2020-04-29 14:33 | 2020-06-25 14:33 |  |  | 100 | 100 | [15 empty] | 93.7337 | 0.03659 | 3.59 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4959 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019987
2604 | Task(Task)-->P (Procurement) | LPBS |  | 1.22.2.5 | LPBS-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->UTILITY- PWDS, SW, DW, MVWS & DS-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-21 09:00 | 2020-06-04 18:00 | 2020-07-25 09:00 | 2020-08-22 18:00 |  |  | 2020-07-24 18:39 | 2020-08-22 12:59 |  |  | 100 | 100 | [15 empty] | 0.78329 | 0.000306 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4960 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019988
2605 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR UTILITY SYSTEM |  | 1.22.2.5 | LT AC MOTORS FOR UTILITY SYSTEM-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->UTILITY- PWDS, SW, DW, MVWS & DS-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-17 09:00 | 2020-03-01 23:59 | 2020-07-07 09:00 | 2020-09-29 18:00 |  |  | 2020-07-07 10:15 | 2020-09-29 14:41 |  |  | 100 | 100 | [15 empty] | 5.483 | 0.00214 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4961 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019989
2606 | Task(Task)-->P (Procurement) | MANUFACTURING & RECEIPT AT SITE (MRN) | 1.22.2.6 | 1.22.2 | MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->UTILITY- PWDS, SW, DW, MVWS & DS-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-02 09:00 | 2021-03-15 18:00 | 2020-06-25 09:00 | 2021-06-11 18:00 |  |  | 2020-08-22 13:02 |  |  |  | 52.6545 | 0 | [15 empty] | 60.0469 | 0.15614 | 15.36 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4962 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019990
2607 | Task(Task)-->P (Procurement) | DS System |  | 1.22.2.6 | DS System-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->UTILITY- PWDS, SW, DW, MVWS & DS-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-12 | 2021-03-15 18:00 | 2020-06-25 09:00 | 2021-01-31 23:59 | [6 empty] | 49.3927 | 0 | [15 empty] | 93.5547 | 0.14608 | 14.37 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4963 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019991
2608 | Task(Task)-->P (Procurement) | LPBS |  | 1.22.2.6 | LPBS-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->UTILITY- PWDS, SW, DW, MVWS & DS-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-05 09:00 | 2020-09-16 18:00 | 2020-08-23 | 2020-12-04 18:00 |  |  | 2020-08-22 13:02 |  |  |  | 100 | 0 | [15 empty] | 0.84635 | 0.001322 | 0.13 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4964 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019992
2609 | Task(Task)-->P (Procurement) | LT AC MOTORS FOR UTILITY SYSTEM |  | 1.22.2.6 | LT AC MOTORS FOR UTILITY SYSTEM-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->UTILITY- PWDS, SW, DW, MVWS & DS-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-02 09:00 | 2020-10-27 18:00 | 2020-10-15 09:00 | 2021-06-11 18:00 |  |  | 2020-09-29 16:43 |  |  |  | 100 | 0 | [15 empty] | 5.599 | 0.008742 | 0.86 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4965 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019993
2610 | Task(Task)-->C (Construction) | CONSTRUCTION | 1.22.3 | 1.22 | CONSTRUCTION-->UTILITY- PWDS, SW, DW, MVWS & DS-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-04-02 09:00 | 2021-07-14 18:00 | 2021-08-26 09:00 | 2021-12-07 18:00 | [6 empty] | 0 | 0 | [15 empty] | 20.0396 | 0.071972 | 7.08 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4966 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019994
2611 | Task(Task)-->C (Construction) | INSTALLATION OF PIPING & FITTINGS |  | 1.22.3 | INSTALLATION OF PIPING & FITTINGS-->CONSTRUCTION-->UTILITY- PWDS, SW, DW, MVWS & DS-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-04-02 09:00 | 2021-06-30 18:00 | 2021-08-26 09:00 | 2021-11-23 18:00 | [6 empty] | 0 | 0 | [15 empty] | 75.8475 | 0.054589 | 5.37 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4968 | 0 | 3 | Low | [7 empty] | 0 | 0 | [222 empty] | Installation | [23 empty] | 1019995
2612 | Task(Task)-->C (Construction) | ELECTRICAL & INSTRUMENTATION |  | 1.22.3 | ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->UTILITY- PWDS, SW, DW, MVWS & DS-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-04-02 09:00 | 2021-06-30 18:00 | 2021-08-26 09:00 | 2021-11-23 18:00 | [6 empty] | 0 | 0 | [15 empty] | 2.4011 | 0.001728 | 0.17 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4969 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019996
2613 | Task(Task)-->C (Construction) | NO LOAD COMMISSIONING & SYSTEM READYNESS FOR TRIAL OPERATION |  | 1.22.3 | NO LOAD COMMISSIONING & SYSTEM READYNESS FOR TRIAL OPERATION-->CONSTRUCTION-->UTILITY- PWDS, SW, DW, MVWS & DS-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-07-01 09:00 | 2021-07-14 18:00 | 2021-11-24 09:00 | 2021-12-07 18:00 | [6 empty] | 0 | 0 | [15 empty] | 21.7514 | 0.015655 | 1.54 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4970 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019997
2614 | Task(Task)-->E (Engineering) | UITLITY- FIRE FIGHTING SYSTEM (FDAS & FHS) | 1.23 | 1 | UITLITY- FIRE FIGHTING SYSTEM (FDAS & FHS)-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-09-27 09:00 | 2021-07-28 18:00 | 2019-10-07 18:00 | 2021-12-08 18:00 |  |  | 2019-09-27 10:57 |  |  |  | 57.3304 | 9.2419 | [15 empty] | 0.0078297 | 0.00783 | 0.77 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4971 | 0 | 1 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019998
2615 | Task(Task)-->E (Engineering) | ENGINEERING | 1.23.1 | 1.23 | ENGINEERING-->UITLITY- FIRE FIGHTING SYSTEM (FDAS & FHS)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-10-07 18:00 | 2020-07-09 17:40 | 2019-10-07 18:00 | 2020-11-15 23:59 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 67.4631 | [15 empty] | 4.3703 | 0.000342 | 4.31 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4972 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1019999
2616 | Task(Task)-->E (Engineering) | MECHANICAL | 1.23.1.1 | 1.23.1 | MECHANICAL-->ENGINEERING-->UITLITY- FIRE FIGHTING SYSTEM (FDAS & FHS)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-06 18:00 | 2020-06-09 17:40 | 2020-04-16 18:00 | 2020-11-15 23:59 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 70.1613 | [15 empty] | 81.2065 | 0.000278 | 3.5 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4973 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036137
2617 | Task(Task)-->E (Engineering) | DBR & SCHEMATIC FOR FIRE FIGHTING SYSTEM |  | 1.23.1.1 | DBR & SCHEMATIC FOR FIRE FIGHTING SYSTEM-->MECHANICAL-->ENGINEERING-->UITLITY- FIRE FIGHTING SYSTEM (FDAS & FHS)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-06 18:00 | 2020-05-11 17:40 | 2020-04-16 18:00 | 2020-08-17 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-FF-DB-6004 |  | 2020-02-13 11:40 | 7012-155-PVM-L-034 |  |  |  | A |  |  |  | 19.1977 | 5.3e-05 | 0.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 250 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4980 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-06 18:00 | 2020-04-16 18:00 |  | 10 |  |  |  | 2020-03-30 17:40 | 2020-05-07 18:00 |  | 30 |  |  |  | 2020-04-04 17:40 | 2020-05-14 18:00 |  | 35 |  |  |  | 2020-04-10 23:59 | 2020-05-21 18:00 |  | 65 | 2020-05-05 23:31 |  |  | 2020-04-17 17:40 | 2020-06-11 18:00 |  | 80 | 2020-05-22 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | 2020-09-18 09:35 | [5 empty] | 80 | 2020-09-18 09:35 | [5 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-11 17:40 | 2020-06-25 18:00 |  | 100 | [122 empty] | Ram Prasad Roy | [5 empty] | U - Water Media & Utility System | [16 empty] | 79 |  |  |  |  | 101093
2618 | Task(Task)-->E (Engineering) | GENERAL LAYOUT PLAN SHOWING FIRE FIGHTING SYSTEM PIPING |  | 1.23.1.1 | GENERAL LAYOUT PLAN SHOWING FIRE FIGHTING SYSTEM PIPING-->MECHANICAL-->ENGINEERING-->UITLITY- FIRE FIGHTING SYSTEM (FDAS & FHS)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-20 18:00 | 2020-05-25 17:40 | 2020-05-05 09:00 | 2020-07-10 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-FF-GA-6007 |  | 2020-02-13 11:40 | 7012-155-PVM-P-037 |  |  |  | A |  |  |  | 15.4728 | 4.3e-05 | 0.54 | Plan & Actual | Date |  | 0 | 0 | 0 | 200 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4981 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-20 18:00 | 2020-05-12 18:00 |  | 10 |  |  |  | 2020-04-13 17:40 | 2020-06-02 18:00 |  | 30 |  |  |  | 2020-04-18 17:40 | 2020-06-09 18:00 |  | 35 |  |  |  | 2020-04-24 23:59 | 2020-06-16 18:00 |  | 65 | 2020-05-05 23:31 |  |  | 2020-05-01 17:40 | 2020-07-07 18:00 |  | 80 | 2020-05-16 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-25 17:40 | 2020-07-07 18:00 |  | 100 | [122 empty] | Ram Prasad Roy | [5 empty] | U - Water Media & Utility System | [16 empty] | 82 |  |  |  |  | 101096
2619 | Task(Task)-->E (Engineering) | GA, CS, DATA SHEET & CURVE OF PUMPS FOR FIRE FIGHTING SYSTEM |  | 1.23.1.1 | GA, CS, DATA SHEET & CURVE OF PUMPS FOR FIRE FIGHTING SYSTEM-->MECHANICAL-->ENGINEERING-->UITLITY- FIRE FIGHTING SYSTEM (FDAS & FHS)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-01 18:00 | 2020-05-25 17:40 | 2020-07-16 18:00 | 2020-09-28 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-FF-GA-6301 |  | 2020-02-13 11:40 | 7012-155-PVM-B-153 |  |  |  | A |  |  |  | 15.4728 | 4.3e-05 | 0.54 | Plan & Actual | Date |  | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4974 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-01 18:00 | 2020-07-16 18:00 |  | 10 |  |  |  | 2020-04-13 17:40 | 2020-07-31 18:00 |  | 30 |  |  |  | 2020-04-18 17:40 | 2020-08-04 18:00 |  | 35 |  |  |  | 2020-04-24 23:59 | 2020-08-08 18:00 |  | 65 | 2020-09-12 14:30 |  |  | 2020-05-01 17:40 | 2020-08-29 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-25 17:40 | 2020-08-29 18:00 |  | 100 | [122 empty] | Ram Prasad Roy | [5 empty] | U - Water Media & Utility System | [16 empty] | 93 |  |  |  |  | 101107
2620 | Task(Task)-->E (Engineering) | DATA SHEET & GA DRG OF MANUAL VALVES & STRAINERS FOR FIRE FIGHTING SYSTEM |  | 1.23.1.1 | DATA SHEET & GA DRG OF MANUAL VALVES & STRAINERS FOR FIRE FIGHTING SYSTEM-->MECHANICAL-->ENGINEERING-->UITLITY- FIRE FIGHTING SYSTEM (FDAS & FHS)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-14 17:40 | 2020-05-26 17:40 | 2020-08-30 23:59 | 2020-11-15 23:59 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-FF-GA-6302 |  | 2020-02-13 11:40 | 7012-155-PVM-B-154 |  |  |  | A |  |  |  | 11.4613 | 3.2e-05 | 0.4 | Plan & Actual | Date |  | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4975 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-16 18:00 | 2020-08-30 23:59 |  | 10 |  |  |  | 2020-04-14 17:40 | 2020-09-06 23:59 |  | 30 |  |  |  | 2020-04-20 17:40 | 2020-09-10 18:00 |  | 35 |  |  |  | 2020-04-27 23:59 | 2020-09-10 18:00 |  | 65 | 2020-09-16 10:02 |  |  | 2020-05-02 17:40 | 2020-10-01 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-26 17:40 | 2020-10-01 18:00 |  | 100 | [122 empty] | Ram Prasad Roy | [5 empty] | U - Water Media & Utility System | [16 empty] | 94 |  |  |  |  | 101108
2621 | Task(Task)-->E (Engineering) | GA DRG & TECHNICAL DATA SHEET FOR HYDRANT VALVE FOR FIRE FIGHTING SYSTEM |  | 1.23.1.1 | GA DRG & TECHNICAL DATA SHEET FOR HYDRANT VALVE FOR FIRE FIGHTING SYSTEM-->MECHANICAL-->ENGINEERING-->UITLITY- FIRE FIGHTING SYSTEM (FDAS & FHS)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-16 17:40 | 2020-05-28 17:40 | 2020-08-20 18:00 | 2020-10-03 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-FF-GA-6303 |  | 2020-02-13 11:40 | 7012-155-PVM-B-155 |  |  |  | A |  |  |  | 11.4613 | 3.2e-05 | 0.4 | Plan & Actual | Date |  | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4976 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-18 18:00 | 2020-08-20 18:00 |  | 10 |  |  |  | 2020-04-16 17:40 | 2020-08-27 18:00 |  | 30 |  |  |  | 2020-04-22 17:40 | 2020-08-31 18:00 |  | 35 |  |  |  | 2020-04-29 23:59 | 2020-08-31 18:00 |  | 65 | 2020-09-12 14:30 |  |  | 2020-05-05 17:40 | 2020-09-21 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-28 17:40 | 2020-09-21 18:00 |  | 100 | [122 empty] | Ram Prasad Roy | [5 empty] | U - Water Media & Utility System | [16 empty] | 95 |  |  |  |  | 101109
2622 | Task(Task)-->E (Engineering) | GA DRG & TECHNICAL DATA SHEET FOR WATER MONITOR FOR FIRE FIGHTING SYSTEM |  | 1.23.1.1 | GA DRG & TECHNICAL DATA SHEET FOR WATER MONITOR FOR FIRE FIGHTING SYSTEM-->MECHANICAL-->ENGINEERING-->UITLITY- FIRE FIGHTING SYSTEM (FDAS & FHS)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-21 17:40 | 2020-06-02 17:40 | 2020-08-16 23:59 | 2020-11-15 23:59 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-FF-GA-6304 |  | 2020-02-13 11:40 | 7012-155-PVM-B-156 |  |  |  | A |  |  |  | 7.7364 | 2.2e-05 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4977 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-23 18:00 | 2020-08-16 23:59 |  | 10 |  |  |  | 2020-04-21 17:40 | 2020-08-23 23:59 |  | 30 |  |  |  | 2020-04-28 17:40 | 2020-08-27 18:00 |  | 35 |  |  |  | 2020-05-04 23:59 | 2020-08-27 18:00 |  | 65 | 2020-09-12 14:30 |  |  | 2020-05-11 17:40 | 2020-09-17 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-02 17:40 | 2020-09-17 18:00 |  | 100 | [122 empty] | Ram Prasad Roy | [5 empty] | U - Water Media & Utility System | [16 empty] | 96 |  |  |  |  | 101110
2623 | Task(Task)-->E (Engineering) | DATA SHEET OF PIPES & PIPE FITTINGS FOR FIRE FIGHTING SYSTEM |  | 1.23.1.1 | DATA SHEET OF PIPES & PIPE FITTINGS FOR FIRE FIGHTING SYSTEM-->MECHANICAL-->ENGINEERING-->UITLITY- FIRE FIGHTING SYSTEM (FDAS & FHS)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-23 17:40 | 2020-06-04 17:40 | 2020-07-25 18:00 | 2020-10-09 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-FF-GA-6305 |  | 2020-02-13 11:40 | 7012-155-PVM-Y-157 |  |  |  | A |  |  |  | 3.7249 | 1e-05 | 0.13 | Plan & Actual | Date |  | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4982 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-25 18:00 | 2020-07-25 18:00 |  | 10 |  |  |  | 2020-04-23 17:40 | 2020-08-01 18:00 |  | 30 |  |  |  | 2020-04-30 17:40 | 2020-08-05 18:00 |  | 35 |  |  |  | 2020-05-06 23:59 | 2020-08-05 18:00 |  | 65 | 2020-08-22 12:45 |  |  | 2020-05-13 17:40 | 2020-08-26 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-04 17:40 | 2020-08-26 18:00 |  | 100 | [122 empty] | Ram Prasad Roy | [5 empty] | U - Water Media & Utility System | [16 empty] | 97 |  |  |  |  | 101111
2624 | Task(Task)-->E (Engineering) | GA DRG & TECHNICAL DATA SHEET FOR HOSE PIPE WITH COUPLING, BRANCH PIPE (NOZZLE) & HOSE BOX FOR FIRE FIGHTING SYSTEM. |  | 1.23.1.1 | GA DRG & TECHNICAL DATA SHEET FOR HOSE PIPE WITH COUPLING, BRANCH PIPE (NOZZLE) & HOSE BOX FOR FIRE FIGHTING SYSTEM.-->MECHANICAL-->ENGINEERING-->UITLITY- FIRE FIGHTING SYSTEM (FDAS & FHS)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-27 17:40 | 2020-06-06 17:40 | 2020-07-20 18:00 | 2020-11-15 23:59 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-FF-GA-6306 |  | 2020-02-13 11:40 | 7012-155-PVM-B-158 |  |  |  | A |  |  |  | 7.7364 | 2.2e-05 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4978 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-27 18:00 | 2020-07-20 18:00 |  | 10 |  |  |  | 2020-04-27 17:40 | 2020-07-27 18:00 |  | 30 |  |  |  | 2020-05-02 17:40 | 2020-07-31 18:00 |  | 35 |  |  |  | 2020-05-08 23:59 | 2020-07-31 18:00 |  | 65 | 2020-09-12 14:30 |  |  | 2020-05-15 17:40 | 2020-08-21 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-06 17:40 | 2020-08-21 18:00 |  | 100 | [122 empty] | Ram Prasad Roy | [5 empty] | U - Water Media & Utility System | [16 empty] | 98 |  |  |  |  | 101112
2625 | Task(Task)-->E (Engineering) | DATA SHEET & GA DRG OF DELUGE VALVE FOR FIRE FIGHTING SYSTEM |  | 1.23.1.1 | DATA SHEET & GA DRG OF DELUGE VALVE FOR FIRE FIGHTING SYSTEM-->MECHANICAL-->ENGINEERING-->UITLITY- FIRE FIGHTING SYSTEM (FDAS & FHS)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-29 17:40 | 2020-06-09 17:40 | 2020-08-14 18:00 | 2020-10-03 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-FF-GA-6307 |  | 2020-02-13 11:40 | 7012-155-PVM-B-159 |  |  |  | A |  |  |  | 7.7364 | 2.2e-05 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4979 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-05-01 18:00 | 2020-08-14 18:00 |  | 10 |  |  |  | 2020-04-29 17:40 | 2020-08-21 18:00 |  | 30 |  |  |  | 2020-05-05 17:40 | 2020-08-25 18:00 |  | 35 |  |  |  | 2020-05-12 23:59 | 2020-08-25 18:00 |  | 65 | 2020-09-16 10:02 |  |  | 2020-05-18 17:40 | 2020-09-15 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-09 17:40 | 2020-09-15 18:00 |  | 100 | [122 empty] | Ram Prasad Roy | [5 empty] | U - Water Media & Utility System | [16 empty] | 99 |  |  |  |  | 101113
2626 | Task(Task)-->E (Engineering) | CIVIL | 1.23.1.2 | 1.23.1 | CIVIL-->ENGINEERING-->UITLITY- FIRE FIGHTING SYSTEM (FDAS & FHS)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-10 23:59 | 2020-07-09 17:40 | 2020-06-30 18:00 | 2020-09-08 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 0 | [15 empty] | 2.7842 | 1e-05 | 0.12 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4983 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036138
2627 | Task(Task)-->E (Engineering) | Design calculation of fire fighting system |  | 1.23.1.2 | Design calculation of fire fighting system-->CIVIL-->ENGINEERING-->UITLITY- FIRE FIGHTING SYSTEM (FDAS & FHS)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-10 23:59 | 2020-07-09 17:40 | 2020-06-30 18:00 | 2020-09-08 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0035 |  | 2020-02-13 11:43 | 7012-155-PVC-U-123 |  |  |  | A |  |  |  | 50 | 5e-06 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 22.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4986 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-05-10 23:59 | 2020-06-30 18:00 |  | 10 |  |  |  | 2020-05-29 17:40 | 2020-07-25 18:00 |  | 30 |  |  |  | 2020-06-04 17:40 | 2020-07-28 18:00 |  | 35 |  |  |  | 2020-06-10 23:59 | 2020-08-04 18:00 |  | 65 |  |  |  | 2020-06-17 17:40 | 2020-08-25 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-07-09 17:40 | 2020-09-08 18:00 |  | 100 | [122 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 223 |  |  |  |  | 101233
2628 | Task(Task)-->E (Engineering) | Fire fighting system : NUM & RC DETAILS (SHT 1) |  | 1.23.1.2 | Fire fighting system : NUM & RC DETAILS (SHT 1)-->CIVIL-->ENGINEERING-->UITLITY- FIRE FIGHTING SYSTEM (FDAS & FHS)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-10 23:59 | 2020-07-09 17:40 | 2020-06-30 18:00 | 2020-09-08 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-NR-0044 |  | 2020-02-13 11:43 | 7012-155-PVC-C-124 |  |  |  | A |  |  |  | 25 | 3e-06 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 11.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4984 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-05-10 23:59 | 2020-06-30 18:00 |  | 10 |  |  |  | 2020-05-29 17:40 | 2020-07-25 18:00 |  | 30 |  |  |  | 2020-06-04 17:40 | 2020-07-28 18:00 |  | 35 |  |  |  | 2020-06-10 23:59 | 2020-08-04 18:00 |  | 65 |  |  |  | 2020-06-17 17:40 | 2020-08-25 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-07-09 17:40 | 2020-09-08 18:00 |  | 100 | [122 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 224 |  |  |  |  | 101234
2629 | Task(Task)-->E (Engineering) | Fire fighting system : NUM & RC DETAILS (SHT 2) |  | 1.23.1.2 | Fire fighting system : NUM & RC DETAILS (SHT 2)-->CIVIL-->ENGINEERING-->UITLITY- FIRE FIGHTING SYSTEM (FDAS & FHS)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-10 23:59 | 2020-07-09 17:40 | 2020-06-30 18:00 | 2020-09-08 18:00 |  |  | 2020-02-21 15:38 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-NR-0045 |  | 2020-02-13 11:43 | 7012-155-PVC-C-125 |  |  |  | A |  |  |  | 25 | 3e-06 | 0.03 | Plan & Actual | Date |  | 0 | 0 | 0 | 11.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4985 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-05-10 23:59 | 2020-06-30 18:00 |  | 10 |  |  |  | 2020-05-29 17:40 | 2020-07-25 18:00 |  | 30 |  |  |  | 2020-06-04 17:40 | 2020-07-28 18:00 |  | 35 |  |  |  | 2020-06-10 23:59 | 2020-08-04 18:00 |  | 65 |  |  |  | 2020-06-17 17:40 | 2020-08-25 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-07-09 17:40 | 2020-09-08 18:00 |  | 100 | [122 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 225 |  |  |  |  | 101235
2630 | Task(Task)-->E (Engineering) | ELECTRICAL | 1.23.1.3 | 1.23.1 | ELECTRICAL-->ENGINEERING-->UITLITY- FIRE FIGHTING SYSTEM (FDAS & FHS)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-10-07 18:00 | 2020-06-06 17:40 | 2019-10-07 18:00 | 2020-11-15 23:59 |  |  | 2020-02-21 14:08 |  |  |  | 100 | 66.0909 | [15 empty] | 16.0093 | 5.5e-05 | 0.69 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4987 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036139
2631 | Task(Task)-->E (Engineering) | FDA SYSTEM CONFIGURATION DIAGRAM |  | 1.23.1.3 | FDA SYSTEM CONFIGURATION DIAGRAM-->ELECTRICAL-->ENGINEERING-->UITLITY- FIRE FIGHTING SYSTEM (FDAS & FHS)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-10-07 18:00 | 2019-11-30 17:40 | 2019-10-07 18:00 | 2020-04-22 18:00 |  |  | 2020-02-21 14:08 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-BE-005 |  | 2020-02-13 11:48 | 7012-155-PVI-Q-005 |  |  |  | A |  |  |  | 7.6923 | 4e-06 | 0.04 | Plan & Actual | Date |  | 0 | 0 | 0 | 15 | 0 | 5.04 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4988 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-10-07 18:00 | 2019-10-07 18:00 |  | 10 | 2019-10-07 23:31 |  |  | 2019-10-23 17:40 | 2019-10-15 18:00 |  | 30 | 2019-10-15 23:31 |  |  | 2019-10-29 17:40 | 2019-10-30 18:00 |  | 35 | 2019-10-30 23:31 |  |  | 2019-11-04 23:59 | 2020-01-16 18:00 |  | 65 | 2020-01-16 23:31 |  |  | 2019-11-09 17:40 | 2020-01-30 18:00 |  | 80 | 2020-01-30 23:31 | [5 empty] | 80 | 2020-05-26 15:35 | [5 empty] | 80 | 2020-05-26 15:35 | [5 empty] | 80 | 2020-07-24 15:55 | [5 empty] | 80 | 2020-07-24 15:55 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2019-11-30 17:40 | 2020-01-30 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [22 empty] | 410 |  |  |  |  | 101422
2632 | Task(Task)-->E (Engineering) | GA,DATA SHEET & SCHEME OF FDA SYSTEM |  | 1.23.1.3 | GA,DATA SHEET & SCHEME OF FDA SYSTEM-->ELECTRICAL-->ENGINEERING-->UITLITY- FIRE FIGHTING SYSTEM (FDAS & FHS)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-27 17:40 | 2020-06-06 17:40 | 2020-06-21 23:59 | 2020-11-15 23:59 |  |  | 2020-02-21 14:09 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-VD-016 |  | 2020-02-13 11:49 | 7012-155-PVI-W-041 |  |  |  | A |  |  |  | 92.3077 | 5.1e-05 | 0.48 | Plan & Actual | Date |  | 0 | 0 | 0 | 180 | 0 | 9.02 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4990 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-28 18:00 | 2020-06-21 23:59 |  | 10 |  |  |  | 2020-04-27 17:40 | 2020-06-26 18:00 |  | 30 |  |  |  | 2020-05-02 17:40 | 2020-06-28 23:59 |  | 35 |  |  |  | 2020-05-08 23:59 | 2020-07-01 18:00 |  | 65 | 2020-10-07 10:15 |  |  | 2020-05-15 17:40 | 2020-07-22 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-06 17:40 | 2020-07-22 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [22 empty] | 446 |  |  |  |  | 101458
2633 | Task(Task)-->P (Procurement) | PROCUREMENT | 1.23.2 | 1.23 | PROCUREMENT-->UITLITY- FIRE FIGHTING SYSTEM (FDAS & FHS)-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-09-27 09:00 | 2021-03-15 18:00 | 2020-01-17 09:00 | 2021-05-26 18:00 |  |  | 2019-09-27 10:57 |  |  |  | 68.6461 | 8.5948 | [15 empty] | 73.2407 | 0.005735 | 72.23 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4991 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020003
2634 | Task(Task)-->P (Procurement) | PURCHASE REQUISITION | 1.23.2.1 | 1.23.2 | PURCHASE REQUISITION-->PROCUREMENT-->UITLITY- FIRE FIGHTING SYSTEM (FDAS & FHS)-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-09-27 09:00 | 2020-03-20 18:00 | 2020-01-17 09:00 | 2020-06-26 18:00 |  |  | 2019-09-27 10:57 |  |  |  | 100 | 100 | [15 empty] | 4.9979 | 0.000287 | 3.61 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4992 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020004
2635 | Task(Task)-->P (Procurement) | FFS System |  | 1.23.2.1 | FFS System-->PURCHASE REQUISITION-->PROCUREMENT-->UITLITY- FIRE FIGHTING SYSTEM (FDAS & FHS)-->NTPC's CHP KERENDARI | Completed | No | No | 2019-09-27 09:00 | 2019-09-27 18:00 | 2020-06-26 09:00 | 2020-06-26 18:00 |  |  | 2019-09-27 10:57 | 2019-09-27 10:57 |  |  | 100 | 100 | [15 empty] | 88.0886 | 0.000253 | 3.18 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4993 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020005
2636 | Task(Task)-->P (Procurement) | LPBS |  | 1.23.2.1 | LPBS-->PURCHASE REQUISITION-->PROCUREMENT-->UITLITY- FIRE FIGHTING SYSTEM (FDAS & FHS)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-20 09:00 | 2020-03-20 18:00 | 2020-04-14 09:00 | 2020-04-14 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4994 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020006
2637 | Task(Task)-->P (Procurement) | HT AC MOTORS |  | 1.23.2.1 | HT AC MOTORS-->PURCHASE REQUISITION-->PROCUREMENT-->UITLITY- FIRE FIGHTING SYSTEM (FDAS & FHS)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-07 09:00 | 2020-01-07 18:00 | 2020-01-17 09:00 | 2020-01-17 18:00 |  |  | 2020-01-17 10:57 | 2020-01-17 10:57 |  |  | 100 | 100 | [15 empty] | 11.9114 | 3.4e-05 | 0.43 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4995 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020007
2638 | Task(Task)-->P (Procurement) | TECHNICAL CLEARANCE | 1.23.2.2 | 1.23.2 | TECHNICAL CLEARANCE-->PROCUREMENT-->UITLITY- FIRE FIGHTING SYSTEM (FDAS & FHS)-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-09-28 09:00 | 2020-04-07 18:00 | 2020-01-17 09:00 | 2020-07-17 18:00 |  |  | 2020-04-11 10:57 |  |  |  | 100 | 11.8467 | [15 empty] | 4.9979 | 0.000287 | 3.61 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4996 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020008
2639 | Task(Task)-->P (Procurement) | FFS System |  | 1.23.2.2 | FFS System-->TECHNICAL CLEARANCE-->PROCUREMENT-->UITLITY- FIRE FIGHTING SYSTEM (FDAS & FHS)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-09-28 09:00 | 2020-04-07 18:00 | 2020-06-26 09:00 | 2020-07-17 18:00 | [6 empty] | 100 | 0 | [15 empty] | 88.0886 | 0.000253 | 3.18 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4997 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020009
2640 | Task(Task)-->P (Procurement) | LPBS |  | 1.23.2.2 | LPBS-->TECHNICAL CLEARANCE-->PROCUREMENT-->UITLITY- FIRE FIGHTING SYSTEM (FDAS & FHS)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-21 09:00 | 2020-04-04 18:00 | 2020-04-14 09:00 | 2020-06-12 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4998 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020010
2641 | Task(Task)-->P (Procurement) | HT AC MOTORS |  | 1.23.2.2 | HT AC MOTORS-->TECHNICAL CLEARANCE-->PROCUREMENT-->UITLITY- FIRE FIGHTING SYSTEM (FDAS & FHS)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-08 09:00 | 2020-01-29 18:00 | 2020-01-17 09:00 | 2020-04-11 18:00 |  |  | 2020-04-11 10:57 | 2020-04-11 10:57 |  |  | 100 | 100 | [15 empty] | 11.9114 | 3.4e-05 | 0.43 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 4999 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020011
2642 | Task(Task)-->P (Procurement) | ORDERING | 1.23.2.3 | 1.23.2 | ORDERING-->PROCUREMENT-->UITLITY- FIRE FIGHTING SYSTEM (FDAS & FHS)-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-01-30 09:00 | 2020-04-27 18:00 | 2020-04-11 09:00 | 2020-08-19 18:00 |  |  | 2020-04-12 09:40 |  |  |  | 100 | 12.0419 | [15 empty] | 9.9958 | 0.000573 | 7.22 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5000 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020012
2643 | Task(Task)-->P (Procurement) | FFS System |  | 1.23.2.3 | FFS System-->ORDERING-->PROCUREMENT-->UITLITY- FIRE FIGHTING SYSTEM (FDAS & FHS)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-08 09:00 | 2020-04-27 18:00 | 2020-07-17 09:00 | 2020-07-31 18:00 | [6 empty] | 100 | 0 | [15 empty] | 87.9501 | 0.000504 | 6.35 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5001 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020013
2644 | Task(Task)-->P (Procurement) | LPBS |  | 1.23.2.3 | LPBS-->ORDERING-->PROCUREMENT-->UITLITY- FIRE FIGHTING SYSTEM (FDAS & FHS)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-05 | 2020-04-20 18:00 | 2020-06-12 09:00 | 2020-08-19 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5002 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020014
2645 | Task(Task)-->P (Procurement) | HT AC MOTORS |  | 1.23.2.3 | HT AC MOTORS-->ORDERING-->PROCUREMENT-->UITLITY- FIRE FIGHTING SYSTEM (FDAS & FHS)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-30 09:00 | 2020-02-20 18:00 | 2020-04-11 09:00 | 2020-06-25 18:00 |  |  | 2020-04-12 09:40 | 2020-06-25 09:40 |  |  | 100 | 100 | [15 empty] | 12.0499 | 6.9e-05 | 0.87 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5003 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020015
2646 | Task(Task)-->P (Procurement) | ITP APPROVAL | 1.23.2.4 | 1.23.2 | ITP APPROVAL-->PROCUREMENT-->UITLITY- FIRE FIGHTING SYSTEM (FDAS & FHS)-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-02-21 09:00 | 2020-06-06 18:00 | 2020-07-29 09:00 | 2020-11-11 18:00 |  |  | 2020-07-29 15:07 |  |  |  | 100 | 0 | [15 empty] | 4.9979 | 0.000287 | 3.61 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5004 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020016
2647 | Task(Task)-->P (Procurement) | FFS System |  | 1.23.2.4 | FFS System-->ITP APPROVAL-->PROCUREMENT-->UITLITY- FIRE FIGHTING SYSTEM (FDAS & FHS)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-28 09:00 | 2020-06-06 18:00 | 2020-07-31 09:00 | 2020-09-30 18:00 | [6 empty] | 100 | 0 | [15 empty] | 88.0886 | 0.000253 | 3.18 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5005 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020017
2648 | Task(Task)-->P (Procurement) | LPBS |  | 1.23.2.4 | LPBS-->ITP APPROVAL-->PROCUREMENT-->UITLITY- FIRE FIGHTING SYSTEM (FDAS & FHS)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-21 09:00 | 2020-05-30 18:00 | 2020-07-29 09:00 | 2020-08-21 18:00 |  |  | 2020-07-29 15:07 | 2020-08-22 12:56 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5006 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020018
2649 | Task(Task)-->P (Procurement) | HT AC MOTORS |  | 1.23.2.4 | HT AC MOTORS-->ITP APPROVAL-->PROCUREMENT-->UITLITY- FIRE FIGHTING SYSTEM (FDAS & FHS)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-21 09:00 | 2020-03-31 18:00 | 2020-09-11 09:00 | 2020-11-11 18:00 |  |  | 2020-09-11 15:20 |  |  |  | 100 | 0 | [15 empty] | 11.9114 | 3.4e-05 | 0.43 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5007 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020019
2650 | Task(Task)-->P (Procurement) | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE | 1.23.2.5 | 1.23.2 | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->UITLITY- FIRE FIGHTING SYSTEM (FDAS & FHS)-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-02-21 09:00 | 2020-09-24 18:00 | 2020-07-18 09:00 | 2020-09-28 18:00 |  |  | 2020-07-07 09:06 |  |  |  | 100 | 11.9628 | [15 empty] | 15.0076 | 0.000861 | 10.84 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5008 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020020
2651 | Task(Task)-->P (Procurement) | FFS System |  | 1.23.2.5 | FFS System-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->UITLITY- FIRE FIGHTING SYSTEM (FDAS & FHS)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-28 09:00 | 2020-09-24 18:00 | 2020-07-31 09:00 | 2020-09-28 18:00 | [6 empty] | 100 | 0 | [15 empty] | 87.9963 | 0.000758 | 9.53 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5009 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020021
2652 | Task(Task)-->P (Procurement) | LPBS |  | 1.23.2.5 | LPBS-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->UITLITY- FIRE FIGHTING SYSTEM (FDAS & FHS)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-21 09:00 | 2020-06-04 18:00 | 2020-07-25 09:00 | 2020-08-22 18:00 |  |  | 2020-07-24 18:36 | 2020-08-22 12:59 |  |  | 100 | 100 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5010 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020022
2653 | Task(Task)-->P (Procurement) | HT AC MOTORS |  | 1.23.2.5 | HT AC MOTORS-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->UITLITY- FIRE FIGHTING SYSTEM (FDAS & FHS)-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-21 09:00 | 2020-05-05 18:00 | 2020-07-18 09:00 | 2020-09-28 18:00 |  |  | 2020-07-07 09:06 | 2020-09-28 10:23 |  |  | 100 | 100 | [15 empty] | 12.0037 | 0.000103 | 1.3 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5011 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020023
2654 | Task(Task)-->P (Procurement) | MANUFACTURING & RECEIPT AT SITE (MRN) | 1.23.2.6 | 1.23.2 | MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->UITLITY- FIRE FIGHTING SYSTEM (FDAS & FHS)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-06 09:00 | 2021-03-15 18:00 | 2020-08-23 | 2021-05-26 18:00 |  |  | 2020-08-22 13:02 |  |  |  | 47.7343 | 0 | [15 empty] | 60.0028 | 0.003441 | 43.34 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5012 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020024
2655 | Task(Task)-->P (Procurement) | FFS System |  | 1.23.2.6 | FFS System-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->UITLITY- FIRE FIGHTING SYSTEM (FDAS & FHS)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-16 | 2021-03-15 18:00 | 2020-09-28 09:00 | 2021-01-31 23:59 | [6 empty] | 41.0377 | 0 | [15 empty] | 87.9326 | 0.003026 | 38.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5013 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020025
2656 | Task(Task)-->P (Procurement) | LPBS |  | 1.23.2.6 | LPBS-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->UITLITY- FIRE FIGHTING SYSTEM (FDAS & FHS)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-05 09:00 | 2020-09-16 18:00 | 2020-08-23 | 2020-12-04 18:00 |  |  | 2020-08-22 13:02 |  |  |  | 100 | 0 | [15 empty] | 0.046147 | 2e-06 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5014 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020026
2657 | Task(Task)-->P (Procurement) | HT AC MOTORS |  | 1.23.2.6 | HT AC MOTORS-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->UITLITY- FIRE FIGHTING SYSTEM (FDAS & FHS)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-06 09:00 | 2020-11-17 18:00 | 2020-11-12 09:00 | 2021-05-26 18:00 |  |  | 2020-09-28 10:24 |  |  |  | 96.4286 | 0 | [15 empty] | 12.0212 | 0.000414 | 5.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5015 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020027
2658 | Task(Task)-->C (Construction) | CONSTRUCTION | 1.23.3 | 1.23 | CONSTRUCTION-->UITLITY- FIRE FIGHTING SYSTEM (FDAS & FHS)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-24 09:00 | 2021-07-28 18:00 | 2020-08-19 09:00 | 2021-12-08 18:00 | [6 empty] | 11.9863 | 0 | [15 empty] | 22.389 | 0.001753 | 22.08 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5016 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020028
2659 | Task(Task)-->C (Construction) | AVAILABILITY OF FRONT BY NTPC |  | 1.23.3 | AVAILABILITY OF FRONT BY NTPC-->CONSTRUCTION-->UITLITY- FIRE FIGHTING SYSTEM (FDAS & FHS)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-24 09:00 | 2020-06-24 18:00 | 2020-08-19 09:00 | 2020-08-19 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0 | 0 | 0 | Plan & Actual | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5607 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020029
2660 | Task(Task)-->C (Construction) | CIVIL |  | 1.23.3 | CIVIL-->CONSTRUCTION-->UITLITY- FIRE FIGHTING SYSTEM (FDAS & FHS)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-01 09:00 | 2020-09-28 18:00 | 2020-08-26 09:00 | 2020-11-23 18:00 | [6 empty] | 100 | 0 | [15 empty] | 12.0018 | 0.00021 | 2.65 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5017 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020030
2661 | Task(Task)-->C (Construction) | INSTALLATION OF PIPING |  | 1.23.3 | INSTALLATION OF PIPING-->CONSTRUCTION-->UITLITY- FIRE FIGHTING SYSTEM (FDAS & FHS)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-03-16 09:00 | 2021-07-13 18:00 | 2021-07-27 09:00 | 2021-11-23 18:00 | [6 empty] | 0 | 0 | [15 empty] | 63.6775 | 0.001116 | 14.06 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5018 | 0 | 3 | Low | [7 empty] | 0 | 0 | [222 empty] | Installation | [23 empty] | 1020031
2662 | Task(Task)-->C (Construction) | ELECTRICAL & INSTRUMENTATION |  | 1.23.3 | ELECTRICAL & INSTRUMENTATION-->CONSTRUCTION-->UITLITY- FIRE FIGHTING SYSTEM (FDAS & FHS)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-05-14 09:00 | 2021-07-13 18:00 | 2021-09-24 09:00 | 2021-11-23 18:00 | [6 empty] | 0 | 0 | [15 empty] | 17.346 | 0.000304 | 3.83 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5019 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020032
2663 | Task(Task)-->C (Construction) | NO LOAD COMMISSIONING & SYSTEM READYNESS FOR TRIAL OPERATION |  | 1.23.3 | NO LOAD COMMISSIONING & SYSTEM READYNESS FOR TRIAL OPERATION-->CONSTRUCTION-->UITLITY- FIRE FIGHTING SYSTEM (FDAS & FHS)-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-07-14 09:00 | 2021-07-28 18:00 | 2021-11-24 09:00 | 2021-12-08 18:00 | [6 empty] | 0 | 0 | [15 empty] | 6.9746 | 0.000122 | 1.54 | Plan & Actual | Quantity | LS | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5020 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020033
2664 | Task(Task)-->E (Engineering) | COMMON FOR ALL AREA | 1.24 | 1 | COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-08-01 18:00 | 2021-09-26 23:59 | 2019-08-01 09:00 | 2021-12-24 18:00 |  |  | 2019-11-12 17:40 |  |  |  | 69.5674 | 25.0414 | [15 empty] | 8.8226 | 8.8226 | 867.64 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5021 | 0 | 1 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020034
2665 | Task(Task)-->E (Engineering) | ENGINEERING | 1.24.1 | 1.24 | ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-10-10 17:40 | 2020-12-15 17:40 | 2019-10-10 09:00 | 2020-12-07 18:00 |  |  | 2019-11-12 17:40 |  |  |  | 99.3983 | 69.4185 | [15 empty] | 2.5379 | 0.22391 | 22.02 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5022 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020035
2666 | Task(Task)-->E (Engineering) | MECHANICAL | 1.24.1.1 | 1.24.1 | MECHANICAL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-10-10 17:40 | 2020-12-15 17:40 | 2019-10-10 09:00 | 2020-12-07 18:00 |  |  | 2020-02-21 14:02 |  |  |  | 89.0503 | 18.0348 | [15 empty] | 5.495 | 0.012304 | 1.21 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5023 | 1 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036140
2667 | Task(Task)-->E (Engineering) | GENERAL PLOT PLAN FOR COAL MINING PROJECT - KERANDARI 'A' |  | 1.24.1.1 | GENERAL PLOT PLAN FOR COAL MINING PROJECT - KERANDARI 'A'-->MECHANICAL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2019-10-24 17:40 | 2019-12-02 17:40 | 2019-11-04 09:00 | 2020-02-07 18:00 |  |  | 2020-06-19 22:19 | 2020-06-19 22:39 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-PP-0001 |  | 2020-02-13 10:26 | 7012-155-PVM-F-001 |  |  |  | A |  |  |  | 18.0328 | 0.002219 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5026 | 3 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-10-01 18:00 | 2019-09-30 18:00 |  | 10 | 2019-09-30 23:31 |  |  | 2019-10-24 17:40 | 2019-10-25 18:00 |  | 30 | 2019-10-25 23:31 |  |  | 2019-10-30 17:40 | 2019-10-30 18:00 |  | 35 | 2019-10-30 23:31 |  |  | 2019-11-05 23:59 | 2019-11-04 18:00 |  | 65 | 2019-11-04 23:31 |  |  | 2019-11-11 17:40 | 2020-01-17 18:00 |  | 80 | 2020-01-17 23:31 | [5 empty] | 80 | 2020-06-13 11:25 | [5 empty] | 80 | 2020-06-13 11:25 | [5 empty] | 80 | 2020-06-13 11:29 | [5 empty] | 80 | 2020-06-13 11:29 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2019-12-02 17:40 | 2020-02-07 18:00 |  | 100 | 2020-02-07 23:31 | [121 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 1 |  |  |  |  | 101015
2668 | Task(Task)-->E (Engineering) | CONTROL WRITE UP / OPERATIONAL PHILOSOPHY OF COAL MINING PROJECT, PART-A |  | 1.24.1.1 | CONTROL WRITE UP / OPERATIONAL PHILOSOPHY OF COAL MINING PROJECT, PART-A-->MECHANICAL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-10-04 23:59 | 2020-12-15 17:40 | 2020-10-04 23:59 | 2020-12-07 18:00 |  |  | 2020-02-21 14:04 |  |  |  | 39.2857 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-DC-0030 |  | 2020-02-13 10:26 | 7012-155-PVM-Y-030 |  |  |  | A |  |  |  | 18.0328 | 0.002219 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5029 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-10-04 23:59 | 2020-10-04 23:59 |  | 10 |  |  |  | 2020-11-03 17:40 | 2020-10-25 23:59 |  | 30 |  |  |  | 2020-11-09 17:40 | 2020-11-01 23:59 |  | 35 |  |  |  | 2020-11-16 23:59 | 2020-11-16 18:00 |  | 65 |  |  |  | 2020-11-21 17:40 | 2020-12-07 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-12-15 17:40 | 2020-12-07 18:00 |  | 100 | [122 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 30 |  |  |  |  | 101044
2669 | Task(Task)-->E (Engineering) | G.A OF BELT VULCANIZER |  | 1.24.1.1 | G.A OF BELT VULCANIZER-->MECHANICAL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-04 18:00 | 2020-07-27 17:40 | 2020-07-10 18:00 | 2020-08-23 23:59 |  |  | 2020-02-21 14:04 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133 -M-BM-CS-GA-1036 |  | 2020-02-13 10:27 | 7012-155-PVM-B-136 |  |  |  | A |  |  |  | 9.0164 | 0.001109 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5024 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-06-04 18:00 | 2020-07-10 18:00 |  | 10 |  |  |  | 2020-06-16 17:40 | 2020-07-25 18:00 |  | 30 |  |  |  | 2020-06-22 17:40 | 2020-07-28 18:00 |  | 35 |  |  |  | 2020-06-27 23:59 | 2020-08-02 23:59 |  | 65 |  |  |  | 2020-07-03 17:40 | 2020-08-23 23:59 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-07-27 17:40 | 2020-08-23 23:59 |  | 100 | [122 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 66 |  |  |  |  | 101080
2670 | Task(Task)-->E (Engineering) | DBR FOR BOREWELL SYSTEM |  | 1.24.1.1 | DBR FOR BOREWELL SYSTEM-->MECHANICAL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-20 18:00 | 2020-05-25 17:40 | 2020-06-21 23:59 | 2020-11-15 23:59 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-BB-DB-6005 |  | 2020-02-13 11:40 | 7012-155-PVM-L-035 |  |  |  | A |  |  |  | 32.7869 | 0.004034 | 0.4 | Plan & Actual | Date |  | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5028 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-20 18:00 | 2020-06-21 23:59 |  | 10 |  |  |  | 2020-04-13 17:40 | 2020-07-12 23:59 |  | 30 |  |  |  | 2020-04-18 17:40 | 2020-07-19 23:59 |  | 35 |  |  |  | 2020-04-24 23:59 | 2020-07-26 23:59 |  | 65 |  |  |  | 2020-05-01 17:40 | 2020-08-16 23:59 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-25 17:40 | 2020-08-30 23:59 |  | 100 | [122 empty] | Ram Prasad Roy | [5 empty] | U - Water Media & Utility System | [16 empty] | 80 |  |  |  |  | 101094
2671 | Task(Task)-->E (Engineering) | GA, CS, DATA SHEET & CURVE OF PUMPS FOR BOREWELL |  | 1.24.1.1 | GA, CS, DATA SHEET & CURVE OF PUMPS FOR BOREWELL-->MECHANICAL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-20 18:00 | 2020-06-17 17:40 | 2020-08-22 18:00 | 2020-10-11 23:59 |  |  | 2020-02-21 14:02 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-BB-GA-6501 |  | 2020-02-13 11:40 | 7012-155-PVM-B-161 |  |  |  | A |  |  |  | 22.1311 | 0.002723 | 0.27 | Plan & Actual | Date |  | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5025 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-20 18:00 | 2020-08-22 18:00 |  | 10 |  |  |  | 2020-05-06 17:40 | 2020-09-06 23:59 |  | 30 |  |  |  | 2020-05-13 17:40 | 2020-09-13 23:59 |  | 35 |  |  |  | 2020-05-19 23:59 | 2020-09-20 23:59 |  | 65 |  |  |  | 2020-05-26 17:40 | 2020-10-11 23:59 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-17 17:40 | 2020-10-11 23:59 |  | 100 | [122 empty] | Ram Prasad Roy | [5 empty] | U - Water Media & Utility System | [16 empty] | 101 |  |  |  |  | 101115
2672 | Task(Task)-->E (Engineering) | FLOW DIAGRAM FOR COAL MINING PROJECT - KERANDARI 'A' |  | 1.24.1.1 | FLOW DIAGRAM FOR COAL MINING PROJECT - KERANDARI 'A'-->MECHANICAL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2019-10-10 17:40 | 2019-11-18 17:40 | 2019-10-10 09:00 | 2019-11-18 18:00 |  |  | 2020-06-19 22:23 | 2020-06-19 22:40 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->2(Mechanical) | O19133-M-BM-CS-FD-0002 |  | 2020-02-13 10:26 | 7012-155-PVM-L-002 |  |  |  | A |  |  |  | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 2 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-10-07 18:00 | 2019-10-20 23:59 |  | 10 | 2019-10-20 23:31 |  |  | 2019-10-10 17:40 | 2019-10-29 18:00 |  | 30 | 2019-10-29 23:31 |  |  | 2019-10-16 17:40 | 2019-11-03 23:59 |  | 35 | 2019-11-03 23:31 |  |  | 2019-10-22 23:59 | 2019-11-05 18:00 |  | 65 | 2019-11-05 23:31 |  |  | 2019-10-28 17:40 | 2019-11-25 18:00 |  | 80 | 2019-11-25 23:31 | [5 empty] | 80 | 2020-03-21 16:43 | [5 empty] | 80 | 2020-03-21 16:43 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2019-11-18 17:40 | 2019-12-27 18:00 |  | 100 | 2019-12-27 23:31 | [121 empty] | Satyanarayana GV | [5 empty] | M - Mechanical Process & Equipment | [16 empty] | 2 |  |  |  |  | 101016
2673 | Task(Task)-->E (Engineering) | CIVIL | 1.24.1.2 | 1.24.1 | CIVIL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-12 17:40 | 2020-02-29 17:40 | 2019-11-13 09:00 | 2020-05-18 18:00 |  |  | 2019-11-12 17:40 | 2020-09-01 14:23 |  |  | 100 | 100 | [15 empty] | 13.6694 | 0.030607 | 3.01 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5030 | 6 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036141
2674 | Task(Task)-->E (Engineering) | BASIC DESIGN CRITERIA FOR CIVIL WORKS |  | 1.24.1.2 | BASIC DESIGN CRITERIA FOR CIVIL WORKS-->CIVIL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-14 17:40 | 2019-12-23 17:40 | 2019-11-13 09:00 | 2019-12-20 18:00 |  |  | 2019-11-14 17:40 | 2020-03-02 10:52 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DB-0001 |  | 2020-02-13 11:41 | 7012-155-PVC-W-001 |  |  |  | A |  |  |  | 12.2112 | 0.003737 | 0.37 | Plan & Actual | Date |  | 0 | 0 | 0 | 136.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5036 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-10-26 18:00 | 2019-10-13 23:59 |  | 10 | 2019-10-13 23:31 |  |  | 2019-11-14 17:40 | 2019-11-03 23:59 |  | 30 | 2019-11-03 23:31 |  |  | 2019-11-20 17:40 | 2019-11-06 18:00 |  | 35 | 2019-11-06 23:31 |  |  | 2019-11-26 23:59 | 2019-11-13 18:00 |  | 65 | 2019-11-13 23:31 |  |  | 2019-12-02 17:40 | 2019-12-19 18:00 |  | 80 | 2019-12-19 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2019-12-23 17:40 | 2019-12-27 18:00 |  | 100 | 2019-12-27 23:31 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 102 |  |  |  |  | 101116
2675 | Task(Task)-->E (Engineering) | BASIC DESIGN CRITERIA FOR STRUCTURAL WORKS |  | 1.24.1.2 | BASIC DESIGN CRITERIA FOR STRUCTURAL WORKS-->CIVIL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-14 17:40 | 2019-12-23 17:40 | 2019-11-13 09:00 | 2019-12-23 18:00 |  |  | 2019-11-14 17:40 | 2020-03-02 10:52 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DB-0002 |  | 2020-02-13 11:41 | 7012-155-PVC-W-002 |  |  |  | A |  |  |  | 12.2112 | 0.003737 | 0.37 | Plan & Actual | Date |  | 0 | 0 | 0 | 136.02 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5037 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-10-26 18:00 | 2019-10-13 23:59 |  | 10 | 2019-10-13 23:31 |  |  | 2019-11-14 17:40 | 2019-11-03 23:59 |  | 30 | 2019-11-03 23:31 |  |  | 2019-11-20 17:40 | 2019-11-06 18:00 |  | 35 | 2019-11-06 23:31 |  |  | 2019-11-26 23:59 | 2019-11-13 18:00 |  | 65 | 2019-11-13 23:31 |  |  | 2019-12-02 17:40 | 2019-12-20 18:00 |  | 80 | 2019-12-20 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2019-12-23 17:40 | 2019-12-27 18:00 |  | 100 | 2019-12-27 23:31 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 103 |  |  |  |  | 101117
2676 | Task(Task)-->E (Engineering) | GENERAL NOTES CIVIL WORKS |  | 1.24.1.2 | GENERAL NOTES CIVIL WORKS-->CIVIL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-19 17:40 | 2019-12-27 17:40 | 2019-11-28 09:00 | 2019-12-18 18:00 |  |  | 2019-11-19 17:40 | 2020-03-02 10:52 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-NR-0001 |  | 2020-02-13 11:41 | 7012-155-PVC-W-003 |  |  |  | A |  |  |  | 7.5908 | 0.002323 | 0.23 | Plan & Actual | Date |  | 0 | 0 | 0 | 86.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5038 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-10-30 18:00 | 2019-10-28 18:00 |  | 10 | 2019-10-28 23:31 |  |  | 2019-11-19 17:40 | 2019-11-18 18:00 |  | 30 | 2019-11-18 23:31 |  |  | 2019-11-25 17:40 | 2019-11-21 18:00 |  | 35 | 2019-11-21 23:31 |  |  | 2019-11-30 23:59 | 2019-11-28 18:00 |  | 65 | 2019-11-28 23:31 |  |  | 2019-12-06 17:40 | 2019-12-16 18:00 |  | 80 | 2019-12-16 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2019-12-27 17:40 | 2019-12-27 18:00 |  | 100 | 2019-12-27 23:31 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 104 |  |  |  |  | 101118
2677 | Task(Task)-->E (Engineering) | TECHNICAL SPECIFICATION FOR TOPOGRAPHICAL SURVEY |  | 1.24.1.2 | TECHNICAL SPECIFICATION FOR TOPOGRAPHICAL SURVEY-->CIVIL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-12 17:40 | 2019-12-20 17:40 | 2019-11-21 09:00 | 2019-12-11 18:00 |  |  | 2019-11-12 17:40 | 2020-03-02 10:52 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0030 |  | 2020-02-13 11:43 | 7012-155-PVC-W-103 |  |  |  | A |  |  |  | 5.9406 | 0.001818 | 0.18 | Plan & Actual | Date |  | 0 | 0 | 0 | 66.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5040 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-10-23 18:00 | 2019-10-17 18:00 |  | 10 | 2019-10-17 23:31 |  |  | 2019-11-12 17:40 | 2019-11-11 18:00 |  | 30 | 2019-11-11 23:31 |  |  | 2019-11-18 17:40 | 2019-11-14 18:00 |  | 35 | 2019-11-14 23:31 |  |  | 2019-11-23 23:59 | 2019-11-21 18:00 |  | 65 | 2019-11-21 23:31 |  |  | 2019-11-29 17:40 | 2019-12-11 18:00 |  | 80 | 2019-12-11 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2019-12-20 17:40 | 2019-12-25 18:00 |  | 100 | 2019-12-11 23:31 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 204 |  |  |  |  | 101214
2678 | Task(Task)-->E (Engineering) | TOPOGRAPHICAL SURVEY - G.A DRAWING |  | 1.24.1.2 | TOPOGRAPHICAL SURVEY - G.A DRAWING-->CIVIL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-12 17:40 | 2019-12-20 17:40 | 2019-11-20 09:00 | 2019-12-30 18:00 |  |  | 2019-11-12 17:40 | 2020-02-29 17:19 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-GA-0025 |  | 2020-02-13 11:43 | 7012-155-PVC-B-104 |  |  |  | A |  |  |  | 10.231 | 0.003131 | 0.31 | Plan & Actual | Date |  | 0 | 0 | 0 | 113.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5031 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-10-23 18:00 | 2019-10-16 18:00 |  | 10 | 2019-10-16 23:31 |  |  | 2019-11-12 17:40 | 2019-11-10 23:59 |  | 30 | 2019-11-10 23:31 |  |  | 2019-11-18 17:40 | 2019-11-13 18:00 |  | 35 | 2019-11-13 23:31 |  |  | 2019-11-23 23:59 | 2019-11-20 18:00 |  | 65 | 2019-11-20 23:31 |  |  | 2019-11-29 17:40 | 2019-12-02 18:00 |  | 80 | 2019-12-02 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2019-12-20 17:40 | 2020-03-24 18:00 |  | 100 | 2020-03-24 23:31 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 205 |  |  |  |  | 101215
2679 | Task(Task)-->E (Engineering) | TECHNICAL SPECIFICATION FOR GEOTECHNICAL INVESTIGATION |  | 1.24.1.2 | TECHNICAL SPECIFICATION FOR GEOTECHNICAL INVESTIGATION-->CIVIL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-20 17:40 | 2020-02-29 17:40 | 2020-01-07 09:00 | 2020-01-21 18:00 |  |  | 2020-01-20 17:40 | 2020-02-29 17:19 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0031 |  | 2020-02-13 11:43 | 7012-155-PVC-W-105 |  |  |  | A |  |  |  | 5.9406 | 0.001818 | 0.18 | Plan & Actual | Date |  | 0 | 0 | 0 | 66.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5041 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-12-31 18:00 | 2019-12-03 18:00 |  | 10 | 2019-12-03 23:31 |  |  | 2020-01-20 17:40 | 2019-12-28 18:00 |  | 30 | 2019-12-28 23:31 |  |  | 2020-01-25 17:40 | 2019-12-31 18:00 |  | 35 | 2019-12-31 23:31 |  |  | 2020-01-31 23:59 | 2020-01-07 18:00 |  | 65 | 2020-01-07 23:31 |  |  | 2020-02-06 17:40 | 2020-01-21 18:00 |  | 80 | 2020-01-21 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-02-29 17:40 | 2020-02-04 18:00 |  | 100 | 2020-01-21 23:31 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 206 |  |  |  |  | 101216
2680 | Task(Task)-->E (Engineering) | SOIL INVESTIGATION REPORT |  | 1.24.1.2 | SOIL INVESTIGATION REPORT-->CIVIL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-31 18:00 | 2020-02-29 17:40 | 2020-04-25 09:00 | 2020-05-08 18:00 |  |  | 2020-02-21 15:38 | 2020-09-01 14:23 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0032 |  | 2020-02-13 11:43 | 7012-155-PVC-U-106 |  |  |  | A |  |  |  | 20.132 | 0.006162 | 0.61 | Plan & Actual | Date |  | 0 | 0 | 0 | 227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5033 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-12-31 18:00 | 2020-03-21 18:00 |  | 10 | 2020-03-21 23:31 |  |  | 2020-01-20 17:40 | 2020-03-21 18:00 |  | 30 | 2020-03-21 23:31 |  |  | 2020-01-25 17:40 | 2020-04-18 18:00 |  | 35 | 2020-04-18 23:31 |  |  | 2020-01-31 23:59 | 2020-04-25 18:00 |  | 65 | 2020-04-25 23:31 |  |  | 2020-02-06 17:40 | 2020-05-16 18:00 |  | 80 | 2020-05-08 23:31 | [5 empty] | 80 | 2020-09-01 00:15 | [5 empty] | 80 | 2020-09-01 00:15 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-02-29 17:40 | 2020-05-30 18:00 |  | 100 | 2020-09-01 14:24 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 207 |  |  |  |  | 101217
2681 | Task(Task)-->E (Engineering) | DESIGN CALCULATION OF ROOF & SIDE CLADDING |  | 1.24.1.2 | DESIGN CALCULATION OF ROOF & SIDE CLADDING-->CIVIL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-30 17:40 | 2020-02-06 17:40 | 2020-04-15 09:00 | 2020-05-18 18:00 |  |  | 2019-12-30 17:40 | 2020-05-18 15:58 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0033 |  | 2020-02-13 11:43 | 7012-155-PVC-U-121 |  |  |  | A |  |  |  | 4.9505 | 0.001515 | 0.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 54.29 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5034 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-12-10 18:00 | 2020-03-26 18:00 |  | 10 | 2020-03-16 23:31 |  |  | 2019-12-30 17:40 | 2020-04-20 18:00 |  | 30 | 2020-04-05 23:31 |  |  | 2020-01-04 17:40 | 2020-04-23 18:00 |  | 35 | 2020-04-12 23:31 |  |  | 2020-01-10 23:59 | 2020-04-30 18:00 |  | 65 | 2020-04-15 23:31 |  |  | 2020-01-16 17:40 | 2020-05-21 18:00 |  | 80 | 2020-05-18 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-02-06 17:40 | 2020-06-04 18:00 |  | 100 | 2020-05-18 23:31 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 221 |  |  |  |  | 101231
2682 | Task(Task)-->E (Engineering) | DESIGN CALCULATION OF METAL DECK SHEETING |  | 1.24.1.2 | DESIGN CALCULATION OF METAL DECK SHEETING-->CIVIL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-30 17:40 | 2020-02-06 17:40 | 2020-04-15 09:00 | 2020-05-18 18:00 |  |  | 2019-12-30 17:40 | 2020-05-18 16:00 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-DC-0034 |  | 2020-02-13 11:43 | 7012-155-PVC-U-122 |  |  |  | A |  |  |  | 4.9505 | 0.001515 | 0.15 | Plan & Actual | Date |  | 0 | 0 | 0 | 54.29 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5035 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-12-10 18:00 | 2020-03-26 18:00 |  | 10 | 2020-03-16 23:31 |  |  | 2019-12-30 17:40 | 2020-04-20 18:00 |  | 30 | 2020-04-05 23:31 |  |  | 2020-01-04 17:40 | 2020-04-23 18:00 |  | 35 | 2020-04-12 23:31 |  |  | 2020-01-10 23:59 | 2020-04-30 18:00 |  | 65 | 2020-04-15 23:31 |  |  | 2020-01-16 17:40 | 2020-05-21 18:00 |  | 80 | 2020-05-18 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-02-06 17:40 | 2020-06-04 18:00 |  | 100 | 2020-05-18 23:31 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 222 |  |  |  |  | 101232
2683 | Task(Task)-->E (Engineering) | LAYOUT DRAWING WITH SOIL TEST LOCATION |  | 1.24.1.2 | LAYOUT DRAWING WITH SOIL TEST LOCATION-->CIVIL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-26 17:40 | 2020-02-03 17:40 | 2020-01-07 09:00 | 2020-02-17 18:00 |  |  | 2019-12-26 17:40 | 2020-02-29 17:19 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-GA-0026 |  | 2020-02-13 11:44 | 7012-155-PVC-B-136 |  |  |  | A |  |  |  | 8.2508 | 0.002525 | 0.25 | Plan & Actual | Date |  | 0 | 0 | 0 | 92.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5032 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-12-15 23:59 | 2019-12-15 23:59 |  | 10 | 2019-12-15 23:31 |  |  | 2019-12-26 17:40 | 2019-12-19 18:00 |  | 30 | 2019-12-19 23:31 |  |  | 2020-01-01 17:40 | 2019-12-25 18:00 |  | 35 | 2019-12-25 23:31 |  |  | 2020-01-07 23:59 | 2020-01-07 18:00 |  | 65 | 2020-01-07 23:31 |  |  | 2020-01-13 17:40 | 2020-02-11 18:00 |  | 80 | 2020-02-11 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-02-03 17:40 | 2020-02-11 18:00 |  | 100 | 2020-02-17 23:31 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 235A |  |  |  |  | 101246
2684 | Task(Task)-->E (Engineering) | GENERAL NOTES STRUCTURAL WORKS |  | 1.24.1.2 | GENERAL NOTES STRUCTURAL WORKS-->CIVIL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-19 17:40 | 2019-12-27 17:40 | 2019-11-30 09:00 | 2019-12-31 18:00 |  |  | 2019-11-19 17:40 | 2020-03-02 10:52 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133-C-BM-CS-GA-0001 |  | 2020-02-13 11:41 | 7012-155-PVC-W-004 |  |  |  | A |  |  |  | 7.5908 | 0.002323 | 0.23 | Plan & Actual | Date |  | 0 | 0 | 0 | 86.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5039 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-10-30 18:00 | 2019-10-30 18:00 |  | 10 | 2019-10-30 23:31 |  |  | 2019-11-19 17:40 | 2019-11-20 18:00 |  | 30 | 2019-11-20 23:31 |  |  | 2019-11-25 17:40 | 2019-11-23 18:00 |  | 35 | 2019-11-23 23:31 |  |  | 2019-11-30 23:59 | 2019-11-30 18:00 |  | 65 | 2019-11-30 23:31 |  |  | 2019-12-06 17:40 | 2019-12-20 18:00 |  | 80 | 2019-12-20 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2019-12-27 17:40 | 2020-01-09 18:00 |  | 100 | 2020-01-09 23:31 | [121 empty] | Chetan Khodke | [5 empty] | C - Civil | [16 empty] | 105 |  |  |  |  | 101119
2685 | Task(Task)-->E (Engineering) | ELECTRICAL | 1.24.1.3 | 1.24.1 | ELECTRICAL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-11-01 18:00 | 2020-08-24 17:40 | 2019-11-06 18:00 | 2020-11-15 23:59 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 58.0572 | [15 empty] | 33.7875 | 0.075653 | 7.44 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5043 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036142
2686 | Task(Task)-->E (Engineering) | MASTER LOAD LIST FOR CHP |  | 1.24.1.3 | MASTER LOAD LIST FOR CHP-->ELECTRICAL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-11-07 18:00 | 2019-12-18 17:40 | 2019-11-06 18:00 | 2020-04-17 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-LL-5001 |  | 2020-02-13 11:44 | 7012-155-PVE-R-001 |  |  |  | I |  |  |  | 6.0647 | 0.004588 | 0.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 165.48 | 0 | 18.02 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5050 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-11-07 18:00 | 2019-11-06 18:00 |  | 10 | 2019-11-06 23:31 |  |  | 2019-11-09 17:40 | 2019-11-13 18:00 |  | 30 | 2019-11-13 23:31 |  |  | 2019-11-15 17:40 | 2019-11-19 18:00 |  | 35 | 2019-11-19 23:31 |  |  | 2019-11-21 23:59 | 2019-11-19 18:00 |  | 65 | 2019-11-19 23:31 |  |  | 2019-11-27 17:40 | 2019-12-10 18:00 |  | 80 | 2019-12-10 23:31 | [5 empty] | 80 | 2020-06-10 12:29 | [5 empty] | 80 | 2020-06-10 12:29 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2019-12-18 17:40 | 2020-04-17 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 236 |  |  |  |  | 101247
2687 | Task(Task)-->E (Engineering) | HT & LT TRANSFORMER SIZING CALCULATION FOR CHP |  | 1.24.1.3 | HT & LT TRANSFORMER SIZING CALCULATION FOR CHP-->ELECTRICAL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-11-01 18:00 | 2019-12-23 17:40 | 2019-11-06 18:00 | 2020-04-17 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DC-5002 |  | 2020-02-13 11:44 | 7012-155-PVE-U-002 |  |  |  | A |  |  |  | 4.4474 | 0.003365 | 0.33 | Plan & Actual | Date |  | 0 | 0 | 0 | 124.21 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5051 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-11-01 18:00 | 2019-11-06 18:00 |  | 10 | 2019-11-02 23:31 |  |  | 2019-11-14 17:40 | 2019-11-14 18:00 |  | 30 | 2019-11-14 23:31 |  |  | 2019-11-20 17:40 | 2019-11-19 18:00 |  | 35 | 2019-11-19 23:31 |  |  | 2019-11-26 23:59 | 2019-11-19 18:00 |  | 65 | 2019-11-19 23:31 |  |  | 2019-12-02 17:40 | 2019-11-28 18:00 |  | 80 | 2019-11-28 23:31 | [5 empty] | 80 | 2020-06-10 12:27 | [5 empty] | 80 | 2020-06-10 12:27 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2019-12-23 17:40 | 2020-04-17 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 237 |  |  |  |  | 101248
2688 | Task(Task)-->E (Engineering) | OVERALL SINGLE LINE DIAGRAM(SLD) FOR CHP |  | 1.24.1.3 | OVERALL SINGLE LINE DIAGRAM(SLD) FOR CHP-->ELECTRICAL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-11-08 18:00 | 2019-12-27 17:40 | 2019-11-15 18:00 | 2020-04-28 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-1L-5003 |  | 2020-02-13 11:44 | 7012-155-PVE-P-003 |  |  |  | A |  |  |  | 1.4825 | 0.001122 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5048 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-11-08 18:00 | 2019-11-15 18:00 |  | 10 | 2019-11-15 23:31 |  |  | 2019-11-19 17:40 | 2019-11-30 18:00 |  | 30 | 2019-11-30 23:31 |  |  | 2019-11-25 17:40 | 2019-11-30 18:00 |  | 35 | 2019-11-30 23:31 |  |  | 2019-11-30 23:59 | 2019-12-03 18:00 |  | 65 | 2019-12-03 23:31 |  |  | 2019-12-06 17:40 | 2019-12-11 18:00 |  | 80 | 2019-12-11 23:31 | [5 empty] | 80 | 2020-04-18 12:55 | [5 empty] | 80 | 2020-04-18 12:55 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2019-12-27 17:40 | 2020-04-28 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 238 |  |  |  |  | 101249
2689 | Task(Task)-->E (Engineering) | HT & LT CABLE SIZING CALCULATION FOR CHP |  | 1.24.1.3 | HT & LT CABLE SIZING CALCULATION FOR CHP-->ELECTRICAL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-11-15 18:00 | 2019-12-30 17:40 | 2019-11-20 18:00 | 2020-05-04 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DC-5004 |  | 2020-02-13 11:44 | 7012-155-PVE-U-004 |  |  |  | A |  |  |  | 4.4474 | 0.003365 | 0.33 | Plan & Actual | Date |  | 0 | 0 | 0 | 124.21 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5052 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-11-15 18:00 | 2019-11-20 18:00 |  | 10 | 2019-11-20 23:31 |  |  | 2019-11-21 17:40 | 2019-12-05 18:00 |  | 30 | 2019-12-05 23:31 |  |  | 2019-11-27 17:40 | 2019-12-05 18:00 |  | 35 | 2019-12-05 23:31 |  |  | 2019-12-03 23:59 | 2019-12-11 18:00 |  | 65 | 2019-12-11 23:31 |  |  | 2019-12-09 17:40 | 2019-12-27 18:00 |  | 80 | 2019-12-27 23:31 | [5 empty] | 80 | 2020-04-21 19:50 | [5 empty] | 80 | 2020-04-21 19:50 | [5 empty] | 80 | 2020-07-28 16:00 | [5 empty] | 80 | 2020-07-28 16:00 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2019-12-30 17:40 | 2020-05-04 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 239 |  |  |  |  | 101250
2690 | Task(Task)-->E (Engineering) | LIGHTING DESIGN MEMORANDUM FOR CHP |  | 1.24.1.3 | LIGHTING DESIGN MEMORANDUM FOR CHP-->ELECTRICAL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-11-11 18:00 | 2019-12-26 17:40 | 2019-11-13 18:00 | 2020-05-06 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-BE-5005 |  | 2020-02-13 11:44 | 7012-155-PVE-U-005 |  |  |  | A |  |  |  | 2.965 | 0.002243 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 82.54 | 0 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5053 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-11-11 18:00 | 2019-11-13 18:00 |  | 10 | 2019-11-13 23:31 |  |  | 2019-11-18 17:40 | 2019-11-28 18:00 |  | 30 | 2019-11-28 23:31 |  |  | 2019-11-23 17:40 | 2019-11-28 18:00 |  | 35 | 2019-11-28 23:31 |  |  | 2019-11-29 23:59 | 2019-11-30 18:00 |  | 65 | 2019-11-30 23:31 |  |  | 2019-12-05 17:40 | 2019-12-11 18:00 |  | 80 | 2019-12-11 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2019-12-26 17:40 | 2020-05-06 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 240 |  |  |  |  | 101251
2691 | Task(Task)-->E (Engineering) | 110V DC BATTERY & BATTERY CHARGER SIZING CALCULATION FOR CHP |  | 1.24.1.3 | 110V DC BATTERY & BATTERY CHARGER SIZING CALCULATION FOR CHP-->ELECTRICAL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-11-14 18:00 | 2020-01-02 17:40 | 2019-11-25 18:00 | 2020-05-01 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DC-5006 |  | 2020-02-13 11:44 | 7012-155-PVE-U-006 |  |  |  | A |  |  |  | 2.965 | 0.002243 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 82.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5054 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-11-14 18:00 | 2019-11-25 18:00 |  | 10 | 2019-11-25 23:31 |  |  | 2019-11-25 17:40 | 2019-12-10 18:00 |  | 30 | 2019-12-10 23:31 |  |  | 2019-11-30 17:40 | 2019-12-10 18:00 |  | 35 | 2019-12-10 23:31 |  |  | 2019-12-06 23:59 | 2019-12-13 18:00 |  | 65 | 2019-12-13 23:31 |  |  | 2019-12-12 17:40 | 2019-12-30 18:00 |  | 80 | 2019-12-30 23:31 | [5 empty] | 80 | 2020-04-18 14:35 | [5 empty] | 80 | 2020-04-18 14:35 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-01-02 17:40 | 2020-05-01 18:00 |  | 100 | 2020-04-28 23:31 | [121 empty] | Varun Parihari | [22 empty] | 241 |  |  |  |  | 101252
2692 | Task(Task)-->E (Engineering) | DC DISTRIBUTION DIAGRAM FOR CHP |  | 1.24.1.3 | DC DISTRIBUTION DIAGRAM FOR CHP-->ELECTRICAL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-11-18 18:00 | 2020-01-06 17:40 | 2019-11-27 18:00 | 2020-05-08 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-1L-5007 |  | 2020-02-13 11:44 | 7012-155-PVE-P-007 |  |  |  | A |  |  |  | 1.4825 | 0.001122 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5049 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-11-18 18:00 | 2019-11-27 18:00 |  | 10 | 2019-11-27 23:31 |  |  | 2019-11-28 17:40 | 2019-12-12 18:00 |  | 30 | 2019-12-12 23:31 |  |  | 2019-12-04 17:40 | 2019-12-12 18:00 |  | 35 | 2019-12-12 23:31 |  |  | 2019-12-10 23:59 | 2019-12-17 18:00 |  | 65 | 2019-12-17 23:31 |  |  | 2019-12-16 17:40 | 2019-12-30 18:00 |  | 80 | 2019-12-30 23:31 | [5 empty] | 80 | 2020-04-22 19:50 | [5 empty] | 80 | 2020-04-22 19:50 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-01-06 17:40 | 2020-05-08 18:00 |  | 100 | 2020-05-01 23:31 | [121 empty] | Varun Parihari | [22 empty] | 242 |  |  |  |  | 101253
2693 | Task(Task)-->E (Engineering) | EARTHING & LIGHTNING PROTECTION CALCULATION FOR CHP |  | 1.24.1.3 | EARTHING & LIGHTNING PROTECTION CALCULATION FOR CHP-->ELECTRICAL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-11-24 23:59 | 2020-01-11 17:40 | 2019-12-04 18:00 | 2020-05-14 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-BE-5008 |  | 2020-02-13 11:44 | 7012-155-PVE-U-008 |  |  |  | A |  |  |  | 2.965 | 0.002243 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 82.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5055 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-11-24 23:59 | 2019-12-04 18:00 |  | 10 | 2019-12-04 23:31 |  |  | 2019-12-04 17:40 | 2019-12-19 18:00 |  | 30 | 2019-12-19 23:31 |  |  | 2019-12-10 17:40 | 2019-12-19 18:00 |  | 35 | 2019-12-19 23:31 |  |  | 2019-12-16 23:59 | 2019-12-27 18:00 |  | 65 | 2019-12-27 23:31 |  |  | 2019-12-21 17:40 | 2020-01-03 18:00 |  | 80 | 2020-01-03 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | 2020-08-03 13:34 | [5 empty] | 80 | 2020-08-03 13:34 | [5 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-01-11 17:40 | 2020-05-14 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 243 |  |  |  |  | 101254
2694 | Task(Task)-->E (Engineering) | TYPICAL EQUIPMENT EARTHING DETAILS AND LIGHTNING PROTECTION DETAILS FOR CHP |  | 1.24.1.3 | TYPICAL EQUIPMENT EARTHING DETAILS AND LIGHTNING PROTECTION DETAILS FOR CHP-->ELECTRICAL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-11-21 18:00 | 2020-01-15 17:40 | 2019-12-20 18:00 | 2020-05-18 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-BE-5009 |  | 2020-02-13 11:44 | 7012-155-PVE-F-009 |  |  |  | A |  |  |  | 1.4825 | 0.001122 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5045 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-11-21 18:00 | 2019-12-20 18:00 |  | 10 | 2019-12-20 23:31 |  |  | 2019-12-07 17:40 | 2020-01-10 18:00 |  | 30 | 2020-01-10 23:31 |  |  | 2019-12-13 17:40 | 2020-01-10 18:00 |  | 35 | 2020-01-10 23:31 |  |  | 2019-12-19 23:59 | 2020-01-16 18:00 |  | 65 | 2020-01-16 23:31 |  |  | 2019-12-25 17:40 | 2020-01-24 18:00 |  | 80 | 2020-01-24 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-01-15 17:40 | 2020-05-18 18:00 |  | 100 | 2020-05-11 23:31 | [121 empty] | Varun Parihari | [22 empty] | 244 |  |  |  |  | 101255
2695 | Task(Task)-->E (Engineering) | NGR SIZING CALCULATION FOR CHP |  | 1.24.1.3 | NGR SIZING CALCULATION FOR CHP-->ELECTRICAL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-12-07 18:00 | 2020-01-20 17:40 | 2019-12-08 23:59 | 2019-12-27 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DC-5010 |  | 2020-02-13 11:44 | 7012-155-PVE-U-010 |  |  |  | A |  |  |  | 0.26954 | 0.000204 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 8.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5056 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-12-07 18:00 | 2019-12-08 23:59 |  | 10 | 2019-12-08 23:31 |  |  | 2019-12-12 17:40 | 2019-12-15 23:59 |  | 30 | 2019-12-15 23:31 |  |  | 2019-12-18 17:40 | 2019-12-15 23:59 |  | 35 | 2019-12-15 23:31 |  |  | 2019-12-24 23:59 | 2019-12-18 18:00 |  | 65 | 2019-12-18 23:31 |  |  | 2019-12-30 17:40 | 2019-12-27 18:00 |  | 80 | 2019-12-27 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-01-20 17:40 | 2019-12-27 18:00 |  | 100 | 2019-12-27 23:31 | [121 empty] | Varun Parihari | [22 empty] | 245 |  |  |  |  | 101256
2696 | Task(Task)-->E (Engineering) | OVERALL EARTHING & LIGHTNING PROTECTION LAYOUT FOR CHP |  | 1.24.1.3 | OVERALL EARTHING & LIGHTNING PROTECTION LAYOUT FOR CHP-->ELECTRICAL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-11-29 18:00 | 2020-01-23 17:40 | 2020-02-25 18:00 | 2020-05-12 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-BE-5012 |  | 2020-02-13 11:44 | 7012-155-PVE-W-012 |  |  |  | A |  |  |  | 6.0647 | 0.004588 | 0.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 165.48 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5059 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-11-29 18:00 | 2020-02-25 18:00 |  | 10 | 2020-02-25 23:31 |  |  | 2019-12-16 17:40 | 2020-03-14 18:00 |  | 30 | 2020-03-14 23:31 |  |  | 2019-12-21 17:40 | 2020-03-19 18:00 |  | 35 | 2020-03-19 23:31 |  |  | 2019-12-27 23:59 | 2020-03-19 18:00 |  | 65 | 2020-03-19 23:31 |  |  | 2020-01-02 17:40 | 2020-04-09 18:00 |  | 80 | 2020-04-21 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-01-23 17:40 | 2020-05-12 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 247 |  |  |  |  | 101258
2697 | Task(Task)-->E (Engineering) | OVERALL CABLE ROUTING LAYOUT FOR CHP |  | 1.24.1.3 | OVERALL CABLE ROUTING LAYOUT FOR CHP-->ELECTRICAL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-06 18:00 | 2020-03-03 17:40 | 2020-04-16 18:00 | 2020-06-04 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5051 |  | 2020-02-13 11:44 | 7012-155-PVE-F-013 |  |  |  | A |  |  |  | 6.0647 | 0.004588 | 0.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 165.48 | 0 | 72 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5046 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-06 18:00 | 2020-04-16 18:00 |  | 10 | 2020-04-16 23:31 |  |  | 2020-01-22 17:40 | 2020-04-30 18:00 |  | 30 | 2020-04-22 23:31 |  |  | 2020-01-28 17:40 | 2020-05-07 18:00 |  | 35 | 2020-04-30 23:31 |  |  | 2020-02-03 23:59 | 2020-05-14 18:00 |  | 65 | 2020-05-15 23:31 |  |  | 2020-02-10 17:40 | 2020-06-04 18:00 |  | 80 | 2020-05-29 23:31 | [5 empty] | 80 | 2020-08-19 16:45 | [5 empty] | 80 | 2020-08-19 16:45 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-03 17:40 | 2020-06-04 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 248 |  |  |  |  | 101259
2698 | Task(Task)-->E (Engineering) | POWER CABLE SCHEDULE |  | 1.24.1.3 | POWER CABLE SCHEDULE-->ELECTRICAL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-24 18:00 | 2020-05-13 17:40 | 2020-04-11 18:00 | 2020-05-23 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5074 |  | 2020-02-13 11:44 | 7012-155-PVE-W-036 |  |  |  | A |  |  |  | 14.9596 | 0.011317 | 1.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 414.29 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5060 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-24 18:00 | 2020-04-11 18:00 |  | 10 | 2020-04-05 23:31 |  |  | 2020-04-01 17:40 | 2020-04-18 18:00 |  | 30 | 2020-04-18 23:31 |  |  | 2020-04-07 17:40 | 2020-04-25 18:00 |  | 35 | 2020-04-25 23:31 |  |  | 2020-04-14 23:59 | 2020-05-02 18:00 |  | 65 | 2020-05-12 23:31 |  |  | 2020-04-20 17:40 | 2020-05-23 18:00 |  | 80 | 2020-06-17 13:13 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-13 17:40 | 2020-05-23 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 271 |  |  |  |  | 101282
2699 | Task(Task)-->E (Engineering) | RELAY SETTING CALCULATION & CO-ORDINATION FOR CHP. |  | 1.24.1.3 | RELAY SETTING CALCULATION & CO-ORDINATION FOR CHP.-->ELECTRICAL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-09 18:00 | 2020-06-29 17:40 | 2020-09-29 18:00 | 2020-11-10 18:00 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5075 |  | 2020-02-13 11:44 | 7012-155-PVE-U-037 |  |  |  | A |  |  |  | 11.9946 | 0.009074 | 0.89 | Plan & Actual | Date |  | 0 | 0 | 0 | 331.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5057 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-05-09 18:00 | 2020-09-29 18:00 |  | 10 |  |  |  | 2020-05-18 17:40 | 2020-10-06 18:00 |  | 30 |  |  |  | 2020-05-25 17:40 | 2020-10-13 18:00 |  | 35 |  |  |  | 2020-05-30 23:59 | 2020-10-20 18:00 |  | 65 |  |  |  | 2020-06-05 17:40 | 2020-11-10 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-29 17:40 | 2020-11-10 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 272 |  |  |  |  | 101283
2700 | Task(Task)-->E (Engineering) | OVERALL LIGHTING LAYOUT FOR APPROACH ROAD & LIGHTING MAST AREA. |  | 1.24.1.3 | OVERALL LIGHTING LAYOUT FOR APPROACH ROAD & LIGHTING MAST AREA.-->ELECTRICAL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-24 18:00 | 2020-06-12 17:40 | 2020-04-14 09:00 | 2020-06-07 23:59 |  |  | 2020-02-29 14:34 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CS-DD-5076 |  | 2020-02-13 11:44 | 7012-155-PVE-G-038 |  |  |  | A |  |  |  | 2.965 | 0.002243 | 0.22 | Plan & Actual | Date |  | 0 | 0 | 0 | 82.54 | 0 | 24.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5047 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-24 18:00 | 2020-04-26 23:59 |  | 10 | 2020-04-04 23:31 |  |  | 2020-05-02 17:40 | 2020-05-03 23:59 |  | 30 | 2020-04-10 23:31 |  |  | 2020-05-08 17:40 | 2020-05-10 23:59 |  | 35 | 2020-04-14 23:31 |  |  | 2020-05-15 23:59 | 2020-05-17 23:59 |  | 65 | 2020-04-14 23:31 |  |  | 2020-05-21 17:40 | 2020-06-07 23:59 |  | 80 | 2020-04-23 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-12 17:40 | 2020-06-07 23:59 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 273 |  |  |  |  | 101284
2701 | Task(Task)-->E (Engineering) | HT CABLE DATA SHEET |  | 1.24.1.3 | HT CABLE DATA SHEET-->ELECTRICAL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-26 18:00 | 2020-04-08 17:40 | 2020-06-21 23:59 | 2020-08-17 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-164 |  | 2020-02-13 11:46 | 7012-155-PVE-Y-109 |  |  |  | A |  |  |  | 0.80863 | 0.000612 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5081 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-26 18:00 | 2020-06-21 23:59 |  | 10 |  |  |  | 2020-02-27 17:40 | 2020-06-28 23:59 |  | 30 |  |  |  | 2020-03-04 17:40 | 2020-07-04 18:00 |  | 35 |  |  |  | 2020-03-10 23:59 | 2020-07-04 18:00 |  | 65 |  |  |  | 2020-03-17 17:40 | 2020-07-25 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-08 17:40 | 2020-07-25 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 344 |  |  |  |  | 101355
2702 | Task(Task)-->E (Engineering) | LT POWER CABLE DATA SHEET |  | 1.24.1.3 | LT POWER CABLE DATA SHEET-->ELECTRICAL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-17 17:40 | 2020-04-28 17:40 | 2020-06-21 23:59 | 2020-08-17 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-165 |  | 2020-02-13 11:46 | 7012-155-PVE-Y-110 |  |  |  | A |  |  |  | 0.80863 | 0.000612 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5082 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-18 18:00 | 2020-06-21 23:59 |  | 10 |  |  |  | 2020-03-17 17:40 | 2020-06-28 23:59 |  | 30 |  |  |  | 2020-03-23 17:40 | 2020-07-03 18:00 |  | 35 |  |  |  | 2020-03-30 23:59 | 2020-07-03 18:00 |  | 65 |  |  |  | 2020-04-04 17:40 | 2020-07-24 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-28 17:40 | 2020-07-24 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 345 |  |  |  |  | 101356
2703 | Task(Task)-->E (Engineering) | GAD, DATA SHEET & BOM OF 110V DC BATTERY FOR CHP |  | 1.24.1.3 | GAD, DATA SHEET & BOM OF 110V DC BATTERY FOR CHP-->ELECTRICAL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-01 17:40 | 2020-05-13 17:40 | 2020-06-21 23:59 | 2020-08-18 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-166 |  | 2020-02-13 11:46 | 7012-155-PVE-W-111 |  |  |  | A |  |  |  | 1.4825 | 0.001122 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5061 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-02 18:00 | 2020-06-21 23:59 |  | 10 |  |  |  | 2020-04-01 17:40 | 2020-06-28 23:59 |  | 30 |  |  |  | 2020-04-07 17:40 | 2020-07-03 18:00 |  | 35 |  |  |  | 2020-04-14 23:59 | 2020-07-03 18:00 |  | 65 |  |  |  | 2020-04-20 17:40 | 2020-07-24 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-13 17:40 | 2020-07-24 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 346 |  |  |  |  | 101357
2704 | Task(Task)-->E (Engineering) | GAD, DATA SHEET, WIRING DIAGRAM & BOM OF 110V DC BATTERY CHARGER FOR CHP |  | 1.24.1.3 | GAD, DATA SHEET, WIRING DIAGRAM & BOM OF 110V DC BATTERY CHARGER FOR CHP-->ELECTRICAL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-01 17:40 | 2020-05-13 17:40 | 2020-06-21 23:59 | 2020-07-31 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-167 |  | 2020-02-13 11:46 | 7012-155-PVE-W-112 |  |  |  | A |  |  |  | 1.4825 | 0.001122 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5062 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-02 18:00 | 2020-06-21 23:59 |  | 10 |  |  |  | 2020-04-01 17:40 | 2020-06-28 23:59 |  | 30 |  |  |  | 2020-04-07 17:40 | 2020-07-03 18:00 |  | 35 |  |  |  | 2020-04-14 23:59 | 2020-07-03 18:00 |  | 65 | 2020-07-28 13:22 |  |  | 2020-04-20 17:40 | 2020-07-24 18:00 |  | 80 | 2020-08-03 10:02 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-13 17:40 | 2020-07-24 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 347 |  |  |  |  | 101358
2705 | Task(Task)-->E (Engineering) | GA, SLD,WIRING DIAGRAM & BOM OF MLDB |  | 1.24.1.3 | GA, SLD,WIRING DIAGRAM & BOM OF MLDB-->ELECTRICAL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-24 17:40 | 2020-05-05 17:40 | 2020-06-30 18:00 | 2020-09-01 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-168 |  | 2020-02-13 11:46 | 7012-155-PVE-W-113 |  |  |  | A |  |  |  | 1.4825 | 0.001122 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5063 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-24 18:00 | 2020-06-30 18:00 |  | 10 |  |  |  | 2020-03-24 17:40 | 2020-07-07 18:00 |  | 30 |  |  |  | 2020-03-31 17:40 | 2020-07-13 18:00 |  | 35 |  |  |  | 2020-04-06 23:59 | 2020-07-13 18:00 |  | 65 |  |  |  | 2020-04-13 17:40 | 2020-08-03 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-05 17:40 | 2020-08-03 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 348 |  |  |  |  | 101359
2706 | Task(Task)-->E (Engineering) | GA,SLD,WIRING DIAGRAM & BOM OF AC & DC LIGHTING PANELS |  | 1.24.1.3 | GA,SLD,WIRING DIAGRAM & BOM OF AC & DC LIGHTING PANELS-->ELECTRICAL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-15 17:40 | 2020-05-27 17:40 | 2020-06-30 18:00 | 2020-10-06 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-169 |  | 2020-02-13 11:46 | 7012-155-PVE-W-114 |  |  |  | A |  |  |  | 1.4825 | 0.001122 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5064 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-15 18:00 | 2020-06-30 18:00 |  | 10 |  |  |  | 2020-04-15 17:40 | 2020-07-07 18:00 |  | 30 |  |  |  | 2020-04-21 17:40 | 2020-07-13 18:00 |  | 35 |  |  |  | 2020-04-28 23:59 | 2020-07-13 18:00 |  | 65 |  |  |  | 2020-05-04 17:40 | 2020-08-03 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-27 17:40 | 2020-08-03 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 349 |  |  |  |  | 101360
2707 | Task(Task)-->E (Engineering) | GAD,SLD, WIRING DIAGRAM & BOM OF DCDB AND DC LDB |  | 1.24.1.3 | GAD,SLD, WIRING DIAGRAM & BOM OF DCDB AND DC LDB-->ELECTRICAL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-18 17:40 | 2020-04-29 17:40 | 2020-06-30 18:00 | 2020-09-03 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-170 |  | 2020-02-13 11:46 | 7012-155-PVE-W-115 |  |  |  | A |  |  |  | 1.4825 | 0.001122 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5065 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-18 18:00 | 2020-06-30 18:00 |  | 10 |  |  |  | 2020-03-18 17:40 | 2020-07-07 18:00 |  | 30 |  |  |  | 2020-03-24 17:40 | 2020-07-13 18:00 |  | 35 |  |  |  | 2020-03-31 23:59 | 2020-07-13 18:00 |  | 65 |  |  |  | 2020-04-06 17:40 | 2020-08-03 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-29 17:40 | 2020-08-03 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 350 |  |  |  |  | 101361
2708 | Task(Task)-->E (Engineering) | GAD,SLD, WIRING DIAGRAM & BOM OF AC MCCB BOX |  | 1.24.1.3 | GAD,SLD, WIRING DIAGRAM & BOM OF AC MCCB BOX-->ELECTRICAL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-05 17:40 | 2020-06-16 17:40 | 2020-06-30 18:00 | 2020-08-21 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-171 |  | 2020-02-13 11:46 | 7012-155-PVE-W-116 |  |  |  | A |  |  |  | 1.4825 | 0.001122 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5066 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-05-05 18:00 | 2020-06-30 18:00 |  | 10 |  |  |  | 2020-05-05 17:40 | 2020-07-07 18:00 |  | 30 |  |  |  | 2020-05-12 17:40 | 2020-07-13 18:00 |  | 35 |  |  |  | 2020-05-18 23:59 | 2020-07-13 18:00 |  | 65 |  |  |  | 2020-05-25 17:40 | 2020-08-03 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-16 17:40 | 2020-08-03 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 351 |  |  |  |  | 101362
2709 | Task(Task)-->E (Engineering) | GAD & DATA SHEET OF CABLE TRAY & ACCESSORIES |  | 1.24.1.3 | GAD & DATA SHEET OF CABLE TRAY & ACCESSORIES-->ELECTRICAL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-05 17:40 | 2020-04-16 17:40 | 2020-06-21 23:59 | 2020-07-27 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-172 |  | 2020-02-13 11:46 | 7012-155-PVE-W-117 |  |  |  | A |  |  |  | 1.4825 | 0.001122 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5067 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-06 18:00 | 2020-06-21 23:59 |  | 10 |  |  |  | 2020-03-05 17:40 | 2020-06-28 23:59 |  | 30 |  |  |  | 2020-03-11 17:40 | 2020-07-03 18:00 |  | 35 |  |  |  | 2020-03-18 23:59 | 2020-07-03 18:00 |  | 65 | 2020-07-28 13:21 |  |  | 2020-03-24 17:40 | 2020-07-24 18:00 |  | 80 | 2020-07-28 17:51 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-16 17:40 | 2020-07-24 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 352 |  |  |  |  | 101363
2710 | Task(Task)-->E (Engineering) | GAD AND DATA SHEET OF LPBS |  | 1.24.1.3 | GAD AND DATA SHEET OF LPBS-->ELECTRICAL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-07 17:40 | 2020-06-18 17:40 | 2020-06-21 23:59 | 2020-08-12 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-173 |  | 2020-02-13 11:46 | 7012-155-PVE-W-118 |  |  |  | A |  |  |  | 1.4825 | 0.001122 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5068 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-05-07 18:00 | 2020-06-21 23:59 |  | 10 |  |  |  | 2020-05-07 17:40 | 2020-06-28 23:59 |  | 30 |  |  |  | 2020-05-14 17:40 | 2020-07-04 18:00 |  | 35 |  |  |  | 2020-05-20 23:59 | 2020-07-04 18:00 |  | 65 |  |  |  | 2020-05-27 17:40 | 2020-07-25 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-18 17:40 | 2020-07-25 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 353 |  |  |  |  | 101364
2711 | Task(Task)-->E (Engineering) | GA DRAWING & WIRING DIAGRAM FOR RECEPTACLES |  | 1.24.1.3 | GA DRAWING & WIRING DIAGRAM FOR RECEPTACLES-->ELECTRICAL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-26 18:00 | 2020-05-11 17:40 | 2020-06-21 23:59 | 2020-07-28 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-174 |  | 2020-02-13 11:46 | 7012-155-PVE-W-119 |  |  |  | A |  |  |  | 1.4825 | 0.001122 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5069 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-26 18:00 | 2020-06-21 23:59 |  | 10 |  |  |  | 2020-03-30 17:40 | 2020-06-28 23:59 |  | 30 |  |  |  | 2020-04-04 17:40 | 2020-07-06 18:00 |  | 35 |  |  |  | 2020-04-10 23:59 | 2020-07-06 18:00 |  | 65 | 2020-07-28 13:21 |  |  | 2020-04-17 17:40 | 2020-07-27 18:00 |  | 80 | 2020-08-03 10:01 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-11 17:40 | 2020-07-27 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 354 |  |  |  |  | 101365
2712 | Task(Task)-->E (Engineering) | GA & DATA SHEET FOR LIGHTING FIXTURES |  | 1.24.1.3 | GA & DATA SHEET FOR LIGHTING FIXTURES-->ELECTRICAL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-28 17:40 | 2020-06-08 17:40 | 2020-06-21 23:59 | 2020-08-17 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-175 |  | 2020-02-13 11:46 | 7012-155-PVE-W-120 |  |  |  | A |  |  |  | 1.4825 | 0.001122 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5070 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-28 18:00 | 2020-06-21 23:59 |  | 10 |  |  |  | 2020-04-28 17:40 | 2020-06-28 23:59 |  | 30 |  |  |  | 2020-05-04 17:40 | 2020-07-04 18:00 |  | 35 |  |  |  | 2020-05-11 23:59 | 2020-07-04 18:00 |  | 65 |  |  |  | 2020-05-16 17:40 | 2020-07-25 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-08 17:40 | 2020-07-25 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 355 |  |  |  |  | 101366
2713 | Task(Task)-->E (Engineering) | GA, SLD, WIRING DIAGRAM & BOM OF WDB |  | 1.24.1.3 | GA, SLD, WIRING DIAGRAM & BOM OF WDB-->ELECTRICAL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-04 17:40 | 2020-05-16 17:40 | 2020-05-10 23:59 | 2020-06-15 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-176 |  | 2020-02-13 11:46 | 7012-155-PVE-W-121 |  |  |  | A |  |  |  | 1.4825 | 0.001122 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5071 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-04 18:00 | 2020-05-10 23:59 |  | 10 | 2020-05-10 23:31 |  |  | 2020-04-04 17:40 | 2020-05-17 23:59 |  | 30 | 2020-05-17 23:31 |  |  | 2020-04-10 17:40 | 2020-05-23 18:00 |  | 35 | 2020-05-23 23:31 |  |  | 2020-04-17 23:59 | 2020-05-23 18:00 |  | 65 | 2020-06-10 09:49 |  |  | 2020-04-23 17:40 | 2020-06-13 18:00 |  | 80 | 2020-07-28 18:04 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-16 17:40 | 2020-06-13 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 356 |  |  |  |  | 101367
2714 | Task(Task)-->E (Engineering) | GA, DATA SHEET OF NGR |  | 1.24.1.3 | GA, DATA SHEET OF NGR-->ELECTRICAL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-04 17:40 | 2020-03-17 17:40 | 2020-03-06 18:00 | 2020-05-22 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-177 |  | 2020-02-13 11:46 | 7012-155-PVE-W-122 |  |  |  | A |  |  |  | 1.4825 | 0.001122 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5072 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-05 18:00 | 2020-03-06 18:00 |  | 10 | 2020-03-06 23:31 |  |  | 2020-02-04 17:40 | 2020-03-21 18:00 |  | 30 | 2020-03-21 23:31 |  |  | 2020-02-11 17:40 | 2020-03-21 18:00 |  | 35 | 2020-04-21 23:31 |  |  | 2020-02-17 23:59 | 2020-04-25 18:00 |  | 65 | 2020-05-15 23:31 |  |  | 2020-02-24 17:40 | 2020-05-16 18:00 |  | 80 | 2020-05-22 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-17 17:40 | 2020-05-16 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 357 |  |  |  |  | 101368
2715 | Task(Task)-->E (Engineering) | GA DRAWINGS & DATA SHEET FOR HT CABLE TERMINATION KIT AND STRAIGHT THROUGH JOINT |  | 1.24.1.3 | GA DRAWINGS & DATA SHEET FOR HT CABLE TERMINATION KIT AND STRAIGHT THROUGH JOINT-->ELECTRICAL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-12 23:59 | 2020-05-25 17:40 | 2020-06-21 23:59 | 2020-11-15 23:59 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-178 |  | 2020-02-13 11:46 | 7012-155-PVE-W-123 |  |  |  | A |  |  |  | 0.80863 | 0.000612 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5073 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-12 23:59 | 2020-06-21 23:59 |  | 10 |  |  |  | 2020-04-13 17:40 | 2020-06-28 23:59 |  | 30 |  |  |  | 2020-04-18 17:40 | 2020-07-03 18:00 |  | 35 |  |  |  | 2020-04-24 23:59 | 2020-07-03 18:00 |  | 65 |  |  |  | 2020-05-01 17:40 | 2020-07-24 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-25 17:40 | 2020-07-24 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 358 |  |  |  |  | 101369
2716 | Task(Task)-->E (Engineering) | GA, BOM & WIRING DIAGRAM FOR BELT WATCH SYSTEM |  | 1.24.1.3 | GA, BOM & WIRING DIAGRAM FOR BELT WATCH SYSTEM-->ELECTRICAL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-12 23:59 | 2020-05-25 17:40 | 2020-06-05 18:00 | 2020-08-21 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-179 |  | 2020-02-13 11:46 | 7012-155-PVE-W-124 |  |  |  | A |  |  |  | 1.4825 | 0.001122 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5074 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-12 23:59 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-04-13 17:40 | 2020-06-12 18:00 |  | 30 |  |  |  | 2020-04-18 17:40 | 2020-06-17 18:00 |  | 35 |  |  |  | 2020-04-24 23:59 | 2020-06-17 18:00 |  | 65 |  |  |  | 2020-05-01 17:40 | 2020-07-08 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-25 17:40 | 2020-07-08 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 359 |  |  |  |  | 101370
2717 | Task(Task)-->E (Engineering) | LIGHTING DESIGN CALCULATION FOR LIGHTING MAST |  | 1.24.1.3 | LIGHTING DESIGN CALCULATION FOR LIGHTING MAST-->ELECTRICAL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-09 17:40 | 2020-04-20 17:40 | 2020-06-05 18:00 | 2020-07-28 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-180 |  | 2020-02-13 11:46 | 7012-155-PVE-U-125 |  |  |  | A |  |  |  | 1.4825 | 0.001122 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 2.11 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5058 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-09 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-03-09 17:40 | 2020-06-12 18:00 |  | 30 |  |  |  | 2020-03-16 17:40 | 2020-06-17 18:00 |  | 35 |  |  |  | 2020-03-21 23:59 | 2020-06-17 18:00 |  | 65 | 2020-07-28 15:45 |  |  | 2020-03-27 17:40 | 2020-07-08 18:00 |  | 80 | 2020-07-28 17:45 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-20 17:40 | 2020-07-08 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 360 |  |  |  |  | 101371
2718 | Task(Task)-->E (Engineering) | GA, DATA SHEET, BOM & CIRCUIT DIAGRAM FOR LIGHTING MAST |  | 1.24.1.3 | GA, DATA SHEET, BOM & CIRCUIT DIAGRAM FOR LIGHTING MAST-->ELECTRICAL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-09 17:40 | 2020-04-20 17:40 | 2020-06-05 18:00 | 2020-07-12 23:59 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-181 |  | 2020-02-13 11:47 | 7012-155-PVE-W-126 |  |  |  | A |  |  |  | 1.4825 | 0.001122 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 4.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5075 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-09 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-03-09 17:40 | 2020-06-12 18:00 |  | 30 |  |  |  | 2020-03-16 17:40 | 2020-06-17 18:00 |  | 35 |  |  |  | 2020-03-21 23:59 | 2020-06-17 18:00 |  | 65 | 2020-08-03 12:01 |  |  | 2020-03-27 17:40 | 2020-07-08 18:00 |  | 80 | 2020-08-03 12:03 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-20 17:40 | 2020-07-08 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 361 |  |  |  |  | 101372
2719 | Task(Task)-->E (Engineering) | DATA SHEET OF FO CABLE FOR SCADA SYSTEM |  | 1.24.1.3 | DATA SHEET OF FO CABLE FOR SCADA SYSTEM-->ELECTRICAL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-07 18:00 | 2020-05-20 17:40 | 2020-06-21 23:59 | 2020-08-21 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-182 |  | 2020-02-13 11:47 | 7012-155-PVE-Y-127 |  |  |  | A |  |  |  | 0.26954 | 0.000204 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 8.17 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5083 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-07 18:00 | 2020-06-21 23:59 |  | 10 |  |  |  | 2020-04-08 17:40 | 2020-06-28 23:59 |  | 30 |  |  |  | 2020-04-15 17:40 | 2020-07-05 23:59 |  | 35 |  |  |  | 2020-04-21 23:59 | 2020-07-05 23:59 |  | 65 |  |  |  | 2020-04-28 17:40 | 2020-07-26 23:59 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-20 17:40 | 2020-07-26 23:59 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 362 |  |  |  |  | 101373
2720 | Task(Task)-->E (Engineering) | GA & SCHEME ,BOM FOR DATA CONCENTRATOR PANEL |  | 1.24.1.3 | GA & SCHEME ,BOM FOR DATA CONCENTRATOR PANEL-->ELECTRICAL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-13 17:40 | 2020-04-24 17:40 | 2020-06-21 23:59 | 2020-09-16 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-183 |  | 2020-02-13 11:47 | 7012-155-PVE-W-128 |  |  |  | A |  |  |  | 0.26954 | 0.000204 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 8.17 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5076 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-13 18:00 | 2020-06-21 23:59 |  | 10 |  |  |  | 2020-03-13 17:40 | 2020-06-28 23:59 |  | 30 |  |  |  | 2020-03-20 17:40 | 2020-07-04 18:00 |  | 35 |  |  |  | 2020-03-26 23:59 | 2020-07-04 18:00 |  | 65 |  |  |  | 2020-04-02 17:40 | 2020-07-25 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-24 17:40 | 2020-07-25 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 363 |  |  |  |  | 101374
2721 | Task(Task)-->E (Engineering) | NETWORK CONFIGURATION DWG FOR PROCESS LAN |  | 1.24.1.3 | NETWORK CONFIGURATION DWG FOR PROCESS LAN-->ELECTRICAL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-13 17:40 | 2020-04-24 17:40 | 2020-06-05 18:00 | 2020-09-16 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-184 |  | 2020-02-13 11:47 | 7012-155-PVE-W-129 |  |  |  | A |  |  |  | 0.80863 | 0.000612 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5077 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-14 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-03-13 17:40 | 2020-06-12 18:00 |  | 30 |  |  |  | 2020-03-20 17:40 | 2020-06-17 18:00 |  | 35 |  |  |  | 2020-03-26 23:59 | 2020-06-17 18:00 |  | 65 |  |  |  | 2020-04-02 17:40 | 2020-07-08 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-24 17:40 | 2020-07-08 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 364 |  |  |  |  | 101375
2722 | Task(Task)-->E (Engineering) | FAT PROCEDURE FOR MMI SYSTEM/DATA CONCENTRATOR |  | 1.24.1.3 | FAT PROCEDURE FOR MMI SYSTEM/DATA CONCENTRATOR-->ELECTRICAL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-12 18:00 | 2020-04-24 17:40 | 2020-06-05 18:00 | 2020-09-16 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-185 |  | 2020-02-13 11:47 | 7012-155-PVE-W-130 |  |  |  | A |  |  |  | 0.80863 | 0.000612 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 20.44 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5078 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-12 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-03-13 17:40 | 2020-06-12 18:00 |  | 30 |  |  |  | 2020-03-20 17:40 | 2020-06-19 18:00 |  | 35 |  |  |  | 2020-03-26 23:59 | 2020-06-19 18:00 |  | 65 |  |  |  | 2020-04-02 17:40 | 2020-07-10 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-24 17:40 | 2020-07-10 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 365 |  |  |  |  | 101376
2723 | Task(Task)-->E (Engineering) | GA & DATA SHEET OF RUBBER MATS |  | 1.24.1.3 | GA & DATA SHEET OF RUBBER MATS-->ELECTRICAL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-12 23:59 | 2020-08-24 17:40 | 2020-06-29 09:00 | 2020-09-02 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-187 |  | 2020-02-13 11:47 | 7012-155-PVE-W-132 |  |  |  | I |  |  |  | 0.26954 | 0.000204 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 8.17 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5079 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-07-12 23:59 | 2020-07-31 18:00 |  | 10 |  |  |  | 2020-07-13 17:40 | 2020-08-07 18:00 |  | 30 |  |  |  | 2020-07-18 17:40 | 2020-08-12 18:00 |  | 35 |  |  |  | 2020-07-24 23:59 | 2020-08-12 18:00 |  | 65 | 2020-07-28 15:43 |  |  | 2020-07-31 17:40 | 2020-09-02 18:00 |  | 80 | 2020-08-03 10:01 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-08-24 17:40 | 2020-09-02 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 367 |  |  |  |  | 101378
2724 | Task(Task)-->E (Engineering) | GA DRAWING OF LIGHTING POLE |  | 1.24.1.3 | GA DRAWING OF LIGHTING POLE-->ELECTRICAL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-12 23:59 | 2020-08-24 17:40 | 2020-06-21 23:59 | 2020-07-24 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-188 |  | 2020-02-13 11:47 | 7012-155-PVE-B-133 |  |  |  | I |  |  |  | 0.26954 | 0.000204 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 8.17 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5044 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-07-12 23:59 | 2020-06-21 23:59 |  | 10 |  |  |  | 2020-07-13 17:40 | 2020-06-28 23:59 |  | 30 |  |  |  | 2020-07-18 17:40 | 2020-07-03 18:00 |  | 35 |  |  |  | 2020-07-24 23:59 | 2020-07-03 18:00 |  | 65 | 2020-07-28 15:42 |  |  | 2020-07-31 17:40 | 2020-07-24 18:00 |  | 80 | 2020-07-28 17:46 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-08-24 17:40 | 2020-07-24 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 368 |  |  |  |  | 101379
2725 | Task(Task)-->E (Engineering) | DATA SHEET OF GLANDS & LUGS |  | 1.24.1.3 | DATA SHEET OF GLANDS & LUGS-->ELECTRICAL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-09 18:00 | 2020-08-24 17:40 | 2020-07-31 18:00 | 2020-09-05 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-189 |  | 2020-02-13 11:47 | 7012-155-PVE-Y-134 |  |  |  | I |  |  |  | 0.26954 | 0.000204 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 8.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5084 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-07-09 18:00 | 2020-07-31 18:00 |  | 10 |  |  |  | 2020-07-13 17:40 | 2020-08-07 18:00 |  | 30 |  |  |  | 2020-07-18 17:40 | 2020-08-15 18:00 |  | 35 |  |  |  | 2020-07-24 23:59 | 2020-08-15 18:00 |  | 65 |  |  |  | 2020-07-31 17:40 | 2020-09-05 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-08-24 17:40 | 2020-09-05 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 369 |  |  |  |  | 101380
2726 | Task(Task)-->E (Engineering) | DATA SHEET OF TRE-FOIL CLAMPS |  | 1.24.1.3 | DATA SHEET OF TRE-FOIL CLAMPS-->ELECTRICAL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-13 17:40 | 2020-08-24 17:40 | 2020-06-21 23:59 | 2020-08-21 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-190 |  | 2020-02-13 11:47 | 7012-155-PVE-Y-135 |  |  |  | I |  |  |  | 0.26954 | 0.000204 | 0.02 | Plan & Actual | Date |  | 0 | 0 | 0 | 8.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5085 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-07-13 18:00 | 2020-06-21 23:59 |  | 10 |  |  |  | 2020-07-13 17:40 | 2020-06-28 23:59 |  | 30 |  |  |  | 2020-07-18 17:40 | 2020-07-02 18:00 |  | 35 |  |  |  | 2020-07-24 23:59 | 2020-07-02 18:00 |  | 65 |  |  |  | 2020-07-31 17:40 | 2020-07-23 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-08-24 17:40 | 2020-07-23 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 370 |  |  |  |  | 101381
2727 | Task(Task)-->E (Engineering) | DATA SHEET OF EARTHING & LIGHTNING MATERIALS |  | 1.24.1.3 | DATA SHEET OF EARTHING & LIGHTNING MATERIALS-->ELECTRICAL-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-11 18:00 | 2020-08-24 17:40 | 2020-07-11 18:00 | 2020-08-14 18:00 |  |  | 2020-02-29 14:35 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->3(Electrical) | O19133-E-BM-CH-VD-408 |  | 2020-02-13 11:47 | 7012-155-PVE-W-144 |  |  |  | A |  |  |  | 1.4825 | 0.001122 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 41.27 | 0 | 8.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5080 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-07-11 18:00 | 2020-07-11 18:00 |  | 10 |  |  |  | 2020-07-13 17:40 | 2020-07-18 18:00 |  | 30 |  |  |  | 2020-07-18 17:40 | 2020-07-24 18:00 |  | 35 |  |  |  | 2020-07-24 23:59 | 2020-07-24 18:00 |  | 65 | 2020-07-28 15:44 |  |  | 2020-07-31 17:40 | 2020-08-14 18:00 |  | 80 | 2020-08-03 10:00 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-08-24 17:40 | 2020-08-14 18:00 |  | 100 | [122 empty] | Varun Parihari | [22 empty] | 379 |  |  |  |  | 101390
2728 | Task(Task)-->E (Engineering) | C&I | 1.24.1.4 | 1.24.1 | C&I-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-10-16 18:00 | 2020-06-15 17:40 | 2019-10-19 18:00 | 2020-12-02 18:00 |  |  | 2020-02-21 14:08 |  |  |  | 100 | 74.6938 | [15 empty] | 47.0481 | 0.10534 | 10.36 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5086 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1036143
2729 | Task(Task)-->E (Engineering) | TYPICAL IO LIST |  | 1.24.1.4 | TYPICAL IO LIST-->C&I-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2019-10-16 18:00 | 2019-11-27 17:40 | 2019-11-29 09:00 | 2020-02-07 18:00 |  |  | 2020-02-21 14:08 | 2020-06-19 12:13 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-BE-001 |  | 2020-02-13 11:48 | 7012-155-PVI-G-001 |  |  |  | A |  |  |  | 0.61224 | 0.000645 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 22.03 | 0 | 0.14 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5096 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-10-16 18:00 | 2019-10-19 18:00 |  | 10 | 2019-10-19 23:31 |  |  | 2019-10-19 17:40 | 2019-10-25 18:00 |  | 30 | 2019-10-25 23:31 |  |  | 2019-10-25 17:40 | 2019-10-30 18:00 |  | 35 | 2019-10-30 23:31 |  |  | 2019-10-31 23:59 | 2019-11-29 18:00 |  | 65 | 2019-11-29 23:31 |  |  | 2019-11-06 17:40 | 2019-12-27 18:00 |  | 80 | 2019-12-27 23:31 | [5 empty] | 80 | 2020-06-01 16:00 | [5 empty] | 80 | 2020-06-01 16:00 | [5 empty] | 80 | 2020-06-03 15:01 | [5 empty] | 80 | 2020-06-03 15:01 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2019-11-27 17:40 | 2020-02-21 18:00 |  | 100 | 2020-05-01 23:31 | [121 empty] | Subhrajyoti Ghosh | [22 empty] | 406 |  |  |  |  | 101418
2730 | Task(Task)-->E (Engineering) | CCTV SYSTEM CONFIGURATION DIAGRAM |  | 1.24.1.4 | CCTV SYSTEM CONFIGURATION DIAGRAM-->C&I-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-10-17 18:00 | 2019-11-27 17:40 | 2019-10-19 18:00 | 2020-03-12 18:00 |  |  | 2020-02-21 14:08 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-BE-003 |  | 2020-02-13 11:48 | 7012-155-PVI-Q-003 |  |  |  | A |  |  |  | 0.61224 | 0.000645 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 22.03 | 0 | 0.07 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5105 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-10-17 18:00 | 2019-10-19 18:00 |  | 10 | 2019-10-19 23:31 |  |  | 2019-10-19 17:40 | 2019-10-21 18:00 |  | 30 | 2019-10-21 23:31 |  |  | 2019-10-25 17:40 | 2019-10-31 18:00 |  | 35 | 2019-10-31 23:31 |  |  | 2019-10-31 23:59 | 2019-12-19 18:00 |  | 65 | 2019-12-19 23:31 |  |  | 2019-11-06 17:40 | 2020-01-30 18:00 |  | 80 | 2020-01-30 23:31 | [5 empty] | 80 | 2020-06-01 11:50 | [5 empty] | 80 | 2020-06-01 11:50 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2019-11-27 17:40 | 2020-03-12 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [22 empty] | 408 |  |  |  |  | 101420
2731 | Task(Task)-->E (Engineering) | PA SYSTEM CONFIGURATION DIAGRAM |  | 1.24.1.4 | PA SYSTEM CONFIGURATION DIAGRAM-->C&I-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-10-19 17:40 | 2019-11-27 17:40 | 2019-12-08 23:59 | 2020-03-17 18:00 |  |  | 2020-02-21 14:08 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-BE-004 |  | 2020-02-13 11:48 | 7012-155-PVI-Q-004 |  |  |  | A |  |  |  | 0.61224 | 0.000645 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 22.03 | 0 | 0.09 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5106 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-10-19 18:00 | 2019-12-08 23:59 |  | 10 | 2019-12-08 23:31 |  |  | 2019-10-19 17:40 | 2019-12-14 18:00 |  | 30 | 2019-12-14 23:31 |  |  | 2019-10-25 17:40 | 2019-12-17 18:00 |  | 35 | 2019-12-17 23:31 |  |  | 2019-10-31 23:59 | 2019-12-20 18:00 |  | 65 | 2019-12-20 23:31 |  |  | 2019-11-06 17:40 | 2020-01-30 18:00 |  | 80 | 2020-01-30 23:31 | [5 empty] | 80 | 2020-06-01 11:09 | [5 empty] | 80 | 2020-06-01 11:09 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2019-11-27 17:40 | 2020-03-17 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [22 empty] | 409 |  |  |  |  | 101421
2732 | Task(Task)-->E (Engineering) | UPS SIZING CALCULATION |  | 1.24.1.4 | UPS SIZING CALCULATION-->C&I-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-12-06 18:00 | 2020-01-16 17:40 | 2019-12-09 18:00 | 2020-05-02 18:00 |  |  | 2020-02-21 14:08 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-BE-009 |  | 2020-02-13 11:48 | 7012-155-PVI-U-009 |  |  |  | A |  |  |  | 1.2245 | 0.00129 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 45 | 0 | 0.16 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5108 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-12-06 18:00 | 2019-12-09 18:00 |  | 10 | 2019-12-09 23:31 |  |  | 2019-12-09 17:40 | 2019-12-13 18:00 |  | 30 | 2019-12-13 23:31 |  |  | 2019-12-14 17:40 | 2019-12-18 18:00 |  | 35 | 2019-12-18 23:31 |  |  | 2019-12-20 23:59 | 2020-02-18 18:00 |  | 65 | 2020-02-18 23:31 |  |  | 2019-12-26 17:40 | 2020-03-19 18:00 |  | 80 | 2020-03-07 23:31 | [5 empty] | 80 | 2020-06-03 15:56 | [5 empty] | 80 | 2020-06-03 15:56 | [5 empty] | 80 | 2020-06-12 11:42 | [5 empty] | 80 | 2020-06-12 11:42 | [5 empty] | 80 | 2020-08-17 11:40 | [5 empty] | 80 | 2020-08-17 11:40 | [5 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-01-16 17:40 | 2020-05-02 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [22 empty] | 414 |  |  |  |  | 101426
2733 | Task(Task)-->E (Engineering) | DRIVE LIST |  | 1.24.1.4 | DRIVE LIST-->C&I-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-12-16 18:00 | 2020-01-24 17:40 | 2019-12-16 18:00 | 2020-05-02 18:00 |  |  | 2020-02-21 14:08 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-DD-001 |  | 2020-02-13 11:48 | 7012-155-PVI-H-010 |  |  |  | A |  |  |  | 1.4286 | 0.001505 | 0.14 | Plan & Actual | Date |  | 0 | 0 | 0 | 52.03 | 0 | 0.19 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5099 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-12-16 18:00 | 2019-12-16 18:00 |  | 10 | 2019-12-16 23:31 |  |  | 2019-12-17 17:40 | 2019-12-23 18:00 |  | 30 | 2019-12-23 23:31 |  |  | 2019-12-23 17:40 | 2019-12-23 18:00 |  | 35 | 2019-12-23 23:31 |  |  | 2019-12-28 23:59 | 2019-12-31 18:00 |  | 65 | 2019-12-31 23:31 |  |  | 2020-01-03 17:40 | 2020-01-31 18:00 |  | 80 | 2020-01-31 23:31 | [5 empty] | 80 | 2020-06-03 16:09 | [5 empty] | 80 | 2020-06-03 16:09 | [5 empty] | 80 | 2020-06-03 16:14 | [5 empty] | 80 | 2020-06-03 16:14 | [5 empty] | 80 | 2020-09-24 18:00 | [5 empty] | 80 | 2020-09-24 18:00 | [5 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-01-24 17:40 | 2020-05-02 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [22 empty] | 415 |  |  |  |  | 101427
2734 | Task(Task)-->E (Engineering) | PROCESS IO LIST |  | 1.24.1.4 | PROCESS IO LIST-->C&I-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-12-04 17:40 | 2020-01-11 17:40 | 2019-12-04 18:00 | 2020-05-02 18:00 |  |  | 2020-02-21 14:08 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-DD-002 |  | 2020-02-13 11:48 | 7012-155-PVI-G-011 |  |  |  | A |  |  |  | 4.0816 | 0.0043 | 0.4 | Plan & Actual | Date |  | 0 | 0 | 0 | 150 | 0 | 6.1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5097 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-12-04 18:00 | 2019-12-04 18:00 |  | 10 | 2019-12-04 23:31 |  |  | 2019-12-04 17:40 | 2019-12-16 18:00 |  | 30 | 2019-12-16 23:31 |  |  | 2019-12-10 17:40 | 2019-12-16 18:00 |  | 35 |  |  |  | 2019-12-16 23:59 | 2019-12-20 18:00 |  | 65 | 2019-12-20 23:31 |  |  | 2019-12-21 17:40 | 2020-01-30 18:00 |  | 80 | 2020-01-30 23:31 | [5 empty] | 80 | 2020-06-01 16:43 | [5 empty] | 80 | 2020-06-01 16:43 | [5 empty] | 80 | 2020-06-03 10:56 | [5 empty] | 80 | 2020-06-03 10:56 | [5 empty] | 80 | 2020-09-24 17:50 | [5 empty] | 80 | 2020-09-24 17:50 | [5 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-01-11 17:40 | 2020-05-02 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [22 empty] | 416 |  |  |  |  | 101428
2735 | Task(Task)-->E (Engineering) | 24VDC SIZING CALCULATION, FEEDER LIST, BATTERY SIZING |  | 1.24.1.4 | 24VDC SIZING CALCULATION, FEEDER LIST, BATTERY SIZING-->C&I-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-02 18:00 | 2020-02-12 17:40 | 2020-01-02 18:00 | 2020-04-01 18:00 |  |  | 2020-09-03 13:26 |  |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-DD-003 |  | 2020-02-13 11:48 | 7012-155-PVI-U-012 |  |  |  | A |  |  |  | 1.6327 | 0.00172 | 0.16 | Plan & Actual | Date |  | 0 | 0 | 0 | 60 | 0 | 2.05 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5109 | 1 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-02 18:00 | 2020-01-02 18:00 |  | 10 | 2020-01-02 23:31 |  |  | 2020-01-03 17:40 | 2020-01-10 18:00 |  | 30 | 2020-01-10 23:31 |  |  | 2020-01-09 17:40 | 2020-01-10 18:00 |  | 35 |  |  |  | 2020-01-15 23:59 | 2020-01-28 18:00 |  | 65 | 2020-01-28 23:31 |  |  | 2020-01-21 17:40 | 2020-03-07 18:00 |  | 80 | 2020-03-07 23:31 | [5 empty] | 80 | 2020-08-17 11:11 | [5 empty] | 80 | 2020-08-17 11:11 | [5 empty] | 80 | 2020-09-03 13:26 | [5 empty] | 80 | 2020-09-03 13:26 | [5 empty] | 80 | 2020-09-15 18:02 | [5 empty] | 80 | 2020-09-15 18:02 | [5 empty] | 80 | 2020-10-07 14:31 | [5 empty] | 80 | 2020-10-07 14:31 |  |  | 2020-02-12 17:40 | 2020-04-01 18:00 |  | 100 | 2020-08-17 11:38 | [121 empty] | Subhrajyoti Ghosh | [22 empty] | 417 |  |  |  |  | 101429
2736 | Task(Task)-->E (Engineering) | BLD LEGEND SHEET |  | 1.24.1.4 | BLD LEGEND SHEET-->C&I-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-26 17:40 | 2020-05-07 17:40 | 2020-04-23 09:00 | 2020-07-08 18:00 |  |  | 2020-02-21 14:08 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-DD-004 |  | 2020-02-13 11:48 | 7012-155-PVI-T-013 |  |  |  | I |  |  |  | 1.2245 | 0.00129 | 0.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 45 | 0 | 12.16 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5087 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-29 23:59 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-03-26 17:40 | 2020-06-10 18:00 |  | 30 |  |  |  | 2020-04-02 17:40 | 2020-06-12 18:00 |  | 35 |  |  |  | 2020-04-08 23:59 | 2020-06-15 18:00 |  | 65 | 2020-04-23 23:31 |  |  | 2020-04-15 17:40 | 2020-07-06 18:00 |  | 80 | 2020-05-16 23:31 | [5 empty] | 80 | 2020-07-08 10:55 | [5 empty] | 80 | 2020-07-08 10:55 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-07 17:40 | 2020-07-06 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [22 empty] | 418 |  |  |  |  | 101430
2737 | Task(Task)-->E (Engineering) | BLD FOR FLAP GATE |  | 1.24.1.4 | BLD FOR FLAP GATE-->C&I-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-03 17:40 | 2020-05-15 17:40 | 2020-05-16 09:00 | 2020-12-02 18:00 |  |  | 2020-02-21 14:08 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-DD-006 |  | 2020-02-13 11:48 | 7012-155-PVI-T-015 |  |  |  | I |  |  |  | 2.8571 | 0.00301 | 0.28 | Plan & Actual | Date |  | 0 | 0 | 0 | 105 | 0 | 26.03 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5088 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-06 18:00 | 2020-10-04 23:59 |  | 10 |  |  |  | 2020-04-03 17:40 | 2020-10-09 18:00 |  | 30 |  |  |  | 2020-04-09 17:40 | 2020-10-11 23:59 |  | 35 |  |  |  | 2020-04-16 23:59 | 2020-10-14 18:00 |  | 65 | 2020-05-16 23:31 |  |  | 2020-04-22 17:40 | 2020-11-04 18:00 |  | 80 | 2020-05-22 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-15 17:40 | 2020-12-02 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [22 empty] | 420 |  |  |  |  | 101432
2738 | Task(Task)-->E (Engineering) | BLD FOR PIPE CONVEYOR |  | 1.24.1.4 | BLD FOR PIPE CONVEYOR-->C&I-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-04 17:40 | 2020-06-15 17:40 | 2020-10-04 23:59 | 2020-12-02 18:00 |  |  | 2020-02-21 14:08 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-DD-007 |  | 2020-02-13 11:48 | 7012-155-PVI-T-016 |  |  |  | I |  |  |  | 3.2653 | 0.00344 | 0.32 | Plan & Actual | Date |  | 0 | 0 | 0 | 120 | 0 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5095 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-05-06 18:00 | 2020-10-04 23:59 |  | 10 |  |  |  | 2020-05-04 17:40 | 2020-10-09 18:00 |  | 30 |  |  |  | 2020-05-11 17:40 | 2020-10-11 23:59 |  | 35 |  |  |  | 2020-05-16 23:59 | 2020-10-14 18:00 |  | 65 |  |  |  | 2020-05-22 17:40 | 2020-11-04 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-15 17:40 | 2020-12-02 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [22 empty] | 421 |  |  |  |  | 101433
2739 | Task(Task)-->E (Engineering) | BLD FOR ILMS/SM/MD |  | 1.24.1.4 | BLD FOR ILMS/SM/MD-->C&I-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-07 17:40 | 2020-05-19 17:40 | 2020-05-02 09:00 | 2020-11-04 18:00 |  |  | 2020-02-21 14:08 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-DD-008 |  | 2020-02-13 11:48 | 7012-155-PVI-T-017 |  |  |  | I |  |  |  | 0.81633 | 0.00086 | 0.08 | Plan & Actual | Date |  | 0 | 0 | 0 | 30 | 0 | 17.03 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5089 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-10 18:00 | 2020-10-04 23:59 |  | 10 |  |  |  | 2020-04-07 17:40 | 2020-10-09 18:00 |  | 30 |  |  |  | 2020-04-14 17:40 | 2020-10-11 23:59 |  | 35 |  |  |  | 2020-04-20 23:59 | 2020-10-14 18:00 |  | 65 | 2020-05-02 23:31 |  |  | 2020-04-27 17:40 | 2020-11-04 18:00 |  | 80 | 2020-05-22 23:31 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-19 17:40 | 2020-11-04 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [22 empty] | 422 |  |  |  |  | 101434
2740 | Task(Task)-->E (Engineering) | BLD FOR APRON FEEDER |  | 1.24.1.4 | BLD FOR APRON FEEDER-->C&I-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-09 17:40 | 2020-05-21 17:40 | 2020-06-23 09:00 | 2020-12-02 18:00 |  |  | 2020-02-21 14:08 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-DD-009 |  | 2020-02-13 11:48 | 7012-155-PVI-T-018 |  |  |  | I |  |  |  | 2.449 | 0.00258 | 0.24 | Plan & Actual | Date |  | 0 | 0 | 0 | 90 | 0 | 7.04 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5090 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-12 23:59 | 2020-10-04 23:59 |  | 10 |  |  |  | 2020-04-09 17:40 | 2020-10-09 18:00 |  | 30 |  |  |  | 2020-04-16 17:40 | 2020-10-11 23:59 |  | 35 |  |  |  | 2020-04-22 23:59 | 2020-10-14 18:00 |  | 65 | 2020-06-23 17:01 |  |  | 2020-04-29 17:40 | 2020-11-04 18:00 |  | 80 | 2020-07-18 10:29 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-21 17:40 | 2020-12-02 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [22 empty] | 423 |  |  |  |  | 101435
2741 | Task(Task)-->E (Engineering) | BLD FOR LT CONVEYOR AND BELT FEEDER |  | 1.24.1.4 | BLD FOR LT CONVEYOR AND BELT FEEDER-->C&I-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-16 17:40 | 2020-05-28 17:40 | 2020-10-04 23:59 | 2020-12-02 18:00 |  |  | 2020-02-21 14:08 |  |  |  | 100 | 65 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-DD-010 |  | 2020-02-13 11:48 | 7012-155-PVI-T-019 |  |  |  | I |  |  |  | 2.449 | 0.00258 | 0.24 | Plan & Actual | Date |  | 0 | 0 | 0 | 90 | 0 | 0.03 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5091 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-19 23:59 | 2020-10-04 23:59 |  | 10 |  |  |  | 2020-04-16 17:40 | 2020-10-09 18:00 |  | 30 |  |  |  | 2020-04-22 17:40 | 2020-10-11 23:59 |  | 35 |  |  |  | 2020-04-29 23:59 | 2020-10-14 18:00 |  | 65 | 2020-11-07 14:40 |  |  | 2020-05-05 17:40 | 2020-11-04 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-28 17:40 | 2020-12-02 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [22 empty] | 424 |  |  |  |  | 101436
2742 | Task(Task)-->E (Engineering) | BLD FOR MISCELLANEOUS ITEMS (UTILITY ITEMS) |  | 1.24.1.4 | BLD FOR MISCELLANEOUS ITEMS (UTILITY ITEMS)-->C&I-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-17 17:40 | 2020-05-29 17:40 | 2020-06-22 09:00 | 2020-12-02 18:00 |  |  | 2020-02-21 14:08 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-DD-011 |  | 2020-02-13 11:48 | 7012-155-PVI-T-020 |  |  |  | I |  |  |  | 2.449 | 0.00258 | 0.24 | Plan & Actual | Date |  | 0 | 0 | 0 | 90 | 0 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5092 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-20 18:00 | 2020-10-04 23:59 |  | 10 |  |  |  | 2020-04-17 17:40 | 2020-10-09 18:00 |  | 30 |  |  |  | 2020-04-23 17:40 | 2020-10-11 23:59 |  | 35 |  |  |  | 2020-04-30 23:59 | 2020-10-14 18:00 |  | 65 | 2020-06-22 17:36 |  |  | 2020-05-06 17:40 | 2020-11-04 18:00 |  | 80 | 2020-07-18 11:11 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-29 17:40 | 2020-12-02 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [22 empty] | 425 |  |  |  |  | 101437
2743 | Task(Task)-->E (Engineering) | BLD FOR SEQUENCE |  | 1.24.1.4 | BLD FOR SEQUENCE-->C&I-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-23 17:40 | 2020-06-04 17:40 | 2020-05-10 | 2020-12-02 18:00 |  |  | 2020-02-21 14:08 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-DD-012 |  | 2020-02-13 11:48 | 7012-155-PVI-T-021 |  |  |  | I |  |  |  | 2.449 | 0.00258 | 0.24 | Plan & Actual | Date |  | 0 | 0 | 0 | 90 | 0 | 17.07 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5093 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-26 23:59 | 2020-10-04 23:59 |  | 10 |  |  |  | 2020-04-23 17:40 | 2020-10-09 18:00 |  | 30 |  |  |  | 2020-04-30 17:40 | 2020-10-11 23:59 |  | 35 |  |  |  | 2020-05-06 23:59 | 2020-10-14 18:00 |  | 65 | 2020-05-10 23:31 |  |  | 2020-05-13 17:40 | 2020-11-04 18:00 |  | 80 | 2020-06-04 16:19 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-04 17:40 | 2020-12-02 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [22 empty] | 426 |  |  |  |  | 101438
2744 | Task(Task)-->E (Engineering) | BLD HMI |  | 1.24.1.4 | BLD HMI-->C&I-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-02 17:40 | 2020-06-12 17:40 | 2020-06-05 18:00 | 2020-11-15 23:59 |  |  | 2020-02-21 14:08 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-DD-013 |  | 2020-02-13 11:48 | 7012-155-PVI-T-022 |  |  |  | I |  |  |  | 4.0816 | 0.0043 | 0.4 | Plan & Actual | Date |  | 0 | 0 | 0 | 150 | 0 | 0.04 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5094 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-05-05 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-05-02 17:40 | 2020-06-10 18:00 |  | 30 |  |  |  | 2020-05-08 17:40 | 2020-06-12 18:00 |  | 35 |  |  |  | 2020-05-15 23:59 | 2020-06-15 18:00 |  | 65 | 2020-06-12 12:13 |  |  | 2020-05-21 17:40 | 2020-07-06 18:00 |  | 80 | 2020-07-06 16:41 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-12 17:40 | 2020-08-03 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [22 empty] | 427 |  |  |  |  | 101439
2745 | Task(Task)-->E (Engineering) | CONTROL CABLE BLOCK DIAGRAM |  | 1.24.1.4 | CONTROL CABLE BLOCK DIAGRAM-->C&I-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-11-08 17:40 | 2019-12-17 17:40 | 2019-11-19 18:00 | 2020-04-29 18:00 |  |  | 2020-02-21 14:08 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-DD-014 |  | 2020-02-13 11:48 | 7012-155-PVI-T-023 |  |  |  | A |  |  |  | 2.0408 | 0.00215 | 0.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 75 | 0 | 0.21 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5107 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-11-10 23:59 | 2019-11-19 18:00 |  | 10 | 2019-11-19 23:31 |  |  | 2019-11-08 17:40 | 2019-11-24 23:59 |  | 30 | 2019-11-24 23:31 |  |  | 2019-11-14 17:40 | 2019-11-26 18:00 |  | 35 | 2019-11-26 23:31 |  |  | 2019-11-20 23:59 | 2019-11-29 18:00 |  | 65 | 2019-11-29 23:31 |  |  | 2019-11-26 17:40 | 2020-01-08 18:00 |  | 80 | 2020-01-08 23:31 | [5 empty] | 80 | 2020-06-01 14:21 | [5 empty] | 80 | 2020-06-01 14:21 | [5 empty] | 80 | 2020-06-03 16:28 | [5 empty] | 80 | 2020-06-03 16:28 | [5 empty] | 80 | 2020-06-12 11:59 | [5 empty] | 80 | 2020-06-12 11:59 | [5 empty] | 80 | [6 empty] | 80 |  |  |  | 2019-12-17 17:40 | 2020-04-29 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [22 empty] | 428 |  |  |  |  | 101440
2746 | Task(Task)-->E (Engineering) | CABLE SCHEDULE WITH INTERCONNECTION |  | 1.24.1.4 | CABLE SCHEDULE WITH INTERCONNECTION-->C&I-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-23 17:40 | 2020-06-04 17:40 | 2020-05-30 18:00 | 2020-11-15 23:59 |  |  | 2020-02-21 14:08 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-DD-015 |  | 2020-02-13 11:48 | 7012-155-PVI-H-024 |  |  |  | I |  |  |  | 12.3469 | 0.013007 | 1.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 450 | 0 | 12.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5100 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-26 23:59 | 2020-05-30 18:00 |  | 10 |  |  |  | 2020-04-23 17:40 | 2020-05-30 18:00 |  | 30 |  |  |  | 2020-04-30 17:40 | 2020-06-02 18:00 |  | 35 |  |  |  | 2020-05-06 23:59 | 2020-06-02 18:00 |  | 65 | 2020-08-21 10:50 |  |  | 2020-05-13 17:40 | 2020-06-23 18:00 |  | 80 | 2020-09-03 12:58 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-06-04 17:40 | 2020-07-21 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [22 empty] | 429 |  |  |  |  | 101441
2747 | Task(Task)-->E (Engineering) | SLD FOR POWER DISTRIBUTION FOR C&I ITEMS |  | 1.24.1.4 | SLD FOR POWER DISTRIBUTION FOR C&I ITEMS-->C&I-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-12-06 17:40 | 2020-01-14 17:40 | 2020-01-14 18:00 | 2020-07-24 18:00 |  |  | 2020-02-21 14:08 |  |  |  | 100 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-DD-016 |  | 2020-02-13 11:48 | 7012-155-PVI-L-025 |  |  |  | I |  |  |  | 0.81633 | 0.00086 | 0.08 | Plan & Actual | Date |  | 0 | 0 | 0 | 30 | 0 | 2.19 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5101 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2019-12-08 23:59 | 2020-01-14 18:00 |  | 10 | 2020-01-14 23:31 |  |  | 2019-12-06 17:40 | 2020-01-19 23:59 |  | 30 | 2020-01-19 23:31 |  |  | 2019-12-12 17:40 | 2020-01-21 18:00 |  | 35 | 2020-01-21 23:31 |  |  | 2019-12-18 23:59 | 2020-01-24 18:00 |  | 65 | 2020-01-24 23:31 |  |  | 2019-12-24 17:40 | 2020-02-17 18:00 |  | 80 | 2020-02-17 23:31 | [5 empty] | 80 | 2020-06-03 11:22 | [5 empty] | 80 | 2020-06-03 11:22 | [5 empty] | 80 | 2020-06-12 11:51 | [5 empty] | 80 | 2020-06-12 11:51 | [5 empty] | 80 | 2020-09-15 17:55 | [5 empty] | 80 | 2020-09-15 17:55 | [5 empty] | 80 | 2020-10-27 16:49 | [5 empty] | 80 | 2020-10-27 16:49 |  |  | 2020-01-14 17:40 | 2020-04-29 18:00 |  | 100 | 2020-09-15 16:20 | [121 empty] | Subhrajyoti Ghosh | [22 empty] | 430 |  |  |  |  | 101442
2748 | Task(Task)-->E (Engineering) | TYPICAL PLC MODULE WIRING |  | 1.24.1.4 | TYPICAL PLC MODULE WIRING-->C&I-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-24 17:40 | 2020-03-05 17:40 | 2020-06-05 18:00 | 2020-10-16 18:00 |  |  | 2020-02-21 14:09 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-VD-002 |  | 2020-02-13 11:48 | 7012-155-PVI-L-027 |  |  |  | I |  |  |  | 0.61224 | 0.000645 | 0.06 | Plan & Actual | Date |  | 0 | 0 | 0 | 22.03 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5102 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-26 23:59 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-01-24 17:40 | 2020-06-10 18:00 |  | 30 | 2020-09-25 12:31 |  |  | 2020-01-30 17:40 | 2020-06-12 18:00 |  | 35 |  |  |  | 2020-02-05 23:59 | 2020-06-15 18:00 |  | 65 | 2020-08-12 14:32 |  |  | 2020-02-12 17:40 | 2020-07-06 18:00 |  | 80 | 2020-08-25 11:23 | [5 empty] | 80 | 2020-09-25 12:14 | [5 empty] | 80 | 2020-09-25 12:14 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-05 17:40 | 2020-07-06 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [22 empty] | 432 |  |  |  |  | 101444
2749 | Task(Task)-->E (Engineering) | GA, POWER DISTRIBUTION SCHEME & BOM FOR CHP PLC |  | 1.24.1.4 | GA, POWER DISTRIBUTION SCHEME & BOM FOR CHP PLC-->C&I-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-24 17:40 | 2020-03-05 17:40 | 2020-07-05 23:59 | 2020-10-16 18:00 |  |  | 2020-02-21 14:09 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-VD-003 |  | 2020-02-13 11:48 | 7012-155-PVI-L-028 |  |  |  | A |  |  |  | 4.898 | 0.00516 | 0.48 | Plan & Actual | Date |  | 0 | 0 | 0 | 180 | 0 | 6.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5103 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-26 23:59 | 2020-07-05 23:59 |  | 10 |  |  |  | 2020-01-24 17:40 | 2020-07-10 18:00 |  | 30 | 2020-08-29 13:23 |  |  | 2020-01-30 17:40 | 2020-07-12 23:59 |  | 35 |  |  |  | 2020-02-05 23:59 | 2020-07-15 18:00 |  | 65 | 2020-08-29 13:23 |  |  | 2020-02-12 17:40 | 2020-08-05 18:00 |  | 80 | 2020-09-03 13:01 | [5 empty] | 80 | 2020-10-07 13:47 | [5 empty] | 80 | 2020-10-07 13:47 | [5 empty] | 80 | 2020-11-06 12:20 | [5 empty] | 80 | 2020-11-06 12:20 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-05 17:40 | 2020-08-05 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [22 empty] | 433 |  |  |  |  | 101445
2750 | Task(Task)-->E (Engineering) | PLC FAT PROCEDURE |  | 1.24.1.4 | PLC FAT PROCEDURE-->C&I-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-27 17:40 | 2020-04-08 17:40 | 2020-06-30 18:00 | 2020-09-25 18:00 |  |  | 2020-02-21 14:09 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-VD-004 |  | 2020-02-13 11:48 | 7012-155-PVI-W-029 |  |  |  | I |  |  |  | 1.6327 | 0.00172 | 0.16 | Plan & Actual | Date |  | 0 | 0 | 0 | 60 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5113 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-29 18:00 | 2020-06-30 18:00 |  | 10 |  |  |  | 2020-02-27 17:40 | 2020-07-05 23:59 |  | 30 |  |  |  | 2020-03-04 17:40 | 2020-07-07 18:00 |  | 35 |  |  |  | 2020-03-10 23:59 | 2020-07-10 18:00 |  | 65 | 2020-08-29 12:57 |  |  | 2020-03-17 17:40 | 2020-07-31 18:00 |  | 80 | 2020-09-03 13:02 | [5 empty] | 80 | 2020-09-25 12:34 | [5 empty] | 80 | 2020-09-25 12:34 | [5 empty] | 80 | 2020-10-31 17:59 | [5 empty] | 80 | 2020-10-31 17:59 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-08 17:40 | 2020-07-31 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [22 empty] | 434 |  |  |  |  | 101446
2751 | Task(Task)-->E (Engineering) | IO ASSIGNMENT FOR PLC |  | 1.24.1.4 | IO ASSIGNMENT FOR PLC-->C&I-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-24 17:40 | 2020-03-05 17:40 | 2020-06-05 18:00 | 2020-11-15 23:59 |  |  | 2020-02-21 14:09 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-VD-005 |  | 2020-02-13 11:48 | 7012-155-PVI-G-030 |  |  |  | I |  |  |  | 8.2653 | 0.008707 | 0.81 | Plan & Actual | Date |  | 0 | 0 | 0 | 300 | 0 | 6.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5098 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-26 23:59 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-01-24 17:40 | 2020-06-10 18:00 |  | 30 | 2020-09-24 18:00 |  |  | 2020-01-30 17:40 | 2020-06-12 18:00 |  | 35 |  |  |  | 2020-02-05 23:59 | 2020-06-15 18:00 |  | 65 | 2020-09-24 18:00 |  |  | 2020-02-12 17:40 | 2020-07-06 18:00 |  | 80 | 2020-10-10 16:00 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-05 17:40 | 2020-07-06 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [22 empty] | 435 |  |  |  |  | 101447
2752 | Task(Task)-->E (Engineering) | MMI SCREENS FOR CHP PLC SYSTEM |  | 1.24.1.4 | MMI SCREENS FOR CHP PLC SYSTEM-->C&I-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-27 17:40 | 2020-04-08 17:40 | 2020-06-05 18:00 | 2020-08-21 18:00 |  |  | 2020-02-21 14:09 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-VD-006 |  | 2020-02-13 11:48 | 7012-155-PVI-V-031 |  |  |  | I |  |  |  | 2.0408 | 0.00215 | 0.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 75 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5110 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-29 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-02-27 17:40 | 2020-06-10 18:00 |  | 30 |  |  |  | 2020-03-04 17:40 | 2020-06-12 18:00 |  | 35 |  |  |  | 2020-03-10 23:59 | 2020-06-15 18:00 |  | 65 |  |  |  | 2020-03-17 17:40 | 2020-07-06 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-08 17:40 | 2020-07-06 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [22 empty] | 436 |  |  |  |  | 101448
2753 | Task(Task)-->E (Engineering) | DATASHEETS OF PLC COMPONENTS |  | 1.24.1.4 | DATASHEETS OF PLC COMPONENTS-->C&I-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-24 17:40 | 2020-03-05 17:40 | 2020-06-05 18:00 | 2020-11-15 23:59 |  |  | 2020-02-21 14:09 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-VD-007 |  | 2020-02-13 11:48 | 7012-155-PVI-Y-032 |  |  |  | I |  |  |  | 3.0612 | 0.003225 | 0.3 | Plan & Actual | Date |  | 0 | 0 | 0 | 112.03 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5120 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-26 23:59 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-01-24 17:40 | 2020-06-10 18:00 |  | 30 | 2020-08-29 13:19 |  |  | 2020-01-30 17:40 | 2020-06-12 18:00 |  | 35 |  |  |  | 2020-02-05 23:59 | 2020-06-15 18:00 |  | 65 | 2020-08-29 13:19 |  |  | 2020-02-12 17:40 | 2020-07-06 18:00 |  | 80 | 2020-09-03 13:03 | [5 empty] | 80 | 2020-09-25 12:37 | [5 empty] | 80 | 2020-09-25 12:37 | [5 empty] | 80 | 2020-11-06 12:46 | [5 empty] | 80 | 2020-11-06 12:46 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-05 17:40 | 2020-07-06 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [22 empty] | 437 |  |  |  |  | 101449
2754 | Task(Task)-->E (Engineering) | DATA SHEETS FOR FIBRE OPTIC CABLE |  | 1.24.1.4 | DATA SHEETS FOR FIBRE OPTIC CABLE-->C&I-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-04 17:40 | 2020-04-15 17:40 | 2020-06-21 23:59 | 2020-09-26 18:00 |  |  | 2020-02-21 14:09 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-VD-008 |  | 2020-02-13 11:48 | 7012-155-PVI-Y-033 |  |  |  | A |  |  |  | 1.0204 | 0.001075 | 0.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 37.03 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5121 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-07 18:00 | 2020-06-21 23:59 |  | 10 |  |  |  | 2020-03-04 17:40 | 2020-06-26 18:00 |  | 30 |  |  |  | 2020-03-10 17:40 | 2020-06-28 23:59 |  | 35 |  |  |  | 2020-03-17 23:59 | 2020-07-01 18:00 |  | 65 | 2020-08-04 16:49 |  |  | 2020-03-23 17:40 | 2020-07-22 18:00 |  | 80 | 2020-08-25 11:25 | [5 empty] | 80 | 2020-08-29 10:28 | [5 empty] | 80 | 2020-08-29 10:28 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-15 17:40 | 2020-07-22 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [22 empty] | 438 |  |  |  |  | 101450
2755 | Task(Task)-->E (Engineering) | DATA SHEET FOR CONTROL & INSTRUMENTATION CABLES |  | 1.24.1.4 | DATA SHEET FOR CONTROL & INSTRUMENTATION CABLES-->C&I-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-20 17:40 | 2020-04-02 17:40 | 2020-06-21 23:59 | 2020-08-21 18:00 |  |  | 2020-02-21 14:09 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-VD-009 |  | 2020-02-13 11:48 | 7012-155-PVI-Y-034 |  |  |  | A |  |  |  | 1.6327 | 0.00172 | 0.16 | Plan & Actual | Date |  | 0 | 0 | 0 | 60 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5122 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-23 23:59 | 2020-06-21 23:59 |  | 10 |  |  |  | 2020-02-20 17:40 | 2020-06-26 18:00 |  | 30 |  |  |  | 2020-02-27 17:40 | 2020-06-28 23:59 |  | 35 |  |  |  | 2020-03-04 23:59 | 2020-07-01 18:00 |  | 65 |  |  |  | 2020-03-10 17:40 | 2020-07-22 18:00 |  | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-02 17:40 | 2020-07-22 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [22 empty] | 439 |  |  |  |  | 101451
2756 | Task(Task)-->E (Engineering) | GA, DATA SHEETS,BOM AND TYPICAL SCHEMES FOR UPS |  | 1.24.1.4 | GA, DATA SHEETS,BOM AND TYPICAL SCHEMES FOR UPS-->C&I-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-05 17:40 | 2020-04-16 17:40 | 2020-06-25 18:00 | 2020-11-15 23:59 |  |  | 2020-02-21 14:09 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-VD-010 |  | 2020-02-13 11:48 | 7012-155-PVI-W-035 |  |  |  | A |  |  |  | 3.0612 | 0.003225 | 0.3 | Plan & Actual | Date |  | 0 | 0 | 0 | 112.03 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5114 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-08 23:59 | 2020-06-25 18:00 |  | 10 |  |  |  | 2020-03-05 17:40 | 2020-06-30 18:00 |  | 30 | 2020-09-01 11:20 |  |  | 2020-03-11 17:40 | 2020-07-02 18:00 |  | 35 |  |  |  | 2020-03-18 23:59 | 2020-07-05 23:59 |  | 65 | 2020-09-01 11:20 |  |  | 2020-03-24 17:40 | 2020-07-26 23:59 |  | 80 | 2020-10-06 10:02 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-16 17:40 | 2020-07-26 23:59 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [22 empty] | 440 |  |  |  |  | 101452
2757 | Task(Task)-->E (Engineering) | GA, DISTRIBUTION SLD, DATA SHEETS,BOM AND TYPICAL SCHEMES FOR 24DC BATTERY AND BATTERY CHARGER |  | 1.24.1.4 | GA, DISTRIBUTION SLD, DATA SHEETS,BOM AND TYPICAL SCHEMES FOR 24DC BATTERY AND BATTERY CHARGER-->C&I-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-28 17:40 | 2020-04-09 17:40 | 2020-07-05 23:59 | 2020-10-30 18:00 |  |  | 2020-02-21 14:09 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-VD-011 |  | 2020-02-13 11:48 | 7012-155-PVI-W-036 |  |  |  | A |  |  |  | 3.2653 | 0.00344 | 0.32 | Plan & Actual | Date |  | 0 | 0 | 0 | 120 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5115 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-01 23:59 | 2020-07-05 23:59 |  | 10 |  |  |  | 2020-02-28 17:40 | 2020-07-10 18:00 |  | 30 | 2020-09-01 11:16 |  |  | 2020-03-05 17:40 | 2020-07-12 23:59 |  | 35 |  |  |  | 2020-03-11 23:59 | 2020-07-15 18:00 |  | 65 | 2020-09-01 11:17 |  |  | 2020-03-18 17:40 | 2020-08-05 18:00 |  | 80 | 2020-10-06 10:15 | [5 empty] | 80 | 2020-10-07 14:14 | [5 empty] | 80 | 2020-10-07 14:14 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-09 17:40 | 2020-08-05 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [22 empty] | 441 |  |  |  |  | 101453
2758 | Task(Task)-->E (Engineering) | GA, AND WIRING OF PDB |  | 1.24.1.4 | GA, AND WIRING OF PDB-->C&I-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-07 17:40 | 2020-04-18 17:40 | 2020-07-11 18:00 | 2020-09-03 18:00 |  |  | 2020-02-21 14:09 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-VD-012 |  | 2020-02-13 11:48 | 7012-155-PVI-W-037 |  |  |  | A |  |  |  | 3.2653 | 0.00344 | 0.32 | Plan & Actual | Date |  | 0 | 0 | 0 | 120 | 0 | 4.02 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5116 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-10 18:00 | 2020-07-11 18:00 |  | 10 |  |  |  | 2020-03-07 17:40 | 2020-07-16 18:00 |  | 30 |  |  |  | 2020-03-13 17:40 | 2020-07-18 18:00 |  | 35 |  |  |  | 2020-03-20 23:59 | 2020-07-21 18:00 |  | 65 | 2020-08-13 12:26 |  |  | 2020-03-26 17:40 | 2020-08-11 18:00 |  | 80 | 2020-09-03 12:53 | [5 empty] | 80 | 2020-09-06 13:47 | [5 empty] | 80 | 2020-09-06 13:47 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-04-18 17:40 | 2020-08-11 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [22 empty] | 442 |  |  |  |  | 101454
2759 | Task(Task)-->E (Engineering) | GA OF CONTROL JUNCTION BOXES |  | 1.24.1.4 | GA OF CONTROL JUNCTION BOXES-->C&I-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-26 17:40 | 2020-05-07 17:40 | 2020-07-21 18:00 | 2020-11-15 23:59 |  |  | 2020-02-21 14:09 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-VD-013 |  | 2020-02-13 11:48 | 7012-155-PVI-W-038 |  |  |  | A |  |  |  | 3.2653 | 0.00344 | 0.32 | Plan & Actual | Date |  | 0 | 0 | 0 | 120 | 0 | 4.03 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5117 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-29 23:59 | 2020-07-21 18:00 |  | 10 |  |  |  | 2020-03-26 17:40 | 2020-07-26 23:59 |  | 30 | 2020-10-28 10:25 |  |  | 2020-04-02 17:40 | 2020-07-28 18:00 |  | 35 |  |  |  | 2020-04-08 23:59 | 2020-07-31 18:00 |  | 65 | 2020-08-04 16:53 |  |  | 2020-04-15 17:40 | 2020-08-21 18:00 |  | 80 | 2020-09-01 10:02 | [5 empty] | 80 | 2020-09-08 20:47 | [5 empty] | 80 | 2020-09-08 20:47 | [5 empty] | 80 | 2020-10-27 17:06 | [5 empty] | 80 | 2020-10-27 17:06 | [5 empty] | 80 | 2020-10-31 11:41 | [5 empty] | 80 | 2020-10-31 11:41 | [5 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-07 17:40 | 2020-08-21 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [22 empty] | 443 |  |  |  |  | 101455
2760 | Task(Task)-->E (Engineering) | GA,DATA SHEET & SCHEME OF CCTV SYSTEM |  | 1.24.1.4 | GA,DATA SHEET & SCHEME OF CCTV SYSTEM-->C&I-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-01 17:40 | 2020-05-13 17:40 | 2020-06-21 23:59 | 2020-11-15 23:59 |  |  | 2020-02-21 14:09 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-VD-014 |  | 2020-02-13 11:49 | 7012-155-PVI-W-039 |  |  |  | A |  |  |  | 4.898 | 0.00516 | 0.48 | Plan & Actual | Date |  | 0 | 0 | 0 | 180 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5118 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-04-04 18:00 | 2020-06-21 23:59 |  | 10 |  |  |  | 2020-04-01 17:40 | 2020-06-26 18:00 |  | 30 |  |  |  | 2020-04-07 17:40 | 2020-06-28 23:59 |  | 35 |  |  |  | 2020-04-14 23:59 | 2020-07-01 18:00 |  | 65 | 2020-07-27 17:31 |  |  | 2020-04-20 17:40 | 2020-07-22 18:00 |  | 80 | 2020-09-01 09:57 | [5 empty] | 80 | 2020-11-07 17:36 | [5 empty] | 80 | 2020-11-07 17:36 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-13 17:40 | 2020-07-22 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [22 empty] | 444 |  |  |  |  | 101456
2761 | Task(Task)-->E (Engineering) | GA,DATA SHEET & SCHEME OF PA SYSTEM. |  | 1.24.1.4 | GA,DATA SHEET & SCHEME OF PA SYSTEM.-->C&I-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-20 17:40 | 2020-05-01 17:40 | 2020-06-21 23:59 | 2020-11-15 23:59 |  |  | 2020-02-21 14:09 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-VD-015 |  | 2020-02-13 11:49 | 7012-155-PVI-W-040 |  |  |  | A |  |  |  | 4.898 | 0.00516 | 0.48 | Plan & Actual | Date |  | 0 | 0 | 0 | 180 | 0 | 9.3 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5119 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-23 18:00 | 2020-06-21 23:59 |  | 10 |  |  |  | 2020-03-20 17:40 | 2020-06-26 18:00 |  | 30 |  |  |  | 2020-03-26 17:40 | 2020-06-28 23:59 |  | 35 |  |  |  | 2020-04-02 23:59 | 2020-07-01 18:00 |  | 65 | 2020-08-14 15:20 |  |  | 2020-04-08 17:40 | 2020-07-22 18:00 |  | 80 | 2020-09-03 13:00 | [5 empty] | 80 | 2020-10-12 11:39 | [5 empty] | 80 | 2020-10-12 11:39 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-01 17:40 | 2020-07-22 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [22 empty] | 445 |  |  |  |  | 101457
2762 | Task(Task)-->E (Engineering) | TECHNICAL DETAILS OF GROUP CONTROL PANEL, PCS AND BSS |  | 1.24.1.4 | TECHNICAL DETAILS OF GROUP CONTROL PANEL, PCS AND BSS-->C&I-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-14 17:40 | 2020-03-26 17:40 | 2020-06-05 18:00 | 2020-09-03 18:00 |  |  | 2020-02-21 14:09 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-VD-017 |  | 2020-02-13 11:49 | 7012-155-PVI-Y-042 |  |  |  | A |  |  |  | 3.6735 | 0.00387 | 0.36 | Plan & Actual | Date |  | 0 | 0 | 0 | 135 | 0 | 2.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5123 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-17 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-02-14 17:40 | 2020-06-10 18:00 |  | 30 |  |  |  | 2020-02-20 17:40 | 2020-06-12 18:00 |  | 35 |  |  |  | 2020-02-27 23:59 | 2020-06-15 18:00 |  | 65 | 2020-08-22 17:38 |  |  | 2020-03-04 17:40 | 2020-07-06 18:00 |  | 80 | 2020-09-03 12:56 | [5 empty] | 80 | 2020-09-05 17:43 | [5 empty] | 80 | 2020-09-05 17:43 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-26 17:40 | 2020-07-06 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [22 empty] | 447 |  |  |  |  | 101459
2763 | Task(Task)-->E (Engineering) | TECHNICAL DETAILS OF ZERO SPEED SWITCH |  | 1.24.1.4 | TECHNICAL DETAILS OF ZERO SPEED SWITCH-->C&I-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-12 17:40 | 2020-03-24 17:40 | 2020-06-05 18:00 | 2020-08-25 18:00 |  |  | 2020-02-21 14:09 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-VD-018 |  | 2020-02-13 11:49 | 7012-155-PVI-Y-043 |  |  |  | A |  |  |  | 1.0204 | 0.001075 | 0.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 37.03 | 0 | 3.01 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5124 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-15 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-02-12 17:40 | 2020-06-10 18:00 |  | 30 |  |  |  | 2020-02-18 17:40 | 2020-06-12 18:00 |  | 35 |  |  |  | 2020-02-25 23:59 | 2020-06-15 18:00 |  | 65 | 2020-08-17 11:56 |  |  | 2020-03-02 17:40 | 2020-07-06 18:00 |  | 80 | 2020-08-25 11:27 | [5 empty] | 80 | 2020-10-08 11:50 | [5 empty] | 80 | 2020-10-08 11:50 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-24 17:40 | 2020-07-06 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [22 empty] | 448 |  |  |  |  | 101460
2764 | Task(Task)-->E (Engineering) | TECHNICAL DETAILS OF CHUTE BLOCK SWITCH |  | 1.24.1.4 | TECHNICAL DETAILS OF CHUTE BLOCK SWITCH-->C&I-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-13 17:40 | 2020-03-25 17:40 | 2020-02-08 18:00 | 2020-07-12 23:59 |  |  | 2020-02-21 14:09 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-VD-019 |  | 2020-02-13 11:49 | 7012-155-PVI-Y-044 |  |  |  | A |  |  |  | 1.0204 | 0.001075 | 0.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 37.03 | 0 | 5.03 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5125 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-02-16 23:59 | 2020-02-08 18:00 |  | 10 | 2020-02-08 23:31 |  |  | 2020-02-13 17:40 | 2020-02-13 18:00 |  | 30 | 2020-02-13 23:31 |  |  | 2020-02-19 17:40 | 2020-02-15 18:00 |  | 35 | 2020-02-15 23:31 |  |  | 2020-02-26 23:59 | 2020-02-18 18:00 |  | 65 | 2020-02-18 23:31 |  |  | 2020-03-03 17:40 | 2020-03-13 18:00 |  | 80 | 2020-03-13 23:31 | [5 empty] | 80 | 2020-06-01 17:05 | [5 empty] | 80 | 2020-06-01 17:05 | [5 empty] | 80 | 2020-06-01 17:11 | [5 empty] | 80 | 2020-06-01 17:11 | [5 empty] | 80 | 2020-07-08 11:02 | [5 empty] | 80 | 2020-07-08 11:02 | [5 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-03-25 17:40 | 2020-05-01 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [22 empty] | 449 |  |  |  |  | 101461
2765 | Task(Task)-->E (Engineering) | TECHNICAL DETAILS OF SINGLE CHANNEL TEMPERATURE TRANSMITTER |  | 1.24.1.4 | TECHNICAL DETAILS OF SINGLE CHANNEL TEMPERATURE TRANSMITTER-->C&I-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-30 17:40 | 2020-05-11 17:40 | 2020-05-21 18:00 | 2020-08-25 18:00 |  |  | 2020-02-21 14:09 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-VD-020 |  | 2020-02-13 11:49 | 7012-155-PVI-Y-045 |  |  |  | A |  |  |  | 1.0204 | 0.001075 | 0.1 | Plan & Actual | Date |  | 0 | 0 | 0 | 37.03 | 0 | 3.06 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5126 | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-03-31 18:00 | 2020-05-21 18:00 |  | 10 |  |  |  | 2020-03-30 17:40 | 2020-05-26 18:00 |  | 30 | 2020-07-24 16:30 |  |  | 2020-04-04 17:40 | 2020-05-28 18:00 |  | 35 |  |  |  | 2020-04-10 23:59 | 2020-05-31 23:59 |  | 65 | 2020-07-27 12:31 |  |  | 2020-04-17 17:40 | 2020-06-21 23:59 |  | 80 | 2020-08-25 11:30 | [5 empty] | 80 | 2020-09-07 12:20 | [5 empty] | 80 | 2020-09-07 12:20 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-05-11 17:40 | 2020-06-21 23:59 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [22 empty] | 450 |  |  |  |  | 101462
2766 | Task(Task)-->E (Engineering) | PLC CONFIGURATION DIAGRAM FOR CHP |  | 1.24.1.4 | PLC CONFIGURATION DIAGRAM FOR CHP-->C&I-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-18 17:40 | 2020-02-28 17:40 | 2020-01-18 09:00 | 2020-07-06 18:00 |  |  | 2020-02-21 14:08 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) | O19133-I-BM-CS-VD-001 |  | 2020-02-13 11:48 | 7012-155-PVI-Q-026 |  |  |  | A |  |  |  | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 15 | 0 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Engineering | 2020-01-20 18:00 | 2020-06-05 18:00 |  | 10 |  |  |  | 2020-01-18 17:40 | 2020-06-10 18:00 |  | 30 | 2020-09-25 12:34 |  |  | 2020-01-24 17:40 | 2020-06-12 18:00 |  | 35 |  |  |  | 2020-01-30 23:59 | 2020-06-15 18:00 |  | 65 | 2020-08-12 14:26 |  |  | 2020-02-05 17:40 | 2020-07-06 18:00 |  | 80 | 2020-08-25 11:21 | [5 empty] | 80 | 2020-09-25 12:32 | [5 empty] | 80 | 2020-09-25 12:32 | [5 empty] | 80 | 2020-10-31 17:55 | [5 empty] | 80 | 2020-10-31 17:55 | [5 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 | [6 empty] | 80 |  |  |  | 2020-02-28 17:40 | 2020-07-06 18:00 |  | 100 | [122 empty] | Subhrajyoti Ghosh | [22 empty] | 431 |  |  |  |  | 101443
2767 | Task(Task)-->E (Engineering) | Fabrication Drawings | 1.24.1.5 | 1.24.1 | Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-12 18:00 | 2020-11-30 18:00 | 2020-06-12 09:00 | 2020-11-30 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No |  | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1098568
2768 | Task(Task)-->E (Engineering) | GENERAL NOTES ON FABRICATION |  | 1.24.1.5 | GENERAL NOTES ON FABRICATION-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-12 18:00 | 2020-06-12 18:00 | 2020-06-12 09:00 | 2020-06-12 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2001 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-06-12 18:00 |  |  | 100 | [122 empty] | 1098580
2769 | Task(Task)-->E (Engineering) | GENERAL GUIDE LINES FOR CORNER DETAILS OF HOOD & CHUTE AND FIXING ARRG. OF SKIRTS, SADDLES, CHUTE BLOCK SWITCH AND LINERS. |  | 1.24.1.5 | GENERAL GUIDE LINES FOR CORNER DETAILS OF HOOD & CHUTE AND FIXING ARRG. OF SKIRTS, SADDLES, CHUTE BLOCK SWITCH AND LINERS.-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-10 18:00 | 2020-07-10 18:00 | 2020-07-10 09:00 | 2020-07-10 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2002 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-07-10 18:00 |  |  | 100 | [122 empty] | 1098581
2770 | Task(Task)-->E (Engineering) | FAB. DETAIL OF STRINGER & SHORT POST FOR SC-1A/B & SC-2A/B (1400mm BELT WIDTH) |  | 1.24.1.5 | FAB. DETAIL OF STRINGER & SHORT POST FOR SC-1A/B & SC-2A/B (1400mm BELT WIDTH)-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-17 18:00 | 2020-06-17 18:00 | 2020-06-17 09:00 | 2020-06-17 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2003 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-06-17 18:00 |  |  | 100 | [122 empty] | 1098582
2771 | Task(Task)-->E (Engineering) | FAB. DETAIL OF STRINGER & SHORT POST FOR SC-3A/B (1800mm BELT WIDTH) |  | 1.24.1.5 | FAB. DETAIL OF STRINGER & SHORT POST FOR SC-3A/B (1800mm BELT WIDTH)-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-26 18:00 | 2020-06-26 18:00 | 2020-06-26 09:00 | 2020-06-26 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2004 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-06-26 18:00 |  |  | 100 | [122 empty] | 1098583
2772 | Task(Task)-->E (Engineering) | FAB. DETAIL OF STRINGER & SHORT POST FOR SY-1A/B (1800mm BELT WIDTH) |  | 1.24.1.5 | FAB. DETAIL OF STRINGER & SHORT POST FOR SY-1A/B (1800mm BELT WIDTH)-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-12 18:00 | 2020-06-12 18:00 | 2020-06-12 09:00 | 2020-06-12 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2005 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-06-12 18:00 |  |  | 100 | [122 empty] | 1098584
2773 | Task(Task)-->E (Engineering) | FAB. DETAIL OF STRINGER & SHORT POST FOR PC-1A/B (2000mm BELT WIDTH) |  | 1.24.1.5 | FAB. DETAIL OF STRINGER & SHORT POST FOR PC-1A/B (2000mm BELT WIDTH)-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-09-11 18:00 | 2020-09-11 18:00 | 2020-09-11 09:00 | 2020-09-11 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2006 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-09-11 18:00 |  |  | 100 | [122 empty] | 1098585
2774 | Task(Task)-->E (Engineering) | FAB. DETAIL OF STRINGER & SHORT POST FOR PC-2A/B (2000mm BELT WIDTH) |  | 1.24.1.5 | FAB. DETAIL OF STRINGER & SHORT POST FOR PC-2A/B (2000mm BELT WIDTH)-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-09-18 18:00 | 2020-09-18 18:00 | 2020-09-18 09:00 | 2020-09-18 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2007 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-09-18 18:00 |  |  | 100 | [122 empty] | 1098586
2775 | Task(Task)-->E (Engineering) | FAB. DETAIL OF STRINGER & SHORT POST FOR DRIBBLE FEEDERS DF-1,DF-2,DF-3 & DF-4 (2200mm BELT WIDTH) |  | 1.24.1.5 | FAB. DETAIL OF STRINGER & SHORT POST FOR DRIBBLE FEEDERS DF-1,DF-2,DF-3 & DF-4 (2200mm BELT WIDTH)-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-26 18:00 | 2020-06-26 18:00 | 2020-06-26 09:00 | 2020-06-26 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2008 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-06-26 18:00 |  |  | 100 | [122 empty] | 1098587
2776 | Task(Task)-->E (Engineering) | FAB. DETAIL OF STRINGER & SHORT POST SECTION FOR BELT FEEDER BF-1/2 2000mm BELT WIDTH |  | 1.24.1.5 | FAB. DETAIL OF STRINGER & SHORT POST SECTION FOR BELT FEEDER BF-1/2 2000mm BELT WIDTH-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-30 18:00 | 2020-06-30 18:00 | 2020-06-30 09:00 | 2020-06-30 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2009 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-06-30 18:00 |  |  | 100 | [122 empty] | 1098588
2777 | Task(Task)-->E (Engineering) | FAB. DETAIL OF DECK PLATE FOR SC-1A/B & SC-2A/B (1400mm BELT WIDTH) |  | 1.24.1.5 | FAB. DETAIL OF DECK PLATE FOR SC-1A/B & SC-2A/B (1400mm BELT WIDTH)-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-23 18:00 | 2020-06-23 18:00 | 2020-06-23 09:00 | 2020-06-23 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2010 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-06-23 18:00 |  |  | 100 | [122 empty] | 1098589
2778 | Task(Task)-->E (Engineering) | FAB. DETAIL OF DECK PLATE FOR SY-1A/B (1800mm BELT WIDTH) |  | 1.24.1.5 | FAB. DETAIL OF DECK PLATE FOR SY-1A/B (1800mm BELT WIDTH)-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-26 18:00 | 2020-06-26 18:00 | 2020-06-26 09:00 | 2020-06-26 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2011 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-06-26 18:00 |  |  | 100 | [122 empty] | 1098590
2779 | Task(Task)-->E (Engineering) | FAB. DETAIL OF DECK PLATE FOR PC-1A/B & PC-2A/B (2000mm BELT WIDTH) |  | 1.24.1.5 | FAB. DETAIL OF DECK PLATE FOR PC-1A/B & PC-2A/B (2000mm BELT WIDTH)-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-28 18:00 | 2020-08-28 18:00 | 2020-08-28 09:00 | 2020-08-28 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2012 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-08-28 18:00 |  |  | 100 | [122 empty] | 1098591
2780 | Task(Task)-->E (Engineering) | FAB. DETAIL OF DECK PLATE FOR BELT FEEDER FEEDER BF-1/2 (2000mm BELT WIDTH) |  | 1.24.1.5 | FAB. DETAIL OF DECK PLATE FOR BELT FEEDER FEEDER BF-1/2 (2000mm BELT WIDTH)-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-30 18:00 | 2020-06-30 18:00 | 2020-06-30 09:00 | 2020-06-30 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2013 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-06-30 18:00 |  |  | 100 | [122 empty] | 1098592
2781 | Task(Task)-->E (Engineering) | FAB. DETAIL OF DECK PLATE FOR DRIBBLE FEEDERS DF-1,DF-2,DF-3 & DF-4 (2200mm BELT WIDTH) |  | 1.24.1.5 | FAB. DETAIL OF DECK PLATE FOR DRIBBLE FEEDERS DF-1,DF-2,DF-3 & DF-4 (2200mm BELT WIDTH)-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-26 18:00 | 2020-06-26 18:00 | 2020-06-26 09:00 | 2020-06-26 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2014 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-06-26 18:00 |  |  | 100 | [122 empty] | 1098593
2782 | Task(Task)-->E (Engineering) | FAB. DETAIL OF DECK PLATE FOR SC-3A/B (1800mm BELT WIDTH) |  | 1.24.1.5 | FAB. DETAIL OF DECK PLATE FOR SC-3A/B (1800mm BELT WIDTH)-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-30 18:00 | 2020-06-30 18:00 | 2020-06-30 09:00 | 2020-06-30 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2015 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-06-30 18:00 |  |  | 100 | [122 empty] | 1098594
2783 | Task(Task)-->E (Engineering) | FAB. DETAIL OF TAIL PULLEY FRAME FOR SC-1A/1B & SC-2A/2B (1400mm BELT WIDTH) |  | 1.24.1.5 | FAB. DETAIL OF TAIL PULLEY FRAME FOR SC-1A/1B & SC-2A/2B (1400mm BELT WIDTH)-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-12 18:00 | 2020-06-12 18:00 | 2020-06-12 09:00 | 2020-06-12 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2016 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-06-12 18:00 |  |  | 100 | [122 empty] | 1098595
2784 | Task(Task)-->E (Engineering) | FAB. DETAIL OF TAIL PULLEY FRAME FOR SC-3A/3B (1800mm BELT WIDTH) |  | 1.24.1.5 | FAB. DETAIL OF TAIL PULLEY FRAME FOR SC-3A/3B (1800mm BELT WIDTH)-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-12 18:00 | 2020-06-12 18:00 | 2020-06-12 09:00 | 2020-06-12 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2017 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-06-12 18:00 |  |  | 100 | [122 empty] | 1098596
2785 | Task(Task)-->E (Engineering) | FAB. DETAIL OF TAIL PULLEY FRAME FOR SY-1A/1B (1800mm BELT WIDTH) |  | 1.24.1.5 | FAB. DETAIL OF TAIL PULLEY FRAME FOR SY-1A/1B (1800mm BELT WIDTH)-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-12 18:00 | 2020-06-12 18:00 | 2020-06-12 09:00 | 2020-06-12 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2018 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-06-12 18:00 |  |  | 100 | [122 empty] | 1098597
2786 | Task(Task)-->E (Engineering) | FAB. DETAIL OF TAIL CUM TAKE-UP PULLEY FRAME FOR BELT FEEDER BF-1/2 (2000mm BELT WIDTH) |  | 1.24.1.5 | FAB. DETAIL OF TAIL CUM TAKE-UP PULLEY FRAME FOR BELT FEEDER BF-1/2 (2000mm BELT WIDTH)-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-30 18:00 | 2020-06-30 18:00 | 2020-06-30 09:00 | 2020-06-30 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2019 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-06-30 18:00 |  |  | 100 | [122 empty] | 1098598
2787 | Task(Task)-->E (Engineering) | FAB. DETAIL OF TAIL CUM TAKE-UP PULLEY FRAME FOR DRIBBLE FEEDER DF-1/2/3/4 (2200mm BELT WIDTH) |  | 1.24.1.5 | FAB. DETAIL OF TAIL CUM TAKE-UP PULLEY FRAME FOR DRIBBLE FEEDER DF-1/2/3/4 (2200mm BELT WIDTH)-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-26 18:00 | 2020-06-26 18:00 | 2020-06-26 09:00 | 2020-06-26 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2020 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-06-26 18:00 |  |  | 100 | [122 empty] | 1098599
2788 | Task(Task)-->E (Engineering) | FAB.DETAIL OF DRIVE CUM DISCHARGE PULLEY FRAME FOR SC-1A/1B & SC-2A/2B (1400mm BELT WIDTH) |  | 1.24.1.5 | FAB.DETAIL OF DRIVE CUM DISCHARGE PULLEY FRAME FOR SC-1A/1B & SC-2A/2B (1400mm BELT WIDTH)-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-17 18:00 | 2020-06-17 18:00 | 2020-06-17 09:00 | 2020-06-17 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2021 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-06-17 18:00 |  |  | 100 | [122 empty] | 1098600
2789 | Task(Task)-->E (Engineering) | FAB.DETAIL OF DRIVE CUM DISCHARGE PULLEY FRAME FOR SC-3A/3B (1800mm BELT WIDTH) |  | 1.24.1.5 | FAB.DETAIL OF DRIVE CUM DISCHARGE PULLEY FRAME FOR SC-3A/3B (1800mm BELT WIDTH)-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-17 18:00 | 2020-06-17 18:00 | 2020-06-17 09:00 | 2020-06-17 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2022 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-06-17 18:00 |  |  | 100 | [122 empty] | 1098601
2790 | Task(Task)-->E (Engineering) | FAB.DETAIL OF DISCHARGE PULLEY FRAME FOR SY-1A/1B (1800mm BELT WIDTH) |  | 1.24.1.5 | FAB.DETAIL OF DISCHARGE PULLEY FRAME FOR SY-1A/1B (1800mm BELT WIDTH)-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-30 18:00 | 2020-06-30 18:00 | 2020-06-30 09:00 | 2020-06-30 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2023 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-06-30 18:00 |  |  | 100 | [122 empty] | 1098602
2791 | Task(Task)-->E (Engineering) | FAB.DETAIL OF DRIVE PULLEY FRAME FOR SY-1A & 1B (1800mm BELT WIDTH) IN DRIVE HOUSE-3 |  | 1.24.1.5 | FAB.DETAIL OF DRIVE PULLEY FRAME FOR SY-1A & 1B (1800mm BELT WIDTH) IN DRIVE HOUSE-3-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-30 18:00 | 2020-06-30 18:00 | 2020-06-30 09:00 | 2020-06-30 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2024 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-06-30 18:00 |  |  | 100 | [122 empty] | 1098603
2792 | Task(Task)-->E (Engineering) | FAB. DETAIL OF DRIVE CUM DISCHARGE PULLEY FRAME FOR DRIBBLE FEEDER, DF-1, DF-2, DF-3 & DF-4 (2200mm BELT WIDTH) |  | 1.24.1.5 | FAB. DETAIL OF DRIVE CUM DISCHARGE PULLEY FRAME FOR DRIBBLE FEEDER, DF-1, DF-2, DF-3 & DF-4 (2200mm BELT WIDTH)-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-26 18:00 | 2020-06-26 18:00 | 2020-06-26 09:00 | 2020-06-26 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2025 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-06-26 18:00 |  |  | 100 | [122 empty] | 1098604
2793 | Task(Task)-->E (Engineering) | FAB.DETAIL OF DRIVE CUM DISCHARGE PULLEY FRAME FOR BELT FEEDER BF-1/2 (2000mm BELT WIDTH) |  | 1.24.1.5 | FAB.DETAIL OF DRIVE CUM DISCHARGE PULLEY FRAME FOR BELT FEEDER BF-1/2 (2000mm BELT WIDTH)-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-30 18:00 | 2020-06-30 18:00 | 2020-06-30 09:00 | 2020-06-30 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2026 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-06-30 18:00 |  |  | 100 | [122 empty] | 1098605
2794 | Task(Task)-->E (Engineering) | FAB.DETAIL OF LT BEND PULLEY FRAME FOR SC-1A/1B & SC-2A/2B (1400mm BELT WIDTH) |  | 1.24.1.5 | FAB.DETAIL OF LT BEND PULLEY FRAME FOR SC-1A/1B & SC-2A/2B (1400mm BELT WIDTH)-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-12 18:00 | 2020-06-12 18:00 | 2020-06-12 09:00 | 2020-06-12 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2027 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-06-12 18:00 |  |  | 100 | [122 empty] | 1098606
2795 | Task(Task)-->E (Engineering) | FAB.DETAIL OF LT BEND PULLEY FRAME FOR SC-3A/3B (1800mm BELT WIDTH) |  | 1.24.1.5 | FAB.DETAIL OF LT BEND PULLEY FRAME FOR SC-3A/3B (1800mm BELT WIDTH)-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-12 18:00 | 2020-06-12 18:00 | 2020-06-12 09:00 | 2020-06-12 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2028 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-06-12 18:00 |  |  | 100 | [122 empty] | 1098607
2796 | Task(Task)-->E (Engineering) | FAB.DETAIL OF LT BEND PULLEY FRAME FOR SY-1A/1B (1800mm BELT WIDTH) |  | 1.24.1.5 | FAB.DETAIL OF LT BEND PULLEY FRAME FOR SY-1A/1B (1800mm BELT WIDTH)-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-12 18:00 | 2020-06-12 18:00 | 2020-06-12 09:00 | 2020-06-12 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2029 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-06-12 18:00 |  |  | 100 | [122 empty] | 1098608
2797 | Task(Task)-->E (Engineering) | FAB.DETAIL OF HT BEND PULLEY FRAME FOR SY-1A/1B (1800mm BELT WIDTH) |  | 1.24.1.5 | FAB.DETAIL OF HT BEND PULLEY FRAME FOR SY-1A/1B (1800mm BELT WIDTH)-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-12 18:00 | 2020-06-12 18:00 | 2020-06-12 09:00 | 2020-06-12 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2030 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-06-12 18:00 |  |  | 100 | [122 empty] | 1098609
2798 | Task(Task)-->E (Engineering) | FAB. DETAIL OF TAIL PULLEY FRAME FOR PC-1A/1B (2000mm BELT WIDTH) |  | 1.24.1.5 | FAB. DETAIL OF TAIL PULLEY FRAME FOR PC-1A/1B (2000mm BELT WIDTH)-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-20 18:00 | 2020-08-20 18:00 | 2020-08-20 09:00 | 2020-08-20 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2031 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-08-20 18:00 |  |  | 100 | [122 empty] | 1098610
2799 | Task(Task)-->E (Engineering) | FAB. DETAIL OF TAIL PULLEY FRAME FOR PC-2A/1B (2000mm BELT WIDTH) |  | 1.24.1.5 | FAB. DETAIL OF TAIL PULLEY FRAME FOR PC-2A/1B (2000mm BELT WIDTH)-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-20 18:00 | 2020-08-20 18:00 | 2020-08-20 09:00 | 2020-08-20 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2032 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-08-20 18:00 |  |  | 100 | [122 empty] | 1098611
2800 | Task(Task)-->E (Engineering) | FAB.DETAIL OF DISCHARGE PULLEY FRAME FOR PC-1A/1B & PC-2A/1B (2000mm BELT WIDTH) |  | 1.24.1.5 | FAB.DETAIL OF DISCHARGE PULLEY FRAME FOR PC-1A/1B & PC-2A/1B (2000mm BELT WIDTH)-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-31 | 2020-08-31 | 2020-08-30 | 2020-08-30 23:59 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2033 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-08-31 |  |  | 100 | [122 empty] | 1098612
2801 | Task(Task)-->E (Engineering) | FAB. DETAIL OF TAIL SIDE DRIVE PULLEY FRAME FOR PC-1A/1B IN SHB & PC-2A/2B IN KDTP-2 |  | 1.24.1.5 | FAB. DETAIL OF TAIL SIDE DRIVE PULLEY FRAME FOR PC-1A/1B IN SHB & PC-2A/2B IN KDTP-2-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-09-04 18:00 | 2020-09-04 18:00 | 2020-09-04 09:00 | 2020-09-04 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2034 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-09-04 18:00 |  |  | 100 | [122 empty] | 1098613
2802 | Task(Task)-->E (Engineering) | FAB. DETAIL OF DRIVE PULLEY FRAME FOR PC-1A -1, PC-1A -2 & PC-1B -1 AT KDTPC-2 AND PC-2A -1, PC-2A -2 & PC-2B -1 AT KDTPC-3 |  | 1.24.1.5 | FAB. DETAIL OF DRIVE PULLEY FRAME FOR PC-1A -1, PC-1A -2 & PC-1B -1 AT KDTPC-2 AND PC-2A -1, PC-2A -2 & PC-2B -1 AT KDTPC-3-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-09-11 18:00 | 2020-09-11 18:00 | 2020-09-11 09:00 | 2020-09-11 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2035 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-09-11 18:00 |  |  | 100 | [122 empty] | 1098614
2803 | Task(Task)-->E (Engineering) | FAB. DETAIL OF DRIVE PULLEY FRAME FOR PC-1B -2 AT KDTPC-2 AND PC-2B -2 AT KDTPC-3 |  | 1.24.1.5 | FAB. DETAIL OF DRIVE PULLEY FRAME FOR PC-1B -2 AT KDTPC-2 AND PC-2B -2 AT KDTPC-3-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-09-11 18:00 | 2020-09-11 18:00 | 2020-09-11 09:00 | 2020-09-11 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2036 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-09-11 18:00 |  |  | 100 | [122 empty] | 1098615
2804 | Task(Task)-->E (Engineering) | FAB.DETAIL OF LT BEND PULLEY FRAME FOR PC-1A AT KDTPC-2 AND PC-2A AT KDTPC-3 ( ON GROUND) |  | 1.24.1.5 | FAB.DETAIL OF LT BEND PULLEY FRAME FOR PC-1A AT KDTPC-2 AND PC-2A AT KDTPC-3 ( ON GROUND)-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-09-18 18:00 | 2020-09-18 18:00 | 2020-09-18 09:00 | 2020-09-18 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2037 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-09-18 18:00 |  |  | 100 | [122 empty] | 1098616
2805 | Task(Task)-->E (Engineering) | FAB.DETAIL OF LT BEND PULLEY FRAME FOR PC-1A , PC-1B, AT KDTPC-2 AND PC-2A & PC-2B AT KDTPC-3 (OVER GROUND) |  | 1.24.1.5 | FAB.DETAIL OF LT BEND PULLEY FRAME FOR PC-1A , PC-1B, AT KDTPC-2 AND PC-2A & PC-2B AT KDTPC-3 (OVER GROUND)-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-09-25 18:00 | 2020-09-25 18:00 | 2020-09-25 09:00 | 2020-09-25 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2038 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-09-25 18:00 |  |  | 100 | [122 empty] | 1098617
2806 | Task(Task)-->E (Engineering) | FAB.DETAIL OF HT BEND PULLEY FRAME FOR PC-1A , PC-1B, AT KDTPC-2 AND PC-2A & PC-2B AT KDTPC-3 (OVER GROUND) |  | 1.24.1.5 | FAB.DETAIL OF HT BEND PULLEY FRAME FOR PC-1A , PC-1B, AT KDTPC-2 AND PC-2A & PC-2B AT KDTPC-3 (OVER GROUND)-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-09-25 18:00 | 2020-09-25 18:00 | 2020-09-25 09:00 | 2020-09-25 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2039 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-09-25 18:00 |  |  | 100 | [122 empty] | 1098618
2807 | Task(Task)-->E (Engineering) | FAB. DETAIL OF DRIVE BASE FRAME FOR APRON FEEDER AF-1, AF-2, AF-3 & AF-4 |  | 1.24.1.5 | FAB. DETAIL OF DRIVE BASE FRAME FOR APRON FEEDER AF-1, AF-2, AF-3 & AF-4-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-09-04 18:00 | 2020-09-04 18:00 | 2020-09-04 09:00 | 2020-09-04 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2040 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-09-04 18:00 |  |  | 100 | [122 empty] | 1098619
2808 | Task(Task)-->E (Engineering) | FAB.DETAIL OF DRIVE BASE FRAME FOR SC-1A/1B, SC-2A/2B & SY 1AB |  | 1.24.1.5 | FAB.DETAIL OF DRIVE BASE FRAME FOR SC-1A/1B, SC-2A/2B & SY 1AB-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-09-11 18:00 | 2020-09-11 18:00 | 2020-09-11 09:00 | 2020-09-11 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2041 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-09-11 18:00 |  |  | 100 | [122 empty] | 1098620
2809 | Task(Task)-->E (Engineering) | FAB.DETAIL OF DRIVE BASE FRAME FOR SC-3A/3B (1800mm BELT WIDTH) |  | 1.24.1.5 | FAB.DETAIL OF DRIVE BASE FRAME FOR SC-3A/3B (1800mm BELT WIDTH)-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-09-15 18:00 | 2020-09-15 18:00 | 2020-09-15 09:00 | 2020-09-15 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2042 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-09-15 18:00 |  |  | 100 | [122 empty] | 1098621
2810 | Task(Task)-->E (Engineering) | FAB.DETAIL OF DRIVE BASE FRAME FOR BELT FEEDER BF-1/2 (2000mm BELT WIDTH) |  | 1.24.1.5 | FAB.DETAIL OF DRIVE BASE FRAME FOR BELT FEEDER BF-1/2 (2000mm BELT WIDTH)-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-09-19 18:00 | 2020-09-19 18:00 | 2020-09-19 09:00 | 2020-09-19 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2043 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-09-19 18:00 |  |  | 100 | [122 empty] | 1098622
2811 | Task(Task)-->E (Engineering) | FAB.DETAIL OF DRIVE BASE FRAME FOR DRIBBLE FEEDER DF-1/2/3/4 (2200mm BELT WIDTH) |  | 1.24.1.5 | FAB.DETAIL OF DRIVE BASE FRAME FOR DRIBBLE FEEDER DF-1/2/3/4 (2200mm BELT WIDTH)-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-09-19 18:00 | 2020-09-19 18:00 | 2020-09-19 09:00 | 2020-09-19 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2044 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-09-19 18:00 |  |  | 100 | [122 empty] | 1098623
2812 | Task(Task)-->E (Engineering) | FAB.DETAIL OF DRIVE BASE FRAME FOR PC-1A/1B & PC-2A/2B (ON GROUND) |  | 1.24.1.5 | FAB.DETAIL OF DRIVE BASE FRAME FOR PC-1A/1B & PC-2A/2B (ON GROUND)-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-10-16 18:00 | 2020-10-16 18:00 | 2020-10-16 09:00 | 2020-10-16 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2045 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-10-16 18:00 |  |  | 100 | [122 empty] | 1098624
2813 | Task(Task)-->E (Engineering) | FAB.DETAIL OF DRIVE BASE FRAME FOR PC-1B & PC-2B (ON SUB STRUCTURE) |  | 1.24.1.5 | FAB.DETAIL OF DRIVE BASE FRAME FOR PC-1B & PC-2B (ON SUB STRUCTURE)-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-10-16 18:00 | 2020-10-16 18:00 | 2020-10-16 09:00 | 2020-10-16 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2046 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-10-16 18:00 |  |  | 100 | [122 empty] | 1098625
2814 | Task(Task)-->E (Engineering) | G.A & FAB. DETAILS OF VGTU WITH ROPE FOR SC-1A/1B & SC-2A/2B (1400mm BELT WIDTH) |  | 1.24.1.5 | G.A & FAB. DETAILS OF VGTU WITH ROPE FOR SC-1A/1B & SC-2A/2B (1400mm BELT WIDTH)-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-30 18:00 | 2020-06-30 18:00 | 2020-06-30 09:00 | 2020-06-30 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2048 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-06-30 18:00 |  |  | 100 | [122 empty] | 1098626
2815 | Task(Task)-->E (Engineering) | G.A & FAB. DETAILS OF VGTU WITH ROPE FOR SC-3A/3B (1800mm BELT WIDTH) |  | 1.24.1.5 | G.A & FAB. DETAILS OF VGTU WITH ROPE FOR SC-3A/3B (1800mm BELT WIDTH)-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-10 18:00 | 2020-07-10 18:00 | 2020-07-10 09:00 | 2020-07-10 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2049 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-07-10 18:00 |  |  | 100 | [122 empty] | 1098627
2816 | Task(Task)-->E (Engineering) | G.A & FAB. DETAILS OF VGTU WITH ROPE FOR SY-1A/1B (1800mm BELT WIDTH) |  | 1.24.1.5 | G.A & FAB. DETAILS OF VGTU WITH ROPE FOR SY-1A/1B (1800mm BELT WIDTH)-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-04 18:00 | 2020-07-04 18:00 | 2020-07-04 09:00 | 2020-07-04 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2050 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-07-04 18:00 |  |  | 100 | [122 empty] | 1098628
2817 | Task(Task)-->E (Engineering) | G.A & FAB. DETAILS OF HGTU COUNTER WEIGHT FRAME FOR PC-1A /1B (2000 mm B/W) |  | 1.24.1.5 | G.A & FAB. DETAILS OF HGTU COUNTER WEIGHT FRAME FOR PC-1A /1B (2000 mm B/W)-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-10-05 18:00 | 2020-10-05 18:00 | 2020-10-05 09:00 | 2020-10-05 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2051 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-10-05 18:00 |  |  | 100 | [122 empty] | 1098629
2818 | Task(Task)-->E (Engineering) | G.A & FAB. DETAILS OF HGTU COUNTER WEIGHT FRAME FOR PC-2A /2B (2000 mm B/W) |  | 1.24.1.5 | G.A & FAB. DETAILS OF HGTU COUNTER WEIGHT FRAME FOR PC-2A /2B (2000 mm B/W)-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-10-05 18:00 | 2020-10-05 18:00 | 2020-10-05 09:00 | 2020-10-05 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2052 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-10-05 18:00 |  |  | 100 | [122 empty] | 1098630
2819 | Task(Task)-->E (Engineering) | G.A & FAB. DETAILS OF HGTU TROLLEY SUPPORT FRAME FOR PC-1A / B |  | 1.24.1.5 | G.A & FAB. DETAILS OF HGTU TROLLEY SUPPORT FRAME FOR PC-1A / B-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-28 18:00 | 2020-08-28 18:00 | 2020-08-28 09:00 | 2020-08-28 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2053 |  | 2020-07-15 15:20 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-08-28 18:00 |  |  | 100 | [122 empty] | 1098631
2820 | Task(Task)-->E (Engineering) | G.A & FAB. DETAILS OF HGTU TROLLEY SUPPORT FRAME FOR PC-2A / B |  | 1.24.1.5 | G.A & FAB. DETAILS OF HGTU TROLLEY SUPPORT FRAME FOR PC-2A / B-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-28 18:00 | 2020-08-28 18:00 | 2020-08-28 09:00 | 2020-08-28 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2054 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-08-28 18:00 |  |  | 100 | [122 empty] | 1098632
2821 | Task(Task)-->E (Engineering) | MARKING G.A. & FAB. DETAIL OF DISCHARGE CHUTE FROM DUMP HOPPER TO AF-1, AF-2, AF-3 & AF-4 AND SKIRT BOARD ON AF-1, AF-2, AF-3 & AF-4 FEEDING TO PRIMARY SIZER-1,2,3&4 RESPECTIVELY INSIDE DUMP HOPPER BUILDING |  | 1.24.1.5 | MARKING G.A. & FAB. DETAIL OF DISCHARGE CHUTE FROM DUMP HOPPER TO AF-1, AF-2, AF-3 & AF-4 AND SKIRT BOARD ON AF-1, AF-2, AF-3 & AF-4 FEEDING TO PRIMARY SIZER-1,2,3&4 RESPECTIVELY INSIDE DUMP HOPPER BUILDING-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-31 18:00 | 2020-07-31 18:00 | 2020-07-31 09:00 | 2020-07-31 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2056 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-07-31 18:00 |  |  | 100 | [122 empty] | 1098633
2822 | Task(Task)-->E (Engineering) | MARKING G.A. & FAB. DETAIL OF DISCHARGE CHUTE BELOW PRIMARY SIZER-1,2,3 & 4 AND TRAMP IRON CHUTE/SPILLAGE CHUTE OF PRIMARY SIZER-1,2,3 & 4 TO SC-1A/1B & SC-2A/2B AND SKIRT BOARD ON SC-1A/1B & SC-2A/2B IN DUMP HOPPER BUILDING |  | 1.24.1.5 | MARKING G.A. & FAB. DETAIL OF DISCHARGE CHUTE BELOW PRIMARY SIZER-1,2,3 & 4 AND TRAMP IRON CHUTE/SPILLAGE CHUTE OF PRIMARY SIZER-1,2,3 & 4 TO SC-1A/1B & SC-2A/2B AND SKIRT BOARD ON SC-1A/1B & SC-2A/2B IN DUMP HOPPER BUILDING-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-24 18:00 | 2020-07-24 18:00 | 2020-07-24 09:00 | 2020-07-24 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2057 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-07-24 18:00 |  |  | 100 | [122 empty] | 1098634
2823 | Task(Task)-->E (Engineering) | MARKING G.A. & FAB. DETAIL OF DISCHARGE CHUTE FROM SC-1A/1B & SC-2A/2B TO SECONDARY SIZER-1,2,3 & 4 IN KDTP-1 BUILDING |  | 1.24.1.5 | MARKING G.A. & FAB. DETAIL OF DISCHARGE CHUTE FROM SC-1A/1B & SC-2A/2B TO SECONDARY SIZER-1,2,3 & 4 IN KDTP-1 BUILDING-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-10 18:00 | 2020-07-10 18:00 | 2020-07-10 09:00 | 2020-07-10 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2058 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-07-10 18:00 |  |  | 100 | [122 empty] | 1098635
2824 | Task(Task)-->E (Engineering) | MARKING G.A. & FAB. DETAIL OF UNDER SIZE CHUTE FROM SECONDARY SIZER-1,2,3 & 4 TO SC-3A/3B AND SKIRT BOARD ON SC-3A/3B IN KDTP-1 BUILDING |  | 1.24.1.5 | MARKING G.A. & FAB. DETAIL OF UNDER SIZE CHUTE FROM SECONDARY SIZER-1,2,3 & 4 TO SC-3A/3B AND SKIRT BOARD ON SC-3A/3B IN KDTP-1 BUILDING-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-17 18:00 | 2020-07-17 18:00 | 2020-07-17 09:00 | 2020-07-17 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2059 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-07-17 18:00 |  |  | 100 | [122 empty] | 1098636
2825 | Task(Task)-->E (Engineering) | MARKING G.A. & FAB. DETAIL OF DISCHARGE CHUTE FROM SC-3A/3B TO SURGE HOPPER-1 & 2 IN SURGE HOPPER BUILDING |  | 1.24.1.5 | MARKING G.A. & FAB. DETAIL OF DISCHARGE CHUTE FROM SC-3A/3B TO SURGE HOPPER-1 & 2 IN SURGE HOPPER BUILDING-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-07 18:00 | 2020-08-07 18:00 | 2020-08-07 09:00 | 2020-08-07 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2060 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-08-07 18:00 |  |  | 100 | [122 empty] | 1098637
2826 | Task(Task)-->E (Engineering) | MARKING G.A. & FAB. DETAIL OF DISCHARGE CHUTE RECEIVING MATERIAL FROM SURGE HOPPER 1 & 2 TO BELT FEEDER-1 & 2 AND SKIRT BOARD ON BELT FEEDER-1 & 2, DISCHARGE CHUTE FROM BELT FEEDER-1 & 2 TO PIPE CONVEYOR PC-1A/1B & SKIRT BOARD ON PIPE CONVEYOR PC-1... |  | 1.24.1.5 | MARKING G.A. & FAB. DETAIL OF DISCHARGE CHUTE RECEIVING MATERIAL FROM SURGE HOPPER 1 & 2 TO BELT FEEDER-1 & 2 AND SKIRT BOARD ON BELT FEEDER-1 & 2, DISCHARGE CHUTE FROM BELT FEEDER-1 & 2 TO PIPE CONVEYOR PC-1A/1B & SKIRT BOARD ON PIPE CONVEYOR PC-1...-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-21 18:00 | 2020-08-21 18:00 | 2020-08-21 09:00 | 2020-08-21 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2061 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-08-21 18:00 |  |  | 100 | [122 empty] | 1098638
2827 | Task(Task)-->E (Engineering) | MARKING G.A. & FAB. DETAIL OF DISCHARGE CHUTE FROM PIPE CONVEYOR PC-1A/1B TO PIPE CONVEYOR PC-2A/2B AND SKIRT BOARD ON PIPE CONVEYOR PC-2A/2B IN KDTP-2 BUILDING |  | 1.24.1.5 | MARKING G.A. & FAB. DETAIL OF DISCHARGE CHUTE FROM PIPE CONVEYOR PC-1A/1B TO PIPE CONVEYOR PC-2A/2B AND SKIRT BOARD ON PIPE CONVEYOR PC-2A/2B IN KDTP-2 BUILDING-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-28 18:00 | 2020-08-28 18:00 | 2020-08-28 09:00 | 2020-08-28 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2062 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-08-28 18:00 |  |  | 100 | [122 empty] | 1098639
2828 | Task(Task)-->E (Engineering) | MARKING G.A. & FAB. DETAIL OF DISCHARGE CHUTE FROM PIPE CONVEYOR PC-2A/2B TO STOCK YARD CONVEYOR SY-1A/1B AND SKIRT BOARD ON STOCK YARD CONVEYOR SY-1A/1B IN KDTP-3 BUILDING |  | 1.24.1.5 | MARKING G.A. & FAB. DETAIL OF DISCHARGE CHUTE FROM PIPE CONVEYOR PC-2A/2B TO STOCK YARD CONVEYOR SY-1A/1B AND SKIRT BOARD ON STOCK YARD CONVEYOR SY-1A/1B IN KDTP-3 BUILDING-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-09-18 18:00 | 2020-09-18 18:00 | 2020-09-18 09:00 | 2020-09-18 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2063 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-09-18 18:00 |  |  | 100 | [122 empty] | 1098640
2829 | Task(Task)-->E (Engineering) | MARKING & FAB. DETAIL OF DEBRIS CHUTE AND ITS SUPPORTING BRACKETS IN DUMP HOPPER BUILDING |  | 1.24.1.5 | MARKING & FAB. DETAIL OF DEBRIS CHUTE AND ITS SUPPORTING BRACKETS IN DUMP HOPPER BUILDING-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-28 18:00 | 2020-08-28 18:00 | 2020-08-28 09:00 | 2020-08-28 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2064 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-08-28 18:00 |  |  | 100 | [122 empty] | 1098641
2830 | Task(Task)-->E (Engineering) | MARKING & FAB. DETAIL OF DEBRIS CHUTE AND ITS SUPPORTING BRACKETS IN KDTP-1 BUILDING |  | 1.24.1.5 | MARKING & FAB. DETAIL OF DEBRIS CHUTE AND ITS SUPPORTING BRACKETS IN KDTP-1 BUILDING-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-07 18:00 | 2020-08-07 18:00 | 2020-08-07 09:00 | 2020-08-07 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2065 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-08-07 18:00 |  |  | 100 | [122 empty] | 1098642
2831 | Task(Task)-->E (Engineering) | MARKING & FAB. DETAIL OF DEBRIS CHUTE AND ITS SUPPORTING BRACKETS IN SURGE HOPPER BUILDING |  | 1.24.1.5 | MARKING & FAB. DETAIL OF DEBRIS CHUTE AND ITS SUPPORTING BRACKETS IN SURGE HOPPER BUILDING-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-07 18:00 | 2020-08-07 18:00 | 2020-08-07 09:00 | 2020-08-07 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2066 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-08-07 18:00 |  |  | 100 | [122 empty] | 1098643
2832 | Task(Task)-->E (Engineering) | MARKING & FAB. DETAIL OF DEBRIS CHUTE AND ITS SUPPORTING BRACKETS IN KDTP-2 BUILDING |  | 1.24.1.5 | MARKING & FAB. DETAIL OF DEBRIS CHUTE AND ITS SUPPORTING BRACKETS IN KDTP-2 BUILDING-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-14 18:00 | 2020-08-14 18:00 | 2020-08-14 09:00 | 2020-08-14 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2067 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-08-14 18:00 |  |  | 100 | [122 empty] | 1098644
2833 | Task(Task)-->E (Engineering) | MARKING & FAB. DETAIL OF DEBRIS CHUTE AND ITS SUPPORTING BRACKETS IN KDTP-3 BUILDING |  | 1.24.1.5 | MARKING & FAB. DETAIL OF DEBRIS CHUTE AND ITS SUPPORTING BRACKETS IN KDTP-3 BUILDING-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-21 18:00 | 2020-08-21 18:00 | 2020-08-21 09:00 | 2020-08-21 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2068 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-08-21 18:00 |  |  | 100 | [122 empty] | 1098645
2834 | Task(Task)-->E (Engineering) | MARKING & FAB. DETAIL OF TRAMP IRON CHUTE IN KDTP-1 BUILDING |  | 1.24.1.5 | MARKING & FAB. DETAIL OF TRAMP IRON CHUTE IN KDTP-1 BUILDING-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-28 18:00 | 2020-08-28 18:00 | 2020-08-28 09:00 | 2020-08-28 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2069 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-08-28 18:00 |  |  | 100 | [122 empty] | 1098646
2835 | Task(Task)-->E (Engineering) | FAB. DETAIL OF INSPECTION DOOR |  | 1.24.1.5 | FAB. DETAIL OF INSPECTION DOOR-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-09-30 18:00 | 2020-09-30 18:00 | 2020-09-30 09:00 | 2020-09-30 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2070 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-09-30 18:00 |  |  | 100 | [122 empty] | 1098647
2836 | Task(Task)-->E (Engineering) | MARKING & FAB. DETAIL OF LINER IN DUMP HOPPER BUILDING |  | 1.24.1.5 | MARKING & FAB. DETAIL OF LINER IN DUMP HOPPER BUILDING-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-14 18:00 | 2020-08-14 18:00 | 2020-08-14 09:00 | 2020-08-14 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2071 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-08-14 18:00 |  |  | 100 | [122 empty] | 1098648
2837 | Task(Task)-->E (Engineering) | FAB. DETAIL OF TAIL PULLEY GUARD FOR TROUGH CONVEYOR |  | 1.24.1.5 | FAB. DETAIL OF TAIL PULLEY GUARD FOR TROUGH CONVEYOR-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-10-07 18:00 | 2020-10-07 18:00 | 2020-10-07 09:00 | 2020-10-07 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2073 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-10-07 18:00 |  |  | 100 | [122 empty] | 1098649
2838 | Task(Task)-->E (Engineering) | FAB. DETAIL OF TAIL PULLEY GUARD FOR PIPE CONVEYOR |  | 1.24.1.5 | FAB. DETAIL OF TAIL PULLEY GUARD FOR PIPE CONVEYOR-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-10-23 18:00 | 2020-10-23 18:00 | 2020-10-23 09:00 | 2020-10-23 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2074 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-10-23 18:00 |  |  | 100 | [122 empty] | 1098650
2839 | Task(Task)-->E (Engineering) | FAB. DETAIL OF TAIL CUM TAKE-UP PULLEY GUARD FOR DRIBBLE FEEDER DF-1,2,3 & 4 IN DUMP HOPPER BUILDING |  | 1.24.1.5 | FAB. DETAIL OF TAIL CUM TAKE-UP PULLEY GUARD FOR DRIBBLE FEEDER DF-1,2,3 & 4 IN DUMP HOPPER BUILDING-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-10-07 18:00 | 2020-10-07 18:00 | 2020-10-07 09:00 | 2020-10-07 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2075 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-10-07 18:00 |  |  | 100 | [122 empty] | 1098651
2840 | Task(Task)-->E (Engineering) | FAB. DETAIL OF TAIL CUM TAKE-UP PULLEY GUARD FOR BELT FEEDER BF-1/2 IN SURGE HOPPER BUILDING |  | 1.24.1.5 | FAB. DETAIL OF TAIL CUM TAKE-UP PULLEY GUARD FOR BELT FEEDER BF-1/2 IN SURGE HOPPER BUILDING-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-10-07 18:00 | 2020-10-07 18:00 | 2020-10-07 09:00 | 2020-10-07 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2076 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-10-07 18:00 |  |  | 100 | [122 empty] | 1098652
2841 | Task(Task)-->E (Engineering) | FAB. DETAIL OF BEND PULLEY GUARD FOR SY-1A/1B |  | 1.24.1.5 | FAB. DETAIL OF BEND PULLEY GUARD FOR SY-1A/1B-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-10-07 18:00 | 2020-10-07 18:00 | 2020-10-07 09:00 | 2020-10-07 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2077 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-10-07 18:00 |  |  | 100 | [122 empty] | 1098653
2842 | Task(Task)-->E (Engineering) | FAB. DETAIL OF BEND PULLEY GUARD FOR SC-3A/3B |  | 1.24.1.5 | FAB. DETAIL OF BEND PULLEY GUARD FOR SC-3A/3B-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-10-07 18:00 | 2020-10-07 18:00 | 2020-10-07 09:00 | 2020-10-07 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2078 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-10-07 18:00 |  |  | 100 | [122 empty] | 1098654
2843 | Task(Task)-->E (Engineering) | FAB. DETAIL OF BEND PULLEY GUARD FOR SC-1A/1B & SC-2A/2B |  | 1.24.1.5 | FAB. DETAIL OF BEND PULLEY GUARD FOR SC-1A/1B & SC-2A/2B-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-10-07 18:00 | 2020-10-07 18:00 | 2020-10-07 09:00 | 2020-10-07 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2079 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-10-07 18:00 |  |  | 100 | [122 empty] | 1098655
2844 | Task(Task)-->E (Engineering) | FAB DETAIL OF HT BEND PULLEY GUARD FOR PIPE CONVEYOR PC-1A/1B & PC-2A/2B |  | 1.24.1.5 | FAB DETAIL OF HT BEND PULLEY GUARD FOR PIPE CONVEYOR PC-1A/1B & PC-2A/2B-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-10-23 18:00 | 2020-10-23 18:00 | 2020-10-23 09:00 | 2020-10-23 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2080 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-10-23 18:00 |  |  | 100 | [122 empty] | 1098656
2845 | Task(Task)-->E (Engineering) | FAB DETAIL OF LT BEND PULLEY GUARD FOR PIPE CONVEYOR PC-1A/1B & PC-2A/2B |  | 1.24.1.5 | FAB DETAIL OF LT BEND PULLEY GUARD FOR PIPE CONVEYOR PC-1A/1B & PC-2A/2B-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-10-23 18:00 | 2020-10-23 18:00 | 2020-10-23 09:00 | 2020-10-23 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2081 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-10-23 18:00 |  |  | 100 | [122 empty] | 1098657
2846 | Task(Task)-->E (Engineering) | FAB DETAIL OF LT BEND PULLEY GUARD FOR PIPE CONVEYOR PC-1A AT KDTP-2 & PC-2A AT KDTP-3. |  | 1.24.1.5 | FAB DETAIL OF LT BEND PULLEY GUARD FOR PIPE CONVEYOR PC-1A AT KDTP-2 & PC-2A AT KDTP-3.-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-10-23 18:00 | 2020-10-23 18:00 | 2020-10-23 09:00 | 2020-10-23 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2082 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-10-23 18:00 |  |  | 100 | [122 empty] | 1098658
2847 | Task(Task)-->E (Engineering) | FAB DETAIL OF TAIL DRIVE PULLEY GUARD FOR PIPE CONVEYOR PC-1A/1B AT SHB & C-2A/2B AT KDTP-2 |  | 1.24.1.5 | FAB DETAIL OF TAIL DRIVE PULLEY GUARD FOR PIPE CONVEYOR PC-1A/1B AT SHB & C-2A/2B AT KDTP-2-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-10-23 18:00 | 2020-10-23 18:00 | 2020-10-23 09:00 | 2020-10-23 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2083 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-10-23 18:00 |  |  | 100 | [122 empty] | 1098659
2848 | Task(Task)-->E (Engineering) | FAB. DETAIL OF DRIVE PULLEY FRAME GUARD FOR PC-1A -1, PC-1A -2 & PC-1B -1 AT KDTPC-2 AND PC-2A -1, PC-2A -2 & PC-2B -1 AT KDTPC-3 |  | 1.24.1.5 | FAB. DETAIL OF DRIVE PULLEY FRAME GUARD FOR PC-1A -1, PC-1A -2 & PC-1B -1 AT KDTPC-2 AND PC-2A -1, PC-2A -2 & PC-2B -1 AT KDTPC-3-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-10-23 18:00 | 2020-10-23 18:00 | 2020-10-23 09:00 | 2020-10-23 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2084 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-10-23 18:00 |  |  | 100 | [122 empty] | 1098660
2849 | Task(Task)-->E (Engineering) | FAB. DETAIL OF DRIVE PULLEY FRAME GUARD FOR PC-1B -2 AT KDTPC-2 AND PC-2B -2 AT KDTPC-3 |  | 1.24.1.5 | FAB. DETAIL OF DRIVE PULLEY FRAME GUARD FOR PC-1B -2 AT KDTPC-2 AND PC-2B -2 AT KDTPC-3-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-10-23 18:00 | 2020-10-23 18:00 | 2020-10-23 09:00 | 2020-10-23 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2085 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-10-23 18:00 |  |  | 100 | [122 empty] | 1098661
2850 | Task(Task)-->E (Engineering) | FAB. DETAIL OF GUARD AROUND VGTU TOWER FOR SC-1A/1B & SC-2A/2B |  | 1.24.1.5 | FAB. DETAIL OF GUARD AROUND VGTU TOWER FOR SC-1A/1B & SC-2A/2B-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-10-23 18:00 | 2020-10-23 18:00 | 2020-10-23 09:00 | 2020-10-23 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2086 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-10-23 18:00 |  |  | 100 | [122 empty] | 1098662
2851 | Task(Task)-->E (Engineering) | FAB. DETAIL OF GUARD AROUND VGTU TOWER FOR SC-3A/3B & SY-1A/1B |  | 1.24.1.5 | FAB. DETAIL OF GUARD AROUND VGTU TOWER FOR SC-3A/3B & SY-1A/1B-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-10-23 18:00 | 2020-10-23 18:00 | 2020-10-23 09:00 | 2020-10-23 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2087 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-10-23 18:00 |  |  | 100 | [122 empty] | 1098663
2852 | Task(Task)-->E (Engineering) | FAB. DETAIL OF GUARD AROUND HGTU TOWER FOR PIPE CONVEYOR PC-1A/1B & PC-2A/2B |  | 1.24.1.5 | FAB. DETAIL OF GUARD AROUND HGTU TOWER FOR PIPE CONVEYOR PC-1A/1B & PC-2A/2B-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-10-23 18:00 | 2020-10-23 18:00 | 2020-10-23 09:00 | 2020-10-23 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2088 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-10-23 18:00 |  |  | 100 | [122 empty] | 1098664
2853 | Task(Task)-->E (Engineering) | GA AND MOUNTING ARRANGEMENT OF PULL CORD SWITCH, BELT SWAY SWITCH & ZERO SPEED SWITCH FOR TROUGH CONVEYOR |  | 1.24.1.5 | GA AND MOUNTING ARRANGEMENT OF PULL CORD SWITCH, BELT SWAY SWITCH & ZERO SPEED SWITCH FOR TROUGH CONVEYOR-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-10-30 18:00 | 2020-10-30 18:00 | 2020-10-30 09:00 | 2020-10-30 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2090 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-10-30 18:00 |  |  | 100 | [122 empty] | 1098665
2854 | Task(Task)-->E (Engineering) | GA AND MOUNTING ARRANGEMENT OF PULL CORD SWITCH, BELT SWAY SWITCH & ZERO SPEED SWITCH FOR PIPE CONVEYOR |  | 1.24.1.5 | GA AND MOUNTING ARRANGEMENT OF PULL CORD SWITCH, BELT SWAY SWITCH & ZERO SPEED SWITCH FOR PIPE CONVEYOR-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-10-30 18:00 | 2020-10-30 18:00 | 2020-10-30 09:00 | 2020-10-30 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2091 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-10-30 18:00 |  |  | 100 | [122 empty] | 1098666
2855 | Task(Task)-->E (Engineering) | G A OF ZIG AND FIXER ARRANEGEMENT FOR PIPE CONVEYOR |  | 1.24.1.5 | G A OF ZIG AND FIXER ARRANEGEMENT FOR PIPE CONVEYOR-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-10-30 18:00 | 2020-10-30 18:00 | 2020-10-30 09:00 | 2020-10-30 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2093 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-10-30 18:00 |  |  | 100 | [122 empty] | 1098667
2856 | Task(Task)-->E (Engineering) | BELT PULLING ARRANGEMENT FOR PIPE CONVEYOR |  | 1.24.1.5 | BELT PULLING ARRANGEMENT FOR PIPE CONVEYOR-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-10-30 18:00 | 2020-10-30 18:00 | 2020-10-30 09:00 | 2020-10-30 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2094 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-10-30 18:00 |  |  | 100 | [122 empty] | 1098668
2857 | Task(Task)-->E (Engineering) | GA & ARRANGEMENT OF PADDLE SWITCH FOR PIPE CONVEYOR |  | 1.24.1.5 | GA & ARRANGEMENT OF PADDLE SWITCH FOR PIPE CONVEYOR-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-10-30 18:00 | 2020-10-30 18:00 | 2020-10-30 09:00 | 2020-10-30 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2095 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-10-30 18:00 |  |  | 100 | [122 empty] | 1098669
2858 | Task(Task)-->E (Engineering) | MARKING DRAWING FOR CONV. SC 1AB,SC 2AB |  | 1.24.1.5 | MARKING DRAWING FOR CONV. SC 1AB,SC 2AB-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-11-30 18:00 | 2020-11-30 18:00 | 2020-11-30 09:00 | 2020-11-30 18:00 | [6 empty] | 0 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2097 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-11-30 18:00 |  |  | 100 | [122 empty] | 1098670
2859 | Task(Task)-->E (Engineering) | MARKING DRAWING FOR CONV. SC 3AB |  | 1.24.1.5 | MARKING DRAWING FOR CONV. SC 3AB-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-11-30 18:00 | 2020-11-30 18:00 | 2020-11-30 09:00 | 2020-11-30 18:00 | [6 empty] | 0 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2098 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-11-30 18:00 |  |  | 100 | [122 empty] | 1098671
2860 | Task(Task)-->E (Engineering) | MARKING DRAWING FOR CONV. SY 1AB |  | 1.24.1.5 | MARKING DRAWING FOR CONV. SY 1AB-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-11-30 18:00 | 2020-11-30 18:00 | 2020-11-30 09:00 | 2020-11-30 18:00 | [6 empty] | 0 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2099 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-11-30 18:00 |  |  | 100 | [122 empty] | 1098672
2861 | Task(Task)-->E (Engineering) | MARKING DRAWING FOR BELT FEEDER BF-1/2 |  | 1.24.1.5 | MARKING DRAWING FOR BELT FEEDER BF-1/2-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-11-30 18:00 | 2020-11-30 18:00 | 2020-11-30 09:00 | 2020-11-30 18:00 | [6 empty] | 0 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2100 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-11-30 18:00 |  |  | 100 | [122 empty] | 1098673
2862 | Task(Task)-->E (Engineering) | MARKING DRAWING FOR DRIBBLE FEEDER DF-1/2/3/4 |  | 1.24.1.5 | MARKING DRAWING FOR DRIBBLE FEEDER DF-1/2/3/4-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-11-30 18:00 | 2020-11-30 18:00 | 2020-11-30 09:00 | 2020-11-30 18:00 | [6 empty] | 0 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2101 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-11-30 18:00 |  |  | 100 | [122 empty] | 1098674
2863 | Task(Task)-->E (Engineering) | MARKING DRAWING FOR PIPE CONV. PC 1AB |  | 1.24.1.5 | MARKING DRAWING FOR PIPE CONV. PC 1AB-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-11-30 18:00 | 2020-11-30 18:00 | 2020-11-30 09:00 | 2020-11-30 18:00 | [6 empty] | 0 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2102 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-11-30 18:00 |  |  | 100 | [122 empty] | 1098675
2864 | Task(Task)-->E (Engineering) | MARKING DRAWING FOR PIPE CONV. PC 2AB |  | 1.24.1.5 | MARKING DRAWING FOR PIPE CONV. PC 2AB-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-11-30 18:00 | 2020-11-30 18:00 | 2020-11-30 09:00 | 2020-11-30 18:00 | [6 empty] | 0 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2103 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | Internal | [101 empty] | 10 | [6 empty] | 30 | [6 empty] | 50 |  |  |  | 2020-11-30 18:00 |  |  | 100 | [122 empty] | 1098676
2865 | Task(Task)-->E (Engineering) | FABRICATION DETAIL OF DEFLECTOR PLATE |  | 1.24.1.5 | FABRICATION DETAIL OF DEFLECTOR PLATE-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | [10 empty] | 0 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2105 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1098677
2866 | Task(Task)-->E (Engineering) | FAB. DETAIL OF SUPPORTING ARRANGEMENT FOR METAL DETECTOR |  | 1.24.1.5 | FAB. DETAIL OF SUPPORTING ARRANGEMENT FOR METAL DETECTOR-->Fabrication Drawings-->ENGINEERING-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | [10 empty] | 0 | 0 |  |  |  | Documents(Documents)-->I (Internal)-->M (Mechanical) | O19133-M-BM-CS-DD-2106 |  | 2020-07-15 15:21 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1098678
2867 | Task(Task)-->P (Procurement) | PROCUREMENT | 1.24.2 | 1.24 | PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-08-01 18:00 | 2021-03-31 18:00 | 2019-08-01 09:00 | 2021-10-25 18:00 |  |  | 2020-01-13 16:08 |  |  |  | 86.1486 | 30.285 | [15 empty] | 76.8683 | 6.7817 | 666.94 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5128 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020040
2868 | Task(Task)-->P (Procurement) | PURCHASE REQUISITION | 1.24.2.1 | 1.24.2 | PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-08-01 18:00 | 2020-12-30 18:00 | 2019-08-01 09:00 | 2020-12-30 18:00 |  |  | 2020-01-13 16:08 |  |  |  | 100 | 97.602 | [15 empty] | 5.0004 | 0.33912 | 33.35 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5129 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020041
2869 | Task(Task)-->P (Procurement) | Manual Hoist |  | 1.24.2.1 | Manual Hoist-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-14 09:00 | 2020-03-14 18:00 | 2020-04-24 09:00 | 2020-04-24 18:00 |  |  | 2020-04-24 10:57 | 2020-04-24 10:57 |  |  | 100 | 100 | [15 empty] | 0.32974 | 0.001118 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5130 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020042
2870 | Task(Task)-->P (Procurement) | Electric Hoist |  | 1.24.2.1 | Electric Hoist-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-14 09:00 | 2020-03-14 18:00 | 2020-04-24 09:00 | 2020-04-24 18:00 |  |  | 2020-04-24 10:57 | 2020-04-24 10:57 |  |  | 100 | 100 | [15 empty] | 2.9376 | 0.009962 | 0.98 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5131 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020043
2871 | Task(Task)-->P (Procurement) | Belt Vulcanizer |  | 1.24.2.1 | Belt Vulcanizer-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-01 09:00 | 2020-01-01 18:00 | 2020-04-28 09:00 | 2020-04-28 18:00 |  |  | 2020-04-28 10:57 | 2020-04-28 10:57 |  |  | 100 | 100 | [15 empty] | 0.89928 | 0.00305 | 0.3 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5132 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020044
2872 | Task(Task)-->P (Procurement) | HT CABLE (33KV & 6.6KV) |  | 1.24.2.1 | HT CABLE (33KV & 6.6KV)-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-10 09:00 | 2020-01-10 18:00 | 2020-02-12 09:00 | 2020-02-12 18:00 |  |  | 2020-02-12 10:57 | 2020-02-12 10:57 |  |  | 100 | 100 | [15 empty] | 15.5276 | 0.052657 | 5.18 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5133 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020045
2873 | Task(Task)-->P (Procurement) | LT POWER CABLES |  | 1.24.2.1 | LT POWER CABLES-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-30 09:00 | 2020-01-30 18:00 | 2020-03-11 09:00 | 2020-03-11 18:00 |  |  | 2020-03-11 10:57 | 2020-03-11 10:57 |  |  | 100 | 100 | [15 empty] | 20.4736 | 0.06943 | 6.83 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5134 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020046
2874 | Task(Task)-->P (Procurement) | LIGHTING MAST |  | 1.24.2.1 | LIGHTING MAST-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-21 09:00 | 2019-12-21 18:00 | 2020-01-13 09:00 | 2020-01-13 18:00 |  |  | 2020-01-13 16:08 | 2020-01-13 16:08 |  |  | 100 | 100 | [15 empty] | 0.68945 | 0.002338 | 0.23 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5135 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020047
2875 | Task(Task)-->P (Procurement) | CABLE TRAY & ACCESSORIES |  | 1.24.2.1 | CABLE TRAY & ACCESSORIES-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-28 09:00 | 2020-01-28 18:00 | 2020-03-16 09:00 | 2020-03-16 18:00 |  |  | 2020-03-16 16:04 | 2020-03-16 16:04 |  |  | 100 | 100 | [15 empty] | 23.2014 | 0.07868 | 7.74 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5136 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020048
2876 | Task(Task)-->P (Procurement) | FLEXIBLE CABLE TRAY SUPPORTS |  | 1.24.2.1 | FLEXIBLE CABLE TRAY SUPPORTS-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-28 09:00 | 2020-01-28 18:00 | 2020-04-10 09:00 | 2020-04-10 18:00 |  |  | 2020-04-10 10:57 | 2020-04-10 10:57 |  |  | 100 | 100 | [15 empty] | 4.6763 | 0.015858 | 1.56 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5137 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020049
2877 | Task(Task)-->P (Procurement) | EARTHING & LIGHTNING PROTECTION MATERIALS |  | 1.24.2.1 | EARTHING & LIGHTNING PROTECTION MATERIALS-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-19 09:00 | 2020-02-19 18:00 | 2020-04-15 09:00 | 2020-04-15 18:00 |  |  | 2020-04-15 10:57 | 2020-04-15 10:57 |  |  | 100 | 100 | [15 empty] | 7.2842 | 0.024702 | 2.43 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5138 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020050
2878 | Task(Task)-->P (Procurement) | HT CABLE ACCESSORIES |  | 1.24.2.1 | HT CABLE ACCESSORIES-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-24 09:00 | 2020-01-24 18:00 | 2020-02-20 09:00 | 2020-02-20 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.77938 | 0.002643 | 0.26 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5139 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020051
2879 | Task(Task)-->P (Procurement) | LT CABLE ACCESSORIES |  | 1.24.2.1 | LT CABLE ACCESSORIES-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-07 09:00 | 2020-02-07 18:00 | 2020-06-20 09:00 | 2020-06-20 18:00 | [6 empty] | 100 | 0 | [15 empty] | 1.6187 | 0.005489 | 0.54 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5140 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020052
2880 | Task(Task)-->P (Procurement) | FO CABLE |  | 1.24.2.1 | FO CABLE-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-05 09:00 | 2020-02-05 18:00 | 2020-04-15 09:00 | 2020-04-15 18:00 |  |  | 2020-04-15 10:57 | 2020-04-15 10:57 |  |  | 100 | 100 | [15 empty] | 1.4988 | 0.005083 | 0.5 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5141 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020053
2881 | Task(Task)-->P (Procurement) | RECEPTACLES |  | 1.24.2.1 | RECEPTACLES-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-12 09:00 | 2020-02-12 18:00 | 2020-04-10 09:00 | 2020-04-10 18:00 |  |  | 2020-04-10 10:57 | 2020-04-10 10:57 |  |  | 100 | 100 | [15 empty] | 1.3489 | 0.004574 | 0.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5142 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020054
2882 | Task(Task)-->P (Procurement) | CONTROL CABLE |  | 1.24.2.1 | CONTROL CABLE-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-27 09:00 | 2020-01-27 18:00 | 2020-02-21 09:00 | 2020-02-21 18:00 |  |  | 2020-02-21 10:57 | 2020-02-21 10:57 |  |  | 100 | 100 | [15 empty] | 7.7038 | 0.026125 | 2.57 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5143 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020055
2883 | Task(Task)-->P (Procurement) | CCTV SYSTEM |  | 1.24.2.1 | CCTV SYSTEM-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-10 09:00 | 2020-01-10 18:00 | 2020-01-14 09:00 | 2020-01-14 18:00 |  |  | 2020-01-14 10:57 | 2020-01-14 10:57 |  |  | 100 | 100 | [15 empty] | 3.8669 | 0.013113 | 1.29 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5234 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020056
2884 | Task(Task)-->P (Procurement) | PA SYSTEM |  | 1.24.2.1 | PA SYSTEM-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-17 09:00 | 2020-01-17 18:00 | 2020-01-17 09:00 | 2020-01-17 18:00 |  |  | 2020-01-17 10:57 | 2020-01-17 10:57 |  |  | 100 | 100 | [15 empty] | 2.9976 | 0.010165 | 1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5233 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020057
2885 | Task(Task)-->P (Procurement) | INSTRUMENTATION CABLE |  | 1.24.2.1 | INSTRUMENTATION CABLE-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-27 09:00 | 2020-01-27 18:00 | 2020-02-21 09:00 | 2020-02-21 18:00 |  |  | 2020-02-21 10:57 | 2020-02-21 10:57 |  |  | 100 | 100 | [15 empty] | 4.1667 | 0.01413 | 1.39 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5144 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020058
2886 | Task(Task)-->E (Engineering) | PACKAGE PR FOR 33KV OVERHEAD TRANSMISSION LINE(DOUBLE CIRCUIT) WITH 220KV MONOPOLE TOWER. |  | 1.24.2.1 | PACKAGE PR FOR 33KV OVERHEAD TRANSMISSION LINE(DOUBLE CIRCUIT) WITH 220KV MONOPOLE TOWER.-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | [6 empty] | 2020-06-14 22:19 |  |  |  | 0 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-OHTL-001 |  | 2020-06-13 18:12 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1037864
2887 | Task(Task)-->E (Engineering) | 33/6.9kV,HT TRANSFORMER (ONAN TYPE) |  | 1.24.2.1 | 33/6.9kV,HT TRANSFORMER (ONAN TYPE)-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-11-28 18:00 | 2019-11-28 18:00 | 2019-11-28 09:00 | 2019-11-28 18:00 |  |  | 2020-06-14 22:19 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-HTTRAF-002 |  | 2020-06-13 18:12 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2019-11-28 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:08 | [5 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037865
2888 | Task(Task)-->E (Engineering) | HT SWGR. (33kV & 6.6kV) |  | 1.24.2.1 | HT SWGR. (33kV & 6.6kV)-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-11-13 18:00 | 2019-11-13 18:00 | 2019-11-13 09:00 | 2019-11-13 18:00 |  |  | 2020-06-14 22:19 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-HTBD-003 |  | 2020-06-13 18:12 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2019-11-13 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:08 | [5 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037866
2889 | Task(Task)-->E (Engineering) | 6.6kV HT VFD |  | 1.24.2.1 | 6.6kV HT VFD-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-12-30 18:00 | 2019-12-30 18:00 | 2019-12-30 09:00 | 2019-12-30 18:00 |  |  | 2020-06-14 22:19 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-HTVFD-004 |  | 2020-06-13 18:12 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2019-12-30 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:08 | [5 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037867
2890 | Task(Task)-->E (Engineering) | 415V LT VFD |  | 1.24.2.1 | 415V LT VFD-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-12-18 18:00 | 2019-12-18 18:00 | 2019-12-18 09:00 | 2019-12-18 18:00 |  |  | 2020-06-14 22:19 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-LTVFD-005 |  | 2020-06-13 18:12 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2019-12-18 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:08 | [5 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037868
2891 | Task(Task)-->E (Engineering) | 6.6kV HT APFC PANEL |  | 1.24.2.1 | 6.6kV HT APFC PANEL-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-24 18:00 | 2020-01-24 18:00 | 2020-01-24 09:00 | 2020-01-24 18:00 |  |  | 2020-06-14 22:19 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-HTAPFC-006 |  | 2020-06-13 18:12 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-01-24 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:08 | [5 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037869
2892 | Task(Task)-->E (Engineering) | HT AC MOTORS |  | 1.24.2.1 | HT AC MOTORS-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-17 18:00 | 2020-01-17 18:00 | 2020-01-17 09:00 | 2020-01-17 18:00 |  |  | 2020-06-14 22:19 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-HTMOT-007 |  | 2020-06-13 18:12 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-01-17 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:08 | [5 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037870
2893 | Task(Task)-->E (Engineering) | 6.6kV/0.433V,LT TRANSFORMER (ONAN TYPE) |  | 1.24.2.1 | 6.6kV/0.433V,LT TRANSFORMER (ONAN TYPE)-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-11-25 18:00 | 2019-11-25 18:00 | 2019-11-25 09:00 | 2019-11-25 18:00 |  |  | 2020-06-14 22:19 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-LTTRAF-O08 |  | 2020-06-13 18:12 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2019-11-25 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:07 | [5 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037871
2894 | Task(Task)-->E (Engineering) | LT BUSDUCT |  | 1.24.2.1 | LT BUSDUCT-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-12-02 18:00 | 2019-12-02 18:00 | 2019-12-02 09:00 | 2019-12-02 18:00 |  |  | 2020-06-14 22:19 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-LTBDT-009 |  | 2020-06-13 18:12 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2019-12-02 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:07 | [5 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037872
2895 | Task(Task)-->E (Engineering) | 415V PMCC |  | 1.24.2.1 | 415V PMCC-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-11-28 18:00 | 2019-11-28 18:00 | 2019-11-28 09:00 | 2019-11-28 18:00 |  |  | 2020-06-14 22:19 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-LTMCC-010 |  | 2020-06-13 18:12 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2019-11-28 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:07 | [5 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037873
2896 | Task(Task)-->E (Engineering) | LT AC MOTORS |  | 1.24.2.1 | LT AC MOTORS-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-12-16 18:00 | 2019-12-16 18:00 | 2019-12-16 09:00 | 2019-12-16 18:00 |  |  | 2020-06-14 22:19 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-LTMOT-011 |  | 2020-06-13 18:12 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2019-12-16 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:07 | [5 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037874
2897 | Task(Task)-->E (Engineering) | HT CABLE (33 kV & 6.6kV) |  | 1.24.2.1 | HT CABLE (33 kV & 6.6kV)-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-10 18:00 | 2020-01-10 18:00 | 2020-01-10 09:00 | 2020-01-10 18:00 |  |  | 2020-06-14 22:19 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-HTCAB-012 |  | 2020-06-13 18:12 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-01-10 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:10 | [5 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037875
2898 | Task(Task)-->E (Engineering) | LT POWER CABLES |  | 1.24.2.1 | LT POWER CABLES-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-30 18:00 | 2020-01-30 18:00 | 2020-01-30 09:00 | 2020-01-30 18:00 |  |  | 2020-06-14 22:19 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-LT POW. CABLE-013 |  | 2020-06-13 18:12 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-01-30 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:10 | [5 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037876
2899 | Task(Task)-->E (Engineering) | MAIN LIGHTING DISTRIBUTION BOARD |  | 1.24.2.1 | MAIN LIGHTING DISTRIBUTION BOARD-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-25 18:00 | 2020-03-25 18:00 | 2020-03-25 09:00 | 2020-03-25 18:00 |  |  | 2020-06-14 22:19 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-MLDB-014 |  | 2020-06-13 18:12 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-03-25 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:10 | [5 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037877
2900 | Task(Task)-->E (Engineering) | LIGHTING PANELS |  | 1.24.2.1 | LIGHTING PANELS-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-25 18:00 | 2020-03-25 18:00 | 2020-03-25 09:00 | 2020-03-25 18:00 |  |  | 2020-06-19 11:29 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-LP-015 |  | 2020-06-13 18:12 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-03-25 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037878
2901 | Task(Task)-->E (Engineering) | LIGHTING FIXTURES |  | 1.24.2.1 | LIGHTING FIXTURES-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-25 18:00 | 2020-03-25 18:00 | 2020-03-25 09:00 | 2020-03-25 18:00 |  |  | 2020-06-14 22:19 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-LGT FIX.-016 |  | 2020-06-13 18:12 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-03-25 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:05 | [5 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037879
2902 | Task(Task)-->E (Engineering) | LIGHTING MAST |  | 1.24.2.1 | LIGHTING MAST-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-12-21 18:00 | 2019-12-21 18:00 | 2019-12-21 09:00 | 2019-12-21 18:00 |  |  | 2020-06-14 22:19 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-LM-017 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2019-12-21 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:05 | [5 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037880
2903 | Task(Task)-->E (Engineering) | LIGHTING POLES |  | 1.24.2.1 | LIGHTING POLES-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-30 18:00 | 2020-04-30 18:00 | 2020-04-30 09:00 | 2020-04-30 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-LP-018 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-04-30 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037881
2904 | Task(Task)-->E (Engineering) | LIGHTING WIRES |  | 1.24.2.1 | LIGHTING WIRES-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-30 18:00 | 2020-04-30 18:00 | 2020-04-30 09:00 | 2020-04-30 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-LGT. WIRE-019 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-04-30 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037882
2905 | Task(Task)-->E (Engineering) | WELDING DISTRIBUTION BOARD |  | 1.24.2.1 | WELDING DISTRIBUTION BOARD-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-14 18:00 | 2020-02-14 18:00 | 2020-02-14 09:00 | 2020-02-14 18:00 |  |  | 2020-06-14 22:19 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-WDB-020 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-02-14 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:05 | [5 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037883
2906 | Task(Task)-->E (Engineering) | DCDB |  | 1.24.2.1 | DCDB-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-25 18:00 | 2020-03-25 18:00 | 2020-03-25 09:00 | 2020-03-25 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-DCDB-021 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-03-25 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037884
2907 | Task(Task)-->E (Engineering) | AC MCCB BOX |  | 1.24.2.1 | AC MCCB BOX-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-25 18:00 | 2020-03-25 18:00 | 2020-03-25 09:00 | 2020-03-25 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-DB-022 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-03-25 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037885
2908 | Task(Task)-->E (Engineering) | 110 V DC BATTERY & BATTERY CHARGER SYSTEM |  | 1.24.2.1 | 110 V DC BATTERY & BATTERY CHARGER SYSTEM-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-13 18:00 | 2020-01-13 18:00 | 2020-01-13 09:00 | 2020-01-13 18:00 |  |  | 2020-06-14 22:19 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-DC SYS-023 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-01-13 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:05 | [5 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037886
2909 | Task(Task)-->E (Engineering) | LOCAL CONTROL STATIONS |  | 1.24.2.1 | LOCAL CONTROL STATIONS-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-14 18:00 | 2020-04-14 18:00 | 2020-04-14 09:00 | 2020-04-14 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-LCS-024 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-04-14 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037887
2910 | Task(Task)-->E (Engineering) | RECEPTACLES |  | 1.24.2.1 | RECEPTACLES-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-31 18:00 | 2020-03-31 18:00 | 2020-03-31 09:00 | 2020-03-31 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-RECEPTACLES-025 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-03-31 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037888
2911 | Task(Task)-->E (Engineering) | LOCAL STARTER PANEL FOR SUMP PUMP |  | 1.24.2.1 | LOCAL STARTER PANEL FOR SUMP PUMP-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-30 18:00 | 2020-05-30 18:00 | 2020-05-30 09:00 | 2020-05-30 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-LSP SUMPS-026 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-05-30 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037889
2912 | Task(Task)-->E (Engineering) | SIREN |  | 1.24.2.1 | SIREN-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-30 18:00 | 2020-04-30 18:00 | 2020-04-30 09:00 | 2020-04-30 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-SIREN-027 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-04-30 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037890
2913 | Task(Task)-->E (Engineering) | CABLE TRAY & ACCESSORIES |  | 1.24.2.1 | CABLE TRAY & ACCESSORIES-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-28 18:00 | 2020-01-28 18:00 | 2020-01-28 09:00 | 2020-01-28 18:00 |  |  | 2020-06-14 22:19 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-CABLETRAY & ACCS.-028 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-01-28 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:04 | [5 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037891
2914 | Task(Task)-->E (Engineering) | FLEXIBLE CABLE TRAY SUPPORTS |  | 1.24.2.1 | FLEXIBLE CABLE TRAY SUPPORTS-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-31 18:00 | 2020-03-31 18:00 | 2020-03-31 09:00 | 2020-03-31 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-FLEX. CABLE TRAY-029 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-03-31 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037892
2915 | Task(Task)-->E (Engineering) | GI CONDUIT ,PIPE, LIGHTING CONDUIT & ACCESSORIES |  | 1.24.2.1 | GI CONDUIT ,PIPE, LIGHTING CONDUIT & ACCESSORIES-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-30 18:00 | 2020-04-30 18:00 | 2020-04-30 09:00 | 2020-04-30 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-GI/HUME PIPE-030 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-04-30 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037893
2916 | Task(Task)-->E (Engineering) | EARTHING & LIGHTNING PROTECTION MATERIALS |  | 1.24.2.1 | EARTHING & LIGHTNING PROTECTION MATERIALS-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-31 18:00 | 2020-03-31 18:00 | 2020-03-31 09:00 | 2020-03-31 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-EARTHING& LIGHTNING-031 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-03-31 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037894
2917 | Task(Task)-->E (Engineering) | JUNCTION BOXES (POWER) |  | 1.24.2.1 | JUNCTION BOXES (POWER)-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-14 18:00 | 2020-04-14 18:00 | 2020-04-14 09:00 | 2020-04-14 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-JB-032 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-04-14 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037895
2918 | Task(Task)-->E (Engineering) | LOCAL STARTERS FOR AXIAL FAN |  | 1.24.2.1 | LOCAL STARTERS FOR AXIAL FAN-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-30 18:00 | 2020-05-30 18:00 | 2020-05-30 09:00 | 2020-05-30 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-MF1 START-033 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-05-30 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037896
2919 | Task(Task)-->E (Engineering) | STRUCTURAL STEEL FOR ELECTRICAL EQUIPMENT SUPPORT |  | 1.24.2.1 | STRUCTURAL STEEL FOR ELECTRICAL EQUIPMENT SUPPORT-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-30 18:00 | 2020-04-30 18:00 | 2020-04-30 09:00 | 2020-04-30 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-STEEL-034 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-04-30 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037897
2920 | Task(Task)-->E (Engineering) | HT CABLE ACCESSORIES |  | 1.24.2.1 | HT CABLE ACCESSORIES-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-24 18:00 | 2020-01-24 18:00 | 2020-01-24 09:00 | 2020-01-24 18:00 |  |  | 2020-06-14 22:19 |  |  |  | 100 | 60 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-HTCABLE ACCSS.-035 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-01-24 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037898
2921 | Task(Task)-->E (Engineering) | 6.6KV NEUTRAL GROUNDING RESISTOR |  | 1.24.2.1 | 6.6KV NEUTRAL GROUNDING RESISTOR-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-12-12 18:00 | 2019-12-12 18:00 | 2019-12-12 09:00 | 2019-12-12 18:00 |  |  | 2020-06-14 22:19 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-NGR-036 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2019-12-12 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:03 | [5 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037899
2922 | Task(Task)-->E (Engineering) | LT AC MOTORS FOR UTILITY SYSTEM |  | 1.24.2.1 | LT AC MOTORS FOR UTILITY SYSTEM-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-16 18:00 | 2020-01-16 18:00 | 2020-01-16 09:00 | 2020-01-16 18:00 |  |  | 2020-06-14 22:19 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-UTLTMOT-037 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-01-16 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:03 | [5 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037900
2923 | Task(Task)-->E (Engineering) | LT CABLE ACCESSORIES |  | 1.24.2.1 | LT CABLE ACCESSORIES-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-15 18:00 | 2020-05-15 18:00 | 2020-05-15 09:00 | 2020-05-15 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-CABLE ACCSS.-038 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-05-15 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037901
2924 | Task(Task)-->E (Engineering) | FIRE SEALING MATERIALS |  | 1.24.2.1 | FIRE SEALING MATERIALS-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-30 18:00 | 2020-04-30 18:00 | 2020-04-30 09:00 | 2020-04-30 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-FIRESEALING-039 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-04-30 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037902
2925 | Task(Task)-->E (Engineering) | LIGHTING JUNCTION BOXES |  | 1.24.2.1 | LIGHTING JUNCTION BOXES-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-30 18:00 | 2020-04-30 18:00 | 2020-04-30 09:00 | 2020-04-30 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-LJB-040 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-04-30 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037903
2926 | Task(Task)-->E (Engineering) | MISCELLANEOUS ITEMS |  | 1.24.2.1 | MISCELLANEOUS ITEMS-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-30 18:00 | 2020-06-30 18:00 | 2020-06-30 09:00 | 2020-06-30 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-MISC.-041 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-06-30 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037904
2927 | Task(Task)-->E (Engineering) | RUBBER MAT |  | 1.24.2.1 | RUBBER MAT-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-30 18:00 | 2020-04-30 18:00 | 2020-04-30 09:00 | 2020-04-30 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-RUBBER MAT-042 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-04-30 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037905
2928 | Task(Task)-->E (Engineering) | SCADA SYSTEM |  | 1.24.2.1 | SCADA SYSTEM-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-12-10 18:00 | 2019-12-10 18:00 | 2019-12-10 09:00 | 2019-12-10 18:00 |  |  | 2020-06-14 22:19 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-FOCAB-044 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2019-12-10 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:03 | [5 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037906
2929 | Task(Task)-->E (Engineering) | GENERAL CONDITION OF SUPPLY |  | 1.24.2.1 | GENERAL CONDITION OF SUPPLY-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | [6 empty] | 2020-06-14 22:26 |  |  |  | 0 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-GC01 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1037907
2930 | Task(Task)-->E (Engineering) | PRIMARY AND SECONDARY SIZERS |  | 1.24.2.1 | PRIMARY AND SECONDARY SIZERS-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | [6 empty] | 2020-06-14 22:26 | 2020-07-06 12:17 |  |  | 0 | 100 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-SZ01-08 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | [235 empty] | EK210PO0000012 | [10 empty] | 1037908
2931 | Task(Task)-->E (Engineering) | SECONDARY SIZER WITH MANDATORY SARES AND SLIDER BED |  | 1.24.2.1 | SECONDARY SIZER WITH MANDATORY SARES AND SLIDER BED-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | [10 empty] | 0 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-SS01-04 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | [235 empty] | EK210PO0000012 | [10 empty] | 1037909
2932 | Task(Task)-->E (Engineering) | APRON FEEDER WITH MANDATORY SPARES |  | 1.24.2.1 | APRON FEEDER WITH MANDATORY SPARES-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | [6 empty] | 2020-06-14 22:26 |  |  |  | 0 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-AF01-04 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1037910
2933 | Task(Task)-->E (Engineering) | IDLERS WITH SPARES FOR TROUGH BELT CONVEYOR |  | 1.24.2.1 | IDLERS WITH SPARES FOR TROUGH BELT CONVEYOR-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-19 18:00 | 2019-12-19 18:00 | 2019-12-19 09:00 | 2019-12-19 18:00 |  |  | 2020-06-14 22:26 | 2020-07-06 12:17 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-ID01 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2019-12-19 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-07-06 12:13 | [5 empty] | 90 | [6 empty] | 100 | 2020-07-06 12:18 | [19 empty] | EK210PO0000040 | [10 empty] | 1037911
2934 | Task(Task)-->E (Engineering) | BELTING FOR TROUGH BELT CONVEYORS/FEEDER WITH MANDATORY SPARES |  | 1.24.2.1 | BELTING FOR TROUGH BELT CONVEYORS/FEEDER WITH MANDATORY SPARES-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-11-07 18:00 | 2019-11-07 18:00 | 2019-11-07 09:00 | 2019-11-07 18:00 |  |  | 2020-06-14 22:26 |  |  |  | 100 | 60 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-BL01 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2019-11-07 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037912
2935 | Task(Task)-->E (Engineering) | PULLEYS WITH SPARES FOR TROUGH BELT CONVEYORS |  | 1.24.2.1 | PULLEYS WITH SPARES FOR TROUGH BELT CONVEYORS-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-15 18:00 | 2020-05-15 18:00 | 2020-05-15 09:00 | 2020-05-15 18:00 |  |  | 2020-06-14 22:26 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-P001 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-05-15 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:36 | [5 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037913
2936 | Task(Task)-->E (Engineering) | PLUMMER BLOCKS WITH SPARES FOR TROUGH BELT CONVEYORS |  | 1.24.2.1 | PLUMMER BLOCKS WITH SPARES FOR TROUGH BELT CONVEYORS-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-18 | 2020-05-18 | 2020-05-17 | 2020-05-17 23:59 |  |  | 2020-06-14 22:26 | 2020-07-06 12:17 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-PL01 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-05-18 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-07-06 12:13 | [5 empty] | 90 | [6 empty] | 100 | 2020-07-06 12:18 | [19 empty] | EK210PO0000018 | [10 empty] | 1037914
2937 | Task(Task)-->E (Engineering) | BEARING WITH SAPRES FOR TROUGH BELT CONVEYOR PULLEYS |  | 1.24.2.1 | BEARING WITH SAPRES FOR TROUGH BELT CONVEYOR PULLEYS-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2020-05-18 | 2020-05-18 | 2020-05-17 | 2020-05-17 23:59 |  |  | 2020-06-14 22:26 | 2020-07-06 12:17 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-B001 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-05-18 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-07-06 12:13 | [5 empty] | 90 | [6 empty] | 100 | 2020-07-06 12:18 | [19 empty] | EK210PO0000016 | [10 empty] | 1037915
2938 | Task(Task)-->E (Engineering) | FLUID COUPLINGS FOR TROUGH CONVEYORS WITH MANDATORY SPARES |  | 1.24.2.1 | FLUID COUPLINGS FOR TROUGH CONVEYORS WITH MANDATORY SPARES-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-25 18:00 | 2019-11-25 18:00 | 2019-11-25 09:00 | 2019-11-25 18:00 |  |  | 2020-06-14 22:26 | 2020-07-06 12:17 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-FC01 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2019-11-25 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-07-06 12:13 | [5 empty] | 90 | [6 empty] | 100 | 2020-07-06 12:18 | [19 empty] | EK210PO0000051 | [10 empty] | 1037916
2939 | Task(Task)-->E (Engineering) | GEARED COUPLING WITH SPARES FOR TROUGH BELT CONVEYORS |  | 1.24.2.1 | GEARED COUPLING WITH SPARES FOR TROUGH BELT CONVEYORS-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-21 18:00 | 2019-11-21 18:00 | 2019-11-21 09:00 | 2019-11-21 18:00 |  |  | 2020-06-14 22:26 | 2020-07-06 12:17 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-GR01 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2019-11-21 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-07-06 12:13 | [5 empty] | 90 | [6 empty] | 100 | 2020-07-06 12:18 | [19 empty] | EK210PO0000022 | [10 empty] | 1037917
2940 | Task(Task)-->E (Engineering) | GEAR BOXES FOR TROUGH CONVEYORS & EQUIPMENT WITH MANDATORY SPARES |  | 1.24.2.1 | GEAR BOXES FOR TROUGH CONVEYORS & EQUIPMENT WITH MANDATORY SPARES-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2019-11-13 18:00 | 2019-11-13 18:00 | 2019-11-13 09:00 | 2019-11-13 18:00 |  |  | 2020-06-14 22:26 | 2020-07-06 12:17 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-GB01-06 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2019-11-13 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-07-06 12:13 | [5 empty] | 90 | [6 empty] | 100 | 2020-07-06 12:18 | [19 empty] | EK210PO0000041 | [10 empty] | 1037918
2941 | Task(Task)-->E (Engineering) | THRUSTOR BRAKE WITH SPARES FOR TROUGH BELT CONVEYOR |  | 1.24.2.1 | THRUSTOR BRAKE WITH SPARES FOR TROUGH BELT CONVEYOR-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-12-18 18:00 | 2019-12-18 18:00 | 2019-12-18 09:00 | 2019-12-18 18:00 |  |  | 2020-06-14 22:26 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-BR01 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2019-12-18 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:36 | [5 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037919
2942 | Task(Task)-->E (Engineering) | INLINE MAGNETIC SEPARATOR AND SUSPENDED MAGNET WITH MANDATORY SPARES |  | 1.24.2.1 | INLINE MAGNETIC SEPARATOR AND SUSPENDED MAGNET WITH MANDATORY SPARES-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | [6 empty] | 2020-06-14 22:26 |  |  |  | 0 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-MS01-08 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | [235 empty] | EK210PO0000010 | [10 empty] | 1037920
2943 | Task(Task)-->E (Engineering) | BELT WEIGH SCALE WITH MANDATORY SPARES FOR TROUGH BELT CONVEYORS |  | 1.24.2.1 | BELT WEIGH SCALE WITH MANDATORY SPARES FOR TROUGH BELT CONVEYORS-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2019-08-12 | 2019-08-12 | 2019-08-11 | 2019-08-11 23:59 |  |  | 2020-06-14 22:26 | 2020-07-06 12:17 |  |  | 100 | 100 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-BS01-04 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2019-08-12 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-07-06 12:13 | [5 empty] | 90 | [6 empty] | 100 | 2020-07-06 12:18 | [19 empty] | EK210PO0000014 | [10 empty] | 1037921
2944 | Task(Task)-->E (Engineering) | FLAP GATE |  | 1.24.2.1 | FLAP GATE-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-06 18:00 | 2020-02-06 18:00 | 2020-02-06 09:00 | 2020-02-06 18:00 |  |  | 2020-06-14 22:26 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-FG01-10 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-02-06 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:21 | [5 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037922
2945 | Task(Task)-->E (Engineering) | ROD GATE |  | 1.24.2.1 | ROD GATE-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-09-25 18:00 | 2019-09-25 18:00 | 2019-09-25 09:00 | 2019-09-25 18:00 |  |  | 2020-06-14 22:26 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-RG01-02 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2019-09-25 18:00 |  |  | 60 | 2020-06-14 22:53 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:21 | [5 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037923
2946 | Task(Task)-->E (Engineering) | RACK AND PINION GATE WITH MANDATORY SPARES |  | 1.24.2.1 | RACK AND PINION GATE WITH MANDATORY SPARES-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-09-25 18:00 | 2019-09-25 18:00 | 2019-09-25 09:00 | 2019-09-25 18:00 |  |  | 2020-06-14 22:26 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-RPG01-02 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2019-09-25 18:00 |  |  | 60 | 2020-06-14 22:54 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:21 | [5 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037924
2947 | Task(Task)-->E (Engineering) | METAL DETECTOR WITH MANDATORY SPARES |  | 1.24.2.1 | METAL DETECTOR WITH MANDATORY SPARES-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | [6 empty] | 2020-06-14 22:26 | 2020-07-06 12:17 |  |  | 0 | 100 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-MD01-06 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | [235 empty] | EK210PO0000026 | [10 empty] | 1037925
2948 | Task(Task)-->E (Engineering) | ELECTRIC HOIST |  | 1.24.2.1 | ELECTRIC HOIST-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-15 18:00 | 2020-06-15 18:00 | 2020-06-15 09:00 | 2020-06-15 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-EH01 |  | 2020-06-13 18:13 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-06-15 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037926
2949 | Task(Task)-->E (Engineering) | MANUAL HOIST / CHAIN PULLEY BLOCK |  | 1.24.2.1 | MANUAL HOIST / CHAIN PULLEY BLOCK-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-22 18:00 | 2020-06-22 18:00 | 2020-06-22 09:00 | 2020-06-22 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-MH01 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-06-22 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037927
2950 | Task(Task)-->E (Engineering) | EXTERNAL & INTERNAL SCRAPERS FOR CONVEYORS AND EQUIPMENTS WITH MANDATORY SPARES |  | 1.24.2.1 | EXTERNAL & INTERNAL SCRAPERS FOR CONVEYORS AND EQUIPMENTS WITH MANDATORY SPARES-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-11-18 | 2019-11-18 | 2019-11-17 | 2019-11-17 23:59 |  |  | 2020-06-14 22:26 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-SC01 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2019-11-18 |  |  | 60 | 2020-06-14 22:54 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:21 | [5 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037928
2951 | Task(Task)-->E (Engineering) | FOUNDATION BOLTS WITH NUTS AND WASHERS |  | 1.24.2.1 | FOUNDATION BOLTS WITH NUTS AND WASHERS-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-15 18:00 | 2020-05-15 18:00 | 2020-05-15 09:00 | 2020-05-15 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-FB01 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-05-15 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037929
2952 | Task(Task)-->E (Engineering) | TROLLEY FOR HGTU FOR PIPE CONVEYOR |  | 1.24.2.1 | TROLLEY FOR HGTU FOR PIPE CONVEYOR-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-22 18:00 | 2020-05-22 18:00 | 2020-05-22 09:00 | 2020-05-22 18:00 |  |  | 2020-07-18 23:01 |  |  |  | 100 | 60 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-TH01 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-05-22 18:00 |  |  | 60 | 2020-07-18 23:02 | [5 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037930
2953 | Task(Task)-->E (Engineering) | SCREW TAKEUP |  | 1.24.2.1 | SCREW TAKEUP-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-21 18:00 | 2020-05-21 18:00 | 2020-05-21 09:00 | 2020-05-21 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-ST01 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-05-21 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037931
2954 | Task(Task)-->E (Engineering) | ROPE SHEAVE |  | 1.24.2.1 | ROPE SHEAVE-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-19 18:00 | 2020-05-19 18:00 | 2020-05-19 09:00 | 2020-05-19 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-RS01 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-05-19 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037932
2955 | Task(Task)-->E (Engineering) | TAKE UP COMPONENTS FOR TROUGH BELT CONVEYORS |  | 1.24.2.1 | TAKE UP COMPONENTS FOR TROUGH BELT CONVEYORS-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-19 18:00 | 2020-05-19 18:00 | 2020-05-19 09:00 | 2020-05-19 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-TU02 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-05-19 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037933
2956 | Task(Task)-->E (Engineering) | TIE ROD WITH FASTENERS FOR TROUGH BELT CONVEYORS |  | 1.24.2.1 | TIE ROD WITH FASTENERS FOR TROUGH BELT CONVEYORS-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-19 18:00 | 2020-05-19 18:00 | 2020-05-19 09:00 | 2020-05-19 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-TU03 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-05-19 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037934
2957 | Task(Task)-->E (Engineering) | PRECAST CONCRETE COUNTER WEIGHT BLOCKS FOR TROUGH BELT CONVEYORS |  | 1.24.2.1 | PRECAST CONCRETE COUNTER WEIGHT BLOCKS FOR TROUGH BELT CONVEYORS-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-18 18:00 | 2020-05-18 18:00 | 2020-05-18 09:00 | 2020-05-18 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-CW01 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-05-18 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037935
2958 | Task(Task)-->E (Engineering) | CONV. TECH. STRUCTURE, CHUTES AND SKIRTS FOR TROUGH BELT CONVEYORS |  | 1.24.2.1 | CONV. TECH. STRUCTURE, CHUTES AND SKIRTS FOR TROUGH BELT CONVEYORS-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-11 18:00 | 2020-05-11 18:00 | 2020-05-11 09:00 | 2020-05-11 18:00 |  |  | 2020-06-14 22:26 |  |  |  | 100 | 60 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-TS01 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-05-11 18:00 |  |  | 60 | 2020-06-14 22:54 | [5 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037936
2959 | Task(Task)-->E (Engineering) | SKIRT BOARD SEALING WITH MANDATORY SPARES |  | 1.24.2.1 | SKIRT BOARD SEALING WITH MANDATORY SPARES-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-14 18:00 | 2020-05-14 18:00 | 2020-05-14 09:00 | 2020-05-14 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-SB01 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-05-14 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037937
2960 | Task(Task)-->E (Engineering) | LUBRICANTS |  | 1.24.2.1 | LUBRICANTS-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-14 18:00 | 2020-08-14 18:00 | 2020-08-14 09:00 | 2020-08-14 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-LU01 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-08-14 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037938
2961 | Task(Task)-->E (Engineering) | BELT VULCANISER |  | 1.24.2.1 | BELT VULCANISER-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-28 18:00 | 2020-02-28 18:00 | 2020-02-28 09:00 | 2020-02-28 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-BV01 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-02-28 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037939
2962 | Task(Task)-->E (Engineering) | TYRE COUPLING WITH MANDATORY SPARES FOR APRON FEEDERS |  | 1.24.2.1 | TYRE COUPLING WITH MANDATORY SPARES FOR APRON FEEDERS-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-05 18:00 | 2020-03-05 18:00 | 2020-03-05 09:00 | 2020-03-05 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-TC01 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-03-05 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [20 empty] | EK210PO0000024 | [10 empty] | 1037940
2963 | Task(Task)-->E (Engineering) | PRECAST CONCRETE COUNTER WEIGHT BLOCKS FOR PIPE CONVEYORS |  | 1.24.2.1 | PRECAST CONCRETE COUNTER WEIGHT BLOCKS FOR PIPE CONVEYORS-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-18 18:00 | 2020-05-18 18:00 | 2020-05-18 09:00 | 2020-05-18 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-PCW01 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-05-18 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037941
2964 | Task(Task)-->E (Engineering) | CONV. TECH. STRUCTURE, CHUTES AND SKIRTS FOR PIPE CONVEYORS |  | 1.24.2.1 | CONV. TECH. STRUCTURE, CHUTES AND SKIRTS FOR PIPE CONVEYORS-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-11 18:00 | 2020-05-11 18:00 | 2020-05-11 09:00 | 2020-05-11 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-PTS01 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-05-11 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037942
2965 | Task(Task)-->E (Engineering) | SKIRT BOARD SEALING FOR PIPE CONVEYORS |  | 1.24.2.1 | SKIRT BOARD SEALING FOR PIPE CONVEYORS-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-14 18:00 | 2020-05-14 18:00 | 2020-05-14 09:00 | 2020-05-14 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-PSB01 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-05-14 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037943
2966 | Task(Task)-->E (Engineering) | IDLERS WITH SPARES FOR PIPE CONVEYOR |  | 1.24.2.1 | IDLERS WITH SPARES FOR PIPE CONVEYOR-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-27 18:00 | 2020-02-27 18:00 | 2020-02-27 09:00 | 2020-02-27 18:00 |  |  | 2020-06-14 22:26 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-PID01 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-02-27 18:00 |  |  | 60 | 2020-06-14 22:54 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:20 | [5 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037944
2967 | Task(Task)-->E (Engineering) | BELTING WITH SPARES FOR PIPE CONVEYOR |  | 1.24.2.1 | BELTING WITH SPARES FOR PIPE CONVEYOR-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-15 18:00 | 2020-02-15 18:00 | 2020-02-15 09:00 | 2020-02-15 18:00 |  |  | 2020-06-14 22:26 |  |  |  | 100 | 60 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-PBL01 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-02-15 18:00 |  |  | 60 | 2020-06-14 22:54 | [5 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037945
2968 | Task(Task)-->E (Engineering) | PULLEYS WITH SPARES FOR PIPE CONVEYORS |  | 1.24.2.1 | PULLEYS WITH SPARES FOR PIPE CONVEYORS-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-15 18:00 | 2020-05-15 18:00 | 2020-05-15 09:00 | 2020-05-15 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-PP001 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-05-15 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037946
2969 | Task(Task)-->E (Engineering) | PLUMMER BLOCKS WITH SPARES FOR PIPE CONVEYORS |  | 1.24.2.1 | PLUMMER BLOCKS WITH SPARES FOR PIPE CONVEYORS-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-18 | 2020-05-18 | 2020-05-17 | 2020-05-17 23:59 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-PPL01 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-05-18 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037947
2970 | Task(Task)-->E (Engineering) | BEARING WITH SAPRES FOR PIPE CONVEYOR PULLEYS |  | 1.24.2.1 | BEARING WITH SAPRES FOR PIPE CONVEYOR PULLEYS-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-18 | 2020-05-18 | 2020-05-17 | 2020-05-17 23:59 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-PB001 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-05-18 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037948
2971 | Task(Task)-->E (Engineering) | GEARED COUPLING WITH SPARES FOR PIPE CONVEYORS |  | 1.24.2.1 | GEARED COUPLING WITH SPARES FOR PIPE CONVEYORS-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-29 18:00 | 2020-02-29 18:00 | 2020-02-29 09:00 | 2020-02-29 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-PGR01 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-02-29 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037949
2972 | Task(Task)-->E (Engineering) | GEARBOX WITH SPARES FOR PIPE CONVEYORS |  | 1.24.2.1 | GEARBOX WITH SPARES FOR PIPE CONVEYORS-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-21 18:00 | 2020-02-21 18:00 | 2020-02-21 09:00 | 2020-02-21 18:00 |  |  | 2020-06-14 22:26 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-PGB01 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-02-21 18:00 |  |  | 60 | 2020-06-14 22:54 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:21 | [5 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037950
2973 | Task(Task)-->E (Engineering) | DISC BRAKE WITH SPARES FOR PIPE CONVEYOR |  | 1.24.2.1 | DISC BRAKE WITH SPARES FOR PIPE CONVEYOR-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-21 18:00 | 2020-03-21 18:00 | 2020-03-21 09:00 | 2020-03-21 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-PBR01 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-03-21 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037951
2974 | Task(Task)-->E (Engineering) | TAKE-UP WINCH WITH CAPSTON BRAKE FOR PIPE CONVEYORS |  | 1.24.2.1 | TAKE-UP WINCH WITH CAPSTON BRAKE FOR PIPE CONVEYORS-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-19 18:00 | 2020-05-19 18:00 | 2020-05-19 09:00 | 2020-05-19 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-PTW01 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-05-19 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037952
2975 | Task(Task)-->E (Engineering) | WINCH WITH BRAKE FOR PIPE CONVEYORS |  | 1.24.2.1 | WINCH WITH BRAKE FOR PIPE CONVEYORS-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-19 18:00 | 2020-05-19 18:00 | 2020-05-19 09:00 | 2020-05-19 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-PW01 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-05-19 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037953
2976 | Task(Task)-->E (Engineering) | ROPE SHEAVE FOR PIPE CONVEYORS |  | 1.24.2.1 | ROPE SHEAVE FOR PIPE CONVEYORS-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-19 18:00 | 2020-05-19 18:00 | 2020-05-19 09:00 | 2020-05-19 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-PTU01 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-05-19 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037954
2977 | Task(Task)-->E (Engineering) | TAKE UP COMPONENTS FOR PIPE CONVEYORS |  | 1.24.2.1 | TAKE UP COMPONENTS FOR PIPE CONVEYORS-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-19 18:00 | 2020-05-19 18:00 | 2020-05-19 09:00 | 2020-05-19 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-PTU02 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-05-19 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037955
2978 | Task(Task)-->E (Engineering) | TIE ROD WITH FASTENERS FOR PIPE CONVEYORS |  | 1.24.2.1 | TIE ROD WITH FASTENERS FOR PIPE CONVEYORS-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-19 18:00 | 2020-05-19 18:00 | 2020-05-19 09:00 | 2020-05-19 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-PTU03 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-05-19 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037956
2979 | Task(Task)-->E (Engineering) | CONVEYOR HOOD FOR TROUGH CONVEYORS |  | 1.24.2.1 | CONVEYOR HOOD FOR TROUGH CONVEYORS-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-19 18:00 | 2020-05-19 18:00 | 2020-05-19 09:00 | 2020-05-19 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-HD01-02 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-05-19 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037957
2980 | Task(Task)-->E (Engineering) | PR FOR DS, SW & PW SYSTEM AND SPARES |  | 1.24.2.1 | PR FOR DS, SW & PW SYSTEM AND SPARES-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-08-01 18:00 | 2019-08-01 18:00 | 2019-08-01 09:00 | 2019-08-01 18:00 |  |  | 2020-06-14 22:49 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->5(Equipment Design) | O19133-M-BM-CS-SP-DS01 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2019-08-01 18:00 |  |  | 60 | 2020-06-14 22:54 | [5 empty] | 70 | [6 empty] | 80 | 2020-06-16 16:44 | [5 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037958
2981 | Task(Task)-->E (Engineering) | PR FOR VENTILATION SYSTEM AND SPARES |  | 1.24.2.1 | PR FOR VENTILATION SYSTEM AND SPARES-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-08-01 18:00 | 2019-08-01 18:00 | 2019-08-01 09:00 | 2019-08-01 18:00 |  |  | 2020-06-14 22:49 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->5(Equipment Design) | O19133-M-BM-CS-SP-VS-01 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2019-08-01 18:00 |  |  | 60 | 2020-06-14 22:54 | [5 empty] | 70 | [6 empty] | 80 | 2020-06-16 16:44 | [5 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037959
2982 | Task(Task)-->E (Engineering) | PR FOR AIR CONDITIONING SYSTEM & SPARES |  | 1.24.2.1 | PR FOR AIR CONDITIONING SYSTEM & SPARES-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-08-03 18:00 | 2019-08-03 18:00 | 2019-08-03 09:00 | 2019-08-03 18:00 |  |  | 2020-06-14 22:49 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->5(Equipment Design) | O19133-M-BM-CS-SP-AC-01 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2019-08-03 18:00 |  |  | 60 | 2020-06-14 22:54 | [5 empty] | 70 | [6 empty] | 80 | 2020-06-16 16:44 | [5 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037960
2983 | Task(Task)-->E (Engineering) | PR FOR FIRE FIGHTING SYSTEM AND SPARES |  | 1.24.2.1 | PR FOR FIRE FIGHTING SYSTEM AND SPARES-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-08-13 18:00 | 2019-08-13 18:00 | 2019-08-13 09:00 | 2019-08-13 18:00 |  |  | 2020-06-14 22:49 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->5(Equipment Design) | O19133-M-BM-CS-SP-FF-01 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2019-08-13 18:00 |  |  | 60 | 2020-06-14 22:54 | [5 empty] | 70 | [6 empty] | 80 | 2020-06-16 16:44 | [5 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037961
2984 | Task(Task)-->E (Engineering) | PR FOR BOREWELL SYSTEM |  | 1.24.2.1 | PR FOR BOREWELL SYSTEM-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-08-26 18:00 | 2019-08-26 18:00 | 2019-08-26 09:00 | 2019-08-26 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->5(Equipment Design) | O19133-M-BM-CS-SP-BB-01 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2019-08-26 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037962
2985 | Task(Task)-->E (Engineering) | PLC System |  | 1.24.2.1 | PLC System-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2019-11-12 18:00 | 2019-11-12 18:00 | 2019-11-12 09:00 | 2019-11-12 18:00 |  |  | 2020-06-14 22:45 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->4(Instrumentation & Control) | O19133-C&I-BM-CS-0001 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2019-11-12 18:00 |  |  | 60 | 2020-06-14 22:54 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:03 | [5 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037963
2986 | Task(Task)-->E (Engineering) | UPS System |  | 1.24.2.1 | UPS System-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-08 18:00 | 2020-01-08 18:00 | 2020-01-08 09:00 | 2020-01-08 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->4(Instrumentation & Control) | O19133-C&I-BM-CS-0002 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-01-08 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037964
2987 | Task(Task)-->E (Engineering) | 24V DC Battery and Battery Charger System |  | 1.24.2.1 | 24V DC Battery and Battery Charger System-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-27 18:00 | 2020-01-27 18:00 | 2020-01-27 09:00 | 2020-01-27 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->4(Instrumentation & Control) | O19133-C&I-BM-CS-0003 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-01-27 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037965
2988 | Task(Task)-->E (Engineering) | CCTV System (IP based) |  | 1.24.2.1 | CCTV System (IP based)-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-10 18:00 | 2020-01-10 18:00 | 2020-01-10 09:00 | 2020-01-10 18:00 |  |  | 2020-06-14 22:45 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->4(Instrumentation & Control) | O19133-C&I-BM-CS-0004 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-01-10 18:00 |  |  | 60 | 2020-06-14 22:54 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:02 | [5 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037966
2989 | Task(Task)-->E (Engineering) | PA System (IP based) |  | 1.24.2.1 | PA System (IP based)-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-17 18:00 | 2020-01-17 18:00 | 2020-01-17 09:00 | 2020-01-17 18:00 |  |  | 2020-06-14 22:45 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->4(Instrumentation & Control) | O19133-C&I-BM-CS-0005 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-01-17 18:00 |  |  | 60 | 2020-06-14 22:54 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:01 | [5 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037967
2990 | Task(Task)-->E (Engineering) | Control and Instrumentation Cable |  | 1.24.2.1 | Control and Instrumentation Cable-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-21 18:00 | 2020-01-21 18:00 | 2020-01-21 09:00 | 2020-01-21 18:00 |  |  | 2020-06-19 12:32 |  |  |  | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->4(Instrumentation & Control) | O19133-C&I-BM-CS-0006 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-01-21 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037968
2991 | Task(Task)-->E (Engineering) | Addressable Conveyor Belt Protection Switches (PCS, BSS, Pull Cord Wire & I - Hooks & Pull cord indication system) |  | 1.24.2.1 | Addressable Conveyor Belt Protection Switches (PCS, BSS, Pull Cord Wire & I - Hooks & Pull cord indication system)-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-08 18:00 | 2020-01-08 18:00 | 2020-01-08 09:00 | 2020-01-08 18:00 |  |  | 2020-06-14 22:45 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->4(Instrumentation & Control) | O19133-C&I-BM-CS-0007 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-01-08 18:00 |  |  | 60 | 2020-06-14 22:54 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:01 | [5 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037969
2992 | Task(Task)-->E (Engineering) | Zero Speed Switch |  | 1.24.2.1 | Zero Speed Switch-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-12-30 18:00 | 2020-12-30 18:00 | 2020-12-30 09:00 | 2020-12-30 18:00 |  |  | 2020-06-14 22:45 |  |  |  | 0 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->4(Instrumentation & Control) | O19133-C&I-BM-CS-0008 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-12-30 18:00 |  |  | 60 | 2020-06-14 22:54 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:01 | [5 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037970
2993 | Task(Task)-->E (Engineering) | Chute Block Switch |  | 1.24.2.1 | Chute Block Switch-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-02 18:00 | 2020-01-02 18:00 | 2020-01-02 09:00 | 2020-01-02 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->4(Instrumentation & Control) | O19133-C&I-BM-CS-0009 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-01-02 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037971
2994 | Task(Task)-->E (Engineering) | Control Junction Box |  | 1.24.2.1 | Control Junction Box-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-03 18:00 | 2020-03-03 18:00 | 2020-03-03 09:00 | 2020-03-03 18:00 |  |  | 2020-06-14 22:45 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->4(Instrumentation & Control) | O19133-C&I-BM-CS-0010 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-03-03 18:00 |  |  | 60 | 2020-06-14 22:54 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:01 | [5 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037972
2995 | Task(Task)-->E (Engineering) | UPS / 24V DC DB |  | 1.24.2.1 | UPS / 24V DC DB-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-19 18:00 | 2020-02-19 18:00 | 2020-02-19 09:00 | 2020-02-19 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->4(Instrumentation & Control) | O19133-C&I-BM-CS-0011 |  | 2020-06-13 18:14 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-02-19 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037973
2996 | Task(Task)-->E (Engineering) | Singlechannel Temperature Transmitter |  | 1.24.2.1 | Singlechannel Temperature Transmitter-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-12 18:00 | 2020-02-12 18:00 | 2020-02-12 09:00 | 2020-02-12 18:00 | [6 empty] | 100 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->4(Instrumentation & Control) | O19133-C&I-BM-CS-0012 |  | 2020-06-13 18:15 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-02-12 18:00 |  |  | 60 | [6 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037974
2997 | Task(Task)-->E (Engineering) | Communication Cable (FO) |  | 1.24.2.1 | Communication Cable (FO)-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-05 18:00 | 2020-02-05 18:00 | 2020-02-05 09:00 | 2020-02-05 18:00 |  |  | 2020-06-14 22:45 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->4(Instrumentation & Control) | O19133-C&I-BM-CS-0013 |  | 2020-06-13 18:15 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-02-05 18:00 |  |  | 60 | 2020-06-14 22:54 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:00 | [5 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037975
2998 | Task(Task)-->E (Engineering) | FDA System |  | 1.24.2.1 | FDA System-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-14 18:00 | 2020-02-14 18:00 | 2020-02-14 09:00 | 2020-02-14 18:00 |  |  | 2020-06-14 22:45 |  |  |  | 100 | 80 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->4(Instrumentation & Control) | O19133-C&I-BM-CS-0014 |  | 2020-06-13 18:15 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-02-14 18:00 |  |  | 60 | 2020-06-14 22:54 | [5 empty] | 70 | [6 empty] | 80 | 2020-08-24 11:00 | [5 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037976
2999 | Task(Task)-->E (Engineering) | Limit Switch |  | 1.24.2.1 | Limit Switch-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-14 18:00 | 2020-02-14 18:00 | 2020-02-14 09:00 | 2020-02-14 18:00 |  |  | 2020-06-14 22:45 |  |  |  | 100 | 60 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->4(Instrumentation & Control) | OXXXXX-C&I-BM-CS-XXXX |  | 2020-06-13 18:15 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-02-14 18:00 |  |  | 60 | 2020-06-14 22:54 | [5 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [31 empty] | 1037977
3000 | Task(Task)-->E (Engineering) | CABLE LUGS AND GLANDS |  | 1.24.2.1 | CABLE LUGS AND GLANDS-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | [6 empty] | 2020-06-30 16:32 |  |  |  | 0 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-LG-045 | [10 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1044541
3001 | Task(Task)-->E (Engineering) | RELAY TESTING KIT |  | 1.24.2.1 | RELAY TESTING KIT-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | [6 empty] | 2020-06-30 16:45 |  |  |  | 0 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) | O19133-E-BM-CS-SP-RLYKIT-043 | [10 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1044542
3002 | Task(Task)-->E (Engineering) | Maintenance Trolley |  | 1.24.2.1 | Maintenance Trolley-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-20 | 2020-07-20 | 2020-07-19 | 2020-07-19 23:59 |  |  | 2020-07-19 16:04 |  |  |  | 100 | 60 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) | O19133-M-BM-CS-SP-MT02 |  | 2020-07-19 16:03 | [8 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | PR STANDARD | [171 empty] | 10 | [6 empty] | 35 |  |  |  | 2020-07-20 |  |  | 60 | 2020-07-19 16:11 | [5 empty] | 70 | [6 empty] | 80 | [6 empty] | 90 | [6 empty] | 100 | [9 empty] | H - Material Handling and Equipment | [21 empty] | 1098720
3003 | Task(Task)-->P (Procurement) | PR DEMO DOCUMENT |  | 1.24.2.1 | PR DEMO DOCUMENT-->PURCHASE REQUISITION-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | [6 empty] | 2020-07-21 12:14 |  |  |  | 0 | 0 |  |  |  | Documents(Documents)-->PR (Purchase Requests)-->1(Civil & Structural) | DEMO-001 | [10 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1098760
3004 | Task(Task)-->P (Procurement) | TECHNICAL CLEARANCE | 1.24.2.2 | 1.24.2 | TECHNICAL CLEARANCE-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2019-12-22 | 2020-05-13 18:00 | 2020-01-13 09:00 | 2020-11-10 18:00 |  |  | 2020-01-15 16:14 |  |  |  | 100 | 96.7026 | [15 empty] | 5.0004 | 0.33912 | 33.35 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5145 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020059
3005 | Task(Task)-->P (Procurement) | Manual Hoist |  | 1.24.2.2 | Manual Hoist-->TECHNICAL CLEARANCE-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-15 | 2020-03-30 18:00 | 2020-04-24 09:00 | 2020-06-10 18:00 |  |  | 2020-06-10 10:57 | 2020-06-10 10:57 |  |  | 100 | 100 | [15 empty] | 0.32974 | 0.001118 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5146 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020060
3006 | Task(Task)-->P (Procurement) | Electric Hoist |  | 1.24.2.2 | Electric Hoist-->TECHNICAL CLEARANCE-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-15 | 2020-03-25 18:00 | 2020-04-24 09:00 | 2020-06-11 18:00 |  |  | 2020-06-11 10:57 | 2020-06-11 10:57 |  |  | 100 | 100 | [15 empty] | 2.9376 | 0.009962 | 0.98 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5147 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020061
3007 | Task(Task)-->P (Procurement) | Belt Vulcanizer |  | 1.24.2.2 | Belt Vulcanizer-->TECHNICAL CLEARANCE-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-02 09:00 | 2020-05-13 18:00 | 2020-04-28 09:00 | 2020-11-10 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.89928 | 0.00305 | 0.3 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5148 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020062
3008 | Task(Task)-->P (Procurement) | HT CABLE (33KV & 6.6KV) |  | 1.24.2.2 | HT CABLE (33KV & 6.6KV)-->TECHNICAL CLEARANCE-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-11 09:00 | 2020-01-25 18:00 | 2020-02-12 09:00 | 2020-05-03 23:59 |  |  | 2020-05-03 10:57 | 2020-05-03 10:57 |  |  | 100 | 100 | [15 empty] | 15.5276 | 0.052657 | 5.18 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5149 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020063
3009 | Task(Task)-->P (Procurement) | LT POWER CABLES |  | 1.24.2.2 | LT POWER CABLES-->TECHNICAL CLEARANCE-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-31 09:00 | 2020-02-13 18:00 | 2020-03-11 09:00 | 2020-05-04 18:00 |  |  | 2020-05-04 10:57 | 2020-05-04 10:57 |  |  | 100 | 100 | [15 empty] | 20.4736 | 0.06943 | 6.83 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5150 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020064
3010 | Task(Task)-->P (Procurement) | LIGHTING MAST |  | 1.24.2.2 | LIGHTING MAST-->TECHNICAL CLEARANCE-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2019-12-22 | 2020-01-13 18:00 | 2020-01-13 09:00 | 2020-04-28 18:00 |  |  | 2020-01-15 16:14 | 2020-04-28 16:14 |  |  | 100 | 100 | [15 empty] | 0.68945 | 0.002338 | 0.23 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5151 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020065
3011 | Task(Task)-->P (Procurement) | CABLE TRAY & ACCESSORIES |  | 1.24.2.2 | CABLE TRAY & ACCESSORIES-->TECHNICAL CLEARANCE-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-29 09:00 | 2020-02-05 18:00 | 2020-03-16 09:00 | 2020-05-04 18:00 |  |  | 2020-03-16 16:05 | 2020-05-04 16:05 |  |  | 100 | 100 | [15 empty] | 23.2014 | 0.07868 | 7.74 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5152 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020066
3012 | Task(Task)-->P (Procurement) | FLEXIBLE CABLE TRAY SUPPORTS |  | 1.24.2.2 | FLEXIBLE CABLE TRAY SUPPORTS-->TECHNICAL CLEARANCE-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-29 09:00 | 2020-02-06 18:00 | 2020-04-10 09:00 | 2020-05-08 18:00 |  |  | 2020-05-08 10:57 | 2020-05-08 10:57 |  |  | 100 | 100 | [15 empty] | 4.6763 | 0.015858 | 1.56 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5153 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020067
3013 | Task(Task)-->P (Procurement) | E ARTHING & LIGHTNING PROTECTION MATERIALS |  | 1.24.2.2 | E ARTHING & LIGHTNING PROTECTION MATERIALS-->TECHNICAL CLEARANCE-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-20 09:00 | 2020-04-18 18:00 | 2020-04-15 09:00 | 2020-06-06 18:00 |  |  | 2020-04-16 17:16 | 2020-06-06 17:16 |  |  | 100 | 100 | [15 empty] | 7.2842 | 0.024702 | 2.43 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5154 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020068
3014 | Task(Task)-->P (Procurement) | HT CABLE ACCESSORIES |  | 1.24.2.2 | HT CABLE ACCESSORIES-->TECHNICAL CLEARANCE-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-25 09:00 | 2020-02-17 18:00 | 2020-02-20 09:00 | 2020-04-02 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.77938 | 0.002643 | 0.26 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5155 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020069
3015 | Task(Task)-->P (Procurement) | LT CABLE ACCESSORIES |  | 1.24.2.2 | LT CABLE ACCESSORIES-->TECHNICAL CLEARANCE-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-08 09:00 | 2020-02-15 18:00 | 2020-06-20 09:00 | 2020-06-20 18:00 | [6 empty] | 100 | 0 | [15 empty] | 1.6187 | 0.005489 | 0.54 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5156 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020070
3016 | Task(Task)-->P (Procurement) | FO CABLE |  | 1.24.2.2 | FO CABLE-->TECHNICAL CLEARANCE-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-06 09:00 | 2020-02-14 18:00 | 2020-04-15 09:00 | 2020-07-16 18:00 |  |  | 2020-07-16 18:13 | 2020-07-16 18:14 |  |  | 100 | 100 | [15 empty] | 1.4988 | 0.005083 | 0.5 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5157 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020071
3017 | Task(Task)-->P (Procurement) | RECEPTACLES |  | 1.24.2.2 | RECEPTACLES-->TECHNICAL CLEARANCE-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-13 09:00 | 2020-02-25 18:00 | 2020-04-10 09:00 | 2020-05-19 18:00 |  |  | 2020-05-19 10:57 | 2020-05-19 10:57 |  |  | 100 | 100 | [15 empty] | 1.3489 | 0.004574 | 0.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5158 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020072
3018 | Task(Task)-->P (Procurement) | CONTROL CABLE |  | 1.24.2.2 | CONTROL CABLE-->TECHNICAL CLEARANCE-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-28 09:00 | 2020-02-04 18:00 | 2020-02-21 09:00 | 2020-05-08 18:00 |  |  | 2020-05-08 10:57 | 2020-05-08 10:57 |  |  | 100 | 100 | [15 empty] | 7.7038 | 0.026125 | 2.57 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5159 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020073
3019 | Task(Task)-->P (Procurement) | CCTV SYSTEM |  | 1.24.2.2 | CCTV SYSTEM-->TECHNICAL CLEARANCE-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-11 09:00 | 2020-02-17 18:00 | 2020-01-14 09:00 | 2020-05-04 18:00 |  |  | 2020-05-04 10:57 | 2020-05-04 10:57 |  |  | 100 | 100 | [15 empty] | 3.8669 | 0.013113 | 1.29 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5236 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020074
3020 | Task(Task)-->P (Procurement) | PA SYSTEM |  | 1.24.2.2 | PA SYSTEM-->TECHNICAL CLEARANCE-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-18 09:00 | 2020-02-12 18:00 | 2020-01-17 09:00 | 2020-05-04 18:00 |  |  | 2020-05-04 10:57 | 2020-05-04 10:57 |  |  | 100 | 100 | [15 empty] | 2.9976 | 0.010165 | 1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5235 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020075
3021 | Task(Task)-->P (Procurement) | INSTRUMENTATION CABLE |  | 1.24.2.2 | INSTRUMENTATION CABLE-->TECHNICAL CLEARANCE-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-28 09:00 | 2020-02-04 18:00 | 2020-02-21 09:00 | 2020-05-08 18:00 |  |  | 2020-05-08 10:57 | 2020-05-08 10:57 |  |  | 100 | 100 | [15 empty] | 4.1667 | 0.01413 | 1.39 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5160 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020076
3022 | Task(Task)-->P (Procurement) | ORDERING | 1.24.2.3 | 1.24.2 | ORDERING-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-01-14 09:00 | 2020-06-16 18:00 | 2020-04-02 09:00 | 2020-12-31 18:00 |  |  | 2020-05-04 17:26 |  |  |  | 100 | 48.8159 | [15 empty] | 9.9994 | 0.67813 | 66.69 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5161 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020077
3023 | Task(Task)-->P (Procurement) | Manual Hoist |  | 1.24.2.3 | Manual Hoist-->ORDERING-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-31 09:00 | 2020-04-29 18:00 | 2020-06-10 09:00 | 2020-07-03 18:00 |  |  | 2020-06-11 14:46 | 2020-07-03 14:46 |  |  | 100 | 100 | [15 empty] | 0.31475 | 0.002134 | 0.21 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5162 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020078
3024 | Task(Task)-->P (Procurement) | Electric Hoist |  | 1.24.2.3 | Electric Hoist-->ORDERING-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-26 09:00 | 2020-04-24 18:00 | 2020-06-11 09:00 | 2020-07-17 18:00 |  |  | 2020-06-11 01:10 | 2020-07-17 01:10 |  |  | 100 | 100 | [15 empty] | 2.9526 | 0.020023 | 1.97 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5163 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020079
3025 | Task(Task)-->P (Procurement) | Belt Vulcanizer |  | 1.24.2.3 | Belt Vulcanizer-->ORDERING-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-05-14 09:00 | 2020-06-12 18:00 | 2020-11-11 09:00 | 2020-12-10 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.89928 | 0.006098 | 0.6 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5164 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020080
3026 | Task(Task)-->P (Procurement) | HT CABLE (33KV & 6.6KV) |  | 1.24.2.3 | HT CABLE (33KV & 6.6KV)-->ORDERING-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-01-26 | 2020-02-10 18:00 | 2020-05-03 | 2020-08-17 18:00 | [6 empty] | 100 | 0 | [15 empty] | 15.5276 | 0.1053 | 10.36 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5165 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020081
3027 | Task(Task)-->P (Procurement) | LT POWER CABLES |  | 1.24.2.3 | LT POWER CABLES-->ORDERING-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-14 09:00 | 2020-02-28 18:00 | 2020-05-04 09:00 | 2020-08-17 18:00 | [6 empty] | 100 | 0 | [15 empty] | 20.4886 | 0.13894 | 13.67 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5166 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020082
3028 | Task(Task)-->P (Procurement) | LIGHTING MAST |  | 1.24.2.3 | LIGHTING MAST-->ORDERING-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2020-01-14 09:00 | 2020-02-05 18:00 | 2020-04-28 09:00 | 2020-06-11 18:00 |  |  | 2020-06-11 10:18 | 2020-06-11 10:18 |  |  | 100 | 100 | [15 empty] | 0.68945 | 0.004675 | 0.46 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5167 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020083
3029 | Task(Task)-->P (Procurement) | CABLE TRAY & ACCESSORIES |  | 1.24.2.3 | CABLE TRAY & ACCESSORIES-->ORDERING-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-06 09:00 | 2020-02-15 18:00 | 2020-05-04 09:00 | 2020-08-07 18:00 |  |  | 2020-05-05 16:06 | 2020-07-06 16:06 |  |  | 100 | 100 | [15 empty] | 23.1865 | 0.15724 | 15.47 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5168 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020084
3030 | Task(Task)-->P (Procurement) | FLEXIBLE CABLE TRAY SUPPORTS |  | 1.24.2.3 | FLEXIBLE CABLE TRAY SUPPORTS-->ORDERING-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-07 09:00 | 2020-02-15 18:00 | 2020-05-08 09:00 | 2020-08-07 18:00 |  |  | 2020-05-09 16:07 | 2020-07-06 16:07 |  |  | 100 | 100 | [15 empty] | 4.6763 | 0.031711 | 3.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5169 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020085
3031 | Task(Task)-->P (Procurement) | EARTHING & LIGHTNING PROTECTION MATERIALS |  | 1.24.2.3 | EARTHING & LIGHTNING PROTECTION MATERIALS-->ORDERING-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-19 | 2020-06-16 18:00 | 2020-06-06 09:00 | 2020-08-17 18:00 |  |  | 2020-06-08 17:15 | 2020-07-06 17:15 |  |  | 100 | 100 | [15 empty] | 7.2992 | 0.049498 | 4.87 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5170 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020086
3032 | Task(Task)-->P (Procurement) | HT CABLE ACCESSORIES |  | 1.24.2.3 | HT CABLE ACCESSORIES-->ORDERING-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-18 09:00 | 2020-03-12 18:00 | 2020-04-02 09:00 | 2020-09-09 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.77938 | 0.005285 | 0.52 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5171 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020087
3033 | Task(Task)-->P (Procurement) | LT CABLE ACCESSORIES |  | 1.24.2.3 | LT CABLE ACCESSORIES-->ORDERING-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-16 | 2020-03-03 18:00 | 2020-06-20 09:00 | 2020-12-31 18:00 | [6 empty] | 100 | 0 | [15 empty] | 1.6187 | 0.010977 | 1.08 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5172 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020088
3034 | Task(Task)-->P (Procurement) | FO CABLE |  | 1.24.2.3 | FO CABLE-->ORDERING-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-15 09:00 | 2020-02-24 18:00 | 2020-07-16 09:00 | 2020-07-27 18:00 |  |  | 2020-07-27 18:14 | 2020-07-27 18:14 |  |  | 100 | 100 | [15 empty] | 1.4988 | 0.010164 | 1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5173 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020089
3035 | Task(Task)-->P (Procurement) | RECEPTACLES |  | 1.24.2.3 | RECEPTACLES-->ORDERING-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-26 09:00 | 2020-03-10 18:00 | 2020-05-19 09:00 | 2020-07-18 18:00 |  |  | 2020-07-13 22:33 | 2020-07-13 22:33 |  |  | 100 | 100 | [15 empty] | 1.3339 | 0.009046 | 0.89 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5174 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020090
3036 | Task(Task)-->P (Procurement) | CONTROL CABLE |  | 1.24.2.3 | CONTROL CABLE-->ORDERING-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-05 09:00 | 2020-02-12 18:00 | 2020-05-08 09:00 | 2020-11-30 18:00 | [6 empty] | 100 | 0 | [15 empty] | 7.7038 | 0.052242 | 5.14 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5175 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020091
3037 | Task(Task)-->P (Procurement) | CCTV SYSTEM |  | 1.24.2.3 | CCTV SYSTEM-->ORDERING-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-18 09:00 | 2020-03-27 18:00 | 2020-05-04 09:00 | 2020-07-18 18:00 |  |  | 2020-05-05 17:27 | 2020-06-24 17:27 |  |  | 100 | 100 | [15 empty] | 3.8669 | 0.026223 | 2.58 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5238 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020092
3038 | Task(Task)-->P (Procurement) | PA SYSTEM |  | 1.24.2.3 | PA SYSTEM-->ORDERING-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-13 09:00 | 2020-03-10 18:00 | 2020-05-04 09:00 | 2020-08-17 18:00 |  |  | 2020-05-04 17:26 | 2020-06-20 17:26 |  |  | 100 | 100 | [15 empty] | 2.9976 | 0.020328 | 2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5237 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020093
3039 | Task(Task)-->P (Procurement) | INSTRUMENTATION CABLE |  | 1.24.2.3 | INSTRUMENTATION CABLE-->ORDERING-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-05 09:00 | 2020-02-12 18:00 | 2020-05-08 09:00 | 2020-11-30 18:00 | [6 empty] | 100 | 0 | [15 empty] | 4.1667 | 0.028256 | 2.78 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5176 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020094
3040 | Task(Task)-->P (Procurement) | ITP APPROVAL | 1.24.2.4 | 1.24.2 | ITP APPROVAL-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-02-06 09:00 | 2020-07-26 23:59 | 2020-05-30 09:00 | 2021-01-19 18:00 |  |  | 2020-05-30 16:50 |  |  |  | 100 | 77.278 | [15 empty] | 5.0004 | 0.33912 | 33.35 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5177 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020095
3041 | Task(Task)-->P (Procurement) | Manual Hoist |  | 1.24.2.4 | Manual Hoist-->ITP APPROVAL-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-30 09:00 | 2020-06-08 18:00 | 2020-07-03 09:00 | 2020-08-21 18:00 |  |  | 2020-07-03 16:09 | 2020-08-21 16:08 |  |  | 100 | 100 | [15 empty] | 0.32974 | 0.001118 | 0.11 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5178 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020096
3042 | Task(Task)-->P (Procurement) | Electric Hoist |  | 1.24.2.4 | Electric Hoist-->ITP APPROVAL-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-25 09:00 | 2020-06-03 18:00 | 2020-07-17 09:00 | 2020-10-09 18:00 |  |  | 2020-07-17 01:13 |  |  |  | 100 | 49.99 | [15 empty] | 2.9376 | 0.009962 | 0.98 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5179 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020097
3043 | Task(Task)-->P (Procurement) | Belt Vulcanizer |  | 1.24.2.4 | Belt Vulcanizer-->ITP APPROVAL-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-13 09:00 | 2020-07-22 18:00 | 2020-12-11 09:00 | 2021-01-19 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.89928 | 0.00305 | 0.3 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5180 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020098
3044 | Task(Task)-->P (Procurement) | HT CABLE (33KV & 6.6KV) |  | 1.24.2.4 | HT CABLE (33KV & 6.6KV)-->ITP APPROVAL-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-11 09:00 | 2020-03-21 18:00 | 2020-08-03 09:00 | 2020-08-21 18:00 |  |  | 2020-08-03 16:20 | 2020-08-21 12:45 |  |  | 100 | 100 | [15 empty] | 15.5276 | 0.052657 | 5.18 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5181 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020099
3045 | Task(Task)-->P (Procurement) | LT POWER CABLES |  | 1.24.2.4 | LT POWER CABLES-->ITP APPROVAL-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-29 09:00 | 2020-04-08 18:00 | 2020-08-03 09:00 | 2020-08-21 18:00 |  |  | 2020-08-03 16:22 | 2020-08-21 12:46 |  |  | 100 | 100 | [15 empty] | 20.4736 | 0.06943 | 6.83 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5182 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020100
3046 | Task(Task)-->P (Procurement) | LIGHTING MAST |  | 1.24.2.4 | LIGHTING MAST-->ITP APPROVAL-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-06 09:00 | 2020-03-16 18:00 | 2020-07-08 09:00 | 2020-09-23 18:00 |  |  | 2020-09-03 12:01 | 2020-09-23 16:50 |  |  | 100 | 100 | [15 empty] | 0.68945 | 0.002338 | 0.23 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5183 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020101
3047 | Task(Task)-->P (Procurement) | CABLE TRAY & ACCESSORIES |  | 1.24.2.4 | CABLE TRAY & ACCESSORIES-->ITP APPROVAL-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-16 | 2020-03-26 18:00 | 2020-05-30 09:00 | 2020-07-28 18:00 |  |  | 2020-05-30 16:50 | 2020-07-28 16:50 |  |  | 100 | 100 | [15 empty] | 23.2014 | 0.07868 | 7.74 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5184 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020102
3048 | Task(Task)-->P (Procurement) | FLEXIBLE CABLE TRAY SUPPORTS |  | 1.24.2.4 | FLEXIBLE CABLE TRAY SUPPORTS-->ITP APPROVAL-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-16 | 2020-03-26 18:00 | 2020-07-22 09:00 | 2020-08-12 18:00 |  |  | 2020-07-22 18:26 | 2020-08-12 12:49 |  |  | 100 | 100 | [15 empty] | 4.6763 | 0.015858 | 1.56 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5185 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020103
3049 | Task(Task)-->P (Procurement) | EARTHING & LIGHTNING PROTECTION MATERIALS |  | 1.24.2.4 | EARTHING & LIGHTNING PROTECTION MATERIALS-->ITP APPROVAL-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2020-06-17 09:00 | 2020-07-26 23:59 | 2020-07-22 09:00 | 2020-08-13 18:00 |  |  | 2020-07-22 18:48 | 2020-08-14 13:04 |  |  | 100 | 100 | [15 empty] | 7.2842 | 0.024702 | 2.43 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5186 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020104
3050 | Task(Task)-->P (Procurement) | HT CABLE ACCESSORIES |  | 1.24.2.4 | HT CABLE ACCESSORIES-->ITP APPROVAL-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-13 09:00 | 2020-04-21 18:00 | 2020-09-10 09:00 | 2020-10-19 18:00 |  |  | 2020-08-03 16:21 | 2020-08-21 12:45 |  |  | 100 | 100 | [15 empty] | 0.77938 | 0.002643 | 0.26 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5187 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020105
3051 | Task(Task)-->P (Procurement) | LT CABLE ACCESSORIES |  | 1.24.2.4 | LT CABLE ACCESSORIES-->ITP APPROVAL-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-04 09:00 | 2020-04-12 23:59 | 2020-08-10 09:00 | 2020-08-10 18:00 | [6 empty] | 100 | 0 | [15 empty] | 1.6187 | 0.005489 | 0.54 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5188 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020106
3052 | Task(Task)-->P (Procurement) | FO CABLE |  | 1.24.2.4 | FO CABLE-->ITP APPROVAL-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-25 09:00 | 2020-04-04 18:00 | 2020-09-23 09:00 | 2020-10-22 18:00 |  |  | 2020-09-23 14:18 | 2020-10-14 15:28 |  |  | 100 | 100 | [15 empty] | 1.4988 | 0.005083 | 0.5 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5189 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020107
3053 | Task(Task)-->P (Procurement) | RECEPTACLES |  | 1.24.2.4 | RECEPTACLES-->ITP APPROVAL-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-11 09:00 | 2020-04-19 23:59 | 2020-07-16 09:00 | 2020-07-16 18:00 |  |  | 2020-07-16 19:23 | 2020-07-16 19:44 |  |  | 100 | 100 | [15 empty] | 1.3489 | 0.004574 | 0.45 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5190 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020108
3054 | Task(Task)-->P (Procurement) | CONTROL CABLE |  | 1.24.2.4 | CONTROL CABLE-->ITP APPROVAL-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-13 09:00 | 2020-03-23 18:00 | 2020-12-01 09:00 | 2021-01-09 18:00 | [6 empty] | 100 | 0 | [15 empty] | 7.7038 | 0.026125 | 2.57 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5191 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020109
3055 | Task(Task)-->P (Procurement) | CCTV SYSTEM |  | 1.24.2.4 | CCTV SYSTEM-->ITP APPROVAL-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-28 09:00 | 2020-05-06 18:00 | 2020-08-01 09:00 | 2020-09-09 18:00 | [6 empty] | 100 | 0 | [15 empty] | 3.8669 | 0.013113 | 1.29 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5240 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020110
3056 | Task(Task)-->P (Procurement) | PA SYSTEM |  | 1.24.2.4 | PA SYSTEM-->ITP APPROVAL-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-11 09:00 | 2020-04-19 23:59 | 2020-09-24 09:00 | 2020-11-30 18:00 |  |  | 2020-09-24 09:43 |  |  |  | 100 | 0 | [15 empty] | 2.9976 | 0.010165 | 1 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5239 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020111
3057 | Task(Task)-->P (Procurement) | INSTRUMENTATION CABLE |  | 1.24.2.4 | INSTRUMENTATION CABLE-->ITP APPROVAL-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-13 09:00 | 2020-03-23 18:00 | 2020-12-01 09:00 | 2021-01-09 18:00 | [6 empty] | 100 | 0 | [15 empty] | 4.1667 | 0.01413 | 1.39 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5192 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020112
3058 | Task(Task)-->P (Procurement) | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE | 1.24.2.5 | 1.24.2 | VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Work In Progress | No | No | 2020-02-06 09:00 | 2020-08-10 18:00 | 2020-05-15 09:00 | 2021-02-14 23:59 |  |  | 2020-06-11 10:20 |  |  |  | 100 | 77.9809 | [15 empty] | 14.9999 | 1.0173 | 100.04 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5193 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020113
3059 | Task(Task)-->P (Procurement) | Manual Hoist |  | 1.24.2.5 | Manual Hoist-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-30 09:00 | 2020-06-28 23:59 | 2020-07-03 09:00 | 2020-09-02 18:00 |  |  | 2020-07-04 01:31 | 2020-09-02 16:09 |  |  | 100 | 100 | [15 empty] | 0.31984 | 0.003254 | 0.32 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5194 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020114
3060 | Task(Task)-->P (Procurement) | Electric Hoist |  | 1.24.2.5 | Electric Hoist-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2020-04-25 09:00 | 2020-06-23 18:00 | 2020-07-17 09:00 | 2020-09-02 18:00 |  |  | 2020-07-17 16:07 | 2020-09-02 16:07 |  |  | 100 | 100 | [15 empty] | 2.9485 | 0.029994 | 2.95 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5195 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020115
3061 | Task(Task)-->P (Procurement) | Belt Vulcanizer |  | 1.24.2.5 | Belt Vulcanizer-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-13 09:00 | 2020-07-22 18:00 | 2020-12-11 09:00 | 2021-01-19 18:00 | [6 empty] | 100 | 0 | [15 empty] | 0.89955 | 0.009151 | 0.9 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5196 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020116
3062 | Task(Task)-->P (Procurement) | HT CABLE (33KV & 6.6KV) |  | 1.24.2.5 | HT CABLE (33KV & 6.6KV)-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-11 09:00 | 2020-03-26 18:00 | 2020-07-31 09:00 | 2020-09-15 18:00 |  |  | 2020-07-31 20:04 | 2020-09-15 16:57 |  |  | 100 | 100 | [15 empty] | 15.5322 | 0.158 | 15.54 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5197 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020117
3063 | Task(Task)-->P (Procurement) | LT POWER CABLES |  | 1.24.2.5 | LT POWER CABLES-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-29 09:00 | 2020-04-13 18:00 | 2020-07-31 09:00 | 2020-09-09 18:00 |  |  | 2020-07-31 20:05 | 2020-09-10 10:03 |  |  | 100 | 100 | [15 empty] | 20.4898 | 0.20843 | 20.5 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5198 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020118
3064 | Task(Task)-->P (Procurement) | LIGHTING MAST |  | 1.24.2.5 | LIGHTING MAST-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-06 09:00 | 2020-03-21 18:00 | 2020-05-15 09:00 | 2020-09-04 18:00 |  |  | 2020-06-11 10:20 | 2020-09-04 10:04 |  |  | 100 | 100 | [15 empty] | 0.68966 | 0.007016 | 0.69 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5199 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020119
3065 | Task(Task)-->P (Procurement) | CABLE TRAY & ACCESSORIES |  | 1.24.2.5 | CABLE TRAY & ACCESSORIES-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-16 | 2020-03-31 18:00 | 2020-05-30 09:00 | 2020-08-08 18:00 |  |  | 2020-07-06 10:19 | 2020-08-08 13:48 |  |  | 100 | 100 | [15 empty] | 23.1884 | 0.23589 | 23.2 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5200 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020120
3066 | Task(Task)-->P (Procurement) | FLEXIBLE CABLE TRAY SUPPORTS |  | 1.24.2.5 | FLEXIBLE CABLE TRAY SUPPORTS-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-16 | 2020-03-31 18:00 | 2020-07-18 09:00 | 2020-08-12 18:00 |  |  | 2020-07-22 11:43 | 2020-08-12 12:49 |  |  | 100 | 100 | [15 empty] | 4.6777 | 0.047584 | 4.68 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5201 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020121
3067 | Task(Task)-->P (Procurement) | EARTHING & LIGHTNING PROTECTION MATERIALS |  | 1.24.2.5 | EARTHING & LIGHTNING PROTECTION MATERIALS-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2020-06-17 09:00 | 2020-08-10 18:00 | 2020-07-07 09:00 | 2020-08-08 18:00 |  |  | 2020-07-22 18:47 | 2020-08-07 14:17 |  |  | 100 | 100 | [15 empty] | 7.2964 | 0.074222 | 7.3 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5202 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020122
3068 | Task(Task)-->P (Procurement) | HT CABLE ACCESSORIES |  | 1.24.2.5 | HT CABLE ACCESSORIES-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-13 09:00 | 2020-04-26 23:59 | 2020-09-07 09:00 | 2020-11-30 18:00 |  |  | 2020-09-07 16:56 |  |  |  | 100 | 0 | [15 empty] | 0.77961 | 0.007931 | 0.78 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5203 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020123
3069 | Task(Task)-->P (Procurement) | LT CABLE ACCESSORIES |  | 1.24.2.5 | LT CABLE ACCESSORIES-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-04 09:00 | 2020-04-17 18:00 | 2021-01-01 09:00 | 2021-02-14 23:59 | [6 empty] | 100 | 0 | [15 empty] | 1.6192 | 0.016471 | 1.62 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5204 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020124
3070 | Task(Task)-->P (Procurement) | FO CABLE |  | 1.24.2.5 | FO CABLE-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2020-02-25 09:00 | 2020-04-09 18:00 | 2020-07-30 09:00 | 2020-09-26 18:00 |  |  | 2020-07-30 14:21 | 2020-09-26 10:37 |  |  | 100 | 100 | [15 empty] | 1.4993 | 0.015251 | 1.5 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5205 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020125
3071 | Task(Task)-->P (Procurement) | RECEPTACLES |  | 1.24.2.5 | RECEPTACLES-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Completed | No | No | 2020-03-11 09:00 | 2020-04-24 18:00 | 2020-05-30 09:00 | 2020-07-29 18:00 |  |  | 2020-07-18 19:22 | 2020-07-29 15:08 |  |  | 100 | 100 | [15 empty] | 1.3393 | 0.013624 | 1.34 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5206 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020126
3072 | Task(Task)-->P (Procurement) | CONTROL CABLE |  | 1.24.2.5 | CONTROL CABLE-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-13 09:00 | 2020-03-28 18:00 | 2020-12-01 09:00 | 2021-01-14 18:00 | [6 empty] | 100 | 0 | [15 empty] | 7.7061 | 0.078391 | 7.71 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5207 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020127
3073 | Task(Task)-->P (Procurement) | CCTV SYSTEM |  | 1.24.2.5 | CCTV SYSTEM-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-28 09:00 | 2020-05-21 18:00 | 2020-05-31 | 2020-12-01 18:00 |  |  | 2020-07-01 10:39 |  |  |  | 100 | 0 | [15 empty] | 3.8681 | 0.039348 | 3.87 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5242 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020128
3074 | Task(Task)-->P (Procurement) | PA SYSTEM |  | 1.24.2.5 | PA SYSTEM-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-11 09:00 | 2020-05-24 23:59 | 2020-07-08 09:00 | 2020-12-01 18:00 |  |  | 2020-07-08 10:37 |  |  |  | 100 | 0 | [15 empty] | 2.9885 | 0.030401 | 2.99 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5241 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020129
3075 | Task(Task)-->P (Procurement) | INSTRUMENTATION CABLE |  | 1.24.2.5 | INSTRUMENTATION CABLE-->VENDOR DRAWING APPROVAL & MANUFACTURING CLEARANCE-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-02-13 09:00 | 2020-03-28 18:00 | 2020-12-01 09:00 | 2021-01-14 18:00 | [6 empty] | 100 | 0 | [15 empty] | 4.1579 | 0.042297 | 4.16 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5208 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020130
3076 | Task(Task)-->P (Procurement) | MANUFACTURING & RECEIPT AT SITE (MRN) | 1.24.2.6 | 1.24.2 | MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-22 | 2021-03-31 18:00 | 2020-07-30 09:00 | 2021-10-25 18:00 |  |  | 2020-07-30 19:58 |  |  |  | 76.9141 | 0.21054 | [15 empty] | 59.9994 | 4.069 | 400.16 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5209 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020131
3077 | Task(Task)-->P (Procurement) | Manual Hoist |  | 1.24.2.6 | Manual Hoist-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-29 09:00 | 2021-01-08 18:00 | 2020-09-02 09:00 | 2020-12-31 18:00 |  |  | 2020-09-02 16:10 |  |  |  | 69.5876 | 20 | [15 empty] | 0.31487 | 0.012812 | 1.26 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5210 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020132
3078 | Task(Task)-->P (Procurement) | Electric Hoist |  | 1.24.2.6 | Electric Hoist-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-06-24 09:00 | 2021-03-19 18:00 | 2020-09-02 09:00 | 2021-02-09 18:00 |  |  | 2020-09-02 16:08 |  |  |  | 52.0446 | 5 | [15 empty] | 2.9512 | 0.12009 | 11.81 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5211 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020133
3079 | Task(Task)-->P (Procurement) | Belt Vulcanizer |  | 1.24.2.6 | Belt Vulcanizer-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-23 09:00 | 2021-02-07 23:59 | 2021-01-20 09:00 | 2021-08-07 18:00 | [6 empty] | 55.5 | 0 | [15 empty] | 0.89962 | 0.036606 | 3.6 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5212 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020134
3080 | Task(Task)-->P (Procurement) | HT CABLE (33KV & 6.6KV) |  | 1.24.2.6 | HT CABLE (33KV & 6.6KV)-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-11 09:00 | 2021-02-03 18:00 | 2020-09-29 09:00 | 2021-07-24 18:00 |  |  | 2020-09-15 12:58 |  |  |  | 71.5719 | 0 | [15 empty] | 15.5284 | 0.63185 | 62.14 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5213 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020135
3081 | Task(Task)-->P (Procurement) | LT POWER CABLES |  | 1.24.2.6 | LT POWER CABLES-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-14 09:00 | 2021-01-09 18:00 | 2020-09-10 09:00 | 2021-06-07 18:00 |  |  | 2020-09-10 10:04 |  |  |  | 77.8598 | 0 | [15 empty] | 20.4913 | 0.83379 | 82 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5214 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020136
3082 | Task(Task)-->P (Procurement) | LIGHTING MAST |  | 1.24.2.6 | LIGHTING MAST-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-22 | 2020-07-03 18:00 | 2020-09-24 09:00 | 2021-01-05 18:00 |  |  | 2020-09-04 10:04 |  |  |  | 100 | 0 | [15 empty] | 0.68471 | 0.027861 | 2.74 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5215 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020137
3083 | Task(Task)-->P (Procurement) | CABLE TRAY & ACCESSORIES |  | 1.24.2.6 | CABLE TRAY & ACCESSORIES-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-01 09:00 | 2020-09-09 18:00 | 2020-08-09 | 2021-01-17 23:59 |  |  | 2020-08-09 13:52 |  |  |  | 100 | 0 | [15 empty] | 23.1951 | 0.94381 | 92.82 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5216 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020138
3084 | Task(Task)-->P (Procurement) | FLEXIBLE CABLE TRAY SUPPORTS |  | 1.24.2.6 | FLEXIBLE CABLE TRAY SUPPORTS-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-01 09:00 | 2020-08-10 18:00 | 2020-08-13 09:00 | 2020-12-22 18:00 |  |  | 2020-08-12 12:48 |  |  |  | 100 | 0 | [15 empty] | 4.6755 | 0.19025 | 18.71 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5217 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020139
3085 | Task(Task)-->P (Procurement) | EARTHING & LIGHTNING PROTECTION MATERIALS |  | 1.24.2.6 | EARTHING & LIGHTNING PROTECTION MATERIALS-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-08-11 09:00 | 2021-02-08 18:00 | 2020-08-14 09:00 | 2021-02-11 18:00 |  |  | 2020-08-11 13:05 |  |  |  | 50.5495 | 0 | [15 empty] | 7.2944 | 0.29681 | 29.19 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5218 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020140
3086 | Task(Task)-->P (Procurement) | HT CABLE ACCESSORIES |  | 1.24.2.6 | HT CABLE ACCESSORIES-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-09-24 09:00 | 2020-12-19 18:00 | 2021-04-30 09:00 | 2021-07-25 23:59 | [6 empty] | 55.1724 | 0 | [15 empty] | 0.77967 | 0.031725 | 3.12 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5219 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020141
3087 | Task(Task)-->P (Procurement) | LT CABLE ACCESSORIES |  | 1.24.2.6 | LT CABLE ACCESSORIES-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-07-17 09:00 | 2020-11-03 18:00 | 2021-05-16 | 2021-09-02 18:00 | [6 empty] | 100 | 0 | [15 empty] | 1.6218 | 0.065992 | 6.49 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5220 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020142
3088 | Task(Task)-->P (Procurement) | FO CABLE |  | 1.24.2.6 | FO CABLE-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-10 09:00 | 2021-01-30 18:00 | 2020-10-23 09:00 | 2021-08-14 18:00 |  |  | 2020-09-26 10:38 |  |  |  | 72.6351 | 0 | [15 empty] | 1.4969 | 0.060907 | 5.99 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5221 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020143
3089 | Task(Task)-->P (Procurement) | RECEPTACLES |  | 1.24.2.6 | RECEPTACLES-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-04-25 09:00 | 2020-08-25 18:00 | 2020-07-30 09:00 | 2020-11-29 23:59 |  |  | 2020-07-30 19:58 |  |  |  | 100 | 0 | [15 empty] | 1.3394 | 0.054502 | 5.36 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5222 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020144
3090 | Task(Task)-->P (Procurement) | CONTROL CABLE |  | 1.24.2.6 | CONTROL CABLE-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-29 | 2021-01-06 18:00 | 2021-01-15 09:00 | 2021-10-25 18:00 | [6 empty] | 79.9296 | 0 | [15 empty] | 7.7042 | 0.31349 | 30.83 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5223 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020145
3091 | Task(Task)-->P (Procurement) | CCTV SYSTEM |  | 1.24.2.6 | CCTV SYSTEM-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-10-24 09:00 | 2021-03-31 18:00 | 2021-05-06 09:00 | 2021-10-11 18:00 | [6 empty] | 11.3208 | 0 | [15 empty] | 3.8659 | 0.1573 | 15.47 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5244 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020146
3092 | Task(Task)-->P (Procurement) | PA SYSTEM |  | 1.24.2.6 | PA SYSTEM-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-10-10 09:00 | 2021-03-31 18:00 | 2021-04-19 09:00 | 2021-10-08 18:00 | [6 empty] | 18.4971 | 0 | [15 empty] | 2.9937 | 0.12182 | 11.98 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5243 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020147
3093 | Task(Task)-->P (Procurement) | INSTRUMENTATION CABLE |  | 1.24.2.6 | INSTRUMENTATION CABLE-->MANUFACTURING & RECEIPT AT SITE (MRN)-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-03-29 | 2020-12-07 18:00 | 2021-01-15 09:00 | 2021-09-25 18:00 | [6 empty] | 89.3701 | 0 | [15 empty] | 4.1632 | 0.1694 | 16.66 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5224 | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020148
3094 | Task(Task)-->P (Procurement) | ITEM LIST | 1.24.2.7 | 1.24.2 | ITEM LIST-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | [6 empty] | 2020-07-06 12:38 |  |  |  | 0 | 0 | [15 empty] | 0 | 0 | 0 |  | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No |  | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1044190
3095 | Task(Task)-->P (Procurement) | PRIMARY AND SECONDARY SIZERS |  | 1.24.2.7 | PRIMARY AND SECONDARY SIZERS-->ITEM LIST-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | [6 empty] | 2020-07-06 12:38 |  |  |  | 0 | 0 |  |  |  | Documents(Documents)-->ITEM (Item List) | EK210PO0000012 | [10 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1047486
3096 | Task(Task)-->P (Procurement) | IDLERS WITH SPARES FOR TROUGH BELT CONVEYOR |  | 1.24.2.7 | IDLERS WITH SPARES FOR TROUGH BELT CONVEYOR-->ITEM LIST-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | [6 empty] | 2020-07-06 12:38 |  |  |  | 0 | 0 |  |  |  | Documents(Documents)-->ITEM (Item List) | EK210PO0000040 | [10 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1047487
3097 | Task(Task)-->P (Procurement) | PLUMMER BLOCKS WITH SPARES FOR TROUGH BELT CONVEYORS |  | 1.24.2.7 | PLUMMER BLOCKS WITH SPARES FOR TROUGH BELT CONVEYORS-->ITEM LIST-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | [6 empty] | 2020-07-06 12:38 |  |  |  | 0 | 0 |  |  |  | Documents(Documents)-->ITEM (Item List) | EK210PO0000018 | [10 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1047488
3098 | Task(Task)-->P (Procurement) | BEARING WITH SAPRES FOR TROUGH BELT CONVEYOR PULLEYS |  | 1.24.2.7 | BEARING WITH SAPRES FOR TROUGH BELT CONVEYOR PULLEYS-->ITEM LIST-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | [6 empty] | 2020-07-06 12:38 |  |  |  | 0 | 0 |  |  |  | Documents(Documents)-->ITEM (Item List) | EK210PO0000016 | [10 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1047489
3099 | Task(Task)-->P (Procurement) | FLUID COUPLINGS FOR TROUGH CONVEYORS WITH MANDATORY SPARES |  | 1.24.2.7 | FLUID COUPLINGS FOR TROUGH CONVEYORS WITH MANDATORY SPARES-->ITEM LIST-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | [6 empty] | 2020-07-06 12:38 |  |  |  | 0 | 0 |  |  |  | Documents(Documents)-->ITEM (Item List) | EK210PO0000051 | [10 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1047490
3100 | Task(Task)-->P (Procurement) | GEARED COUPLING WITH SPARES FOR TROUGH BELT CONVEYORS |  | 1.24.2.7 | GEARED COUPLING WITH SPARES FOR TROUGH BELT CONVEYORS-->ITEM LIST-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | [6 empty] | 2020-07-06 12:38 |  |  |  | 0 | 0 |  |  |  | Documents(Documents)-->ITEM (Item List) | EK210PO0000022 | [10 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1047491
3101 | Task(Task)-->P (Procurement) | GEAR BOXES FOR TROUGH CONVEYORS & EQUIPMENT WITH MANDATORY SPARES |  | 1.24.2.7 | GEAR BOXES FOR TROUGH CONVEYORS & EQUIPMENT WITH MANDATORY SPARES-->ITEM LIST-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | [6 empty] | 2020-07-06 12:38 |  |  |  | 0 | 0 |  |  |  | Documents(Documents)-->ITEM (Item List) | EK210PO0000041 | [10 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1047492
3102 | Task(Task)-->P (Procurement) | INLINE MAGNETIC SEPARATOR AND SUSPENDED MAGNET WITH MANDATORY SPARES |  | 1.24.2.7 | INLINE MAGNETIC SEPARATOR AND SUSPENDED MAGNET WITH MANDATORY SPARES-->ITEM LIST-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | [6 empty] | 2020-07-06 12:38 |  |  |  | 0 | 0 |  |  |  | Documents(Documents)-->ITEM (Item List) | EK210PO0000010 | [10 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1047493
3103 | Task(Task)-->P (Procurement) | BELT WEIGH SCALE WITH MANDATORY SPARES FOR TROUGH BELT CONVEYORS |  | 1.24.2.7 | BELT WEIGH SCALE WITH MANDATORY SPARES FOR TROUGH BELT CONVEYORS-->ITEM LIST-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | [6 empty] | 2020-07-06 12:38 |  |  |  | 0 | 0 |  |  |  | Documents(Documents)-->ITEM (Item List) | EK210PO0000014 | [10 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1047494
3104 | Task(Task)-->P (Procurement) | METAL DETECTOR WITH MANDATORY SPARES |  | 1.24.2.7 | METAL DETECTOR WITH MANDATORY SPARES-->ITEM LIST-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | [6 empty] | 2020-07-06 12:38 |  |  |  | 0 | 0 |  |  |  | Documents(Documents)-->ITEM (Item List) | EK210PO0000026 | [10 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1047495
3105 | Task(Task)-->P (Procurement) | sample item |  | 1.24.2.7 | sample item-->ITEM LIST-->PROCUREMENT-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | [6 empty] | 2020-07-18 11:53 |  |  |  | 0 | 0 |  |  |  | Documents(Documents)-->ITEM (Item List) | test-1 | [10 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | No | No |  | 0 | 4 | Low | [7 empty] | 0 | 0 | [246 empty] | 1098712
3106 | Task(Task)-->C (Construction) | CONSTRUCTION | 1.24.3 | 1.24 | CONSTRUCTION-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-09-08 09:00 | 2021-09-26 23:59 | 2020-12-30 09:00 | 2021-12-24 18:00 | [6 empty] | 4.0001 | 0 | [15 empty] | 20.5938 | 1.8169 | 178.68 |  | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5225 | 0 | 2 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020149
3107 | Task(Task)-->C (Construction) | PRECAST FOR TAKE-UP WEIGHT OF CONVEYORS |  | 1.24.3 | PRECAST FOR TAKE-UP WEIGHT OF CONVEYORS-->CONSTRUCTION-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-09-08 09:00 | 2021-03-07 23:59 | 2020-12-30 09:00 | 2021-06-28 18:00 | [6 empty] | 35.3591 | 0 | [15 empty] | 5.9377 | 0.10788 | 10.61 | Plan & Actual | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5227 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020150
3108 | Task(Task)-->C (Construction) | PRECAST FOR DRAIN COVER |  | 1.24.3 | PRECAST FOR DRAIN COVER-->CONSTRUCTION-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-09-08 09:00 | 2021-02-04 18:00 | 2020-12-30 09:00 | 2021-05-28 18:00 | [6 empty] | 42.6667 | 0 | [15 empty] | 4.4546 | 0.080936 | 7.96 | Plan & Actual | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5445 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020151
3109 | Task(Task)-->C (Construction) | APPROACH ROAD |  | 1.24.3 | APPROACH ROAD-->CONSTRUCTION-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-01-07 09:00 | 2021-05-06 18:00 | 2021-04-30 09:00 | 2021-08-27 18:00 | [6 empty] | 0 | 0 | [15 empty] | 45.9511 | 0.83488 | 82.11 | Plan & Actual | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5228 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020152
3110 | Task(Task)-->C (Construction) | DRAINAGE SYSTEM - CONNECTION FROM GARLAND DRAIN TO MAIN DRAIN AND RAIN WATER HARVASTING |  | 1.24.3 | DRAINAGE SYSTEM - CONNECTION FROM GARLAND DRAIN TO MAIN DRAIN AND RAIN WATER HARVASTING-->CONSTRUCTION-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-12-08 09:00 | 2021-05-07 18:00 | 2021-03-31 09:00 | 2021-08-28 18:00 | [6 empty] | 0 | 0 | [15 empty] | 8.6686 | 0.1575 | 15.49 | Plan & Actual | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5229 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020153
3111 | Task(Task)-->C (Construction) | SEWAGE SYSTEM/ SOAK PIT |  | 1.24.3 | SEWAGE SYSTEM/ SOAK PIT-->CONSTRUCTION-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2020-12-08 09:00 | 2021-05-07 18:00 | 2021-03-31 09:00 | 2021-08-28 18:00 | [6 empty] | 0 | 0 | [15 empty] | 1.8804 | 0.034164 | 3.36 | Plan & Actual | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5230 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020154
3112 | Task(Task)-->C (Construction) | ERECTION OF MONORAIL & HOISTS |  | 1.24.3 | ERECTION OF MONORAIL & HOISTS-->CONSTRUCTION-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-03-20 09:00 | 2021-09-15 18:00 | 2021-02-10 09:00 | 2021-08-08 23:59 | [6 empty] | 0 | 0 | [15 empty] | 2.2217 | 0.040366 | 3.97 | Plan & Actual | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5598 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020155
3113 | Task(Task)-->C (Construction) | SHEETING WORKS |  | 1.24.3 | SHEETING WORKS-->CONSTRUCTION-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-05-30 | 2021-09-26 23:59 | 2021-04-22 09:00 | 2021-08-19 18:00 | [6 empty] | 0 | 0 | [15 empty] | 27.7184 | 0.50362 | 49.53 | Plan & Actual | Quantity | Square Meter | 0 | 0 | 0 | 0 | 0 | 0 | 28436 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5603 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020156
3114 | Task(Task)-->C (Construction) | CCTV SYSTEM |  | 1.24.3 | CCTV SYSTEM-->CONSTRUCTION-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-04-01 09:00 | 2021-05-30 23:59 | 2021-10-12 09:00 | 2021-12-10 18:00 | [6 empty] | 0 | 0 | [15 empty] | 1.7125 | 0.031114 | 3.06 | Plan & Actual | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5245 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020157
3115 | Task(Task)-->C (Construction) | PA SYSTEM |  | 1.24.3 | PA SYSTEM-->CONSTRUCTION-->COMMON FOR ALL AREA-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-04-01 09:00 | 2021-05-30 23:59 | 2021-10-26 09:00 | 2021-12-24 18:00 | [6 empty] | 0 | 0 | [15 empty] | 1.455 | 0.026436 | 2.6 | Plan & Actual | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5246 | 0 | 3 | Low | [7 empty] | 0 | 0 | [246 empty] | 1020158
3116 | Task(Task)-->C (Construction) | TRAIL OPERATION AND COMPLETION OF FACILITIES |  | 1 | TRAIL OPERATION AND COMPLETION OF FACILITIES-->NTPC's CHP KERENDARI | Unscheduled | No | No | 2021-09-14 09:00 | 2021-09-27 18:00 | 2022-05-07 09:00 | 2022-05-20 18:00 | [6 empty] | 0 | 0 | [15 empty] | 0.015659 | 0.015659 | 1.54 | Plan & Actual | Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No | 5606 | 0 | 1 | High | [7 empty] | 0 | 0 | [246 empty] | 1020159
3117 | Task(Task)-->E (Engineering) | HGTU OF PIPE CONV FOR PC 1A/1B & PC 2A/2B : DESIGN CALCULATION FOR SUPER STRUCTURE |  |  | HGTU OF PIPE CONV FOR PC 1A/1B & PC 2A/2B : DESIGN CALCULATION FOR SUPER STRUCTURE | Completed | No | No | [6 empty] | 2020-10-08 14:03 | 2020-10-09 20:10 |  |  | 0 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-DC-0047 |  | 2020-09-30 16:08 | 7012-155-PVC-U-139 | [7 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 0 | Low | [7 empty] | 0 | 0 | [246 empty] | 10105066
3118 | Task(Task)-->E (Engineering) | HGTU OF PIPE CONV FOR PC 1A/1B & PC 2A/2B : DESIGN CALCULATION FOR SUB STRUCTURE |  |  | HGTU OF PIPE CONV FOR PC 1A/1B & PC 2A/2B : DESIGN CALCULATION FOR SUB STRUCTURE | Completed | No | No | [6 empty] | 2020-10-08 14:03 | 2020-10-28 20:42 |  |  | 0 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-DC-0048 |  | 2020-09-30 16:08 | 7012-155-PVC-U-140 | [7 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 0 | Low | [7 empty] | 0 | 0 | [246 empty] | 10105067
3119 | Task(Task)-->E (Engineering) | PIPE CONV PC 1A/1B : (TRANSITION ZONE) : DESIGN CALCULATION FOR SUPER STRUCTURE |  |  | PIPE CONV PC 1A/1B : (TRANSITION ZONE) : DESIGN CALCULATION FOR SUPER STRUCTURE | Unscheduled | No | No | [6 empty] | 2020-10-08 14:03 |  |  |  | 0 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-DC-0049 |  | 2020-09-30 16:08 | 7012-155-PVC-U-141 | [7 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 0 | Low | [7 empty] | 0 | 0 | [246 empty] | 10105068
3120 | Task(Task)-->E (Engineering) | PIPE CONV PC 2A/2B : (TRANSITION ZONE) : DESIGN CALCULATION FOR SUPER STRUCTURE |  |  | PIPE CONV PC 2A/2B : (TRANSITION ZONE) : DESIGN CALCULATION FOR SUPER STRUCTURE | Unscheduled | No | No | [6 empty] | 2020-10-08 14:03 |  |  |  | 0 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-DC-0050 |  | 2020-09-30 16:08 | 7012-155-PVC-U-142 | [7 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 0 | Low | [7 empty] | 0 | 0 | [246 empty] | 10105069
3121 | Task(Task)-->E (Engineering) | HGTU OF PIPE CONV FOR PC 1A/1B : GA & RC DETAIL OF FOUNDATION |  |  | HGTU OF PIPE CONV FOR PC 1A/1B : GA & RC DETAIL OF FOUNDATION | Unscheduled | No | No | [6 empty] | 2020-10-31 14:43 |  |  |  | 0 | 0 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-NR-0050 |  | 2020-10-31 11:13 | 7012-155-PVC-C-143 | [7 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 0 | Low | [7 empty] | 0 | 0 | [246 empty] | 10113256
3122 | Task(Task)-->E (Engineering) | HGTU OF PIPE CONV FOR PC 2A/2B : GA & RC DETAIL OF FOUNDATION |  |  | HGTU OF PIPE CONV FOR PC 2A/2B : GA & RC DETAIL OF FOUNDATION | Completed | No | No | [6 empty] | 2020-10-31 14:45 | 2020-11-03 22:48 |  |  | 0 | 100 |  |  |  | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | O19133 -C-BM-CS-NR-0051 |  | 2020-10-31 11:13 | 7012-155-PVC-C-144 | [7 empty] | 0 | 0 | 0 | Plan & Actual | Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | No | No |  | 0 | 0 | Low | [7 empty] | 0 | 0 | [246 empty] | 10113257

## LOVSheet (hidden)
|  |  |  | 101000 |  |  |  |  | -330 | India Standard Time
Task(Task)-->C (Construction) | 1 | V0008223 | Documents(Documents)-->CC (Client Comments) | Customer | BHEL(BHARAT HEAVY ELECTRICS LIMITED) | A | CLEARANCE WORKFLOW | Engineering | 101 | BD-Standard | ABHIJITG(Abhijit Ghosh) | For Approval | Excavation | Construction-Civil | A - Architecture | DCP 1 | B - Basic Engineering /General Notes/Standard drawings | CEC | Calculation | 001 - Plant General Engineering | Offers Evaluated | A0 | C & A TRADE ASSOCIATES PRIVATE LIMITED | Cubic Meters
Task(Task)-->E (Engineering) | 1.10 | VCA00947 | Documents(Documents)-->CORRESPONDENCE (Correspondence)-->MAILS (Mails) | Internal | Buxar(Buxar) | I | ITP WORKFLOW | Internal | 102 | BID DOCUMENT | ABHIKMAITRA(Abhik Maitra) | As Build | Installation | Construction-Fabrication | C - Civil | DCP 2 | D - Detail Engineering drawings / documents | L&T | D | 008 - Power Generation | RFQ Floated | A1 | SREE GANESH CORPORATION | Metric Tonnes
Task(Task)-->G (General) | 1.10.1 | VCA00866 | Documents(Documents)-->EXT (External)-->1(Civil & Structural) | Other Unit | BUYER(BUYER) | R | Unguided Workflow | PR STANDARD | 1013 | CLEARANCE WORKFLOW | ABISHEK_GUPTA(Abishek Gupta) | Good for Construction | PCC |  | F - Fire Fighting | DCP 3 | Fabrication | SYSTRA | Electrical SLD | 045 - STP/Water Treatment |  | A2 | S S SOLUTION | Running Meters
Task(Task)-->P (Procurement) | 1.10.1.1 | AVSRUPESH | Documents(Documents)-->EXT (External)-->2(Mechanical) | Vendor | CIL(Coal India Limited) |  |  | Vendor | 1012 | Elihaad- Client Submission WF | ACHOUDHURY(Abhijit Choudhury) | For information | RCC |  | H - Material Handling and Equipment | L&T | G - General Arrangement drawings |  | No IDC | 080 - Water Media & Utility systems |  | A3 | TRISITA ENGINEERING LLP
| 1.10.1.2 | AALIBANGBANG | Documents(Documents)-->EXT (External)-->3(Electrical) |  | CIV(Civil / Structural / Geotechnica) |  |  |  | 103 | Etihad JV interface check | ADMIN(ADMINISTRATOR) | Preliminary |  |  | I - Instrumentation & Automation | L&T/SITE | Internal Document |  | P&ID | 100 - Conveying System |  | A4 | BHARTI AIRTEL LIMITED ( BHUBHANESWAR )
| 1.10.1.3 | V0056434 | Documents(Documents)-->EXT (External)-->4(Instrumentation & Control) |  | CMPC(CMPC) |  |  |  | 104 | External | AFOUZDER(Ashim Fouzder) | For Tender Purpose |  |  | M - Mechanical Process & Equipment | L&T/V | K - Calculation / Document |  |  | 250 - Fume Extraction & Plant Dedusting |  |  | DEEPAK TRAVELS
| 1.10.1.4 | VCA00871 | Documents(Documents)-->EXT (External)-->5(Equipment Design) |  | DC(Document Controller) |  |  |  | 105 | External-Standard | AGR(Avirup Ghosh Roy) |  |  |  | P - Pollution Control | L&T/V ACE | PR Document |  |  | 255 - Cranes and hoists |  |  | AVENTURE INFRA
| 1.10.2 | V0054997 | Documents(Documents)-->EXT (External)-->6(General) |  | ELE(Electrical) |  |  |  | 106 | Inspection Call Workflow | AHG(Ankhi Ghosh Datta) |  |  |  | Q - HVAC | L&T/V AL | V - Vendor Document / drawing |  |  | 300 - Laboratory Facilities |  |  | RANJEET SINGH
| 1.10.2.1 | ABESH | Documents(Documents)-->I (Internal)-->C (Civil & Structural) |  | ETIHAAD RAIL(ETIHAAD RAIL) |  |  |  | 107 | Internal Standard | AIS(Arijit Saha) |  |  |  | S - Structural | L&T/V ATC | Z - 3D Plant modelling |  |  | 450 - Gold Process |  |  | SUMANT KUMAR SAHA
| 1.10.2.2 | KALSI | Documents(Documents)-->I (Internal)-->E (Electrical) |  | FCC(Formwork) |  |  |  | 108 | ITP WORKFLOW | AJITABH(Ajitabh Shah) |  |  |  | U - Water Media & Utility System | L&T/V NALCO |  |  |  | 501 - Workshop & Store Facilities |  |  | SURESH CHAND JAIN
| 1.10.2.3 | ACHOUDHURY | Documents(Documents)-->I (Internal)-->EQ (Equipment Design) |  | HIL(Hindalco Industries Limited) |  |  |  | 109 | Maden Workflow | AKHANDELWAL(Ankit Khandelwal) |  |  |  |  | L&T/V PAHARPUR |  |  |  | 900 - General/Common Services |  |  | RAJENDRA PRASAD
| 1.10.2.4 | ABHIJITDAS | Documents(Documents)-->I (Internal)-->I (Instrumentation & Control) |  | HR(Human Resources) |  |  |  | 1010 | PO-MRN | AKLANKJAIN(Aklank Kumar Jain) |  |  |  |  | L&T/V SANDVIK |  |  |  | 910 - Plant Infrastructure |  |  | PANKAJ KUMAR SAHA
| 1.10.2.5 | ABHIJITG | Documents(Documents)-->I (Internal)-->M (Mechanical) |  | HZL(Hindutan Zinc Limited) |  |  |  |  | PR FINAL STANDARD | AMITPARASHAR(Amit Parashar) |  |  |  |  | L&T/V SIEMENS |  |  |  | 950 - Plant Electrics |  |  | RAM EKBAL SINGH
| 1.10.2.6 | ABHIJITPAL | Documents(Documents)-->IC (Inspection Call) |  | I&C(Instrumentation and Control) |  |  |  |  | Price Submission Workflow | AMITTHAPAR(AMIT THAPAR) |  |  |  |  | L&T/V WARTSILA |  |  |  | 980 - Plant Instrumentation & Automation |  |  | NAYAMAT ALI
| 1.10.3 | SANPUI | Documents(Documents)-->ITEM (Item List) |  | JSW(JINDAL STEEL WORKS) |  |  |  |  | PR-PO STANDARD | AMLANPRATIK(Amlan Pratik Das) |  |  |  |  | L&T/V WETICO | [6 empty] | MD TASLIM
| 1.10.3.1 | ABHIKGHOSH | Documents(Documents)-->MAILS (Mails) |  | KIOCL(KIOCL LIMITED,BANGALORE) |  |  |  |  | T&C Workflow | ANS(Anurag Sharan) |  |  |  |  | OTE | [6 empty] | ASHMI ENGINEERING AND ADVISORY SERVICES PRIVATE LIMITED
| 1.10.3.2 | ABHIKMAITRA | Documents(Documents)-->MANPOWER (Manpower) |  | L&T HYDROCARBON(L&T Hydrocarbon Engineering Limited) |  |  |  |  | Technical Document WF | ANUBHAB(Anubhab Mukhopadhyay) |  |  |  |  | OTE/L&T | [6 empty] | MD RIYAZ MIYA
| 1.10.3.3 | ABHIMANYUDAS | Documents(Documents)-->PO (Purchase Order) |  | L&T MHPS(L&T MHPS) |  |  |  |  | Vendor Drawings | ANUPAMKUMAR(ANUPAM KUMAR) |  |  |  |  | VOID | [6 empty] | HASMAT ALI
| 1.10.3.4 | ABHIPRIYA2020 | Documents(Documents)-->PR (Purchase Requests)-->1(Civil & Structural) |  | MA'ADEN(MA'ADEN) | [5 empty] | ANUPAMM(Anupam Mitra) | [11 empty] | KPMG INDIA SERVICES LLP
| 1.11 | ABW | Documents(Documents)-->PR (Purchase Requests)-->2(Mechanical) |  | MECH(Mechanical & Utility) | [5 empty] | APURBASINGH(Apurba Singh) | [11 empty] | MD DAUD
| 1.11.1 | ABHII | Documents(Documents)-->PR (Purchase Requests)-->3(Electrical) |  | MMH(MMH) | [5 empty] | ARUNAVABALL(Arunava Ball) | [11 empty] | SURVEILLANCE SECURITY PVT. LTD.
| 1.11.1.1 | APL | Documents(Documents)-->PR (Purchase Requests)-->4(Instrumentation & Control) |  | NCL(NORTHEN COALFIELDS LIMITED) | [5 empty] | ARUNMAJI(ARUN KUMAR MAJI)
| 1.11.1.2 | ABHSHK | Documents(Documents)-->PR (Purchase Requests)-->5(Equipment Design) |  | NTPC(NATIONAL THERMAL POWER CORPORATION LTD) | [5 empty] | ASHISC(Ashis Chatterjee)
| 1.11.1.3 | ATS2020 | Documents(Documents)-->PR (Purchase Requests)-->6(General) |  | PH(Project Head) | [5 empty] | BARUNDEV(Barundev Lahiri)
| 1.11.1.4 | ABISHEK_GUPTA | Documents(Documents)-->PRICE (Price Submission) |  | QA/QC(Quality) | [5 empty] | BASANT(Basant Kumar Mahto)
| 1.11.2 | VQA00158 | Documents(Documents)-->S (Services)-->CMPC (CMPC) |  | RINL(Rashtriya Ispat Nigam Limited) | [5 empty] | BCH(Biswapriya Chakraborti)
| 1.11.2.1 | ADITYASHIV | Documents(Documents)-->S (Services)-->FCC (FCC) |  | Sample Vendor(Sample Vendor) | [5 empty] | BGREDDY(Gangadhara Reddy B)
| 1.11.2.2 | ADMIN | Documents(Documents)-->T&C (Terms and Condition) |  | Tech. Provider(Technology Provider) | [5 empty] | BHAWAL(P K Bhowal)
| 1.11.2.3 | V0014530 | Documents(Documents)-->TD (Tender Documents) |  | V0071399(Machino Spares) | [5 empty] | BSKM(B.S.K.Murugananthan)
| 1.11.2.4 | V8001276 | Documents(Documents)-->TE (Technical Evaluation Documents) |  | VENDORS(Vendors) | [5 empty] | CDK(Chetan Khodke)
| 1.11.2.5 | V0054519 | Documents(Documents)-->V (Vendor Drawings)-->ELE (Electrical) |  | VQH00015(HMTC Engineering Company ( Kolkata ) Private Limited) | [5 empty] | CHIRANJITSAHA(Chiranjit Saha)
| 1.11.2.6 | VBA00709 | Documents(Documents)-->V (Vendor Drawings)-->G (General) |  | VQK00063(Krishna Gears) | [5 empty] | CPD(Chandra Prakash Dewangan)
| 1.11.3 | V0049873 | Documents(Documents)-->V (Vendor Drawings)-->I&A (Instrumentation & Automation) |  | WGG(Wrench Guest Group) | [5 empty] | DASDEB(Debasis Das)
| 1.11.3.1 | AIGUA | Documents(Documents)-->V (Vendor Drawings)-->MECH (Mechanical) |  | WORLEY(Worley Design Consultant) | [5 empty] | DDU(Debashis Dutta)
| 1.11.3.2 | AIRBOOST | [8 empty] | DEBASISHGHOSH(Debasish Ghosh)
| 1.11.3.3 | AJITKHATUA | [8 empty] | DEBOSREE(Debosree Roy)
| 1.11.3.6 | AJITABH | [8 empty] | DESHMUKH(Sugandh Deshmukh)
| 1.12 | AJMALP | [8 empty] | DJY(Deepjoy Ghosh)
| 1.12.1 | NILAKASH | [8 empty] | DKUMARPANDEY(Dharmendra Kumar Pandey)
| 1.12.1.1 | AKLANKJAIN | [8 empty] | DMANNA(DIBYENDU MANNA)
| 1.12.1.2 | VMT00924 | [8 empty] | DOKA-CCRO(PRADIP HAIT)
| 1.12.1.3 | AMALSINHA | [8 empty] | GANESHK(K.Ganesh)
| 1.12.1.4 | AMARKR | [8 empty] | GANESHMAITI(GANESH MAITI)
| 1.12.2 | AMBARISHS | [8 empty] | GGKRAJU(Gottemukkala Gopala Krishnam Raju)
| 1.12.2.1 | AMEEYARANJAN | [8 empty] | G-SIVASAI(Goriparthi Siva Sai Krishna)
| 1.12.2.2 | AADH | [8 empty] | GSR(G SRINIVAS)
| 1.12.2.3 | AID | [8 empty] | GSRK(G.Srirama Kishore)
| 1.12.2.4 | DASAMIT | [8 empty] | HIMANSU(Himansu Kumar Das)
| 1.12.2.5 | AMITKOLEY | [8 empty] | IMUKHERJEE(Indraneel Mukherjee)
| 1.12.2.6 | AMITKDUTTA | [8 empty] | INDIRA(Indira Chatterjee)
| 1.12.3 | AMITPARASHAR | [8 empty] | JANESHWOR(Naorem Janeshwor Singh)
| 1.12.3.1 | AMITSAHASAHA | [8 empty] | JAYATI(JAYATI SARKAR)
| 1.12.3.2 | ASW | [8 empty] | JKN(JAYANTA KUMAR NANDI)
| 1.12.3.4 | AMITTHAPAR | [8 empty] | JMANNA(Jaydev Manna)
| 1.13 | AMITAVAROY | [8 empty] | JYMI(Joy Munshi)
| 1.13.1 | AMLANBASU | [8 empty] | KABYA(Kabya Bhattacharya)
| 1.13.1.1 | AMLANPRATIK | [8 empty] | KALSI(ABHIJEET KALSI)
| 1.13.1.2 | V0001529 | [8 empty] | KAUSHIKC(kaushikc)
| 1.13.2 | AMRITAP | [8 empty] | KUMARESAN(T.Kumaresan)
| 1.13.2.1 | ASARKHEL | [8 empty] | KUMARTARUN(Tarun Kumar)
| 1.13.2.2 | ANIMESH | [8 empty] | MAIDUL(Sk. Maidul Ali)
| 1.13.2.3 | ANIMESHSANTRA | [8 empty] | MANASKHARA(Manas Kumar Khara)
| 1.13.2.4 | ADEY | [8 empty] | MANASPATRA(Manas Patra)
| 1.13.2.5 | ANG | [8 empty] | MANIKC(Manik Chakraborty)
| 1.13.2.6 | ANISHJAGGI | [8 empty] | MANU(Manohar Reddy)
| 1.13.3 | ANISHMDR | [8 empty] | MDALI(Md Ali)
| 1.13.3.1 | ANKHIDEY | [8 empty] | MFS(Md Feradul Shaikh)
| 1.13.3.2 | AHG | [8 empty] | MJM(Mrityunjay Mishra)
| 1.13.3.3 | AKHANDELWAL | [8 empty] | MMJUDDIN(Md. Merajuddin)
| 1.14 | ANNAPURNA | [8 empty] | NIRMALYA(Nirmalya Burman)
| 1.14.1 | ANTARA | [8 empty] | NKAMLE(Niharendu Kamle)
| 1.14.1.1 | V0005977 | [8 empty] | NSARAVANA(Saravanakumar Natarajan)
| 1.14.1.2 | ANUBHAB | [8 empty] | NTPC(NTPC)
| 1.14.2 | ANUPNASKAR | [8 empty] | PALASHIS(ASHIS PAL)
| 1.14.2.1 | VAA00566 | [8 empty] | PAMPIBISWAS(Pampi Biswas)
| 1.14.2.2 | ANUPAMKUMAR | [8 empty] | PAYEL(Payel Bhowmick)
| 1.14.2.3 | ANUPAMM | [8 empty] | PBAGCHI(Prosenjit Bagchi)
| 1.14.2.4 | ANS | [8 empty] | PKPAL(Prabir Kumar Pal)
| 1.14.2.5 | AUD | [8 empty] | PRABINMOHTA(Prabin Mohta)
| 1.14.2.6 | APURBASINGH | [8 empty] | PRADEEP-KUMAR(BODIGE PRADEEP KUMAR)
| 1.14.3 | ARABINDAB | [8 empty] | PROSENJIT(Prosenjit Sarker)
| 1.14.3.1 | ARABINDA.GOUDA | [8 empty] | PSAHA(Parag Saha)
| 1.14.3.2 | ARADHANASEN | [8 empty] | PSOM(Paramartha Som)
| 1.14.3.3 | V0057975 | [8 empty] | RAM.KISHORE(Ram Kishore)
| 1.15 | ARGHYARC | [8 empty] | RAMPRASAD(Ram Prasad Roy)
| 1.15.1 | ARIJITNANDY | [8 empty] | RANJITGHOSH(RANJIT GHOSH)
| 1.15.1.1 | AIS | [8 empty] | RKNIT(Ramesh Kumar)
| 1.15.1.2 | ARINDAMBASAK | [8 empty] | ROYSHIBASHIS(Shibashis Roy)
| 1.15.2 | AUB | [8 empty] | RSINI(Srinivasan R)
| 1.15.2.1 | APRODHAN | [8 empty] | RSK(R.Suresh Kumar)
| 1.15.2.2 | ARINDAM | [8 empty] | RUPANMITRA(Rupan Chandra Mitra)
| 1.15.2.3 | VQA00024 | [8 empty] | SAA(Shaik Abdul Afeej)
| 1.15.2.4 | ARNABDUTTA | [8 empty] | SADHIKARY(SUBRATA ADHIKARY)
| 1.15.2.5 | ARPITAKHAN | [8 empty] | SAMB(SAMARESH BHATTACHARYA)
| 1.15.2.6 | ARUNBHORE | [8 empty] | SAMBITBISWAS(Sambit Biswas)
| 1.15.3 | ARUNGAYEN | [8 empty] | SAMIR(SAMIR BHATTACHARYYA)
| 1.15.3.1 | ARUNMAJI | [8 empty] | SAMIRON(Samiron Mukherjee)
| 1.15.3.2 | ARUN.MISHRA | [8 empty] | SANDIPANB(SANDIPAN BHAR)
| 1.15.3.3 | ARUNVERMA | [8 empty] | SANDIPBASAK(Sandip Basak)
| 1.16 | ARUNAVABALL | [8 empty] | SANDIPDEY(Sandip Dey)
| 1.16.1 | ARUNAVAS | [8 empty] | SANJAYKSAHA(Sanjay Kumar Saha)
| 1.16.1.1 | ARC | [8 empty] | SANKAR(Sankara Rao Boddu)
| 1.16.1.2 | AFOUZDER | [8 empty] | SANPUI(Abhijit Sanpui)
| 1.16.1.3 | AKROY | [8 empty] | SANTOSHANAND(Santosh Anand)
| 1.16.2 | ASHISC | [8 empty] | SASWATA(Saswata Bhattacharya)
| 1.16.2.1 | PALASHIS | [8 empty] | SATYAGV(Satyanarayana GV)
| 1.16.2.2 | ASHOKGUPTA | [8 empty] | SCHANDRU(Chandrasekar Shanmugam)
| 1.16.2.3 | ASHOKE | [8 empty] | SGL(Sutanu Ganguly)
| 1.16.2.4 | ASHOK.SINGHANIA | [8 empty] | SHASHIBKUMAR(Shashi Bhushan Kumar)
| 1.16.2.5 | ASASMAL | [8 empty] | SHYAMKUMARS(Shyam Kumar)
| 1.16.2.6 | ASIT | [8 empty] | SIDDHARTHAPAL(Siddhartha Pal)
| 1.16.3 | ASPIRE2020 | [8 empty] | SOMESHGHOSH(Somesh Ghosh)
| 1.16.3.1 | ATANU.GHOSH | [8 empty] | SOMRAJ(Somraj Sen)
| 1.16.3.2 | ATANUGHOSH | [8 empty] | SOUMOMANDAL(Soumo Mandal)
| 1.16.3.3 | V8001257 | [8 empty] | SOURAV(Sourav Kumar Singh)
| 1.17 | AVG | [8 empty] | SOURAVMUKHERJEE(Sourav Mukherjee)
| 1.17.1 | AMARICK | [8 empty] | SPAIKARA(Samaresh Paikara)
| 1.17.1.1 | AVIK | [8 empty] | SRIKUMARAN(Sri Kumaran K S)
| 1.17.1.2 | AGR | [8 empty] | SRINATHC(Srinath C)
| 1.17.1.3 | ACH | [8 empty] | SRU(Sanghamitra Rout)
| 1.17.2 | AYB | [8 empty] | SSIKDAR(SARABINDU SIKDAR)
| 1.17.2.1 | AZGARH | [8 empty] | SUBHRA2008(Subhrajyoti Ghosh)
| 1.17.2.2 | BSKM | [8 empty] | SUBHRAJYOTI(Subhrajyoti Banerjee)
| 1.17.2.3 | VCB00489 | [8 empty] | SUBM(Subarna Mazumdar)
| 1.17.2.4 | BAPAN | [8 empty] | SUJ(Sujata Chatterjee)
| 1.17.2.5 | BARATH | [8 empty] | SUMAN.K(SUMAN KUNDU)
| 1.17.2.6 | BKB | [8 empty] | SUMITG(Sumit Gupta)
| 1.17.3 | BARUNC | [8 empty] | SURESHBAHADUR(Suresh Bahadur Singh)
| 1.17.3.1 | BARUNDEV | [8 empty] | SURYAKUMAR.B(SURYA KUMAR BEHERA)
| 1.17.3.2 | BASANT | [8 empty] | SUSANTAKHAN(Susanta Kumar Khan)
| 1.17.3.3 | BK_KUILA | [8 empty] | SWAMYSG(Rayi Swamy)
| 1.18 | V8001057 | [8 empty] | SWAPANB(SWAPAN BERA)
| 1.18.1 | VCB00293 | [8 empty] | SYH(Soumya Bhattacharya)
| 1.18.1.1 | V0018742 | [8 empty] | TAMAGHANA(Tamaghana Bose)
| 1.18.1.2 | VBB00290 | [8 empty] | TAMALSENGUPTA(Tamal Sengupta)
| 1.18.1.3 | DASBHASKAR | [8 empty] | TB(Tanmoy Biswas)
| 1.18.2 | YADADRI | [8 empty] | TESTVENDOR(Test Vendor)
| 1.18.2.1 | BTR | [8 empty] | UJJALM(UJJALKUMAR MAITY)
| 1.18.2.2 | V0002938 | [8 empty] | UTTAMPARIA(Uttam Paria)
| 1.18.2.3 | BIJETREEB | [8 empty] | VINODKINTALI(Kintali Vinod)
| 1.18.2.4 | BHI | [8 empty] | VRP(Varun Parihari)
| 1.18.2.5 | BILAS
| 1.18.2.6 | BINU
| 1.18.3 | BIPIN
| 1.18.3.1 | BIPINKUMAR
| 1.18.3.2 | BIPLABMUNSHI
| 1.18.3.3 | BIPLABPATRA
| 1.19 | BSHEE
| 1.19.1 | BSRAY
| 1.19.1.1 | BBIPUL
| 1.19.1.2 | BDATTA
| 1.19.2 | BSABUI
| 1.19.2.1 | BCH
| 1.19.2.2 | V0077255
| 1.19.2.3 | PRADEEP-KUMAR
| 1.19.2.4 | V0019600
| 1.19.2.5 | V9001730
| 1.19.2.6 | BRAHMAB
| 1.19.3 | BUXAR
| 1.19.3.1 | V0020314
| 1.19.3.2 | V8001252
| 1.19.3.3 | V0013771
| 1.2 | CDS
| 1.20 | CDINDA
| 1.20.1 | CPAIRA
| 1.20.1.1 | CPD
| 1.20.1.2 | SHEKHARCHANDRA
| 1.20.2 | TCKREDDY
| 1.20.2.1 | SCHANDRU
| 1.20.2.2 | V0012538
| 1.20.2.3 | CDK
| 1.20.2.4 | CHINNI
| 1.20.2.5 | CHIRANJITSAHA
| 1.20.2.6 | CHRISTIANK
| 1.20.3 | VBC00250O
| 1.20.3.1 | DOC.SHJ
| 1.20.3.2 | VCC00880
| 1.21 | VMC00862
| 1.21.1 | VCC00872
| 1.21.1.1 | DVP
| 1.21.1.2 | DALVEERPANESAR
| 1.21.2 | DRAGHU
| 1.21.2.1 | DPATNAIK
| 1.21.2.2 | DDU
| 1.21.2.3 | DCH
| 1.21.2.4 | DASDEB
| 1.21.2.5 | DEBASISHGHOSH
| 1.21.2.6 | DEBASISHH
| 1.21.3 | DEBAYANKAR
| 1.21.3.1 | DEBIPRASADGHOSH
| 1.21.3.2 | DEBJIT.MUKHERJEE
| 1.21.3.3 | DEBOSREE
| 1.22 | DBC
| 1.22.1 | DPATHANIA
| 1.22.1.1 | DJY
| 1.22.1.2 | VCD00167
| 1.22.1.3 | V0000367
| 1.22.2 | V0022166
| 1.22.2.1 | VLD00246
| 1.22.2.2 | VAD00229
| 1.22.2.3 | DKUMARPANDEY
| 1.22.2.4 | DHIMANM
| 1.22.2.5 | DPURKAIT
| 1.22.2.6 | DHRUBAC
| 1.22.3 | DIAMONDFABRICAT
| 1.23 | DMANNA
| 1.23.1 | DILEEPUNNI
| 1.23.1.1 | DILIPSARKAR
| 1.23.1.2 | DINESHM
| 1.23.1.3 | DINESHMONI
| 1.23.2 | BERAD
| 1.23.2.1 | DUDHICHUA
| 1.23.2.2 | V0014391
| 1.23.2.3 | V0054587
| 1.23.2.4 | VQE00014
| 1.23.2.5 | V0024588
| 1.23.2.6 | VQE00050
| 1.23.3 | VQE00076
| 1.24 | VME00858
| 1.24.1 | VCE00155
| 1.24.1.1 | VCE00198
| 1.24.1.2 | VME00891
| 1.24.1.3 | V0068269
| 1.24.1.4 | VEE00006
| 1.24.1.5 | VME00862
| 1.24.2 | VQE00054
| 1.24.2.1 | VCE00214
| 1.24.2.2 | EMK
| 1.24.2.3 | ETIHAAD
| 1.24.2.4 | VCE00203
| 1.24.2.5 | V0002844
| 1.24.2.6 | V0019347
| 1.24.2.7 | V0053484
| 1.24.3 | FELUWA
| 1.3 | V0068769
| 1.3.1 | FIROJKHAN
| 1.3.1.1 | FLOWLINK
| 1.3.1.2 | VBF00103
| 1.3.1.3 | V0018548
| 1.3.1.4 | VHF00767
| 1.3.2 | VCF00148
| 1.3.2.1 | GSR
| 1.3.2.2 | VMG00802
| 1.3.2.3 | GSRK
| 1.3.2.4 | GANESHMAITI
| 1.3.2.5 | GAN
| 1.3.2.6 | GANESHGKR
| 1.3.3 | BGREDDY
| 1.3.3.1 | GAUTAMAGARWAL
| 1.3.3.2 | JASHU
| 1.3.3.3 | SINGHGHANSHYAM
| 1.3.3.5 | V0072229
| 1.4 | GOBINDAG
| 1.4.1 | V0069846
| 1.4.1.1 | VDG00170
| 1.4.1.2 | V0050877
| 1.4.1.3 | GOPINATHC
| 1.4.1.4 | GBH
| 1.4.2 | G-SIVASAI
| 1.4.2.1 | GGKRAJU
| 1.4.2.2 | GGO
| 1.4.2.3 | GOUTAM.ROY
| 1.4.2.4 | GOUTAMS
| 1.4.2.5 | V0019284
| 1.4.2.6 | VQG00044
| 1.4.3 | GMU
| 1.4.3.1 | BHANUG
| 1.4.3.2 | HARERAM
| 1.4.3.3 | GRHK
| 1.4.3.4 | V0010071
| 1.5 | VCF00109
| 1.5.1 | HASANSK
| 1.5.1.1 | VLH00864
| 1.5.1.2 | HSARDER
| 1.5.1.3 | VCH00151
| 1.5.1.4 | VLH00828
| 1.5.2 | V0064424
| 1.5.2.1 | V0053842
| 1.5.2.2 | VMH00163
| 1.5.2.3 | HIMANSU
| 1.5.2.4 | HIMANSUBARAL
| 1.5.2.5 | VAH00143
| 1.5.2.6 | HITECHMETAL
| 1.5.3 | V0010114
| 1.5.3.1 | VQH00015
| 1.5.3.2 | V0020739
| 1.5.3.3 | V0019825
| 1.5.3.5 | VBI00160
| 1.6 | INDCON
| 1.6.1 | VBI00131
| 1.6.1.1 | INDIRA
| 1.6.1.2 | IRH
| 1.6.1.3 | IMUKHERJEE
| 1.6.1.4 | C.INDRANIL
| 1.6.2 | VHI00075
| 1.6.2.1 | INGERSOLL
| 1.6.2.2 | INTERVALVE
| 1.6.2.3 | VQI00072
| 1.6.2.4 | V0019880
| 1.6.2.5 | JYOTI.DAS
| 1.6.2.6 | JAIGARH
| 1.6.3 | VLJ00772
| 1.6.3.1 | JJO
| 1.6.3.2 | JKMONDAL
| 1.6.3.3 | JKN
| 1.6.3.4 | VBJ00175
| 1.7 | JAYATI
| 1.7.1 | JMANNA
| 1.7.1.1 | JAYDIPC
| 1.7.1.2 | JAYDIPDAS
| 1.7.1.3 | JEEVITESH
| 1.7.1.4 | JYMI
| 1.7.2 | JOYDEEP
| 1.7.2.1 | JUSTINTHOMAS
| 1.7.2.2 | JPJ
| 1.7.2.3 | JV1
| 1.7.2.4 | JYOTIRBANMALLICK
| 1.7.2.5 | GANESHK
| 1.7.2.6 | KNSEN
| 1.7.3 | KABERI
| 1.7.3.1 | KABYA
| 1.7.3.2 | V0047110
| 1.7.3.3 | KAJALC
| 1.7.3.5 | VBK00356
| 1.8 | VQK00055
| 1.8.1 | VCK00400
| 1.8.1.1 | KAMALP
| 1.8.1.2 | VAK00912
| 1.8.1.3 | HKANANI
| 1.8.1.4 | VCK00431
| 1.8.2 | VBK00344
| 1.8.2.1 | KARTHIPL
| 1.8.2.2 | KARTHI.K
| 1.8.2.3 | KARTHIS
| 1.8.2.4 | V0056038
| 1.8.2.5 | KDU
| 1.8.2.6 | KAUSHIKG
| 1.8.3 | K.SARKAR
| 1.8.3.1 | KAUSHIKC
| 1.8.3.2 | V0020611
| 1.8.3.3 | VCK00218
| 1.8.3.4 | KERENDARI
| 1.9 | KHARAVEL
| 1.9.1 | V9002542
| 1.9.1.1 | KHURJA
| 1.9.1.2 | VINODKINTALI
| 1.9.1.3 | V0001608
| 1.9.1.4 | VLK00901
| 1.9.2 | KIKUSH
| 1.9.2.1 | VCK00224
| 1.9.2.2 | V0050684
| 1.9.2.3 | KOUSHIKGANGULY
| 1.9.2.4 | KOUSIKB
| 1.9.2.5 | VQK00063
| 1.9.2.6 | KRISHNENDUC
| 1.9.3 | KULDEEPSHARMA
| 1.9.3.1 | KUNALRAY
| 1.9.3.2 | KUTUB
| 1.9.3.3 | VCL00862
| 1.9.3.6 | LNTEWL
LNTKBL2020
V0053017
LAYEE
VBL00151
LIJESH
V9002691
VDM00622
V0028222
MAADEN
MAADENMMGP
V0071399
VQM00099
MAHAVEER
MAHESHKOMMURU
MAHESH.SONKUSARE
MAKLESUR
MANASKHARA
MANASPATRA
MANIKC
MANISHA
MANU
MANOJ
MANOJBERA
MLDAS
MANOJTIKADAR
V0014929
VMM01153
RESHMAMATCHA
MATTA
MCNALLY
MDALI
MFS
RIZWANM
EKRAMUL
MMJUDDIN
NAWAJ
VAM00587
V0008456
VMM00875
V0005548
VAM00648
V0057586
VCM00779
MILANM
MITAGANGULY
MITHUNMONDAL
VQM00019
V0005833
MNKR
V0016802
V0073910
MONOJG
MSG
MMITRA
MRINMOY
MJM
V0012457
MUKULM
MURARIMONDAL
NABANKURD
V0061971
V9002721
V0061185
VCN00153
JANESHWOR
NTIWARI
NASH
V0056712
NAVEEN.KUMAR1
V0075941
V0022353
V0000071
VCN00273
NKAMLE
NIKITACHAUDHARY
NILADRI
NIR
NIRMALYA
NISITH
NTPC
V0007307
VQO00002
BHAWAL
PKSINHA
PKUNDU
PAMPIBISWAS
PSAHA
PSOM
VQP00037
PARKAIRE
PMB
MISHRAPARTH
PARTHAAICH
PPP
PSB
PATRATU
PAWANKUMAR
PAYEL
VLP00874
VMP00869
VMP00864
V0010524
PML
VCP00519
VCP00372
V0061431
PRABINMOHTA
PROBIRDUTTA
PRABIRGHOSAL
PKPAL
PRADEEPS
PRADIPDEY
DOKA-CCRO
PMAJUMDAR
VBP00397
PRAKASHJIS
PRS
PGUIN
PHL
PRO
PCHATTERJEE
PRATIMGHOSH
PRAVAKAR.MALIK
PHAJARE
VAP00462
VCP00381
V8000200
PRITAMADAK
PRIYATOSHDHARA
V0061237
PROMITRAY
V0060055
PRONOBESH
PDAFADAR
PBAGCHI
PROSENJIT
VQP00015
RABINDRAKUMAR
TARKESH
RAJ.GUPTA
RSK
RABINDAS
VCR00874
RAJAD
DRAJA
RAJARSHI
PATHAKR
V0070159
RAJAT.BORAL
RAJESHM
RAJIBD
RAJIBB
RAJIBM
RAJIBSEN
KRAKESH
RAM.KISHORE
RAMPRASAD
RAMSHARMA
RKNIT
RAMESHS
RPA
RJM
RANDHIRKUMAR
RANGANATHMKR
RANJAN
RANJITGHOSH
RANJITSAHA
RASHEDAHMED
SRATHNAKUMAR
V9000506
SWAMYSG
BHARDWAJRAJAT
SULTANARAZIA
V0002633
JREPUELA
VDR00301
V0010053
JRINGEVAL
RINLVIZAG
RINTUMALLICK
RITESHK
RITESHS
RWK
V0053378
VDR00408
ROHTASHSINGH
RONGALI
RUBELDHAR
RUMELI
RUPANMITRA
SATRUJIT
SOUVIKSAHA
GURUNADH
SABYASACHIC
V0013639
V0075010
SBERA
SAIBALSAHA
SAIKATROY
SAIKATSRIMANI
SAIT
SAJALC
SALILBERA
V0061582
SAMB
MANNAS
SPAIKARA
SAMBITBISWAS
SAMBITGIRI
SAMIRANJAN
SAMIR
SAMIRON
SAMRATDEY
SANDEEP.BARIK
MSANDEEPKR
SANDEEP.MOZUMDAR
SANDHIREDDY
SANDIPBASAK
SANDIPDEY
SANDIPCHANDRA
SANDIPSARKAR
SANDIPANB
SRU
SANJAYHALDER
SANJAYKSAHA
SSU
SANJIBKMONDAL
BSANJOY
SJU
SANKARD
DASSANKAR
SANKAR
SANKHA
SANTANUBANIK
SANTIGOPALKAR
SANTOSHANAND
SSIKDAR
NSARAVANA
ASARAVANAN
SARAVANAN
SASWATA
SATHISHPSK
SATTWIKNAG
SATYAGV
VQF00025
V0010020
V0050692
SEERAT
VMS01151
VQS00105
VCS01489
SETHU
SAA
SSTHAKUR
SMALLICK
SHANTANUKHAMARU
SHAONIDAS
SHARANC
SHARMILA
SHASHANK.SHEKHAR
SHASHIBKUMAR
SHATAYU
ROYSHIBASHIS
SBT
VCS01452
V0049799
SHUB
SHYAMKUMARS
SHYENJIT
SIDDHARTHAPAL
VCS00892
SILADITYAM
SIRSHAKMAJI
SISIR.CHHETRI
SITANGSHU.ROY
V0001465
SHN
MAIDUL
IFTIKAR
VCS01447
V0001771
SMC2020
SMITASHA
SYY
SOMALI
SOMESHGHOSH
HSOMNATH
MUKHERJEES
SOR
SOMRAJ
SDUBEY
SOMYAKANTABEHERA
V0044673
SONJIT
SOUMENDATTA
SOUMEN-MALLICK
SOUMOMANDAL
SYH
SOURAV.BHOUMIK
SOURAVDAS
SOURAVDUTTA
GHOSGSOURAV
SOURAV
SOURAV.MODI
SOURAVMUDI
SOURAVMUKHERJEE
SOURAVPATRA
SOURISHSEN
SOUTRIK
SOUVIK
SOVANLAL
V0025620
VMS00853
SRIKUMARAN
SRIDAM
SBANDYO
SRINATHC
VMS01758
RSINI
SRINWANTI
V0015037
VMS00882
V0046813
SUBM
SUBHAJIT
SUBHAJITGHOSH
SUBHANKARB
SUBHASISNAYAK
BARMANS
B-SUBHENDU
SUBHENDU
SDY
SUBHRAJYOTI
SUBHRA2008
ARSUBBU
SADHIKARY
SHH
SUBRATADEY
SGAYEN
SUBRATASEN
SDM
SUDARSHAN.BEHERA
SUDEEPTANANDI
SUDIPBISWAS
SUDIPDEY
SKD
DEBNATHS
SUDIPTAPAL
SUDIPTASARKAR
DESHMUKH
CSUGATA
SUJ
SUJAY
SJW
SUJOYDEY
SUJOYDC
SUKALYANGHOSH
SUKHENDU
SUMANBANIK
SUMAN.HATI
SUMAN.K
SUMANPODDER
SUMANROY
SUMANA
SDE
SUMANTA.KM
SNASKAR
SUMITC
SUMITDAS
SUMITG
JENA
SUMITKARN
SUMITKROY
VYS00067
SUMON.MAJUMDAR
VCS00777
SUNNYCHOWDHURY
SKARMAKAR
SUPRIYOB
SAICH
SURAJITK
SURAJITPAL
SURAJIT_ROY
SURANJIT.MOHANTY
SURESHBAHADUR
SUG
SURYAKUMAR.B
SUSANTAKHAN
SUSANTAP
SUSHANTA
SUSMI
SUSMITPAUL
SUTANUBISWAS
SUTANU GANGULY
SGL
V0014340
SUVADEEP
SUVAJITGHOSH
RAKSHIT
SUVAM
SUVANKAR
SUVASISH
SUVENDUSENAPATI
SUVRADIP
SWAPANB
VCS01350
TGR
KUMARESAN
TAMAGHANA
TDM
TAMALSENGUPTA
TANIA
TANMAYDAS
TB
VQT00022
TAPAND
TKU
TSADHU
TAPASKUMAR
TKC
S.TAPAS
V0042109
KUMARTARUN
TATSATDUTTA
V0000103
VCT01044
V0059516
V0048626
TEMASMEVESSELEX
V0050386
TESTVENDOR
TEST VENDOR
V0008515
V0002843
TIRTHANKARSINHA
VLT00254
VQT00029
TRANSGIETZ
TRIDEEPC
V0050834
VCT01073
BARUATRIDIB
TUFAN
TUHINM
UDAYAN
UJJALM
UJJWALPAL
URA
V0013174
VMU00831
V0064928
V0061820
VCU00092
UNITEDENGINEERI
VBU00099
VCU00117
V0007942
VQU00008
UPJ
UTTAMPARIA
V0073419
V0010083
VRP
VQV00004
VSD
CPVV
V0021352
VICTORHAZRA
VIJAYAR
VINAY.SILSWAL
VINOD.CHOUDHARY
VINOTHILAYA
VISHAL-CHAUHAN
VISHAL
VIZAGPHS
V0052770
VCV00207
SCV00013
VCV00203
WEIR
WEIRINDIA
VCW00045
VCM00441
WINSTON.P
WKDC
YOU_HB
V0072337